## Project_Work_Order6385882168867
Project Work Order
From 01 Jan 2016 To 31 Jul 2024
Page 1 of 1
Total Records: 35436 Records 1 To 35436
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ASMI | 1 | 0 | 10 Feb 2016 | TANGENT SURVEYORS | Land Survey | Plain Table Survey | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | chetan | chetan | Construction | 18 Apr 2016 |  | Land Cost | Approved | chetan | 1900-01-01
GANGA ASMI | 1 | 1 | 10 Feb 2016 | TANGENT SURVEYORS | Land Survey | Plain Table Survey | No. | 1 | 7000 | 7000 | 0 | 7000 | 0 | 1 | 7000 | 0 | 7000 | 0 | 0 |  | 100 |  | Nilesh | chetan | Construction | 18 Apr 2016 |  | Land Cost | Approved | chetan | 1900-01-01
GANGA ASMI | 1 | 2 | 10 Feb 2016 | TANGENT SURVEYORS | Land Survey | Plain Table Survey | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | Nilesh | chetan | Construction | 18 Apr 2016 |  | Land Cost | Approved | chetan | 1900-01-01
GANGA ASMI | 2 | 0 | 30 Mar 2016 | DAMU RATHOD | Compound Wall Concrete Pole Fixing | Transport charges -DCW | No. | 1 | 10200 | 10200 | 0 | 10200 | 0 | 0.62 | 6324 | 0 | 6324 | 0.38 | 3876 |  | 62 |  | Nilesh | chetan | construction open | 18 Apr 2016 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 2 | 0 | 30 Mar 2016 | DAMU RATHOD | Compound Wall Concrete Pole Fixing | Departmental Labour- DCW | No. | 40 | 350 | 14000 | 0 | 14000 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | Nilesh | chetan | construction open | 18 Apr 2016 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 2 | 0 | 30 Mar 2016 | DAMU RATHOD | Compound Wall Concrete Pole Fixing | Transport charges -DCW | No. | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Nilesh | chetan | construction open | 18 Apr 2016 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 2 | 0 | 30 Mar 2016 | DAMU RATHOD | Compound Wall Concrete Pole Fixing | Concrete Pole - Dld | No. | 75 | 140 | 10500 | 0 | 10500 | 0 | 25 | 3500 | 0 | 3500 | 50 | 7000 |  | 33.3333 |  | Nilesh | chetan | construction open | 18 Apr 2016 |  | DEV. Landscape/Equipment | Approved | chetan | 1900-01-01
GANGA ASMI | 2 | 0 | 30 Mar 2016 | DAMU RATHOD | Compound Wall Concrete Pole Fixing | Departmental Labour- DCW | No. | 62 | 350 | 21700 | 0 | 21700 | 0 | 62 | 21700 | 0 | 21700 | 0 | 0 |  | 100 |  | Nilesh | chetan | construction open | 18 Apr 2016 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 3 | 0 | 18 Jun 2016 | PATILS FABRICATORS | Compound Wall Barbed Wire Fencing | Barbed Wire Fixing - DCW | R.Ft | 820 | 38 | 31160 | 0 | 31160 | 0 | 820 | 31160 | 0 | 31160 | 0 | 0 |  | 100 |  | Nilesh | chetan | Construction | 08 Sep 2016 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 4 | 0 | 24 Jun 2016 | JAI GANESH EARTHMOVERS | Plot Levelling Work by JCB | JCB Charges | Hrs | 10.5 | 650 | 6825 | 0 | 6825 | 0 | 10.5 | 6825 | 0 | 6825 | 0 | 0 |  | 100 |  | Nilesh | skmishra | Construction | 24 Oct 2016 |  | 01 EARTHWORK & ROADWORK | Approved | skmishra | 1900-01-01
GANGA ASMI | 5 | 0 | 05 Jul 2016 | SITARAM GANGADHAR AUTI | Site Staff | Site Staff | Month | 12 | 9090 | 109080 | 0 | 109080 | 0 | 2 | 18180.15 | 0 | 18180.15 | 10 | 90899.85 |  | 25 |  | Nilesh | chetan | construction open | 09 Jul 2016 |  | S OH Site Staff | Approved | chetan | 1900-01-01
GANGA ASMI | 6 | 0 | 14 Sep 2016 | SURESH KUMAR MURALIDHAR | JCB/ Poclain/ Crane Charges For Misc Dev.Work | Department Labour-Dev | No. | 10 | 350 | 3500 | 0 | 3500 | 0 | 10 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | Nilesh | chetan | Construction | 26 Sep 2016 |  | DEV. Murum Filling | Approved | chetan | 1900-01-01
GANGA ASMI | 7 | 1 | 09 Jan 2017 | SURESH KUMAR MURALIDHAR | Compound Wall Exc. & Concreting for Pole Foundation | Departmental Labour- DCW | No. | 5 | 350 | 1750 | 0 | 1750 | 0 | 5 | 1750 | 0 | 1750 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 27 Jan 2017 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 7 | 0 | 09 Jan 2017 | SURESH KUMAR MURALIDHAR | Concrete Pole Fixing for Green & Blue Line Marking | Concrete Pole - Dld | No. | 10 | 120 | 1200 | 0 | 1200 | 2.5 | 10 | 1200 | 0 | 1200 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 27 Jan 2017 |  | DEV. Landscape/Equipment | Approved | chetan | 1900-01-01
GANGA ASMI | 7 | 1 | 09 Jan 2017 | SURESH KUMAR MURALIDHAR | Compound Wall Exc. & Concreting for Pole Foundation | Pit Excavation & Concreting - DCW | No. | 18 | 120 | 2160 | 0 | 2160 | 2.5 | 18 | 2160 | 0 | 2160 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 27 Jan 2017 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 8 | 0 | 28 Jun 2017 | DEEP MAN ENTERPRISES | Borewell Pump & Installation Work | Borewell Flushing-UWR | R.Ft | 200 | 40 | 8000 | 0 | 8000 | 0 | 200 | 8000 | 0 | 8000 | 0 | 0 |  | 100 |  | Nilesh | chetan | Construction | 14 Jul 2017 |  | UTI. Water Supply | Approved | chetan | 25 Jul 2017
GANGA ASMI | 8 | 0 | 28 Jun 2017 | DEEP MAN ENTERPRISES | Borewell Pump & Installation Work | PVC Casing Work - UWR | R.Ft | 3 | 250 | 750 | 0 | 750 | 0 | 3 | 750 | 0 | 750 | 0 | 0 |  | 100 |  | Nilesh | chetan | Construction | 14 Jul 2017 |  | UTI. Water Supply | Approved | chetan | 25 Jul 2017
GANGA ASMI | 9 | 0 | 25 Jul 2017 | SURESH KUMAR MURALIDHAR | Brickwork & Plaster for Bore Chambers | Departmental work -UTI- | No. | 0 | 250 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MANDARP |  | Construction | 1900-01-01 |  | UTI. Electricity Infrastructur | Cancelled | skmishra | 19 Aug 2017
GANGA ASMI | 9 | 0 | 25 Jul 2017 | SURESH KUMAR MURALIDHAR | Brickwork & Plaster for Bore Chambers | Departmental work -UTI- | No. | 1 | 350 | 350 | 0 | 350 | 0 | 1 | 350 | 0 | 350 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | chetan | 04 Sep 2017
GANGA ASMI | 9 | 0 | 25 Jul 2017 | SURESH KUMAR MURALIDHAR | Brickwork & Plaster for Bore Chambers | Departmental work -UTI- | No. | 1 | 650 | 650 | 0 | 650 | 0 | 1 | 650 | 0 | 650 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | chetan | 04 Sep 2017
GANGA ASMI | 10 | 0 | 19 Sep 2017 | SHRADDHA ENTERPRISES (PROP. SUNEEL KUMAR) | Compound Wall & Gate Fabrication work | G.I. Sheet fixing - Dev DCW | Sq.Ft | 840 | 4 | 3360 | 604.8 | 3964.8 | 2.5 | 840 | 3360 | 604.8 | 3964.8 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 26 Sep 2017 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 10 | 0 | 19 Sep 2017 | SHRADDHA ENTERPRISES (PROP. SUNEEL KUMAR) | Compound Wall & Gate Fabrication work | Fab (M)-DCW | Kgs | 503.26 | 38 | 19123.88 | 3442.3 | 22566.18 | 0 | 503.26 | 19123.88 | 3442.3 | 22566.18 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 26 Sep 2017 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 10 | 0 | 19 Sep 2017 | SHRADDHA ENTERPRISES (PROP. SUNEEL KUMAR) | Compound Wall & Gate Fabrication work | Fab (L)-DCW | Kgs | 503.26 | 15.2 | 7649.55 | 1376.92 | 9026.47 | 2.5 | 503.26 | 7649.55 | 1376.92 | 9026.47 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 26 Sep 2017 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 11 | 0 | 19 Sep 2017 | SHRADDHA ENTERPRISES (PROP. SUNEEL KUMAR) | Grill for Old Office | M.S. Grill (m+l) | Sq.Ft | 20 | 125 | 2500 | 450 | 2950 | 2.5 | 20 | 2500 | 450 | 2950 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 26 Sep 2017 |  | B.C. Customer Changes | Approved | chetan | 1900-01-01
GANGA ASMI | 12 | 0 | 19 Sep 2017 | SHRADDHA ENTERPRISES (PROP. SUNEEL KUMAR) | Borewell MS Chamber Cover | Chamber MS Cover-BCP | Sq.Ft | 9 | 350 | 3150 | 567 | 3717 | 0 | 9 | 3150 | 567 | 3717 | 0 | 0 |  | 100 |  | MANDARP | chetan | Construction | 26 Sep 2017 |  | B.C. Building Common Items | Approved | chetan | 1900-01-01
GANGA ASMI | 13 | 0 | 10 Oct 2018 | VIKAS GARADE | Plot levelling Before Plowing Work | Plumbing Work lumpsum-BRE | No. | 1 | 1560 | 1560 | 0 | 1560 | 0 | 1 | 1560 | 0 | 1560 | 0 | 0 |  | 100 |  | MANDARP | chetan | construction open | 18 Oct 2018 |  | DEV. Extrawork/Rework | Approved | nilesh | 19 Oct 2018
GANGA ASMI | 13 | 0 | 10 Oct 2018 | VIKAS GARADE | Plot levelling Before Plowing Work | Departmental Labour | No. | 6 | 500 | 3000 | 0 | 3000 | 0 | 6 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | MANDARP | chetan | construction open | 18 Oct 2018 |  | B.C. Rework/Extrawork | Approved | nilesh | 19 Oct 2018
GANGA ASMI | 13 | 0 | 10 Oct 2018 | VIKAS GARADE | Plot levelling Before Plowing Work | Labour lumpsum | No. | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | MANDARP | chetan | construction open | 18 Oct 2018 |  | B.C. Rework/Extrawork | Approved | nilesh | 19 Oct 2018
GANGA ASMI | 13 | 1 | 10 Oct 2018 | VIKAS GARADE | Plot levelling Before Plowing Work | Labour lumpsum | No. | 1 | 12000 | 12000 | 0 | 12000 | 0 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | MANDARP | chetan | construction open | 18 Oct 2018 |  | B.C. Rework/Extrawork | Approved | chetan | 1900-01-01
GANGA ASMI | 13 | 0 | 10 Oct 2018 | VIKAS GARADE | Plot levelling Before Plowing Work | Labour lumpsum | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | MANDARP | chetan | construction open | 18 Oct 2018 |  | B.C. Rework/Extrawork | Approved | nilesh | 19 Oct 2018
GANGA ASMI | 14 | 0 | 07 Feb 2020 | KAKADE RASHMI RAVINDRA | Wakad ECBC compliance report | ECBC Compliance | No. | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | GANDHI | chetan | consultancy | 22 Feb 2020 |  | 03 CONSULTANCY | Approved | chetan | 1900-01-01
GANGA ASMI | 15 | 0 | 07 Feb 2020 | KAKADE RASHMI RAVINDRA | Wakad Traffic analysis report | Detailed Traffic & Transportation study | No. | 1 | 65000 | 65000 | 0 | 65000 | 0 | 1 | 65000 | 0 | 65000 | 0 | 0 |  | 100 |  | GANDHI | chetan | consultancy | 22 Feb 2020 |  | Consultacy Architectural | Approved | chetan | 1900-01-01
GANGA ASMI | 16 | 0 | 26 Feb 2020 | GOLDEN POOLS | Wakad Swimming pool EC meeting charges | Professional Fees. | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | GANDHI |  | consultancy | 1900-01-01 |  | 03 CONSULTANCY | Un-Approved |  | 1900-01-01
GANGA ASMI | 17 | 0 | 14 Mar 2020 | DUROCRETE ENGINEERING SERVICES PVT LTD | Soil Invistigation test report Bore Hole | Geo-Technical Report | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | SHUBHAM GIRI | chetan | Construction | 14 Mar 2020 |  | 16 Testing, Analysis & Reports | Approved | chetan | 1900-01-01
GANGA ASMI | 17 | 0 | 14 Mar 2020 | DUROCRETE ENGINEERING SERVICES PVT LTD | Soil Invistigation test report Bore Hole | Mobilisation - SOS | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 1 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | SHUBHAM GIRI | chetan | Construction | 14 Mar 2020 |  | S OH Infrastructure | Approved | chetan | 1900-01-01
GANGA ASMI | 17 | 0 | 14 Mar 2020 | DUROCRETE ENGINEERING SERVICES PVT LTD | Soil Invistigation test report Bore Hole | Soil Investigation work- SOS | No. | 9 | 28000 | 252000 | 45360 | 297360 | 0 | 9 | 252000 | 45360 | 297360 | 0 | 0 | Standard Specification Test in soil and collecting/Preserving SPT soil samples at every 1.5m vertical interval Preservation & handling over of soil and rock samples & Testing in Laboratory ( For Details Ref Remark) | 100 |  | SHUBHAM GIRI | chetan | Construction | 14 Mar 2020 |  | S OH Infrastructure | Approved | chetan | 1900-01-01
GANGA ASMI | 18 | 0 | 16 Mar 2020 | VECTOR SURVEYORS | Land Cost Land Survey | Plot Boundary & Contour Survey | Acre | 7 | 3500 | 24500 | 0 | 24500 | 0 | 7 | 24500 | 0 | 24500 | 0 | 0 |  | 100 |  | SHUBHAM GIRI | chetan | Construction | 03 May 2020 |  | Land Cost | Approved | chetan | 1900-01-01
GANGA ASMI | 19 | 0 | 16 Mar 2020 | JAI GANESH EARTHMOVERS | Land Levelling and cutting - 1 No. | Labour Lumpsum | No. | 1 | 19200 | 19200 | 0 | 19200 | 2.5 | 1 | 19200 | 0 | 19200 | 0 | 0 |  | 100 |  | SHUBHAM GIRI | chetan | construction open | 03 May 2020 |  | DEV. Ext Development | Approved | chetan | 1900-01-01
GANGA ASMI | 20 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | Wing-3 MEP Consultancy | MEP Consultancy | Sq.Ft | 141486 | 4 | 565944 | 101869.92 | 667813.92 | 0 | 35371.5 | 141486 | 25467.5 | 166953.5 | 106114.5 | 500860.42 |  | 25 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ASMI | 20 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | Wing-1 MEP Consultancy | MEP Consultancy | Sq.Ft | 154957 | 4 | 619828 | 111569.04 | 731397.04 | 0 | 154957 | 619828 | 111569.02 | 731397.02 | 0 | 0.02 |  | 100 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ASMI | 20 | 1 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | MEP Consultancy Area Difference | MEP Consultancy (Qty Diff.) | Sq.Ft | 358506 | 4 | 1434024 | 258124.32 | 1692148.32 | 0 | 124999.9 | 499999.6 | 89999.94 | 589999.54 | 233506.1 | 1102148.78 |  | 34.8669 |  | Dushant Gore | Swapnil Erande | consultancy | 26 Jun 2020 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 20 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | MHADA MEP Consultancy | MEP Consultancy | Sq.Ft | 32275 | 4 | 129100 | 23238 | 152338 | 0 | 32275 | 129100 | 23238 | 152338 | 0 | 0 |  | 100 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ASMI | 20 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | Wing-2 MEP Consultancy | MEP Consultancy | Sq.Ft | 160683 | 4 | 642732 | 115691.76 | 758423.76 | 0 | 99746.85 | 398987.4 | 71817.74 | 470805.14 | 60936.15 | 287618.62 |  | 62.0768 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ASMI | 20 | 0 | 25 May 2020 | UNICORN M.E.P. CONSULTANTS PVT LTD | Shop @ Wing 3 MEP Consultancy | MEP Consultancy | Sq.Ft | 1370 | 4 | 5480 | 986.4 | 6466.4 | 0 | 342.5 | 1370 | 246.6 | 1616.6 | 1027.5 | 4849.8 |  | 25 |  | chetan | chetan | consultancy | 26 Jun 2020 |  | Consultancy MEP | Approved | chetan | 1900-01-01
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure Excavation Work | Excavation work Lumsum-DPo | No. | 1 | 7000 | 7000 | 0 | 7000 | 0 | 1 | 7000 | 0 | 7000 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 03 Jul 2020 |  | DEV. Podium | Approved | chetan | 1900-01-01
GANGA ASMI | 21 | 1 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure UCR Masonary Work(0.75m)-(Cu.Ft) | UCR Masonary - SOS | Cu.Ft | 2705.31 | 97 | 262415.07 | 0 | 262415.07 | 2.5 | 2705.31 | 262415.07 | 0 | 262415.07 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | construction open | 03 Jul 2020 |  | S OH Infrastructure | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure Excavation Work | Excavation work Lumsum-DPo | No. | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh |  | construction open | 03 Jul 2020 |  | DEV. Podium | Cancelled | skmishra | 03 Jul 2020
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure Plinth PCC Work(0.1m)-(Sq.Ft) | PCC Work | Sq.Ft | 5484.88 | 43 | 235849.84 | 0 | 235849.84 | 0 | 5484.88 | 235849.84 | 0 | 235849.84 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 03 Jul 2020 |  | 02 RCC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure Excavation Work | Excavation work Lumsum-DPo | No. | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh |  | construction open | 03 Jul 2020 |  | DEV. Podium | Cancelled | skmishra | 30 Jun 2020
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure UCR Masonary Work(0.75m)-(Cu.Ft) | UCR Masonary - SOS | Cu.Ft | 4301.69 | 97 | 417263.93 | 0 | 417263.93 | 0 | 4301.69 | 417263.93 | 0 | 417263.93 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 03 Jul 2020 |  | S OH Infrastructure | Approved | chetan | 1900-01-01
GANGA ASMI | 21 | 1 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure Plinth PCC Work(0.1m)-(Sq.Ft) | PCC Work | Sq.Ft | 94.92 | 43 | 4081.56 | 0 | 4081.56 | 2.5 | 94.92 | 4081.56 | 0 | 4081.56 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | construction open | 03 Jul 2020 |  | 02 RCC WORK | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure UCR PCC Work(0.1m)-(Sq.Ft) | PCC Work | Sq.Ft | 874.65 | 43 | 37609.95 | 0 | 37609.95 | 0 | 874.65 | 37609.95 | 0 | 37609.95 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 03 Jul 2020 |  | 02 RCC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 21 | 1 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure UCR PCC Work(0.1m)-(Sq.Ft) | PCC Work | Sq.Ft | 129.35 | 43 | 5562.05 | 0 | 5562.05 | 2.5 | 129.35 | 5562.05 | 0 | 5562.05 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | construction open | 03 Jul 2020 |  | 02 RCC WORK | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure Plinth PCC Work(0.1m)-(Sq.Ft) | PCC Work | Sq.Ft | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh |  | construction open | 03 Jul 2020 |  | 02 RCC WORK | Cancelled | skmishra | 03 Jul 2020
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure UCR PCC Work(0.1m)-(Sq.Ft) | PCC Work | Sq.Ft | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh |  | construction open | 03 Jul 2020 |  | 02 RCC WORK | Cancelled | skmishra | 03 Jul 2020
GANGA ASMI | 21 | 0 | 30 Jun 2020 | VIJAY MOHITE | S.O - Substructure UCR Masonary Work(0.75m)-(Cu.Ft) | UCR Masonary - SOS | Cu.Ft | 0 | 97 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh |  | construction open | 03 Jul 2020 |  | S OH Infrastructure | Cancelled | skmishra | 03 Jul 2020
GANGA ASMI | 22 | 0 | 07 Jul 2020 | JAI GANESH ENTERPRISES | S.O - Substructure Murum Filling | Murum Supply- BC | Cu.Ft | 15832.26 | 7 | 110825.82 | 19948.64 | 130774.46 | 0 | 15832.26 | 110825.82 | 19948.64 | 130774.46 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | construction open | 07 Jul 2020 |  | B.C. RCC Substructure | Approved | chetan | 1900-01-01
GANGA ASMI | 22 | 0 | 07 Jul 2020 | JAI GANESH ENTERPRISES | S.O - Substructure Murum Filling | Murum Filling-Mkt | Cu.Ft | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh |  | construction open | 07 Jul 2020 |  | MKT. Marketing Infrastructure | Cancelled | SKMISHRA | 07 Jul 2020
GANGA ASMI | 23 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | Fabrication work (L) | Kgs | 0 | 23.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 18 Aug 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 0 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | MS Barrication for plot boundry | Fabrication work (L) | Kgs | 0 | 18.9 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 18 Aug 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 0 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | MS Barrication for plot boundry | Self Tapping Screw - SOSB | No. | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 18 Aug 2020 |  | S OH Infrastructure | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 0 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | MS Barrication for plot boundry | GI Sheet fixing-SO | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 18 Aug 2020 |  | S OH Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 0 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | MS Barrication for plot boundry | Pit Excavation & Concreting - SOS | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 18 Aug 2020 |  | S OH Infrastructure | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | Excavation & Concrete Pit - Dld | No. | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 18 Aug 2020 |  | DEV. Landscape/Equipment | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 0 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | MS Barrication for plot boundry | Fabrication work (L) | Kgs | 0 | 24.3 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 18 Aug 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | GI Sheet fixing-SO | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 18 Aug 2020 |  | S OH Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | Fabrication work (L) | Kgs | 0 | 18.9 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 18 Aug 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | Self Tamping Screw (L) | No. | 0 | 0.34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 18 Aug 2020 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 23 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | Fabrication work (M) | Kgs | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 18 Aug 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 20 Jul 2020
GANGA ASMI | 24 | 0 | 09 Jul 2020 | NAREDCO WEST FOUNDATION | ONLINE / DIGITAL Social / Digital Activity | Subcription Fees | No. | 1 | 45000 | 45000 | 8100 | 53100 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | PROJECT LISITING - HOUSING FOR ALL.COM PERIOD AS ON 10TH JULY 2020 TO 09TH JULY 2021 | 0 |  | tejas | sunitas | construction open | 10 Jul 2020 |  | MKT. Media | Approved | sunitas | 1900-01-01
GANGA ASMI | 25 | 0 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | MS Barrication for plot boundry | Fabrication work (M) | Kgs | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 23 Jul 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 25 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | Fabrication work (M) | Kgs | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 25 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | Fabrication work (M) | Kgs | 0 | 42 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 25 | 1 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Barrication with GI Sheet | Self Tamping Screw (M) | No. | 0 | 2.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 25 | 0 | 09 Jul 2020 | OM SAI ALLUMINIUM & FABRICATION | MS Barrication for plot boundry | Fabrication work (M) | Kgs | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 23 Jul 2020 |  | Admin. Direct Expenses | Cancelled | skmishra | 18 Aug 2020
GANGA ASMI | 26 | 0 | 11 Jul 2020 | SHUBHAVANTI PRINTERS | PRINTING PRINTING-NO.-(NA) | Star Flex | Sq.Ft | 368 | 20 | 7360 | 1324.8 | 8684.8 | 0 | 368 | 7360 | 1324.8 | 8684.8 | 0 | 0 | STAR FLEX PRINT WITH PAST ON MS FRAME - SIZE AS 19X8 QTY 2 AND 8X8 QTY 1 | 100 |  | tejas | sunitas | construction open | 13 Jul 2020 |  | MKT. Media | Approved | sunitas | 1900-01-01
GANGA ASMI | 27 | 0 | 13 Jul 2020 | JAI GANESH ENTERPRISES | Sales office&Show Flats - Murum Shifting & JCB Chargs | JCB Charges | Hrs | 40 | 800 | 32000 | 5760 | 37760 | 0 | 40 | 32000 | 5760 | 37760 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 14 Jul 2020 |  | UTI. Drainage | Approved | chetan | 1900-01-01
GANGA ASMI | 27 | 0 | 13 Jul 2020 | JAI GANESH ENTERPRISES | Sales office&Show Flats - Murum Shifting & JCB Chargs | Murum Shifting work | Cu.Mtrs | 1700.68 | 200 | 340136 | 61224.48 | 401360.48 | 0 | 1700.68 | 340136 | 61224.48 | 401360.48 | 0 | 0 |  | 100 |  | GANDHI | chetan | construction open | 14 Jul 2020 |  | 01 EARTHWORK & ROADWORK | Approved | chetan | 1900-01-01
GANGA ASMI | 28 | 0 | 16 Jul 2020 | YASH FLOWER NURSERY | Tree work | Labour Lumpsum - SOSB | No. | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | chetan | chetan | construction open | 22 Jul 2020 |  | S OH Infrastructure | Approved | chetan | 1900-01-01
GANGA ASMI | 29 | 0 | 17 Jul 2020 | DATTATRAYA DNYANOBA DHUMAL | Sales office&Show Flats - Murum Shifting & JCB Chargs | Roller- BC | Day | 2 | 6500 | 13000 | 0 | 13000 | 0 | 2 | 13000 | 0 | 13000 | 0 | 0 |  | 100 |  | chetan | chetan | construction open | 22 Jul 2020 |  | B.C. RCC Substructure | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 0 | 148000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan |  | construction open | 1900-01-01 |  | 14 MISC WORK | Cancelled | skmishra | 20 Jul 2020
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 148000 | 148000 | 26640 | 174640 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 1 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 2 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 30 | 3 | 20 Jul 2020 | B.S. KATURE | Sales Office&Show Flats -Rent for Mandap | Rent for Tent | Month | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 31 | 0 | 20 Jul 2020 | B.S. KATURE | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | S OH Expenses | Cancelled | skmishra | 14 Aug 2020
GANGA ASMI | 32 | 0 | 20 Jul 2020 | VIJAY MOHITE | Plot Levelling&Grass Cutting | Lumpsum work- DCW | No. | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | chetan | chetan | construction open | 23 Jul 2020 |  | DEV. Compound Wall | Approved | chetan | 1900-01-01
GANGA ASMI | 33 | 3 | 24 Jul 2020 | PAPPU BAGELA | New Sales Office (Wing-1) Tiling Work (L) | Vitrified Flooring - MKT - Sq.Ft | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA.CHOUGULE | 30 Aug 2023
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Granite Vertical - Mkt | No. | 0 | 1000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Show Flat-Flooring&Tiling(L) | Vitrified Flooring - MKT - Sq.Ft | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 1 | 24 Jul 2020 | PAPPU BAGELA | Sample flat tile fixing (Old sales office) | Vitrified Flooring -BC | Sq.Ft | 305 | 20 | 6100 | 1098 | 7198 | 2.5 | 159.7258 | 3194.52 | 0 | 3194.52 | 145.2742 | 4003.48 |  | 52.3691 |  | Dushant Gore | Swapnil Erande | construction open | 11 Aug 2020 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 3 | 24 Jul 2020 | PAPPU BAGELA | New Sales Office (Wing-1) Tiling Work (L) | Granite Kitchen Otta - Mkt | R.Ft | 8.62 | 600 | 5172 | 0 | 5172 | 2.5 | 0 | 0 | 0 | 0 | 8.62 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 3 | 24 Jul 2020 | PAPPU BAGELA | New Sales Office (Wing-1) Tiling Work (L) | Dado - Mkt | Sq.Ft | 265.15 | 23 | 6098.45 | 0 | 6098.45 | 2.5 | 265.15 | 6098.45 | 0 | 6098.45 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Granite Edge Polish- Mkt. | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Granite Tread | R.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | B.C. Building Common Items | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Show Flat-Flooring&Tiling(L) | Ceramic Skirting - Mkt | R.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 3 | 24 Jul 2020 | PAPPU BAGELA | New Sales Office (Wing-1) Tiling Work (L) | Ceramic Flooring - MKT | Sq.Ft | 175.58 | 20 | 3511.6 | 0 | 3511.6 | 2.5 | 175.58 | 3511.6 | 0 | 3511.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Granite Umbra Patti- BCo | R.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | B.C. Building Common Items | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 1 | 24 Jul 2020 | PAPPU BAGELA | Sample flat tile fixing (Old sales office) | Vitrified Flooring -BC | Sq.Ft | 85 | 20 | 1700 | 306 | 2006 | 2.5 | 77.633 | 1552.66 | 0 | 1552.66 | 7.367 | 453.34 |  | 91.3329 |  | Dushant Gore | Swapnil Erande | construction open | 11 Aug 2020 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Show Flat-Flooring&Tiling(L) | Granite Umbra Patti- BCo | R.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | B.C. Building Common Items | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Show Flat-Flooring&Tiling(L) | Granite Kitchen Otta - Mkt | R.Ft | 0 | 450 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Vitrified Flooring - MKT - Sq.Ft | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 1 | 24 Jul 2020 | PAPPU BAGELA | Sample flat tile fixing (Old sales office) | Vitrified Flooring 2ftx2ft-BC | Sq.Ft | 1500 | 22 | 33000 | 5940 | 38940 | 2.5 | 1212.0885 | 26665.95 | 0 | 26665.95 | 287.9115 | 12274.05 |  | 80.8059 |  | Dushant Gore | Swapnil Erande | construction open | 11 Aug 2020 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Show Flat-Flooring&Tiling(L) | Granite Edge Polish- Mkt. | R.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 3 | 24 Jul 2020 | PAPPU BAGELA | New Sales Office (Wing-1) Tiling Work (L) | Granite Umbra Patti (L)- Mkt | No. | 2.44 | 45 | 109.8 | 0 | 109.8 | 2.5 | 0 | 0 | 0 | 0 | 2.44 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 3 | 24 Jul 2020 | PAPPU BAGELA | New Sales Office (Wing-1) Tiling Work (L) | Vitrified Skirting - MKT - R.Ft | R.Ft | 516.45 | 22 | 11361.9 | 0 | 11361.9 | 2.5 | 516.45 | 11361.9 | 0 | 11361.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 1 | 24 Jul 2020 | PAPPU BAGELA | Sample flat tile fixing (Old sales office) | Vitrified Flooring -BC | Sq.Ft | 75 | 20 | 1500 | 270 | 1770 | 2.5 | 64.443 | 1288.86 | 0 | 1288.86 | 10.557 | 481.14 |  | 85.924 |  | Dushant Gore | Swapnil Erande | construction open | 11 Aug 2020 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 3 | 24 Jul 2020 | PAPPU BAGELA | New Sales Office (Wing-1) Tiling Work (L) | Vitrified Skirting - MKT - R.Ft | R.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA.CHOUGULE | 30 Aug 2023
GANGA ASMI | 33 | 2 | 24 Jul 2020 | PAPPU BAGELA | Sales Toilet outside passage tiling | Tiling work (L) | Sq.Ft | 100 | 22 | 2200 | 0 | 2200 | 2.5 | 100 | 2200 | 0 | 2200 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Aug 2020 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Granite Kitchen Otta - Mkt | R.Ft | 0 | 450 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Show Flat-Flooring&Tiling(L) | Ceramic Flooring - MKT | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 2 | 24 Jul 2020 | PAPPU BAGELA | Sales Toilet outside passage tiling | Tiling work (L) | Sq.Ft | 400 | 20 | 8000 | 0 | 8000 | 2.5 | 400 | 8000 | 0 | 8000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Aug 2020 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Ceramic Flooring - MKT | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Granite Riser - Mkt | R.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 3 | 24 Jul 2020 | PAPPU BAGELA | New Sales Office (Wing-1) Tiling Work (L) | Vitrified Flooring - MKT - Sq.Ft | Sq.Ft | 2981.3 | 22 | 65588.6 | 0 | 65588.6 | 2.5 | 2981.3 | 65588.6 | 0 | 65588.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Show Flat-Flooring&Tiling(L) | Granite Ledge Wall Top - Mkt | R.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Show Flat-Flooring&Tiling(L) | Vitrified Skirting - MKT - R.Ft | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Vitrified Skirting - MKT - R.Ft | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 33 | 0 | 24 Jul 2020 | PAPPU BAGELA | Sales Office-Flooring&Tiling(L) | Dado - Mkt | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | GANDHI | chetan | construction open | 11 Aug 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 19 Sep 2020
GANGA ASMI | 34 | 0 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Sales Office&Show Flats-Gypsum Board Partition,False Ceiling | Gypsum Board Partition (M+L)-BC | Sq.Ft | 0 | 110 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh |  | construction open | 12 Sep 2020 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 27 Jul 2020
GANGA ASMI | 34 | 2 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Miscellaneous Expenses | No. | 1 | 7000 | 7000 | 1260 | 8260 | 0 | 1 | 7000 | 1260 | 8260 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Sep 2020 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum partition (L) | R.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 12 Sep 2020 |  | No category | Cancelled | Dushant Gore | 28 Nov 2022
GANGA ASMI | 34 | 0 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Sales Office&Show Flats-Gypsum Board Partition,False Ceiling | Gypsum False Ceiling. (M+L) - BC | R.Ft | 0 | 65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 12 Sep 2020 |  | B.C. Internal Finishing Itmes | Cancelled | skmishra | 12 Sep 2020
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Board Partition (L) | Sq.Ft | 545 | 150 | 81750 | 14715 | 96465 | 2.5 | 350.1135 | 52517.03 | 9453.06 | 61970.09 | 194.8865 | 34494.92 |  | 64.241 |  | Dushant Gore | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Partition Top (L) | R.Ft | 129 | 130 | 16770 | 3018.6 | 19788.6 | 2.5 | 129 | 16770 | 3018.6 | 19788.6 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum partition (L) | R.Ft | 0 | 110 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 12 Sep 2020 |  | No category | Cancelled | Dushant Gore | 28 Nov 2022
GANGA ASMI | 34 | 2 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Board Partition (L) | Sq.Ft | 15.93 | 130 | 2070.9 | 372.76 | 2443.66 | 2.5 | 15.93 | 2070.9 | 372.76 | 2443.66 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 0 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Sales Office&Show Flats-Gypsum Board Partition,False Ceiling | Gypsum Board Partition (M+L)-BC | Sq.Ft | 0 | 110 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 12 Sep 2020 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 12 Sep 2020
GANGA ASMI | 34 | 0 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Sales Office&Show Flats-Gypsum Board Partition,False Ceiling | Gala Cutting -Mkt | No. | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 12 Sep 2020 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 12 Sep 2020
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum partition (L) | R.Ft | 0 | 130 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 12 Sep 2020 |  | No category | Cancelled | Dushant Gore | 28 Nov 2022
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Partition Top (L) | R.Ft | 160 | 110 | 17600 | 3168 | 20768 | 2.5 | 160 | 17600 | 3168 | 20768 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Board Partition (L) | Sq.Ft | 435 | 180 | 78300 | 14094 | 92394 | 2.5 | 435 | 78300 | 14094 | 92394 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Board Partition (L) | Sq.Ft | 500 | 220 | 110000 | 19800 | 129800 | 2.5 | 273.76 | 60227.2 | 10840.9 | 71068.1 | 226.24 | 58731.9 |  | 54.752 |  | Dushant Gore | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Board Partition (L) | Sq.Ft | 235 | 130 | 30550 | 5499 | 36049 | 2.5 | 235 | 30550 | 5499 | 36049 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum partition (L) | R.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 12 Sep 2020 |  | No category | Cancelled | Dushant Gore | 28 Nov 2022
GANGA ASMI | 34 | 0 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Sales Office&Show Flats-Gypsum Board Partition,False Ceiling | Gypsum Patta/Top (M+L) | R.Ft | 0 | 82.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Cancelled | skmishra | 12 Sep 2020
GANGA ASMI | 34 | 2 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Partition Top (L) | R.Ft | 20.44 | 95 | 1941.8 | 349.52 | 2291.32 | 2.5 | 20.44 | 1941.8 | 349.52 | 2291.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Partition Top (L) | R.Ft | 165 | 160 | 26400 | 4752 | 31152 | 2.5 | 107.6526 | 17224.42 | 3100.4 | 20324.82 | 57.3474 | 10827.18 |  | 65.244 |  | Dushant Gore | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 34 | 1 | 24 Jul 2020 | A K INTERIOR CONTRACTOR | Show Flats (2 BHK & 3BHK) - Gypsum work | Gypsum Partition Top (L) | R.Ft | 124 | 95 | 11780 | 2120.4 | 13900.4 | 2.5 | 124 | 11780 | 2120.4 | 13900.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 12 Sep 2020 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 35 | 0 | 25 Jul 2020 | SARATHI SYSTECH PRIVATE LIMITED | Show Flats- Deep Cleaning Work | Deep Cleaning work | Sq.Ft | 1535.38 | 3 | 4606.14 | 829.1 | 5435.24 | 2.5 | 0 | 0 | 0 | 0 | 1535.38 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 11 Aug 2020 |  | B.C. Rework/Extrawork | Approved | chetan | 1900-01-01
GANGA ASMI | 35 | 0 | 25 Jul 2020 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office-Deep Cleaning Work | Deep Cleaning work | Sq.Ft | 2802.41 | 3 | 8407.23 | 1513.3 | 9920.53 | 2.5 | 0 | 0 | 0 | 0 | 2802.41 | 0 |  | 0 |  | tausif shaikh | chetan | construction open | 11 Aug 2020 |  | B.C. Rework/Extrawork | Approved | chetan | 1900-01-01
GANGA ASMI | 36 | 1 | 25 Jul 2020 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | No. | 1 | 675000 | 675000 | 121500 | 796500 | 0 | 1 | 675000 | 121500 | 796500 | 0 | 0 |  | 100 |  | tausif | chetan.jewalikar | consultancy | 05 Aug 2020 |  | 03 CONSULTANCY | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 36 | 0 | 25 Jul 2020 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | No. | 1 | 470000 | 470000 | 84600 | 554600 | 0 | 1 | 470000 | 84600 | 554600 | 0 | 0 |  | 100 |  | tausif shaikh | chetan | consultancy | 05 Aug 2020 |  | 03 CONSULTANCY | Approved | chetan | 1900-01-01
GANGA ASMI | 37 | 0 | 22 Sep 2020 | VIJAY MOHITE | Site Infra Vastu Wall UCR masonry & PCC work | UCR Masonary - SOS | Cu.Ft | 2655 | 97 | 257535 | 0 | 257535 | 2.5 | 2655 | 257535 | 0 | 257535 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | construction open | 08 Oct 2020 |  | S OH Infrastructure | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 37 | 0 | 22 Sep 2020 | VIJAY MOHITE | Site Infra Vastu Wall UCR masonry & PCC work | PCC | Sq.Ft | 885 | 43 | 38055 | 0 | 38055 | 2.5 | 885 | 38055 | 0 | 38055 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | construction open | 08 Oct 2020 |  | B.C. Building Common Items | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Tea Expenses-SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 24 Sep 2020
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9482 | 9482 | 0 | 9482 | 0.0518 | 518 |  | 94.82 |  | Dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9704 | 9704 | 0 | 9704 | 0.0296 | 296 |  | 97.04 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.6397 | 6397 | 0 | 6397 | 0.3603 | 3603 |  | 63.97 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.6365 | 6365 | 0 | 6365 | 0.3635 | 3635 |  | 63.65 |  | tausif.shaikh | tausif.shaikh | construction open | 1900-01-01 |  | S OH Expenses | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9817 | 9817 | 0 | 9817 | 0.0183 | 183 |  | 98.17 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.5879 | 5879 | 0 | 5879 | 0.4121 | 4121 |  | 58.79 |  | Dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9377 | 9377 | 0 | 9377 | 0.0623 | 623 |  | 93.77 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Tea Expenses-SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 24 Sep 2020
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9146 | 9146 | 0 | 9146 | 0.0854 | 854 |  | 91.46 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.982 | 9820 | 0 | 9820 | 0.018 | 180 |  | 98.2 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9391 | 9391 | 0 | 9391 | 0.0609 | 609 |  | 93.91 |  | Dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Tea Expenses-SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 24 Sep 2020
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.902 | 9020 | 0 | 9020 | 0.098 | 980 |  | 90.2 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9777 | 9777 | 0 | 9777 | 0.0223 | 223 |  | 97.77 |  | tausif.shaikh | tausif.shaikh | construction open | 1900-01-01 |  | S OH Expenses | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | construction open | 1900-01-01 |  | S OH Expenses | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 3 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 4822 | 4822 | 0 | 4822 | 0 | 1 | 4822 | 0 | 4822 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | construction open | 1900-01-01 |  | S OH Expenses | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Tea Expenses-SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 24 Sep 2020
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9998 | 9998 | 0 | 9998 | 0.0002 | 2 |  | 99.98 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.4106 | 4106 | 0 | 4106 | 0.5894 | 5894 |  | 41.06 |  | tausif.shaikh | tausif.shaikh | construction open | 1900-01-01 |  | S OH Expenses | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.971 | 9710 | 0 | 9710 | 0.029 | 290 |  | 97.1 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9478 | 9478 | 0 | 9478 | 0.0522 | 522 |  | 94.78 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Tea Expenses-SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 24 Sep 2020
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9815 | 9815 | 0 | 9815 | 0.0185 | 185 |  | 98.15 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9825 | 9825 | 0 | 9825 | 0.0175 | 175 |  | 98.25 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | tausif.shaikh | tausif.shaikh | construction open | 1900-01-01 |  | S OH Expenses | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9935 | 9935 | 0 | 9935 | 0.0065 | 65 |  | 99.35 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.4253 | 4253 | 0 | 4253 | 0.5747 | 5747 |  | 42.53 |  | tausif.shaikh | tausif.shaikh | construction open | 1900-01-01 |  | S OH Expenses | Approved | tausif.shaikh | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 2 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Tea Expenses-SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 24 Sep 2020
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 0 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Tea Expenses-SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif.shaikh |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 24 Sep 2020
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.7903 | 7903 | 0 | 7903 | 0.2097 | 2097 |  | 79.03 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9995 | 9995 | 0 | 9995 | 0.0005 | 5 |  | 99.95 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 5 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 4 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.9998 | 9998 | 0 | 9998 | 0.0002 | 2 |  | 99.98 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 38 | 1 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Expenses | Approved | chetan.jewalikar | 07 Feb 2022
GANGA ASMI | 38 | 3 | 24 Sep 2020 | VIKAS GARADE | Site Expenses | Site Expenses -SO | Month | 1 | 12000 | 12000 | 0 | 12000 | 0 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 39 | 0 | 12 Oct 2020 | ARYAN PRINT AND SIGN | Site Expenses Certificates | Digital Printing | No. | 50 | 17.86 | 893 | 160.74 | 1053.74 | 0 | 50 | 893 | 160.74 | 1053.74 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 16 Oct 2020 |  | 19.MEDIA | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 40 | 0 | 13 Oct 2020 | MODEL ART (PROP BALAJI EKBOTE) | Block Model Consultancy | Block Model | No. | 1 | 750000 | 750000 | 135000 | 885000 | 0 | 1 | 750000 | 135000 | 885000 | 0 | 0 |  | 100 |  | tausif | mandar parande | consultancy | 13 Oct 2020 |  | 03 CONSULTANCY | Approved | mandar parande | 1900-01-01
GANGA ASMI | 40 | 2 | 13 Oct 2020 | MODEL ART (PROP BALAJI EKBOTE) | Block Model Consultancy | Block Model Rate Diff | No. | 0 | 125000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 13 Oct 2020 |  | 03 CONSULTANCY | Cancelled | tausif | 29 Jun 2021
GANGA ASMI | 40 | 0 | 13 Oct 2020 | MODEL ART (PROP BALAJI EKBOTE) | Block Model Consultancy | Block Model | No. | 0 | 885000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 13 Oct 2020 |  | 03 CONSULTANCY | Cancelled | skmishra | 13 Oct 2020
GANGA ASMI | 40 | 1 | 13 Oct 2020 | MODEL ART (PROP BALAJI EKBOTE) | Block Model Consultancy | Block Model | No. | 0 | 1200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Material- Acrylic, with Laser Cutting HIP sheet, PVC Sheet, Deco Paint, Acrylic Paint, Aluminium Base. Model Size-- 14ft X 6ft 6inch X 9ft 6inch (building size-27inchx52inchxTower Height 98inch) | 0 |  | tausif | tausif | consultancy | 13 Oct 2020 |  | 03 CONSULTANCY | Cancelled | skmishra | 29 Jun 2021
GANGA ASMI | 40 | 3 | 13 Oct 2020 | MODEL ART (PROP BALAJI EKBOTE) | Block Model Consultancy | Block Model | No. | 0 | 60000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | consultancy | 13 Oct 2020 |  | 03 CONSULTANCY | Cancelled | skmishra | 30 Nov 2021
GANGA ASMI | 40 | 2 | 13 Oct 2020 | MODEL ART (PROP BALAJI EKBOTE) | Block Model Consultancy | Block Model Rate Diff | No. | 1 | 125000 | 125000 | 22500 | 147500 | 0 | 1 | 125000 | 22500 | 147500 | 0 | 0 | For Extra 1 Parking & 4 Floor | 100 |  | tausif | tausif | consultancy | 13 Oct 2020 |  | 03 CONSULTANCY | Approved | tausif | 1900-01-01
GANGA ASMI | 41 | 0 | 23 Oct 2020 | YOGESH BALU ICHAKE | Land Cost Plot Survey | Plot Boundary & Contour Survey | Acre | 7.07 | 1500 | 10605 | 0 | 10605 | 0 | 7.07 | 10605 | 0 | 10605 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Oct 2020 |  | Land Cost | Approved | tausif | 1900-01-01
GANGA ASMI | 41 | 1 | 23 Oct 2020 | YOGESH BALU ICHAKE | Land Cost Plot Survey | Plot Boundary & Contour Survey | Acre | 3.01 | 3000 | 9030 | 0 | 9030 | 0 | 3.01 | 9030 | 0 | 9030 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Oct 2020 |  | Land Cost | Approved | tausif | 1900-01-01
GANGA ASMI | 42 | 0 | 24 Oct 2020 | SPACE DESIGNERS STUDIO | Phase-A Wing-2 Architectural Consultancy | Architectural Consultancy | Sq.Ft | 171601 | 20 | 3432020 | 617763.6 | 4049783.6 | 0 | 8580.05 | 171601 | 30888.18 | 202489.18 | 163020.95 | 3847294.42 |  | 5 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Foreclose | ADITYA CHOUGULE | 14 Jan 2023
GANGA ASMI | 42 | 0 | 24 Oct 2020 | SPACE DESIGNERS STUDIO | Phase-A COMM BLDG Architectural Consultancy | Architectural Consultancy | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Foreclose | ADITYA CHOUGULE | 14 Jan 2023
GANGA ASMI | 42 | 0 | 24 Oct 2020 | SPACE DESIGNERS STUDIO | Phase-A Wing-1 Architectural Consultancy | Architectural Consultancy | Sq.Ft | 167053 | 20 | 3341060 | 601390.8 | 3942450.8 | 0 | 18352.65 | 367053 | 66069.54 | 433122.54 | 148700.35 | 3509328.26 |  | 10.9861 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Foreclose | ADITYA CHOUGULE | 14 Jan 2023
GANGA ASMI | 42 | 0 | 24 Oct 2020 | SPACE DESIGNERS STUDIO | Phase-A Wing-3 Architectural Consultancy | Architectural Consultancy | Sq.Ft | 152132 | 20 | 3042640 | 547675.2 | 3590315.2 | 0 | 7606.6 | 152132 | 27383.76 | 179515.76 | 144525.4 | 3410799.44 |  | 5 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Foreclose | ADITYA CHOUGULE | 14 Jan 2023
GANGA ASMI | 42 | 0 | 24 Oct 2020 | SPACE DESIGNERS STUDIO | Phase-A MAHADA Architectural Consultancy | Architectural Consultancy | Sq.Ft | 27728 | 20 | 554560 | 99820.8 | 654380.8 | 0 | 1386.4 | 27728 | 4991.04 | 32719.04 | 26341.6 | 621661.76 |  | 5 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Foreclose | ADITYA CHOUGULE | 14 Jan 2023
GANGA ASMI | 42 | 0 | 24 Oct 2020 | SPACE DESIGNERS STUDIO | Phase-A PARKING AREA Architectural Consultancy | Architectural Consultancy | Sq.Ft | 4091.88 | 10 | 40918.8 | 7365.38 | 48284.18 | 0 | 204.594 | 2045.94 | 368.26 | 2414.2 | 3887.286 | 45869.98 |  | 5 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy Architectural | Foreclose | ADITYA CHOUGULE | 14 Jan 2023
GANGA ASMI | 43 | 0 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Wing-1,2,3 Parking RCC Consultancy | RCC Consultancy | Sq.Ft | 264732 | 6 | 1588392 | 285910.56 | 1874302.56 | 0 | 39709.8 | 238258.8 | 42886.58 | 281145.38 | 225022.2 | 1593157.18 |  | 15 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 43 | 0 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Wing-2 RCC Consultancy | RCC Consultancy | Sq.Ft | 269275 | 6 | 1615650 | 290817 | 1906467 | 0 | 13463.75 | 80782.5 | 14540.86 | 95323.36 | 255811.25 | 1811143.64 |  | 5 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 43 | 0 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Wing-3 RCC Consultancy | RCC Consultancy | Sq.Ft | 266650 | 6 | 1599900 | 287982 | 1887882 | 0 | 0 | 0 | 0 | 0 | 266650 | 0 |  | 0 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 43 | 0 | 31 Oct 2020 | G.A.BHILARE CONSULTANTS PVT LTD | Wing-1 RCC Consultancy | RCC Consultancy | Sq.Ft | 266650 | 6 | 1599900 | 287982 | 1887882 | 0 | 39997.5 | 239985 | 43197.3 | 283182.3 | 226652.5 | 1604699.7 |  | 15 |  | tausif | chetan.jawalikar | consultancy | 31 Oct 2020 |  | Consultacy RCC | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 44 | 2 | 05 Nov 2020 | DREAMTREE EXPERIENCE | PRINTING PRINTING-NO.-(NA) | Eco Vinyal With Foam Sheet | Sq.Ft | 1200 | 90 | 108000 | 19440 | 127440 | 0 | 555 | 49950 | 8991 | 58941 | 645 | 68499 | ECO SOLVENT VINYAL PRINT - PAST ON FOAM SHEET WITH INSTALLATION FOR GANGA ASMI BRANDING | 46.25 |  | Tejas Raverkar | sunita shirolkar | construction open | 10 Nov 2020 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 44 | 0 | 05 Nov 2020 | DREAMTREE EXPERIENCE | PRINTING PRINTING-NO.-(NA) | Star Flex | Sq.Ft | 16000 | 18 | 288000 | 51840 | 339840 | 0 | 16000 | 288000 | 51840 | 339840 | 0 | 0 | STAR FRONTLIT FLEX PRINT WITH PASTING ON MS FRAME GANAG ASMI BRANDING | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 10 Nov 2020 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 44 | 3 | 05 Nov 2020 | DREAMTREE EXPERIENCE | PRINTING PRINTING-NO.-(NA) | Backlet Box / Backlet Display Frame / Board | Sq.Ft | 1216 | 200 | 243200 | 43776 | 286976 | 0 | 1020.235 | 204047 | 36728.46 | 240775.46 | 195.765 | 46200.54 | BACKLET DISPLAY PANEL BARNDING AT WAKAD GANGA ASMI | 83.9009 |  | Tejas Raverkar | sunita shirolkar | construction open | 10 Nov 2020 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 44 | 1 | 05 Nov 2020 | DREAMTREE EXPERIENCE | PRINTING PRINTING-NO.-(NA) | Eco Vinyal with Lamination | Sq.Ft | 450 | 65 | 29250 | 5265 | 34515 | 0 | 450 | 29250 | 5265 | 34515 | 0 | 0 | ECO SOLVENT VINYAL PRINT WITH LAMINATION + PASTING FOR GANGA ASMI BRANDING | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 10 Nov 2020 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 45 | 0 | 06 Nov 2020 | Mr.Umakant Bhimrao Sabale | Sales Office&Show Flats Grass Cutting Work | Lumpsum work- DCW | No. | 1 | 30000 | 30000 | 0 | 30000 | 0 | 1 | 30000 | 0 | 30000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Nov 2020 |  | DEV. Compound Wall | Approved | tausif | 1900-01-01
GANGA ASMI | 46 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Media Frame Fabrication Work | Transport Charges | No. | 1 | 7500 | 7500 | 1350 | 8850 | 0 | 1 | 7500 | 1350 | 8850 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 27 Nov 2020 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 46 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Media Frame Fabrication Work | Fabrication work (L) | Kgs | 987.21 | 21.2 | 20928.85 | 3767.2 | 24696.05 | 2.5 | 674.1657 | 14292.31 | 2572.62 | 16864.93 | 313.0443 | 7831.12 |  | 68.29 |  | tausif | tausif | construction open | 27 Nov 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 47 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Media Frame Fabrication Work | Fabrication work (M) | Kgs | 987.21 | 53 | 52322.13 | 9417.98 | 61740.11 | 0 | 674.1953 | 35732.35 | 6431.82 | 42164.17 | 313.0147 | 19575.94 |  | 68.293 |  | tausif | tausif | construction open | 27 Nov 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 48 | 1 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Partition Rework Extrawork Shedge Vasti | Department Labour- BC | No. | 1 | 1400 | 1400 | 252 | 1652 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | tausif | construction open | 10 Dec 2020 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ASMI | 48 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Infra MS Gate Safety Posters Frames | Fabrication work (L) | Kgs | 56 | 17.6 | 985.6 | 177.4 | 1163 | 2.5 | 56 | 985.6 | 177.4 | 1163 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Dec 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 48 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Infra MS Gate Safety Posters Frames | Fabrication work (L) | Kgs | 135 | 21.2 | 2862 | 515.16 | 3377.16 | 2.5 | 135 | 2862 | 515.16 | 3377.16 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Dec 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 48 | 1 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Partition Rework Extrawork Shedge Vasti | Department Labour- BC | No. | 0 | 1400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | shubham giri |  | construction open | 10 Dec 2020 |  | B.C. RCC Substructure | Cancelled | tausif | 16 Feb 2021
GANGA ASMI | 48 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Infra Safety Posters | Fabrication work (L) | Kgs | 163.65 | 21.2 | 3469.38 | 624.48 | 4093.86 | 2.5 | 112.8498 | 2392.42 | 430.64 | 2823.06 | 50.8002 | 1270.8 |  | 68.958 |  | tausif | tausif | construction open | 10 Dec 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 48 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Infra Safety Posters | Fabrication work (L) | Kgs | 81.6 | 17.6 | 1436.16 | 258.5 | 1694.66 | 2.5 | 59.9923 | 1055.86 | 190.06 | 1245.92 | 21.6077 | 448.74 |  | 73.52 |  | tausif | tausif | construction open | 10 Dec 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 48 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION | Site Infra MS Gate Safety Posters Frames | GI Sheet fixing-SO | Sq.Ft | 216 | 6 | 1296 | 233.28 | 1529.28 | 2.5 | 0 | 0 | 0 | 0 | 216 | 0 |  | 0 |  | tausif | tausif | construction open | 10 Dec 2020 |  | S OH Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 49 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Site Infra MS Gate Safety Posters Frames | Aldrop- SO | No. | 2 | 75 | 150 | 27 | 177 | 0 | 2 | 150 | 27 | 177 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Dec 2020 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 49 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Site Infra MS Gate Safety Posters Frames | Hinges- SOS | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 4 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Dec 2020 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 49 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Site Infra Safety Posters | Fabrication work (M) | Kgs | 81.6 | 44 | 3590.4 | 646.28 | 4236.68 | 0 | 59.9997 | 2639.99 | 475.2 | 3115.19 | 21.6003 | 1121.49 |  | 73.529 |  | tausif | tausif | construction open | 10 Dec 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 49 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Site Infra MS Gate Safety Posters Frames | Self Tappping Screw- SOLC | No. | 40 | 2.5 | 100 | 18 | 118 | 0 | 40 | 100 | 18 | 118 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Dec 2020 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 49 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Site Infra MS Gate Safety Posters Frames | Fabrication work (M) | Kgs | 135 | 53 | 7155 | 1287.9 | 8442.9 | 0 | 135 | 7155 | 1287.9 | 8442.9 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Dec 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 49 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Site Infra MS Gate Safety Posters Frames | Tower Bolt SOSB | No. | 2 | 150 | 300 | 54 | 354 | 0 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Dec 2020 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 49 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Site Infra MS Gate Safety Posters Frames | Fabrication work (M) | Kgs | 56 | 44 | 2464 | 443.52 | 2907.52 | 0 | 56 | 2464 | 443.52 | 2907.52 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Dec 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 49 | 0 | 12 Nov 2020 | OM SAI ALLUMINIUM & FABRICATION (Material) | Site Infra Safety Posters | Fabrication work (M) | Kgs | 163.65 | 53 | 8673.45 | 1561.22 | 10234.67 | 0 | 112.8498 | 5981.04 | 1076.58 | 7057.62 | 50.8002 | 3177.05 |  | 68.958 |  | tausif | tausif | construction open | 10 Dec 2020 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 50 | 1 | 19 Nov 2020 | JAI GANESH ENTERPRISES | Tree Replantation Work | JCB Charges. | Day | 2 | 6400 | 12800 | 2304 | 15104 | 0 | 2 | 12800 | 2304 | 15104 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 19 Nov 2020 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 50 | 2 | 19 Nov 2020 | JAI GANESH ENTERPRISES | Tree Replantation Work | JCB Charges. | Day | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 1152 | 7552 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 19 Nov 2020 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 50 | 0 | 19 Nov 2020 | JAI GANESH ENTERPRISES | Sales Office&Show Flats Material Shifting for Vastu Wall & m | JCB Charges | Hrs | 12.16 | 800 | 9728 | 1751.04 | 11479.04 | 0 | 12.16 | 9728 | 1751.04 | 11479.04 | 0 | 0 |  | 100 |  | shubham giri | tausif | construction open | 19 Nov 2020 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 50 | 0 | 19 Nov 2020 | JAI GANESH ENTERPRISES | Sales Office&Show Flats Material Shifting for Vastu Wall & m | JCB Charges | Hrs | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | shubham giri |  | construction open | 19 Nov 2020 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 19 Nov 2020
GANGA ASMI | 51 | 0 | 19 Nov 2020 | SUMAN ENTERPRISES | Site Infra Vastu Wall Material Shifting | JCB Charges | Hrs | 32.16 | 750 | 24120 | 4341.6 | 28461.6 | 0 | 32.16 | 24120 | 4341.6 | 28461.6 | 0 | 0 |  | 100 |  | shubham giri | tausif | construction open | 10 Dec 2020 |  | UTI. Drainage | Approved | tausif | 1900-01-01
GANGA ASMI | 51 | 0 | 19 Nov 2020 | SUMAN ENTERPRISES | Site Infra Vastu Wall Material Shifting | Poclain Charges - BC - | Hrs | 9.75 | 1600 | 15600 | 2808 | 18408 | 0 | 9.75 | 15600 | 2808 | 18408 | 0 | 0 |  | 100 |  | shubham giri | tausif | construction open | 10 Dec 2020 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ASMI | 52 | 0 | 28 Dec 2020 | SUMAN ENTERPRISES | Plot Levelling&Grass Cutting | Lumpsum work- DCW | No. | 1 | 28000 | 28000 | 5040 | 33040 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 01 Feb 2021 |  | DEV. Compound Wall | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 53 | 0 | 20 Jan 2021 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 3 | 149999.4 | 26999.88 | 176999.28 | 3 | 177000.72 | GANGA ASMI PROJECT BRANDING HOARDING DISPLAY CHARGES AS ON 21.01.2021 TO 20.07.2021 @50000/- + TAX | 50 |  | Tejas Raverkar | sunita shirolkar | construction open | 11 Feb 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 54 | 0 | 20 Jan 2021 | PARICHAY PUBLICITY (PRAKASH MARUTI JAMDADE) | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 4 | 200000.4 | 36000.06 | 236000.46 | 2 | 117999.54 | GANGA ASMI PROJECT BRANDING HOARDING DISPLAY CHARGES AS ON 21.01.2021 TO 20.07.2021 @50000/- + TAX | 66.6667 |  | Tejas Raverkar | chetan.jawalikar | construction open | 20 Feb 2021 |  | MKT. Media | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 55 | 0 | 20 Jan 2021 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 4 | 200000.4 | 36000.06 | 236000.46 | 2 | 117999.54 | GANGA ASMI PROJECT BRANDING HOARDING DISPLAY CHARGES AS ON 21.01.2021 TO 20.07.2021 @50000/- + TAX SIZE AS 40 X 20 SQ FT. @ OPP. INDIRA INSTITUTE TATHAWADE, TRAFFIC FROM PUNE TO MUMBAI | 66.6667 |  | Tejas Raverkar | sunita shirolkar | construction open | 19 Mar 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 55 | 1 | 20 Jan 2021 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 25000 | 150000 | 27000 | 177000 | 0 | 4 | 100000.2 | 18000.04 | 118000.24 | 2 | 58999.76 | GANGA ASMI PROJECT BRANDING HOARDING DISPLAY CHARGES AS ON 21.01.2021 TO 20.07.2021 @25000/- + TAX SIZE AS 30 X 30 SQ. FT. @ NEAR VTP BLUE WATER PROJECT, MAHALUNGE, TRAFFIC FROM MAHALUNGE TO VTP | 66.6667 |  | Tejas Raverkar | chetan.jawalikar | construction open | 19 Mar 2021 |  | MKT. Media | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 56 | 1 | 20 Jan 2021 | OM SAI CORP | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 1000 | 8 | 8000 | 1440 | 9440 | 0 | 1000 | 8000 | 1440 | 9440 | 0 | 0 | GANGA ASMI WAKAD HOARDING FLEX PRINTING WITH MOUNTING AT WOODLIFE FURNITURE KASPATE WASTI, WAKAD SIZE AS 50 X 20 SQ FT. | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 25 Jan 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 56 | 0 | 20 Jan 2021 | OM SAI CORP | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 5600 | 8 | 44800 | 8064 | 52864 | 0 | 5600 | 44800 | 8064 | 52864 | 0 | 0 | GANGA ASMI WAKAD PROJECT HOARDING FLEX PRINTING WITH MOUNTING | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 25 Jan 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 56 | 2 | 20 Jan 2021 | OM SAI CORP | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 1200 | 8 | 9600 | 1728 | 11328 | 0 | 1200 | 9600 | 1728 | 11328 | 0 | 0 | GANGA ASMI PROJECT DISPLAY BRANDING HOARDING FLEX PRINT WITH MOUNT @ BHUMKAR CHOWK, FACING DANGE CHOWK, WAKAD, PUNE SIZE AS 60 X 20 SQ FT. | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 25 Jan 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 57 | 0 | 23 Jan 2021 | JAI GANESH ENTERPRISES. | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 80000 | 480000 | 86400 | 566400 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | GANGA ASMI HOARDING DISPLAY CHARGES @ WOODLIFE FURNITURE SHOWROOM, KASPATE WASTI, WAKAD SIZE AS 50 X 40 SQ FT. @80000/- + TAX AS ON 23.01.2021 TO 22.07.2021 | 0 |  | Tejas Raverkar | tausif | construction open | 08 May 2021 |  | MKT. Media | Approved | tausif | 1900-01-01
GANGA ASMI | 58 | 0 | 25 Jan 2021 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | PRINTING PRINTING-NO.-(NA) | Booklet / Notepad / Diary / Pocket Print | No. | 5000 | 36 | 180000 | 21600 | 201600 | 0 | 5000 | 180000 | 21600 | 201600 | 0 | 0 | GANGA ASMI DOCKET PRINT READY SIZE AS A-4, CENTRE GATE 2 FOLD WITH CREASING 300 GSM ART PAPER MATT LAMINATION FRONT SIDE LOGO SPOT UV F/B PRINT INNER SIDE POCKET WITH 5 INSERT | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 30 Jan 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 59 | 0 | 25 Jan 2021 | GAURI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 40000 | 240000 | 43200 | 283200 | 0 | 3 | 119999.52 | 21599.94 | 141599.46 | 3 | 141600.54 | GANGA ASMI PROJECT DISPLAY BRANDING RENTAL HOARDING MONTHLY CHARGES @ BHUMKAR CHOWK, FACING DANGE CHOWK, WAKAD, PUNE SIZE AS 60 X 20 SQ FT. @40000/- + TAX AS ON 26.01.2021 TO 25.07.2021 | 50 |  | Tejas Raverkar | sunita shirolkar | construction open | 30 Jan 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 60 | 0 | 28 Jan 2021 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | PRINTING PRINTING-NO.-(NA) | LEAFLET PRINTING | No. | 96000 | 0.76 | 72960 | 8755.2 | 81715.2 | 0 | 96000 | 72960 | 8755.2 | 81715.2 | 0 | 0 | GANGA ASMI WAKAD PROJECT SALES PROMOTION WITH BRANDING LEAFLET PRINT F/B, 90 GSM QTY 96 K @0.76/- + TAX | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 30 Jan 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 61 | 0 | 29 Jan 2021 | DREAMTREE EXPERIENCE | MEDIA Event Expenses | Event Expenses | No. | 1 | 31625 | 31625 | 5692.5 | 37317.5 | 0 | 1 | 31625 | 5692.5 | 37317.5 | 0 | 0 | GANGA ASMI PROJECT LAUNCHING EVENT DTD 28.01.2021 STAGE, RED CARPET, LED CANS, FAIRY LIGHTS, VIP CHAIRS, ROUND TABLE, TRANPORT ETC. | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 04 Feb 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 62 | 0 | 08 Feb 2021 | SHREE MAHALAXMI CRANE SERVICES | Tree Replantation Work | Crane charges | Day | 2 | 6000 | 12000 | 2160 | 14160 | 0 | 2 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 63 | 0 | 08 Feb 2021 | ANIL MAHTO ENTERPRISES | Sales Office - OBD Paint 1 coat | OBD (M+L) BC | Sq.Ft | 3893 | 2 | 7786 | 1401.48 | 9187.48 | 2.5 | 3768.9963 | 7537.99 | 1356.84 | 8894.83 | 124.0037 | 292.65 |  | 96.8147 |  | tausif | tausif | construction open | 08 Feb 2021 |  | B.C. Building Common Items | Approved | tausif | 1900-01-01
GANGA ASMI | 63 | 1 | 08 Feb 2021 | ANIL MAHTO ENTERPRISES | Sales Office Renovation - Painting work | OBD (M+L) BC | Sq.Ft | 3600 | 2 | 7200 | 1296 | 8496 | 2.5 | 3353.004 | 6706.01 | 1207.08 | 7913.09 | 246.996 | 582.91 |  | 93.139 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Feb 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 63 | 0 | 08 Feb 2021 | ANIL MAHTO ENTERPRISES | Sales Office - Oil Paint for MS Gate | Oil Paint | Sq.Ft | 100 | 10 | 1000 | 180 | 1180 | 2.5 | 100 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 08 Feb 2021 |  | UTI. Water treatment plant | Approved | tausif | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | Plug Point - Mkt | No. | 35 | 265 | 9275 | 0 | 9275 | 2.5 | 35 | 9275 | 0 | 9275 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 1 | 08 Feb 2021 | LAXMI ELECTRICALS | Sales office renovation - Electrical work | 4 Way TPN DB Fixing - DPo | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | Electrician | No. | 15 | 850 | 12750 | 0 | 12750 | 2.5 | 15 | 12750 | 0 | 12750 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | LIght Point - Mkt | No. | 60 | 265 | 15900 | 0 | 15900 | 2.5 | 60 | 15900 | 0 | 15900 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | Camera Point | No. | 15 | 350 | 5250 | 0 | 5250 | 2.5 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | 8 Way TPN DB | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 1 | 08 Feb 2021 | LAXMI ELECTRICALS | Sales office renovation - Electrical work | Light Fitting Fixing | No. | 89 | 100 | 8900 | 0 | 8900 | 2.5 | 80.0021 | 8000.21 | 0 | 8000.21 | 8.9979 | 899.79 |  | 89.89 |  | DUSHANT GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 1 | 08 Feb 2021 | LAXMI ELECTRICALS | Sales office renovation - Electrical work | secondary light point | No. | 78 | 112 | 8736 | 0 | 8736 | 2.5 | 78 | 8736 | 0 | 8736 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | Power Point - DSP | No. | 2 | 350 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | secondary light point | No. | 60 | 135 | 8100 | 0 | 8100 | 2.5 | 60 | 8100 | 0 | 8100 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | Fan Point - Mkt | No. | 30 | 265 | 7950 | 0 | 7950 | 2.5 | 30 | 7950 | 0 | 7950 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 0 | 08 Feb 2021 | LAXMI ELECTRICALS | CP Lounge CP Lounge Electrical Work | Socket point-BC | No. | 2 | 200 | 400 | 72 | 472 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. Building Common Items | Approved | tausif | 1900-01-01
GANGA ASMI | 64 | 1 | 08 Feb 2021 | LAXMI ELECTRICALS | Sales office renovation - Electrical work | Primary Point (L) | No. | 11 | 300 | 3300 | 0 | 3300 | 2.5 | 11 | 3300 | 0 | 3300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 0 | 08 Feb 2021 | LAXMI ELECTRICALS | CP Lounge CP Lounge Electrical Work | Socket point-BC | No. | 5 | 200 | 1000 | 180 | 1180 | 2.5 | 5 | 1000 | 0 | 1000 | 0 | 180 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. Building Common Items | Approved | tausif | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | Fan Fixing - Mkt | No. | 30 | 100 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | Cat 6 Cable laying -Mkt | Mtrs | 200 | 20 | 4000 | 0 | 4000 | 2.5 | 200 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | LED Light Fitting | No. | 120 | 100 | 12000 | 0 | 12000 | 2.5 | 0 | 0 | 0 | 0 | 120 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 2 | 08 Feb 2021 | LAXMI ELECTRICALS | New Sales Office Electrical Work | AC Point - Mkt | No. | 20 | 350 | 7000 | 0 | 7000 | 2.5 | 20 | 7000 | 0 | 7000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 1 | 08 Feb 2021 | LAXMI ELECTRICALS | Sales office renovation - Electrical work | 10 sqmm Cable Laying (L). | Mtrs | 50 | 36 | 1800 | 0 | 1800 | 2.5 | 50 | 1800 | 0 | 1800 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 64 | 0 | 08 Feb 2021 | LAXMI ELECTRICALS | CP Lounge CP Lounge Electrical Work | Tube Light Fixing | No. | 8 | 50 | 400 | 72 | 472 | 2.5 | 8 | 400 | 0 | 400 | 0 | 72 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 64 | 1 | 08 Feb 2021 | LAXMI ELECTRICALS | Sales office renovation - Electrical work | 6 AMP Plug Point - Mkt | No. | 10 | 225 | 2250 | 0 | 2250 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 65 | 1 | 08 Feb 2021 | DAMU RATHOD | CP Lounge Work | Lumpsum work- DCW | No. | 3 | 500 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | tausif | tausif | construction open | 26 Feb 2021 |  | DEV. Compound Wall | Approved | tausif | 1900-01-01
GANGA ASMI | 65 | 0 | 08 Feb 2021 | DAMU RATHOD | CP Lounge Work | Concreting for Pole Fixing | No. | 12 | 150 | 1800 | 0 | 1800 | 0 | 12 | 1800 | 0 | 1800 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | 02 RCC WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 65 | 0 | 08 Feb 2021 | DAMU RATHOD | CP Lounge Work | PCC | Sq.Ft | 550 | 6 | 3300 | 0 | 3300 | 0 | 545.215 | 3271.29 | 0 | 3271.29 | 4.785 | 28.71 |  | 99.13 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. Building Common Items | Approved | tausif | 1900-01-01
GANGA ASMI | 65 | 1 | 08 Feb 2021 | DAMU RATHOD | CP Lounge Work | Brickwork 6" | Sq.Ft | 28 | 12 | 336 | 0 | 336 | 0 | 28 | 336 | 0 | 336 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. Rework/Extrawork | Approved | tausif | 1900-01-01
GANGA ASMI | 65 | 1 | 08 Feb 2021 | DAMU RATHOD | CP Lounge Work | Backfilling - UDR | Cu.Ft | 175.37 | 3.5 | 613.8 | 0 | 613.8 | 0 | 175.37 | 613.8 | 0 | 613.8 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | UTI. Drainage | Approved | tausif | 1900-01-01
GANGA ASMI | 65 | 0 | 08 Feb 2021 | DAMU RATHOD | CP Lounge Work | Excavation | Cu.Ft | 120 | 6.5 | 780 | 0 | 780 | 0 | 120 | 780 | 0 | 780 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ASMI | 66 | 0 | 08 Feb 2021 | PAPPU BAGELA | CP Lounge Work | Vitrified Flooring -BC | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 08 Feb 2021 |  | B.C. Internal Finishing Itmes | Cancelled | tausif | 08 Feb 2021
GANGA ASMI | 66 | 0 | 08 Feb 2021 | PAPPU BAGELA | CP Lounge Work | Vitrified Flooring -BC | Sq.Ft | 550.25 | 20 | 11005 | 1980.9 | 12985.9 | 2.5 | 550.25 | 11005 | 1980.9 | 12985.9 | 0 | 0 | to be done by contractor. | 100 |  | tausif | tausif | construction open | 08 Feb 2021 |  | B.C. Internal Finishing Itmes | Approved | tausif | 1900-01-01
GANGA ASMI | 67 | 0 | 08 Feb 2021 | SAI PLUMBING WORKS | PCMC Water Connection | GI Line 1/2" | R.Ft | 68 | 4 | 272 | 48.96 | 320.96 | 2.5 | 0 | 0 | 0 | 0 | 68 | 0 |  | 0 |  | tausif | tausif | construction open | 26 Feb 2021 |  | 08 PLUMBING WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 67 | 0 | 08 Feb 2021 | SAI PLUMBING WORKS | PCMC Water Connection | Water Meter Fixing Work - UWR | No. | 1 | 100 | 100 | 18 | 118 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | tausif | construction open | 26 Feb 2021 |  | UTI. Water Supply | Approved | tausif | 1900-01-01
GANGA ASMI | 67 | 0 | 08 Feb 2021 | SAI PLUMBING WORKS | PCMC Water Connection | ASTM Pipe Line 1/2"- SOI | R.Ft | 308 | 4 | 1232 | 221.76 | 1453.76 | 2.5 | 0 | 0 | 0 | 0 | 308 | 0 |  | 0 |  | tausif | tausif | construction open | 26 Feb 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 67 | 0 | 08 Feb 2021 | SAI PLUMBING WORKS | PCMC Water Connection | 1/2" Ball Valve Fixing - UWR | No. | 2 | 100 | 200 | 36 | 236 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | tausif | tausif | construction open | 26 Feb 2021 |  | UTI. Water Supply | Approved | tausif | 1900-01-01
GANGA ASMI | 68 | 0 | 08 Feb 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | PCMC Water Connection | Excavation | Cu.Ft | 1146 | 6.5 | 7449 | 0 | 7449 | 0 | 472.8751 | 3073.69 | 0 | 3073.69 | 673.1249 | 4375.31 |  | 41.2631 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | Fabrication work (L) | Kgs | 413.25 | 23.4 | 9670.05 | 1740.6 | 11410.65 | 2.5 | 371.0146 | 8681.74 | 1562.72 | 10244.46 | 42.2354 | 1166.19 |  | 89.7797 |  | tausif | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | Fabrication work (L) | Kgs | 1470 | 23.4 | 34398 | 6191.64 | 40589.64 | 2.5 | 1358.6578 | 31792.59 | 5722.66 | 37515.25 | 111.3422 | 3074.39 |  | 92.4257 |  | tausif | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | Fabrication work (L) | Kgs | 203.5 | 23.4 | 4761.9 | 857.14 | 5619.04 | 2.5 | 203.5 | 4761.9 | 857.14 | 5619.04 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | Fabrication work (L) | Kgs | 183.6 | 31.05 | 5700.78 | 1026.14 | 6726.92 | 2.5 | 162.1799 | 5035.69 | 906.42 | 5942.11 | 21.4201 | 784.81 |  | 88.3333 |  | tausif | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | Fabrication work (L) | Kgs | 34 | 23.4 | 795.6 | 143.2 | 938.8 | 2.5 | 34 | 795.6 | 143.2 | 938.8 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | Plate 4" x 4" (L) | No. | 12 | 27 | 324 | 58.32 | 382.32 | 2.5 | 12 | 324 | 58.32 | 382.32 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | J Hook - Mkt | No. | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Cancelled | tausif | 10 Feb 2021
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | GI Sheet Fixing | Sq.Ft | 1981 | 7 | 13867 | 2496.06 | 16363.06 | 2.5 | 1981 | 13867 | 2496.06 | 16363.06 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | DEV. Entrance Gate | Approved | tausif | 1900-01-01
GANGA ASMI | 69 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Fabrication Work | Transportation | No. | 1 | 4000 | 4000 | 720 | 4720 | 2.5 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | DEV. Ext Development | Approved | tausif | 1900-01-01
GANGA ASMI | 70 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | CP Lounge Fabrication Work | Fabrication work (M) | Kgs | 1470 | 52 | 76440 | 13759.2 | 90199.2 | 0 | 1358.6622 | 70650.43 | 12717.08 | 83367.51 | 111.3378 | 6831.69 |  | 92.426 |  | tausif | tausif | construction open | 09 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 70 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | CP Lounge Fabrication Work | Fabrication work (M) | Kgs | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 09 Feb 2021 |  | Admin. Direct Expenses | Cancelled | tausif | 09 Feb 2021
GANGA ASMI | 70 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | CP Lounge Fabrication Work | Plate 4" x 4" (M) | No. | 12 | 60 | 720 | 129.6 | 849.6 | 0 | 12 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 09 Feb 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 70 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | CP Lounge Fabrication Work | J Hook - Mkt | No. | 700 | 6 | 4200 | 756 | 4956 | 0 | 700 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 09 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 70 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | CP Lounge Fabrication Work | Fabrication work (M) | Kgs | 203.5 | 52 | 10582 | 1904.76 | 12486.76 | 0 | 203.5 | 10582 | 1904.76 | 12486.76 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 09 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 70 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | CP Lounge Fabrication Work | Fabrication work (M) | Kgs | 413.25 | 52 | 21489 | 3868.02 | 25357.02 | 0 | 370.9828 | 19291.11 | 3472.4 | 22763.51 | 42.2672 | 2593.51 |  | 89.772 |  | tausif | tausif | construction open | 09 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 70 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | CP Lounge Fabrication Work | Fabrication work (M) | Kgs | 183.6 | 69 | 12668.4 | 2280.32 | 14948.72 | 0 | 162.1739 | 11190 | 2014.2 | 13204.2 | 21.4261 | 1744.52 |  | 88.33 |  | tausif | tausif | construction open | 09 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 70 | 0 | 09 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | CP Lounge Fabrication Work | Fabrication work (M) | Kgs | 34 | 52 | 1768 | 318.24 | 2086.24 | 0 | 34 | 1768 | 318.24 | 2086.24 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 09 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 71 | 0 | 11 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | L Bracket Supports For Side Media | Fabrication work (M) | Kgs | 20.7 | 69 | 1428.3 | 257.1 | 1685.4 | 0 | 15.318 | 1056.94 | 190.24 | 1247.18 | 5.382 | 438.22 |  | 74 |  | shubham giri | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 72 | 0 | 11 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | L Bracket Supports For Side Media | Department Labour - Day | Day | 4 | 700 | 2800 | 504 | 3304 | 0 | 4 | 2800 | 504 | 3304 | 0 | 0 |  | 100 |  | shubham giri | tausif | construction open | 26 Feb 2021 |  | SOC. M. Civil Work Maintenace | Approved | tausif | 1900-01-01
GANGA ASMI | 73 | 0 | 11 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Precoated Sheet Fixing Near Open Gutter Near Nalla | Fabrication work (M) | Kgs | 20.7 | 69 | 1428.3 | 257.1 | 1685.4 | 0 | 20.7 | 1428.3 | 257.1 | 1685.4 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 73 | 0 | 11 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Precoated Sheet Fixing Near Open Gutter Near Nalla | Hardware Material | No. | 1 | 500 | 500 | 90 | 590 | 0 | 1 | 500 | 90 | 590 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 73 | 0 | 11 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Precoated Sheet Fixing Near Open Gutter Near Nalla | Fabrication work (M) | Kgs | 56 | 52 | 2912 | 524.16 | 3436.16 | 0 | 49.84 | 2591.68 | 466.5 | 3058.18 | 6.16 | 377.98 |  | 89 |  | shubham giri | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 74 | 0 | 12 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | Precoated Sheet Fixing Near Open Gutter Near Nalla | GI Sheet Fixing | Sq.Ft | 120 | 16 | 1920 | 345.6 | 2265.6 | 2.5 | 120 | 1920 | 345.6 | 2265.6 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | DEV. Entrance Gate | Approved | tausif | 1900-01-01
GANGA ASMI | 75 | 0 | 18 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | Media Frames Sales office&12m Road | Transport Charges | No. | 1 | 3000 | 3000 | 540 | 3540 | 2.5 | 1 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 75 | 0 | 18 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | Media Frames Sales office&12m Road | Fabrication work (L) | Kgs | 854.55 | 27.6 | 23585.58 | 4245.4 | 27830.98 | 2.5 | 854.4646 | 23583.22 | 4244.96 | 27828.18 | 0.0854 | 2.8 |  | 99.99 |  | tausif | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 75 | 0 | 18 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | Media Frames Sales office&12m Road | Fabrication work (L) | Kgs | 0 | 31.05 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | tausif | 19 Feb 2021
GANGA ASMI | 76 | 0 | 18 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Media Frames Sales office&12m Road | Hardware Material | No. | 1 | 1000 | 1000 | 180 | 1180 | 0 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 76 | 0 | 18 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Media Frames Sales office&12m Road | Fabrication work (M) | Kgs | 854.55 | 69 | 58963.95 | 10613.52 | 69577.47 | 0 | 854.55 | 58963.95 | 10613.52 | 69577.47 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 77 | 0 | 19 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | MS Stage For Selfi Point | Fabrication work (L) | Kgs | 51.75 | 27.6 | 1428.3 | 257.1 | 1685.4 | 2.5 | 47.7135 | 1316.89 | 237.04 | 1553.93 | 4.0365 | 131.47 |  | 92.2 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 77 | 1 | 19 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | Frames&Arch Fabrication Rework | Department Labour- BC | No. | 1 | 4900 | 4900 | 882 | 5782 | 0 | 1 | 4900 | 882 | 5782 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ASMI | 77 | 0 | 19 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | Media Flex MS Arch | Fabrication work (L) | Kgs | 547.52 | 23.4 | 12811.97 | 2306.16 | 15118.13 | 2.5 | 519.1037 | 12147.03 | 2186.46 | 14333.49 | 28.4163 | 784.64 |  | 94.81 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 77 | 0 | 19 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION | Media Flex Box Type Arch Surrounding Frames | Fabrication work (L) | Kgs | 189.75 | 27.6 | 5237.1 | 942.68 | 6179.78 | 2.5 | 127.6638 | 3523.52 | 634.24 | 4157.76 | 62.0862 | 2022.02 |  | 67.28 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 79 | 0 | 19 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Media Flex MS Arch | Fabrication work (M) | Kgs | 547.52 | 52 | 28471.04 | 5124.78 | 33595.82 | 0 | 519.1037 | 26993.39 | 4858.82 | 31852.21 | 28.4163 | 1743.61 | (MS Angle 40 x 40 x 5)mm | 94.81 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 79 | 0 | 19 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Media Flex Box Type Arch Surrounding Frames | Fabrication work (M) | Kgs | 189.75 | 69 | 13092.75 | 2356.7 | 15449.45 | 0 | 127.6638 | 8808.8 | 1585.58 | 10394.38 | 62.0862 | 5055.07 |  | 67.28 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 79 | 0 | 19 Feb 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | MS Stage For Selfi Point | Fabrication work (M) | Kgs | 51.75 | 69 | 3570.75 | 642.74 | 4213.49 | 0 | 47.7135 | 3292.23 | 592.6 | 3884.83 | 4.0365 | 328.66 |  | 92.2 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 80 | 0 | 19 Feb 2021 | VIJAY MOHITE | Site Infra Gate pole footing Exca & Concrete work | Concrete Work - UWT | Cu.Ft | 35.152 | 125 | 4394 | 0 | 4394 | 0 | 35.152 | 4394 | 0 | 4394 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | UTI. U.G.W.T | Approved | tausif | 1900-01-01
GANGA ASMI | 80 | 1 | 19 Feb 2021 | VIJAY MOHITE | Sales office UCR work for DG Foundation | UCR Masonary - SOS | Cu.Ft | 27 | 97 | 2619 | 0 | 2619 | 2.5 | 27 | 2619 | 0 | 2619 | 0 | 0 |  | 100 |  | shubham giri | tausif | construction open | 26 Feb 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 80 | 1 | 19 Feb 2021 | VIJAY MOHITE | Sales office BBM Work & PCC Work | Blockwork-UST | Sq.Ft | 53.62 | 75 | 4021.5 | 0 | 4021.5 | 2.5 | 53.6195 | 4021.46 | 0 | 4021.46 | 0.0005 | 0.04 |  | 99.9991 |  | shubham giri | tausif | construction open | 26 Feb 2021 |  | UTI. S.T.P | Approved | tausif | 1900-01-01
GANGA ASMI | 80 | 3 | 19 Feb 2021 | VIJAY MOHITE | M.S. Barrication work | MS Barrication work (M+L) | Sq.Ft | 4091 | 225 | 920475 | 0 | 920475 | 2.5 | 0 | 0 | 0 | 0 | 4091 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 26 Feb 2021 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 80 | 2 | 19 Feb 2021 | VIJAY MOHITE | Sales Office&Show Flats -Masonary & Plaster(L) | Tar Plaster- MKt | Sq.Ft | 2275 | 35 | 79625 | 0 | 79625 | 2.5 | 2275 | 79625 | 0 | 79625 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 80 | 2 | 19 Feb 2021 | VIJAY MOHITE | Sales Office&Show Flats -Masonary & Plaster(L) | Brickwork 6" - Mkt | Sq.Ft | 1244 | 75 | 93300 | 0 | 93300 | 2.5 | 1244 | 93300 | 0 | 93300 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 80 | 0 | 19 Feb 2021 | VIJAY MOHITE | Site Infra Gate pole footing Exca & Concrete work | Excavation - DEn | No. | 2 | 1000 | 2000 | 0 | 2000 | 0 | 2 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | DEV. Entrance Gate | Approved | tausif | 1900-01-01
GANGA ASMI | 80 | 1 | 19 Feb 2021 | VIJAY MOHITE | Sales office BBM Work & PCC Work | PCC Work | Sq.Ft | 267 | 43 | 11481 | 0 | 11481 | 2.5 | 267 | 11481 | 0 | 11481 | 0 | 0 |  | 100 |  | shubham giri | tausif | construction open | 26 Feb 2021 |  | 02 RCC WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 81 | 2 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 53rd National Safety Week 2023 | Flag | No. | 1 | 400 | 400 | 0 | 400 | 0 | 1 | 400 | 0 | 400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | Food Expenses | No. | 1050 | 30 | 31500 | 0 | 31500 | 0 | 1050 | 31500 | 0 | 31500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | Safety Banner with design | No. | 3 | 2000 | 6000 | 0 | 6000 | 0 | 3 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | Safety Banner with design | No. | 6 | 1700 | 10200 | 0 | 10200 | 0 | 6 | 10200 | 0 | 10200 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | First Aid Training Program | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2021 |  | Admin. Indirect Expenses | Cancelled | ADITYA.CHOUGULE | 24 Feb 2024
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | Food Expenses | No. | 500 | 30 | 15000 | 0 | 15000 | 0 | 500 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 2 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 53rd National Safety Week 2023 | Safety Banner | No. | 1 | 600 | 600 | 0 | 600 | 0 | 1 | 600 | 0 | 600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 1 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 52nd Year National Safety Week 2022 | Safety Banner | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2021 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 81 | 1 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 52nd Year National Safety Week 2022 | Safety Banner | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2021 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 81 | 2 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 53rd National Safety Week 2023 | Safety Badge | No. | 50 | 4 | 200 | 0 | 200 | 0 | 50 | 200 | 0 | 200 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | Flag | No. | 6 | 500 | 3000 | 0 | 3000 | 0 | 6 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | Safety Badge | No. | 300 | 4 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 300 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | Labour lumpsum | No. | 1 | 41500 | 41500 | 0 | 41500 | 0 | 0.8095 | 33594.25 | 0 | 33594.25 | 0.1905 | 7905.75 |  | 80.95 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | First Aid Training Program | No. | 20 | 1000 | 20000 | 0 | 20000 | 0 | 20 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 3 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 54th National Safety Week 2024 | Flex Printing- No. | No. | 5 | 400 | 2000 | 0 | 2000 | 0 | 5 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 81 | 0 | 24 Feb 2021 | SACHIN PRALHAD GAIKWAD | 50 Year National Safety Week 2021 | Miscellaneous Expenses | No. | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0.9211 | 6908.25 | 0 | 6908.25 | 0.0789 | 591.75 |  | 92.11 |  | shubham giri | tausif | construction open | 24 Feb 2021 |  | 14 MISC WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Rework Fabrication | Gate Removing Work DEn | No. | 1 | 800 | 800 | 144 | 944 | 2.5 | 1 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | DEV. Extrawork/Rework | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Rework Fabrication | Excavation & Concrete Pit - Dld | No. | 17 | 300 | 5100 | 918 | 6018 | 2.5 | 17 | 5100 | 918 | 6018 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Media Flex Media Frames | Fabrication work lumpsum -SOSB | No. | 1 | 18000 | 18000 | 3240 | 21240 | 2.5 | 1 | 18000 | 3240 | 21240 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Media Flex Media Frames | Fabrication work lumpsum -SOSB | No. | 1 | 20000 | 20000 | 3600 | 23600 | 2.5 | 0.895 | 17900 | 3222 | 21122 | 0.105 | 2478 |  | 89.5 |  | tausif | tausif | construction open | 26 Feb 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Media Flex Media Frames | Fabrication work (M) | Kgs | 390.64 | 56 | 21875.84 | 3937.66 | 25813.5 | 0 | 390.64 | 21875.84 | 3937.66 | 25813.5 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Rework Fabrication | Fabrication work-lumpsum-DEn | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 1 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | DEV. Entrance Gate | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Media Flex Media Frames | Excavation & Concrete Pit - Dld | No. | 11 | 400 | 4400 | 792 | 5192 | 2.5 | 11 | 4400 | 792 | 5192 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Media Flex Media Frames | Fabrication work (M) | Kgs | 61.96 | 43 | 2664.28 | 479.58 | 3143.86 | 0 | 61.96 | 2664.28 | 479.58 | 3143.86 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Media Flex Media Frames | Transport charges-SOS | No. | 1 | 1500 | 1500 | 270 | 1770 | 0 | 1 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Rework Fabrication | Fabrication work (M) | Kgs | 59.7 | 43 | 2567.1 | 462.08 | 3029.18 | 0 | 59.7 | 2567.1 | 462.08 | 3029.18 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Media Flex Media Frames | Fabrication work (M) | Kgs | 212.21 | 56 | 11883.76 | 2139.08 | 14022.84 | 0 | 0 | 0 | 0 | 0 | 212.21 | 0 |  | 0 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Rework Fabrication | Idle charges-BC | No. | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ASMI | 82 | 0 | 24 Feb 2021 | SHIVAM FABRICATION & STEEL FURNITURE | Rework Fabrication | Fabrication work (M) | Kgs | 63.51 | 43 | 2730.93 | 491.56 | 3222.49 | 0 | 63.51 | 2730.93 | 491.56 | 3222.49 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 26 Feb 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 1 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office - Housekeeping Material - 1 No. | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 1 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office - Housekeeping Material - 1 No. | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 1 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office - Housekeeping Material - 1 No. | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.998 | 1996 | 359.28 | 2355.28 | 0.002 | 4.72 |  | 99.8 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 1 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office - Housekeeping Material - 1 No. | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.134 | 268 | 48.24 | 316.24 | 0.866 | 2043.76 |  | 13.4 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 1 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office - Housekeeping Material - 1 No. | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.993 | 1986 | 357.48 | 2343.48 | 0.007 | 16.52 |  | 99.3 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.052 | 104 | 0 | 104 | 0.948 | 2256 |  | 5.2 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.8315 | 1663 | 299.34 | 1962.34 | 0.1685 | 397.66 |  | 83.15 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.9975 | 1995 | 359.1 | 2354.1 | 0.0025 | 5.9 |  | 99.75 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 83 | 0 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.995 | 1990 | 358.2 | 2348.2 | 0.005 | 11.8 |  | 99.5 |  | tausif | tausif | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 83 | 2 | 25 Feb 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 13 Mar 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | skmishra | 14 Sep 2021
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 1 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 33000 | 33000 | 5940 | 38940 | 0 | 1 | 33000 | 5940 | 38940 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jawalikar | 16 Jul 2021
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 1 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 33000 | 33000 | 5940 | 38940 | 0 | 1 | 33000 | 5940 | 38940 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jawalikar | 16 Jul 2021
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 0 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 33333 | 33333 | 5999.94 | 39332.94 | 0 | 1 | 33333 | 5999.94 | 39332.94 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jawalikar | 16 Jul 2021
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 3 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Mar 2021 |  | S OH Expenses | Cancelled | ADITYA CHOUGULE | 19 Aug 2022
GANGA ASMI | 84 | 1 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 33000 | 33000 | 5940 | 38940 | 0 | 1 | 33000 | 5940 | 38940 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jawalikar | 16 Jul 2021
GANGA ASMI | 84 | 0 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 33333 | 33333 | 5999.94 | 39332.94 | 0 | 1 | 33333 | 5999.94 | 39332.94 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jawalikar | 16 Jul 2021
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 0 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 33333 | 33333 | 5999.94 | 39332.94 | 0 | 1 | 33333 | 5999.94 | 39332.94 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jawalikar | 16 Jul 2021
GANGA ASMI | 84 | 4 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 60000 | 60000 | 10800 | 70800 | 0 | 1 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 84 | 2 | 26 Feb 2021 | UNIQUE AIR CONDITIONING PROJECTS INDIA PVT LTD | Sales Office - AC Rental charges | Rental Charges - So | Month | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 13 Mar 2021 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 85 | 0 | 04 Mar 2021 | SHREE MAHALAXMI CRANE SERVICES | Box Type Arch Vertical Pole & Horizontal Pole Errection | Crane Charges - MWB | Hrs | 5 | 850 | 4250 | 765 | 5015 | 0 | 5 | 4250 | 765 | 5015 | 0 | 0 |  | 100 |  | shubham giri | tausif | construction open | 13 Mar 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 85 | 1 | 04 Mar 2021 | SHREE MAHALAXMI CRANE SERVICES | Safety Tank Placing&Old Ele Pole removing work | Crane Charges - MWB | Hrs | 4 | 800 | 3200 | 576 | 3776 | 0 | 4 | 3200 | 576 | 3776 | 0 | 0 |  | 100 |  | Runal Kindalkar | skmishra | construction open | 13 Mar 2021 |  | MKT. Marketing Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 86 | 0 | 09 Mar 2021 | PRIYANKA KULKARNI | Site Expenses | Site Expenses -SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 09 Mar 2021 |  | S OH Expenses | Cancelled | skmishra | 09 Mar 2021
GANGA ASMI | 86 | 1 | 09 Mar 2021 | PRIYANKA KULKARNI | Marketing Expenses | Marketing Operating Expenses | Month | 12 | 10000 | 120000 | 0 | 120000 | 0 | 4.4482 | 44482.12 | 0 | 44482.12 | 7.5518 | 75517.88 |  | 37.0683 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Mar 2021 |  | MKT. Marketing Operating Expen | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 86 | 0 | 09 Mar 2021 | PRIYANKA KULKARNI | Marketing Expenses | Marketing Operating Expenses | Month | 10 | 10000 | 100000 | 0 | 100000 | 0 | 3.8869 | 38868.9 | 0 | 38868.9 | 6.1131 | 61131.1 |  | 38.869 |  | shubham giri | tausif | construction open | 09 Mar 2021 |  | MKT. Marketing Operating Expen | Approved | tausif | 1900-01-01
GANGA ASMI | 86 | 1 | 09 Mar 2021 | PRIYANKA KULKARNI | Marketing Expenses | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Mar 2021 |  | MKT. Marketing Operating Expen | Cancelled | skmishra | 28 Feb 2022
GANGA ASMI | 86 | 0 | 09 Mar 2021 | PRIYANKA KULKARNI | Site Expenses | Site Expenses -SO | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 09 Mar 2021 |  | S OH Expenses | Cancelled | tausif | 09 Mar 2021
GANGA ASMI | 87 | 0 | 11 Mar 2021 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | PRINTING PRINTING-NO.-(NA) | LEAFLET PRINTING | No. | 96000 | 0.82 | 78720 | 9446.4 | 88166.4 | 0 | 96000 | 78720 | 9446.4 | 88166.4 | 0 | 0 | GANGA ASMI WAKAD PROJECT SALES PROMOTION LEAFLET PRINT FOR NEWS PAPER INSERTION SIZE AS A - 4 F/B PRINT QTY. 96 K | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 12 Mar 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 88 | 0 | 17 Mar 2021 | YOGESH BALU ICHAKE | Survey Work | Total Statiotn Survey | Day | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | Land Cost | Approved | tausif | 1900-01-01
GANGA ASMI | 89 | 1 | 17 Mar 2021 | AZIZ KHAN | CP Lounge Gypsum Sheet Strip Fixing | Gypsum Board Fixing (M+L) | R.Ft | 200 | 32.5 | 6500 | 0 | 6500 | 0 | 187.2 | 6084 | 0 | 6084 | 12.8 | 416 |  | 93.6 |  | tausif | chetan.jawalikar | construction open | 05 Apr 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 89 | 0 | 17 Mar 2021 | AZIZ KHAN | CP Lounge False Ceiling Work | False Ceiling work - Mkt | Sq.Ft | 550.25 | 65 | 35766.25 | 0 | 35766.25 | 0 | 550.25 | 35766.25 | 0 | 35766.25 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 90 | 0 | 17 Mar 2021 | DAMU RATHOD | Excavation For Cable ,Bore Line ,Arch& Concrete for Arch Pi | Concrete work- Mkt | No. | 2 | 1000 | 2000 | 0 | 2000 | 0 | 2 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 90 | 0 | 17 Mar 2021 | DAMU RATHOD | Excavation For Cable ,Bore Line ,Arch& Concrete for Arch Pi | Excavation work- cc | Cu.Ft | 285.25 | 6.5 | 1854.13 | 0 | 1854.13 | 0 | 285.25 | 1854.13 | 0 | 1854.13 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | B.C. Customer Changes | Approved | tausif | 1900-01-01
GANGA ASMI | 90 | 1 | 17 Mar 2021 | DAMU RATHOD | Aluform material storage area civil work | Grouting Work - Dld | No. | 2 | 1000 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 90 | 1 | 17 Mar 2021 | DAMU RATHOD | Aluform material storage area civil work | Excavation & Concrete -DSP - | No. | 64 | 200 | 12800 | 0 | 12800 | 0 | 64 | 12800 | 0 | 12800 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 90 | 1 | 17 Mar 2021 | DAMU RATHOD | Aluform material storage area civil work | Excavation & Concrete -DSP - | No. | 0 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Apr 2021 |  | DEV. Swimming Pool | Cancelled | ADITYA CHOUGULE | 27 Feb 2023
GANGA ASMI | 90 | 0 | 17 Mar 2021 | DAMU RATHOD | Excavation For Cable ,Bore Line ,Arch& Concrete for Arch Pi | Transportation- Mkt | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 91 | 0 | 17 Mar 2021 | SUMAN ENTERPRISES | Temporary Road Filling for Vastu Wall | Filling Work -Dld | Cu.Ft | 3883 | 7 | 27181 | 4892.58 | 32073.58 | 0 | 3883 | 27181 | 4892.58 | 32073.58 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 92 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | Copper Pipe with Insulation (L) | Mtrs | 26 | 139.2 | 3619.2 | 651.46 | 4270.66 | 0 | 22.178 | 3087.18 | 555.7 | 3642.88 | 3.822 | 627.78 |  | 85.3 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 04 ELECTRICAL WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 92 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | A.C. Installation (L)-ARW | No. | 2 | 1500 | 3000 | 540 | 3540 | 0 | 1.6 | 2400 | 432 | 2832 | 0.4 | 708 |  | 80 |  | shubham giri | tausif | Construction | 04 May 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 92 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | Gas Charging (L). | Kgs | 3 | 160 | 480 | 86.4 | 566.4 | 0 | 3 | 480 | 86.4 | 566.4 | 0 | 0 |  | 100 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 04 ELECTRICAL WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 92 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | SITC of Communication Cable (L) | Mtrs | 28 | 29 | 812 | 146.16 | 958.16 | 0 | 24.1724 | 701 | 126.18 | 827.18 | 3.8276 | 130.98 |  | 86.33 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | tausif | 1900-01-01
GANGA ASMI | 92 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | SITC of Drain Pipe (L) | Mtrs | 6 | 22 | 132 | 23.76 | 155.76 | 0 | 6 | 132 | 23.76 | 155.76 | 0 | 0 |  | 100 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | tausif | 1900-01-01
GANGA ASMI | 92 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | Table Top Stand for Spilt AC (L) | No. | 2 | 160 | 320 | 57.6 | 377.6 | 0 | 2 | 320 | 57.6 | 377.6 | 0 | 0 |  | 100 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 04 ELECTRICAL WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 93 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | SITC of Drain Pipe (M) | Mtrs | 6 | 88 | 528 | 95.04 | 623.04 | 0 | 6 | 528 | 95.04 | 623.04 | 0 | 0 |  | 100 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | tausif | 1900-01-01
GANGA ASMI | 93 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | Gas Charging (M). | Kgs | 3 | 640 | 1920 | 345.6 | 2265.6 | 0 | 3 | 1920 | 345.6 | 2265.6 | 0 | 0 |  | 100 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 04 ELECTRICAL WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 93 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | Copper Pipe with Insulation (M) | Mtrs | 26 | 556.8 | 14476.8 | 2605.82 | 17082.62 | 0 | 22.178 | 12348.71 | 2222.76 | 14571.47 | 3.822 | 2511.15 |  | 85.3 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 04 ELECTRICAL WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 93 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | Table Top Stand for Spilt AC (M) | No. | 2 | 640 | 1280 | 230.4 | 1510.4 | 0 | 2 | 1280 | 230.4 | 1510.4 | 0 | 0 |  | 100 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 04 ELECTRICAL WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 93 | 0 | 18 Mar 2021 | NEPTUNE ENGINEERS | CP Lounge AC Work | SITC of Communication Cable (M) | Mtrs | 28 | 116 | 3248 | 584.64 | 3832.64 | 0 | 24.1724 | 2804 | 504.72 | 3308.72 | 3.8276 | 523.92 |  | 86.33 |  | shubham giri | tausif | Construction | 04 May 2021 |  | 13 Lift,Firefightng,Mech Equip | Approved | tausif | 1900-01-01
GANGA ASMI | 94 | 2 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Excavation In Hard Rock - DTR | Cu.Mtrs | 413.63 | 210 | 86862.3 | 15635.22 | 102497.52 | 0 | 413.63 | 86862.3 | 15635.22 | 102497.52 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 05 Apr 2021 |  | DEV. Trimix Road | Approved | skmishra | 1900-01-01
GANGA ASMI | 94 | 7 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Poclain Charges - BC - | Hrs | 20 | 1800 | 36000 | 6480 | 42480 | 0 | 20 | 36000 | 6480 | 42480 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 94 | 3 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 513.85 | 15 | 7707.75 | 1387.4 | 9095.15 | 0 | 513.85 | 7707.75 | 1387.4 | 9095.15 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 94 | 9 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Excavation in Hard Rock | Cu.Mtrs | 1125 | 210 | 236250 | 42525 | 278775 | 0 | 0 | 0 | 0 | 0 | 1125 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 94 | 2 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 413.63 | 15 | 6204.45 | 1116.8 | 7321.25 | 0 | 413.63 | 6204.45 | 1116.8 | 7321.25 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | skmishra | 1900-01-01
GANGA ASMI | 94 | 9 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Excavation In Hard Rock Rate Diff DTR | Cu.Mtrs | 800 | 80 | 64000 | 11520 | 75520 | 0 | 450.57 | 36045.6 | 6488.2 | 42533.8 | 349.43 | 32986.2 |  | 56.3213 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 05 Apr 2021 |  | DEV. Trimix Road | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 94 | 1 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 1310.36 | 15 | 19655.4 | 3537.98 | 23193.38 | 0 | 1310.36 | 19655.4 | 3537.98 | 23193.38 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 94 | 3 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 513.85 | 60 | 30831 | 5549.58 | 36380.58 | 0 | 513.85 | 30831 | 5549.58 | 36380.58 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 94 | 0 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 2088.8 | 150 | 313320 | 56397.6 | 369717.6 | 0 | 2088.8 | 313320 | 56397.6 | 369717.6 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 94 | 8 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Murum supply & filling for wing 1 plinth | Murum Supply- BC | Cu.Ft | 55016.355 | 7 | 385114.49 | 69320.6 | 454435.09 | 0 | 52353.9486 | 366477.64 | 65965.98 | 432443.62 | 2662.4064 | 21991.46 |  | 95.1607 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 94 | 6 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Backfilling | Cu.Mtrs | 5707.75 | 15 | 85616.25 | 15410.92 | 101027.17 | 0 | 5707.75 | 85616.25 | 15410.92 | 101027.17 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 94 | 5 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Collapse Soil Removing | Spreading & Levelling Work | Cu.Mtrs | 370 | 15 | 5550 | 999 | 6549 | 0 | 0 | 0 | 0 | 0 | 370 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 94 | 5 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Collapse Soil Removing | Soil Removing | Cu.Mtrs | 370 | 150 | 55500 | 9990 | 65490 | 0 | 0 | 0 | 0 | 0 | 370 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 94 | 8 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Parking Murum supply & filling for wing 1 podium park | Murum Supply- BC | Cu.Ft | 16237.837 | 7 | 113664.86 | 20459.68 | 134124.54 | 0 | 0 | 0 | 0 | 0 | 16237.837 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 94 | 4 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 450.09 | 15 | 6751.35 | 1215.24 | 7966.59 | 0 | 450.09 | 6751.35 | 1215.24 | 7966.59 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | skmishra | 1900-01-01
GANGA ASMI | 94 | 0 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 8355.18 | 15 | 125327.7 | 22558.98 | 147886.68 | 2.5 | 8355.1716 | 125327.57 | 22558.96 | 147886.53 | 0.0084 | 0.15 |  | 99.9999 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 94 | 1 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 1310.36 | 150 | 196554 | 35379.72 | 231933.72 | 0 | 1310.36 | 196554 | 35379.72 | 231933.72 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 94 | 4 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 450.09 | 150 | 67513.5 | 12152.44 | 79665.94 | 0 | 0 | 0 | 0 | 0 | 450.09 | 0 |  | 0 |  | Avinash Padmanabha | skmishra | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | skmishra | 1900-01-01
GANGA ASMI | 94 | 0 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 6266.38 | 60 | 375982.8 | 67676.9 | 443659.7 | 0 | 6266.38 | 375982.8 | 67676.9 | 443659.7 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 94 | 8 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Road Murum supply & filling for East, West & south side road | Murum Supply- BC | Cu.Ft | 52879.798 | 7 | 370158.59 | 66628.54 | 436787.13 | 0 | 0 | 0 | 0 | 0 | 52879.798 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 94 | 9 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 1125 | 15 | 16875 | 3037.5 | 19912.5 | 0 | 0 | 0 | 0 | 0 | 1125 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 94 | 9 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Excavation in Hard Rock | Cu.Mtrs | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA.CHOUGULE | 08 Nov 2023
GANGA ASMI | 95 | 1 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Parking Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 381.12 | 150 | 57168 | 10290.24 | 67458.24 | 0 | 381.12 | 57168 | 10290.24 | 67458.24 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 95 | 0 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Parking Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 18665.28 | 15 | 279979.2 | 50396.26 | 330375.46 | 0 | 9779.3572 | 146690.36 | 26404.26 | 173094.62 | 8885.9228 | 157280.84 |  | 52.3933 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 95 | 2 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Backfilling | Cu.Mtrs | 13138.94 | 15 | 197084.1 | 35475.14 | 232559.24 | 0 | 8426.7511 | 126401.27 | 22752.22 | 149153.49 | 4712.1889 | 83405.75 |  | 64.1357 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | DUSHANT.GORE | 10 Aug 2023
GANGA ASMI | 95 | 3 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Murum Supply- BC | Cu.Ft | 60963 | 7 | 426741 | 76813.38 | 503554.38 | 0 | 0 | 0 | 0 | 0 | 60963 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. RCC Substructure | Approved | DUSHANT.GORE | 10 Aug 2023
GANGA ASMI | 95 | 4 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 800 | 300 | 240000 | 43200 | 283200 | 0 | 450.578 | 135173.4 | 24331.22 | 159504.62 | 349.422 | 123695.38 |  | 56.3223 |  | DUSHANT.GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | DUSHANT.GORE | 10 Aug 2023
GANGA ASMI | 95 | 5 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Murum Supply- BC | Cu.Ft | 264330 | 7 | 1850310 | 333055.8 | 2183365.8 | 0 | 236699.7966 | 1656898.58 | 298241.74 | 1955140.32 | 27630.2034 | 228225.48 |  | 89.5471 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 95 | 0 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Parking Substructure Excavation Work | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 13998.96 | 60 | 839937.6 | 151188.76 | 991126.36 | 0 | 4945.6837 | 296741.02 | 53413.38 | 350154.4 | 9053.2763 | 640971.96 |  | 35.3289 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 95 | 1 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Parking Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 381.12 | 15 | 5716.8 | 1029.02 | 6745.82 | 0 | 381.12 | 5716.8 | 1029.02 | 6745.82 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 95 | 0 | 19 Mar 2021 | DRAUPADA EARTHMOVERS | Parking Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 4666.32 | 150 | 699948 | 125990.64 | 825938.64 | 0 | 4666.32 | 699948 | 125990.64 | 825938.64 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 96 | 2 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Backfilling | Cu.Mtrs | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 21 Mar 2022
GANGA ASMI | 96 | 1 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 1170.71 | 150 | 175606.5 | 31609.18 | 207215.68 | 0 | 1170.71 | 175606.5 | 31609.18 | 207215.68 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 96 | 2 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 0 | 225 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 96 | 0 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 5707.75 | 60 | 342465 | 61643.7 | 404108.7 | 0 | 4060.4645 | 243627.87 | 43853 | 287480.87 | 1647.2855 | 116627.83 |  | 71.1395 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 96 | 2 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Excavation By Needle (Shifting Inside) | Cu.Mtrs | 4096 | 225 | 921600 | 165888 | 1087488 | 0 | 4066.68 | 915003 | 164700.54 | 1079703.54 | 29.32 | 7784.46 |  | 99.2842 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 96 | 0 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 1902.59 | 150 | 285388.5 | 51369.94 | 336758.44 | 0 | 1902.59 | 285388.5 | 51369.94 | 336758.44 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 96 | 1 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 1170.71 | 15 | 17560.65 | 3160.92 | 20721.57 | 0 | 1170.71 | 17560.65 | 3160.92 | 20721.57 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 96 | 0 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 7610.34 | 15 | 114155.1 | 20547.92 | 134703.02 | 0 | 7610.0523 | 114150.78 | 20547.12 | 134697.9 | 0.2877 | 5.12 |  | 99.9962 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 97 | 0 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 2088.8 | 150 | 313320 | 56397.6 | 369717.6 | 0 | 2088.8 | 313320 | 56397.6 | 369717.6 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 97 | 1 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 662.91 | 150 | 99436.5 | 17898.58 | 117335.08 | 0 | 662.91 | 99436.5 | 17898.58 | 117335.08 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 97 | 1 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 662.91 | 15 | 9943.65 | 1789.86 | 11733.51 | 0 | 662.91 | 9943.65 | 1789.86 | 11733.51 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 97 | 2 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Parking Substructure Excavation Work | Excavation in Hard Rock | Cu.Mtrs | 432.88 | 210 | 90904.8 | 16362.86 | 107267.66 | 0 | 432.88 | 90904.8 | 16362.86 | 107267.66 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 97 | 0 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 8355.18 | 15 | 125327.7 | 22558.98 | 147886.68 | 0 | 6430.4362 | 96456.54 | 17362.16 | 113818.7 | 1924.7438 | 34067.98 |  | 76.9635 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 97 | 2 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Parking Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 432.88 | 15 | 6493.2 | 1168.78 | 7661.98 | 0 | 432.88 | 6493.2 | 1168.78 | 7661.98 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 97 | 0 | 20 Mar 2021 | DRAUPADA EARTHMOVERS | Wing-3 Substructure Excavation Work | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 6266.38 | 60 | 375982.8 | 67676.9 | 443659.7 | 0 | 4835.4951 | 290129.71 | 52223.36 | 342353.07 | 1430.8849 | 101306.63 |  | 77.1657 |  | chetan.jawalikar | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 98 | 0 | 22 Mar 2021 | DRAUPADA EARTHMOVERS | Plot Levelling&Cleaning | JCB Charges. | Day | 2 | 850 | 1700 | 306 | 2006 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 99 | 0 | 22 Mar 2021 | LAXMI ELECTRICALS | CP Lounge CP Lounge Electrical Work | 4 Sqmm Cable Laying | Mtrs | 200 | 25 | 5000 | 0 | 5000 | 2.5 | 110 | 2750 | 495 | 3245 | 90 | 1755 |  | 55 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 04 ELECTRICAL WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 99 | 0 | 22 Mar 2021 | LAXMI ELECTRICALS | CP Lounge CP Lounge Electrical Work | Light Point BC | No. | 8 | 200 | 1600 | 0 | 1600 | 2.5 | 8 | 1600 | 288 | 1888 | 0 | -288 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | B.C. Building Common Items | Approved | tausif | 1900-01-01
GANGA ASMI | 99 | 0 | 22 Mar 2021 | LAXMI ELECTRICALS | CP Lounge CP Lounge Electrical Work | Socket point-BC | No. | 5 | 200 | 1000 | 0 | 1000 | 2.5 | 5 | 1000 | 180 | 1180 | 0 | -180 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | B.C. Building Common Items | Approved | tausif | 1900-01-01
GANGA ASMI | 99 | 0 | 22 Mar 2021 | LAXMI ELECTRICALS | CP Lounge CP Lounge Electrical Work | AC Point BC | No. | 2 | 220 | 440 | 0 | 440 | 2.5 | 2 | 440 | 79.2 | 519.2 | 0 | -79.2 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | B.C. Internal Finishing Itmes | Approved | tausif | 1900-01-01
GANGA ASMI | 99 | 0 | 22 Mar 2021 | LAXMI ELECTRICALS | CP Lounge CP Lounge Electrical Work | 1.5 Sqmm Cable Laying | Mtrs | 100 | 25 | 2500 | 0 | 2500 | 2.5 | 100 | 2500 | 450 | 2950 | 0 | -450 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 04 ELECTRICAL WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 100 | 1 | 27 Mar 2021 | OM SAI ALLUMINIUM & FABRICATION | Media Frames For CP Lounge | Fabrication work (L) | Kgs | 91.295 | 24.15 | 2204.77 | 396.86 | 2601.63 | 2.5 | 0 | 0 | 0 | 0 | 91.295 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 05 Apr 2021 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 100 | 0 | 27 Mar 2021 | OM SAI ALLUMINIUM & FABRICATION | Media Frames For CP Lounge | Fabrication work (L) | Kgs | 412.84 | 24.15 | 9970.09 | 1794.62 | 11764.71 | 2.5 | 324.4344 | 7835.09 | 1410.32 | 9245.41 | 88.4056 | 2519.3 | Including Profit & Supervision Charges | 78.586 |  | tausif | tausif | construction open | 05 Apr 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 101 | 0 | 27 Mar 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Media Frames For CP Lounge | Fabrication work (M) | Kgs | 412.84 | 69 | 28485.96 | 5127.48 | 33613.44 | 0 | 324.4344 | 22385.97 | 4029.48 | 26415.45 | 88.4056 | 7197.99 |  | 78.586 |  | tausif | tausif | construction open | 05 Apr 2021 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 101 | 1 | 27 Mar 2021 | OM SAI ALLUMINIUM & FABRICATION (Material) | Media Frames For CP Lounge | Fabrication work (M) | Kgs | 91.295 | 69 | 6299.36 | 1133.88 | 7433.24 | 0 | 0 | 0 | 0 | 0 | 91.295 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 05 Apr 2021 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 102 | 0 | 27 Mar 2021 | AZIZ KHAN | CP Lounge Work | Puff Sheet (L) | Sq.Ft | 958 | 15 | 14370 | 0 | 14370 | 0 | 735.0063 | 11025.09 | 1984.52 | 13009.61 | 222.9937 | 1360.39 |  | 76.723 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 103 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work for DG Foundation for 125KVA & 45 KVA - 1 No. | PCC | Sq.Ft | 292.5 | 4 | 1170 | 0 | 1170 | 2.5 | 0 | 0 | 0 | 0 | 292.5 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 103 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work for DG Foundation for 125KVA & 45 KVA - 1 No. | Solling SOS | Sq.Ft | 243 | 6.5 | 1579.5 | 0 | 1579.5 | 2.5 | 0 | 0 | 0 | 0 | 243 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 103 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Road Crossing Chamber 12m Road | Excavation | Cu.Ft | 682 | 6.5 | 4433 | 0 | 4433 | 0 | 300 | 1950 | 0 | 1950 | 382 | 2483 |  | 43.9883 |  | tausif | tausif | construction open | 05 Apr 2021 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ASMI | 103 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work for DG Foundation for 125KVA & 45 KVA - 1 No. | Back Filling- LC | Cu.Ft | 486 | 3.5 | 1701 | 0 | 1701 | 0 | 0 | 0 | 0 | 0 | 486 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 103 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work for DG Foundation for 125KVA & 45 KVA - 1 No. | 9" Brick Work | Sq.Ft | 198 | 15 | 2970 | 0 | 2970 | 2.5 | 0 | 0 | 0 | 0 | 198 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 103 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Road Crossing Chamber 12m Road | Chamber 24" x 36" (5ft Ht) - UTI | No. | 2 | 1500 | 3000 | 0 | 3000 | 0 | 2 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | UTI. Electricity Infrastructur | Approved | tausif | 1900-01-01
GANGA ASMI | 103 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work for DG Foundation for 125KVA & 45 KVA - 1 No. | Excavation | Cu.Ft | 72 | 6.5 | 468 | 0 | 468 | 0 | 0 | 0 | 0 | 0 | 72 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 103 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work for DG Foundation for 125KVA & 45 KVA - 1 No. | PCC | Sq.Ft | 66 | 4 | 264 | 0 | 264 | 2.5 | 0 | 0 | 0 | 0 | 66 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 104 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Barrication Work | Excavation & Concrete Pit - Dld | No. | 22 | 150 | 3300 | 0 | 3300 | 0 | 16.0002 | 2400.03 | 0 | 2400.03 | 5.9998 | 899.97 |  | 72.7282 |  | tausif | tausif | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 104 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Main Entrance Barrication work | Excavation & Concrete Pit - Dld | No. | 2 | 1000 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Runal Kindalkar | skmishra | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | skmishra | 1900-01-01
GANGA ASMI | 104 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Main Entrance Barrication work | Excavation & Concrete Pit - Dld | No. | 12 | 150 | 1800 | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | Runal Kindalkar | skmishra | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | skmishra | 1900-01-01
GANGA ASMI | 104 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Construction Gate Fabrication Work | Excavation & Concrete Pit - Dld | No. | 2 | 1000 | 2000 | 0 | 2000 | 0 | 2 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 105 | 0 | 27 Mar 2021 | DAMU RATHOD | Box Type Arch Vertical Pole Pit Excavation &Old Pit Backfill | Transport Charges | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 105 | 0 | 27 Mar 2021 | DAMU RATHOD | Box Type Arch Vertical Pole Pit Excavation &Old Pit Backfill | Excavation | Cu.Ft | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | B.C. RCC Substructure | Cancelled | tausif | 31 Mar 2021
GANGA ASMI | 105 | 0 | 27 Mar 2021 | DAMU RATHOD | Box Type Arch Vertical Pole Pit Excavation &Old Pit Backfill | Excavation | Cu.Ft | 112 | 6.5 | 728 | 0 | 728 | 0 | 112 | 728 | 0 | 728 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | tausif | 1900-01-01
GANGA ASMI | 105 | 0 | 27 Mar 2021 | DAMU RATHOD | Box Type Arch Vertical Pole Pit Excavation &Old Pit Backfill | Backfilling Work USL | Cu.Ft | 112 | 3.5 | 392 | 0 | 392 | 0 | 112 | 392 | 0 | 392 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | UTI. Strom Line | Approved | tausif | 1900-01-01
GANGA ASMI | 105 | 0 | 27 Mar 2021 | DAMU RATHOD | Box Type Arch Vertical Pole Pit Excavation &Old Pit Backfill | Pit Concrete work | No. | 2 | 1000 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | tausif | tausif | construction open | 1900-01-01 |  | 02 RCC WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 105 | 0 | 27 Mar 2021 | DAMU RATHOD | Box Type Arch Vertical Pole Pit Excavation &Old Pit Backfill | Excavation & Concrete Pit - Dld | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Cancelled | tausif | 30 Mar 2021
GANGA ASMI | 106 | 0 | 27 Mar 2021 | YOGESH BALU ICHAKE | Wing-1 Excavation Point&Superimposed Dwg to Arch Layout | Total Statiotn Survey | Day | 0.5 | 4500 | 2250 | 0 | 2250 | 0 | 0.5 | 2250 | 0 | 2250 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | Land Cost | Approved | tausif | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | JCB Charges | Hrs | 4 | 850 | 3400 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | Soling Work -Mkt | Sq.Ft | 1040 | 6.5 | 6760 | 0 | 6760 | 0 | 1001 | 6506.5 | 0 | 6506.5 | 39 | 253.5 |  | 96.25 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | Backfilling - UDR | Cu.Ft | 1560 | 3.5 | 5460 | 0 | 5460 | 0 | 0 | 0 | 0 | 0 | 1560 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 107 | 2 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | JCB Charges | Hrs | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Apr 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 27 Jul 2022
GANGA ASMI | 107 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | PCC - SO | Sq.Ft | 1108 | 6 | 6648 | 0 | 6648 | 0 | 997.6432 | 5985.86 | 0 | 5985.86 | 110.3568 | 662.14 |  | 90.04 |  | tausif | chetan.jawalikar | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | Grouting Work - Dld | No. | 16 | 200 | 3200 | 0 | 3200 | 2.5 | 16 | 3200 | 0 | 3200 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 107 | 2 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | Back Filling- Dld | Cu.Ft | 1308.83 | 3.5 | 4580.91 | 0 | 4580.91 | 0 | 891.4206 | 3119.97 | 0 | 3119.97 | 417.4094 | 1460.93 |  | 68.1082 |  | tausif | tausif | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 107 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Excavation&Grouting For Customer Visitor Platform | Grouting of Pits MWB | No. | 4 | 300 | 1200 | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | tausif | tausif | construction open | 05 Apr 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 107 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | PCC - SO | Sq.Ft | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 05 Apr 2021 |  | S OH Infrastructure | Cancelled | tausif | 09 Apr 2021
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | PCC | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Apr 2021 |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 03 Aug 2022
GANGA ASMI | 107 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | PCC - SO | Sq.Ft | 1722 | 4 | 6888 | 0 | 6888 | 0 | 997.7268 | 3990.91 | 0 | 3990.91 | 724.2732 | 2897.09 |  | 57.94 |  | tausif | tausif | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 107 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | Jali fixing | Sq.Ft | 1108 | 8 | 8864 | 0 | 8864 | 0 | 997.7429 | 7981.94 | 0 | 7981.94 | 110.2571 | 882.06 |  | 90.049 |  | tausif | chetan.jawalikar | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 107 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | Rubble Soling. -S.O | Sq.Ft | 868 | 6.5 | 5642 | 0 | 5642 | 0 | 291.9778 | 1897.86 | 0 | 1897.86 | 576.0222 | 3744.14 |  | 33.638 |  | tausif | chetan.jawalikar | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | PCC | Sq.Ft | 1040 | 6 | 6240 | 0 | 6240 | 2.5 | 1001 | 6006 | 0 | 6006 | 39 | 234 |  | 96.25 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | M.S Jali Binding | Kgs | 550 | 8 | 4400 | 0 | 4400 | 2.5 | 550 | 4400 | 0 | 4400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 107 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | Rubble Soling. -S.O | Sq.Ft | 732 | 6.5 | 4758 | 0 | 4758 | 0 | 732 | 4758 | 0 | 4758 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 107 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | JCB Charges | Hrs | 4 | 800 | 3200 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | tausif | tausif | construction open | 05 Apr 2021 |  | UTI. Drainage | Approved | tausif | 1900-01-01
GANGA ASMI | 107 | 2 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | Brickwork 6" -DLd | Sq.Ft | 231.08 | 12 | 2772.96 | 0 | 2772.96 | 0 | 231.08 | 2772.96 | 0 | 2772.96 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | 9" Brick Work | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Apr 2021 |  | 12 MASONARY WORK | Cancelled | ADITYA CHOUGULE | 03 Aug 2022
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | 9" Brick Work | Sq.Ft | 212 | 15 | 3180 | 0 | 3180 | 2.5 | 120.0132 | 1800.2 | 0 | 1800.2 | 91.9868 | 1379.8 |  | 56.61 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | M.S Jali Binding | Kgs | 0 | 8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Apr 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 03 Aug 2022
GANGA ASMI | 107 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | Grouting of Pits MWB | No. | 16 | 300 | 4800 | 0 | 4800 | 0 | 10 | 3000 | 0 | 3000 | 6 | 1800 |  | 62.5 |  | tausif | chetan.jawalikar | construction open | 05 Apr 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 107 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | JCB Charges | Hrs | 4 | 800 | 3200 | 0 | 3200 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 05 Apr 2021 |  | UTI. Drainage | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 107 | 3 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | PCC | Sq.Ft | 1040 | 4 | 4160 | 0 | 4160 | 2.5 | 1001 | 4004 | 0 | 4004 | 39 | 156 |  | 96.25 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2021 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 107 | 2 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | Sand Face Plaster DLd | Sq.Ft | 238.56 | 12 | 2862.72 | 0 | 2862.72 | 0 | 0 | 0 | 0 | 0 | 238.56 | 0 |  | 0 |  | tausif | tausif | construction open | 05 Apr 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 107 | 1 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | PCC - SO | Sq.Ft | 868 | 4 | 3472 | 0 | 3472 | 0 | 0 | 0 | 0 | 0 | 868 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 05 Apr 2021 |  | S OH Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 107 | 0 | 27 Mar 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Work | Grouting of Pits MWB | No. | 15 | 300 | 4500 | 0 | 4500 | 0 | 15 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 108 | 0 | 30 Mar 2021 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | PRINTING PRINTING-NO.-(NA) | print | No. | 10000 | 0.9 | 9000 | 1080 | 10080 | 0 | 10000 | 9000 | 1080 | 10080 | 0 | 0 | GANGA ASMI ENQUIRY FORM PRINT QTY. 10000 SIZE AS A - 5 BOTH SIDE COLOUR PRINT | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 03 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 109 | 0 | 30 Mar 2021 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 45000 | 270000 | 48600 | 318600 | 0 | 3 | 135000.54 | 24300.1 | 159300.64 | 3 | 159299.36 | GANGA ASMI WAKAD PROJECT DISPLAY ADVERTISING @ WAKAD - HINJEWADI ROAD, NEAR BAJAJ SHOWROOM, WAKAD CHOWK, WAKAD. FACING AUNDH SIZE AS 30 X 42 Sq Ft as on 01/04/2021 to 30/06/2021 Rs 45000/- + Tax. | 50 |  | Tejas Raverkar | sunita shirolkar | construction open | 03 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 109 | 1 | 30 Mar 2021 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding display charges | No. | 6 | 5000 | 30000 | 5400 | 35400 | 0 | 3.0012 | 15006 | 2701.08 | 17707.08 | 2.9988 | 17692.92 | GANGA ASMI WAKAD PROJECT DISPLAY ADVERTISING @ WAKAD - HINJEWADI ROAD, NEAR BAJAJ SHOWROOM, WAKAD CHOWK, WAKAD. FACING AUNDH SIZE AS 30 X 42 Sq Ft as on 01/04/2021 to 30/06/2021 ADDITIONAL COST AGST. BACK SIDE HOARDING Rs 5000/- + Tax.. (PAYMENT AFTER 1 MONTH AFTER COMPLETED DURATION/ PERIOD ) | 50.02 |  | Tejas Raverkar | sunita shirolkar | construction open | 03 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 110 | 0 | 06 Apr 2021 | RED TREE DESIGN STUDIO PRIVATE LIMITED | ONLINE / DIGITAL Social / Digital Activity | Image Purchase-Mkt | No. | 1 | 32000 | 32000 | 5760 | 37760 | 0 | 1 | 32000 | 5760 | 37760 | 0 | 0 | IMAGE PURCHASE GANGA ASMI WAKAD - FOR SALES PROMOTION WITH BRANDING. 100% ADVANCE PAYMENT WITH TAX | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 06 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 111 | 0 | 09 Apr 2021 | MOHAN SHANKAR RATHOD | Rabbit Shifting by Tractor Inside The Premises | Rabbit Shifting - BRE | Trips | 7 | 700 | 4900 | 0 | 4900 | 0 | 7 | 4900 | 0 | 4900 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | B.C. Rework/Extrawork | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 112 | 0 | 09 Apr 2021 | SURESH KUMAR MURALIDHAR | Site Infra Road Nala Side Cleaning Work | Department Labour- BC | No. | 1 | 6500 | 6500 | 0 | 6500 | 0 | 1 | 6500 | 0 | 6500 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | B.C. RCC Substructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 113 | 1 | 10 Apr 2021 | VISION INFRA | 8.5m Road Work | Trimix Work | Sq.Ft | 293 | 10 | 2930 | 527.4 | 3457.4 | 0 | 293 | 2930 | 527.4 | 3457.4 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | UTI. Drainage | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 113 | 1 | 10 Apr 2021 | VISION INFRA | 8.5m Road Work | Groove Cutting & Bituminous filling | Mtrs | 517.33 | 40 | 20693.2 | 3724.78 | 24417.98 | 0 | 0 | 0 | 0 | 0 | 517.33 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 113 | 0 | 10 Apr 2021 | VISION INFRA | 8.5m Road Work | Dressing, Levelling & Cleaning | Sq.Ft | 13209 | 3.5 | 46231.5 | 8321.68 | 54553.18 | 0 | 13209 | 46231.5 | 8321.68 | 54553.18 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 113 | 0 | 10 Apr 2021 | VISION INFRA | 8.5m Road Work | Trimix Work | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | UTI. Drainage | Cancelled | tausif | 10 Apr 2021
GANGA ASMI | 113 | 0 | 10 Apr 2021 | VISION INFRA | 8.5m Road Work | Trimix Work | Sq.Ft | 13209 | 10 | 132090 | 23776.2 | 155866.2 | 0 | 13209 | 132090 | 23776.2 | 155866.2 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | UTI. Drainage | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 114 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Fabrication work (L) | Kgs | 555.12 | 18 | 9992.16 | 1798.58 | 11790.74 | 2.5 | 258.5838 | 4654.51 | 837.82 | 5492.33 | 296.5362 | 6298.41 |  | 46.5816 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 114 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Fabrication work (L) | Kgs | 14383.92 | 18 | 258910.56 | 46603.9 | 305514.46 | 2.5 | 8254.5146 | 148581.26 | 26744.62 | 175325.88 | 6129.4054 | 130188.58 |  | 57.3871 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 114 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Deck Sheet (L)- BCo | Sq.Ft | 2080 | 7 | 14560 | 2620.8 | 17180.8 | 2.5 | 997.7552 | 6984.29 | 1257.18 | 8241.47 | 1082.2448 | 8939.33 |  | 47.969 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 114 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | tausif | 10 Apr 2021
GANGA ASMI | 114 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | M.S. Door fixing-Dld. | No. | 32 | 800 | 25600 | 4608 | 30208 | 2.5 | 16 | 12800 | 2304 | 15104 | 16 | 15104 |  | 50 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 114 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | GI Sheet Fixing (L) | Sq.Ft | 10890 | 5 | 54450 | 9801 | 64251 | 2.5 | 5451.6211 | 27258.11 | 4906.46 | 32164.57 | 5438.3789 | 32086.43 |  | 50.0608 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | UTI. Vermiculture | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 114 | 1 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | G.I. Sheet (M+L) - BC | Sq.Ft | 160 | 30 | 4800 | 864 | 5664 | 2.5 | 160 | 4800 | 864 | 5664 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 115 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Jali fixing | Sq.Ft | 336 | 20 | 6720 | 1209.6 | 7929.6 | 0 | 79.8 | 1596 | 287.28 | 1883.28 | 256.2 | 6046.32 |  | 23.75 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | S OH Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 115 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Fabrication work (M) | Kgs | 99.68 | 54 | 5382.72 | 968.88 | 6351.6 | 0 | 63.0008 | 3402.04 | 612.36 | 4014.4 | 36.6792 | 2337.2 |  | 63.203 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | Admin. Direct Expenses | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 115 | 1 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Fabrication work (M) | Kgs | 42.81 | 64 | 2739.84 | 493.18 | 3233.02 | 0 | 0 | 0 | 0 | 0 | 42.81 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 16 Apr 2021 |  | Admin. Direct Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 115 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Self Tapping Screw - SOSB | No. | 3300 | 2.5 | 8250 | 1485 | 9735 | 0 | 1539.021 | 3847.55 | 692.56 | 4540.11 | 1760.979 | 5194.89 |  | 46.637 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | S OH Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 115 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Fabrication work (M) | Kgs | 15487.025 | 54 | 836299.35 | 150533.88 | 986833.23 | 0 | 8768.2504 | 473485.52 | 85227.4 | 558712.92 | 6718.7746 | 428120.31 |  | 56.6168 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | Admin. Direct Expenses | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 115 | 0 | 10 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Labour Camp MS Fabrication (2 Floors) | Fabrication work (M) | Kgs | 138.42 | 64 | 8858.88 | 1594.6 | 10453.48 | 0 | 138.42 | 8858.88 | 1594.6 | 10453.48 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | Admin. Direct Expenses | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 116 | 0 | 12 Apr 2021 | YOGESH BALU ICHAKE | Land Cost Joint Lvl For Poyta Soil Top Wing-2 | Total Station Point marking- | Day | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 16 Apr 2021 |  | B.C. RCC Substructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 117 | 1 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Hinges- SO | No. | 4 | 30 | 120 | 21.6 | 141.6 | 2.5 | 4 | 120 | 21.6 | 141.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 117 | 1 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | MS Aldrop (M) | No. | 1 | 150 | 150 | 27 | 177 | 0 | 1 | 150 | 27 | 177 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 117 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Hinges- SO | No. | 3 | 30 | 90 | 16.2 | 106.2 | 0 | 3 | 90 | 16.2 | 106.2 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 117 | 1 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Aldrop- SO | No. | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 22 Apr 2022
GANGA ASMI | 117 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (M) | Kgs | 55.2 | 64 | 3532.8 | 635.9 | 4168.7 | 0 | 55.2 | 3532.8 | 635.9 | 4168.7 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 117 | 1 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Aldrop- SO | No. | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 22 Apr 2022
GANGA ASMI | 117 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (M) | Kgs | 430.6 | 64 | 27558.4 | 4960.52 | 32518.92 | 0 | 430.6 | 27558.4 | 4960.52 | 32518.92 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 117 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Aldrop- SO | No. | 2 | 180 | 360 | 64.8 | 424.8 | 0 | 2 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 117 | 1 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Sliding Door Bearing | No. | 4 | 80 | 320 | 57.6 | 377.6 | 2.5 | 4 | 320 | 57.6 | 377.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 117 | 1 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (L) | Kgs | 76.453 | 18 | 1376.15 | 247.7 | 1623.85 | 2.5 | 76.453 | 1376.15 | 247.7 | 1623.85 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 117 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Tower Bolt SOSB | No. | 2 | 80 | 160 | 28.8 | 188.8 | 0 | 2 | 160 | 28.8 | 188.8 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 117 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (M) | Kgs | 705.6 | 54 | 38102.4 | 6858.44 | 44960.84 | 0 | 612.525 | 33076.35 | 5953.74 | 39030.09 | 93.075 | 5930.75 |  | 86.8091 |  | tausif | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 117 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (M) | Kgs | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jawalikar |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | tausif | 12 Apr 2021
GANGA ASMI | 117 | 1 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | MS Aldrop (L) | No. | 2 | 30 | 60 | 10.8 | 70.8 | 2.5 | 2 | 60 | 10.8 | 70.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 117 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Sliding Door Bearing | No. | 4 | 80 | 320 | 57.6 | 377.6 | 0 | 2 | 160 | 28.8 | 188.8 | 2 | 188.8 |  | 50 |  | tausif | tausif | construction open | 1900-01-01 |  | 09 CARPENTRY WORK | Approved | tausif | 1900-01-01
GANGA ASMI | 118 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | GI Sheet Fixing (L) | Sq.Ft | 1900 | 5 | 9500 | 1710 | 11210 | 2.5 | 1445.0203 | 7225.1 | 1300.52 | 8525.62 | 454.9797 | 2684.38 |  | 76.0537 |  | chetan.jawalikar | tausif | construction open | 1900-01-01 |  | UTI. Vermiculture | Approved | tausif | 1900-01-01
GANGA ASMI | 118 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jawalikar |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | tausif | 12 Apr 2021
GANGA ASMI | 118 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Aldrop- SO | No. | 2 | 60 | 120 | 21.6 | 141.6 | 2.5 | 2 | 120 | 21.6 | 141.6 | 0 | 0 |  | 100 |  | chetan.jawalikar | tausif | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 118 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (L) | Kgs | 1191.4 | 18 | 21445.2 | 3860.14 | 25305.34 | 2.5 | 1191.4 | 21445.2 | 3860.14 | 25305.34 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | tausif | 1900-01-01
GANGA ASMI | 118 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jawalikar |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | tausif | 12 Apr 2021
GANGA ASMI | 118 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jawalikar |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | tausif | 12 Apr 2021
GANGA ASMI | 118 | 0 | 12 Apr 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication&Gate for Seperation Sale Area | Sliding Door (L) | No. | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jawalikar |  | construction open | 1900-01-01 |  | 09 CARPENTRY WORK | Cancelled | tausif | 12 Apr 2021
GANGA ASMI | 119 | 0 | 12 Apr 2021 | DREAMTREE EXPERIENCE | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 900 | 9 | 8100 | 1458 | 9558 | 0 | 900 | 8100 | 1458 | 9558 | 0 | 0 | HOARDING FLEX PRINT WITH MOUNT FOR GANGA ASMI WAKAD HOARDING SIZE AS 30 X 30 SQ FT. OPP. SITE | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 120 | 0 | 13 Apr 2021 | REFLECTION PRINTING SOLUTIONS | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 9220 | 9 | 82980 | 14936.4 | 97916.4 | 0 | 9220 | 82980 | 14936.4 | 97916.4 | 0 | 0 | HOARDING FLEX PRINT WITH MOUNT FOR GANGA ASMI WAKAD PROJECT "ACT TODAY, OWNTMRW" | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 07 May 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 121 | 2 | 17 Apr 2021 | SPACE TECK | 3D Walkthrough consultancy | 3D Walkthrough-Mkt | No. | 1 | 875000 | 875000 | 157500 | 1032500 | 0 | 1 | 875000 | 157500 | 1032500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 13 May 2021 |  | MKT. Media | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 121 | 1 | 17 Apr 2021 | SPACE TECK | Virtual Walkthrough Consultancy | Virtual Walkthrough | No. | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0.9 | 450000 | 81000 | 531000 | 0.1 | 59000 | Pricing for 8 3D rendered Images (Print media 4K) & Price for a Walkthrough of Maximum 4.30 Minutes be (1920-1080 Full HD) | 90 |  | tausif | tausif | consultancy | 13 May 2021 |  | Consultacy Architectural | Approved | tausif | 1900-01-01
GANGA ASMI | 121 | 0 | 17 Apr 2021 | SPACE TECK | Virtual Walkthrough Consultancy | Virtual Walkthrough | No. | 0 | 541000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1) Pricing for 8 3D rendered Images (Print Media 4K) woulde be 126000 plus Taxes 2) Price for a Walkthrough of Maximum 4.30 Minutes would be (1920-1080 Full HD) - 415000 Plus Taxes | 0 |  | tausif | CHETAN.JAWALIKAR | consultancy | 13 May 2021 |  | Consultacy Architectural | Cancelled | skmishra | 29 Jun 2021
GANGA ASMI | 122 | 1 | 17 Apr 2021 | REVANTI FURNITURE | CP Lounge -Door Frame In Ply Lamination | Lumpsum work- DCW | No. | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 Apr 2021 |  | DEV. Compound Wall | Approved | tausif | 1900-01-01
GANGA ASMI | 122 | 2 | 17 Apr 2021 | REVANTI FURNITURE | Sales Office- Selfi Point Ply Fixing ,Display Board Carpent | Lumpsum work- DCW | No. | 1 | 2000 | 2000 | 0 | 2000 | 0 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 Apr 2021 |  | DEV. Compound Wall | Approved | tausif | 1900-01-01
GANGA ASMI | 122 | 0 | 17 Apr 2021 | REVANTI FURNITURE | Sales Office- Selfi Point Ply Fixing ,Display Board Carpent | Lumpsum work- DCW | No. | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 22 Apr 2021 |  | DEV. Compound Wall | Cancelled | tausif | 26 Jun 2021
GANGA ASMI | 122 | 3 | 17 Apr 2021 | REVANTI FURNITURE | CP Lounge Display Unit Material-(No.) | Carpentry Work (L) | No. | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Runal Kindalkar | skmishra | construction open | 22 Apr 2021 |  | Admin. Indirect Expenses | Approved | skmishra | 1900-01-01
GANGA ASMI | 122 | 2 | 17 Apr 2021 | REVANTI FURNITURE | Sales Office- Selfi Point Ply Fixing ,Display Board Carpent | Lumpsum work- DCW | No. | 4 | 3000 | 12000 | 0 | 12000 | 0 | 4 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 Apr 2021 |  | DEV. Compound Wall | Approved | tausif | 1900-01-01
GANGA ASMI | 122 | 0 | 17 Apr 2021 | REVANTI FURNITURE | Sales Office- Selfi Point Ply Fixing ,Display Board Carpent | Lumpsum work- DCW | No. | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 22 Apr 2021 |  | DEV. Compound Wall | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 122 | 0 | 17 Apr 2021 | REVANTI FURNITURE | Sales Office- Selfi Point Ply Fixing ,Display Board Carpent | Lumpsum work- DCW | No. | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 22 Apr 2021 |  | DEV. Compound Wall | Cancelled | tausif | 26 Jun 2021
GANGA ASMI | 122 | 2 | 17 Apr 2021 | REVANTI FURNITURE | Sales Office- Selfi Point Ply Fixing ,Display Board Carpent | Lumpsum work- DCW | No. | 2 | 3000 | 6000 | 0 | 6000 | 0 | 2 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 Apr 2021 |  | DEV. Compound Wall | Approved | tausif | 1900-01-01
GANGA ASMI | 123 | 0 | 20 Apr 2021 | ANIL MAHTO ENTERPRISES | CP Lounge Ceiling Paint-Premium Emulsion Paint-(Sq.Ft) | Premium Emulsion(m+l) - Mkt | Sq.Ft | 525 | 12 | 6300 | 1134 | 7434 | 2.5 | 0 | 0 | 0 | 0 | 525 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 22 Apr 2021 |  | MKT. Marketing Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 124 | 0 | 26 Apr 2021 | ANTS DESIGN | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS AS ON 01.05.2021 | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 1900-01-01 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 124 | 5 | 26 Apr 2021 | ANTS DESIGN | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 6TH MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 124 | 2 | 26 Apr 2021 | ANTS DESIGN | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 3RD MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 124 | 4 | 26 Apr 2021 | ANTS DESIGN | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 5TH MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 124 | 3 | 26 Apr 2021 | ANTS DESIGN | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 4TH MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 124 | 1 | 26 Apr 2021 | ANTS DESIGN | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 5 | 100000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 2ND MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 125 | 0 | 26 Apr 2021 | ANTS DESIGN | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 1ST MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 126 | 5 | 26 Apr 2021 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 6TH MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 26 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 126 | 1 | 26 Apr 2021 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 2ND MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 26 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 126 | 4 | 26 Apr 2021 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 5TH MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 26 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 126 | 0 | 26 Apr 2021 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 1ST MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 26 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 126 | 2 | 26 Apr 2021 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 3RD MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 26 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 126 | 3 | 26 Apr 2021 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ONLINE DIGITAL CAMPAIN FOR SALES PROMOTION WITH PROJECT BRANDING GOOGLE ADS 4TH MONTH ESTIMATED COST RS. 100000/- + TAX. (50% ADVANCE AT THE TIME OF START A CAMPAIGN THEN 50% AFTER) | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 26 Apr 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 127 | 0 | 08 May 2021 | SPACE TECK | Virtual Walkthrough Consultancy | Virtual Walkthrough | No. | 0 | 541000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 11 May 2021 |  | Consultacy Architectural | Cancelled | skmishra | 29 Jun 2021
GANGA ASMI | 128 | 0 | 13 May 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Door Frame Changes(Size Rework) | Fabrication work lumpsum -SOSB | No. | 1 | 2230 | 2230 | 401.4 | 2631.4 | 0 | 1 | 2230 | 401.4 | 2631.4 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 May 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 128 | 1 | 13 May 2021 | OM SAI ALLUMINIUM & FABRICATION | Media Flex Media Frames | Fabrication work lumpsum -SOSB | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 1 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 May 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 128 | 0 | 13 May 2021 | OM SAI ALLUMINIUM & FABRICATION | CP Lounge Door Frame Changes(Size Rework) | Contractor Profit-Mkt | No. | 1 | 334 | 334 | 60.12 | 394.12 | 0 | 1 | 334 | 60.12 | 394.12 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 May 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 129 | 0 | 13 May 2021 | BHAGYSHREE PRAKASH WADEKAR | CP Lounge Work | Acid Wash - Mkt | Sq.Ft | 525 | 4 | 2100 | 0 | 2100 | 0 | 0 | 0 | 0 | 0 | 525 | 0 |  | 0 |  | tausif | tausif | construction open | 22 May 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 129 | 3 | 13 May 2021 | BHAGYSHREE PRAKASH WADEKAR | Sales Office & Sample flat Acid Wash | Tile Grouting Work (L) | Sq.Ft | 5800 | 1.5 | 8700 | 0 | 8700 | 0 | 0 | 0 | 0 | 0 | 5800 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 22 May 2021 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 129 | 2 | 13 May 2021 | BHAGYSHREE PRAKASH WADEKAR | Sales Office & Sample flat Acid Wash | Acid Wash | Sq.Ft | 5800 | 3 | 17400 | 0 | 17400 | 0 | 5800 | 17400 | 0 | 17400 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 May 2021 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 129 | 1 | 13 May 2021 | BHAGYSHREE PRAKASH WADEKAR | Sample Flats (2 & 3 Bhk) Deep Cleaning | Deep Cleaning work | Sq.Ft | 2500 | 4 | 10000 | 0 | 10000 | 0 | 2155.875 | 8623.5 | 0 | 8623.5 | 344.125 | 1376.5 |  | 86.235 |  | Dushant Gore | Swapnil Erande | construction open | 22 May 2021 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 130 | 0 | 13 May 2021 | YOGESH BALU ICHAKE | Joint Lvl of Poyta Soil Wing-1,2,3 & Podium | Total Station Point marking- | Day | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 20 May 2021 |  | B.C. RCC Substructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 130 | 1 | 13 May 2021 | YOGESH BALU ICHAKE | Soft Rock Top&Hard Rock Top Lvl at Wing-1(Bldg+Podium) | Total Station Point marking- | Day | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 20 May 2021 |  | B.C. RCC Substructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Wing-1(Podium To 28th Fl) Liasoning Architect Consultancy - | Liasoning Consultancy (Architectural) | Sq.Ft | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Cancelled | skmishra | 22 Oct 2021
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | A Building Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 46897.46 | 4 | 187589.84 | 33766.18 | 221356.02 | 0 | 21103.615 | 84414.46 | 15194.6 | 99609.06 | 25793.845 | 121746.96 |  | 44.9995 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Wing-3 (Podium To 28th Fl) Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 306739.01 | 4 | 1226956.04 | 220852.08 | 1447808.12 | 0 | 68249.1277 | 272996.51 | 49139.38 | 322135.89 | 238489.8823 | 1125672.23 |  | 22.2499 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Wing-1(Podium To 28th Fl) Liasoning Architect Consultancy - | Liasoning Consultancy (Architectural) | Sq.Ft | 304898.26 | 4 | 1219593.04 | 219526.74 | 1439119.78 | 0 | 137203.815 | 548815.26 | 98786.76 | 647602.02 | 167694.445 | 791517.76 |  | 44.9999 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Wing-2 (Podium To 28th Fl) Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Cancelled | skmishra | 22 Oct 2021
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Parking - Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Cancelled | skmishra | 22 Oct 2021
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Parking - Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 329612.73 | 4 | 1318450.92 | 237321.16 | 1555772.08 | 0 | 16480.6365 | 65922.55 | 11866.06 | 77788.61 | 313132.0935 | 1477983.47 |  | 5 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Security Cabin- Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 96.88 | 4 | 387.52 | 69.76 | 457.28 | 0 | 0 | 0 | 0 | 0 | 96.88 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | OH Tank Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 1722.24 | 4 | 6888.96 | 1240.02 | 8128.98 | 0 | 0 | 0 | 0 | 0 | 1722.24 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | STP Area Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 1799.09 | 4 | 7196.36 | 1295.34 | 8491.7 | 0 | 0 | 0 | 0 | 0 | 1799.09 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | MHADA Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 59577.34 | 4 | 238309.36 | 42895.68 | 281205.04 | 0 | 20851.851 | 83407.4 | 15013.34 | 98420.74 | 38725.489 | 182784.3 |  | 34.9996 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Wing-3 (Podium To 28th Fl) Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Cancelled | skmishra | 22 Oct 2021
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Transformer Room-Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 2801.43 | 4 | 11205.72 | 2017.02 | 13222.74 | 0 | 0 | 0 | 0 | 0 | 2801.43 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Wing-2 (Podium To 28th Fl) Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 315425.25 | 4 | 1261701 | 227106.18 | 1488807.18 | 0 | 63085 | 252340 | 45421.2 | 297761.2 | 252340.25 | 1191045.98 |  | 20 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | UG Water Tank Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 2785.15 | 4 | 11140.6 | 2005.3 | 13145.9 | 0 | 0 | 0 | 0 | 0 | 2785.15 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 132 | 0 | 31 May 2021 | KIMAYA ASSOCIATES | Architect Projection Liasoning Architect Consultancy | Liasoning Consultancy (Architectural) | Sq.Ft | 110300.32 | 4 | 441201.28 | 79416.24 | 520617.52 | 0 | 22060 | 88240 | 15883.2 | 104123.2 | 88240.32 | 416494.32 |  | 19.9999 |  | Avinash Padmanabha | chetan.jewalikar | consultancy | 22 Oct 2021 |  | Consultacy Architectural | Approved | Dushant Gore | 06 Oct 2022
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 93 | 41999.73 | 7559.96 | 49559.69 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 466.66 | 41999.4 | 7559.9 | 49559.3 | 0 | 69.003 | 32200.94 | 5796.16 | 37997.1 | 20.997 | 11562.2 |  | 76.67 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 84 | 500 | 42000 | 7560 | 49560 | 0 | 82.0008 | 41000.4 | 7380.08 | 48380.48 | 1.9992 | 1179.52 |  | 97.62 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 466.66 | 41999.4 | 7559.9 | 49559.3 | 0 | 90 | 41999.4 | 7559.9 | 49559.3 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 88.0003 | 39741.82 | 7153.52 | 46895.34 | 4.9997 | 2664.35 |  | 94.624 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 466.66 | 41999.4 | 7559.9 | 49559.3 | 0 | 87 | 40599.42 | 7307.9 | 47907.32 | 3 | 1651.98 |  | 96.6667 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 90 | 40644.9 | 7316.08 | 47960.98 | 3 | 1598.71 |  | 96.7742 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 466.66 | 41999.4 | 7559.9 | 49559.3 | 0 | 90 | 41999.4 | 7559.9 | 49559.3 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 466.66 | 41999.4 | 7559.9 | 49559.3 | 0 | 90 | 41999.4 | 7559.9 | 49559.3 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 93 | 41999.73 | 7559.96 | 49559.69 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 82 | 37032.02 | 6665.76 | 43697.78 | 11 | 5861.91 |  | 88.172 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 93 | 41999.73 | 7559.96 | 49559.69 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 466.66 | 41999.4 | 7559.9 | 49559.3 | 0 | 81.0009 | 37799.88 | 6803.98 | 44603.86 | 8.9991 | 4955.44 |  | 90.001 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 466.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Cancelled | tausif | 01 Jun 2021
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 93 | 41999.73 | 7559.96 | 49559.69 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 92.0002 | 41548.21 | 7478.68 | 49026.89 | 0.9998 | 532.8 |  | 98.9249 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 92.0002 | 41548.21 | 7478.68 | 49026.89 | 0.9998 | 532.8 |  | 98.9249 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 466.66 | 41999.4 | 7559.9 | 49559.3 | 0 | 90 | 41999.4 | 7559.9 | 49559.3 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 133 | 1 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 70.0002 | 31612.79 | 5690.3 | 37303.09 | 22.9998 | 12256.6 |  | 75.269 |  | Dushant Gore | chetan.jewalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 466.66 | 41999.4 | 7559.9 | 49559.3 | 0 | 90 | 41999.4 | 7559.9 | 49559.3 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 93 | 41999.73 | 7559.96 | 49559.69 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 133 | 0 | 01 Jun 2021 | SARATHI SYSTECH PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 451.61 | 41999.73 | 7559.96 | 49559.69 | 0 | 92 | 41548.12 | 7478.66 | 49026.78 | 1 | 532.91 |  | 98.9247 |  | tausif | chetan.jawalikar | construction open | 01 Jun 2021 |  | 18. Maintenance & Repair Work | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 134 | 0 | 05 Jun 2021 | PAPPU BAGELA | CP Lounge Door Sill & Sales Urinal Partition | Departmental Labour | No. | 1 | 1300 | 1300 | 234 | 1534 | 0 | 1 | 1300 | 234 | 1534 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 09 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 135 | 0 | 05 Jun 2021 | VISION INFRA | Site Infra Misc Work | Lumpsum work- DCW | No. | 1 | 8800 | 8800 | 1584 | 10384 | 0 | 1 | 8800 | 1584 | 10384 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 09 Jun 2021 |  | DEV. Compound Wall | Approved | tausif | 1900-01-01
GANGA ASMI | 136 | 0 | 05 Jun 2021 | VISION INFRA | 8.5m Road Work | Lumpsum work- DCW | No. | 0 | 20100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 10 Jun 2021 |  | DEV. Compound Wall | Cancelled | tausif | 10 Jun 2021
GANGA ASMI | 136 | 0 | 05 Jun 2021 | VISION INFRA | 8.5m Road Work | Traveling Expanses - LC | No. | 8 | 500 | 4000 | 720 | 4720 | 0 | 8 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Jun 2021 |  | Land Cost | Approved | tausif | 1900-01-01
GANGA ASMI | 136 | 0 | 05 Jun 2021 | VISION INFRA | 8.5m Road Work | Department Labour - Day | Day | 25.5 | 500 | 12750 | 2295 | 15045 | 0 | 25.5 | 12750 | 2295 | 15045 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 10 Jun 2021 |  | SOC. M. Civil Work Maintenace | Approved | tausif | 1900-01-01
GANGA ASMI | 137 | 0 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | Electrical Work HT/LT Line Underground | JCB Charges. | Day | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 09 Jun 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | tausif | 09 Jun 2021
GANGA ASMI | 137 | 3 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | UGWT Land Slide Murum Shifting | Murum Shifting work | Cu.Mtrs | 155.53 | 60 | 9331.8 | 1679.72 | 11011.52 | 0 | 155.53 | 9331.8 | 1679.72 | 11011.52 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Jun 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 137 | 1 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | UGWT Excavation work | Spreading & Levelling Work | Cu.Mtrs | 5035.97 | 15 | 75539.55 | 13597.12 | 89136.67 | 0 | 4228.84 | 63432.6 | 11417.86 | 74850.46 | 807.13 | 14286.21 |  | 83.9727 |  | DUSHANT GORE | Swapnil Erande | construction open | 09 Jun 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 137 | 2 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | UGWT Excavation work | Excavation in Hard Rock | Cu.Mtrs | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 09 Jun 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 137 | 0 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | Electrical Work HT/LT Line Underground | JCB Charges. | Day | 1 | 6400 | 6400 | 1152 | 7552 | 0 | 1 | 6400 | 1152 | 7552 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 09 Jun 2021 |  | 01 EARTHWORK & ROADWORK | Approved | tausif | 1900-01-01
GANGA ASMI | 137 | 2 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | UGWT Excavation work | Excavation in Hard Rock | Cu.Mtrs | 194.62 | 150 | 29193 | 5254.74 | 34447.74 | 0 | 194.62 | 29193 | 5254.74 | 34447.74 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 09 Jun 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 137 | 1 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | UGWT Excavation work | Excavation by Bucket | Cu.Mtrs | 5035.97 | 60 | 302158.2 | 54388.48 | 356546.68 | 0 | 4228.844 | 253730.64 | 45671.52 | 299402.16 | 807.126 | 57144.52 |  | 83.9728 |  | DUSHANT GORE | Swapnil Erande | construction open | 09 Jun 2021 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 137 | 2 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | UGWT Excavation work | Spreading & Levelling Work | Cu.Mtrs | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 09 Jun 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 137 | 4 | 07 Jun 2021 | DRAUPADA EARTHMOVERS | UGWT Excavation work | Excavation in Hard Rock | Cu.Mtrs | 340.171 | 150 | 51025.65 | 9184.62 | 60210.27 | 0 | 340.171 | 51025.65 | 9184.62 | 60210.27 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Jun 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 138 | 0 | 07 Jun 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Toilet Civil Work | PCC | Sq.Ft | 447.31 | 4 | 1789.24 | 0 | 1789.24 | 0 | 414.5 | 1658 | 0 | 1658 | 32.81 | 131.24 |  | 92.665 |  | tausif | tausif | construction open | 09 Jun 2021 |  | B.C. Building Common Items | Approved | tausif | 1900-01-01
GANGA ASMI | 138 | 0 | 07 Jun 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Toilet Civil Work | Brickwork 9" - SO | Sq.Ft | 572.75 | 15 | 8591.25 | 0 | 8591.25 | 0 | 134.16 | 2012.4 | 0 | 2012.4 | 438.59 | 6578.85 |  | 23.4238 |  | tausif | tausif | construction open | 09 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 138 | 0 | 07 Jun 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Toilet Civil Work | Back Filling- Dld | Cu.Ft | 498.88 | 3.5 | 1746.08 | 0 | 1746.08 | 0 | 465.75 | 1630.13 | 0 | 1630.13 | 33.13 | 115.96 |  | 93.3591 |  | tausif | tausif | construction open | 09 Jun 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 138 | 0 | 07 Jun 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Toilet Civil Work | Rubble Soling. -S.O | Sq.Ft | 301.69 | 6 | 1810.14 | 0 | 1810.14 | 0 | 301.69 | 1810.14 | 0 | 1810.14 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 09 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 138 | 0 | 07 Jun 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Toilet Civil Work | Sand Face Plaster DLd | Sq.Ft | 261.13 | 12 | 3133.56 | 0 | 3133.56 | 0 | 0 | 0 | 0 | 0 | 261.13 | 0 |  | 0 |  | tausif | tausif | construction open | 09 Jun 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | HT Feeder Piller Removing | No. | 0 | 2000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 18 Jun 2021 |  | UTI. Electricity Infrastructur | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | Electrical work lumpsum-SO | No. | 1 | 25000 | 25000 | 0 | 25000 | 0 | 0.7912 | 19780 | 0 | 19780 | 0.2088 | 5220 |  | 79.12 |  | tausif | tausif | construction open | 18 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | Electrical work lumpsum-SO | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 18 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | 4 way Feeder Pillar fixing-UTI | No. | 0 | 4000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 18 Jun 2021 |  | UTI. Electricity Infrastructur | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | Earthing Pit (L+M) UDG | No. | 0 | 6000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 18 Jun 2021 |  | UTI. D.G.Set | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | 150 Sqmm LT Cable Termination | No. | 0 | 800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 18 Jun 2021 |  | 04 ELECTRICAL WORK | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | 240 Sqmm,3.5 LT Core | No. | 0 | 5000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 18 Jun 2021 |  | 04 ELECTRICAL WORK | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | 240 Sqmm LT Cable Termination | No. | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 18 Jun 2021 |  | 04 ELECTRICAL WORK | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 139 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Electrical Work Feeder Pilllar Shifting towards Road | HT Feeder Piller Removing | No. | 0 | 2000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 18 Jun 2021 |  | UTI. Electricity Infrastructur | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 140 | 1 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Weigh Bridge Earthing Work | Earthing work(m+l)- BC | No. | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | -180 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 140 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Labour Camp Electrical Work | Earthing work(m+l)- BC | No. | 1 | 4000 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 140 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Labour Camp Electrical Work | Light Point - UTI | No. | 24 | 200 | 4800 | 0 | 4800 | 2.5 | 22 | 4400 | 0 | 4400 | 2 | 400 |  | 91.6667 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 140 | 1 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Weigh Bridge Earthing Work | Earthing work(m+l)- BC | No. | 2 | 5000 | 10000 | 0 | 10000 | 2.5 | 2 | 10000 | 1800 | 11800 | 0 | -1800 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 140 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Labour Camp Electrical Work | Earthing Pit (L+M) UDG | No. | 0 | 4000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 1900-01-01 |  | UTI. D.G.Set | Cancelled | tausif | 18 Jun 2021
GANGA ASMI | 140 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Labour Camp Electrical Work | MCB 4 Pole Fixing | No. | 1 | 200 | 200 | 0 | 200 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 140 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Labour Camp Electrical Work | MCB 2 Pole Fixing | No. | 2 | 150 | 300 | 0 | 300 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 140 | 1 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Weigh Bridge Earthing Work | 8 Gauge GI Wire | Mtrs | 100 | 9 | 900 | 0 | 900 | 2.5 | 100 | 900 | 162 | 1062 | 0 | -162 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 140 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Labour Camp Electrical Work | 6 AMP Plug Point - Mkt | No. | 16 | 200 | 3200 | 0 | 3200 | 2.5 | 16 | 3200 | 0 | 3200 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 140 | 0 | 07 Jun 2021 | LAXMI ELECTRICALS ENTERPRISES | Labour Camp Electrical Work | Lumpsum work- DCW | No. | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 1900-01-01 |  | DEV. Compound Wall | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 141 | 0 | 09 Jun 2021 | DREAMTREE EXPERIENCE | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 4320 | 9 | 38880 | 6998.4 | 45878.4 | 0 | 0 | 0 | 0 | 0 | 4320 | 0 | GANGA ASMI HOARDING FLEX PRINT WITH MOUNT SIZE AS 30X30 QTY. 2 AND SIZE AS 30X42 QTY. 2 | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 142 | 0 | 12 Jun 2021 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding display charges | No. | 6 | 38000 | 228000 | 41040 | 269040 | 0 | 3.0012 | 114045.6 | 20528.2 | 134573.8 | 2.9988 | 134466.2 | GANGA ASMI WAKAD PROJECT HOARDING DISPLAY CHARGES @ WAKAD - MUMBAI HIGHWAY OPP. GARVE BAJAJ SHOWROOM, NEAR WAKAD CHOWK, FACING HINJEWADI IT PARK SIZE AS 30 X 30 SQ FT. RS. 38000/- + TAX PER MONTH | 50.02 |  | Tejas Raverkar | sunita shirolkar | construction open | 06 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 143 | 0 | 15 Jun 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Barrication Cross Support&Sliding Gate Ramp Concrete Work | Concrete work- UGB | No. | 8 | 150 | 1200 | 0 | 1200 | 0 | 7 | 1050 | 0 | 1050 | 1 | 150 |  | 87.5 |  | tausif | tausif | construction open | 22 Jun 2021 |  | UTI. Gas Bank | Approved | tausif | 1900-01-01
GANGA ASMI | 143 | 0 | 15 Jun 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Barrication Cross Support&Sliding Gate Ramp Concrete Work | Concreting Work-Dld | Sq.Ft | 72 | 9 | 648 | 0 | 648 | 0 | 72 | 648 | 0 | 648 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 22 Jun 2021 |  | DEV. Landscape/Equipment | Approved | tausif | 1900-01-01
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Soil Analysis Test- SOS | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | NOise Test Day SOS | No. | 0 | 125 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Effluent Sample | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Soil Analysis Test- SOS | No. | 16 | 1500 | 24000 | 4320 | 28320 | 0 | 1 | 1500 | 270 | 1770 | 15 | 26550 |  | 6.25 |  | tausif | tausif | construction open | 24 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Manure from OWC | No. | 4 | 1500 | 6000 | 1080 | 7080 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | tausif | tausif | construction open | 24 Jun 2021 |  | 16 Testing, Analysis & Reports | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Manure from OWC | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | 16 Testing, Analysis & Reports | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Water Testing report - SOS | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Air Test SOS | No. | 20 | 1500 | 30000 | 5400 | 35400 | 0 | 3 | 4500 | 810 | 5310 | 17 | 30090 |  | 15 |  | tausif | tausif | construction open | 24 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Water Testing report - SOS | No. | 48 | 1000 | 48000 | 8640 | 56640 | 0 | 2 | 2000 | 360 | 2360 | 46 | 54280 |  | 4.1667 |  | tausif | tausif | construction open | 24 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Stack Monitoring Report SOS | No. | 20 | 900 | 18000 | 3240 | 21240 | 0 | 1 | 900 | 162 | 1062 | 19 | 20178 |  | 5 |  | tausif | tausif | construction open | 24 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Effluent Sample | No. | 8 | 1000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | tausif | tausif | construction open | 24 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Air Test SOS | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Effluent Sample | No. | 8 | 1000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | tausif | tausif | construction open | 24 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | NOise Test Day SOS | No. | 40 | 125 | 5000 | 900 | 5900 | 0 | 5 | 625 | 112.5 | 737.5 | 35 | 5162.5 |  | 12.5 |  | tausif | tausif | construction open | 24 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Effluent Sample | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Stack Monitoring Report SOS | No. | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Noise Test Night SOS | No. | 40 | 175 | 7000 | 1260 | 8260 | 0 | 5 | 875 | 157.5 | 1032.5 | 35 | 7227.5 |  | 12.5 |  | tausif | tausif | construction open | 24 Jun 2021 |  | S OH Infrastructure | Approved | tausif | 24 Jun 2021
GANGA ASMI | 144 | 0 | 18 Jun 2021 | INSTA POLLUTECH LABS | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Noise Test Night SOS | No. | 0 | 175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 24 Jun 2021 |  | S OH Infrastructure | Cancelled | tausif | 24 Jun 2021
GANGA ASMI | 145 | 0 | 21 Jun 2021 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Al. Arm. Cable laying 3C 300sqmm-UTI | Mtrs | 0 | 90 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 08 Apr 2022 |  | UTI. Electricity Infrastructur | Cancelled | Dushant Gore | 08 Apr 2022
GANGA ASMI | 145 | 0 | 21 Jun 2021 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Al. Arm. Cable laying 3.5C 185sqmm-UTI | Mtrs | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | tausif |  | construction open | 08 Apr 2022 |  | UTI. Electricity Infrastructur | Cancelled | Dushant Gore | 08 Apr 2022
GANGA ASMI | 146 | 11 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | EXECUTION / MONETORING / MANAGEMENT CHARGES - FEES | No. | 1 | 320000 | 320000 | 57600 | 377600 | 0 | 0.3853 | 123296 | 22193.28 | 145489.28 | 0.6147 | 232110.72 | GANGA ASMI WAKAD PROJECT THIRD PARTY THROUGH MARKETING + SALE WITH BRANDING ONLINE CAMPAIGN -MARKETING EXECUTION CHARGES 10% (3200000/-) + TAX | 38.53 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 3 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | GOOGLE AD WORDS / KEY WORD | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0.3287 | 32870 | 5916.6 | 38786.6 | 0.6713 | 79213.4 | 4) GOOGLE - GSP - CPC - ESTD. LEADS - 118, QLEADS - 18, ESTD SV - 5 APPROX RS. 100000 + TAX | 32.87 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 9 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | (C) 3) NATIVE PLATFORM - TIMES COLUMBIA - CPC - ESTD. LEADS - 700, QLEADS - 26, ESTD. SV - 7, APPROX RS. 100000 + TAX | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 7 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | (C) 1) NATIVE PLATFORM - TABOOLA - CPC - ESTD. LEADS - 125, QLEADS - 23, ESTD SV - 6 APPROX RS. 100000 + TAX | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 0 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | GOOGLE AD WORDS / KEY WORD | No. | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | (A) 1)GOOGLE SEARCH ADS - CPC- ESTD. 417 LEADS, QLEADS133, ESTD. SV 40 TOTAL APPROX SPEND RS. 500000 + TAX, | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 10 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | Subcription Fees | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 | GANGA ASMI WAKAD PROJECT THIRD PARTY THROUGH MARKETING + SALE WITH BRANDING ONLINE CAMPAIGN - SET UP FEES RS. 100000 +TAX | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 6 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | FaceBook Paid Campaign | No. | 1 | 300000 | 300000 | 54000 | 354000 | 0 | 1 | 300000 | 54000 | 354000 | 0 | 0 | (B) 3) FACEBOOK CAMPAIGN -NEWFEED (REGIONAL) ESTD. LEADS - 1500, QLEADS - 165, ESTD. SV - 40, APPROX RS. 300000 + TAX | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 2 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | GOOGLE AD WORDS / KEY WORD | No. | 1 | 900000 | 900000 | 162000 | 1062000 | 0 | 1 | 900000 | 162000 | 1062000 | 0 | 0 | (A) 3) GOOGLE DISCOVERY CTW - CPC ESTD. LEADS 1125, QLEADS - 203, ESTD. SV - 57, APPROX RS. 900000 + TAX., | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 5 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | FaceBook Paid Campaign | No. | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | (B) 2) FACEBOOK CAMPAIGN NEWS FEED (SECONDARY) CPC - ESTD. LEADS - 667, QLEADS - 73, ESTD. SV - 17, APPROX RS. 200000 + TAX | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 8 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | (C) 2) NATIVE PLATFORM - ADGEBRA (MARATHI) CPC - ESTD. LEADS - 133, QLEADS - 23, ESTD. SV - 6, APPROX RS. 100000 + TAX | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 4 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | FaceBook Paid Campaign | No. | 1 | 600000 | 600000 | 108000 | 708000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | (B) 1) ONLINE FACEBOOK CAMPAIGN - NEWS FEED ADS - CPM - ESTD. LEADS - 3000, QLEADS - 330, ESTD. SV - 79 APPROX RS. 600000 + TAX | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 146 | 1 | 22 Jun 2021 | ANAROCK PROPERTY CONSULTANTS PVT. LTD. | ONLINE / DIGITAL Social / Digital Activity | GOOGLE AD WORDS / KEY WORD | No. | 1 | 300000 | 300000 | 54000 | 354000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | (A) 2) GOOGLE DISPLAY (CUSTOM INTENT + REMARKETING) CPC -ESTD. -500 LEADS, QLEADS - 70, ESTD. SV -19 TOTAL APPROX RS. 300000 + TAX, | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jun 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 147 | 0 | 24 Jun 2021 | REVANTI FURNITURE | CP Lounge Glass Door Fixing | Glass work- Mkt | No. | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 12 Jul 2021 |  | MKT. Marketing Infrastructure | Approved | tausif | 1900-01-01
GANGA ASMI | 148 | 0 | 07 Jul 2021 | YOGESH BALU ICHAKE | Landscape Green Belt Area Co-ordinate Marking | Total Station Point marking- | Day | 1 | 4500 | 4500 | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | tausif | chetan.jawalikar | construction open | 06 Aug 2021 |  | B.C. RCC Substructure | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 149 | 0 | 12 Jul 2021 | OM SAI CORP | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 8020 | 9 | 72180 | 12992.4 | 85172.4 | 0 | 8020 | 72180 | 12992.38 | 85172.38 | 0 | 0.02 | GANGA ASMI WAKAD PROJECT HOARDING FLEX PRINT WITH MOUNT - Today Is The Time To #OWN TMRW! | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 13 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 150 | 1 | 20 Jul 2021 | MEGAPOWER SOLUTION PVT LTD | DG Set-125 KVA AMC Work | AMC Charges | Month | 0 | 875 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | Construction | 20 Jul 2021 |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 22 Aug 2022
GANGA ASMI | 150 | 0 | 20 Jul 2021 | MEGAPOWER SOLUTION PVT LTD | DG Set-125 KVA AMC Work | AMC Charges | Month | 12 | 875 | 10500 | 1890 | 12390 | 0 | 12 | 10500 | 1889.98 | 12389.98 | 0 | 0.02 |  | 100 |  | tausif | chetan.jawalikar | Construction | 20 Jul 2021 |  | Admin. Indirect Expenses | Approved | Aniket Mohite | 13 Oct 2021
GANGA ASMI | 150 | 1 | 20 Jul 2021 | MEGAPOWER SOLUTION PVT LTD | DG Set-125 KVA AMC Work | AMC Charges | Month | 12 | 875 | 10500 | 1890 | 12390 | 0 | 12 | 10500 | 1890 | 12390 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | Construction | 20 Jul 2021 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 151 | 0 | 21 Jul 2021 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 38000 | 228000 | 41040 | 269040 | 0 | 6 | 228000 | 41040.04 | 269040.04 | 0 | -0.04 | GANGA ASMI PROJECT BRANDING PUTDOOR DISPLAY HOARDING @ OPP. GANGA ASMI PROJECT FACING HINJEWADI SIZE AS 30 X 30 SQ FT. Rs 38000/- + tax per month as on 18/09/2021 to 17/03/2022 | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 21 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 151 | 1 | 21 Jul 2021 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 5 | 250000.2 | 45000.02 | 295000.22 | 1 | 58999.78 | GANGA ASMI PROJECT BRANDING PUTDOOR DISPLAY HOARDING @ PUNE - BANGLORE HIGHWAY, TATHAWADE SIZE AS 50 X 30 SQ FT Rs 50000/- + TAX PER MONTH AS ON 21/07/2021 TO 20/01/2022 | 83.3333 |  | Tejas Raverkar | sunita shirolkar | construction open | 21 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 151 | 2 | 21 Jul 2021 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 4 | 200000.4 | 36000.06 | 236000.46 | 2 | 117999.54 | GANGA ASMI PROJECT BRANDING PUTDOOR DISPLAY HOARDING @ GANGA ASMI PROJECT SIZE AS 30 X 42 SQ FT Rs 50000/- + TAX BOTH SIDE FRONT WITH BACK SIDE AS ON 01/07/2021 TO 31/12/2021 | 66.6667 |  | Tejas Raverkar | sunita shirolkar | construction open | 21 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 152 | 1 | 21 Jul 2021 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 25000 | 150000 | 27000 | 177000 | 0 | 6 | 150000 | 27000 | 177000 | 0 | 0 | GANGA ASMI PROJECT BRANDING PUTDOOR DISPLAY HOARDING @ NEAR VTP PROJECT- BLUE WATER , MHALUNGE SIZE AS 30 X 30 SQ FT Rs 25000/- + TAX PER MONTH AS ON 21/07/2021 TO 20/01/2022 | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 21 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 152 | 0 | 21 Jul 2021 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 6 | 300000 | 53999.98 | 353999.98 | 0 | 0.02 | GANGA ASMI PROJECT BRANDING PUTDOOR DISPLAY HOARDING @ INDIRA INSTITUATE , TATHAWADE SIZE AS 40 X 30 SQ FT Rs 50000/- + TAX PER MONTH AS ON 21/07/2021 TO 20/01/2022 | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 21 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 153 | 0 | 21 Jul 2021 | PARICHAY PUBLICITY (PRAKASH MARUTI JAMDADE) | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 6 | 300000 | 53999.98 | 353999.98 | 0 | 0.02 | GANGA ASMI PROJECT BRANDING PUTDOOR DISPLAY HOARDING @ HINJEWADI PHASE 1, TOWARDS MAHARUNJI SIZE AS 50 X 20 SQ FT Rs 50000/- + TAX AS ON 21/07/2021 TO 20/01/2022 | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jul 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 154 | 0 | 23 Jul 2021 | SURESH KUMAR MURALIDHAR | CP Lounge Work | Sand Face Plaster | Sq.Ft | 37.68 | 15 | 565.2 | 0 | 565.2 | 2.5 | 0 | 0 | 0 | 0 | 37.68 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jawalikar | construction open | 23 Jul 2021 |  | 05 GYPSUM & PLASTER | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 154 | 0 | 23 Jul 2021 | SURESH KUMAR MURALIDHAR | CP Lounge Work | PCC | Sq.Ft | 19.98 | 6 | 119.88 | 0 | 119.88 | 2.5 | 0 | 0 | 0 | 0 | 19.98 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jawalikar | construction open | 23 Jul 2021 |  | B.C. Building Common Items | Approved | chetan.jawalikar | 1900-01-01
GANGA ASMI | 155 | 0 | 24 Aug 2021 | ARYA CONSULTANCY | Electrical Work HT LT Line Shifting Work | H.T. & L.T. Line Shifting- UTI | No. | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 1 | 150000 | 27000 | 177000 | 0 | 0 |  | 100 |  | Runal Kindalkar | skmishra | construction open | 19 Oct 2021 |  | UTI. Electricity Infrastructur | Approved | skmishra | 1900-01-01
GANGA ASMI | 155 | 0 | 24 Aug 2021 | ARYA CONSULTANCY | Electrical Work Construction Meter along with Execution | Construction Meter Charges -UTI | No. | 1 | 50000 | 50000 | 9000 | 59000 | 0 | 1 | 50000 | 9000 | 59000 | 0 | 0 |  | 100 |  | Runal Kindalkar | skmishra | construction open | 19 Oct 2021 |  | UTI. Electricity Infrastructur | Approved | skmishra | 1900-01-01
GANGA ASMI | 156 | 0 | 30 Aug 2021 | JW CONSULTANTS LLP | Wing-1,2,3 Parking RCC Consultancy | RCC Consultancy | Sq.Ft | 187000 | 7.5 | 1402500 | 252450 | 1654950 | 0 | 177649.9333 | 1332374.5 | 239827.42 | 1572201.92 | 9350.0667 | 82748.08 |  | 95 |  | Runal Kindalkar | chetan.jewalikar | consultancy | 09 Sep 2021 |  | Consultacy RCC | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 156 | 0 | 30 Aug 2021 | JW CONSULTANTS LLP | Wing-2 RCC Consultancy | RCC Consultancy | Sq.Ft | 385000 | 7.5 | 2887500 | 519750 | 3407250 | 0 | 365749.9333 | 2743124.5 | 493762.42 | 3236886.92 | 19250.0667 | 170363.08 |  | 95 |  | Runal Kindalkar | chetan.jewalikar | consultancy | 09 Sep 2021 |  | Consultacy RCC | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 156 | 0 | 30 Aug 2021 | JW CONSULTANTS LLP | Wing-3 RCC Consultancy | RCC Consultancy | Sq.Ft | 373000 | 7.5 | 2797500 | 503550 | 3301050 | 0 | 274954.2667 | 2062157 | 371188.26 | 2433345.26 | 98045.7333 | 867704.74 |  | 73.7143 |  | Runal Kindalkar | chetan.jewalikar | consultancy | 09 Sep 2021 |  | Consultacy RCC | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 156 | 0 | 30 Aug 2021 | JW CONSULTANTS LLP | Wing-1 RCC Consultancy | RCC Consultancy | Sq.Ft | 373000 | 7.5 | 2797500 | 503550 | 3301050 | 0 | 354349.8 | 2657623.5 | 478372.24 | 3135995.74 | 18650.2 | 165054.26 |  | 94.9999 |  | Runal Kindalkar | chetan.jewalikar | consultancy | 09 Sep 2021 |  | Consultacy RCC | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 157 | 0 | 02 Sep 2021 | VIKAS GARADE | Land Cultivation for Tree Plantation - 1 No. | Lumpsum work- DCW | No. | 1 | 8000 | 8000 | 0 | 8000 | 0 | 1 | 8000 | 0 | 8000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 09 Sep 2021 |  | DEV. Compound Wall | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 158 | 0 | 07 Sep 2021 | PAPPU BAGELA | Sales Office&Show Flats Flooring & Tiling Rework | Departmental Labour | No. | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 08 Sep 2021 |  | S OH Infrastructure | Cancelled | skmishra | 08 Sep 2021
GANGA ASMI | 158 | 0 | 07 Sep 2021 | PAPPU BAGELA | Sales Office&Show Flats Flooring & Tiling Rework | Departmental Labour | No. | 1 | 2200 | 2200 | 396 | 2596 | 0 | 1 | 2200 | 396 | 2596 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 08 Sep 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 158 | 0 | 07 Sep 2021 | PAPPU BAGELA | Sales Office&Show Flats Flooring & Tiling Rework | Departmental Labour | No. | 0 | 2200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 08 Sep 2021 |  | S OH Infrastructure | Cancelled | skmishra | 08 Sep 2021
GANGA ASMI | 159 | 0 | 07 Sep 2021 | YOGESH BALU ICHAKE | Demarkation Setting out of Wing-1 Block | Total Statiotn Survey | Day | 2 | 4500 | 9000 | 0 | 9000 | 2.5 | 2 | 9000 | 0 | 9000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 09 Sep 2021 |  | Land Cost | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 160 | 0 | 08 Sep 2021 | VIKAS GARADE | Sales Office & Sample Flat Signage Work - 1 No. | Acrylic Plate Fixing- BC | No. | 1 | 11160 | 11160 | 0 | 11160 | 0 | 1 | 11160 | 0 | 11160 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 09 Sep 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 161 | 0 | 09 Sep 2021 | VIKAS GARADE | Marketing Expenses Plantation Drive Inaugration | Lumpsum work- DCW | No. | 1 | 12085 | 12085 | 0 | 12085 | 0 | 1 | 12085 | 0 | 12085 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | DEV. Compound Wall | Approved | skmishra | 1900-01-01
GANGA ASMI | 162 | 0 | 13 Sep 2021 | ANIL MAHTO | Internal Finishing Work. | Apex Paint (M+L) - BC | Sq.Ft | 0 | 8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 15 Sep 2021 |  | B.C. Building Common Items | Cancelled | Aniket Mohite | 15 Sep 2021
GANGA ASMI | 162 | 0 | 13 Sep 2021 | ANIL MAHTO | Internal Finishing Work. | Oil paint BC (M+L) | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 15 Sep 2021 |  | B.C. Building Common Items | Cancelled | Aniket Mohite | 15 Sep 2021
GANGA ASMI | 163 | 0 | 14 Sep 2021 | SHREE MAHALAXMI CRANE SERVICES | Removing &refixing main ent Arch Kaman - 1 No. | Crane Charges - MWB | Hrs | 16 | 800 | 12800 | 2304 | 15104 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | Runal Kindalkar | skmishra | construction open | 30 Sep 2021 |  | MKT. Marketing Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 164 | 0 | 15 Sep 2021 | ANIL MAHTO ENTERPRISES | Internal Finishing Work. | Apex Paint (M+L) - BC | Sq.Ft | 0 | 8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Avinash Padmanabha |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | skmishra | 15 Sep 2021
GANGA ASMI | 164 | 0 | 15 Sep 2021 | ANIL MAHTO ENTERPRISES | Internal Finishing Work. | Apex Paint (M+L) - BC | Sq.Ft | 1470.19 | 12 | 17642.28 | 3175.62 | 20817.9 | 2.5 | 1470.19 | 17642.28 | 3175.62 | 20817.9 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | skmishra | 1900-01-01
GANGA ASMI | 164 | 0 | 15 Sep 2021 | ANIL MAHTO ENTERPRISES | Internal Finishing Work. | Oil paint BC (M+L) | Sq.Ft | 275.58 | 15 | 4133.7 | 744.06 | 4877.76 | 2.5 | 275.58 | 4133.7 | 744.06 | 4877.76 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | skmishra | 1900-01-01
GANGA ASMI | 165 | 0 | 15 Sep 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Toilet Block Fixing | Toilet Fixing - SO | No. | 5 | 1000 | 5000 | 0 | 5000 | 0 | 5 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.75 | 6000 | 1080 | 7080 | 0.25 | 2360 |  | 75 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 0.75 | 3000 | 540 | 3540 | 0.25 | 1180 |  | 75 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.625 | 5000 | 900 | 5900 | 0.375 | 3540 |  | 62.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 0.75 | 3000 | 540 | 3540 | 0.25 | 1180 |  | 75 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 0.75 | 3000 | 540 | 3540 | 0.25 | 1180 |  | 75 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 0 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | skmishra | 1900-01-01
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 2 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 3 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 166 | 1 | 16 Sep 2021 | S.R.Enterprises | Sales Office,Lab Camp,Site Office area-Fogging Work | Fogging work-SO | Month | 1 | 4000 | 4000 | 720 | 4720 | 0 | 1 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Sep 2021 |  | S OH Infrastructure | Foreclose | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 167 | 0 | 27 Sep 2021 | OM SAI CORP | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 8020 | 9 | 72180 | 12992.4 | 85172.4 | 0 | 2519.884 | 22678.96 | 4082.2 | 26761.16 | 5500.116 | 58411.24 | GANGA ASMI WAKAD HOARDING FLEX PRINTING WITH MOUNTING TOTAL 7 HOARDING | 31.42 |  | Tejas Raverkar | sunita shirolkar | construction open | 04 Oct 2021 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 168 | 0 | 04 Oct 2021 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | GOOGLE AD WORDS / KEY WORD | No. | 3 | 100000 | 300000 | 54000 | 354000 | 0 | 1.0001 | 100005 | 18000.9 | 118005.9 | 2 | 235994.1 | GANGA ASMI WAKAD PROJECT ONLINE BRANDING, MARKETING ACTIVITY, SALES PROMOTION THROUGH GOOGLE KEY ADWORD AS ON 01.10.2021 FOR 3 MONTH @100000/- + TAX PER MONTH | 33.3367 |  | Tejas Raverkar | Tejas Raverkar | construction open | 07 Apr 2022 |  | MKT. Media | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 169 | 0 | 06 Oct 2021 | SITARAM GANGADHAR AUTI | Landscape Plantation Work in Green Zone Area | Pit Excavation - BC | No. | 1000 | 100 | 100000 | 0 | 100000 | 0 | 400 | 40000 | 0 | 40000 | 600 | 60000 |  | 40 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 20 Oct 2021 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 170 | 0 | 14 Oct 2021 | YOGESH BALU ICHAKE | Wing-1 Substructure Line Out Work Site Visit Survey | Visiting Charges-AIE | No. | 1 | 4500 | 4500 | 0 | 4500 | 2.5 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 20 Oct 2021 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Aluminium window (M+L) | Sq.Ft | 48 | 260 | 12480 | 2246.4 | 14726.4 | 2.5 | 0 | 0 | 0 | 0 | 48 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Hinges 4" (M+L) | No. | 0 | 850 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 08 Jun 2022
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (M) | Kgs | 55.68 | 68 | 3786.24 | 681.52 | 4467.76 | 0 | 0 | 0 | 0 | 0 | 55.68 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 1 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Internal Finishing Work. | Fabrication work (M) | Kgs | 53.5 | 66 | 3531 | 635.58 | 4166.58 | 0 | 29.7727 | 1965 | 353.7 | 2318.7 | 23.7273 | 1847.88 |  | 55.6499 |  | Aniket Mohite | chetan.jewalikar | construction open | 16 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Hinges 4" (M+L) | No. | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 08 Jun 2022
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Door Aldrop Hinges (M+L) | No. | 1 | 850 | 850 | 153 | 1003 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 0 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Internal Finishing Work. | Fabrication work (M) | Kgs | 672.03 | 66 | 44353.98 | 7983.72 | 52337.7 | 0 | 233.0062 | 15378.41 | 2768.12 | 18146.53 | 439.0238 | 34191.17 |  | 34.672 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 16 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (M) | Kgs | 18.9 | 60 | 1134 | 204.12 | 1338.12 | 0 | 0 | 0 | 0 | 0 | 18.9 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (M) | Kgs | 150.96 | 68 | 10265.28 | 1847.76 | 12113.04 | 0 | 0 | 0 | 0 | 0 | 150.96 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (M) | Kgs | 115.2 | 68 | 7833.6 | 1410.04 | 9243.64 | 0 | 0 | 0 | 0 | 0 | 115.2 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (M) | Kgs | 80.5 | 60 | 4830 | 869.4 | 5699.4 | 0 | 0 | 0 | 0 | 0 | 80.5 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (M) | Kgs | 20.12 | 60 | 1207.2 | 217.3 | 1424.5 | 0 | 0 | 0 | 0 | 0 | 20.12 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (M)- Kgs | Kgs | 247.69 | 60 | 14861.4 | 2675.06 | 17536.46 | 0 | 0 | 0 | 0 | 0 | 247.69 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 171 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (M)- Kgs | Kgs | 285.57 | 60 | 17134.2 | 3084.16 | 20218.36 | 0 | 0 | 0 | 0 | 0 | 285.57 | 0 | 1. Partially material available on site rest material should be supplied by contractor. 2. Material should be free from cracks, bends and other defects. 3. Material of welding rod should be Mangalam Brand. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 0 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Internal Finishing Work. | Bison Board Fixing (L) | Sq.Ft | 911 | 12 | 10932 | 1967.76 | 12899.76 | 2.5 | 720.0088 | 8640.11 | 1555.22 | 10195.33 | 190.9912 | 2704.43 |  | 79.035 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 16 Dec 2021 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (L) | Kgs | 18.9 | 18 | 340.2 | 61.24 | 401.44 | 2.5 | 0 | 0 | 0 | 0 | 18.9 | 0 | 1.Structural work to be done with proper line level & Alignment. 2.Temporary supporting structure or frame if required then it is to be done by contractor & no extra cost will be paid. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 1 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Internal Finishing Work. | Fabrication work (L) | Kgs | 53.5 | 18 | 963 | 173.34 | 1136.34 | 0 | 29.773 | 535.91 | 96.46 | 632.37 | 23.727 | 503.97 |  | 55.6505 |  | Aniket Mohite | chetan.jewalikar | construction open | 16 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 08 Jun 2022
GANGA ASMI | 172 | 0 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Internal Finishing Work. | Sliding Window (M+L) | Sq.Ft | 60 | 260 | 15600 | 2808 | 18408 | 2.5 | 60 | 15600 | 2808 | 18408 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (L) | Kgs | 247.69 | 18 | 4458.42 | 802.52 | 5260.94 | 2.5 | 0 | 0 | 0 | 0 | 247.69 | 0 | 1.Structural work to be done with proper line level & Alignment. 2.Temporary supporting structure or frame if required then it is to be done by contractor & no extra cost will be paid. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 0 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Internal Finishing Work. | Fabrication work (L) | Kgs | 672.03 | 18 | 12096.54 | 2177.38 | 14273.92 | 2.5 | 233.0062 | 4194.11 | 754.94 | 4949.05 | 439.0238 | 9324.87 |  | 34.672 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 16 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (L) | Kgs | 80.5 | 18 | 1449 | 260.82 | 1709.82 | 2.5 | 0 | 0 | 0 | 0 | 80.5 | 0 | 1.Structural work to be done with proper line level & Alignment. 2.Temporary supporting structure or frame if required then it is to be done by contractor & no extra cost will be paid. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (L) | Kgs | 115.2 | 18 | 2073.6 | 373.24 | 2446.84 | 2.5 | 0 | 0 | 0 | 0 | 115.2 | 0 | 1.Structural work to be done with proper line level & Alignment. 2.Temporary supporting structure or frame if required then it is to be done by contractor & no extra cost will be paid. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Sheet Fixing - AIE | Sq.Ft | 1060 | 5 | 5300 | 954 | 6254 | 2.5 | 0 | 0 | 0 | 0 | 1060 | 0 | 1. GI Sheet will be supplied by GGG. 2. Screws will be supplied by contractors including fixing. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (L) | Kgs | 150.96 | 18 | 2717.28 | 489.12 | 3206.4 | 2.5 | 0 | 0 | 0 | 0 | 150.96 | 0 | 1.Structural work to be done with proper line level & Alignment. 2.Temporary supporting structure or frame if required then it is to be done by contractor & no extra cost will be paid. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (L) | Kgs | 285.57 | 18 | 5140.26 | 925.24 | 6065.5 | 2.5 | 0 | 0 | 0 | 0 | 285.57 | 0 | 1.Structural work to be done with proper line level & Alignment. 2.Temporary supporting structure or frame if required then it is to be done by contractor & no extra cost will be paid. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (L) | Kgs | 55.68 | 18 | 1002.24 | 180.4 | 1182.64 | 2.5 | 0 | 0 | 0 | 0 | 55.68 | 0 | 1.Structural work to be done with proper line level & Alignment. 2.Temporary supporting structure or frame if required then it is to be done by contractor & no extra cost will be paid. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 172 | 2 | 16 Oct 2021 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (L) | Kgs | 20.12 | 18 | 362.16 | 65.18 | 427.34 | 2.5 | 0 | 0 | 0 | 0 | 20.12 | 0 | 1.Structural work to be done with proper line level & Alignment. 2.Temporary supporting structure or frame if required then it is to be done by contractor & no extra cost will be paid. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Shiv yantra | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Vasturaviraj Pyramid Lapiz WB - No. | No. | 0 | 1028.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Mandal Remedy | No. | 0 | 135000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Vasturaviraj Pyramid Yellow WB - No. | No. | 0 | 1028.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Kamakhya Yantra (Large) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | PT (Large) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Consultancy Visit Charges | Visiting Charges-AIE | No. | 1 | 33898.3 | 33898.3 | 6101.7 | 40000 | 0 | 1 | 33898.3 | 6101.7 | 40000 | 0 | 0 |  | 100 |  | Avinash Padmanabha | skmishra | consultancy | 22 Oct 2021 |  | Admin. Indirect Expenses | Approved | skmishra | 1900-01-01
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Vasturaviraj Pyramid Yellow WB - No. | No. | 0 | 1028.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | consultancy | 22 Oct 2021 |  | No category | Cancelled | MONALI CHAUDHAR | 22 May 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Vasturaviraj Pyramid Clear Quartz WB - No. | No. | 0 | 1028.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Vasturaviraj Pyramid Lapiz WB - No. | No. | 0 | 1028.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | consultancy | 22 Oct 2021 |  | No category | Cancelled | MONALI CHAUDHAR | 22 May 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Vasturaviraj Pyramid (with crystal) | No. | 0 | 255 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 173 | 0 | 22 Oct 2021 | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | Vastu Remedy Material | Surya (L) | No. | 0 | 1636.25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | consultancy | 22 Oct 2021 |  | No category | Cancelled | DUSHANT.GORE | 14 Jun 2024
GANGA ASMI | 174 | 0 | 22 Oct 2021 | GLOBAL GEOTECHNICS | Site Infra Soil Test-Site Visit Wing-1,2,3 | Visiting Charges-AIE | No. | 6 | 7500 | 45000 | 8100 | 53100 | 0 | 6 | 44999.63 | 8100 | 53099.63 | 0.0001 | 0.38 |  | 100 |  | Avinash Padmanabha | skmishra | consultancy | 28 Oct 2021 |  | Admin. Indirect Expenses | Approved | skmishra | 1900-01-01
GANGA ASMI | 174 | 1 | 22 Oct 2021 | GLOBAL GEOTECHNICS | Site Infra Soil Test-Site Visit Wing-1,2,3 | Visiting Charges-AIE | No. | 6 | 7500 | 45000 | 8100 | 53100 | 0 | 6 | 45000 | 8100 | 53100 | 0 | 0 | Site Visit for strata verification of Wing 2, Wing 3 & Podium area. | 100 |  | DUSHANT GORE | chetan jewalikar | consultancy | 28 Oct 2021 |  | Admin. Indirect Expenses | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 175 | 0 | 12 Nov 2021 | DREAMTREE EXPERIENCE | PRINTING PRINTING-NO.-(NA) | FLEX PRINTING & MOUNTING | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GANGA ASMI MAIN GATE ARCH FLEX PRINT WITH MOUNT | 0 |  | Tejas Raverkar |  | construction open | 24 Nov 2021 |  | MKT. Media | Cancelled | sunita shirolkar | 24 Nov 2021
GANGA ASMI | 176 | 0 | 17 Nov 2021 | DUROCRETE ENGINEERING SERVICES PVT LTD | Steel Test - 1 No. | Tensile Strength & % Elongation-SOS | No. | 9 | 154 | 1386 | 249.48 | 1635.48 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 176 | 0 | 17 Nov 2021 | DUROCRETE ENGINEERING SERVICES PVT LTD | Steel Test - 1 No. | 90/180 Bend Test-SOS | No. | 18 | 154 | 2772 | 498.96 | 3270.96 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 176 | 0 | 17 Nov 2021 | DUROCRETE ENGINEERING SERVICES PVT LTD | Steel Test - 1 No. | 135/157.5 Rebend Test-SOS | No. | 18 | 154 | 2772 | 498.96 | 3270.96 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 176 | 0 | 17 Nov 2021 | DUROCRETE ENGINEERING SERVICES PVT LTD | Steel Test - 1 No. | Weight per Meter-SOS | No. | 18 | 28 | 504 | 90.72 | 594.72 | 0 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 176 | 0 | 17 Nov 2021 | DUROCRETE ENGINEERING SERVICES PVT LTD | Steel Test - 1 No. | Chemical Testing of Steel-SOS | No. | 6 | 420 | 2520 | 453.6 | 2973.6 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 176 | 0 | 17 Nov 2021 | DUROCRETE ENGINEERING SERVICES PVT LTD | Steel Test - 1 No. | Tensile Strength & % Elongation-SOS | No. | 9 | 189 | 1701 | 306.18 | 2007.18 | 0 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | Runal Kindalkar | chetan.jewalikar | construction open | 24 Nov 2021 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 177 | 0 | 19 Nov 2021 | TATVA LEGAL MUMBAI | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 712500 | 712500 | 128250 | 840750 | 0 | 1 | 712500 | 128250 | 840750 | 0 | 0 | GANGA ASMI WAKAD PROJECT - PROFESSIONAL FEES TOWARDS CONDUCTION TITLE DUE DILIGENCE | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 19 Nov 2021 |  | 03 CONSULTANCY | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 177 | 1 | 19 Nov 2021 | TATVA LEGAL MUMBAI | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 337500 | 337500 | 0 | 337500 | 0 | 1 | 337500 | 0 | 337500 | 0 | 0 | GANAG ASMI WAKAD PROJECT VALUATION OF A LAND PARCEL LOCATED AT WAKAD - COMMISSIONING FEES | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 19 Nov 2021 |  | 03 CONSULTANCY | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 178 | 0 | 19 Nov 2021 | CBRE SOUTH ASIA PVT. LTD. | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 1 | 150000 | 27000 | 177000 | 0 | 0 | GANGA ASMI WAKAD PROJECT -COMMISSION TOWARDS CONDUCTION VALUATION SERVICE REPORT | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 19 Nov 2021 |  | 03 CONSULTANCY | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 179 | 0 | 19 Nov 2021 | QUANTUM PROJECT INFRA PVT. LTD. | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 210000 | 210000 | 37800 | 247800 | 0 | 1 | 210000 | 37800 | 247800 | 0 | 0 | GANGA ASMI WAKAD PROJECT - ENGAGEMENT FEES FOR TECHNICAL DUE DILIGENCE | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 19 Nov 2021 |  | 03 CONSULTANCY | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 179 | 1 | 19 Nov 2021 | QUANTUM PROJECT INFRA PVT. LTD. | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 90000 | 90000 | 16200 | 106200 | 0 | 1 | 90000 | 16200 | 106200 | 0 | 0 | GANAG ASMI WAKAD PROJECT FEES ON SUBMISSION OF DRAFT REPORT FOR TECHNICAL DUE - DILIGENCE FOR PROJECT BEING DEVELOPED IN PUNE | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 19 Nov 2021 |  | 03 CONSULTANCY | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 180 | 0 | 19 Nov 2021 | KPMG INDIA SERVICES LLP | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 650000 | 650000 | 117000 | 767000 | 0 | 1 | 650000 | 117000 | 767000 | 0 | 0 | GANGA ASMI WAKAD PROJECT - PAYMENT REQUIRE FOR PROFESSIONAL SERVICES IN CONNECTION WITH PROJECT SERENITY | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 19 Nov 2021 |  | 03 CONSULTANCY | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 181 | 0 | 20 Nov 2021 | TATVA LEGAL MUMBAI | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 337500 | 337500 | 0 | 337500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | GANAG ASMI PROJECT PROFEESIONAL FEES TOWARDS CONSDUCTION TITLE DUE DILIGENCE REPORT | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | 03 CONSULTANCY | Un-Approved |  | 1900-01-01
GANGA ASMI | 182 | 0 | 05 Dec 2021 | WORLD WEB SOLUTIONS | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | GANGA ASMI WAKAD PROJECT ONLINE- DIGITAL SALES/ MARKETING PROMOTION WITH BRANDING (GENERATE THE ENQUIERY) THROUGH GOOGLE AND FACEBOOK | 0 |  | Tejas Raverkar | Tejas Raverkar | construction open | 05 Dec 2021 |  | MKT. Media | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 182 | 1 | 05 Dec 2021 | WORLD WEB SOLUTIONS | ONLINE / DIGITAL Social / Digital Activity | EXECUTION / MONETORING / MANAGEMENT CHARGES - FEES | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | GOOGLE AND FACEBOOK LEAD GENERATION CAMPAIGN MONITORING, EXECUTION CHARGES | 0 |  | Tejas Raverkar |  | construction open | 05 Dec 2021 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 183 | 0 | 14 Dec 2021 | S.R.Enterprises | Wing-1 Parking Antitermite Treatment | Antitermite Treatment - BC] | Sq.Ft | 5096.32 | 4 | 20385.28 | 3669.36 | 24054.64 | 2.5 | 1019.264 | 4077.06 | 733.88 | 4810.94 | 4077.056 | 19243.7 |  | 20 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 183 | 0 | 14 Dec 2021 | S.R.Enterprises | Wing-1 Substructure Antitermite Treatment | Antitermite Treatment - BC] | Sq.Ft | 12194.75 | 4 | 48779 | 8780.22 | 57559.22 | 2.5 | 10975.275 | 43901.1 | 7902.2 | 51803.3 | 1219.475 | 5755.92 |  | 90 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Brickwork-9" | 9" Brick Work | Sq.Ft | 170 | 15 | 2550 | 459 | 3009 | 0 | 161.007 | 2415.11 | 0 | 2415.11 | 8.993 | 593.9 |  | 94.71 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | 12 MASONARY WORK | Approved | Dushant Gore | 20 Apr 2022
GANGA ASMI | 184 | 1 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | 9" Brick Work | Sq.Ft | 131 | 14 | 1834 | 0 | 1834 | 2.5 | 0 | 0 | 0 | 0 | 131 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 12 MASONARY WORK | Approved | Dushant Gore | 20 Apr 2022
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Brickwork-6" | 6" Brick Work | Sq.Ft | 16.5 | 12 | 198 | 35.64 | 233.64 | 0 | 16.5 | 198 | 0 | 198 | 0 | 35.64 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | 12 MASONARY WORK | Approved | Dushant Gore | 20 Apr 2022
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Sand Face Plaster | Sand face Plaster-Utv | Sq.Ft | 225 | 15 | 3375 | 607.5 | 3982.5 | 0 | 203.5012 | 3052.52 | 0 | 3052.52 | 21.4988 | 929.98 |  | 90.445 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | UTI. Vermiculture | Approved | Dushant Gore | 20 Apr 2022
GANGA ASMI | 184 | 1 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Labour Camp Toilet Civil Work | Mobile Toilet Fixing | No. | 4 | 500 | 2000 | 0 | 2000 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank PCC Site Mix | PCC | Sq.Ft | 224 | 6 | 1344 | 241.92 | 1585.92 | 0 | 224 | 1344 | 0 | 1344 | 0 | 241.92 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Dushant Gore | 20 Apr 2022
GANGA ASMI | 184 | 2 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work Domestic tank& mobile toilet fixing | Labour Lumsum | No. | 1 | 13000 | 13000 | 0 | 13000 | 2.5 | 0.95 | 12350 | 0 | 12350 | 0.05 | 650 |  | 95 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 184 | 1 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | Backfilling - UDR | Cu.Ft | 90.75 | 3.5 | 317.63 | 0 | 317.63 | 0 | 0 | 0 | 0 | 0 | 90.75 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Soiling Work | Soling work- DLd | Sq.Ft | 0 | 6.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Cancelled | Aniket Mohite | 16 Dec 2021
GANGA ASMI | 184 | 1 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | Soling Work -Mkt | Sq.Ft | 30.25 | 6.5 | 196.63 | 0 | 196.63 | 0 | 0 | 0 | 0 | 0 | 30.25 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 184 | 2 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work Domestic tank& mobile toilet fixing | Labour Lumsum | No. | 0 | 13000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 05 Sep 2022
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Fixing Lab Toilet | Toilet Fixing - SO | No. | 1 | 500 | 500 | 90 | 590 | 0 | 1 | 500 | 0 | 500 | 0 | 90 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Dushant Gore | 20 Apr 2022
GANGA ASMI | 184 | 1 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | New Labour Camp | PCC | Sq.Ft | 142 | 6 | 852 | 0 | 852 | 0 | 0 | 0 | 0 | 0 | 142 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 184 | 2 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil work Domestic tank& mobile toilet fixing | Labour Lumsum | No. | 0 | 13000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 05 Sep 2022
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Brickwork-6" | 6" Brick Work | Sq.Ft | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 1900-01-01 |  | 12 MASONARY WORK | Cancelled | Aniket Mohite | 16 Dec 2021
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Soiling Work | Soling work- DLd | Sq.Ft | 55 | 6.5 | 357.5 | 64.36 | 421.86 | 0 | 55 | 357.5 | 0 | 357.5 | 0 | 64.36 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Dushant Gore | 20 Apr 2022
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Brickwork-9" | 9" Brick Work | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 1900-01-01 |  | 12 MASONARY WORK | Cancelled | Aniket Mohite | 16 Dec 2021
GANGA ASMI | 184 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Domestic Water Tank Mururm Filling | Murum filling Dld | Cu.Ft | 165 | 3.5 | 577.5 | 103.96 | 681.46 | 0 | 165 | 577.5 | 0 | 577.5 | 0 | 103.96 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Dushant Gore | 20 Apr 2022
GANGA ASMI | 185 | 2 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Plinth Preparation (Wing 1) | JCB Charges | Hrs | 64 | 850 | 54400 | 9792 | 64192 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | Approximate Area- 11000 Sq.ft | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 185 | 3 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Plinth Preparation (Wing 2) | Bobcat Hiring Charges | Hrs | 200 | 800 | 160000 | 28800 | 188800 | 0 | 200 | 160000 | 28800 | 188800 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 185 | 0 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Spreading & Levelling Work | Cu.Mtrs | 430.68 | 15 | 6460.2 | 1162.84 | 7623.04 | 0 | 430.68 | 6460.2 | 1162.84 | 7623.04 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 185 | 0 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Excavation By Bucket (Shifting Inside) | Cu.Mtrs | 430.68 | 60 | 25840.8 | 4651.34 | 30492.14 | 0 | 430.68 | 25840.8 | 4651.34 | 30492.14 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 185 | 2 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Plinth Preparation (Wing 2) | JCB Charges | Hrs | 64 | 850 | 54400 | 9792 | 64192 | 0 | 0 | 0 | 0 | 0 | 64 | 0 | Approximate Area- 6700 sq.ft | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 185 | 3 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Plinth Preparation (Wing 2) | Bobcat Hiring Charges | Hrs | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 10 Dec 2022
GANGA ASMI | 185 | 1 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Wing-1 Substructure Excavation Work | Poclain Charges - BC - | Hrs | 16 | 2200 | 35200 | 6336 | 41536 | 0 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 24 Dec 2021 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 185 | 2 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Plinth Preparation (Wing 2) | Bobcat Hiring Charges | Hrs | 64 | 600 | 38400 | 6912 | 45312 | 0 | 64 | 38400 | 6912 | 45312 | 0 | 0 | Approximate Area- 6700 sq.ft | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 185 | 2 | 16 Dec 2021 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Plinth Preparation (Wing 1) | Bobcat Hiring Charges | Hrs | 64 | 600 | 38400 | 6912 | 45312 | 2.5 | 64 | 38400 | 6912 | 45312 | 0 | 0 | Approximate Area- 11000 Sq.ft | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 186 | 0 | 16 Dec 2021 | YOGESH BALU ICHAKE | Wing-1 Substructure Line Out Work Site Visit Survey | Total Station Point marking- | Day | 1 | 4500 | 4500 | 0 | 4500 | 0 | 1 | 4500 | 0 | 4500 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 187 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil Work Steel Cutting Yard | PCC | Sq.Ft | 374 | 6 | 2244 | 0 | 2244 | 0 | 0 | 0 | 0 | 0 | 374 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 187 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil Work Steel Cutting Yard | Pit Excavation and Concreting | Cu.Ft | 112.5 | 6.5 | 731.25 | 0 | 731.25 | 0 | 0 | 0 | 0 | 0 | 112.5 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 187 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil Work Steel Cutting Yard | Excavation | Cu.Ft | 70 | 6.5 | 455 | 0 | 455 | 0 | 0 | 0 | 0 | 0 | 70 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 187 | 0 | 16 Dec 2021 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Civil Work Steel Cutting Yard | JCB Charges | Hrs | 4 | 850 | 3400 | 0 | 3400 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 7.332 | 3666 | 0 | 3666 | 12.668 | 6334 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 36.66 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 7 | 3500 | 0 | 3500 | 13 | 6500 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 35 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 5.664 | 2832 | 0 | 2832 | 11.336 | 5668 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 33.3176 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 10 | 5000 | 0 | 5000 | 10 | 5000 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 50 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 0 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Cleaning | Cleaning Charges | No. | 4 | 500 | 2000 | 0 | 2000 | 0 | 4 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 7 | 3500 | 0 | 3500 | 13 | 6500 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 35 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 7.74 | 3870 | 0 | 3870 | 12.26 | 6130 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 38.7 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 0 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 16 Dec 2021 |  | S OH Infrastructure | Cancelled | Aniket Mohite | 16 Dec 2021
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 11.05 | 5525 | 0 | 5525 | 5.95 | 2975 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 65 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 5.357 | 2678.5 | 0 | 2678.5 | 14.643 | 7321.5 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 26.785 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 8.5 | 4250 | 0 | 4250 | 8.5 | 4250 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 7 | 3500 | 0 | 3500 | 13 | 6500 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 35 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 8.092 | 4046 | 0 | 4046 | 8.908 | 4454 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 47.6 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 6.792 | 3396 | 0 | 3396 | 13.208 | 6604 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 33.96 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 12.4661 | 6233.05 | 0 | 6233.05 | 4.5339 | 2266.95 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 73.33 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 15.916 | 7958 | 0 | 7958 | 4.084 | 2042 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 79.58 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 4.192 | 2096 | 0 | 2096 | 15.808 | 7904 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 20.96 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 8 | 4000 | 0 | 4000 | 12 | 6000 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 40 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 1 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 20 | 500 | 10000 | 0 | 10000 | 0 | 10 | 5000 | 0 | 5000 | 10 | 5000 | Sales Toilet- 4No, Staff Toilet- 1No, Labour Camp 3- 2No, Labour Camp 1- 8No Labour Camp 2- 4No, Old Toilet- 1No. Total- 20Nos. | 50 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 17 | 500 | 8500 | 0 | 8500 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Toilets- Labour Camp 1- 10 Nos, Labour Camp 2- 4 Nos, Labour Camp 3- 2 Nos, Staff- 1No. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 188 | 2 | 16 Dec 2021 | SHRI MAHAVIR PRASAD KHOKAR | Labour Camp Toilet Cleaning | Toilet Cleaning Work | No. | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 16 Dec 2021 |  | SOC. M. Maintenace Staff | Cancelled | ADITYA.CHOUGULE | 20 Jul 2023
GANGA ASMI | 189 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 17 Dec 2021 |  | S OH Infrastructure | Cancelled | skmishra | 17 Dec 2021
GANGA ASMI | 190 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 0 | 1750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 17 Dec 2021 |  | S OH Infrastructure | Cancelled | Aniket Mohite | 17 Dec 2021
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 1 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aniket Mohite |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | Aniket Mohite | 18 Dec 2021
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 1 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0.6129 | 2145.15 | 0 | 2145.15 | 0.3871 | 1354.85 |  | 61.29 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 1 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0.5 | 1750 | 0 | 1750 | 0.5 | 1750 |  | 50 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0.5 | 1750 | 0 | 1750 | 0.5 | 1750 |  | 50 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 0.5 | 3500 | 1750 | 0 | 1750 | 0 | 0.2667 | 933.45 | 0 | 933.45 | 0.2333 | 816.55 | For The Month of SEP-2021. | 53.34 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 191 | 0 | 17 Dec 2021 | MAHAVIRPRASAD S KHOKHAR | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | Month | 1 | 3500 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 192 | 0 | 20 Dec 2021 | AQUARIUS WATERPROOFING | Wing-1 Substructure Lift Pit Waterproofing(Horizontal) | Perma Waterproofing (M) | Sq.Ft | 1567.62 | 27 | 42325.74 | 7618.64 | 49944.38 | 0 | 1524.1499 | 41152.05 | 7407.36 | 48559.41 | 43.4701 | 1384.97 |  | 97.227 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | Dushant Gore | 26 May 2022
GANGA ASMI | 192 | 2 | 20 Dec 2021 | AQUARIUS WATERPROOFING | Wing-1 Qty Diff. Lift Pit Waterproofing(Vertical) | Perma Waterproofing (M) | Sq.Ft | 380.05 | 40 | 15202 | 2736.36 | 17938.36 | 0 | 380.05 | 15202 | 2736.36 | 17938.36 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 192 | 0 | 20 Dec 2021 | AQUARIUS WATERPROOFING | Wing-1 Substructure Lift Pit Waterproofing(Vertical) | Perma Waterproofing (M) | Sq.Ft | 11329.24 | 30 | 339877.2 | 61177.9 | 401055.1 | 0 | 11329.24 | 339877.2 | 61177.9 | 401055.1 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | Dushant Gore | 26 May 2022
GANGA ASMI | 192 | 1 | 20 Dec 2021 | AQUARIUS WATERPROOFING | Wing-1 Substructure Lift Pit Waterproofing(Vertical) | Rate Diff. For Perma Waterproofing (M) | Sq.Ft | 7192.24 | 10 | 71922.4 | 12946.04 | 84868.44 | 0 | 7191.5208 | 71915.21 | 12944.74 | 84859.95 | 0.7192 | 8.49 |  | 99.99 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | Dushant Gore | 26 May 2022
GANGA ASMI | 193 | 2 | 20 Dec 2021 | AQUARIUS WATERPROOFING | Wing-1 Qty Diff. Lift Pit Waterproofing(Vertical) | Perma Waterproofing (L) | Sq.Ft | 380.05 | 15 | 5700.75 | 1026.14 | 6726.89 | 10 | 380.05 | 5700.75 | 1026.14 | 6726.89 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 193 | 1 | 20 Dec 2021 | AQUARIUS WATERPROOFING | Wing-1 Substructure Lift Pit Waterproofing(Vertical) | Rate Diff. For Perma Waterproofing (L) | Sq.Ft | 7192.24 | 3 | 21576.72 | 3883.8 | 25460.52 | 10 | 7191.5208 | 21574.56 | 3883.42 | 25457.98 | 0.7192 | 2.54 |  | 99.99 |  | Dushant Gore | Swapnil Erande | construction open | 24 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 193 | 0 | 20 Dec 2021 | AQUARIUS WATERPROOFING | Wing-1 Substructure Lift Pit Waterproofing(Vertical) | Perma Waterproofing (L) | Sq.Ft | 11329.24 | 12 | 135950.88 | 24471.16 | 160422.04 | 2.5 | 11329.24 | 135950.88 | 24471.16 | 160422.04 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 193 | 0 | 20 Dec 2021 | AQUARIUS WATERPROOFING | Wing-1 Substructure Lift Pit Waterproofing(Horizontal) | Perma Waterproofing (L) | Sq.Ft | 1567.62 | 10 | 15676.2 | 2821.72 | 18497.92 | 2.5 | 1524.1499 | 15241.5 | 2743.48 | 17984.98 | 43.4701 | 512.94 |  | 97.227 |  | Aniket Mohite | chetan.jewalikar | construction open | 24 Dec 2021 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 194 | 0 | 23 Dec 2021 | CBRE SOUTH ASIA PVT. LTD. | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 125000 | 125000 | 22500 | 147500 | 0 | 1 | 125000 | 22500 | 147500 | 0 | 0 | GANAG ASMI WAKAD PROJECT VALUATION OF A LAND PARCEL LOCATED AT WAKAD - COMMISSIONING FEES | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 23 Dec 2021 |  | 03 CONSULTANCY | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 195 | 0 | 24 Dec 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication work for DP Road Side | Fabrication work (L) | Kgs | 179.44 | 18 | 3229.92 | 581.38 | 3811.3 | 2.5 | 0 | 0 | 0 | 0 | 179.44 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 195 | 0 | 24 Dec 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication work for DP Road Side | Fabrication work (L) | Kgs | 336.42 | 18 | 6055.56 | 1090 | 7145.56 | 2.5 | 0 | 0 | 0 | 0 | 336.42 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 195 | 0 | 24 Dec 2021 | SHRUSHTI GLASS & ALUMINIUM | Barrication work for DP Road Side | GI Sheet Fixing (L) | Sq.Ft | 870 | 5.5 | 4785 | 861.3 | 5646.3 | 2.5 | 0 | 0 | 0 | 0 | 870 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | UTI. Vermiculture | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 196 | 0 | 28 Dec 2021 | QUANTUM PROJECT INFRA PVT. LTD. | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 700000 | 700000 | 126000 | 826000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | TECHNICAL DUE - CONSULTANCY FEES CHARGES FOR GANGA ASMI WAKAD | 0 |  | Tejas Raverkar | Tejas Raverkar | construction open | 28 Dec 2021 |  | 03 CONSULTANCY | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 197 | 0 | 28 Dec 2021 | ERNST AND YOUNG LLP | FINANCE CONSULTANCY Proffessional Consultancy | TECHNICAL - TITLE DUE - DELIGENCE / PROJECT FINANCE REPORT / | No. | 1 | 1400000 | 1400000 | 252000 | 1652000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | GANGA ASMI WAKAD TECHNICAL TILE DUE DELIGANCE PROJECT REPORT FINANCE CONSULTANCY CHARGES ADVANCE PAYMENT + TAX | 0 |  | Tejas Raverkar | Tejas Raverkar | construction open | 28 Dec 2021 |  | 03 CONSULTANCY | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 198 | 0 | 05 Jan 2022 | AZB AND PARTNERS | FINANCE CONSULTANCY Proffessional Consultancy | Legal Consultancy.- | No. | 1 | 1000000 | 1000000 | 180000 | 1180000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | LEGAL CONSUTANCY CHARGES FOR GANGA ASMI WAKAD PROJECT ADVICE, CORPORATE DUE DILIGENCE, LEGAL DOCUMENT- MATTER ETC. | 0 |  | Tejas Raverkar | Tejas Raverkar | construction open | 06 Jan 2022 |  | Consultancy Legal | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 0 | 62 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | vaibhav biradar | 14 Jan 2022
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (M)- Kgs | Kgs | 247.69 | 60 | 14861.4 | 2675.06 | 17536.46 | 0 | 0 | 0 | 0 | 0 | 247.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 199 | 1 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | Dushant Gore | 07 Jun 2022
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 530.6 | 69 | 36611.4 | 6590.06 | 43201.46 | 0 | 354.0269 | 24427.86 | 4397.02 | 28824.88 | 176.5731 | 14376.58 |  | 66.722 |  | vaibhav biradar | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (M) | Kgs | 150.96 | 68 | 10265.28 | 1847.76 | 12113.04 | 0 | 0 | 0 | 0 | 0 | 150.96 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | vaibhav biradar | 14 Jan 2022
GANGA ASMI | 199 | 1 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 0 | 64 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | Dushant Gore | 07 Jun 2022
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Hinges 4" (M+L) | No. | 0 | 850 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 08 Jun 2022
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (M)- Kgs | Kgs | 285.57 | 60 | 17134.2 | 3084.16 | 20218.36 | 0 | 0 | 0 | 0 | 0 | 285.57 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 0 | 69 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | skmishra | 14 Jan 2022
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Door Aldrop Hinges (M+L) | No. | 1 | 850 | 850 | 153 | 1003 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (M) | Kgs | 18.9 | 60 | 1134 | 204.12 | 1338.12 | 0 | 0 | 0 | 0 | 0 | 18.9 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Top Bearing Of Gate | No. | 24 | 180 | 4320 | 777.6 | 5097.6 | 0 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | vaibhav biradar | chetan.jewalikar | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 298.205 | 62 | 18488.71 | 3327.96 | 21816.67 | 0 | 187.8602 | 11647.33 | 2096.52 | 13743.85 | 110.3448 | 8072.82 |  | 62.997 |  | vaibhav biradar | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 392.825 | 69 | 27104.93 | 4878.88 | 31983.81 | 0 | 158.0885 | 10908.11 | 1963.46 | 12871.57 | 234.7365 | 19112.24 |  | 40.244 |  | vaibhav biradar | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Sliding Door Bearing | No. | 6 | 650 | 3900 | 702 | 4602 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | vaibhav biradar | chetan.jewalikar | construction open | 1900-01-01 |  | 09 CARPENTRY WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (M)- Kgs | Kgs | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 07 Jun 2022
GANGA ASMI | 199 | 1 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 0 | 54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | Dushant Gore | 07 Jun 2022
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (M) | Kgs | 115.2 | 68 | 7833.6 | 1410.04 | 9243.64 | 0 | 0 | 0 | 0 | 0 | 115.2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (M) | Kgs | 80.5 | 60 | 4830 | 869.4 | 5699.4 | 0 | 0 | 0 | 0 | 0 | 80.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 199 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 1331.02 | 62 | 82523.24 | 14854.18 | 97377.42 | 0 | 1179.5899 | 73134.57 | 13164.22 | 86298.79 | 151.4301 | 11078.63 |  | 88.623 |  | vaibhav biradar | chetan.jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 199 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (M) | Kgs | 20.12 | 60 | 1207.2 | 217.3 | 1424.5 | 0 | 0 | 0 | 0 | 0 | 20.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 200 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 530.6 | 18 | 9550.8 | 1719.14 | 11269.94 | 2.5 | 360.9353 | 6496.84 | 1169.44 | 7666.28 | 169.6647 | 3603.66 |  | 68.024 |  | vaibhav biradar | chetan.jewalikar | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Approved | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 1331.02 | 18 | 23958.36 | 4312.5 | 28270.86 | 2.5 | 1331.02 | 23958.36 | 4312.5 | 28270.86 | 0 | 0 |  | 100 |  | vaibhav biradar | chetan.jewalikar | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Approved | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 3 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (L) | Kgs | 150.96 | 18 | 2717.28 | 489.12 | 3206.4 | 2.5 | 0 | 0 | 0 | 0 | 150.96 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 200 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Cancelled | skmishra | 14 Jan 2022
GANGA ASMI | 200 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | vaibhav biradar |  | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Cancelled | skmishra | 14 Jan 2022
GANGA ASMI | 200 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 392.825 | 18 | 7070.85 | 1272.76 | 8343.61 | 2.5 | 158.0885 | 2845.59 | 512.2 | 3357.79 | 234.7365 | 4985.82 |  | 40.244 |  | vaibhav biradar | chetan.jewalikar | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Approved | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 1 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Cancelled | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 298.205 | 18 | 5367.69 | 966.18 | 6333.87 | 2.5 | 187.8572 | 3381.43 | 608.66 | 3990.09 | 110.3478 | 2343.78 |  | 62.996 |  | vaibhav biradar | chetan.jewalikar | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Approved | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 2 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Aluminium Window refixing | No. | 1 | 3200 | 3200 | 576 | 3776 | 2.5 | 1 | 3200 | 576 | 3776 | 0 | 0 | Old Aluminium window cutting and refitting,Window new bearing & Labour Charges for Aluminium Windows frame support with MS Pipe only. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 3 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (L) | Kgs | 285.57 | 18 | 5140.26 | 925.24 | 6065.5 | 2.5 | 0 | 0 | 0 | 0 | 285.57 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 200 | 3 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (L) | Kgs | 18.9 | 18 | 340.2 | 61.24 | 401.44 | 2.5 | 0 | 0 | 0 | 0 | 18.9 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 200 | 0 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | GI Sheet Fixing (L) | Sq.Ft | 2801 | 5.5 | 15405.5 | 2773 | 18178.5 | 2.5 | 2801 | 15405.5 | 2773 | 18178.5 | 0 | 0 |  | 100 |  | vaibhav biradar | chetan.jewalikar | construction open | 14 Jan 2022 |  | UTI. Vermiculture | Approved | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 1 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Cancelled | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 3 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | Sheet Fixing - AIE | Sq.Ft | 1060 | 5 | 5300 | 954 | 6254 | 2.5 | 0 | 0 | 0 | 0 | 1060 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jan 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 200 | 3 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (L) | Kgs | 80.5 | 18 | 1449 | 260.82 | 1709.82 | 2.5 | 0 | 0 | 0 | 0 | 80.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 200 | 1 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | GI Sheet Fixing (L) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 14 Jan 2022 |  | UTI. Vermiculture | Cancelled | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 1 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 14 Jan 2022 |  | Admin. Direct Expenses | Cancelled | Dushant Gore | 18 Apr 2022
GANGA ASMI | 200 | 3 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Square Pipe (L) | Kgs | 115.2 | 18 | 2073.6 | 373.24 | 2446.84 | 2.5 | 0 | 0 | 0 | 0 | 115.2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 200 | 3 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | MS Angle. (L) | Kgs | 20.12 | 18 | 362.16 | 65.18 | 427.34 | 2.5 | 0 | 0 | 0 | 0 | 20.12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 200 | 3 | 14 Jan 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Site Office,Store,Laboratory Mobile Crench | ISMC 100 (L) | Kgs | 247.69 | 18 | 4458.42 | 802.52 | 5260.94 | 2.5 | 0 | 0 | 0 | 0 | 247.69 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 201 | 0 | 22 Jan 2022 | SNS INFRA | Wing-1 Substructure RCC Work | RCC Work -Dld | No. | 1 | 700000 | 700000 | 126000 | 826000 | 0 | 1 | 700000 | 126000 | 826000 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 01 Feb 2022 |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 202 | 1 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Carpentary work (L)-BC | No. | 1 | 278313 | 278313 | 0 | 278313 | 2.5 | 1 | 278313 | 0 | 278313 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 202 | 1 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Carpentary work (L)-BC | No. | 1 | 368251 | 368251 | 0 | 368251 | 2.5 | 1 | 368251 | 0 | 368251 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 202 | 3 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Carpentary work (L)-BC | No. | 1 | 1100000 | 1100000 | 0 | 1100000 | 2.5 | 1 | 1100000 | 0 | 1100000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 202 | 6 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Misclaneous Work | Labour Lumsum | No. | 1 | 2000 | 2000 | 0 | 2000 | 0 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 202 | 4 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Carpentary work (L)-BC | No. | 0 | 1500000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA CHOUGULE | 20 Aug 2022
GANGA ASMI | 202 | 3 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Carpentary work (L)-BC | No. | 1 | 1500000 | 1500000 | 0 | 1500000 | 2.5 | 1 | 1500000 | 0 | 1500000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 202 | 5 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Labour Lumsum | No. | 1 | 4000 | 4000 | 0 | 4000 | 2.5 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 202 | 2 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Carpentary work (L)-BC | No. | 1 | 1281329 | 1281329 | 0 | 1281329 | 2.5 | 1 | 1281329 | 0 | 1281329 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 202 | 0 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Carpentary work (L)-BC | No. | 0 | 1000000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | skmishra | 11 Mar 2022
GANGA ASMI | 202 | 4 | 27 Jan 2022 | LAXMI FURNITURE | Goel House Carpentary Work | Carpentary work (L)-BC | No. | 1 | 1500000 | 1500000 | 0 | 1500000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royal Paint (Patta) | R.Ft | 0 | 27.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Groove | R.Ft | 113.46 | 82.8 | 9394.49 | 0 | 9394.49 | 2.5 | 113.46 | 9394.49 | 1691 | 11085.49 | 0 | -1691 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 5 | 27 Jan 2022 | UMESH YADAV | Goel House Lashkar Police Station Painting | Lumpsum work- DCW | No. | 1 | 5000 | 5000 | 900 | 5900 | 2.5 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Mar 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 193.31 | 87.4 | 16895.29 | 0 | 16895.29 | 2.5 | 193.31 | 16895.29 | 3041.16 | 19936.45 | 0 | -3041.16 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Lambi + Primer Paint | Sq.Ft | 112.58 | 9.2 | 1035.74 | 0 | 1035.74 | 2.5 | 112.58 | 1035.74 | 186.44 | 1222.18 | 0 | -186.44 | for Room no: 5 | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Groove | R.Ft | 1301.23 | 82.8 | 107741.84 | 0 | 107741.84 | 2.5 | 1301.23 | 107741.84 | 19393.54 | 127135.38 | 0 | -19393.54 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Patta | R.Ft | 199.55 | 101.2 | 20194.46 | 0 | 20194.46 | 2.5 | 199.55 | 20194.46 | 3635 | 23829.46 | 0 | -3635 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Groove | R.Ft | 42 | 82.8 | 3477.6 | 0 | 3477.6 | 2.5 | 41.9928 | 3477 | 0 | 3477 | 0.0072 | 0.6 |  | 99.9829 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Patt | R.Ft | 16.98 | 142.6 | 2421.35 | 0 | 2421.35 | 2.5 | 16.9776 | 2421.01 | 0 | 2421.01 | 0.0024 | 0.34 |  | 99.9859 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U | Sq.Ft | 132.5 | 184 | 24380 | 0 | 24380 | 2.5 | 132.5 | 24380 | 0 | 24380 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Groove | R.Ft | 14.6 | 55.2 | 805.92 | 0 | 805.92 | 2.5 | 14.6 | 805.92 | 145.06 | 950.98 | 0 | -145.06 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 0 | 87.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Patt | R.Ft | 0 | 142.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish Groove | R.Ft | 54.74 | 55.2 | 3021.65 | 0 | 3021.65 | 2.5 | 54.7283 | 3021 | 0 | 3021 | 0.0117 | 0.65 |  | 99.9786 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | UV Ultraviolet Lipping | R.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Groove | R.Ft | 0 | 55.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 0 | 87.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 5 | 27 Jan 2022 | UMESH YADAV | Goel House Out house Painting | Lumpsum work- DCW | No. | 1 | 3000 | 3000 | 540 | 3540 | 2.5 | 1 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Mar 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish | Sq.Ft | 570.43 | 193.2 | 110207.08 | 0 | 110207.08 | 2.5 | 570.4296 | 110207 | 0 | 110207 | 0.0004 | 0.08 |  | 99.9999 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royal Paint (Patta) | R.Ft | 17.99 | 27.6 | 496.52 | 0 | 496.52 | 2.5 | 17.99 | 496.52 | 89.38 | 585.9 | 0 | -89.38 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royal Paint (Patta) | R.Ft | 251.23 | 27.6 | 6933.95 | 0 | 6933.95 | 2.5 | 251.1957 | 6933 | 0 | 6933 | 0.0343 | 0.95 |  | 99.9863 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 96.24 | 119.6 | 11510.3 | 0 | 11510.3 | 2.5 | 96.24 | 11510.3 | 2071.86 | 13582.16 | 0 | -2071.86 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Patta | R.Ft | 0 | 101.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish Groove | R.Ft | 65.73 | 55.2 | 3628.3 | 0 | 3628.3 | 2.5 | 65.7246 | 3628 | 0 | 3628 | 0.0054 | 0.3 |  | 99.9918 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royal Paint (Patta) | R.Ft | 59.32 | 27.6 | 1637.23 | 0 | 1637.23 | 2.5 | 59.32 | 1637.23 | 294.7 | 1931.93 | 0 | -294.7 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Lambi + Primer Paint | Sq.Ft | 236.21 | 18.4 | 4346.26 | 0 | 4346.26 | 2.5 | 236.1957 | 4346 | 0 | 4346 | 0.0143 | 0.26 |  | 99.9939 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U | Sq.Ft | 118.08 | 285.2 | 33676.42 | 0 | 33676.42 | 2.5 | 118.08 | 33676.42 | 6061.76 | 39738.18 | 0 | -6061.76 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U. Polish-AIE | Sq.Ft | 0 | 193.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 988.4 | 87.4 | 86386.16 | 0 | 86386.16 | 2.5 | 988.3982 | 86386 | 0 | 86386 | 0.0018 | 0.16 |  | 99.9998 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Groove | R.Ft | 7.16 | 82.8 | 592.85 | 0 | 592.85 | 2.5 | 7.16 | 592.85 | 106.72 | 699.57 | 0 | -106.72 | for Room no: 5 | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Patta | R.Ft | 0 | 101.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royal Paint (Patta) | R.Ft | 0 | 27.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 0 | 87.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U. Polish-AIE | Sq.Ft | 139.95 | 193.2 | 27038.34 | 0 | 27038.34 | 2.5 | 139.95 | 27038.34 | 4866.9 | 31905.24 | 0 | -4866.9 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 86.45 | 119.6 | 10339.42 | 0 | 10339.42 | 2.5 | 86.45 | 10339.42 | 1861.1 | 12200.52 | 0 | -1861.1 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U. Polish-AIE | Sq.Ft | 0 | 193.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish patta | R.Ft | 99.96 | 101.2 | 10115.95 | 0 | 10115.95 | 2.5 | 99.9506 | 10115 | 0 | 10115 | 0.0094 | 0.95 |  | 99.9906 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 450.46 | 87.4 | 39370.2 | 0 | 39370.2 | 2.5 | 450.4577 | 39370 | 0 | 39370 | 0.0023 | 0.2 |  | 99.9995 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Patta | R.Ft | 0 | 101.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Groove | R.Ft | 30.47 | 55.2 | 1681.94 | 0 | 1681.94 | 2.5 | 30.4529 | 1681 | 0 | 1681 | 0.0171 | 0.94 |  | 99.9439 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Patt | R.Ft | 0 | 142.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Patta | R.Ft | 217.4 | 101.2 | 22000.88 | 0 | 22000.88 | 2.5 | 217.4 | 22000.88 | 3960.16 | 25961.04 | 0 | -3960.16 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Patta | R.Ft | 1245.47 | 101.2 | 126041.56 | 0 | 126041.56 | 2.5 | 1245.4644 | 126041 | 0 | 126041 | 0.0056 | 0.57 |  | 99.9996 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U. Polish-AIE | Sq.Ft | 132.57 | 193.2 | 25612.52 | 0 | 25612.52 | 2.5 | 132.57 | 25612.52 | 4610.26 | 30222.78 | 0 | -4610.26 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | UV Ultraviolet Lipping | R.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 2531.11 | 87.4 | 221219.01 | 0 | 221219.01 | 2.5 | 2531.11 | 221219.01 | 39819.42 | 261038.43 | 0 | -39819.42 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 0 | 44.16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Groove | R.Ft | 0 | 55.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | External Paint DCW - | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | External Apex paint (RA NO- 8) | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Duco Paint | Sq.Ft | 241.58 | 193.2 | 46673.26 | 0 | 46673.26 | 2.5 | 241.5787 | 46673 | 0 | 46673 | 0.0013 | 0.25 |  | 99.9995 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U | Sq.Ft | 160.81 | 285.2 | 45863.01 | 0 | 45863.01 | 2.5 | 160.81 | 45863.01 | 0 | 45863.01 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U. Polish-AIE | Sq.Ft | 709.82 | 193.2 | 137137.22 | 0 | 137137.22 | 2.5 | 709.8188 | 137136.99 | 0 | 137136.99 | 0.0012 | 0.23 |  | 99.9998 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U | Sq.Ft | 56.15 | 285.2 | 16013.98 | 0 | 16013.98 | 2.5 | 56.15 | 16013.98 | 2882.52 | 18896.5 | 0 | -2882.52 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Duco Paint Patta 3"- ARW | R.Ft | 782.5 | 101.2 | 79189 | 0 | 79189 | 2.5 | 782.5 | 79189 | 0 | 79189 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U | Sq.Ft | 0 | 285.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Oil Paint | Sq.Ft | 0 | 25.76 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | UTI. Water treatment plant | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | UV Ultraviolet Patta | R.Ft | 0 | 210 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Lambi + Primer Paint | Sq.Ft | 247.85 | 18.4 | 4560.44 | 0 | 4560.44 | 2.5 | 247.8261 | 4560 | 0 | 4560 | 0.0239 | 0.44 |  | 99.9904 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Satin Mat Paint | Sq.Ft | 0 | 27.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 522.13 | 44.16 | 23057.26 | 0 | 23057.26 | 2.5 | 522.13 | 23057.26 | 4150.3 | 27207.56 | 0 | -4150.3 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Primer Coat | Sq.Ft | 0 | 9.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Groove | R.Ft | 613.62 | 55.2 | 33871.82 | 0 | 33871.82 | 2.5 | 613.62 | 33871.82 | 6096.92 | 39968.74 | 0 | -6096.92 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Primer Coat | Sq.Ft | 3222.03 | 9.2 | 29642.68 | 0 | 29642.68 | 2.5 | 3221.9565 | 29642 | 0 | 29642 | 0.0735 | 0.68 |  | 99.9977 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | UV Ultraviolet Patta | R.Ft | 0 | 210 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 320.29 | 44.16 | 14144.01 | 0 | 14144.01 | 2.5 | 320.29 | 14144.01 | 2545.92 | 16689.93 | 0 | -2545.92 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Patt | R.Ft | 275.5 | 142.6 | 39286.3 | 0 | 39286.3 | 2.5 | 275.4979 | 39286 | 0 | 39286 | 0.0021 | 0.3 |  | 99.9992 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 0 | 44.16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 920.31 | 44.16 | 40640.89 | 0 | 40640.89 | 2.5 | 920.2899 | 40640 | 0 | 40640 | 0.0201 | 0.89 |  | 99.9978 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 577.29 | 44.16 | 25493.13 | 0 | 25493.13 | 2.5 | 577.29 | 25493.13 | 4588.76 | 30081.89 | 0 | -4588.76 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Duco Paint Patta 3"- ARW | R.Ft | 277.2 | 101.2 | 28052.64 | 0 | 28052.64 | 2.5 | 277.2 | 28052.64 | 5049.48 | 33102.12 | 0 | -5049.48 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 0 | 44.16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Apex Exterior Paint | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 196.23 | 87.4 | 17150.5 | 0 | 17150.5 | 2.5 | 196.2243 | 17150 | 0 | 17150 | 0.0057 | 0.5 |  | 99.9971 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Groove | R.Ft | 0 | 55.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish | Sq.Ft | 353.56 | 193.2 | 68307.79 | 0 | 68307.79 | 2.5 | 353.5559 | 68307 | 0 | 68307 | 0.0041 | 0.79 |  | 99.9988 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Patta | R.Ft | 1026.45 | 101.2 | 103876.74 | 0 | 103876.74 | 2.5 | 1026.45 | 103876.74 | 18697.82 | 122574.56 | 0 | -18697.82 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U | Sq.Ft | 57.15 | 285.2 | 16299.18 | 0 | 16299.18 | 2.5 | 57.1494 | 16299.01 | 0 | 16299.01 | 0.0006 | 0.17 |  | 99.999 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Groove | R.Ft | 20 | 64.4 | 1288 | 0 | 1288 | 2.5 | 20 | 1288 | 0 | 1288 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish | Sq.Ft | 1286.87 | 193.2 | 248623.28 | 0 | 248623.28 | 2.5 | 1286.8685 | 248622.99 | 0 | 248622.99 | 0.0015 | 0.29 |  | 99.9999 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Patta | R.Ft | 258.19 | 101.2 | 26128.83 | 0 | 26128.83 | 2.5 | 258.19 | 26128.83 | 4703.18 | 30832.01 | 0 | -4703.18 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish | Sq.Ft | 194.75 | 193.2 | 37625.7 | 0 | 37625.7 | 2.5 | 194.7464 | 37625 | 0 | 37625 | 0.0036 | 0.7 |  | 99.9982 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 132.46 | 87.4 | 11577 | 0 | 11577 | 2.5 | 132.46 | 11577 | 2083.86 | 13660.86 | 0 | -2083.86 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 213.64 | 119.6 | 25551.34 | 0 | 25551.34 | 2.5 | 213.64 | 25551.34 | 4599.24 | 30150.58 | 0 | -4599.24 | for Room no: 5 | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 150.77 | 44.16 | 6658 | 0 | 6658 | 2.5 | 150.7699 | 6658 | 0 | 6658 | 0.0001 | 0 |  | 99.9999 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royal Paint (Patta) | R.Ft | 171.14 | 27.6 | 4723.46 | 0 | 4723.46 | 2.5 | 171.1232 | 4723 | 0 | 4723 | 0.0168 | 0.46 |  | 99.9902 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U Polish Libbing | R.Ft | 1456.96 | 87.4 | 127338.3 | 0 | 127338.3 | 2.5 | 1456.96 | 127338.3 | 22920.9 | 150259.2 | 0 | -22920.9 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 0 | 142.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 1324.01 | 44.16 | 58468.28 | 0 | 58468.28 | 2.5 | 1324.0036 | 58468 | 0 | 58468 | 0.0064 | 0.28 |  | 99.9995 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 116.18 | 142.6 | 16567.27 | 0 | 16567.27 | 2.5 | 116.1781 | 16567 | 0 | 16567 | 0.0019 | 0.27 |  | 99.9984 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish patta | R.Ft | 757 | 101.2 | 76608.4 | 0 | 76608.4 | 2.5 | 756.996 | 76608 | 0 | 76608 | 0.004 | 0.4 |  | 99.9995 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 0 | 142.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royal Paint (Patta) | R.Ft | 65.12 | 27.6 | 1797.31 | 0 | 1797.31 | 2.5 | 65.12 | 1797.31 | 323.52 | 2120.83 | 0 | -323.52 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U | Sq.Ft | 245.88 | 285.2 | 70124.98 | 0 | 70124.98 | 2.5 | 245.88 | 70124.98 | 12622.5 | 82747.48 | 0 | -12622.5 | for Room no: 5 | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Groove | R.Ft | 0 | 82.8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | skmishra | 09 Mar 2022
GANGA ASMI | 203 | 0 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish | Sq.Ft | 298.2 | 193.2 | 57612.24 | 0 | 57612.24 | 2.5 | 298.1988 | 57612.01 | 0 | 57612.01 | 0.0012 | 0.23 |  | 99.9996 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Groove | R.Ft | 104.1 | 82.8 | 8619.48 | 0 | 8619.48 | 2.5 | 104.0942 | 8619 | 0 | 8619 | 0.0058 | 0.48 |  | 99.9944 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish Groove | R.Ft | 226.4 | 55.2 | 12497.28 | 0 | 12497.28 | 2.5 | 226.3949 | 12497 | 0 | 12497 | 0.0051 | 0.28 |  | 99.9977 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish patta | R.Ft | 369.64 | 101.2 | 37407.57 | 0 | 37407.57 | 2.5 | 369.6344 | 37407 | 0 | 37407 | 0.0056 | 0.57 |  | 99.9985 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 35.4 | 87.4 | 3093.96 | 0 | 3093.96 | 2.5 | 35.389 | 3093 | 0 | 3093 | 0.011 | 0.96 |  | 99.9689 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | UV Ultraviolet | Sq.Ft | 0 | 410 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | UV Ultraviolet | Sq.Ft | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Scaffolding & Removing | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | B.C. Building Common Items | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 4 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Labour Painting Lumpsum -BC - | No. | 1 | 435762 | 435762 | 0 | 435762 | 2.5 | 1 | 435762 | 78437.16 | 514199.16 | 0 | -78437.16 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour PU Big Moulding | R.Ft | 39.52 | 92 | 3635.84 | 0 | 3635.84 | 2.5 | 39.5109 | 3635 | 0 | 3635 | 0.0091 | 0.84 |  | 99.977 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 151.37 | 44.16 | 6684.5 | 0 | 6684.5 | 2.5 | 151.3587 | 6684 | 0 | 6684 | 0.0113 | 0.5 |  | 99.9925 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Patt | R.Ft | 35.12 | 142.6 | 5008.11 | 0 | 5008.11 | 2.5 | 35.12 | 5008.11 | 901.46 | 5909.57 | 0 | -901.46 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Patt | R.Ft | 166.91 | 142.6 | 23801.37 | 0 | 23801.37 | 2.5 | 166.91 | 23801.37 | 4284.24 | 28085.61 | 0 | -4284.24 | for Room no: 5 | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Patt | R.Ft | 268.56 | 142.6 | 38296.66 | 0 | 38296.66 | 2.5 | 268.56 | 38296.66 | 6893.4 | 45190.06 | 0 | -6893.4 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 187.4 | 87.4 | 16378.76 | 0 | 16378.76 | 2.5 | 187.3913 | 16378 | 0 | 16378 | 0.0087 | 0.76 |  | 99.9954 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 284.76 | 44.16 | 12575 | 0 | 12575 | 2.5 | 284.76 | 12575 | 0 | 12575 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish patta | R.Ft | 1920.52 | 101.2 | 194356.62 | 0 | 194356.62 | 2.5 | 1920.5138 | 194356 | 0 | 194356 | 0.0062 | 0.63 |  | 99.9997 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Lambi + Primer Paint | Sq.Ft | 87.74 | 9.2 | 807.21 | 0 | 807.21 | 2.5 | 87.74 | 807.21 | 145.3 | 952.51 | 0 | -145.3 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Duco Paint | Sq.Ft | 258.43 | 193.2 | 49928.68 | 0 | 49928.68 | 2.5 | 258.43 | 49928.68 | 8987.16 | 58915.84 | 0 | -8987.16 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 2 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U. Polish-AIE | Sq.Ft | 0 | 193.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Mar 2022 |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U. Polish-AIE | Sq.Ft | 1488.81 | 193.2 | 287638.09 | 0 | 287638.09 | 2.5 | 1488.81 | 287638.09 | 51774.86 | 339412.95 | 0 | -51774.86 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | P.U. Polish-AIE | Sq.Ft | 231.19 | 193.2 | 44665.91 | 0 | 44665.91 | 2.5 | 231.19 | 44665.91 | 8039.86 | 52705.77 | 0 | -8039.86 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 3 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | Royale Paint | Sq.Ft | 496.06 | 44.16 | 21906.01 | 0 | 21906.01 | 2.5 | 496.06 | 21906.01 | 3943.08 | 25849.09 | 0 | -3943.08 |  | 100 |  | AVINASH PADMANABHAN | Swapnil Erande | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA Colour P.U Libbing | R.Ft | 490.49 | 142.6 | 69943.87 | 0 | 69943.87 | 2.5 | 490.4839 | 69943 | 0 | 69943 | 0.0061 | 0.87 |  | 99.9988 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 203 | 1 | 27 Jan 2022 | UMESH YADAV | Goel House Painting Work | ICA P.U Polish patta | R.Ft | 527.42 | 101.2 | 53374.9 | 0 | 53374.9 | 2.5 | 527.4111 | 53374 | 0 | 53374 | 0.0089 | 0.9 |  | 99.9983 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Mar 2022 |  | 10 PAINTING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 204 | 0 | 28 Jan 2022 | SHREE MAHALAXMI CRANE SERVICES | Weigh Bridge Unloading&Placing | Crane charges | Day | 1 | 7800 | 7800 | 1404 | 9204 | 0 | 0.8125 | 6337.5 | 0 | 6337.5 | 0.1875 | 2866.5 |  | 81.25 |  | Dushant Gore | chetan.jewalikar | construction open | 28 Jan 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Profile Light Cutting | R.Ft | 73 | 125 | 9125 | 0 | 9125 | 2.5 | 73 | 9125 | 0 | 9125 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 4 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (L) | Sq.Ft | 160 | 150 | 24000 | 0 | 24000 | 2.5 | 160 | 24000 | 0 | 24000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 13.25 | 125 | 1656.25 | 0 | 1656.25 | 2.5 | 13.25 | 1656.25 | 0 | 1656.25 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (M+L) | Sq.Ft | 60 | 150 | 9000 | 0 | 9000 | 2.5 | 0 | 0 | 0 | 0 | 60 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling Grove | R.Ft | 18.75 | 15 | 281.25 | 0 | 281.25 | 2.5 | 18.7333 | 281 | 0 | 281 | 0.0167 | 0.25 |  | 99.9109 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Sheet Fixing for Floor Protection | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | MKT. Marketing Infrastructure | Cancelled | Dushant Gore | 30 Aug 2022
GANGA ASMI | 205 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Light Gala Cutting- SOf | No. | 5 | 60 | 300 | 0 | 300 | 0 | 5 | 300 | 0 | 300 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (L) | Sq.Ft | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (L) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 266 | 125 | 33250 | 0 | 33250 | 2.5 | 0 | 0 | 0 | 0 | 266 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | POP Wall Mounting- AIE | Sq.Ft | 583.75 | 35 | 20431.25 | 0 | 20431.25 | 2.5 | 583.75 | 20431.25 | 0 | 20431.25 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | A/C Grill Gala Cutting | No. | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | POP Wall Mounting- AIE | Sq.Ft | 567.25 | 35 | 19853.75 | 0 | 19853.75 | 2.5 | 0 | 0 | 0 | 0 | 567.25 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Light Gala Cutting- SOf | No. | 39 | 60 | 2340 | 0 | 2340 | 2.5 | 39 | 2340 | 0 | 2340 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | POP Wall Mounting- AIE | Sq.Ft | 151 | 35 | 5285 | 0 | 5285 | 2.5 | 151 | 5285 | 0 | 5285 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | A/C Grill Gala Cutting | No. | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling Grove | R.Ft | 165.75 | 15 | 2486.25 | 0 | 2486.25 | 2.5 | 165.7333 | 2486 | 0 | 2486 | 0.0167 | 0.25 |  | 99.9899 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 21.25 | 125 | 2656.25 | 0 | 2656.25 | 2.5 | 21.25 | 2656.25 | 0 | 2656.25 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 79.5 | 75 | 5962.5 | 0 | 5962.5 | 2.5 | 79.5 | 5962.5 | 0 | 5962.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 119.75 | 125 | 14968.75 | 0 | 14968.75 | 2.5 | 0 | 0 | 0 | 0 | 119.75 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling Grove | R.Ft | 147 | 15 | 2205 | 0 | 2205 | 2.5 | 147 | 2205 | 0 | 2205 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling Grove | R.Ft | 97.5 | 15 | 1462.5 | 0 | 1462.5 | 2.5 | 97.4667 | 1462 | 0 | 1462 | 0.0333 | 0.5 |  | 99.9658 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | POP Wall Mounting- AIE | Sq.Ft | 65.25 | 35 | 2283.75 | 0 | 2283.75 | 2.5 | 0 | 0 | 0 | 0 | 65.25 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 513 | 125 | 64125 | 0 | 64125 | 2.5 | 513 | 64125 | 0 | 64125 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling Grove | R.Ft | 126 | 15 | 1890 | 0 | 1890 | 2.5 | 126 | 1890 | 0 | 1890 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (L) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | skmishra | 09 Mar 2022
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Light Gala Cutting- SOf | No. | 3 | 60 | 180 | 0 | 180 | 2.5 | 3 | 180 | 0 | 180 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 99.25 | 125 | 12406.25 | 0 | 12406.25 | 2.5 | 99.25 | 12406.25 | 0 | 12406.25 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling - BC | Sq.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 365 | 125 | 45625 | 0 | 45625 | 2.5 | 365 | 45625 | 0 | 45625 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Light Gala Cutting- SOf | No. | 16 | 60 | 960 | 0 | 960 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Cotton Ceiling | Sq.Ft | 28.5 | 50 | 1425 | 0 | 1425 | 2.5 | 0 | 0 | 0 | 0 | 28.5 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Sheet Fixing for Floor Protection | Sq.Ft | 475 | 5 | 2375 | 0 | 2375 | 2.5 | 0 | 0 | 0 | 0 | 475 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Cotton Ceiling | Sq.Ft | 33 | 50 | 1650 | 0 | 1650 | 2.5 | 0 | 0 | 0 | 0 | 33 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 4 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Light Gala Cutting- SOf | No. | 8 | 60 | 480 | 0 | 480 | 2.5 | 8 | 480 | 0 | 480 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Labour Lumpsum - SOS | No. | 4 | 500 | 2000 | 0 | 2000 | 2.5 | 4 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Board False Ceiling (L) | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | skmishra | 09 Mar 2022
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (L) | Sq.Ft | 45.5 | 60 | 2730 | 0 | 2730 | 2.5 | 0 | 0 | 0 | 0 | 45.5 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Light Gala Cutting- SOf | No. | 12 | 60 | 720 | 0 | 720 | 2.5 | 12 | 720 | 0 | 720 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Wall Finishing | R.Ft | 70 | 20 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 70 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 3 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (L) | Sq.Ft | 196 | 150 | 29400 | 0 | 29400 | 2.5 | 0 | 0 | 0 | 0 | 196 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | A/C Grill Gala Cutting | No. | 2 | 1000 | 2000 | 0 | 2000 | 2.5 | 2 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Light Gala Cutting- SOf | No. | 10 | 60 | 600 | 0 | 600 | 2.5 | 10 | 600 | 0 | 600 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Touch up | R.Ft | 19 | 35 | 665 | 0 | 665 | 2.5 | 19 | 665 | 0 | 665 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (M+L) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | MKT. Marketing Infrastructure | Cancelled | Dushant Gore | 30 Aug 2022
GANGA ASMI | 205 | 4 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Labour Lumpsum - SOS | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 205 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Breaking Work - Dld | Sq.Ft | 601.5 | 15 | 9022.5 | 0 | 9022.5 | 0 | 601.4667 | 9022 | 0 | 9022 | 0.0333 | 0.5 |  | 99.9945 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 205 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling - BC | Sq.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | skmishra | 09 Mar 2022
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling - BC | Sq.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling - BC | Sq.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling - BC | Sq.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 205 | 2 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling - BC | Sq.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 206 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Board False Ceiling (M+L) | Sq.Ft | 176.5 | 75 | 13237.5 | 0 | 13237.5 | 2.5 | 176.4933 | 13237 | 0 | 13237 | 0.0067 | 0.5 |  | 99.9962 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 206 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | POP False Ceiling (m+l) | Sq.Ft | 565 | 30 | 16950 | 0 | 16950 | 2.5 | 565 | 16950 | 0 | 16950 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | DEV. Podium | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 206 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Touchup | R.Ft | 25 | 125 | 3125 | 0 | 3125 | 2.5 | 25 | 3125 | 0 | 3125 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 206 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling (M+L)- AIE | Sq.Ft | 127.19 | 140 | 17806.6 | 0 | 17806.6 | 2.5 | 127.1857 | 17806 | 0 | 17806 | 0.0043 | 0.6 |  | 99.9966 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 206 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling (M+L)- AIE | Sq.Ft | 1341.5 | 125 | 167687.5 | 0 | 167687.5 | 0 | 1341.496 | 167687 | 0 | 167687 | 0.004 | 0.5 |  | 99.9997 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 206 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | POP (L+M) | Sq.Ft | 70 | 35 | 2450 | 0 | 2450 | 2.5 | 70 | 2450 | 0 | 2450 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 206 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum Ceiling - BC | Sq.Ft | 315.5 | 125 | 39437.5 | 0 | 39437.5 | 2.5 | 315.496 | 39437 | 0 | 39437 | 0.004 | 0.5 |  | 99.9987 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 206 | 1 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Grid False Ceiling (M+L) | Sq.Ft | 108 | 175 | 18900 | 0 | 18900 | 2.5 | 108 | 18900 | 0 | 18900 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 206 | 0 | 28 Jan 2022 | NA DECORATES | Goel House Gypsum Work | Gypsum on Wall | Sq.Ft | 531 | 20 | 10620 | 0 | 10620 | 2.5 | 531 | 10620 | 0 | 10620 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | 05 GYPSUM & PLASTER | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 207 | 0 | 28 Jan 2022 | YOGESH BALU ICHAKE | Wing-1 Substructure Line Out Work Site Visit Survey | Total Station Point marking- | Day | 3 | 4500 | 13500 | 0 | 13500 | 0 | 3 | 13500 | 0 | 13500 | 0 | 0 |  | 100 |  | Dushant gore | chetan.jewalikar | construction open | 28 Jan 2022 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 208 | 4 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Fabrication rennovation work | GI Sheet Fixing | Sq.Ft | 1243 | 5 | 6215 | 1118.7 | 7333.7 | 2.5 | 1243 | 6215 | 1118.7 | 7333.7 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 5 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Outhouse Add. Fabrication work | Fabrication Work (L) | Kgs | 1881.16 | 21 | 39504.36 | 7110.78 | 46615.14 | 2.5 | 1532.4762 | 32182 | 5792.76 | 37974.76 | 348.6838 | 8640.38 | Above Fabrication charges including Crane. | 81.4644 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 1 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Store shade making work | Fabrication work (L) | Kgs | 990 | 22 | 21780 | 3920.4 | 25700.4 | 2.5 | 772.6364 | 16998 | 3059.64 | 20057.64 | 217.3636 | 5642.76 |  | 78.0441 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 0 | 29 Jan 2022 | PATILS FABRICATORS | Goel House DG Room GI Shutter patti fixing work | Removing work.-SOS | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 1 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | dushant gore | Swapnil Erande | construction open | 29 Jan 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 0 | 29 Jan 2022 | PATILS FABRICATORS | Goel House DG Room GI Shutter patti fixing work | Fabrication work (L) | Kgs | 480 | 31.25 | 15000 | 2700 | 17700 | 2.5 | 480 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | dushant gore | Swapnil Erande | construction open | 29 Jan 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 0 | 29 Jan 2022 | PATILS FABRICATORS | Goel House DG Room GI Shutter patti fixing work | Tapping Screw- Den | No. | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 29 Jan 2022 |  | DEV. Entrance Gate | Cancelled | skmishra | 29 Jan 2022
GANGA ASMI | 208 | 5 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Outhouse Add. Fabrication work | Deck Sheet (L) | Kgs | 800 | 10 | 8000 | 1440 | 9440 | 2.5 | 409 | 4090 | 736.2 | 4826.2 | 391 | 4613.8 |  | 51.125 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pargola Gas Cutting | Department Labour - DEn | No. | 5 | 800 | 4000 | 720 | 4720 | 0 | 5 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 4 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Fabrication rennovation work | Fabrication work (L) | Kgs | 334 | 17 | 5678 | 1022.04 | 6700.04 | 2.5 | 334 | 5678 | 1022.04 | 6700.04 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pargola Gas Cutting | Department Labour - DEn | No. | 16 | 700 | 11200 | 2016 | 13216 | 0 | 16 | 11200 | 2016 | 13216 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 1 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Store shade making work | Sheet Fixing-SOS | Sq.Ft | 2000 | 6 | 12000 | 2160 | 14160 | 2.5 | 1774 | 10644 | 1915.92 | 12559.92 | 226 | 1600.08 |  | 88.7 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pargola Gas Cutting | Gas Cutting Work | Day | 6 | 8400 | 50400 | 9072 | 59472 | 0 | 6 | 50400 | 9072 | 59472 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 0 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Store shade making work | Fabrication work (L) | Kgs | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 29 Jan 2022 |  | Admin. Direct Expenses | Cancelled | Dushant Gore | 22 Feb 2022
GANGA ASMI | 208 | 3 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Fabrication rennovation work | Fabrication removing work Lumpsum | No. | 1 | 21000 | 21000 | 3780 | 24780 | 0 | 1 | 21000 | 3780 | 24780 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Jan 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 208 | 6 | 29 Jan 2022 | PATILS FABRICATORS | GH Rain Water Gutter Making Work - 1 No. | GI Gutter Sheet (L) | Sq.Ft | 204 | 50 | 10200 | 1836 | 12036 | 2.5 | 0 | 0 | 0 | 0 | 204 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 3 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Outhouse Add. Fabrication work | MS Angle 50 x 50 x 5mm | Kgs | 19 | 60 | 1140 | 205.2 | 1345.2 | 0 | 11.4 | 684 | 123.12 | 807.12 | 7.6 | 538.08 |  | 60 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 0 | 29 Jan 2022 | PATILS FABRICATORS | Goel House DG Room GI Shutter patti fixing work | Fabrication work (M) | Kgs | 480 | 120 | 57600 | 10368 | 67968 | 0 | 480 | 57600 | 10368 | 67968 | 0 | 0 |  | 100 |  | dushant gore | Swapnil Erande | construction open | 29 Jan 2022 |  | Admin. Direct Expenses | Approved | Dushant Gore | 19 Jul 2022
GANGA ASMI | 209 | 3 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Outhouse Add. Fabrication work | 125 I Section (M) | Kgs | 655 | 60 | 39300 | 7074 | 46374 | 0 | 595.0667 | 35704 | 6426.72 | 42130.72 | 59.9333 | 4243.28 |  | 90.8499 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Pipe (M) | Kgs | 34.95 | 75 | 2621.25 | 471.82 | 3093.07 | 0 | 17.7467 | 1331 | 239.58 | 1570.58 | 17.2033 | 1522.49 |  | 50.7774 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 19 Jul 2022
GANGA ASMI | 209 | 0 | 29 Jan 2022 | PATILS FABRICATORS | Goel House DG Room GI Shutter patti fixing work | Tapping Screw- Den | No. | 1000 | 2 | 2000 | 360 | 2360 | 0 | 1000 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | dushant gore | Swapnil Erande | construction open | 29 Jan 2022 |  | DEV. Entrance Gate | Approved | Dushant Gore | 19 Jul 2022
GANGA ASMI | 209 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | M.S. Plate (M+L)-Mkt | Kgs | 5 | 100 | 500 | 90 | 590 | 0 | 5 | 500 | 90 | 590 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 3 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Outhouse Add. Fabrication work | 200 I Section (M) | Kgs | 1115 | 60 | 66900 | 12042 | 78942 | 0 | 937.4167 | 56245 | 10124.1 | 66369.1 | 177.5833 | 12572.9 |  | 84.0732 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Square Pipe (M) | Kgs | 144.12 | 75 | 10809 | 1945.62 | 12754.62 | 0 | 144.12 | 10809 | 1945.62 | 12754.62 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 19 Jul 2022
GANGA ASMI | 209 | 3 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Outhouse Add. Fabrication work | MS Plate (M) | Kgs | 92.16 | 75 | 6912 | 1244.16 | 8156.16 | 0 | 61.4 | 4605 | 828.9 | 5433.9 | 30.76 | 2722.26 |  | 66.6233 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 4 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Gym Work | Fabrication Work (M) | Kgs | 236 | 65 | 15340 | 2761.2 | 18101.2 | 0 | 236 | 15340 | 2761.2 | 18101.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Square Pipe (M) | Kgs | 25.98 | 75 | 1948.5 | 350.74 | 2299.24 | 0 | 25.98 | 1948.5 | 350.74 | 2299.24 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 19 Jul 2022
GANGA ASMI | 209 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Square Pipe (M) | Kgs | 225.9 | 75 | 16942.5 | 3049.66 | 19992.16 | 0 | 225.9 | 16942.5 | 3049.66 | 19992.16 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 19 Jul 2022
GANGA ASMI | 209 | 2 | 29 Jan 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Square Pipe (M) | Kgs | 536.33 | 75 | 40224.75 | 7240.46 | 47465.21 | 2.5 | 536.33 | 40224.75 | 7240.46 | 47465.21 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Dushant Gore | 19 Jul 2022
GANGA ASMI | 209 | 3 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Outhouse Add. Fabrication work | Deck Sheet (M) | Kgs | 800 | 75 | 60000 | 10800 | 70800 | 0 | 409 | 30675 | 5521.5 | 36196.5 | 391 | 34603.5 |  | 51.125 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 1 | 29 Jan 2022 | PATILS FABRICATORS | Goel House Store shade making work | Fabrication work (M) | Kgs | 990 | 72 | 71280 | 12830.4 | 84110.4 | 0 | 772.6667 | 55632 | 10013.76 | 65645.76 | 217.3333 | 18464.64 |  | 78.0471 |  | Dushant Gore | Swapnil Erande | construction open | 29 Jan 2022 |  | Admin. Direct Expenses | Approved | Dushant Gore | 19 Jul 2022
GANGA ASMI | 209 | 5 | 29 Jan 2022 | PATILS FABRICATORS | GH Rain Water Gutter Making Work - 1 No. | GI Gutter Sheet (M) | Sq.Ft | 408 | 90 | 36720 | 6609.6 | 43329.6 | 0 | 0 | 0 | 0 | 0 | 408 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 209 | 5 | 29 Jan 2022 | PATILS FABRICATORS | GH Rain Water Gutter Making Work - 1 No. | Bracket | Kgs | 40 | 65 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Jan 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 210 | 0 | 01 Jan 2022 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 50000 | 150000 | 27000 | 177000 | 0 | 3 | 150000 | 27000 | 177000 | 0 | 0 | GANGA ASMI WAKAD HOARDING DISPLAY CHARGES @ BEFORE PROJECT FRONT + BACK BOTH SIDED DISPLAY SIZE AS 30X42 SQ FT. AS ON 01/01/2022 TO 31/03/2022 RS. 50000/- + TAX. | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 07 Feb 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 211 | 1 | 04 Feb 2022 | KHUSHI CUSHIONS WORKS | Goel House living room leather panel removing & refixing | Removing & Refixing Cushion | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 12 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 211 | 0 | 04 Feb 2022 | KHUSHI CUSHIONS WORKS | GH Ceiling Cushion Labour Charges | Ceiling Cushion - | Sq.Ft | 144 | 175 | 25200 | 0 | 25200 | 0 | 144 | 25200 | 0 | 25200 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 12 Feb 2022 |  | 09 CARPENTRY WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 211 | 1 | 04 Feb 2022 | KHUSHI CUSHIONS WORKS | Goel House living room leather panel removing & refixing | Ceiling Cushion - | Sq.Ft | 16 | 175 | 2800 | 0 | 2800 | 2.5 | 16 | 2800 | 0 | 2800 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 12 Feb 2022 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 80 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 24 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 80 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical Waterproofing (L) | Sq.Ft | 5070 | 15 | 76050 | 13689 | 89739 | 10 | 4666 | 69990 | 12598.2 | 82588.2 | 404 | 7150.8 |  | 92.0316 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 80 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 24 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 24 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 212 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (L) | R.Ft | 270 | 24 | 6480 | 1166.4 | 7646.4 | 10 | 220 | 5280 | 950.4 | 6230.4 | 50 | 1416 |  | 81.4815 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical Waterproofing (M) | Sq.Ft | 5070 | 40 | 202800 | 36504 | 239304 | 0 | 4666 | 186640 | 33595.2 | 220235.2 | 404 | 19068.8 |  | 92.0316 |  | dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment(m) - R.Ft | R.Ft | 270 | 56 | 15120 | 2721.6 | 17841.6 | 0 | 220 | 12320 | 2217.6 | 14537.6 | 50 | 3304 |  | 81.4815 |  | dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical W/P - Bco | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 213 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Waterproofing Sheet Joint Treatment (M) - R.Ft | R.Ft | 0 | 56 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | SKMISHRA | 07 Feb 2022
GANGA ASMI | 214 | 3 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing (L) | Sq.Ft | 481 | 15 | 7215 | 1298.7 | 8513.7 | 10 | 481 | 7215 | 1298.7 | 8513.7 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 2 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House Gym Work | Chemical Waterproofing (L) | Sq.Ft | 1100 | 15 | 16500 | 2970 | 19470 | 10 | 1097.0667 | 16456 | 2962.08 | 19418.08 | 2.9333 | 51.92 |  | 99.7333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing Rate Diff. (L) - Sq.Ft | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 07 Feb 2022
GANGA ASMI | 214 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing Rate Diff. (L) - Sq.Ft | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 07 Feb 2022
GANGA ASMI | 214 | 1 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Wall Crack filling and Chemical Coating (L) | Sq.Ft | 3500 | 15 | 52500 | 9450 | 61950 | 10 | 3500 | 52500 | 9450 | 61950 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing (L) | Sq.Ft | 234 | 15 | 3510 | 631.8 | 4141.8 | 10 | 0 | 0 | 0 | 0 | 234 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 214 | 4 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House (L) Gym Room Arch Chemical Waterproofing | Membrane Waterproofing (L) | Mtrs | 90.8476 | 247.5 | 22484.78 | 4047.26 | 26532.04 | 2.5 | 90.8476 | 22484.78 | 4047.26 | 26532.04 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 1 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Wall Crack filling & Chemical Coating (L) - Sq.Ft | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | ADITYA CHOUGULE | 19 Jul 2022
GANGA ASMI | 214 | 4 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House (L) Gym Room Arch Chemical Waterproofing | Membrane Waterproofing | R.Ft | 0 | 247.5 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 12 Sep 2023
GANGA ASMI | 214 | 1 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical Waterproofing (L) | Sq.Ft | 660 | 15 | 9900 | 1782 | 11682 | 10 | 660 | 9900 | 1782 | 11682 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 1 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Cementous injection grouting treatment | No. | 25 | 450 | 11250 | 2025 | 13275 | 10 | 25 | 11250 | 2025 | 13275 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 1 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | PU Injection grouting treatment | No. | 5 | 3500 | 17500 | 3150 | 20650 | 10 | 5 | 17500 | 3150 | 20650 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 2 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House Gym Work | Ghotai Plaster- BC | Sq.Ft | 700 | 15 | 10500 | 1890 | 12390 | 10 | 700 | 10500 | 0 | 10500 | 0 | 1890 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 4 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House (L) Gym Room Arch Chemical Waterproofing | Membrane Horizontal Waterproofing (L) | Sq.Ft | 519 | 13 | 6747 | 1214.46 | 7961.46 | 10 | 519 | 6747 | 1214.46 | 7961.46 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 214 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing (L) | Sq.Ft | 1296 | 15 | 19440 | 3499.2 | 22939.2 | 10 | 1058 | 15870 | 2856.6 | 18726.6 | 238 | 4212.6 |  | 81.6358 |  | dushant gore | chetan.jewalikar | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 215 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing (M) Rate Diff | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 07 Feb 2022
GANGA ASMI | 215 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing (M) | Sq.Ft | 1296 | 40 | 51840 | 9331.2 | 61171.2 | 0 | 1058 | 42320 | 7617.6 | 49937.6 | 238 | 11233.6 |  | 81.6358 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 215 | 2 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House Gym Work | Chemical Waterproofing (M) | Sq.Ft | 1100 | 40 | 44000 | 7920 | 51920 | 0 | 1097.1 | 43884 | 7899.12 | 51783.12 | 2.9 | 136.88 |  | 99.7364 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 215 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing (M) Rate Diff | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Cancelled | skmishra | 07 Feb 2022
GANGA ASMI | 215 | 4 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House (L) Gym Room Arch Chemical Waterproofing | Membrane Waterproofing (M) | R.Ft | 0 | 577.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 07 Feb 2022 |  | No category | Cancelled | DUSHANT.GORE | 12 Sep 2023
GANGA ASMI | 215 | 3 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing (M) | Sq.Ft | 481 | 40 | 19240 | 3463.2 | 22703.2 | 0 | 481 | 19240 | 3463.2 | 22703.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 215 | 1 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Chemical Waterproofing (M) | Sq.Ft | 660 | 45 | 29700 | 5346 | 35046 | 0 | 660 | 29700 | 5346 | 35046 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 215 | 4 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House (L) Gym Room Arch Chemical Waterproofing | Membrane Horizontal Waterproofing (M) | Sq.Ft | 519 | 34 | 17646 | 3176.28 | 20822.28 | 0 | 519 | 17646 | 3176.28 | 20822.28 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 215 | 0 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House -Chemical Waterproofing | Chemical Waterproofing (M) | Sq.Ft | 234 | 40 | 9360 | 1684.8 | 11044.8 | 0 | 0 | 0 | 0 | 0 | 234 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 215 | 1 | 07 Feb 2022 | AQUARIUS WATERPROOFING | GH Chemical waterproofing treatment | Wall Crack filling & Chemical Coating (M) | Sq.Ft | 3500 | 35 | 122500 | 22050 | 144550 | 0 | 3500 | 122500 | 22050 | 144550 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 215 | 4 | 07 Feb 2022 | AQUARIUS WATERPROOFING | Goel House (L) Gym Room Arch Chemical Waterproofing | Membrane Waterproofing (M). | Mtrs | 90.8476 | 577.5 | 52464.49 | 9443.6 | 61908.09 | 0 | 90.8476 | 52464.49 | 9443.6 | 61908.09 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Fix - | Sq.Ft | 0 | 1700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 2 | 300 | 600 | 0 | 600 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Skirting- | R.Ft | 141.74 | 140 | 19843.6 | 0 | 19843.6 | 2.5 | 141.74 | 19843.6 | 0 | 19843.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Chamfer Polish - BCE | R.Ft | 9.25 | 40 | 370 | 0 | 370 | 2.5 | 9.25 | 370 | 0 | 370 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Cutting & fixing | Sq.Ft | 483.71 | 125 | 60463.75 | 0 | 60463.75 | 2.5 | 483.71 | 60463.75 | 0 | 60463.75 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Breaking Work. | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble cutting work - | No. | 1 | 500 | 500 | 0 | 500 | 2.5 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Top - AIE | Sq.Ft | 0 | 1700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Kitchen Platform- cc | R.Ft | 6 | 1000 | 6000 | 0 | 6000 | 2.5 | 6 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Basin Counter | R.Ft | 7 | 1700 | 11900 | 0 | 11900 | 2.5 | 7 | 11900 | 0 | 11900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Fix - | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Material Shifting | Sq.Ft | 2411.78 | 15 | 36176.7 | 0 | 36176.7 | 0 | 2411.78 | 36176.7 | 0 | 36176.7 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Skirting- | R.Ft | 74 | 140 | 10360 | 0 | 10360 | 2.5 | 74 | 10360 | 0 | 10360 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Labour Lumpsum - SOS | No. | 1 | 2500 | 2500 | 0 | 2500 | 0 | 1 | 2500 | 0 | 2500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Kitchen Platform- cc | R.Ft | 48 | 1000 | 48000 | 0 | 48000 | 2.5 | 48 | 48000 | 0 | 48000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Material Shifting | Sq.Ft | 900 | 15 | 13500 | 0 | 13500 | 0 | 900 | 13500 | 0 | 13500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Dado Fixing | Sq.Ft | 108.25 | 45 | 4871.25 | 0 | 4871.25 | 2.5 | 108.2444 | 4871 | 0 | 4871 | 0.0056 | 0.25 |  | 99.9948 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Breaking Work -DPo | Sq.Ft | 137.87 | 30 | 4136.1 | 0 | 4136.1 | 0 | 0 | 0 | 0 | 0 | 137.87 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 9 | 35 | 315 | 0 | 315 | 2.5 | 9 | 315 | 0 | 315 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Zero Point | R.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Cutting & fixing | Sq.Ft | 43.37 | 125 | 5421.25 | 0 | 5421.25 | 2.5 | 43.368 | 5421 | 0 | 5421 | 0.002 | 0.25 |  | 99.9954 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Cutting & Fixing Work | Sq.Ft | 632 | 140 | 88480 | 0 | 88480 | 2.5 | 632 | 88480 | 0 | 88480 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble cutting work - | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | V Groove - AIE | R.Ft | 83.75 | 75 | 6281.25 | 0 | 6281.25 | 2.5 | 83.7467 | 6281 | 0 | 6281 | 0.0033 | 0.25 |  | 99.9961 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Top - AIE | R.Ft | 13 | 1700 | 22100 | 0 | 22100 | 2.5 | 0 | 0 | 0 | 0 | 13 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Labour Lumpsum - SOS | No. | 1 | 2500 | 2500 | 0 | 2500 | 0 | 1 | 2500 | 0 | 2500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Full Round Moulding & Polish | R.Ft | 87.67 | 125 | 10958.75 | 0 | 10958.75 | 2.5 | 87.67 | 10958.75 | 0 | 10958.75 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Champher Polish- DSP | R.Ft | 37.9 | 50 | 1895 | 0 | 1895 | 2.5 | 37.9 | 1895 | 0 | 1895 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | DEV. Swimming Pool | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Cutting & fixing | Sq.Ft | 612.23 | 125 | 76528.75 | 0 | 76528.75 | 2.5 | 612.23 | 76528.75 | 0 | 76528.75 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Moulding-mkt | R.Ft | 62.75 | 150 | 9412.5 | 0 | 9412.5 | 2.5 | 62.75 | 9412.5 | 0 | 9412.5 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Tile Fixing Work-DER | Sq.Ft | 21.25 | 40 | 850 | 0 | 850 | 2.5 | 21.25 | 850 | 0 | 850 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | DEV. Extrawork/Rework | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 14 | 300 | 4200 | 0 | 4200 | 2.5 | 0 | 0 | 0 | 0 | 14 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Dado Fixing | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | skmishra | 09 Mar 2022
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Self & Verticle Fixing | Sq.Ft | 149.84 | 110 | 16482.4 | 0 | 16482.4 | 2.5 | 149.8364 | 16482 | 0 | 16482 | 0.0036 | 0.4 |  | 99.9976 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Fix - | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Epoxy Grout Filling- | R.Ft | 148 | 20 | 2960 | 0 | 2960 | 2.5 | 148 | 2960 | 0 | 2960 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Fixing -SOS | Sq.Ft | 244.75 | 125 | 30593.75 | 0 | 30593.75 | 2.5 | 244.75 | 30593.75 | 0 | 30593.75 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Facia Patti Moulding | R.Ft | 48.25 | 125 | 6031.25 | 0 | 6031.25 | 2.5 | 48.248 | 6031 | 0 | 6031 | 0.002 | 0.25 |  | 99.9959 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Cutting & Fixing Work | Sq.Ft | 312.44 | 140 | 43741.6 | 0 | 43741.6 | 2.5 | 312.44 | 43741.6 | 0 | 43741.6 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 1 | 300 | 300 | 0 | 300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Tile Fixing Work-DER | Sq.Ft | 438.75 | 40 | 17550 | 0 | 17550 | 2.5 | 438.75 | 17550 | 0 | 17550 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | DEV. Extrawork/Rework | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Breaking Work -DPo | Sq.Ft | 148 | 30 | 4440 | 0 | 4440 | 0 | 148 | 4440 | 0 | 4440 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Cutting & Fixing Work | Sq.Ft | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | ADITYA CHOUGULE | 17 Jun 2022
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Cutting & fixing | Sq.Ft | 768.12 | 125 | 96015 | 0 | 96015 | 2.5 | 768.12 | 96015 | 0 | 96015 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Fixing -SOS | Sq.Ft | 66 | 125 | 8250 | 0 | 8250 | 2.5 | 66 | 8250 | 0 | 8250 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Window Sill BC | R.Ft | 83.33 | 160 | 13332.8 | 0 | 13332.8 | 2.5 | 83.33 | 13332.8 | 0 | 13332.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Flooring | Sq.Ft | 370.23 | 140 | 51832.2 | 0 | 51832.2 | 2.5 | 370.23 | 51832.2 | 0 | 51832.2 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Breaking Work -DPo | Sq.Ft | 257.32 | 30 | 7719.6 | 0 | 7719.6 | 0 | 0 | 0 | 0 | 0 | 257.32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 276.67 | 35 | 9683.45 | 0 | 9683.45 | 2.5 | 276.6571 | 9683 | 0 | 9683 | 0.0129 | 0.45 |  | 99.9953 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Facia Patti Moulding | R.Ft | 10.25 | 125 | 1281.25 | 0 | 1281.25 | 2.5 | 10.248 | 1281 | 0 | 1281 | 0.002 | 0.25 |  | 99.9805 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Moulding-mkt | R.Ft | 24.92 | 150 | 3738 | 0 | 3738 | 2.5 | 24.92 | 3738 | 0 | 3738 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Side Strap Polish | No. | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Zero Point Moulding - Mkt | R.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Cutting & Fixing Work | Sq.Ft | 48.75 | 1500 | 73125 | 0 | 73125 | 2.5 | 0 | 0 | 0 | 0 | 48.75 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Cutting & Fixing Work | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | dushant gore | 07 Feb 2022
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Skirting- | R.Ft | 165.44 | 140 | 23161.6 | 0 | 23161.6 | 2.5 | 165.44 | 23161.6 | 0 | 23161.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 19.5 | 35 | 682.5 | 0 | 682.5 | 2.5 | 19.5 | 682.5 | 0 | 682.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 24 | 125 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 24 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Labour Lumpsum - SOS | No. | 1 | 2500 | 2500 | 0 | 2500 | 2.5 | 1 | 2500 | 0 | 2500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Window Sill - cc | R.Ft | 236.17 | 110 | 25978.7 | 0 | 25978.7 | 2.5 | 236.17 | 25978.7 | 0 | 25978.7 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Zero Point Moulding - Mkt | R.Ft | 4 | 180 | 720 | 0 | 720 | 2.5 | 4 | 720 | 0 | 720 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Window Sill - cc | R.Ft | 40.43 | 125 | 5053.75 | 0 | 5053.75 | 2.5 | 40.43 | 5053.75 | 0 | 5053.75 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Tikli | No. | 2 | 500 | 1000 | 0 | 1000 | 2.5 | 2 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Breking Work - No. | No. | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 37 | 35 | 1295 | 0 | 1295 | 2.5 | 37 | 1295 | 0 | 1295 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Moulding-mkt | R.Ft | 38 | 150 | 5700 | 0 | 5700 | 2.5 | 38 | 5700 | 0 | 5700 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Plaster work- cc | Sq.Ft | 76 | 35 | 2660 | 0 | 2660 | 2.5 | 76 | 2660 | 0 | 2660 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Mirror Polish Wrk | R.Ft | 83.75 | 60 | 5025 | 0 | 5025 | 2.5 | 83.75 | 5025 | 0 | 5025 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Bharat Flooring | Sq.Ft | 31 | 275 | 8525 | 0 | 8525 | 2.5 | 31 | 8525 | 0 | 8525 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 2 | 700 | 1400 | 0 | 1400 | 2.5 | 2 | 1400 | 0 | 1400 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble cutting & Fixing. | No. | 1 | 2500 | 2500 | 0 | 2500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Fixing -SOS | Sq.Ft | 80.18 | 125 | 10022.5 | 0 | 10022.5 | 2.5 | 80.18 | 10022.5 | 0 | 10022.5 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 11 | 35 | 385 | 0 | 385 | 2.5 | 11 | 385 | 0 | 385 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Fix - | Sq.Ft | 60.43 | 225 | 13596.75 | 0 | 13596.75 | 2.5 | 60.43 | 13596.75 | 0 | 13596.75 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Chemical Appliying Backside | Sq.Ft | 742.75 | 10 | 7427.5 | 0 | 7427.5 | 2.5 | 742.75 | 7427.5 | 0 | 7427.5 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 06 WATERPROOFING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite/Shahabad Flooring Breaking - Dld | Sq.Ft | 102 | 30 | 3060 | 0 | 3060 | 2.5 | 102 | 3060 | 0 | 3060 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Simple Flooring | Sq.Ft | 125.82 | 40 | 5032.8 | 0 | 5032.8 | 2.5 | 125.82 | 5032.8 | 0 | 5032.8 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Holes | No. | 2 | 700 | 1400 | 0 | 1400 | 2.5 | 2 | 1400 | 0 | 1400 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Dado Fixing | Sq.Ft | 357.15 | 90 | 32143.5 | 0 | 32143.5 | 2.5 | 357.15 | 32143.5 | 0 | 32143.5 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Plaster work- cc | Sq.Ft | 32 | 35 | 1120 | 0 | 1120 | 2.5 | 32 | 1120 | 0 | 1120 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | PCC | Sq.Ft | 49 | 35 | 1715 | 0 | 1715 | 2.5 | 49 | 1715 | 0 | 1715 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Chamfer Polish - BCE | R.Ft | 3.17 | 40 | 126.8 | 0 | 126.8 | 2.5 | 0 | 0 | 0 | 0 | 3.17 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 26.66 | 35 | 933.1 | 0 | 933.1 | 2.5 | 0 | 0 | 0 | 0 | 26.66 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Mirror Polish Wrk | R.Ft | 74 | 60 | 4440 | 0 | 4440 | 2.5 | 74 | 4440 | 0 | 4440 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Simple Flooring | Sq.Ft | 132 | 40 | 5280 | 0 | 5280 | 2.5 | 132 | 5280 | 0 | 5280 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 1 | 250 | 250 | 0 | 250 | 2.5 | 1 | 250 | 0 | 250 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Grout filling | Sq.Ft | 483.71 | 20 | 9674.2 | 0 | 9674.2 | 2.5 | 483.7 | 9674 | 0 | 9674 | 0.01 | 0.2 |  | 99.9979 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Zero Point Moulding - Mkt | R.Ft | 50.66 | 180 | 9118.8 | 0 | 9118.8 | 2.5 | 50.66 | 9118.8 | 0 | 9118.8 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 26.66 | 35 | 933.1 | 0 | 933.1 | 2.5 | 0 | 0 | 0 | 0 | 26.66 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Basin Counter | R.Ft | 0 | 1700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | ADITYA CHOUGULE | 07 Jun 2022
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Grout filling | Sq.Ft | 768.12 | 20 | 15362.4 | 0 | 15362.4 | 2.5 | 768.1 | 15362 | 0 | 15362 | 0.02 | 0.4 |  | 99.9974 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Chamfer Polish - BCE | R.Ft | 0 | 40 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA CHOUGULE | 07 Jun 2022
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Mirror Polish Wrk | R.Ft | 1 | 500 | 500 | 0 | 500 | 2.5 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Electric Chamber Levelling - No. | No. | 10 | 300 | 3000 | 0 | 3000 | 2.5 | 10 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 0 | 700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA CHOUGULE | 07 Jun 2022
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Cutting & Fixing Work | Sq.Ft | 0 | 119.12 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | dushant gore |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | skmishra | 19 Feb 2022
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Fixing -SOS | Sq.Ft | 41.87 | 70 | 2930.9 | 0 | 2930.9 | 2.5 | 41.87 | 2930.9 | 0 | 2930.9 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Moulding Zero Point | R.Ft | 26 | 180 | 4680 | 0 | 4680 | 2.5 | 26 | 4680 | 0 | 4680 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 4 | 700 | 2800 | 0 | 2800 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble cutting work - | No. | 6 | 350 | 2100 | 0 | 2100 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Cladding | Sq.Ft | 86.82 | 225 | 19534.5 | 0 | 19534.5 | 2.5 | 86.82 | 19534.5 | 0 | 19534.5 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Moulding & Polish | R.Ft | 38 | 150 | 5700 | 0 | 5700 | 2.5 | 38 | 5700 | 0 | 5700 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Chamfer Polish - BCE | R.Ft | 46.66 | 40 | 1866.4 | 0 | 1866.4 | 2.5 | 46.66 | 1866.4 | 0 | 1866.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Zero Point Moulding - Mkt | R.Ft | 27.5 | 180 | 4950 | 0 | 4950 | 2.5 | 0 | 0 | 0 | 0 | 27.5 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Top - AIE | R.Ft | 8 | 160 | 1280 | 0 | 1280 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Fix - | Sq.Ft | 0 | 1700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Wooden Flooring - BCo | Sq.Ft | 148 | 70 | 10360 | 0 | 10360 | 2.5 | 0 | 0 | 0 | 0 | 148 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Skirting- | R.Ft | 0 | 140 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA CHOUGULE | 07 Jun 2022
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Flooring work- cc | Sq.Ft | 10.5 | 40 | 420 | 0 | 420 | 2.5 | 10.5 | 420 | 0 | 420 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 2 | 1500 | 3000 | 0 | 3000 | 2.5 | 2 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 2 | 700 | 1400 | 0 | 1400 | 2.5 | 2 | 1400 | 0 | 1400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Floor Breaking | No. | 1 | 500 | 500 | 0 | 500 | 2.5 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Floor Breaking | No. | 1 | 2000 | 2000 | 0 | 2000 | 0 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 2 | 700 | 1400 | 0 | 1400 | 2.5 | 2 | 1400 | 0 | 1400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Breaking Work -DPo | Sq.Ft | 30.5 | 30 | 915 | 0 | 915 | 0 | 30.5 | 915 | 0 | 915 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Breaking Work -DPo | Sq.Ft | 155 | 30 | 4650 | 0 | 4650 | 0 | 155 | 4650 | 0 | 4650 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | DEV. Podium | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Kitchen Platform Moulding | R.Ft | 16.34 | 150 | 2451 | 0 | 2451 | 2.5 | 16.34 | 2451 | 0 | 2451 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Top - AIE | Sq.Ft | 0 | 1700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Facia Patti | R.Ft | 55.25 | 110 | 6077.5 | 0 | 6077.5 | 2.5 | 55.25 | 6077.5 | 0 | 6077.5 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Tile Cladding | Sq.Ft | 39.42 | 175 | 6898.5 | 0 | 6898.5 | 2.5 | 39.42 | 6898.5 | 0 | 6898.5 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Cutting & fixing | Sq.Ft | 132.42 | 125 | 16552.5 | 0 | 16552.5 | 2.5 | 132.42 | 16552.5 | 0 | 16552.5 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Top - AIE | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Edge Polish - BCE | R.Ft | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | B.C. Elevation Features | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Edge Polish - BCE | R.Ft | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | B.C. Elevation Features | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Vertical Holes | No. | 2 | 1100 | 2200 | 0 | 2200 | 2.5 | 2 | 2200 | 0 | 2200 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Top - AIE | R.Ft | 13 | 1700 | 22100 | 0 | 22100 | 2.5 | 0 | 0 | 0 | 0 | 13 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Dado Fixing | Sq.Ft | 108.67 | 175 | 19017.25 | 0 | 19017.25 | 2.5 | 108.6686 | 19017.01 | 0 | 19017.01 | 0.0014 | 0.25 |  | 99.9987 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Fix - | Sq.Ft | 21.17 | 140 | 2963.8 | 0 | 2963.8 | 2.5 | 21.17 | 2963.8 | 0 | 2963.8 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Fix - | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Breaking Work. | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Removing work.-SOS | No. | 1 | 2000 | 2000 | 0 | 2000 | 0 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Dado Fixing | Sq.Ft | 93.25 | 90 | 8392.5 | 0 | 8392.5 | 2.5 | 93.25 | 8392.5 | 0 | 8392.5 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Fixing -SOS | Sq.Ft | 64.9 | 110 | 7139 | 0 | 7139 | 2.5 | 64.9 | 7139 | 0 | 7139 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Flooring | Sq.Ft | 190.65 | 140 | 26691 | 0 | 26691 | 2.5 | 0 | 0 | 0 | 0 | 190.65 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Skirting- | R.Ft | 83.75 | 140 | 11725 | 0 | 11725 | 2.5 | 83.75 | 11725 | 0 | 11725 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Paving Blocks Fixing | No. | 1 | 2500 | 2500 | 0 | 2500 | 2.5 | 1 | 2500 | 0 | 2500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Epoxy Grout Filling- | R.Ft | 132.42 | 20 | 2648.4 | 0 | 2648.4 | 2.5 | 132.4 | 2648 | 0 | 2648 | 0.02 | 0.4 |  | 99.9849 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Holes | No. | 2 | 350 | 700 | 0 | 700 | 2.5 | 2 | 700 | 0 | 700 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Self & Verticle Fixing | Sq.Ft | 210.37 | 110 | 23140.7 | 0 | 23140.7 | 2.5 | 210.37 | 23140.7 | 0 | 23140.7 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Kitchen Pot Fixing | No. | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 71 | 35 | 2485 | 0 | 2485 | 2.5 | 71 | 2485 | 0 | 2485 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Chamfer Polish - BCE | R.Ft | 36.16 | 40 | 1446.4 | 0 | 1446.4 | 2.5 | 36.15 | 1446 | 0 | 1446 | 0.01 | 0.4 |  | 99.9723 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Zero Joint-BCo | R.Ft | 46.66 | 180 | 8398.8 | 0 | 8398.8 | 2.5 | 0 | 0 | 0 | 0 | 46.66 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Zero Point | R.Ft | 3.5 | 180 | 630 | 0 | 630 | 2.5 | 3.5 | 630 | 0 | 630 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Basin Counter | R.Ft | 5 | 1700 | 8500 | 0 | 8500 | 2.5 | 5 | 8500 | 0 | 8500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Window Sill BC | R.Ft | 26.66 | 160 | 4265.6 | 0 | 4265.6 | 2.5 | 26.66 | 4265.6 | 0 | 4265.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Kitchen Platform (L)- SOS | R.Ft | 10.25 | 1000 | 10250 | 0 | 10250 | 2.5 | 10.25 | 10250 | 0 | 10250 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Skirting Fixing - AIE | R.Ft | 23 | 140 | 3220 | 0 | 3220 | 2.5 | 23 | 3220 | 0 | 3220 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Chamfer Polish - BCE | R.Ft | 3.17 | 40 | 126.8 | 0 | 126.8 | 2.5 | 0 | 0 | 0 | 0 | 3.17 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Dado Fixing | Sq.Ft | 13.98 | 40 | 559.2 | 0 | 559.2 | 2.5 | 13.975 | 559 | 0 | 559 | 0.005 | 0.2 |  | 99.9642 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Zero Point Moulding - Mkt | R.Ft | 3.25 | 180 | 585 | 0 | 585 | 2.5 | 3.25 | 585 | 0 | 585 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Top - AIE | R.Ft | 18 | 160 | 2880 | 0 | 2880 | 2.5 | 0 | 0 | 0 | 0 | 18 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Zero Point Moulding - Mkt | R.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Cancelled | Dushant Gore | 24 Jun 2022
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Mirror Polish Wrk | R.Ft | 18.17 | 60 | 1090.2 | 0 | 1090.2 | 2.5 | 18.1667 | 1090 | 0 | 1090 | 0.0033 | 0.2 |  | 99.9818 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Edge Polish - BCE | R.Ft | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Feb 2022 |  | B.C. Elevation Features | Cancelled | ADITYA CHOUGULE | 07 Jun 2022
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 116.49 | 35 | 4077.15 | 0 | 4077.15 | 2.5 | 116.4857 | 4077 | 0 | 4077 | 0.0043 | 0.15 |  | 99.9963 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Top.- BRE | No. | 2.5 | 2500 | 6250 | 0 | 6250 | 2.5 | 2.5 | 6250 | 0 | 6250 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Epoxy Grout Filling- | R.Ft | 82 | 20 | 1640 | 0 | 1640 | 2.5 | 82 | 1640 | 0 | 1640 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Plaster work- cc | Sq.Ft | 125 | 35 | 4375 | 0 | 4375 | 2.5 | 125 | 4375 | 0 | 4375 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 168.76 | 35 | 5906.6 | 0 | 5906.6 | 2.5 | 168.76 | 5906.6 | 0 | 5906.6 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Top.- BRE | No. | 2 | 2500 | 5000 | 0 | 5000 | 2.5 | 2 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Zero Point Moulding - Mkt | R.Ft | 2 | 180 | 360 | 0 | 360 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Fixing -SOS | Sq.Ft | 9 | 125 | 1125 | 0 | 1125 | 2.5 | 9 | 1125 | 0 | 1125 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Fixing -SOS | Sq.Ft | 62 | 125 | 7750 | 0 | 7750 | 2.5 | 62 | 7750 | 0 | 7750 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Holes | No. | 0 | 700 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Feb 2022 |  | 11 TILING WORK | Cancelled | skmishra | 09 Mar 2022
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | POP Breaking | Sq.Ft | 91.18 | 30 | 2735.4 | 0 | 2735.4 | 2.5 | 91.1667 | 2735 | 0 | 2735 | 0.0133 | 0.4 |  | 99.9854 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 1 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Hole Making | No. | 2 | 700 | 1400 | 0 | 1400 | 2.5 | 2 | 1400 | 0 | 1400 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 0 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Material Shifting | Sq.Ft | 108.67 | 15 | 1630.05 | 0 | 1630.05 | 0 | 108.6667 | 1630 | 0 | 1630 | 0.0033 | 0.05 |  | 99.997 |  | dushant gore | chetan.jewalikar | construction open | 07 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 216 | 2 | 07 Feb 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Italian Marble Top - AIE | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Feb 2022 |  | Admin. Indirect Expenses | Cancelled | Dushant Gore | 20 Aug 2022
GANGA ASMI | 217 | 0 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House Excavation,Soling and PCC Work (Living Area) | Labour Lumpsum - SOS | No. | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 217 | 1 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House- Solling,Excavation & PCC Work.(DG Set Side) | Labour Lumpsum - SOS | No. | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 217 | 2 | 08 Feb 2022 | PRAKASH CONTRACTOR | One boat club-Paving Block Removing,loading,unloading work | Paving Blocks removing,loading,Unloading | Sq.Ft | 3009 | 6 | 18054 | 0 | 18054 | 0 | 3009 | 18054 | 0 | 18054 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 15 Feb 2022 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 218 | 0 | 08 Feb 2022 | NISAR AHMAD ANSARI | GH Antik finish & Kitchen lobby ceiling paint | Painting work lumpsum- cc | No. | 1 | 23480 | 23480 | 4226.4 | 27706.4 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. Customer Changes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 219 | 0 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House Kitchen- PCC Work | PCC Work | Sq.Ft | 468 | 6 | 2808 | 0 | 2808 | 2.5 | 468 | 2808 | 0 | 2808 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 219 | 1 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Gym Room- Dpt Labour Work | Departmental Labour | No. | 30 | 550 | 16500 | 0 | 16500 | 0 | 30 | 16500 | 0 | 16500 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 15 Feb 2022 |  | B.C. Rework/Extrawork | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 219 | 1 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Gym Room- Dpt Labour Work | Contractor Profit-Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 15 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 219 | 1 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Gym Room- Dpt Labour Work | Transport Charges | No. | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 15 Feb 2022 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 220 | 1 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Gym Room side tree plantation work | Contractor Profit-Mkt | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 15 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 220 | 1 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Gym Room side tree plantation work | Transportaion | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 15 Feb 2022 |  | B.C. Rework/Extrawork | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 220 | 2 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Kitchen Garden Work | Transport Charges | No. | 1 | 800 | 800 | 0 | 800 | 0 | 1 | 800 | 0 | 800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 220 | 1 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Gym Room side tree plantation work | Breaking Work (day) | Day | 2 | 1300 | 2600 | 0 | 2600 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 15 Feb 2022 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 220 | 2 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Kitchen Garden Work | Contractor Profit-Mkt | No. | 1 | 800 | 800 | 0 | 800 | 0 | 1 | 800 | 0 | 800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 220 | 1 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Gym Room side tree plantation work | Male Coolie | No. | 10 | 550 | 5500 | 0 | 5500 | 0 | 10 | 5500 | 0 | 5500 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 220 | 0 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House Excavation & RCC Work | RCC Work lumpsum- SOS | No. | 1 | 12000 | 12000 | 0 | 12000 | 2.5 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | DEV. Ext Development | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 220 | 2 | 08 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Kitchen Garden Work | Male Coolie | No. | 16 | 550 | 8800 | 0 | 8800 | 0 | 16 | 8800 | 0 | 8800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 0 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House Department Work | Male Coolie | No. | 13 | 600 | 7800 | 0 | 7800 | 0 | 13 | 7800 | 0 | 7800 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | 9" Brick Work | Sq.Ft | 1385 | 30 | 41550 | 0 | 41550 | 2.5 | 1385 | 41550 | 0 | 41550 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 1 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House Misclaneous plaster & BBM Work | Mason - DCW | No. | 5 | 1050 | 5250 | 0 | 5250 | 0 | 5 | 5250 | 0 | 5250 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 4 | 08 Feb 2022 | JAY GANESH ENTERPRISES | GH Back Side Compound Wall BBM & Plaster | Single Coat Plaster (L) | Sq.Ft | 620 | 30 | 18600 | 0 | 18600 | 2.5 | 620 | 18600 | 0 | 18600 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 2 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Coping WorkDCW | R.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 27 Feb 2023
GANGA ASMI | 221 | 0 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House Department Work | Male Coolie | No. | 13 | 500 | 6500 | 0 | 6500 | 0 | 13 | 6500 | 0 | 6500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Coping Work Rate Diff.- Dev | R.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | DEV. Landscape/Equipment | Cancelled | ADITYA CHOUGULE | 27 Feb 2023
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Brick Work Rate Diff | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 12 MASONARY WORK | Cancelled | ADITYA CHOUGULE | 27 Feb 2023
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | BBM Mason - UDR | No. | 3 | 1000 | 3000 | 0 | 3000 | 0 | 3 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 2 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | 9" Brick Work | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 15 Feb 2022 |  | 12 MASONARY WORK | Cancelled | ADITYA CHOUGULE | 27 Feb 2023
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Transport Charges | No. | 1 | 12000 | 12000 | 0 | 12000 | 0 | 1 | 12000 | 0 | 12000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Plaster Mason - UDR | No. | 4 | 1200 | 4800 | 0 | 4800 | 0 | 4 | 4800 | 0 | 4800 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Female Coolie | No. | 3 | 500 | 1500 | 0 | 1500 | 0 | 3 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 4 | 08 Feb 2022 | JAY GANESH ENTERPRISES | GH Back Side Compound Wall BBM & Plaster | Male Coolie | No. | 4 | 600 | 2400 | 0 | 2400 | 2.5 | 4 | 2400 | 0 | 2400 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 0 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House Department Work | Mason - DCW | No. | 13 | 1200 | 15600 | 0 | 15600 | 0 | 13 | 15600 | 0 | 15600 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Plaster Work Rate Diff | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA CHOUGULE | 27 Feb 2023
GANGA ASMI | 221 | 1 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House Misclaneous plaster & BBM Work | Female Coolie - SOS | No. | 2 | 350 | 700 | 0 | 700 | 0 | 2 | 700 | 0 | 700 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 15 Feb 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 4 | 08 Feb 2022 | JAY GANESH ENTERPRISES | GH Back Side Compound Wall BBM & Plaster | Mason - DCW | No. | 4 | 1200 | 4800 | 0 | 4800 | 2.5 | 4 | 4800 | 0 | 4800 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 2 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Plaster Work - BRE | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. Rework/Extrawork | Cancelled | ADITYA CHOUGULE | 27 Feb 2023
GANGA ASMI | 221 | 2 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Transport Charges | No. | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 15 Feb 2022 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 27 Feb 2023
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Coping WorkDCW | R.Ft | 200 | 20 | 4000 | 0 | 4000 | 2.5 | 200 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Plaster Work - BRE | Sq.Ft | 3284 | 30 | 98520 | 0 | 98520 | 2.5 | 3284 | 98520 | 0 | 98520 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 3 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House - Gym area BBM & plaster | Male Coolie | No. | 4 | 600 | 2400 | 0 | 2400 | 0 | 4 | 2400 | 0 | 2400 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 1 | 08 Feb 2022 | JAY GANESH ENTERPRISES | Goel House Misclaneous plaster & BBM Work | Male Coolie - SOS | No. | 5 | 550 | 2750 | 0 | 2750 | 0 | 5 | 2750 | 0 | 2750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 15 Feb 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 221 | 4 | 08 Feb 2022 | JAY GANESH ENTERPRISES | GH Back Side Compound Wall BBM & Plaster | 9" Brick Work | Sq.Ft | 340 | 30 | 10200 | 0 | 10200 | 2.5 | 340 | 10200 | 0 | 10200 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 500 | 15500 | 0 | 15500 | 0 | 31 | 15500 | 0 | 15500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 1 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 480 | 14400 | 0 | 14400 | 0 | 26 | 12480 | 0 | 12480 | 4 | 1920 |  | 86.6667 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 550 | 16500 | 0 | 16500 | 0 | 30 | 16500 | 0 | 16500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 500 | 15500 | 0 | 15500 | 0 | 31 | 15500 | 0 | 15500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 500 | 15000 | 0 | 15000 | 0 | 30 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 1 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 480 | 14400 | 0 | 14400 | 0 | 23 | 11040 | 0 | 11040 | 7 | 3360 |  | 76.6667 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 550 | 17050 | 0 | 17050 | 0 | 29 | 15950 | 0 | 15950 | 2 | 1100 |  | 93.5484 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 500 | 15000 | 0 | 15000 | 0 | 28 | 14000 | 0 | 14000 | 2 | 1000 |  | 93.3333 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 550 | 17050 | 0 | 17050 | 0 | 28 | 15400 | 0 | 15400 | 3 | 1650 |  | 90.3226 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 1 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 480 | 14880 | 0 | 14880 | 0 | 23 | 11040 | 0 | 11040 | 8 | 3840 |  | 74.1935 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 550 | 16500 | 0 | 16500 | 0 | 25 | 13750 | 0 | 13750 | 5 | 2750 |  | 83.3333 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 500 | 15000 | 0 | 15000 | 0 | 30 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 600 | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 1 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 480 | 14880 | 0 | 14880 | 0 | 31 | 14880 | 0 | 14880 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 600 | 18600 | 0 | 18600 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 500 | 15500 | 0 | 15500 | 0 | 31 | 15500 | 0 | 15500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 600 | 18600 | 0 | 18600 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 500 | 15500 | 0 | 15500 | 0 | 29 | 14500 | 0 | 14500 | 2 | 1000 |  | 93.5484 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 600 | 18600 | 0 | 18600 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 500 | 15000 | 0 | 15000 | 0 | 30 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 500 | 15500 | 0 | 15500 | 0 | 31 | 15500 | 0 | 15500 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 28 | 500 | 14000 | 0 | 14000 | 0 | 26 | 13000 | 0 | 13000 | 2 | 1000 |  | 92.8571 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 500 | 15500 | 0 | 15500 | 0 | 25 | 12500 | 0 | 12500 | 6 | 3000 |  | 80.6452 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 0 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 500 | 15500 | 0 | 15500 | 0 | 30 | 15000 | 0 | 15000 | 1 | 500 |  | 96.7742 |  | dushant gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 28 | 550 | 15400 | 0 | 15400 | 0 | 28 | 15400 | 0 | 15400 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 600 | 18600 | 0 | 18600 | 0 | 10 | 6000 | 0 | 6000 | 21 | 12600 |  | 32.2581 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 550 | 17050 | 0 | 17050 | 0 | 31 | 17050 | 0 | 17050 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 600 | 18600 | 0 | 18600 | 0 | 26 | 15600 | 0 | 15600 | 5 | 3000 |  | 83.871 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 550 | 16500 | 0 | 16500 | 0 | 30 | 16500 | 0 | 16500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 600 | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 550 | 16500 | 0 | 16500 | 0 | 30 | 16500 | 0 | 16500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 600 | 18600 | 0 | 18600 | 0 | 25 | 15000 | 0 | 15000 | 6 | 3600 |  | 80.6452 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 550 | 17050 | 0 | 17050 | 0 | 31 | 17050 | 0 | 17050 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 600 | 18600 | 0 | 18600 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 550 | 17050 | 0 | 17050 | 0 | 26 | 14300 | 0 | 14300 | 5 | 2750 |  | 83.871 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 550 | 17050 | 0 | 17050 | 0 | 31 | 17050 | 0 | 17050 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 2 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 31 | 550 | 17050 | 0 | 17050 | 0 | 28 | 15400 | 0 | 15400 | 3 | 1650 |  | 90.3226 |  | DUSHANT GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 29 | 600 | 17400 | 0 | 17400 | 0 | 10 | 6000 | 0 | 6000 | 19 | 11400 |  | 34.4828 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 600 | 18000 | 0 | 18000 | 0 | 30 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 222 | 3 | 08 Feb 2022 | SWAMI GOLAPPA | Goel House Monthly Department Labour | Department Labour - Day | Day | 30 | 600 | 18000 | 0 | 18000 | 0 | 30 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 4 | 08 Feb 2022 | PATILS FABRICATORS | GH Gym Room GI Shutter Patti Fixing | Tapping Screw- Den | No. | 710 | 3.5 | 2485 | 447.3 | 2932.3 | 2.5 | 710 | 2485 | 447.3 | 2932.3 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Feb 2022 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (L) - BCo | Kgs | 769.86 | 22 | 16936.92 | 3048.64 | 19985.56 | 2.5 | 769.8182 | 16936 | 3048.48 | 19984.48 | 0.0418 | 1.08 |  | 99.9946 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 223 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (L) - BCo | Kgs | 2026.16 | 22 | 44575.52 | 8023.6 | 52599.12 | 2.5 | 1983.4091 | 43635 | 7854.3 | 51489.3 | 42.7509 | 1109.82 |  | 97.8901 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 223 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (L) - BCo | Kgs | 812.52 | 22 | 17875.44 | 3217.58 | 21093.02 | 2.5 | 760.2728 | 16726 | 3010.68 | 19736.68 | 52.2472 | 1356.34 |  | 93.5697 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 223 | 2 | 08 Feb 2022 | PATILS FABRICATORS | Goel House Gym Work | Jali fixing | Sq.Ft | 150 | 15 | 2250 | 405 | 2655 | 2.5 | 90 | 1350 | 243 | 1593 | 60 | 1062 |  | 60 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Feb 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 2 | 08 Feb 2022 | PATILS FABRICATORS | Goel House Gym Work | Fabrication Work (L) | Kgs | 236 | 20 | 4720 | 849.6 | 5569.6 | 2.5 | 236 | 4720 | 849.6 | 5569.6 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Feb 2022 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Chemical Fastner fixing (L) | No. | 520 | 60 | 31200 | 5616 | 36816 | 2.5 | 129 | 7740 | 1393.2 | 9133.2 | 391 | 27682.8 |  | 24.8077 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 223 | 2 | 08 Feb 2022 | PATILS FABRICATORS | Goel House Gym Work | M.S. Door fixing-Dld. | No. | 1 | 800 | 800 | 144 | 944 | 2.5 | 1 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 3 | 08 Feb 2022 | PATILS FABRICATORS | Goel House VOX Facade for Gym Room - 1 No. | Fabrication Work (L)- AIE | Kgs | 944.86 | 20 | 18897.2 | 3401.5 | 22298.7 | 2.5 | 829.965 | 16599.3 | 2987.88 | 19587.18 | 114.895 | 2711.52 |  | 87.84 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 1 | 08 Feb 2022 | PATILS FABRICATORS | Goel House (L) Bed2 Shutter GI Patti Fixing | Fabrication work (L) | Kgs | 270 | 20 | 5400 | 972 | 6372 | 2.5 | 207 | 4140 | 745.2 | 4885.2 | 63 | 1486.8 |  | 76.6667 |  | Dushant Gore | Swapnil Erande | construction open | 14 Feb 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (L) - BCo | Kgs | 2332.4 | 22 | 51312.8 | 9236.3 | 60549.1 | 2.5 | 2331.6364 | 51296 | 9233.28 | 60529.28 | 0.7636 | 19.82 |  | 99.9673 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 223 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (L) - BCo | Kgs | 1104 | 22 | 24288 | 4371.84 | 28659.84 | 2.5 | 1104 | 24288 | 4371.84 | 28659.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 223 | 4 | 08 Feb 2022 | PATILS FABRICATORS | GH Gym Room GI Shutter Patti Fixing | GI Shutter Patti (L) | Kgs | 248.82 | 20 | 4976.4 | 895.76 | 5872.16 | 2.5 | 248.82 | 4976.4 | 895.76 | 5872.16 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (L) - BCo | Kgs | 1136 | 22 | 24992 | 4498.56 | 29490.56 | 2.5 | 676.091 | 14874 | 2677.32 | 17551.32 | 459.909 | 11939.24 |  | 59.5151 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 223 | 2 | 08 Feb 2022 | PATILS FABRICATORS | Goel House Gym Work | Sheet Fixing - AIE | Sq.Ft | 60 | 10 | 600 | 108 | 708 | 2.5 | 60 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 223 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Puff Sheet (L) | Sq.Ft | 4000 | 7 | 28000 | 5040 | 33040 | 2.5 | 4000 | 28000 | 5040 | 33040 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 224 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Red Oxide Paint SOS | Ltrs | 20 | 300 | 6000 | 1080 | 7080 | 0 | 15 | 4500 | 810 | 5310 | 5 | 1770 |  | 75 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 224 | 2 | 08 Feb 2022 | PATILS FABRICATORS | GH Gym Room GI Shutter Patti Fixing | GI Shutter Patti (M) | Kgs | 248.82 | 120 | 29858.4 | 5374.52 | 35232.92 | 0 | 248.82 | 29858.4 | 5374.52 | 35232.92 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 224 | 1 | 08 Feb 2022 | PATILS FABRICATORS | Goel House (L) Bed2 Shutter GI Patti Fixing | Fabrication work (M) | Kgs | 270 | 120 | 32400 | 5832 | 38232 | 0 | 207 | 24840 | 4471.2 | 29311.2 | 63 | 8920.8 |  | 76.6667 |  | Dushant Gore | Swapnil Erande | construction open | 14 Feb 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 224 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (M) - BCo | Kgs | 1104 | 73 | 80592 | 14506.56 | 95098.56 | 0 | 1104 | 80592 | 14506.56 | 95098.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 224 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Foundation Bolt Fixing - BCo | No. | 72 | 250 | 18000 | 3240 | 21240 | 0 | 0 | 0 | 0 | 0 | 72 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 224 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (M) - BCo | Kgs | 2332.4 | 73 | 170265.2 | 30647.74 | 200912.94 | 0 | 2332.2876 | 170256.99 | 30646.26 | 200903.25 | 0.1124 | 9.69 |  | 99.9952 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 224 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (M) - BCo | Kgs | 1136 | 73 | 82928 | 14927.04 | 97855.04 | 0 | 324.7809 | 23709.01 | 4267.62 | 27976.63 | 811.2191 | 69878.41 |  | 28.5899 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 224 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (M) - BCo | Kgs | 2026.16 | 73 | 147909.68 | 26623.74 | 174533.42 | 0 | 1984.0138 | 144833.01 | 26069.94 | 170902.95 | 42.1462 | 3630.47 |  | 97.9199 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 224 | 1 | 08 Feb 2022 | PATILS FABRICATORS | Goel House (L) Bed2 Shutter GI Patti Fixing | Tapping Screw- Den | No. | 400 | 3.5 | 1400 | 252 | 1652 | 0 | 400 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 14 Feb 2022 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 224 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (M) - BCo | Kgs | 769.86 | 73 | 56199.78 | 10115.96 | 66315.74 | 0 | 769.8493 | 56199 | 10115.82 | 66314.82 | 0.0107 | 0.92 |  | 99.9986 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 224 | 0 | 08 Feb 2022 | PATILS FABRICATORS | GH Rennovation of Structural Fabrication | Fabrication Work (M) - BCo | Kgs | 812.52 | 73 | 59313.96 | 10676.52 | 69990.48 | 0 | 760.2877 | 55501 | 9990.18 | 65491.18 | 52.2323 | 4499.3 |  | 93.5716 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 14 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 1 | 1500 | 1500 | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Consultancy Proffessional | Cancelled | skmishra | 02 Mar 2022
GANGA ASMI | 225 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Travelling Allowance | Travelling Allowance | Month | 1 | 1500 | 1500 | 0 | 1500 | 0 | 1 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 1900-01-01 |  | Consultancy Proffessional | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Feb 2022 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 22 Mar 2022
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Feb 2022 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 22 Mar 2022
GANGA ASMI | 226 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 226 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Garbage Collection | Garbage Collection- SO | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.9978 | 4989 | 0 | 4989 | 0.0022 | 11 |  | 99.78 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.482 | 4820 | 0 | 4820 | 0.518 | 5180 |  | 48.2 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.5972 | 2986 | 0 | 2986 | 0.4028 | 2014 |  | 59.72 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 1 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.3225 | 3225 | 0 | 3225 | 0.6775 | 6775 |  | 32.25 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.978 | 4890 | 0 | 4890 | 0.022 | 110 |  | 97.8 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.042 | 210 | 0 | 210 | 0.958 | 4790 |  | 4.2 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.17 | 850 | 0 | 850 | 0.83 | 4150 |  | 17 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.38 | 1900 | 0 | 1900 | 0.62 | 3100 |  | 38 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.1 | 500 | 0 | 500 | 0.9 | 4500 |  | 10 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.1858 | 929 | 0 | 929 | 0.8142 | 4071 |  | 18.58 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 227 | 0 | 08 Feb 2022 | HEMANT G MAHABALESHWARKAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.997 | 4985 | 0 | 4985 | 0.003 | 15 |  | 99.7 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 270.54 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 0.75 | 30000 | 0 | 30000 | 0.25 | 10000 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 1 | 40000 | 0 | 40000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 0.75 | 30000 | 0 | 30000 | 0.25 | 10000 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 1 | 40000 | 0 | 40000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 0.75 | 30000 | 0 | 30000 | 0.25 | 10000 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 0.75 | 30000 | 0 | 30000 | 0.25 | 10000 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 420.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 420.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 420.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 1 | 40000 | 0 | 40000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 420.83 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 450.89 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 1 | 40000 | 0 | 40000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 252.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 1 | 40000 | 0 | 40000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 252.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | SOC. M. Maintenace of Aminitie | Cancelled | skmishra | 07 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 252.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 252.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 01 Apr 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 0.75 | 30000 | 0 | 30000 | 0.25 | 10000 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 1 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance | Month | 1 | 40000 | 40000 | 0 | 40000 | 0 | 1 | 40000 | 0 | 40000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 244.35 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 12 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 228 | 0 | 09 Feb 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden Maintenance Work | Day | 0 | 407.26 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Feb 2022 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 09 Feb 2022
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 1 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 1 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 229 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House Tata Sky DTH Monthly WO | Tata Sky DTH | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 14 MISC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 16 Sqmm Armd Cable (L) | R.Ft | 59 | 20 | 1180 | 212.4 | 1392.4 | 2.5 | 59 | 1180 | 212.4 | 1392.4 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Exhaust Fan Point - BCo | No. | 2 | 260 | 520 | 93.6 | 613.6 | 2.5 | 2 | 520 | 93.6 | 613.6 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 16 AMP Plug Point - Mkt | No. | 5 | 350 | 1750 | 315 | 2065 | 2.5 | 5 | 1750 | 315 | 2065 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Telephone Point - Mkt | No. | 2 | 210 | 420 | 75.6 | 495.6 | 2.5 | 2 | 420 | 75.6 | 495.6 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | MCB 4 Pole Fixing | No. | 1 | 900 | 900 | 162 | 1062 | 2.5 | 1 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | M.S. Bracket fixing-DWB | No. | 3 | 150 | 450 | 81 | 531 | 2.5 | 3 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Water Body | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 1706 | 12 | 20472 | 3684.96 | 24156.96 | 2.5 | 1706 | 20472 | 3684.96 | 24156.96 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Two way Point - DCH | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Club House | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 16 AMP Plug Point - Mkt | No. | 3 | 350 | 1050 | 189 | 1239 | 2.5 | 3 | 1050 | 189 | 1239 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 160 Amp Main Switch- | No. | 2 | 2500 | 5000 | 900 | 5900 | 2.5 | 2 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | MCB 1 Pole Fixing | No. | 24 | 150 | 3600 | 648 | 4248 | 2.5 | 24 | 3600 | 648 | 4248 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Light Point - DSP | No. | 47 | 260 | 12220 | 2199.6 | 14419.6 | 2.5 | 47 | 12220 | 2199.6 | 14419.6 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Swimming Pool | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 16 Way SPN DB | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 1 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | CAT 6 Cable- | R.Ft | 858 | 12 | 10296 | 1853.28 | 12149.28 | 2.5 | 858 | 10296 | 1853.28 | 12149.28 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 13 Amp Plug Point | No. | 14 | 300 | 4200 | 756 | 4956 | 2.5 | 14 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Tube Light Fixing BC | No. | 40 | 70 | 2800 | 504 | 3304 | 2.5 | 40 | 2800 | 504 | 3304 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Two way Point - DCH | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Club House | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 4 Way SPN DB | No. | 1 | 450 | 450 | 81 | 531 | 2.5 | 1 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Fan Fixing - Mkt | No. | 4 | 300 | 1200 | 216 | 1416 | 2.5 | 4 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Light Point - DSP | No. | 35 | 260 | 9100 | 1638 | 10738 | 2.5 | 35 | 9100 | 1638 | 10738 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Swimming Pool | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 4 Sqmm Cable (L) | R.Ft | 469 | 16 | 7504 | 1350.72 | 8854.72 | 2.5 | 469 | 7504 | 1350.72 | 8854.72 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 6 way TPN DB fixing MCB-DCH | No. | 1 | 2500 | 2500 | 450 | 2950 | 2.5 | 1 | 2500 | 450 | 2950 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Club House | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Fan Point - BCo | No. | 4 | 300 | 1200 | 216 | 1416 | 2.5 | 4 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | Wall & Hanging Light Fitting Fixing - Mk | No. | 12 | 200 | 2400 | 432 | 2832 | 2.5 | 12 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | MCB 2 Pole Fixing | No. | 1 | 500 | 500 | 90 | 590 | 2.5 | 1 | 500 | 90 | 590 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | AC Point BC | No. | 2 | 350 | 700 | 126 | 826 | 2.5 | 2 | 700 | 126 | 826 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 927 | 8 | 7416 | 1334.88 | 8750.88 | 2.5 | 927 | 7416 | 1334.88 | 8750.88 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | 6 Way Enclosure Box Fixing | No. | 2 | 1500 | 3000 | 540 | 3540 | 2.5 | 2 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 230 | 0 | 09 Feb 2022 | RAJ ELECTRICAL SERVICES | GH North Side out house Electrical Work | RCCB 4 Pole | No. | 1 | 900 | 900 | 162 | 1062 | 2.5 | 1 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 231 | 0 | 09 Feb 2022 | HEMANT G MAHABALESHWARKAR | Goel House- Housekeeping material | Housekeeping Material - | Month | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Tile Cutting work | R.Ft | 144 | 30 | 4320 | 777.6 | 5097.6 | 2.5 | 144 | 4320 | 777.6 | 5097.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Epoxy Grout Filling- | R.Ft | 133.09 | 15 | 1996.35 | 359.34 | 2355.69 | 2.5 | 133.09 | 1996.35 | 359.34 | 2355.69 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Dado Fixing | Sq.Ft | 210.43 | 105 | 22095.15 | 3977.12 | 26072.27 | 2.5 | 210.43 | 22095.15 | 3977.12 | 26072.27 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Drill Hole | No. | 505 | 136.5 | 68932.5 | 12407.86 | 81340.36 | 2.5 | 106 | 14469 | 2604.42 | 17073.42 | 399 | 64266.94 |  | 20.9901 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Dado Fixing | Sq.Ft | 467.68 | 126 | 58927.68 | 10606.98 | 69534.66 | 2.5 | 202.98 | 25575.48 | 4603.58 | 30179.06 | 264.7 | 39355.6 |  | 43.4015 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Flooring | Sq.Ft | 816.66 | 94.5 | 77174.37 | 13891.38 | 91065.75 | 2.5 | 816.66 | 77174.37 | 13891.38 | 91065.75 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Flooring work- cc | Sq.Ft | 171.09 | 52.5 | 8982.23 | 1616.8 | 10599.03 | 2.5 | 171.09 | 8982.23 | 1616.8 | 10599.03 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 3 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Italian Marble Mirror Polish- | Sq.Ft | 12.79 | 68.25 | 872.92 | 157.12 | 1030.04 | 2.5 | 12.79 | 872.92 | 157.12 | 1030.04 | 0 | 0 | Courtyard area bothside staircase polishing work. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Floor Groove Grouting | Sq.Ft | 828.51 | 15.75 | 13049.03 | 2348.82 | 15397.85 | 2.5 | 828.51 | 13049.03 | 2348.82 | 15397.85 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Italian Marble Laying - Mkt | Sq.Ft | 38 | 120 | 4560 | 820.8 | 5380.8 | 2.5 | 38 | 4560 | 820.8 | 5380.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 2 | 10 Feb 2022 | R K INTERIOR | Goel House Italian marble mirror polish work | Italian Marble Skirting Leather Polish | R.Ft | 65.12 | 55 | 3581.6 | 644.68 | 4226.28 | 2.5 | 0 | 0 | 0 | 0 | 65.12 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Granite Border - DCH | R.Ft | 6 | 90 | 540 | 97.2 | 637.2 | 2.5 | 6 | 540 | 97.2 | 637.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Club House | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 3 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Italian Marble Mirror Polish | R.Ft | 65.87 | 68.25 | 4495.63 | 809.22 | 5304.85 | 2.5 | 65.87 | 4495.63 | 809.22 | 5304.85 | 0 | 0 | Courtyard area bothside staircase polishing work. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 3 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Brush Polish for Granite Floor | Sq.Ft | 137.88 | 130 | 17924.4 | 3226.4 | 21150.8 | 2.5 | 137.88 | 17924.4 | 3226.4 | 21150.8 | 0 | 0 | Courtyard area bothside staircase polishing work. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Demolishing Brickwork-cc | Sq.Ft | 5.99 | 36.75 | 220.13 | 39.62 | 259.75 | 2.5 | 5.99 | 220.13 | 39.62 | 259.75 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Zero Point Joint Making | R.Ft | 5.25 | 200 | 1050 | 189 | 1239 | 2.5 | 5.25 | 1050 | 189 | 1239 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Dado Work - Dld | Sq.Ft | 79.97 | 120.75 | 9656.38 | 1738.14 | 11394.52 | 2.5 | 79.97 | 9656.38 | 1738.14 | 11394.52 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Slate Tile Flooring work | Sq.Ft | 133.09 | 70 | 9316.3 | 1676.94 | 10993.24 | 2.5 | 133.09 | 9316.3 | 1676.94 | 10993.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 2 | 10 Feb 2022 | R K INTERIOR | Goel House Italian marble mirror polish work | Italian Marble Top/ Botom Mirror Polish - | R.Ft | 238.02 | 55 | 13091.1 | 2356.4 | 15447.5 | 2.5 | 43.0364 | 2367 | 426.06 | 2793.06 | 194.9836 | 12654.44 |  | 18.081 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 3 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Brush Polish for Granite Floor | Sq.Ft | 7537.84 | 68.25 | 514457.58 | 92602.36 | 607059.94 | 2.5 | 5661.978 | 386430 | 69557.4 | 455987.4 | 1875.862 | 151072.54 | Courtyard area bothside staircase polishing work. | 75.1141 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Full Moulding (L) | R.Ft | 27.16 | 210 | 5703.6 | 1026.64 | 6730.24 | 2.5 | 27.16 | 5703.6 | 1026.64 | 6730.24 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Italian Marble Mirror Polish- BC | R.Ft | 9.88 | 65 | 642.2 | 115.6 | 757.8 | 2.5 | 9.88 | 642.2 | 115.6 | 757.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Flooring work- cc | Sq.Ft | 212.77 | 52.5 | 11170.43 | 2010.68 | 13181.11 | 2.5 | 212.77 | 11170.43 | 2010.68 | 13181.11 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Breaking Of Tile - DER | Sq.Ft | 133.09 | 10 | 1330.9 | 239.56 | 1570.46 | 2.5 | 133.09 | 1330.9 | 239.56 | 1570.46 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Extrawork/Rework | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Chamfer Polish - BCE | R.Ft | 5.25 | 85 | 446.25 | 80.32 | 526.57 | 2.5 | 5.25 | 446.25 | 80.32 | 526.57 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 2 | 10 Feb 2022 | R K INTERIOR | Goel House Italian marble mirror polish work | Edge Polish- BCo | R.Ft | 215.88 | 35 | 7555.8 | 1360.04 | 8915.84 | 2.5 | 147.1429 | 5150 | 927 | 6077 | 68.7371 | 2838.84 |  | 68.1596 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Italian Marble Mirror Polish- | Sq.Ft | 143.57 | 73.5 | 10552.4 | 1899.44 | 12451.84 | 2.5 | 143.57 | 10552.4 | 1899.44 | 12451.84 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Flooring work- cc | Sq.Ft | 703.63 | 36.75 | 25858.4 | 4654.52 | 30512.92 | 2.5 | 703.63 | 25858.4 | 4654.52 | 30512.92 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 0 | 10 Feb 2022 | R K INTERIOR | GH Room No-6 & Dinning & MT.Rm-3 Tiling | Italian Marble Sill- BC- | R.Ft | 9.88 | 105 | 1037.4 | 186.74 | 1224.14 | 2.5 | 9.88 | 1037.4 | 186.74 | 1224.14 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Cobble fixing -Dld | Sq.Ft | 84.96 | 110.25 | 9366.84 | 1686.04 | 11052.88 | 2.5 | 84.1104 | 9273.17 | 1669.18 | 10942.35 | 0.8496 | 110.53 |  | 99 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | V Groove - AIE | R.Ft | 52.58 | 68.25 | 3588.59 | 645.94 | 4234.53 | 2.5 | 52.58 | 3588.59 | 645.94 | 4234.53 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | L Groove - BCV | R.Ft | 113.97 | 157.5 | 17950.28 | 3231.06 | 21181.34 | 2.5 | 113.97 | 17950.28 | 3231.06 | 21181.34 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Epoxy Grout Filling | Sq.Ft | 944.04 | 15.75 | 14868.63 | 2676.36 | 17544.99 | 2.5 | 944.04 | 14868.63 | 2676.36 | 17544.99 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Italian Marble Mirror Polish | R.Ft | 497.2 | 68.25 | 33933.9 | 6108.1 | 40042 | 2.5 | 497.2 | 33933.9 | 6108.1 | 40042 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Champher/ Bullnose Moulding Polish | R.Ft | 333.97 | 68.25 | 22793.45 | 4102.82 | 26896.27 | 2.5 | 333.97 | 22793.45 | 4102.82 | 26896.27 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Skirting Fixing - AIE | R.Ft | 53.16 | 52.5 | 2790.9 | 502.36 | 3293.26 | 2.5 | 53.16 | 2790.9 | 502.36 | 3293.26 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 2 | 10 Feb 2022 | R K INTERIOR | Goel House Italian marble mirror polish work | Italian Marble Dado Leather Polish | Sq.Ft | 201.16 | 55 | 11063.8 | 1991.48 | 13055.28 | 2.5 | 100 | 5500 | 990 | 6490 | 101.16 | 6565.28 |  | 49.7117 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Italian Marble Dado Leather Polish | Sq.Ft | 51.63 | 68.25 | 3523.75 | 634.28 | 4158.03 | 2.5 | 51.63 | 3523.75 | 634.28 | 4158.03 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Edge Polish - Dld | R.Ft | 416.48 | 36.75 | 15305.64 | 2755.02 | 18060.66 | 2.5 | 416.48 | 15305.64 | 2755.02 | 18060.66 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Acid Wash | Sq.Ft | 1818.76 | 8.4 | 15277.58 | 2749.96 | 18027.54 | 2.5 | 1818.76 | 15277.58 | 2749.96 | 18027.54 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Tappa (L) - BC | R.Ft | 4.25 | 94.5 | 401.63 | 72.3 | 473.93 | 2.5 | 4.25 | 401.63 | 72.3 | 473.93 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Mirror Polish-BCo | Sq.Ft | 37 | 131.25 | 4856.25 | 874.12 | 5730.37 | 2.5 | 37 | 4856.25 | 874.12 | 5730.37 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Champher-DCH | R.Ft | 295.75 | 89.25 | 26395.69 | 4751.22 | 31146.91 | 2.5 | 295.75 | 26395.69 | 4751.22 | 31146.91 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Wooden Tile Top fixing | R.Ft | 25.74 | 126 | 3243.24 | 583.78 | 3827.02 | 2.5 | 25.2252 | 3178.38 | 572.1 | 3750.48 | 0.5148 | 76.54 |  | 98 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Pebbles fixing | Sq.Ft | 115.93 | 175 | 20287.75 | 3651.8 | 23939.55 | 2.5 | 115.93 | 20287.75 | 3651.8 | 23939.55 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Granite Buffing - | R.Ft | 346.76 | 20 | 6935.2 | 1248.34 | 8183.54 | 2.5 | 346.76 | 6935.2 | 1248.34 | 8183.54 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 3 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Brush Polish for Granite Floor. | R.Ft | 1620.23 | 68.25 | 110580.7 | 19904.52 | 130485.22 | 2.5 | 1513.9927 | 103330 | 18599.4 | 121929.4 | 106.2373 | 8555.82 | Courtyard area bothside staircase polishing work. | 93.4431 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 2 | 10 Feb 2022 | R K INTERIOR | Goel House Italian marble mirror polish work | Italian Marble Skirting Mirror polish. | R.Ft | 886.83 | 55 | 48775.65 | 8779.62 | 57555.27 | 2.5 | 886.2727 | 48745 | 8774.1 | 57519.1 | 0.5573 | 36.17 |  | 99.9372 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Chamber Fixing - Mkt | No. | 7 | 1000 | 7000 | 1260 | 8260 | 2.5 | 7 | 7000 | 1260 | 8260 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 1 | 10 Feb 2022 | R K INTERIOR | Goel House Meeting Rm.3 Flooring Marble Mirror Polish - 1 | Department Labour- BC | No. | 8 | 1100 | 8800 | 1584 | 10384 | 0 | 8 | 8800 | 1584 | 10384 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. RCC Substructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Grout filling | Sq.Ft | 115.93 | 25 | 2898.25 | 521.68 | 3419.93 | 2.5 | 115.93 | 2898.25 | 521.68 | 3419.93 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Italian Marble Skirting Mirror polish. | R.Ft | 218.33 | 57.75 | 12608.56 | 2269.54 | 14878.1 | 2.5 | 218.33 | 12608.56 | 2269.54 | 14878.1 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Italian Marble Buffing (sft) | Sq.Ft | 271.71 | 20 | 5434.2 | 978.16 | 6412.36 | 2.5 | 271.71 | 5434.2 | 978.16 | 6412.36 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 2 | 10 Feb 2022 | R K INTERIOR | Goel House Italian marble mirror polish work | Italian Marble Mirror Polish- | Sq.Ft | 7022.59 | 55 | 386242.45 | 69523.64 | 455766.09 | 2.5 | 5853.6728 | 321952 | 57951.36 | 379903.36 | 1168.9172 | 75862.73 |  | 83.3549 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 2 | 10 Feb 2022 | R K INTERIOR | Goel House Italian marble mirror polish work | Italian Marble Floor Leather Polish | Sq.Ft | 303.39 | 55 | 16686.45 | 3003.56 | 19690.01 | 2.5 | 303.39 | 16686.45 | 3003.56 | 19690.01 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Italian Marble Mirror Polish- | Sq.Ft | 160.55 | 73.5 | 11800.43 | 2124.08 | 13924.51 | 2.5 | 160.55 | 11800.43 | 2124.08 | 13924.51 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 4 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Edge Polish - BCE | R.Ft | 340.73 | 36.75 | 12521.83 | 2253.92 | 14775.75 | 2.5 | 340.73 | 12521.83 | 2253.92 | 14775.75 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Demolish Work. | Sq.Ft | 28.12 | 36.75 | 1033.41 | 186.02 | 1219.43 | 2.5 | 28.12 | 1033.41 | 186.02 | 1219.43 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Zero Point Joint Making | R.Ft | 50.56 | 210 | 10617.6 | 1911.16 | 12528.76 | 2.5 | 50.56 | 10617.6 | 1911.16 | 12528.76 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 2 | 10 Feb 2022 | R K INTERIOR | Goel House Italian marble mirror polish work | Champher/ Bullnose Moulding Polish | R.Ft | 624.02 | 50 | 31201 | 5616.18 | 36817.18 | 2.5 | 28.06 | 1403 | 252.54 | 1655.54 | 595.96 | 35161.64 |  | 4.4967 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Border Fixing- | R.Ft | 33.75 | 94.5 | 3189.38 | 574.08 | 3763.46 | 2.5 | 33.75 | 3189.38 | 574.08 | 3763.46 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Granite Border Fixing- | R.Ft | 565.94 | 94.5 | 53481.33 | 9626.64 | 63107.97 | 2.5 | 565.94 | 53481.33 | 9626.64 | 63107.97 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 5 | 10 Feb 2022 | R K INTERIOR | Goel House (L) Gym Flooring work | Dado Fixing | Sq.Ft | 342.15 | 136.5 | 46703.48 | 8406.62 | 55110.1 | 2.5 | 338.7285 | 46236.44 | 8322.56 | 54559 | 3.4215 | 551.09 |  | 99 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 3 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Edge Polish - BCE | R.Ft | 170.59 | 36.75 | 6269.18 | 1128.46 | 7397.64 | 2.5 | 169.9864 | 6247 | 1124.46 | 7371.46 | 0.6036 | 26.18 | Courtyard area bothside staircase polishing work. | 99.6462 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 232 | 3 | 10 Feb 2022 | R K INTERIOR | Goel House Flooring Work | Champher/ Bullnose Moulding Polish | R.Ft | 853.03 | 68.25 | 58219.3 | 10479.48 | 68698.78 | 2.5 | 829.9927 | 56647 | 10196.46 | 66843.46 | 23.0373 | 1855.32 | Courtyard area bothside staircase polishing work. | 97.2994 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 233 | 0 | 10 Feb 2022 | RAJYOG ENTERPRISES | Goel House Glass Fitting In Security cabin. | Fabrication work (L) | Kgs | 700 | 30 | 21000 | 3780 | 24780 | 2.5 | 700 | 21000 | 3780 | 24780 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 10 Feb 2022 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 233 | 0 | 10 Feb 2022 | RAJYOG ENTERPRISES | Goel House Glass Fitting In Security cabin. | Fabrication Work (M+L) - Mkt | Kgs | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 10 Feb 2022 |  | MKT. Marketing Infrastructure | Cancelled | skmishra | 10 Feb 2022
GANGA ASMI | 233 | 0 | 10 Feb 2022 | RAJYOG ENTERPRISES | Goel House Glass Fitting In Security cabin. | Glass Fixing (M+L) | Sq.Ft | 0 | 400 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 10 Feb 2022 |  | B.C. Building Common Items | Cancelled | skmishra | 10 Feb 2022
GANGA ASMI | 233 | 0 | 10 Feb 2022 | RAJYOG ENTERPRISES | Goel House Glass Fitting In Security cabin. | Glass fixing- SOS | Sq.Ft | 288 | 400 | 115200 | 20736 | 135936 | 2.5 | 258.75 | 103500 | 18630 | 122130 | 29.25 | 13806 |  | 89.8438 |  | Dushant Gore | chetan.jewalikar | construction open | 10 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | P.U. Polish-AIE | Sq.Ft | 0 | 193.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Royal Paint | Sq.Ft | 0 | 44.16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | No category | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Satin Mat Paint | Sq.Ft | 0 | 27.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | P.U Polish Libbing | R.Ft | 0 | 87.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Apex Exterior Paint | Sq.Ft | 0 | 25.76 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Satin Mat Paint | Sq.Ft | 4332.32 | 26.4 | 114373.25 | 0 | 114373.25 | 2.5 | 4332.32 | 114373.25 | 0 | 114373.25 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | P.U Polish Libbing | R.Ft | 48.45 | 83.6 | 4050.42 | 0 | 4050.42 | 2.5 | 48.45 | 4050.42 | 0 | 4050.42 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | P.U Polish Patta | R.Ft | 0 | 101.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Royal Paint | Sq.Ft | 3410.38 | 42.24 | 144054.45 | 0 | 144054.45 | 2.5 | 3410.38 | 144054.45 | 0 | 144054.45 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Apex Exterior Paint | Sq.Ft | 7236.76 | 24.64 | 178313.77 | 0 | 178313.77 | 2.5 | 7236.76 | 178313.77 | 0 | 178313.77 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | ICA Colour P.U | Sq.Ft | 0 | 285.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Lambi + Primer Paint | Sq.Ft | 0 | 9.2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | P.U. Polish-AIE | Sq.Ft | 222.22 | 184.8 | 41066.26 | 0 | 41066.26 | 2.5 | 222.22 | 41066.26 | 0 | 41066.26 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | ICA Colour P.U Patt | R.Ft | 0 | 142.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | P.U Polish Patta | R.Ft | 404.65 | 96.8 | 39170.12 | 0 | 39170.12 | 2.5 | 404.65 | 39170.12 | 0 | 39170.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | ICA Colour P.U | Sq.Ft | 171.26 | 272.8 | 46719.73 | 0 | 46719.73 | 2.5 | 171.26 | 46719.73 | 0 | 46719.73 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 234 | 0 | 10 Feb 2022 | UMESH YADAV | GH External Wall Texture painting | External Paint (acrylic)-BC (m+l) | Sq.Ft | 19832.43 | 22 | 436313.46 | 0 | 436313.46 | 2.5 | 19832.43 | 436313.46 | 0 | 436313.46 | 0 | 0 | 1 Coat Primer + 2 Coat 100% Acrylic Point with Surface Preparation & including Scffolding & Removing. | 100 |  | dushant gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Lambi + Primer Paint | Sq.Ft | 0 | 18.4 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Cancelled | ADITYA.CHOUGULE | 02 Dec 2023
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | ICA Colour P.U Patt | R.Ft | 62.16 | 136.4 | 8478.62 | 0 | 8478.62 | 2.5 | 62.16 | 8478.62 | 0 | 8478.62 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 234 | 1 | 10 Feb 2022 | UMESH YADAV | GH Gym Room Painting Work | Lambi + Primer Paint | Sq.Ft | 109.28 | 17.6 | 1923.33 | 0 | 1923.33 | 2.5 | 109.28 | 1923.33 | 0 | 1923.33 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 235 | 0 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misclaneous Work | Breaker-BC | No. | 4 | 1300 | 5200 | 0 | 5200 | 0 | 4 | 5200 | 0 | 5200 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 235 | 5 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misc Work. | Breaker | Day | 4 | 1300 | 5200 | 0 | 5200 | 0 | 4 | 5200 | 0 | 5200 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 235 | 6 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Backside planter soil shifting | Transportaion | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Feb 2022 |  | B.C. Rework/Extrawork | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 235 | 6 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Backside planter soil shifting | Male Collie - SM | No. | 20 | 550 | 11000 | 0 | 11000 | 0 | 20 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 235 | 4 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Department Work | Male Coolie | No. | 6 | 500 | 3000 | 0 | 3000 | 0 | 6 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 235 | 1 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misc Work. | Breaker | Day | 2 | 1000 | 2000 | 0 | 2000 | 0 | 2 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 235 | 4 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Department Work | Big Breaker | No. | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Feb 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 15 Dec 2022
GANGA ASMI | 235 | 7 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misclaneous Work | Labour Lumsum | No. | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 235 | 1 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misc Work. | Department Labour - Day | Day | 53.5 | 500 | 26750 | 0 | 26750 | 0 | 53.5 | 26750 | 0 | 26750 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | SOC. M. Civil Work Maintenace | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 235 | 5 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misc Work. | Male Coolie | No. | 16 | 550 | 8800 | 0 | 8800 | 0 | 16 | 8800 | 0 | 8800 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 235 | 3 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Department Work | Department Labour-Dev | No. | 32.5 | 550 | 17875 | 0 | 17875 | 0 | 32.5 | 17875 | 0 | 17875 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Murum Filling | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 235 | 1 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misc Work. | Breaker | Day | 2.5 | 1300 | 3250 | 0 | 3250 | 0 | 2.5 | 3250 | 0 | 3250 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 235 | 0 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misclaneous Work | Departmental Labour | No. | 41 | 500 | 20500 | 0 | 20500 | 0 | 41 | 20500 | 0 | 20500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 235 | 2 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Department Work | Department Labour-Dev | No. | 14 | 500 | 7000 | 0 | 7000 | 0 | 14 | 7000 | 0 | 7000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Murum Filling | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 235 | 6 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House (L) Backside planter soil shifting | Contractor Profit-Mkt | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 24 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 235 | 4 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Department Work | Big Breaker | No. | 6 | 1300 | 7800 | 0 | 7800 | 0 | 6 | 7800 | 0 | 7800 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 235 | 2 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Department Work | Department Labour-Dev | No. | 80 | 500 | 40000 | 0 | 40000 | 0 | 80 | 40000 | 0 | 40000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | DEV. Murum Filling | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 235 | 0 | 10 Feb 2022 | PRAKASH CONTRACTOR | Goel House Misclaneous Work | Departmental Labour | No. | 14 | 500 | 7000 | 0 | 7000 | 0 | 14 | 7000 | 0 | 7000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 236 | 0 | 10 Feb 2022 | F. G. SHAIKH | Goel House Rabbit Shifting | Rabbit Shifting - AIE | Trips | 35 | 900 | 31500 | 0 | 31500 | 0 | 35 | 31500 | 0 | 31500 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 15 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 236 | 3 | 10 Feb 2022 | F. G. SHAIKH | Goel House Rabbit Shifting | Rabbit Shifting - AIE | Trips | 35 | 900 | 31500 | 0 | 31500 | 0 | 35 | 31500 | 0 | 31500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 15 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 236 | 2 | 10 Feb 2022 | F. G. SHAIKH | Goel House Rabbit Shifting | Rabbit Shifting - AIE | Trips | 10 | 900 | 9000 | 0 | 9000 | 0 | 10 | 9000 | 0 | 9000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 236 | 1 | 10 Feb 2022 | F. G. SHAIKH | Goel House store site tractor trip | Tractor Trips - SOS | No. | 25 | 900 | 22500 | 0 | 22500 | 0 | 25 | 22500 | 0 | 22500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 6th Flr to 7th Floor Lvl. | Rebar Coupler- BC | No. | 526 | 170 | 89420 | 16095.6 | 105515.6 | 2.5 | 0 | 0 | 0 | 0 | 526 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 5 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P5 to P6 Lvl. | Rebar Coupler- BC | No. | 592 | 100 | 59200 | 10656 | 69856 | 2.5 | 206.0036 | 20600.36 | 3708.06 | 24308.42 | 385.9964 | 45547.58 |  | 34.7979 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 5th Flr to 6th Floor Lvl. | Rebar Coupler- BC | No. | 306 | 170 | 52020 | 9363.6 | 61383.6 | 2.5 | 0 | 0 | 0 | 0 | 306 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 11th Flr to 12th Floor Lvl | Rebar Coupler- BC | No. | 264 | 100 | 26400 | 4752 | 31152 | 2.5 | 0 | 0 | 0 | 0 | 264 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 1 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P2 to P3 Lvl. | Rebar Coupler- BC | No. | 874 | 100 | 87400 | 15732 | 103132 | 2.5 | 864.016 | 86401.6 | 15552.28 | 101953.88 | 9.984 | 1178.12 |  | 98.8577 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 237 | 1 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P2 to P3 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | Dushant Gore | 10 Jun 2022
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 1st Flr to 2nd Floor Lvl. | Rebar Coupler- BC | No. | 366 | 170 | 62220 | 11199.6 | 73419.6 | 2.5 | 0 | 0 | 0 | 0 | 366 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 1 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | Dushant Gore | 10 Jun 2022
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 11th Flr to 12th Floor Lvl | Rebar Coupler- BC | No. | 80 | 170 | 13600 | 2448 | 16048 | 2.5 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 4 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P4 to P5 Lvl. | Rebar Coupler- BC | No. | 920 | 100 | 92000 | 16560 | 108560 | 2.5 | 919.0024 | 91900.24 | 16542.04 | 108442.28 | 0.9976 | 117.72 | Wing-1 Couplers P4 to P5 level- C8-38,C9-38,C11-114,C12-52,C13-52,C14-156,C15-114,C16-52,C17-52,C18-156,C26-28,C34-68. | 99.8916 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 12th Flr to 13th Floor Lvl | Reducer Coupler | No. | 98 | 165 | 16170 | 2910.6 | 19080.6 | 2.5 | 0 | 0 | 0 | 0 | 98 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 5 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P6 to Podium Lvl | Rebar Coupler- BC | No. | 410 | 100 | 41000 | 7380 | 48380 | 2.5 | 404.0003 | 40400.03 | 7272 | 47672.03 | 5.9997 | 707.97 |  | 98.5367 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 20th Flr to 21st Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 17th Flr to 18th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 13th Flr to 14th Floor Lvl | Rebar Coupler- BC | No. | 40 | 170 | 6800 | 1224 | 8024 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 2nd Flr to 3rd Floor Lvl. | Rebar Coupler- BC | No. | 210 | 100 | 21000 | 3780 | 24780 | 2.5 | 0 | 0 | 0 | 0 | 210 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 3rd Flr to 4th Floor Lvl. | Rebar Coupler- BC | No. | 384 | 170 | 65280 | 11750.4 | 77030.4 | 2.5 | 0 | 0 | 0 | 0 | 384 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 12th Flr to 13th Floor Lvl | Rebar Coupler- BC | No. | 210 | 100 | 21000 | 3780 | 24780 | 2.5 | 0 | 0 | 0 | 0 | 210 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 9th Flr to 10th Floor Lvl | Rebar Coupler- BC | No. | 78 | 170 | 13260 | 2386.8 | 15646.8 | 2.5 | 0 | 0 | 0 | 0 | 78 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 11th Flr to 12th Floor Lvl | Reducer Coupler | No. | 68 | 165 | 11220 | 2019.6 | 13239.6 | 2.5 | 0 | 0 | 0 | 0 | 68 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 6th Flr to 7th Floor Lvl. | Rebar Coupler- BC | No. | 170 | 100 | 17000 | 3060 | 20060 | 2.5 | 0 | 0 | 0 | 0 | 170 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 5th Flr to 6th Floor Lvl. | Rebar Coupler- BC | No. | 152 | 100 | 15200 | 2736 | 17936 | 2.5 | 0 | 0 | 0 | 0 | 152 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 12th Flr to 13th Floor Lvl | Rebar Coupler- BC | No. | 44 | 170 | 7480 | 1346.4 | 8826.4 | 2.5 | 0 | 0 | 0 | 0 | 44 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 4th Flr to 5th Floor Lvl. | Reducer Coupler | No. | 38 | 165 | 6270 | 1128.6 | 7398.6 | 2.5 | 0 | 0 | 0 | 0 | 38 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 13th Flr to 14th Floor Lvl | Rebar Coupler- BC | No. | 254 | 100 | 25400 | 4572 | 29972 | 2.5 | 0 | 0 | 0 | 0 | 254 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 27th Flr to 28th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 7th Flr to 8th Floor Lvl. | Rebar Coupler- BC | No. | 168 | 170 | 28560 | 5140.8 | 33700.8 | 2.5 | 0 | 0 | 0 | 0 | 168 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 1st Flr to 2nd Floor Lvl. | Rebar Coupler- BC | No. | 248 | 100 | 24800 | 4464 | 29264 | 2.5 | 0 | 0 | 0 | 0 | 248 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 18th Flr to 19th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 8th Flr to 9th Floor Lvl | Rebar Coupler- BC | No. | 260 | 100 | 26000 | 4680 | 30680 | 2.5 | 0 | 0 | 0 | 0 | 260 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 4th Flr to 5th Floor Lvl. | Rebar Coupler- BC | No. | 344 | 170 | 58480 | 10526.4 | 69006.4 | 2.5 | 0 | 0 | 0 | 0 | 344 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 28th Flr to Terr Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers Podium to 1st Floor Lvl. | Rebar Coupler- BC | No. | 366 | 170 | 62220 | 11199.6 | 73419.6 | 2.5 | 0 | 0 | 0 | 0 | 366 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 19th Flr to 20th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 25th Flr to 26th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 3 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P3 to P4 Lvl. | Rebar Coupler- BC | No. | 930 | 100 | 93000 | 16740 | 109740 | 2.5 | 923.0027 | 92300.27 | 16614.04 | 108914.31 | 6.9973 | 825.69 |  | 99.2476 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 22nd Flr to 23rd Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 3 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P2 to P3 Lvl. | Rebar Coupler- BC | No. | 56 | 100 | 5600 | 1008 | 6608 | 2.5 | 56 | 5600 | 1008 | 6608 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 24th Flr to 25th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 5th Flr to 6th Floor Lvl. | Reducer Coupler | No. | 38 | 165 | 6270 | 1128.6 | 7398.6 | 2.5 | 0 | 0 | 0 | 0 | 38 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 4th Flr to 5th Floor Lvl. | Rebar Coupler- BC | No. | 118 | 100 | 11800 | 2124 | 13924 | 2.5 | 0 | 0 | 0 | 0 | 118 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 9th Flr to 10th Floor Lvl | Reducer Coupler | No. | 6 | 165 | 990 | 178.2 | 1168.2 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 23rd Flr to 24th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 9th Flr to 10th Floor Lvl | Rebar Coupler- BC | No. | 272 | 100 | 27200 | 4896 | 32096 | 2.5 | 0 | 0 | 0 | 0 | 272 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 1 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 876 | 100 | 87600 | 15768 | 103368 | 2.5 | 869.0052 | 86900.52 | 15642.1 | 102542.62 | 6.9948 | 825.38 |  | 99.2015 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 13th Flr to 14th Floor Lvl | Reducer Coupler | No. | 4 | 165 | 660 | 118.8 | 778.8 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 8th Flr to 9th Floor Lvl | Rebar Coupler- BC | No. | 84 | 170 | 14280 | 2570.4 | 16850.4 | 2.5 | 0 | 0 | 0 | 0 | 84 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 15th Flr to 16th Floor Lvl | Rebar Coupler- BC | No. | 96 | 100 | 9600 | 1728 | 11328 | 2.5 | 0 | 0 | 0 | 0 | 96 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 3rd Flr to 4th Floor Lvl. | Rebar Coupler- BC | No. | 210 | 100 | 21000 | 3780 | 24780 | 2.5 | 0 | 0 | 0 | 0 | 210 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 6th Flr to 7th Floor Lvl. | Reducer Coupler | No. | 62 | 165 | 10230 | 1841.4 | 12071.4 | 2.5 | 0 | 0 | 0 | 0 | 62 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 10th Flr to 11th Floor Lvl | Rebar Coupler- BC | No. | 74 | 170 | 12580 | 2264.4 | 14844.4 | 2.5 | 0 | 0 | 0 | 0 | 74 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 26th Flr to 27th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 16th Flr to 17th Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 2nd Flr to 3rd Floor Lvl. | Rebar Coupler- BC | No. | 368 | 170 | 62560 | 11260.8 | 73820.8 | 2.5 | 0 | 0 | 0 | 0 | 368 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 0 | 10 Feb 2022 | POWER SPLICER | Wing-1 Substructure Coupling for Column Work(25mm&32mm Dia) | Rebar Coupler- BC | No. | 10 | 170 | 1700 | 306 | 2006 | 2.5 | 10 | 1700 | 306 | 2006 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 3rd Flr to 4th Floor Lvl. | Reducer Coupler | No. | 10 | 165 | 1650 | 297 | 1947 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 10th Flr to 11th Floor Lvl | Reducer Coupler | No. | 16 | 165 | 2640 | 475.2 | 3115.2 | 2.5 | 0 | 0 | 0 | 0 | 16 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 7th Flr to 8th Floor Lvl. | Reducer Coupler | No. | 60 | 165 | 9900 | 1782 | 11682 | 2.5 | 0 | 0 | 0 | 0 | 60 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 8th Flr to 9th Floor Lvl | Reducer Coupler | No. | 76 | 165 | 12540 | 2257.2 | 14797.2 | 2.5 | 0 | 0 | 0 | 0 | 76 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers 2nd Flr to 3rd Floor Lvl. | Reducer Coupler | No. | 30 | 165 | 4950 | 891 | 5841 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 14th Flr to 15th Floor Lvl | Reducer Coupler | No. | 8 | 165 | 1320 | 237.6 | 1557.6 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 2 | 10 Feb 2022 | POWER SPLICER | Wing 1 - Rebar Couplers Rebar Coupling P2 to P3 Lvl. | Rebar Coupler- BC | No. | 870 | 100 | 87000 | 15660 | 102660 | 2.5 | 92 | 9200 | 1656 | 10856 | 778 | 91804 |  | 10.5747 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 10th Flr to 11th Floor Lvl | Rebar Coupler- BC | No. | 322 | 100 | 32200 | 5796 | 37996 | 2.5 | 0 | 0 | 0 | 0 | 322 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 21st Flr to 22nd Floor Lvl | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 237 | 0 | 10 Feb 2022 | POWER SPLICER | Wing-1 Substructure Coupling for Column Work(25mm&32mm Dia) | Rebar Coupler- BC | No. | 2200 | 100 | 220000 | 39600 | 259600 | 2.5 | 2163.0048 | 216300.48 | 38934.1 | 255234.58 | 36.9952 | 4365.42 |  | 98.3184 |  | DUSHANT GORE | chetan.jewalikar | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 . Rebar Couplers Podium to 1st Floor Lvl. | Rebar Coupler- BC | No. | 248 | 100 | 24800 | 4464 | 29264 | 2.5 | 0 | 0 | 0 | 0 | 248 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Coupler 14th Flr to 15th Floor Lvl | Rebar Coupler- BC | No. | 188 | 100 | 18800 | 3384 | 22184 | 2.5 | 0 | 0 | 0 | 0 | 188 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 237 | 6 | 10 Feb 2022 | POWER SPLICER | Wing 1 Rebar Couplers 7th Flr to 8th Floor Lvl. | Rebar Coupler- BC | No. | 226 | 100 | 22600 | 4068 | 26668 | 2.5 | 0 | 0 | 0 | 0 | 226 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Feb 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 238 | 0 | 11 Feb 2022 | AUTOHOMES | Goel House AMC charges for home automation | AMC Charges | Month | 12 | 5000 | 60000 | 10800 | 70800 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE |  | Construction | 1900-01-01 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 239 | 0 | 11 Feb 2022 | A O SMITH INDIA WATER PRODUCTS PRIVATE LIMITED | Goel House AMC Charges AO smith water purifier | AMC Charges | Month | 12 | 437.85 | 5254.2 | 945.76 | 6199.96 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 12 Feb 2022 |  | Admin. Indirect Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 240 | 0 | 12 Feb 2022 | 99acres.com | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 3 | 100000 | 300000 | 54000 | 354000 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | GANGA ASMI WAKAD PROJECT SALES PROMOTION WITH MARKETING THROUGH ONLINE PORTAL 99ACRES.COM LEAD GENERATION FOR 3 MONTHS | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 03 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl)Qty Diff Elevational Chajja RCC | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 5 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium Lvl) Qty Diff Elevational Chajja R | RCC Superstructure (B-up area) | Sq.Ft | 258.34 | 200 | 51668 | 9300.24 | 60968.24 | 2.5 | 0 | 0 | 0 | 0 | 258.34 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking PCC Work | PCC | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 10426 | 52130 | 9383.4 | 61513.4 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 270 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | Dushant Gore | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 165 | 860145 | 154826.1 | 1014971.1 | 2.5 | 5213 | 860145 | 154826.1 | 1014971.1 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 155 | 808015 | 145442.7 | 953457.7 | 2.5 | 5213 | 808015 | 145442.7 | 953457.7 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 1 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - RCC Retaining wall Shuttering (L) | Shuttering Work-Mkt | Sq.m. | 177 | 500 | 88500 | 15930 | 104430 | 2.5 | 127.655 | 63827.5 | 11488.96 | 75316.46 | 49.345 | 29113.54 |  | 72.1215 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 175 | 912275 | 164209.5 | 1076484.5 | 2.5 | 5213 | 912275 | 164209.5 | 1076484.5 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Qty Diff Elevational Chajja RCC | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Qty Diff Elevational Chajja RCC | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Qty Diff Elevational Chajja RCC | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 265.1 | 1381966.3 | 248753.94 | 1630720.24 | 2.5 | 5213 | 1381966.3 | 248753.94 | 1630720.24 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) 1st Slab RCC slab,beam,ST,Shear w | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 165 | 860145 | 154826.1 | 1014971.1 | 2.5 | 5213 | 860145 | 154826.1 | 1014971.1 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) 1st Slab RCC slab,beam,ST,Shear w | RCC Superstructure (B-up area) | Sq.Ft | 0 | 255 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 4 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 1803 | 200 | 360600 | 64908 | 425508 | 2.5 | 1000 | 200000 | 36000 | 236000 | 803 | 189508 |  | 55.4631 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking plinth beam | RCC Beam | Sq.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 4 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 1803 | 200 | 360600 | 64908 | 425508 | 2.5 | 1000 | 200000 | 36000 | 236000 | 803 | 189508 |  | 55.4631 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 265.1 | 1381966.3 | 248753.94 | 1630720.24 | 2.5 | 5213 | 1381966.3 | 248753.94 | 1630720.24 | 0 | 0 |  | 100 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | Quality (BC) | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) 1st Slab RCC slab,beam,ST,Shear w | RCC Superstructure (B-up area) | Sq.Ft | 0 | 255 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Qty Diff Elevational Chajja RCC | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 155 | 808015 | 145442.7 | 953457.7 | 2.5 | 5213 | 808015 | 145442.7 | 953457.7 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | Schedule- BC | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 0 | 28.89 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) 1st Slab RCC slab,beam,ST,Shear w | RCC Superstructure (B-up area) | Sq.Ft | 0 | 270 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl)Qty Diff Elevational Chajja RCC | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) 1st Slab RCC slab,beam,ST,Shear w | RCC Superstructure (B-up area) | Sq.Ft | 0 | 270 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 4 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 1803 | 200 | 360600 | 64908 | 425508 | 2.5 | 1000 | 200000 | 36000 | 236000 | 803 | 189508 |  | 55.4631 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 270 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking PCC Work | PCC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | B.C. Building Common Items | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Qty Diff Elevational Chajja RCC | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 10426 | 28.91 | 301363.53 | 54245.44 | 355608.97 | 2.5 | 10426 | 301363.53 | 54245.44 | 355608.97 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 175 | 912275 | 164209.5 | 1076484.5 | 2.5 | 5211.951 | 912091.43 | 164176.46 | 1076267.89 | 1.049 | 216.62 |  | 99.9799 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 433.84 | 200 | 86768 | 15618.24 | 102386.24 | 2.5 | 0 | 0 | 0 | 0 | 433.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 1 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - RCC Retaining wall Steel Binding (L) | Reinforcement (L) | Kgs | 3490 | 8 | 27920 | 5025.6 | 32945.6 | 2.5 | 2236 | 17888 | 3219.84 | 21107.84 | 1254 | 11837.76 |  | 64.0688 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 433.84 | 200 | 86768 | 15618.24 | 102386.24 | 2.5 | 0 | 0 | 0 | 0 | 433.84 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Qty Diff Elevational Chajja RCC | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 433.84 | 200 | 86768 | 15618.24 | 102386.24 | 2.5 | 433.84 | 86768 | 15618.24 | 102386.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Qty Diff Elevational Chajja RCC | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) 1st Slab RCC slab,beam,ST,Shear w | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jewalikar |  | construction open | 15 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 15 Feb 2022
GANGA ASMI | 241 | 4 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | RCC Superstructure (B-up area) | Sq.Ft | 1848 | 200 | 369600 | 66528 | 436128 | 2.5 | 1000 | 200000 | 36000 | 236000 | 848 | 200128 |  | 54.1126 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl)Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 433.84 | 400 | 173536 | 31236.48 | 204772.48 | 2.5 | 201.4276 | 80571.04 | 14502.78 | 95073.82 | 232.4124 | 109698.66 |  | 46.429 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 1 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - RCC retaining wall Concrete (L) | Concreting Work | Cu.Mtrs | 55.148 | 300 | 16544.4 | 2978 | 19522.4 | 2.5 | 30.66 | 9198 | 1655.64 | 10853.64 | 24.488 | 8668.76 | 1. RT Wall- 43.42 cum. 2. Tie Beam at G.L- 9.258 cum. 3. Elevational Brackets- 2.47 cum. | 55.5959 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl)Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 433.84 | 200 | 86768 | 15618.24 | 102386.24 | 2.5 | 201.42 | 40284 | 7251.12 | 47535.12 | 232.42 | 54851.12 |  | 46.4273 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking PCC Work | PCC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | chetan.jewalikar |  | construction open | 15 Feb 2022 |  | B.C. Building Common Items | Cancelled | skmishra | 15 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 4 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 1803 | 200 | 360600 | 64908 | 425508 | 2.5 | 1000 | 200000 | 36000 | 236000 | 803 | 189508 |  | 55.4631 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 241 | 4 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 858 | 400 | 343200 | 61776 | 404976 | 2.5 | 400 | 160000 | 28800 | 188800 | 458 | 216176 |  | 46.62 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) 1st Slab RCC slab,beam,ST,Shear w | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking plinth beam | RCC Beam | Sq.Ft | 10426 | 55 | 573430 | 103217.4 | 676647.4 | 2.5 | 10425.9999 | 573429.99 | 103217.4 | 676647.39 | 0.0001 | 0.01 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 160 | 834080 | 150134.4 | 984214.4 | 2.5 | 5212.7654 | 834042.46 | 150127.66 | 984170.12 | 0.2346 | 44.28 |  | 99.9955 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) 1st Slab RCC slab,beam,ST,Shear w | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 160 | 834080 | 150134.4 | 984214.4 | 2.5 | 5212.6872 | 834029.95 | 150125.38 | 984155.33 | 0.3128 | 59.07 |  | 99.994 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Footing & Column | Footing & Column | Sq.Ft | 10426 | 65 | 677690 | 121984.2 | 799674.2 | 2.5 | 10426 | 677690 | 121984.2 | 799674.2 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Qty Diff Elevational Chajja RCC | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Bldg RCC slab,beam,ST,S | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 10426 | 6 | 62556 | 11260.08 | 73816.08 | 0 | 10426 | 62556 | 11260.08 | 73816.08 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 14 Jul 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 7th Slab (Girder) Bldg RCC slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 270 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 3 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Qty Diff Elevational Chajja RCC | RCC Superstructure (B-up area) | Sq.Ft | 0 | 260 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | ADITYA CHOUGULE | 16 Nov 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 275 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Footing & Column | Footing & Column | Sq.Ft | 0 | 65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 260 | 1355380 | 243968.4 | 1599348.4 | 2.5 | 5213 | 1355380 | 243968.4 | 1599348.4 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5213 | 260 | 1355380 | 243968.4 | 1599348.4 | 2.5 | 5213 | 1355380 | 239468.4 | 1594848.4 | 0 | 4500 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | Quality (BC) | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 241 | 0 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Bldg slab,beam,ST,Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 275 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 15 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 16 Feb 2022
GANGA ASMI | 241 | 2 | 14 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Bldg RCC slab,beam,ST,Shear wall | Schedule- BC | Sq.Ft | 10426 | 5 | 52130 | 9383.4 | 61513.4 | 2.5 | 0 | 0 | 0 | 0 | 10426 | 0 |  | 0 |  | aditya chougule | Swapnil Erande | construction open | 15 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 242 | 0 | 14 Feb 2022 | NAJAMA HANIF SHAIKH | Garden Work | Misc. Garden work | No. | 1 | 278569 | 278569 | 0 | 278569 | 0 | 1 | 278569 | 0 | 278569 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | S OH Repair & Maintenance | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 938.1569 | 180 | 168868.24 | 30396.28 | 199264.52 | 2.5 | 0 | 0 | 0 | 0 | 938.1569 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Footing & Column | Footing & Column | Sq.Ft | 2486.93 | 55 | 136781.15 | 24620.6 | 161401.75 | 2.5 | 0 | 0 | 0 | 0 | 2486.93 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking PCC Work | PCC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | B.C. Building Common Items | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 938.363 | 155 | 145446.27 | 26180.32 | 171626.59 | 2.5 | 0 | 0 | 0 | 0 | 938.363 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 1472.545 | 6 | 8835.27 | 1590.34 | 10425.61 | 0 | 1472.545 | 8835.27 | 1590.34 | 10425.61 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Foreclose | DUSHANT.GORE | 31 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 938.1569 | 170 | 159486.67 | 28707.6 | 188194.27 | 2.5 | 0 | 0 | 0 | 0 | 938.1569 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Footing & Column | Footing & Column | Sq.Ft | 1472.5 | 55 | 80987.5 | 14577.76 | 95565.26 | 2.5 | 1472.5 | 80987.5 | 14577.76 | 95565.26 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 31 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1979.715 | 170 | 336551.55 | 60579.28 | 397130.83 | 2.5 | 0 | 0 | 0 | 0 | 1979.715 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1041.5581 | 180 | 187480.46 | 33746.48 | 221226.94 | 2.5 | 1041.5581 | 187480.46 | 33746.48 | 221226.94 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 938.1569 | 170 | 159486.67 | 28707.6 | 188194.27 | 2.5 | 0 | 0 | 0 | 0 | 938.1569 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Footing & Column | Footing & Column | Sq.Ft | 0 | 65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1979.715 | 155 | 306855.83 | 55234.04 | 362089.87 | 2.5 | 434.51 | 67349.05 | 12122.82 | 79471.87 | 1545.205 | 282618 |  | 21.9481 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1979.715 | 180 | 356348.7 | 64142.76 | 420491.46 | 2.5 | 0 | 0 | 0 | 0 | 1979.715 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 914.605 | 180 | 164628.9 | 29633.2 | 194262.1 | 2.5 | 0 | 0 | 0 | 0 | 914.605 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 31 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 3935.32 | 5 | 19676.6 | 3541.78 | 23218.38 | 2.5 | 0 | 0 | 0 | 0 | 3935.32 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 938.363 | 155 | 145446.27 | 26180.32 | 171626.59 | 2.5 | 0 | 0 | 0 | 0 | 938.363 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 2486.885 | 6 | 14921.31 | 2685.84 | 17607.15 | 2.5 | 0 | 0 | 0 | 0 | 2486.885 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1041 | 180 | 187380 | 33728.4 | 221108.4 | 2.5 | 1041 | 187380 | 33728.4 | 221108.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1979.715 | 180 | 356348.7 | 64142.76 | 420491.46 | 2.5 | 0 | 0 | 0 | 0 | 1979.715 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking plinth beam | RCC Beam | Sq.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 31 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1979.715 | 155 | 306855.83 | 55234.04 | 362089.87 | 2.5 | 0 | 0 | 0 | 0 | 1979.715 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1041.352 | 155 | 161409.56 | 29053.72 | 190463.28 | 2.5 | 1041.352 | 161409.56 | 29053.72 | 190463.28 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 3935.32 | 5 | 19676.6 | 3541.78 | 23218.38 | 2.5 | 0 | 0 | 0 | 0 | 3935.32 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 6th Slab (Podium floor Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 3959.43 | 19 | 75229.17 | 13541.26 | 88770.43 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1041.5581 | 170 | 177064.88 | 31871.68 | 208936.56 | 2.5 | 1041.5581 | 177064.88 | 31871.68 | 208936.56 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1979.715 | 170 | 336551.55 | 60579.28 | 397130.83 | 2.5 | 0 | 0 | 0 | 0 | 1979.715 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking PCC Work | PCC | Sq.Ft | 2486.83 | 5 | 12434.15 | 2238.14 | 14672.29 | 2.5 | 0 | 0 | 0 | 0 | 2486.83 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1041.5581 | 170 | 177064.88 | 31871.68 | 208936.56 | 2.5 | 1041.5581 | 177064.88 | 31871.68 | 208936.56 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 0 | 29 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | Schedule- BC | Sq.Ft | 3959.43 | 5 | 19797.15 | 3563.48 | 23360.63 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking plinth beam | RCC Beam | Sq.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 5th Slab (P6 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 3rd Slab (P4 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking PCC Work | PCC | Sq.Ft | 1472.5 | 5 | 7362.5 | 1325.26 | 8687.76 | 2.5 | 1472.5 | 7362.5 | 1325.26 | 8687.76 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | B.C. Building Common Items | Foreclose | DUSHANT.GORE | 31 Oct 2023
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 4th Slab (P5 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing-1 Parking plinth beam | RCC Beam | Sq.Ft | 3959.43 | 45 | 178174.35 | 32071.38 | 210245.73 | 2.5 | 0 | 0 | 0 | 0 | 3959.43 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 17 Feb 2022 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 2nd Slab (P3 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 17 Feb 2022 |  | 02 RCC WORK | Cancelled | skmishra | 17 Feb 2022
GANGA ASMI | 243 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Wing 1 - 1st Slab (P2 Lvl) Podium RCC Slab,beam,SW | RCC Superstructure (B-up area) | Sq.Ft | 1041.352 | 155 | 161409.56 | 29053.72 | 190463.28 | 2.5 | 1041.352 | 161409.56 | 29053.72 | 190463.28 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 17 Feb 2022 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 30 Oct 2023
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | Dushant Gore | 02 Sep 2022
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | ADITYA CHOUGULE | 04 Oct 2022
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | 02 RCC WORK | Cancelled | Dushant Gore | 16 Feb 2022
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | ADITYA CHOUGULE | 04 Oct 2022
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | ADITYA CHOUGULE | 04 Oct 2022
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | Dushant Gore | 02 Sep 2022
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | Dushant Gore | 02 Sep 2022
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | Dushant Gore | 02 Sep 2022
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 0 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | Dushant Gore | 02 Sep 2022
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | ADITYA CHOUGULE | 04 Oct 2022
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | Dushant Gore | 02 Sep 2022
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 244 | 0 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | ADITYA CHOUGULE | 04 Oct 2022
GANGA ASMI | 244 | 1 | 16 Feb 2022 | SAIRAJ CONSTRUCTION | Ganga Asmi SuperStucture RMC Pump Charges | Pump Hiring for RMC | Month | 1 | 200000 | 200000 | 36000 | 236000 | 0 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 02 RCC WORK | Foreclose | DUSHANT.GORE | 21 Nov 2023
GANGA ASMI | 245 | 1 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Site Infra Sludge removing for PCC & Footing - wing 2 | Tractor & Bobcat | Day | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 24 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Cancelled | Dushant Gore | 05 Nov 2022
GANGA ASMI | 245 | 3 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Misc. Development work | JCB Charges | Hrs | 50 | 900 | 45000 | 8100 | 53100 | 0 | 50 | 45000 | 8100 | 53100 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 245 | 1 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Site Infra Sludge removing for PCC & Footing - wing 2 | Bobcat Hiring Charges | Hrs | 40 | 600 | 24000 | 4320 | 28320 | 0 | 40 | 24000 | 4320 | 28320 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 245 | 2 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Labour Camp Work | JCB Charges | Hrs | 30 | 900 | 27000 | 4860 | 31860 | 0 | 30 | 27000 | 4860 | 31860 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 245 | 1 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Site Infra Misc Work | JCB Hiring | Hrs | 64 | 850 | 54400 | 9792 | 64192 | 0 | 62.9998 | 53549.83 | 9638.98 | 63188.81 | 1.0002 | 1003.19 |  | 98.4372 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 245 | 2 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Labour Camp Work | Tractor Trip - Dld | No. | 50 | 400 | 20000 | 3600 | 23600 | 0 | 50 | 20000 | 0 | 20000 | 0 | 3600 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 245 | 1 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Site Infra Misc Work | Bobcat Hiring Charges | Hrs | 120 | 600 | 72000 | 12960 | 84960 | 0 | 120 | 72000 | 12960 | 84960 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 245 | 0 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Site Infra Misc Work | JCB Hiring | Hrs | 16 | 850 | 13600 | 2448 | 16048 | 0 | 15.9166 | 13529.11 | 2435.24 | 15964.35 | 0.0834 | 83.65 |  | 99.4788 |  | Dushant Gore | chetan.jewalikar | construction open | 24 Feb 2022 |  | 01 EARTHWORK & ROADWORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 245 | 3 | 16 Feb 2022 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Misc. Development work | Tractor Trip - DCW | Trips | 70 | 400 | 28000 | 5040 | 33040 | 0 | 40 | 16000 | 0 | 16000 | 30 | 17040 |  | 57.1429 |  | DUSHANT.GORE | Swapnil Erande | construction open | 24 Feb 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 246 | 0 | 17 Feb 2022 | GREENCON INFRATECH SOLUTION | Goel House Rennovation Aerocon Panel Work | Aerocon Partition (M+L) BC | Sq.Ft | 340 | 150 | 51000 | 9180 | 60180 | 0 | 0 | 0 | 0 | 0 | 340 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 247 | 0 | 17 Feb 2022 | MAGICBRICKS REALTY SERVICES LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 3 | 100000 | 300000 | 54000 | 354000 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | GANGA ASMI WAKAD PROJECT DIGITAL, ONLINE SOCIAL MEDIA THROUGH SALES PROMOTION WITH BRANDING THROUGH MAGICBRICKS.COM FOR 3 MONTH | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 03 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 248 | 0 | 18 Feb 2022 | RAJYOG ENTERPRISES | Goel House Toughend Glass Removing Bed 4,5,6,7 - 1 No. | Glass removing -Mkt | Sq.Ft | 112 | 125 | 14000 | 2520 | 16520 | 2.5 | 0 | 0 | 0 | 0 | 112 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 18 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 248 | 0 | 18 Feb 2022 | RAJYOG ENTERPRISES | Goel House Toughend Glass Removing Bed 4,5,6,7 - 1 No. | Glass removing -Mkt | Sq.Ft | 460 | 125 | 57500 | 10350 | 67850 | 0 | 460 | 57500 | 10350 | 67850 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 18 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 248 | 0 | 18 Feb 2022 | RAJYOG ENTERPRISES | Goel House Toughend Glass Removing Bed 4,5,6,7 - 1 No. | Glass removing -Mkt | Sq.Ft | 800 | 125 | 100000 | 18000 | 118000 | 2.5 | 484 | 60500 | 10890 | 71390 | 316 | 46610 |  | 60.5 |  | Dushant Gore | chetan.jewalikar | construction open | 18 Feb 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 249 | 0 | 19 Feb 2022 | JALDIP DILIP SHAH | Goel House rennovation-supervision work | Supervision Charges- BRE | No. | 0 | 700000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Cancelled | skmishra | 09 Mar 2022
GANGA ASMI | 249 | 0 | 19 Feb 2022 | JALDIP DILIP SHAH | Goel House rennovation-supervision work | Supervision Charges- BRE | No. | 0 | 3000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Cancelled | SKMISHRA | 12 Mar 2022
GANGA ASMI | 249 | 0 | 19 Feb 2022 | JALDIP DILIP SHAH | Goel House rennovation-supervision work | Supervision Charges- BRE | No. | 1 | 2500000 | 2500000 | 0 | 2500000 | 0 | 0.68 | 1700000 | 0 | 1700000 | 0.32 | 800000 |  | 68 |  | Dushant Gore | SKMISHRA | construction open | 09 Mar 2022 |  | Admin. Indirect Expenses | Approved | SKMISHRA | 1900-01-01
GANGA ASMI | 250 | 1 | 21 Feb 2022 | VIKAS GARADE | 52nd Year National Safety Week 2022 | Miscellaneous Expenses | No. | 1 | 3500 | 3500 | 0 | 3500 | 0 | 1 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Mar 2022 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 250 | 0 | 21 Feb 2022 | VIKAS GARADE | Site Expenses | Miscellaneous Expenses - SO | No. | 1 | 2800 | 2800 | 0 | 2800 | 0 | 1 | 2800 | 0 | 2800 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 250 | 0 | 21 Feb 2022 | VIKAS GARADE | Site Expenses | Miscellaneous Expenses - SO | No. | 1 | 3500 | 3500 | 0 | 3500 | 2.5 | 1 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 250 | 0 | 21 Feb 2022 | VIKAS GARADE | Site Expenses | Miscellaneous Expenses - SO | No. | 1 | 1750 | 1750 | 0 | 1750 | 0 | 1 | 1750 | 0 | 1750 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 11 Mar 2022 |  | S OH Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 250 | 2 | 21 Feb 2022 | VIKAS GARADE | Wing 1 - MS Staircase dismantling work | Dismantling work | No. | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 38 | 20 | 760 | 136.8 | 896.8 | 2.5 | 38 | 760 | 136.8 | 896.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 6 Sq.mm Cable | R.Ft | 63 | 50 | 3150 | 567 | 3717 | 2.5 | 63 | 3150 | 567 | 3717 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Single Pole MCB Fixing | No. | 6 | 200 | 1200 | 216 | 1416 | 2.5 | 6 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 10 | 285 | 2850 | 513 | 3363 | 2.5 | 10 | 2850 | 513 | 3363 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Single Pole MCB Fixing | No. | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 02 Apr 2022
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 1 | 210 | 210 | 37.8 | 247.8 | 2.5 | 1 | 210 | 37.8 | 247.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | LIght Point - Mkt | No. | 3 | 285 | 855 | 153.9 | 1008.9 | 2.5 | 3 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | MCB 4 Pole Fixing | No. | 4 | 1000 | 4000 | 720 | 4720 | 2.5 | 4 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 0 | 285 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 13 Amp Plug Point Secondary | No. | 3 | 250 | 750 | 135 | 885 | 2.5 | 3 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | CAT 6 Cable- | R.Ft | 45 | 13 | 585 | 105.3 | 690.3 | 2.5 | 45 | 585 | 105.3 | 690.3 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 45 | 25 | 1125 | 202.5 | 1327.5 | 2.5 | 45 | 1125 | 202.5 | 1327.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | secondary light point | No. | 5 | 150 | 750 | 135 | 885 | 2.5 | 5 | 750 | 135 | 885 | 0 | 0 | Secondary Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 34 | 25 | 850 | 153 | 1003 | 2.5 | 34 | 850 | 153 | 1003 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Speaker Point - BC | No. | 6 | 200 | 1200 | 216 | 1416 | 2.5 | 6 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 28 | 50 | 1400 | 252 | 1652 | 2.5 | 28 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Street Light Fixing - UTI | No. | 8 | 150 | 1200 | 216 | 1416 | 2.5 | 8 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 6 Sq.mm Cable | R.Ft | 164 | 50 | 8200 | 1476 | 9676 | 2.5 | 164 | 8200 | 1476 | 9676 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 1 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 58 | 25 | 1450 | 261 | 1711 | 2.5 | 58 | 1450 | 261 | 1711 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Removing work.-SOS | No. | 1 | 450 | 450 | 81 | 531 | 0 | 1 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 way MCB Encloser Box (L) | No. | 2 | 200 | 400 | 72 | 472 | 2.5 | 2 | 400 | 72 | 472 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 13 Amp Plug Point | No. | 0 | 350 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 02 Apr 2022
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Fan Point | No. | 3 | 350 | 1050 | 189 | 1239 | 2.5 | 3 | 1050 | 189 | 1239 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 115 | 20 | 2300 | 414 | 2714 | 2.5 | 97 | 1940 | 349.2 | 2289.2 | 18 | 424.8 |  | 84.3478 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Tata Sky DTH | No. | 2 | 450 | 900 | 162 | 1062 | 2.5 | 2 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 6 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Chandelier Removing and Fixing | Chandelier Removing & Fixing | No. | 4 | 5000 | 20000 | 3600 | 23600 | 2.5 | 4 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 24 | 25 | 600 | 108 | 708 | 2.5 | 24 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 13 Amp Plug Point | No. | 3 | 250 | 750 | 135 | 885 | 2.5 | 3 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 54 | 25 | 1350 | 243 | 1593 | 2.5 | 54 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 60 | 15 | 900 | 162 | 1062 | 2.5 | 60 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Fan Fixing | No. | 3 | 200 | 600 | 108 | 708 | 2.5 | 3 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 110 | 20 | 2200 | 396 | 2596 | 2.5 | 0 | 0 | 0 | 0 | 110 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 6 Sq.mm Cable | R.Ft | 164 | 50 | 8200 | 1476 | 9676 | 2.5 | 164 | 8200 | 1476 | 9676 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | LIght Point - Mkt | No. | 3 | 285 | 855 | 153.9 | 1008.9 | 2.5 | 3 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | CAT 6 Cable- | R.Ft | 120 | 13 | 1560 | 280.8 | 1840.8 | 2.5 | 120 | 1560 | 280.8 | 1840.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 | Fan point- 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Light Fitting Fixing | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Automation Box Fixing | No. | 1 | 900 | 900 | 162 | 1062 | 2.5 | 1 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 125 | 20 | 2500 | 450 | 2950 | 2.5 | 101 | 2020 | 363.6 | 2383.6 | 24 | 566.4 |  | 80.8 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker Fixing Point- | No. | 4 | 200 | 800 | 144 | 944 | 2.5 | 4 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 2 Pole Fixing | No. | 7 | 600 | 4200 | 756 | 4956 | 2.5 | 7 | 4200 | 756 | 4956 | 0 | 0 | Two Pole MCB (Wire Termination) with Fixing. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 68 | 25 | 1700 | 306 | 2006 | 2.5 | 68 | 1700 | 306 | 2006 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 38 | 20 | 760 | 136.8 | 896.8 | 2.5 | 38 | 760 | 136.8 | 896.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 45 | 25 | 1125 | 202.5 | 1327.5 | 2.5 | 45 | 1125 | 202.5 | 1327.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Single Pole MCB Fixing | No. | 151 | 200 | 30200 | 5436 | 35636 | 2.5 | 151 | 30200 | 5436 | 35636 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | MCB Single Pole | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | MCB 2 Pole Fixing | No. | 1 | 600 | 600 | 108 | 708 | 2.5 | 1 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 158 | 22 | 3476 | 625.68 | 4101.68 | 2.5 | 158 | 3476 | 625.68 | 4101.68 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 125 | 20 | 2500 | 450 | 2950 | 2.5 | 120 | 2400 | 432 | 2832 | 5 | 118 |  | 96 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 250 Amp Busbar fixing | No. | 1 | 3500 | 3500 | 630 | 4130 | 2.5 | 1 | 3500 | 630 | 4130 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 80mm PVC Channel Patti Fixing | R.Ft | 183 | 45 | 8235 | 1482.3 | 9717.3 | 2.5 | 183 | 8235 | 1482.3 | 9717.3 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 25 | 20 | 500 | 90 | 590 | 2.5 | 25 | 500 | 90 | 590 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 Way MCB Box w/ MCB -BC | No. | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA CHOUGULE | 24 Sep 2022
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 10 Sq.mm 4 Core Flexible Cable | R.Ft | 25 | 150 | 3750 | 675 | 4425 | 2.5 | 25 | 3750 | 675 | 4425 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 145 | 20 | 2900 | 522 | 3422 | 2.5 | 141 | 2820 | 507.6 | 3327.6 | 4 | 94.4 |  | 97.2414 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 4 Sqmm Cable (L) | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Cancelled | Aditya Chougule | 25 May 2022
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Schandeliour Fixing- BCo | No. | 4 | 5000 | 20000 | 3600 | 23600 | 2.5 | 4 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 55 | 25 | 1375 | 247.5 | 1622.5 | 2.5 | 55 | 1375 | 247.5 | 1622.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB Fixing BCP | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Two way Point - DCH | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 13 Amp Plug Point | No. | 0 | 350 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 17 Mar 2022
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 128 | 22 | 2816 | 506.88 | 3322.88 | 2.5 | 128 | 2816 | 506.88 | 3322.88 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Steam Sensor Box (L) | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 0 | 285 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 220 | 15 | 3300 | 594 | 3894 | 2.5 | 220 | 3300 | 594 | 3894 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 55 | 25 | 1375 | 247.5 | 1622.5 | 2.5 | 55 | 1375 | 247.5 | 1622.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | CCTV Camera wire | R.Ft | 20 | 15 | 300 | 54 | 354 | 2.5 | 20 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 0 | 285 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 4 Sqmm Cable - MKt | R.Ft | 10 | 22 | 220 | 39.6 | 259.6 | 2.5 | 10 | 220 | 39.6 | 259.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 110 | 22 | 2420 | 435.6 | 2855.6 | 2.5 | 110 | 2420 | 435.6 | 2855.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 56 | 50 | 2800 | 504 | 3304 | 2.5 | 56 | 2800 | 504 | 3304 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 87 | 15 | 1305 | 234.9 | 1539.9 | 2.5 | 87 | 1305 | 234.9 | 1539.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 12 | 50 | 600 | 108 | 708 | 2.5 | 12 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 37 | 25 | 925 | 166.5 | 1091.5 | 2.5 | 37 | 925 | 166.5 | 1091.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 16 AMP Plug Point - Mkt | No. | 20 | 425 | 8500 | 1530 | 10030 | 2.5 | 20 | 8500 | 1530 | 10030 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | primary light point from DB | No. | 6 | 285 | 1710 | 307.8 | 2017.8 | 2.5 | 6 | 1710 | 307.8 | 2017.8 | 0 | 0 | Primary Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | LED Strip Fixing | R.Ft | 30 | 50 | 1500 | 270 | 1770 | 2.5 | 30 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | AC Point BC | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 12 | 50 | 600 | 108 | 708 | 2.5 | 12 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 61 | 25 | 1525 | 274.5 | 1799.5 | 2.5 | 61 | 1525 | 274.5 | 1799.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 56 | 25 | 1400 | 252 | 1652 | 2.5 | 56 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 16 AMP Plug Point - Mkt | No. | 2 | 425 | 850 | 153 | 1003 | 2.5 | 2 | 850 | 153 | 1003 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 way MCB Encloser Box (L) | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Double Fan Fastener & Fan Fixing | No. | 0 | 375 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 May 2022
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 133 | 50 | 6650 | 1197 | 7847 | 2.5 | 127 | 6350 | 1143 | 7493 | 6 | 354 |  | 95.4887 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | AC Point BC | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Light Point DPo | No. | 1 | 285 | 285 | 51.3 | 336.3 | 2.5 | 1 | 285 | 51.3 | 336.3 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 68 | 25 | 1700 | 306 | 2006 | 2.5 | 68 | 1700 | 306 | 2006 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 68 | 25 | 1700 | 306 | 2006 | 2.5 | 68 | 1700 | 306 | 2006 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Exhaust Fan fixing | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 34 | 25 | 850 | 153 | 1003 | 2.5 | 34 | 850 | 153 | 1003 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Double Fan Fastener & Fan Fixing | No. | 0 | 375 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 May 2022
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 98 | 50 | 4900 | 882 | 5782 | 2.5 | 98 | 4900 | 882 | 5782 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 138 | 20 | 2760 | 496.8 | 3256.8 | 2.5 | 60 | 1200 | 216 | 1416 | 78 | 1840.8 |  | 43.4783 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Light Point DPo | No. | 8 | 285 | 2280 | 410.4 | 2690.4 | 2.5 | 8 | 2280 | 410.4 | 2690.4 | 0 | 0 | Street Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 5 | 50 | 250 | 45 | 295 | 2.5 | 5 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 10 sqmm TPN | R.Ft | 43 | 70 | 3010 | 541.8 | 3551.8 | 2.5 | 43 | 3010 | 541.8 | 3551.8 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 10 | 20 | 200 | 36 | 236 | 2.5 | 10 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 1 | 285 | 285 | 51.3 | 336.3 | 2.5 | 1 | 285 | 51.3 | 336.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 20 | 50 | 1000 | 180 | 1180 | 2.5 | 20 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 108 | 20 | 2160 | 388.8 | 2548.8 | 2.5 | 44 | 880 | 158.4 | 1038.4 | 64 | 1510.4 |  | 40.7407 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Light Fitting Fixing | No. | 3 | 150 | 450 | 81 | 531 | 2.5 | 3 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 10 Sq.mm 4 Core Flexible Cable | R.Ft | 25 | 70 | 1750 | 315 | 2065 | 2.5 | 25 | 1750 | 315 | 2065 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | RCCB 4 Pole | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Single Pole MCB Fixing | No. | 20 | 200 | 4000 | 720 | 4720 | 2.5 | 20 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 1 | 285 | 285 | 51.3 | 336.3 | 2.5 | 1 | 285 | 51.3 | 336.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 75mm x75mm PVC Channel Patti | R.Ft | 30 | 20 | 600 | 108 | 708 | 2.5 | 30 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | LED Point (L) | No. | 6 | 285 | 1710 | 307.8 | 2017.8 | 2.5 | 6 | 1710 | 307.8 | 2017.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Light Fitting Fixing | No. | 1 | 150 | 150 | 27 | 177 | 2.5 | 1 | 150 | 27 | 177 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 16 Way SPN DB | No. | 6 | 1600 | 9600 | 1728 | 11328 | 2.5 | 6 | 9600 | 1728 | 11328 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | RCCB 4 Pole | No. | 0 | 1000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Cancelled | Dushant Gore | 02 Apr 2022
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | LED Point (L) | No. | 6 | 285 | 1710 | 307.8 | 2017.8 | 2.5 | 6 | 1710 | 307.8 | 2017.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB Box 8 Way TPN | No. | 8 | 2600 | 20800 | 3744 | 24544 | 2.5 | 8 | 20800 | 3744 | 24544 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 12 | 350 | 4200 | 756 | 4956 | 2.5 | 12 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 125 | 15 | 1875 | 337.5 | 2212.5 | 2.5 | 125 | 1875 | 337.5 | 2212.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | LED Point (L) | No. | 5 | 285 | 1425 | 256.5 | 1681.5 | 2.5 | 5 | 1425 | 256.5 | 1681.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Light Point DPo | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Single Pole MCB Fixing | No. | 6 | 200 | 1200 | 216 | 1416 | 2.5 | 6 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | D-Link Rack box fixing | No. | 1 | 900 | 900 | 162 | 1062 | 2.5 | 1 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 6 | 150 | 900 | 162 | 1062 | 2.5 | 6 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | AC Point - Mkt | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 1 | 425 | 76.5 | 501.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 2 | 350 | 700 | 126 | 826 | 2.5 | 1 | 350 | 63 | 413 | 1 | 413 |  | 50 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 74 | 15 | 1110 | 199.8 | 1309.8 | 2.5 | 74 | 1110 | 199.8 | 1309.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 42 | 25 | 1050 | 189 | 1239 | 2.5 | 42 | 1050 | 189 | 1239 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Single Pole MCB Fixing | No. | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 18 Mar 2022
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 8 | 150 | 1200 | 216 | 1416 | 2.5 | 8 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 68 | 25 | 1700 | 306 | 2006 | 2.5 | 68 | 1700 | 306 | 2006 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 2 | 350 | 700 | 126 | 826 | 2.5 | 2 | 700 | 126 | 826 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 56 | 22 | 1232 | 221.76 | 1453.76 | 2.5 | 56 | 1232 | 221.76 | 1453.76 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 14 | 150 | 2100 | 378 | 2478 | 2.5 | 14 | 2100 | 378 | 2478 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 81 | 25 | 2025 | 364.5 | 2389.5 | 2.5 | 81 | 2025 | 364.5 | 2389.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Single Pole MCB Fixing | No. | 23 | 200 | 4600 | 828 | 5428 | 2.5 | 23 | 4600 | 828 | 5428 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 34 | 25 | 850 | 153 | 1003 | 2.5 | 34 | 850 | 153 | 1003 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 55 | 25 | 1375 | 247.5 | 1622.5 | 2.5 | 55 | 1375 | 247.5 | 1622.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 99 | 20 | 1980 | 356.4 | 2336.4 | 2.5 | 99 | 1980 | 356.4 | 2336.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 40 | 15 | 600 | 108 | 708 | 2.5 | 40 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 39 | 25 | 975 | 175.5 | 1150.5 | 2.5 | 39 | 975 | 175.5 | 1150.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 2.5 Sqmm Cable (L) | R.Ft | 85 | 18 | 1530 | 275.4 | 1805.4 | 2.5 | 85 | 1530 | 275.4 | 1805.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Data Point | No. | 3 | 250 | 750 | 135 | 885 | 2.5 | 3 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 0 | 285 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 6 Sq.mm Cable | R.Ft | 108 | 50 | 5400 | 972 | 6372 | 2.5 | 108 | 5400 | 972 | 6372 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Exhaust Fan Point - BCo | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Building Common Items | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 91 | 22 | 2002 | 360.36 | 2362.36 | 2.5 | 91 | 2002 | 360.36 | 2362.36 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 0 | 285 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | secondary light point | No. | 14 | 150 | 2100 | 378 | 2478 | 2.5 | 14 | 2100 | 378 | 2478 | 0 | 0 | Secondary Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Wall Light Fitting fixing | No. | 5 | 150 | 750 | 135 | 885 | 2.5 | 5 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Data Point | No. | 3 | 250 | 750 | 135 | 885 | 2.5 | 2 | 500 | 90 | 590 | 1 | 295 |  | 66.6667 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 90 | 15 | 1350 | 243 | 1593 | 2.5 | 90 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 6 Sq.mm Cable | R.Ft | 219 | 50 | 10950 | 1971 | 12921 | 2.5 | 219 | 10950 | 1971 | 12921 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 75 | 22 | 1650 | 297 | 1947 | 2.5 | 75 | 1650 | 297 | 1947 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Light Fitting Fixing | No. | 15 | 150 | 2250 | 405 | 2655 | 2.5 | 15 | 2250 | 405 | 2655 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 6 Sq.mm Cable | R.Ft | 157 | 50 | 7850 | 1413 | 9263 | 2.5 | 157 | 7850 | 1413 | 9263 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker fittings | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 16 | 150 | 2400 | 432 | 2832 | 2.5 | 13 | 1950 | 351 | 2301 | 3 | 531 |  | 81.25 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Light Point BC | No. | 3 | 285 | 855 | 153.9 | 1008.9 | 2.5 | 3 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 50 | 22 | 1100 | 198 | 1298 | 2.5 | 50 | 1100 | 198 | 1298 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Light Fitting Fixing | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Light Point BC | No. | 16 | 285 | 4560 | 820.8 | 5380.8 | 2.5 | 16 | 4560 | 820.8 | 5380.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 80 | 20 | 1600 | 288 | 1888 | 2.5 | 80 | 1600 | 288 | 1888 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker fittings | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 79 | 20 | 1580 | 284.4 | 1864.4 | 2.5 | 79 | 1580 | 284.4 | 1864.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Chandelier Fitting | No. | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 10 | 285 | 2850 | 513 | 3363 | 2.5 | 10 | 2850 | 513 | 3363 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 17 | 20 | 340 | 61.2 | 401.2 | 2.5 | 17 | 340 | 61.2 | 401.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 16 Sq.mm Cable | R.Ft | 48 | 135 | 6480 | 1166.4 | 7646.4 | 2.5 | 48 | 6480 | 1166.4 | 7646.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 37 | 25 | 925 | 166.5 | 1091.5 | 2.5 | 37 | 925 | 166.5 | 1091.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4C x 4sqmm flexible cable (L) | R.Ft | 58 | 45 | 2610 | 469.8 | 3079.8 | 2.5 | 58 | 2610 | 469.8 | 3079.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 114 | 20 | 2280 | 410.4 | 2690.4 | 2.5 | 114 | 2280 | 410.4 | 2690.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 4 Pole Fixing | No. | 3 | 1000 | 3000 | 540 | 3540 | 2.5 | 3 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 42 | 25 | 1050 | 189 | 1239 | 2.5 | 42 | 1050 | 189 | 1239 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 12 | 350 | 4200 | 756 | 4956 | 2.5 | 12 | 4200 | 756 | 4956 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 114 | 20 | 2280 | 410.4 | 2690.4 | 2.5 | 114 | 2280 | 410.4 | 2690.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 4 Pole Fixing | No. | 13 | 1000 | 13000 | 2340 | 15340 | 2.5 | 13 | 13000 | 2340 | 15340 | 0 | 0 | Four Pole MCB (Wire Termination) with Fixing. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 23 | 25 | 575 | 103.5 | 678.5 | 2.5 | 23 | 575 | 103.5 | 678.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Labour lumpsum | No. | 1 | 16000 | 16000 | 2880 | 18880 | 2.5 | 1 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 90 | 20 | 1800 | 324 | 2124 | 2.5 | 90 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 4 Pole Fixing | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 64 | 20 | 1280 | 230.4 | 1510.4 | 2.5 | 64 | 1280 | 230.4 | 1510.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 2 Pole Fixing | No. | 2 | 600 | 1200 | 216 | 1416 | 2.5 | 2 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | MCB 4 Pole Fixing | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 8 Way MCB Encloser Box (L) | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 125 | 20 | 2500 | 450 | 2950 | 2.5 | 120 | 2400 | 432 | 2832 | 5 | 118 |  | 96 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 54 | 25 | 1350 | 243 | 1593 | 2.5 | 54 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 113 | 22 | 2486 | 447.48 | 2933.48 | 2.5 | 113 | 2486 | 447.48 | 2933.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 79 | 20 | 1580 | 284.4 | 1864.4 | 2.5 | 79 | 1580 | 284.4 | 1864.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 145 | 20 | 2900 | 522 | 3422 | 2.5 | 141 | 2820 | 507.6 | 3327.6 | 4 | 94.4 |  | 97.2414 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 44 | 25 | 1100 | 198 | 1298 | 2.5 | 44 | 1100 | 198 | 1298 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 68 | 25 | 1700 | 306 | 2006 | 2.5 | 68 | 1700 | 306 | 2006 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 73 | 15 | 1095 | 197.1 | 1292.1 | 2.5 | 73 | 1095 | 197.1 | 1292.1 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 2 Pole Fixing | No. | 2 | 600 | 1200 | 216 | 1416 | 2.5 | 2 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 40 | 20 | 800 | 144 | 944 | 2.5 | 40 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 13 Amp Plug Point | No. | 11 | 350 | 3850 | 693 | 4543 | 2.5 | 11 | 3850 | 693 | 4543 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 32 | 15 | 480 | 86.4 | 566.4 | 2.5 | 32 | 480 | 86.4 | 566.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Single Pole MCB Fixing | No. | 2 | 200 | 400 | 72 | 472 | 2.5 | 2 | 400 | 72 | 472 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 8 | 285 | 2280 | 410.4 | 2690.4 | 2.5 | 8 | 2280 | 410.4 | 2690.4 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 43 | 25 | 1075 | 193.5 | 1268.5 | 2.5 | 43 | 1075 | 193.5 | 1268.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 43 | 25 | 1075 | 193.5 | 1268.5 | 2.5 | 43 | 1075 | 193.5 | 1268.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker Cable (L) | R.Ft | 97 | 18 | 1746 | 314.28 | 2060.28 | 2.5 | 97 | 1746 | 314.28 | 2060.28 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 20 | 285 | 5700 | 1026 | 6726 | 2.5 | 20 | 5700 | 1026 | 6726 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 88 | 22 | 1936 | 348.48 | 2284.48 | 2.5 | 88 | 1936 | 348.48 | 2284.48 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 42 | 25 | 1050 | 189 | 1239 | 2.5 | 42 | 1050 | 189 | 1239 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker Cable (L) | R.Ft | 55 | 18 | 990 | 178.2 | 1168.2 | 2.5 | 55 | 990 | 178.2 | 1168.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 160 Amp Main Switch- | No. | 1 | 1300 | 1300 | 234 | 1534 | 2.5 | 1 | 1300 | 234 | 1534 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 way MCB Encloser Box (L) | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker Cable (L) | R.Ft | 25 | 18 | 450 | 81 | 531 | 2.5 | 25 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 1 | 285 | 285 | 51.3 | 336.3 | 2.5 | 1 | 285 | 51.3 | 336.3 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 4 Sqmm Cable - MKt | R.Ft | 105 | 22 | 2310 | 415.8 | 2725.8 | 2.5 | 105 | 2310 | 415.8 | 2725.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 58 | 25 | 1450 | 261 | 1711 | 2.5 | 58 | 1450 | 261 | 1711 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Speaker Cable (L) | R.Ft | 75 | 18 | 1350 | 243 | 1593 | 2.5 | 75 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 1 | 285 | 285 | 51.3 | 336.3 | 2.5 | 1 | 285 | 51.3 | 336.3 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | Labour lumpsum | No. | 0 | 16000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 02 Mar 2022 |  | B.C. Rework/Extrawork | Cancelled | Dushant Gore | 02 Apr 2022
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 way MCB Encloser Box (L) | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | LIght Point - Mkt | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | LED Strip Fixing | R.Ft | 58 | 50 | 2900 | 522 | 3422 | 2.5 | 58 | 2900 | 522 | 3422 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 69 | 22 | 1518 | 273.24 | 1791.24 | 2.5 | 69 | 1518 | 273.24 | 1791.24 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 1 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | AC Point - Mkt | No. | 8 | 425 | 3400 | 612 | 4012 | 2.5 | 8 | 3400 | 612 | 4012 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 50 | 15 | 750 | 135 | 885 | 2.5 | 50 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 Way MCB Box w/ MCB -BC | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 4 Way MCB Box w/ MCB -BC | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 133 | 50 | 6650 | 1197 | 7847 | 2.5 | 133 | 6650 | 1197 | 7847 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 1.5 Sqmm Cable (L) | R.Ft | 32 | 15 | 480 | 86.4 | 566.4 | 2.5 | 32 | 480 | 86.4 | 566.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Pathway Light Point fixing | No. | 6 | 325 | 1950 | 351 | 2301 | 2.5 | 6 | 1950 | 351 | 2301 | 0 | 0 | Pathway Light point 2.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Way MCB Box w/ MCB -BC | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | AC Point - Mkt | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 1 | 425 | 76.5 | 501.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 1.5 Sqmm Cable (L) | R.Ft | 110 | 15 | 1650 | 297 | 1947 | 2.5 | 110 | 1650 | 297 | 1947 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | MCB Box 8 Way TPN | No. | 1 | 2600 | 2600 | 468 | 3068 | 2.5 | 1 | 2600 | 468 | 3068 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | RG 6 TV Cable (L) | R.Ft | 145 | 15 | 2175 | 391.5 | 2566.5 | 2.5 | 144 | 2160 | 388.8 | 2548.8 | 1 | 17.7 |  | 99.3103 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Light Fitting Fixing | No. | 7 | 150 | 1050 | 189 | 1239 | 2.5 | 7 | 1050 | 189 | 1239 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 46 | 15 | 690 | 124.2 | 814.2 | 2.5 | 46 | 690 | 124.2 | 814.2 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 115 | 20 | 2300 | 414 | 2714 | 2.5 | 97 | 1940 | 349.2 | 2289.2 | 18 | 424.8 |  | 84.3478 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | RG 6 TV Cable (L) | R.Ft | 125 | 15 | 1875 | 337.5 | 2212.5 | 2.5 | 101 | 1515 | 272.7 | 1787.7 | 24 | 424.8 |  | 80.8 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Light Fitting Fixing | No. | 59 | 150 | 8850 | 1593 | 10443 | 2.5 | 59 | 8850 | 1593 | 10443 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 0 | 285 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 32 | 20 | 640 | 115.2 | 755.2 | 2.5 | 32 | 640 | 115.2 | 755.2 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Light Fitting Fixing | No. | 20 | 150 | 3000 | 540 | 3540 | 2.5 | 20 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 16 AMP Plug Point - Mkt | No. | 36 | 425 | 15300 | 2754 | 18054 | 2.5 | 36 | 15300 | 2754 | 18054 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 1.5 Sqmm Cable - MKt - R.Ft | R.Ft | 30 | 15 | 450 | 81 | 531 | 2.5 | 30 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 32 | 20 | 640 | 115.2 | 755.2 | 2.5 | 32 | 640 | 115.2 | 755.2 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 4 Pole Fixing | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | LED Strip Fixing | R.Ft | 15 | 50 | 750 | 135 | 885 | 2.5 | 15 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 6 | 150 | 900 | 162 | 1062 | 2.5 | 6 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 40 | 20 | 800 | 144 | 944 | 2.5 | 40 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 4 Pole Fixing | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | RCCB 4 Pole | No. | 6 | 1000 | 6000 | 1080 | 7080 | 2.5 | 6 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 45 | 25 | 1125 | 202.5 | 1327.5 | 2.5 | 45 | 1125 | 202.5 | 1327.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 4 Pole Fixing | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 61 | 25 | 1525 | 274.5 | 1799.5 | 2.5 | 61 | 1525 | 274.5 | 1799.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 43 | 25 | 1075 | 193.5 | 1268.5 | 2.5 | 43 | 1075 | 193.5 | 1268.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker Point - BC | No. | 2 | 200 | 400 | 72 | 472 | 2.5 | 2 | 400 | 72 | 472 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 4 Pole Fixing | No. | 2 | 1000 | 2000 | 360 | 2360 | 2.5 | 2 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 81 | 25 | 2025 | 364.5 | 2389.5 | 2.5 | 81 | 2025 | 364.5 | 2389.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Chandelier Light Fitting- DCH | No. | 1 | 285 | 285 | 51.3 | 336.3 | 2.5 | 1 | 285 | 51.3 | 336.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | DEV. Club House | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 144 | 22 | 3168 | 570.24 | 3738.24 | 2.5 | 144 | 3168 | 570.24 | 3738.24 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | MCB 4 Pole Fixing | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 way MCB Encloser Box (L) | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 24 | 25 | 600 | 108 | 708 | 2.5 | 24 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 40 | 22 | 880 | 158.4 | 1038.4 | 2.5 | 40 | 880 | 158.4 | 1038.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 88 | 22 | 1936 | 348.48 | 2284.48 | 2.5 | 88 | 1936 | 348.48 | 2284.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 58 | 25 | 1450 | 261 | 1711 | 2.5 | 58 | 1450 | 261 | 1711 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 0 | 210 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 54 | 22 | 1188 | 213.84 | 1401.84 | 2.5 | 54 | 1188 | 213.84 | 1401.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | LED Point- BCE | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 55 | 25 | 1375 | 247.5 | 1622.5 | 2.5 | 55 | 1375 | 247.5 | 1622.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | primary light point from DB | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | RCCB 4 Pole | No. | 2 | 1000 | 2000 | 360 | 2360 | 2.5 | 2 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 135 | 22 | 2970 | 534.6 | 3504.6 | 2.5 | 135 | 2970 | 534.6 | 3504.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 13 AMP Plug Point - Mkt | No. | 7 | 350 | 2450 | 441 | 2891 | 2.5 | 7 | 2450 | 441 | 2891 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 46 | 15 | 690 | 124.2 | 814.2 | 2.5 | 46 | 690 | 124.2 | 814.2 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Speaker Point - BC | No. | 2 | 200 | 400 | 72 | 472 | 2.5 | 2 | 400 | 72 | 472 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 2 | 350 | 700 | 126 | 826 | 2.5 | 1 | 350 | 63 | 413 | 1 | 413 |  | 50 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 13 AMP Plug Point - Mkt | No. | 4 | 350 | 1400 | 252 | 1652 | 2.5 | 4 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 50 | 15 | 750 | 135 | 885 | 2.5 | 50 | 750 | 135 | 885 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 13 Amp Plug Point | No. | 2 | 350 | 700 | 126 | 826 | 2.5 | 2 | 700 | 126 | 826 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Wall & Hanging Light Fitting Fixing - Mk | No. | 3 | 500 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | primary light point from DB | No. | 3 | 285 | 855 | 153.9 | 1008.9 | 2.5 | 3 | 855 | 153.9 | 1008.9 | 0 | 0 | Primary Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 13 Amp Plug Point Primery | No. | 2 | 350 | 700 | 126 | 826 | 2.5 | 2 | 700 | 126 | 826 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 Sqmm Cable (L) | R.Ft | 16 | 45 | 720 | 129.6 | 849.6 | 2.5 | 16 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 40 | 20 | 800 | 144 | 944 | 2.5 | 40 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 90 | 20 | 1800 | 324 | 2124 | 2.5 | 90 | 1800 | 324 | 2124 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 0 | 210 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 26 May 2022
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 13 | 20 | 260 | 46.8 | 306.8 | 2.5 | 13 | 260 | 46.8 | 306.8 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 75 | 20 | 1500 | 270 | 1770 | 2.5 | 75 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 20 | 285 | 5700 | 1026 | 6726 | 2.5 | 18 | 5130 | 923.4 | 6053.4 | 2 | 672.6 |  | 90 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | primary light point from DB | No. | 15 | 285 | 4275 | 769.5 | 5044.5 | 2.5 | 15 | 4275 | 769.5 | 5044.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 110 | 20 | 2200 | 396 | 2596 | 2.5 | 90 | 1800 | 324 | 2124 | 20 | 472 |  | 81.8182 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 69 | 20 | 1380 | 248.4 | 1628.4 | 2.5 | 69 | 1380 | 248.4 | 1628.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 8 | 285 | 2280 | 410.4 | 2690.4 | 2.5 | 8 | 2280 | 410.4 | 2690.4 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | primary light point from DB | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 | Primary Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 148 | 20 | 2960 | 532.8 | 3492.8 | 2.5 | 0 | 0 | 0 | 0 | 148 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 75 | 20 | 1500 | 270 | 1770 | 2.5 | 75 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 6 Way Enclosure Box Fixing | No. | 1 | 900 | 900 | 162 | 1062 | 2.5 | 1 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | primary light point from DB | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 | Primary Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 148 | 20 | 2960 | 532.8 | 3492.8 | 2.5 | 120 | 2400 | 432 | 2832 | 28 | 660.8 |  | 81.0811 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 84 | 20 | 1680 | 302.4 | 1982.4 | 2.5 | 84 | 1680 | 302.4 | 1982.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Speaker Cable (L) | R.Ft | 26 | 18 | 468 | 84.24 | 552.24 | 2.5 | 26 | 468 | 84.24 | 552.24 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 1 | 210 | 210 | 37.8 | 247.8 | 2.5 | 1 | 210 | 37.8 | 247.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Speaker Cable (L) | R.Ft | 35 | 18 | 630 | 113.4 | 743.4 | 2.5 | 35 | 630 | 113.4 | 743.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 40 | 20 | 800 | 144 | 944 | 2.5 | 40 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Speaker Cable (L) | R.Ft | 90 | 18 | 1620 | 291.6 | 1911.6 | 2.5 | 90 | 1620 | 291.6 | 1911.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 2.5 Sqmm Cable (L) | R.Ft | 110 | 18 | 1980 | 356.4 | 2336.4 | 2.5 | 110 | 1980 | 356.4 | 2336.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 10 | 20 | 200 | 36 | 236 | 2.5 | 10 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | TV Point | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 1 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 16 | 150 | 2400 | 432 | 2832 | 2.5 | 15 | 2250 | 405 | 2655 | 1 | 177 |  | 93.75 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 45 | 25 | 1125 | 202.5 | 1327.5 | 2.5 | 45 | 1125 | 202.5 | 1327.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 10 | 20 | 200 | 36 | 236 | 2.5 | 10 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Light Fitting Fixing | No. | 3 | 150 | 450 | 81 | 531 | 2.5 | 3 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 68 | 25 | 1700 | 306 | 2006 | 2.5 | 68 | 1700 | 306 | 2006 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 40 | 20 | 800 | 144 | 944 | 2.5 | 40 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 6 | 250 | 1500 | 270 | 1770 | 2.5 | 6 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 43 | 25 | 1075 | 193.5 | 1268.5 | 2.5 | 43 | 1075 | 193.5 | 1268.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 125 | 20 | 2500 | 450 | 2950 | 2.5 | 101 | 2020 | 363.6 | 2383.6 | 24 | 566.4 |  | 80.8 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 2 | 350 | 700 | 126 | 826 | 2.5 | 2 | 700 | 126 | 826 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 1 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 4 Sqmm Cable - MKt | R.Ft | 105 | 22 | 2310 | 415.8 | 2725.8 | 2.5 | 105 | 2310 | 415.8 | 2725.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 75 | 20 | 1500 | 270 | 1770 | 2.5 | 75 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | MCB 4 Pole Fixing | No. | 0 | 1000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA.CHOUGULE | 30 Jun 2023
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 69 | 20 | 1380 | 248.4 | 1628.4 | 2.5 | 69 | 1380 | 248.4 | 1628.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 - 8 way TPN MCB Box (L) | No. | 1 | 2600 | 2600 | 468 | 3068 | 2.5 | 1 | 2600 | 468 | 3068 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Single Pole MCB Fixing | No. | 4 | 200 | 800 | 144 | 944 | 2.5 | 4 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 60 | 22 | 1320 | 237.6 | 1557.6 | 2.5 | 60 | 1320 | 237.6 | 1557.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 108 | 20 | 2160 | 388.8 | 2548.8 | 2.5 | 0 | 0 | 0 | 0 | 108 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Zumber Fixing Glass,Bulb Removing & Fixing | No. | 3 | 3000 | 9000 | 1620 | 10620 | 2.5 | 3 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 138 | 20 | 2760 | 496.8 | 3256.8 | 2.5 | 44 | 880 | 158.4 | 1038.4 | 94 | 2218.4 |  | 31.8841 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 150 | 22 | 3300 | 594 | 3894 | 2.5 | 150 | 3300 | 594 | 3894 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 13 | 20 | 260 | 46.8 | 306.8 | 2.5 | 13 | 260 | 46.8 | 306.8 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 - 8 way TPN MCB Box (L) | No. | 2 | 2600 | 5200 | 936 | 6136 | 2.5 | 2 | 5200 | 936 | 6136 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 10 | 20 | 200 | 36 | 236 | 2.5 | 10 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 52 | 22 | 1144 | 205.92 | 1349.92 | 2.5 | 52 | 1144 | 205.92 | 1349.92 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 85 | 22 | 1870 | 336.6 | 2206.6 | 2.5 | 85 | 1870 | 336.6 | 2206.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | MCB 4 Pole Fixing | No. | 1 | 1000 | 1000 | 180 | 1180 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 64 | 22 | 1408 | 253.44 | 1661.44 | 2.5 | 64 | 1408 | 253.44 | 1661.44 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 4 Sqmm Cable (L) | R.Ft | 135 | 25 | 3375 | 607.5 | 3982.5 | 2.5 | 0 | 0 | 0 | 0 | 135 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 75 | 22 | 1650 | 297 | 1947 | 2.5 | 75 | 1650 | 297 | 1947 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | LIght Point - Mkt | No. | 3 | 285 | 855 | 153.9 | 1008.9 | 2.5 | 3 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 4 Sqmm Cable - MKt | R.Ft | 25 | 22 | 550 | 99 | 649 | 2.5 | 25 | 550 | 99 | 649 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 4 Sqmm Cable (L) | R.Ft | 140 | 25 | 3500 | 630 | 4130 | 2.5 | 60 | 1500 | 270 | 1770 | 80 | 2360 |  | 42.8571 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 134 | 22 | 2948 | 530.64 | 3478.64 | 2.5 | 134 | 2948 | 530.64 | 3478.64 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 2.5 Sqmm Cable (L) | R.Ft | 150 | 18 | 2700 | 486 | 3186 | 2.5 | 150 | 2700 | 486 | 3186 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 4 Sqmm Cable (L) | R.Ft | 138 | 25 | 3450 | 621 | 4071 | 2.5 | 0 | 0 | 0 | 0 | 138 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Speaker Cable (L) | R.Ft | 20 | 18 | 360 | 64.8 | 424.8 | 2.5 | 20 | 360 | 64.8 | 424.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 4 Sqmm Cable (L) | R.Ft | 145 | 25 | 3625 | 652.5 | 4277.5 | 2.5 | 0 | 0 | 0 | 0 | 145 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | TV Point | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 1 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 6 | 250 | 1500 | 270 | 1770 | 2.5 | 6 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker Cable (L) | R.Ft | 55 | 18 | 990 | 178.2 | 1168.2 | 2.5 | 55 | 990 | 178.2 | 1168.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | CAT 6 Cable- | R.Ft | 105 | 13 | 1365 | 245.7 | 1610.7 | 2.5 | 101 | 1313 | 236.34 | 1549.34 | 4 | 61.36 |  | 96.1905 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 56 | 25 | 1400 | 252 | 1652 | 2.5 | 56 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | CAT 6 Cable- | R.Ft | 148 | 13 | 1924 | 346.32 | 2270.32 | 2.5 | 0 | 0 | 0 | 0 | 148 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 160 | 15 | 2400 | 432 | 2832 | 2.5 | 160 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 4 way MCB Encloser Box (L) | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | CAT 6 Cable- | R.Ft | 125 | 13 | 1625 | 292.5 | 1917.5 | 2.5 | 101 | 1313 | 236.34 | 1549.34 | 24 | 368.16 |  | 80.8 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 34 | 25 | 850 | 153 | 1003 | 2.5 | 34 | 850 | 153 | 1003 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 262 | 15 | 3930 | 707.4 | 4637.4 | 2.5 | 262 | 3930 | 707.4 | 4637.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | 2.5 Sqmm Cable - DCH | R.Ft | 58 | 25 | 1450 | 261 | 1711 | 2.5 | 58 | 1450 | 261 | 1711 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Speaker Cable (L) | R.Ft | 112 | 18 | 2016 | 362.88 | 2378.88 | 2.5 | 112 | 2016 | 362.88 | 2378.88 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | secondary light point | No. | 1 | 150 | 150 | 27 | 177 | 2.5 | 1 | 150 | 27 | 177 | 0 | 0 | Secondary Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 2.5 Sqmm Cable (L) | R.Ft | 134 | 18 | 2412 | 434.16 | 2846.16 | 2.5 | 134 | 2412 | 434.16 | 2846.16 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | secondary light point | No. | 11 | 150 | 1650 | 297 | 1947 | 2.5 | 11 | 1650 | 297 | 1947 | 0 | 0 | Secondary Light Point 1.5 Sq.mm | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | LIght Point - Mkt | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House DB Room Electrical Work | 6 Sq.mm Cable | R.Ft | 167 | 50 | 8350 | 1503 | 9853 | 2.5 | 167 | 8350 | 1503 | 9853 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | Speaker Cable (L) | R.Ft | 60 | 18 | 1080 | 194.4 | 1274.4 | 2.5 | 60 | 1080 | 194.4 | 1274.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 35mm Ceiling Profaile Pati & Led Strip Fixing | R.Ft | 152 | 75 | 11400 | 2052 | 13452 | 2.5 | 152 | 11400 | 2052 | 13452 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 2.5 Sqmm Cable (L) | R.Ft | 158 | 18 | 2844 | 511.92 | 3355.92 | 2.5 | 158 | 2844 | 511.92 | 3355.92 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 5 | 22 Feb 2022 | VAISHALI ELECTRICAL | GH Gym Room Electrical Work | LED Strip Fixing | R.Ft | 98 | 50 | 4900 | 882 | 5782 | 2.5 | 98 | 4900 | 882 | 5782 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 20 | 50 | 1000 | 180 | 1180 | 2.5 | 7 | 350 | 63 | 413 | 13 | 767 |  | 35 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Double Fan Fastener & Fan Fixing | No. | 0 | 375 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 May 2022
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 40 | 50 | 2000 | 360 | 2360 | 2.5 | 40 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 56 | 50 | 2800 | 504 | 3304 | 2.5 | 23 | 1150 | 207 | 1357 | 33 | 1947 |  | 41.0714 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Double Fan Fastener & Fan Fixing | No. | 0 | 375 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 27 May 2022
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 98 | 50 | 4900 | 882 | 5782 | 2.5 | 98 | 4900 | 882 | 5782 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 3 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 18 | 150 | 2700 | 486 | 3186 | 2.5 | 18 | 2700 | 486 | 3186 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Light Fitting Fixing | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 56 | 20 | 1120 | 201.6 | 1321.6 | 2.5 | 56 | 1120 | 201.6 | 1321.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 2.5 Sqmm Cable (L) | R.Ft | 75 | 20 | 1500 | 270 | 1770 | 2.5 | 75 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Ceiling Fan Fitting | No. | 4 | 350 | 1400 | 252 | 1652 | 2.5 | 4 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Light Fitting Fixing | No. | 4 | 150 | 600 | 108 | 708 | 2.5 | 4 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | LED Strip Fixing | R.Ft | 46 | 50 | 2300 | 414 | 2714 | 2.5 | 46 | 2300 | 414 | 2714 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Light Fitting Fixing | No. | 10 | 150 | 1500 | 270 | 1770 | 2.5 | 10 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Light Fitting Fixing | No. | 15 | 150 | 2250 | 405 | 2655 | 2.5 | 15 | 2250 | 405 | 2655 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Light Fitting Fixing | No. | 3 | 150 | 450 | 81 | 531 | 2.5 | 3 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 137 | 22 | 3014 | 542.52 | 3556.52 | 2.5 | 137 | 3014 | 542.52 | 3556.52 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4 Sqmm Cable - MKt | R.Ft | 125 | 22 | 2750 | 495 | 3245 | 2.5 | 125 | 2750 | 495 | 3245 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | 4 Sqmm Cable - MKt | R.Ft | 99 | 22 | 2178 | 392.04 | 2570.04 | 2.5 | 99 | 2178 | 392.04 | 2570.04 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Fan Fixing | No. | 4 | 375 | 1500 | 270 | 1770 | 2.5 | 4 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | DEV. Landscape/Equipment | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | CAT 6 Cable- | R.Ft | 105 | 13 | 1365 | 245.7 | 1610.7 | 2.5 | 0 | 0 | 0 | 0 | 105 | 0 |  | 0 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | CAT 6 Cable- | R.Ft | 148 | 13 | 1924 | 346.32 | 2270.32 | 2.5 | 141 | 1833 | 329.94 | 2162.94 | 7 | 107.38 |  | 95.2703 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 2 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | CAT 6 Cable- | R.Ft | 145 | 13 | 1885 | 339.3 | 2224.3 | 2.5 | 141 | 1833 | 329.94 | 2162.94 | 4 | 61.36 |  | 97.2414 |  | Aditya Chougule | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 30 | 15 | 450 | 81 | 531 | 2.5 | 30 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 1 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Garden Outside Electrical Work | Pathway Light Fitting & fixing. - No. | No. | 6 | 350 | 2100 | 378 | 2478 | 2.5 | 6 | 2100 | 378 | 2478 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4C x 6sqmm Flexible Cable (L) | R.Ft | 90 | 50 | 4500 | 810 | 5310 | 2.5 | 50 | 2500 | 450 | 2950 | 40 | 2360 |  | 55.5556 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 4 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House (L) - Gym Electrical Work (L) | 4C x 6sqmm Flexible Cable (L) | R.Ft | 90 | 50 | 4500 | 810 | 5310 | 2.5 | 50 | 2500 | 450 | 2950 | 40 | 2360 |  | 55.5556 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 251 | 0 | 22 Feb 2022 | VAISHALI ELECTRICAL | Goel House Ground Floor electrical work | Chandelier Glass Handi,Criestal, Round Handi Bulb Removing & | No. | 1 | 5000 | 5000 | 900 | 5900 | 2.5 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 02 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Italian Marble Skirting Leather Polish | R.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | 11 TILING WORK | Cancelled | skmishra | 04 Mar 2022
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Edge Polish- BCo | R.Ft | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | B.C. Building Common Items | Cancelled | skmishra | 04 Mar 2022
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Champher/ Bullnose Moulding Polish | R.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | 11 TILING WORK | Cancelled | skmishra | 04 Mar 2022
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Italian Marble Mirror Polish- | Sq.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | 11 TILING WORK | Cancelled | skmishra | 04 Mar 2022
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Italian Marble Dado Leather Polish | Sq.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | 11 TILING WORK | Cancelled | skmishra | 04 Mar 2022
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Champher/ Bullnose Moulding Polish | R.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | 11 TILING WORK | Cancelled | Dushant Gore | 04 Mar 2022
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Italian Marble Floor Leather Polish | Sq.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | 11 TILING WORK | Cancelled | skmishra | 04 Mar 2022
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Italian Marble Skirting Mirror polish. | R.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | 11 TILING WORK | Cancelled | skmishra | 04 Mar 2022
GANGA ASMI | 252 | 0 | 22 Feb 2022 | R.K. INTERIOR (FIRM) | Goel House Italian marble mirror polish work | Italian Marble Top/ Botom Mirror Polish - | R.Ft | 0 | 55 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Mar 2022 |  | 11 TILING WORK | Cancelled | skmishra | 04 Mar 2022
GANGA ASMI | 253 | 1 | 23 Feb 2022 | LAXMI ELECTRICALS | Temporary Electrical Work DG Shifting & Earthing | Feeder Pillar fixing-ULT | No. | 0 | 2750 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 06 Jun 2022 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT.GORE | 09 Dec 2023
GANGA ASMI | 253 | 0 | 23 Feb 2022 | LAXMI ELECTRICALS | Weigh Bridge Earthing Work | Earthing work(m+l)- BC | No. | 0 | 3500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Jun 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 06 Jun 2022
GANGA ASMI | 253 | 0 | 23 Feb 2022 | LAXMI ELECTRICALS | Weigh Bridge Earthing Work | GI Earthing Patti 32x 6 (m+l) | Mtrs | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Jun 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 06 Jun 2022
GANGA ASMI | 253 | 0 | 23 Feb 2022 | LAXMI ELECTRICALS | Weigh Bridge Earthing Work | Earthing work(m+l)- BC | No. | 0 | 5000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Jun 2022 |  | B.C. Building Common Items | Cancelled | Dushant Gore | 06 Jun 2022
GANGA ASMI | 254 | 0 | 23 Feb 2022 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 3 | 150000 | 450000 | 81000 | 531000 | 0 | 0.8 | 120000 | 21600 | 141600 | 2.2 | 389400 | GANGA ASMI WAKAD PROJECT SALES PROMOTION WITH ENQ. GENERATION ONLINE DIGITAL CAMPAIGN ACITIVITY FOR 3 MONTHS GOOGLE KEY ADWORDS | 26.6667 |  | Tejas Raverkar | sunita shirolkar | construction open | 08 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 255 | 0 | 23 Feb 2022 | ANTS DESIGN | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 3 | 150000 | 450000 | 81000 | 531000 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | GANGA ASMI WAKAD PROJECT SALES PROMOTION WITH ENQ. GENERATION ONLINE DIGITAL CAMPAIGN ACITIVITY FOR 3 MONTHS GOOGLE KEY ADWORDS | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 08 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 256 | 0 | 23 Feb 2022 | REALATTE VENTURES LLP | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 3 | 300000 | 900000 | 162000 | 1062000 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | GANGA ASMI WAKAD PROJECT SALES PROMOTION WITH ENQ GENERATION THROUGH ONLINE DIGITAL CAMPAIGN ACTIVITY FOR 3 MONTH GOOGLE KEY ADWORDS | 0 |  | Tejas Raverkar | sunita shirolkar | construction open | 08 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 257 | 0 | 04 Mar 2022 | VIKAS GARADE | Testing & Certification of const.material & structure test | Testing & Certification Charges | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0.9752 | 97516 | 17552.88 | 115068.88 | 0.0248 | 2931.12 |  | 98.27 |  | Dushant Gore | Swapnil Erande | construction open | 14 Apr 2022 |  | S OH Infrastructure | Approved | Dushant Gore | 30 Jul 2022
GANGA ASMI | 257 | 1 | 04 Mar 2022 | VIKAS GARADE | Testing & Certification of const.material & structure test | Testing & Certification Charges | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.9243 | 92428 | 11909.7 | 104337.7 | 0.0757 | -4337.7 |  | 92.43 |  | DUSHANT GORE | chetan jewalikar | construction open | 14 Apr 2022 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 257 | 2 | 04 Mar 2022 | VIKAS GARADE | Testing & Certification of const.material & structure test | Testing & Certification Charges | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.7746 | 77455 | 13941.9 | 91396.9 | 0.2255 | 8603.1 |  | 98.56 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 258 | 0 | 08 Mar 2022 | DREAMTREE EXPERIENCE | MEDIA Event Expenses | Event Expenses | No. | 1 | 89000 | 89000 | 16020 | 105020 | 0 | 1 | 89000 | 16020 | 105020 | 0 | 0 | GANGA ASMI WAKAD PROJECT SALES PROMOTION CHANEL PARTNER MEET EVENT DTD 17TH FEB. 2022 AT SITE SALES OFFICE | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 12 Mar 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 259 | 0 | 09 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | GH Window & Partition removing work | Removing Work | Sq.Ft | 144.83 | 95 | 13758.85 | 2476.6 | 16235.45 | 0 | 60.7789 | 5774 | 1039.32 | 6813.32 | 84.0511 | 9422.13 | Goel House Window and Partition removing work. | 41.9657 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 259 | 0 | 09 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | GH Window & Partition removing work | Removing Work | Sq.Ft | 272.69 | 55 | 14997.95 | 2699.64 | 17697.59 | 0 | 272.69 | 14997.95 | 2699.64 | 17697.59 | 0 | 0 | Goel House Window and Partition removing work. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Dushant Gore | 09 Mar 2022
GANGA ASMI | 259 | 0 | 09 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | GH Window & Partition removing work | Removing Work | Sq.Ft | 570.92 | 95 | 54237.4 | 9762.74 | 64000.14 | 0 | 462.2947 | 43918 | 7905.24 | 51823.24 | 108.6253 | 12176.9 | Goel House Window and Partition removing work. | 80.9736 |  | Dushant Gore | Swapnil Erande | construction open | 09 Mar 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 260 | 0 | 11 Mar 2022 | DHIRAJ ELECTRICALS | Goel House Electrical Work | Electrical Work (M+L) | No. | 1 | 115000 | 115000 | 0 | 115000 | 2.5 | 1 | 115000 | 0 | 115000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 12 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 261 | 2 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Aluminium Powder Coated Angle- R.Ft | R.Ft | 16 | 568.08 | 9089.28 | 1636.08 | 10725.36 | 0 | 16 | 9089.28 | 1636.08 | 10725.36 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 261 | 1 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Strucural glazing work - 1 No. | Glazing Work (M+L) - AIE | Sq.Ft | 0 | 1695 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2022 |  | Admin. Indirect Expenses | Cancelled | skmishra | 24 Mar 2022
GANGA ASMI | 261 | 1 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Strucural glazing work - 1 No. | PVDF Aluminium sliding window (m+l) | Sq.Ft | 0 | 1071 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 24 Mar 2022
GANGA ASMI | 261 | 2 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Aluminium Powder Coated Angle- R.Ft | R.Ft | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 19 Jul 2022
GANGA ASMI | 261 | 2 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Silicon Filling. | Mtrs | 0 | 274 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 19 Jul 2022
GANGA ASMI | 261 | 1 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Strucural glazing work - 1 No. | PVDF Aluminium sliding window (m+l) | Sq.Ft | 0 | 1176 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | skmishra | 24 Mar 2022
GANGA ASMI | 261 | 1 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Strucural glazing work - 1 No. | PVDF Aluminium sliding window (m+l) | Sq.Ft | 27.34 | 1140 | 31167.6 | 5610.16 | 36777.76 | 2.5 | 27.34 | 31167.6 | 5610.16 | 36777.76 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 261 | 1 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Strucural glazing work - 1 No. | PVDF Aluminium sliding window (m+l) | Sq.Ft | 36.45 | 1038 | 37835.1 | 6810.32 | 44645.42 | 2.5 | 36.45 | 37835.1 | 6810.32 | 44645.42 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 261 | 0 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Sliding window work | 3 Track Sliding Window | Sq.Ft | 93 | 1080 | 100440 | 18079.2 | 118519.2 | 0 | 91.1796 | 98473.97 | 17725.32 | 116199.29 | 1.8204 | 2319.91 |  | 98.0426 |  | Dushant Gore | Swapnil Erande | construction open | 14 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 261 | 2 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Aluminium Powder Coated Angle- R.Ft | R.Ft | 0 | 688 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 14 Mar 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 19 Jul 2022
GANGA ASMI | 261 | 3 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Strucural glazing work - 1 No. | Glazing Work (M+L) - AIE | Sq.Ft | 36.94 | 1644 | 60729.36 | 10931.28 | 71660.64 | 0 | 36.94 | 60729.36 | 10931.28 | 71660.64 | 0 | 0 |  | 100 |  | Sanket Patil | Swapnil Erande | construction open | 14 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 261 | 2 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Silicon Filling. | Mtrs | 28 | 226.25 | 6335 | 1140.3 | 7475.3 | 0 | 28 | 6335 | 1140.3 | 7475.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 261 | 1 | 14 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Strucural glazing work - 1 No. | Glazing Work (M+L) - AIE | Sq.Ft | 36.94 | 1644 | 60729.36 | 10931.28 | 71660.64 | 2.5 | 36.94 | 60729.36 | 10931.28 | 71660.64 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 14 Mar 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.133 | 532 | 0 | 532 | 0.867 | 3468 |  | 13.3 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.7322 | 2928.8 | 0 | 2928.8 | 0.2678 | 1071.2 |  | 73.22 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Cancelled | ADITYA CHOUGULE | 22 Mar 2022
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.4988 | 1995.2 | 0 | 1995.2 | 0.5012 | 2004.8 |  | 49.88 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0.871 | 871 | 0 | 871 | 0.129 | 129 |  | 87.1 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.6 | 2400 | 0 | 2400 | 0.4 | 1600 |  | 60 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0.645 | 645 | 0 | 645 | 0.355 | 355 |  | 64.5 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.7098 | 2839.2 | 0 | 2839.2 | 0.2902 | 1160.8 |  | 70.98 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0.667 | 667 | 0 | 667 | 0.333 | 333 |  | 66.7 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.4322 | 1728.8 | 0 | 1728.8 | 0.5678 | 2271.2 |  | 43.22 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.5332 | 2132.8 | 0 | 2132.8 | 0.4668 | 1867.2 |  | 53.32 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.3325 | 1330 | 0 | 1330 | 0.6675 | 2670 |  | 33.25 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.6 | 2400 | 0 | 2400 | 0.4 | 1600 |  | 60 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0.742 | 2968 | 0 | 2968 | 0.258 | 1032 |  | 74.2 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 0 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 4000 | 4000 | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 262 | 1 | 15 Mar 2022 | UTTAM RAMESH MAKWANA | Goel House Toilet cleaning work | Toilet Cleaning Work | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0.903 | 903 | 0 | 903 | 0.097 | 97 |  | 90.3 |  | ADITYA CHOUGULE | chetan.jewalikar | construction open | 21 Mar 2022 |  | SOC. M. Maintenace Staff | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 263 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Contract Labour Act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 1 | 8750 | 8750 | 1575 | 10325 | 0 | 1 | 8750 | 1575 | 10325 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | Consultancy Labour act Regist. | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 263 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Contract Labour Act Registration & Compliance | Registration of Company (RC) | No. | 1 | 21000 | 21000 | 3780 | 24780 | 0 | 1 | 21000 | 3780 | 24780 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 263 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Contract Labour Act Registration & Compliance | Registration Charges | No. | 1 | 300 | 300 | 54 | 354 | 0 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 263 | 0 | 15 Mar 2022 | NIKISHA CONSULTANCY SERVICES | Contract Labour Act Registration & Compliance | Registration Charges | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan.jewalikar | Construction | 21 Mar 2022 |  | 03 CONSULTANCY | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 264 | 0 | 15 Mar 2022 | SAHARA ENTERPRISES (PROP. ALTAF SHAIKH) | Goel House- Housekeeping material | Housekeeping Work | No. | 1 | 9800 | 9800 | 1764 | 11564 | 0 | 1 | 9800 | 1764 | 11564 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 265 | 0 | 19 Mar 2022 | THE BIRD BARRIER | Goel House Bird Spike - Installation work | Bird Spike Installation | Sq.Ft | 1700 | 40 | 68000 | 12240 | 80240 | 2.5 | 1467 | 58680 | 10562.4 | 69242.4 | 233 | 10997.6 |  | 86.2941 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 23 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Exhaust Air Fan (L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Testing,Commissioning & Handing over of exhaust air fan without filtre. | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | No category | Cancelled | Dushant Gore | 22 Mar 2022
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Fresh Air Fans (L) | No. | 1 | 3000 | 3000 | 540 | 3540 | 2.5 | 1 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Dushant Gore | 13 Dec 2022
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Canvas Connection (L) | No. | 0 | 500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 22 Mar 2022
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | AC Installation & Commissioning (L) | No. | 1 | 15000 | 15000 | 2700 | 17700 | 2.5 | 1 | 15000 | 2700 | 17700 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - SITC of Electric cable 2.5sqmm x 4C-(Mt | 4C x 2.5sqmm copper flexible cable (L) | Mtrs | 115 | 20 | 2300 | 414 | 2714 | 2.5 | 115 | 2300 | 414 | 2714 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Fresh Air Fans (L) | No. | 0 | 3000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Testing,Commissioning & Handing over of fresh air fan with filtre. | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | No category | Cancelled | Dushant Gore | 22 Mar 2022
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 3C x 2.5sqmm (L) | Mtrs | 10 | 20 | 200 | 36 | 236 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | GI Cowl with Bird Screen (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Dushant Gore | 13 Dec 2022
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Nitrogen Pressure & Leak Testing (L) | No. | 90 | 15 | 1350 | 243 | 1593 | 2.5 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | SA Grill (L) | Sq.m. | 1.5 | 800 | 1200 | 216 | 1416 | 2.5 | 0.6 | 480 | 86.4 | 566.4 | 0.9 | 849.6 |  | 40 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Dushant Gore | 13 Dec 2022
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | M.S. Stand | No. | 6 | 1000 | 6000 | 1080 | 7080 | 2.5 | 4 | 4000 | 720 | 4720 | 2 | 2360 |  | 66.6667 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | GI Cowl with Bird Screen (L) | No. | 0 | 500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | No category | Cancelled | Dushant Gore | 22 Mar 2022
GANGA ASMI | 266 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym Readymade Outdoor unit stand-(No.) | Stand for ODU unit (L) | No. | 8 | 150 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Exhaust Air Fan (L) | No. | 1 | 3000 | 3000 | 540 | 3540 | 2.5 | 1 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Dushant Gore | 13 Dec 2022
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | hard Copper 18 Guage Ref Piping (L) | Mtrs | 6 | 175 | 1050 | 189 | 1239 | 2.5 | 2 | 350 | 63 | 413 | 4 | 826 |  | 33.3333 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Canvas Connection (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Dushant Gore | 13 Dec 2022
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 22 Guage Gi Ducting (L) | Sq.m. | 32 | 168 | 5376 | 967.68 | 6343.68 | 2.5 | 25.5 | 4284 | 771.12 | 5055.12 | 6.5 | 1288.56 |  | 79.6875 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | SITC of Drain Pipe (L) | Mtrs | 65 | 20 | 1300 | 234 | 1534 | 2.5 | 38.4 | 768 | 138.24 | 906.24 | 26.6 | 627.76 |  | 59.0769 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | RA Grill (L) | Sq.m. | 2.5 | 800 | 2000 | 360 | 2360 | 2.5 | 0.8 | 640 | 115.2 | 755.2 | 1.7 | 1604.8 |  | 32 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Dushant Gore | 13 Dec 2022
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Soft Copper 22 Guage Ref Piping (L) | Mtrs | 90 | 175 | 15750 | 2835 | 18585 | 2.5 | 42.4 | 7420 | 1335.6 | 8755.6 | 47.6 | 9829.4 |  | 47.1111 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 3 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | One Boat Club AC & Ducting Removing Work | Labour lumpsum | No. | 1 | 42000 | 42000 | 7560 | 49560 | 0 | 0.4762 | 20000.4 | 3600.08 | 23600.48 | 0.5238 | 25959.52 |  | 47.62 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 2.5 Sqmm 4 Core Cable (L) | Mtrs | 110 | 20 | 2200 | 396 | 2596 | 2.5 | 48.5 | 970 | 174.6 | 1144.6 | 61.5 | 1451.4 |  | 44.0909 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Canvas Connection (L) | No. | 2 | 500 | 1000 | 180 | 1180 | 2.5 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - SITC Drain pipe I/C Nitrile rubber insu | Drain Pipe with Insulation (L) | Mtrs | 100 | 20 | 2000 | 360 | 2360 | 2.5 | 50 | 1000 | 180 | 1180 | 50 | 1180 |  | 50 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym -Installation of 2 TR Split AC | Installation of Split Unit | No. | 8 | 1500 | 12000 | 2160 | 14160 | 2.5 | 8 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - Nitrogen Pressure testing for Copper pi | Nitrogen Pressure & Leak Testing (L). | Mtrs | 106 | 15 | 1590 | 286.2 | 1876.2 | 2.5 | 106 | 1590 | 286.2 | 1876.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Thermal Insulation (L) | Sq.m. | 32 | 120 | 3840 | 691.2 | 4531.2 | 2.5 | 32 | 3840 | 691.2 | 4531.2 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - SITC of Copper piping i/c Nitrile rubbe | Copper Piping with insulation (L) | Mtrs | 106 | 150 | 15900 | 2862 | 18762 | 2.5 | 106 | 15900 | 2862 | 18762 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | GI Ducting (L) | Sq.m. | 70 | 240 | 16800 | 3024 | 19824 | 2.5 | 65.4083 | 15697.99 | 2825.64 | 18523.63 | 4.5917 | 1300.37 | The Price Shall include flanges,turning vans, galvanised supports full threaded rod & Hardware Nutset,Sealant(Neoprene gasket),Hangers,sheet thickness as per duct size & Guage etc. | 93.4404 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Dushant Gore | 13 Dec 2022
GANGA ASMI | 266 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | GI Ducting (L) | Sq.m. | 0 | 240 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | The Price shall include flanges,turning vans,galvnized supports full threaded rod & Hardware nutset,sealant (neoprene gasket),hangers,sheet thickness as per duct size & Gauge etc. | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 22 Mar 2022
GANGA ASMI | 266 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | AC Installation & Commissioning (L) | No. | 6 | 2500 | 15000 | 2700 | 17700 | 2.5 | 4 | 10000 | 1800 | 11800 | 2 | 5900 |  | 66.6667 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Dushant Gore | 13 Dec 2022
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Canvas Connection (M) | No. | 2 | 1500 | 3000 | 540 | 3540 | 0 | 2 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - Nitrogen Pressure testing for Copper pi | Nitrogen Pressure & Leak Testing (M). | Mtrs | 106 | 40 | 4240 | 763.2 | 5003.2 | 0 | 106 | 4240 | 763.2 | 5003.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 23 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - Gas Charging | Gas Charging (M). | Kgs | 34 | 1150 | 39100 | 7038 | 46138 | 0 | 2.72 | 3128 | 563.04 | 3691.04 | 31.28 | 42446.96 |  | 8 |  | DUSHANT GORE | Swapnil Erande | construction open | 23 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | M.S. Stand | No. | 6 | 4000 | 24000 | 4320 | 28320 | 0 | 4 | 16000 | 2880 | 18880 | 2 | 9440 |  | 66.6667 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Fresh Air Fans (M) | No. | 1 | 23380 | 23380 | 4208.4 | 27588.4 | 0 | 1 | 23380 | 4208.4 | 27588.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Nitrogen Pressure & Leak Testing (M) | No. | 90 | 40 | 3600 | 648 | 4248 | 0 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Gas Charging (M). | Kgs | 12 | 1250 | 15000 | 2700 | 17700 | 0 | 10 | 12500 | 2250 | 14750 | 2 | 2950 |  | 83.3333 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Soft Copper 22 Guage Ref Piping (M) | Mtrs | 90 | 800 | 72000 | 12960 | 84960 | 0 | 42.4 | 33920 | 6105.6 | 40025.6 | 47.6 | 44934.4 |  | 47.1111 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | SA Grill (M) | Sq.m. | 1.5 | 6250 | 9375 | 1687.5 | 11062.5 | 0 | 0.6 | 3750 | 675 | 4425 | 0.9 | 6637.5 |  | 40 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 2.5 Sqmm 4 Core Cable (M) | Mtrs | 110 | 119.08 | 13098.8 | 2357.78 | 15456.58 | 0 | 48.4632 | 5771 | 1038.78 | 6809.78 | 61.5368 | 8646.8 |  | 44.0575 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - SITC of Copper piping i/c Nitrile rubbe | Copper Piping with insulation (M) | Mtrs | 106 | 800 | 84800 | 15264 | 100064 | 0 | 106 | 84800 | 15264 | 100064 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 23 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym Readymade Outdoor unit stand-(No.) | Stand for ODU unit (M) | No. | 8 | 1250 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 23 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | GI Cowl with Bird Screen (M) | No. | 2 | 3000 | 6000 | 1080 | 7080 | 0 | 2 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - SITC Drain pipe I/C Nitrile rubber insu | Drain Pipe with Insulation (M) | Mtrs | 100 | 65 | 6500 | 1170 | 7670 | 0 | 50 | 3250 | 585 | 3835 | 50 | 3835 |  | 50 |  | DUSHANT GORE | Swapnil Erande | construction open | 23 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Canvas Connection (M) | No. | 2 | 2500 | 5000 | 900 | 5900 | 0 | 2 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 3C x 2.5sqmm (M) | Mtrs | 10 | 160.8 | 1608 | 289.44 | 1897.44 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | RA Grill (M) | Sq.m. | 2.5 | 4000 | 10000 | 1800 | 11800 | 0 | 0.8 | 3200 | 576 | 3776 | 1.7 | 8024 |  | 32 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Thermal Insulation (M) | Sq.m. | 32 | 440 | 14080 | 2534.4 | 16614.4 | 0 | 32 | 14080 | 2534.4 | 16614.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | 22 Guage GI Ducting (M) | Sq.m. | 32 | 1010 | 32320 | 5817.6 | 38137.6 | 0 | 25.5 | 25755 | 4635.9 | 30390.9 | 6.5 | 7746.7 |  | 79.6875 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | SITC of Drain Pipe (M) | Mtrs | 65 | 72 | 4680 | 842.4 | 5522.4 | 0 | 38.3889 | 2764 | 497.52 | 3261.52 | 26.6111 | 2260.88 |  | 59.0598 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | GI Ducting (M) | Sq.m. | 70 | 970 | 67900 | 12222 | 80122 | 0 | 65.4093 | 63447.02 | 11420.46 | 74867.48 | 4.5907 | 5254.52 |  | 93.4419 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 1 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Rennovation Installation of AC System | Hard Copper 18 Guage Ref Piping (M) | Mtrs | 6 | 1200 | 7200 | 1296 | 8496 | 0 | 2 | 2400 | 432 | 2832 | 4 | 5664 |  | 33.3333 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 2 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) Gym - SITC of Electric cable 2.5sqmm x 4C-(Mt | 4C x 2.5sqmm copper flexible cable (M) | Mtrs | 115 | 119.65 | 13759.75 | 2476.76 | 16236.51 | 0 | 115 | 13759.75 | 2476.76 | 16236.51 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 23 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 267 | 0 | 21 Mar 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House Pump room ventilation (L) | Exhaust Air Fan (M) | No. | 1 | 20700 | 20700 | 3726 | 24426 | 0 | 1 | 20700 | 3726 | 24426 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 23 Mar 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.9387 | 5632.2 | 0 | 5632.2 | 0.0613 | 367.8 |  | 93.87 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.885 | 5310 | 0 | 5310 | 0.115 | 690 |  | 88.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.424 | 2544 | 0 | 2544 | 0.576 | 3456 |  | 42.4 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.7687 | 4612.2 | 0 | 4612.2 | 0.2313 | 1387.8 |  | 76.87 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.908 | 5448 | 0 | 5448 | 0.092 | 552 |  | 90.8 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.804 | 4824 | 0 | 4824 | 0.196 | 1176 |  | 80.4 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.8074 | 4844.4 | 0 | 4844.4 | 0.1926 | 1155.6 |  | 80.74 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.8508 | 5104.8 | 0 | 5104.8 | 0.1492 | 895.2 |  | 85.08 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 1 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.8373 | 5023.8 | 0 | 5023.8 | 0.1627 | 976.2 |  | 83.73 |  | DUSHANT GORE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 268 | 0 | 23 Mar 2022 | ANIL SHRIHARI MEDHAKE | Site Expenses | Tea Expenses-SO | Month | 1 | 6000 | 6000 | 0 | 6000 | 0 | 0.7786 | 4671.6 | 0 | 4671.6 | 0.2214 | 1328.4 |  | 77.86 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 3 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Goel House (L) Borewell Work | Casing Caping For Bore well | R.Ft | 0 | 350 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | Dushant Gore | 06 May 2022
GANGA ASMI | 269 | 2 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | Casing Caping For Bore well | R.Ft | 0 | 350 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 27 Apr 2022
GANGA ASMI | 269 | 4 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | Casing Caping For Bore well | R.Ft | 10 | 350 | 3500 | 0 | 3500 | 2.5 | 10 | 3500 | 630 | 4130 | 0 | -630 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 2 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | Bore Survey - UWR | No. | 1 | 4000 | 4000 | 0 | 4000 | 0 | 1 | 4000 | 720 | 4720 | 0 | -720 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Water Supply | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 2 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | Casing Caping For Bore well | R.Ft | 80 | 350 | 28000 | 0 | 28000 | 0 | 80 | 28000 | 5040 | 33040 | 0 | -5040 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 0 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | Bore Survey - UWR | No. | 1 | 4000 | 4000 | 0 | 4000 | 2.5 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Water Supply | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 0 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | Drilling work- UTR | R.Ft | 600 | 95 | 57000 | 0 | 57000 | 2.5 | 600 | 57000 | 0 | 57000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Rainwater harvesting | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 3 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Goel House (L) Borewell Work | Casing Caping For Bore well | R.Ft | 10 | 350 | 3500 | 0 | 3500 | 0 | 10 | 3500 | 630 | 4130 | 0 | -630 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 1 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Goel House (L) Borewell Work | Casing Caping For Bore well | R.Ft | 0 | 350 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | Dushant Gore | 02 Apr 2022
GANGA ASMI | 269 | 0 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | Casing Caping For Bore well | R.Ft | 70 | 350 | 24500 | 0 | 24500 | 2.5 | 70 | 24500 | 0 | 24500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 1 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Goel House (L) Borewell Work | 6" Bore Well | R.Ft | 250 | 95 | 23750 | 0 | 23750 | 2.5 | 250 | 23750 | 0 | 23750 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 2 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | Borewell Work - UWR | No. | 0 | 4000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | UTI. Water Supply | Cancelled | ADITYA CHOUGULE | 27 Apr 2022
GANGA ASMI | 269 | 2 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | 6" Bore Well | R.Ft | 600 | 95 | 57000 | 0 | 57000 | 0 | 560.004 | 53200.38 | 9576.06 | 62776.44 | 39.996 | -5776.44 |  | 93.334 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 1 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Goel House (L) Borewell Work | Casing Caping For Bore well | R.Ft | 30 | 350 | 10500 | 0 | 10500 | 2.5 | 30 | 10500 | 0 | 10500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 269 | 2 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Borewell Work | 6" Bore Well | R.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | skmishra | 27 Apr 2022
GANGA ASMI | 269 | 1 | 23 Mar 2022 | DEEP MAN ENTERPRISES | Goel House (L) Borewell Work | 6" Bore Well | R.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | Dushant Gore | 02 Apr 2022
GANGA ASMI | 270 | 0 | 28 Mar 2022 | RAJSAN ENTERPRISES | Goel House New Extension-roofing work | Tensile Canopy | Sq.Ft | 2530 | 350 | 885500 | 159390 | 1044890 | 0 | 1667.8 | 583730 | 105071.4 | 688801.4 | 862.2 | 356088.6 |  | 65.9209 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 28 Mar 2022 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 270 | 1 | 28 Mar 2022 | RAJSAN ENTERPRISES | Goel House New Extension-roofing work | Tensile Canopy | Sq.Ft | 0 | 410 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 28 Mar 2022 |  | DEV. Swimming Pool | Cancelled | ADITYA CHOUGULE | 17 Sep 2022
GANGA ASMI | 270 | 1 | 28 Mar 2022 | RAJSAN ENTERPRISES | Goel House New Extension-roofing work | Tensile Canopy | Sq.Ft | 101 | 410 | 41410 | 7453.8 | 48863.8 | 0 | 101 | 41410 | 7453.8 | 48863.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 28 Mar 2022 |  | DEV. Swimming Pool | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 271 | 0 | 29 Mar 2022 | F. G. SHAIKH | Goel House Material shifting - 1 No. | Tractor Trips DLT | Trips | 10 | 900 | 9000 | 0 | 9000 | 0 | 10 | 9000 | 0 | 9000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Mar 2022 |  | DEV. Local Trips | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 272 | 0 | 29 Mar 2022 | BAJRANG ENTERPRISES | GH Outhouse New Interior & Furnishing new - 1 No. | Carpentary work (L)-BC | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 272 | 0 | 29 Mar 2022 | BAJRANG ENTERPRISES | GH Outhouse New Interior & Furnishing new - 1 No. | Carpentary work (L)-BC | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 272 | 0 | 29 Mar 2022 | BAJRANG ENTERPRISES | GH Outhouse New Interior & Furnishing new - 1 No. | Carpentary work (L)-BC | No. | 1 | 13000 | 13000 | 2340 | 15340 | 0 | 1 | 13000 | 2340 | 15340 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Mar 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 273 | 0 | 29 Mar 2022 | NISAR AHMAD ANSARI | Goel House Meeting room 3 interior Work - 1 No. | P.U. Paint | Sq.Ft | 132 | 180 | 23760 | 4276.8 | 28036.8 | 2.5 | 132 | 23760 | 4276.8 | 28036.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 273 | 0 | 29 Mar 2022 | NISAR AHMAD ANSARI | Goel House Meeting room 3 interior Work - 1 No. | P.U. Matt | R.Ft | 142.2 | 55 | 7821 | 1407.78 | 9228.78 | 2.5 | 142.2 | 7821 | 1407.78 | 9228.78 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 273 | 0 | 29 Mar 2022 | NISAR AHMAD ANSARI | Goel House Meeting room 3 interior Work - 1 No. | Duco P.U. Paint - BCo | Sq.Ft | 87.46 | 250 | 21865 | 3935.7 | 25800.7 | 2.5 | 87.46 | 21865 | 3935.7 | 25800.7 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Mar 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 273 | 1 | 29 Mar 2022 | NISAR AHMAD ANSARI | Goel House Laser Cut Jali Back Support MS frame | Zinc Polish | R.Ft | 6181 | 35 | 216335 | 38940.3 | 255275.3 | 0 | 0 | 0 | 0 | 0 | 6181 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Mar 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 274 | 0 | 29 Mar 2022 | RAJYOG ENTERPRISES | Goel House (L) Removing & fixing work of glass | Transport Charges | No. | 1 | 4500 | 4500 | 810 | 5310 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 274 | 0 | 29 Mar 2022 | RAJYOG ENTERPRISES | Goel House (L) Removing & fixing work of glass | Fixing of laminated Glass | Sq.Ft | 69 | 550 | 37950 | 6831 | 44781 | 2.5 | 0 | 0 | 0 | 0 | 69 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 274 | 0 | 29 Mar 2022 | RAJYOG ENTERPRISES | Goel House (L) Removing & fixing work of glass | Removing of damaged Glass | Sq.Ft | 69 | 120 | 8280 | 1490.4 | 9770.4 | 0 | 0 | 0 | 0 | 0 | 69 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 275 | 0 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Sliding Window with top fix | Sq.Ft | 189.39 | 1286.25 | 243602.89 | 43848.52 | 287451.41 | 2.5 | 189.39 | 243602.89 | 43848.52 | 287451.41 | 0 | 0 | 3.910 x 2100/2250- 2 nos, 3 Track shutter 1 mesh shutter with top 2 part fix. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 0 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Cap Curtainwall Glazing- Skylight | Sq.Ft | 338.97 | 1553.93 | 526735.65 | 94812.42 | 621548.07 | 2.5 | 338.97 | 526735.65 | 94812.42 | 621548.07 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 2 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation Material req for Room No-4 & 7 | Glass Removing and Refixing | Sq.Ft | 36.41 | 71.52 | 2604.04 | 468.72 | 3072.76 | 2.5 | 36.41 | 2604.04 | 468.72 | 3072.76 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 2 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation Material req for Room No-4 & 7 | Glass Removing and Refixing | Sq.Ft | 0 | 71.52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Aug 2022
GANGA ASMI | 275 | 1 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Cap Curtainwall Glazing- Skylight | Sq.Ft | 338.97 | 1553.93 | 526735.65 | 94812.42 | 621548.07 | 2.5 | 338.97 | 526735.65 | 94812.42 | 621548.07 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 2 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation Material req for Room No-4 & 7 | Glass Replacement | Sq.Ft | 17.76 | 570.25 | 10127.64 | 1822.98 | 11950.62 | 2.5 | 0 | 0 | 0 | 0 | 17.76 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 2 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation Material req for Room No-4 & 7 | Handle Fixing - Mkt | No. | 1 | 2860.8 | 2860.8 | 514.94 | 3375.74 | 2.5 | 1 | 2860.8 | 514.94 | 3375.74 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 2 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation Material req for Room No-4 & 7 | Glass Replacement | Sq.Ft | 18.65 | 754.29 | 14067.51 | 2532.16 | 16599.67 | 2.5 | 0 | 0 | 0 | 0 | 18.65 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 2 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House Rennovation Material req for Room No-4 & 7 | Glass Removing and Refixing | Sq.Ft | 18.76 | 71.52 | 1341.72 | 241.5 | 1583.22 | 2.5 | 18.76 | 1341.72 | 241.5 | 1583.22 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 0 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Fix Window | Sq.Ft | 77.65 | 719.77 | 55890.14 | 10060.22 | 65950.36 | 2.5 | 77.65 | 55890.14 | 10060.22 | 65950.36 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 275 | 0 | 30 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Fix Window | Sq.Ft | 77.19 | 719.77 | 55559.05 | 10000.62 | 65559.67 | 2.5 | 77.19 | 55559.05 | 10000.62 | 65559.67 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 276 | 0 | 31 Mar 2022 | ALFA FACADE SYSTEMS PRIVATE LIMITED | Goel House (L) Facad work | Casement Door (M+L) - Sq.Ft | Sq.Ft | 38.75 | 1581 | 61263.75 | 11027.48 | 72291.23 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 | Bed room 5 & 6 glass side ac maintainance work. | 0 |  | Ranjit Deore |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 277 | 0 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Park (Flex Printing) | No. | 1 | 130 | 130 | 23.4 | 153.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Assembly point (Flex Printing)- No. | No. | 0 | 210 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 04 Apr 2022 |  | No category | Cancelled | MONALI CHAUDHAR | 10 Jul 2024
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Posters (Flex Printing) | No. | 0 | 180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Cancelled | MONALI CHAUDHAR | 10 Jul 2024
GANGA ASMI | 277 | 0 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Lab & Safety Equipments Site Safety Material | Safety Posters (Flex Printing) | No. | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Cancelled | skmishra | 04 Apr 2022
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Assembly point (Flex Printing)- No. | No. | 2 | 180 | 360 | 64.8 | 424.8 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 04 Apr 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 277 | 1 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Park (Flex Printing) (Rate diff.) | No. | 1 | 1470 | 1470 | 264.6 | 1734.6 | 0 | 1 | 1470 | 264.6 | 1734.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Apr 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 277 | 0 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Lab & Safety Equipments Site Safety Material | Safety Park (Flex Printing) | No. | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Cancelled | skmishra | 04 Apr 2022
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Posters (Flex Printing) | No. | 54 | 130 | 7020 | 1263.6 | 8283.6 | 0 | 0 | 0 | 0 | 0 | 54 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Park (Flex Printing) | No. | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Cancelled | MONALI CHAUDHAR | 10 Jul 2024
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Park (Flex Printing) | No. | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Cancelled | MONALI CHAUDHAR | 10 Jul 2024
GANGA ASMI | 277 | 0 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Park (Flex Printing) | No. | 0 | 130 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Cancelled | Dushant Gore | 04 Apr 2022
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Park (Flex Printing) | No. | 0 | 1920 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Cancelled | MONALI CHAUDHAR | 09 Jul 2024
GANGA ASMI | 277 | 0 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Posters (Flex Printing) | No. | 43 | 130 | 5590 | 1006.2 | 6596.2 | 0 | 43 | 5590 | 1006.2 | 6596.2 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Posters (Flex Printing) | No. | 0 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Cancelled | MONALI CHAUDHAR | 09 Jul 2024
GANGA ASMI | 277 | 2 | 01 Apr 2022 | MAYUR ARTS & ENTERPRISES | Safety Boards/Flex Printing | Safety Park (Flex Printing) | No. | 1 | 1600 | 1600 | 288 | 1888 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 04 Apr 2022 |  | 17 SIGNAGES | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 278 | 0 | 02 Apr 2022 | AKASH ENTERPRISES (PROP. DAMU RATHOD) | Wing-1 Substructure Lift Pit Screeding Work | Screeding W/P-BCo | Sq.Ft | 1567.62 | 12 | 18811.44 | 0 | 18811.44 | 10 | 1567.62 | 18811.44 | 3386.06 | 22197.5 | 0 | -3386.06 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 120 | 500 | 60000 | 10800 | 70800 | 0 | 100.0008 | 50000.4 | 3600.08 | 53600.48 | 19.9992 | 17199.52 |  | 83.334 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 124 | 62000 | 11160 | 73160 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 120 | 500 | 60000 | 10800 | 70800 | 0 | 105.8004 | 52900.2 | 9522.04 | 62422.24 | 14.1996 | 8377.76 |  | 88.167 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 36 | 18000 | 0 | 18000 | 88 | 55160 |  | 29.0323 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 1 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Sludge removing for PCC & Footing - wing 2 | Male Coolie | Day | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Apr 2022 |  | SOC. M. Maintenace of Utilitie | Cancelled | ADITYA CHOUGULE | 09 Aug 2022
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 120 | 500 | 60000 | 10800 | 70800 | 0 | 42.6 | 21300 | 3834 | 25134 | 77.4 | 45666 |  | 35.5 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 1 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Sludge removing for PCC & Footing - wing 2 | Male Coolie | No. | 60 | 550 | 33000 | 5940 | 38940 | 0 | 45 | 24750 | 4455 | 29205 | 15 | 9735 |  | 75 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 120 | 500 | 60000 | 10800 | 70800 | 0 | 0 | 0 | 0 | 0 | 120 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 120 | 500 | 60000 | 10800 | 70800 | 0 | 56.4 | 28200 | 5076 | 33276 | 63.6 | 37524 |  | 47 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 120 | 500 | 60000 | 10800 | 70800 | 0 | 120 | 60000 | 10800 | 70800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 112 | 500 | 56000 | 10080 | 66080 | 0 | 93.8 | 46900 | 8442 | 55342 | 18.2 | 10738 |  | 83.75 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 120 | 500 | 60000 | 10800 | 70800 | 0 | 34.8 | 17400 | 0 | 17400 | 85.2 | 53400 |  | 29 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 124 | 62000 | 11160 | 73160 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 82.5 | 41250 | 7425 | 48675 | 41.5 | 24485 |  | 66.5323 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 67 | 33500 | 6030 | 39530 | 57 | 33630 |  | 54.0323 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 120 | 500 | 60000 | 10800 | 70800 | 0 | 33.6 | 16800 | 0 | 16800 | 86.4 | 54000 |  | 28 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 20.2021 | 10101.05 | 1818.2 | 11919.25 | 103.7979 | 61240.75 |  | 16.292 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 124 | 62000 | 11160 | 73160 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 124 | 62000 | 11160 | 73160 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 65.4 | 32700 | 5886 | 38586 | 58.6 | 34574 |  | 52.7419 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 0 | 0 | 0 | 0 | 124 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 112 | 500 | 56000 | 10080 | 66080 | 0 | 112 | 56000 | 10080 | 66080 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 91.701 | 45850.5 | 5067.08 | 50917.58 | 32.299 | 22242.42 |  | 73.9524 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 86.2011 | 43100.55 | 7758.1 | 50858.65 | 37.7989 | 22301.35 |  | 69.517 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 31.8 | 15900 | 0 | 15900 | 92.2 | 57260 |  | 25.6452 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 279 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Site Infra Departmental Labour | Male Coolie | No. | 124 | 500 | 62000 | 11160 | 73160 | 0 | 105.6009 | 52800.45 | 9504.08 | 62304.53 | 18.3991 | 10855.47 |  | 85.162 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Weigh Bridge civil work | Concrete Work - BCP | Cu.Mtrs | 3.458 | 300 | 1037.4 | 186.74 | 1224.14 | 2.5 | 3.458 | 1037.4 | 186.74 | 1224.14 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Misc. Development Work | Fitter | No. | 8 | 1000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Weigh Bridge civil work | Shuttering work-Mkt | Sq.m. | 38.68 | 500 | 19340 | 3481.2 | 22821.2 | 2.5 | 38.68 | 19340 | 3481.2 | 22821.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Weigh Bridge civil work | Soling Work-BC- | Sq.Ft | 397.407 | 6.5 | 2583.15 | 464.96 | 3048.11 | 0 | 397.407 | 2583.15 | 464.96 | 3048.11 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Misc. Development Work | Tractor Trips-BRE | Trips | 11 | 1000 | 11000 | 1980 | 12980 | 0 | 11 | 11000 | 1980 | 12980 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Weigh Bridge civil work | Concrete Work - BCP | Cu.Mtrs | 6.57 | 300 | 1971 | 354.78 | 2325.78 | 2.5 | 6.57 | 1971 | 354.78 | 2325.78 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Misc. Development Work | Crane Charges-SOSE | No. | 4 | 1500 | 6000 | 1080 | 7080 | 0 | 4 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 1 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Steel Cutting Yard Steel Yard Vertical Pole Grouting | Misc Work - AIE | No. | 1 | 12000 | 12000 | 2160 | 14160 | 0 | 0.9167 | 11000.4 | 1980.08 | 12980.48 | 0.0833 | 1179.52 |  | 91.67 |  | Dushant Gore | Swapnil Erande | construction open | 07 Apr 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 3 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Concrete Road Maintenance | Lumpsum work- DCW | No. | 1 | 7000 | 7000 | 1260 | 8260 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 2 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Misc. Development Work | Transportaion | No. | 1 | 829 | 829 | 149.22 | 978.22 | 0 | 1 | 829 | 149.22 | 978.22 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Weigh Bridge civil work | Concrete Breaking work-DER | Cu.Mtrs | 3.522 | 750 | 2641.5 | 475.48 | 3116.98 | 0 | 3.522 | 2641.5 | 475.48 | 3116.98 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | DEV. Extrawork/Rework | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Weigh Bridge civil work | Excavation | Cu.Ft | 828.374 | 6.5 | 5384.43 | 969.2 | 6353.63 | 0 | 828.2083 | 5383.35 | 969 | 6352.35 | 0.1657 | 1.28 |  | 99.98 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 0 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Weigh Bridge civil work | Reinforcement (L) | Kgs | 505.923 | 7.5 | 3794.42 | 683 | 4477.42 | 2.5 | 500.8638 | 3756.48 | 676.16 | 4432.64 | 5.0592 | 44.78 |  | 99 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 280 | 4 | 02 Apr 2022 | SAIRAJ CONSTRUCTION | Labour Camp Toilet Civil Work | Labour Lumsum-BC | No. | 1 | 18000 | 18000 | 3240 | 21240 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 07 Apr 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 31 | 30 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 30 | 30 | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 30 | 30 | 900 | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 31 | 30 | 930 | 0 | 930 | 0 | 31 | 930 | 0 | 930 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 31 | 30 | 930 | 0 | 930 | 0 | 31 | 930 | 0 | 930 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 28 | 30 | 840 | 0 | 840 | 0 | 28 | 840 | 0 | 840 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 31 | 30 | 930 | 0 | 930 | 0 | 31 | 930 | 0 | 930 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 0 | 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Cancelled | skmishra | 06 Apr 2022
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 30 | 30 | 900 | 0 | 900 | 0 | 28 | 840 | 0 | 840 | 2 | 60 |  | 93.3333 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 31 | 30 | 930 | 0 | 930 | 0 | 31 | 930 | 0 | 930 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 31 | 30 | 930 | 0 | 930 | 0 | 31 | 930 | 0 | 930 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 31 | 30 | 930 | 0 | 930 | 0 | 0 | 0 | 0 | 0 | 31 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 30 | 30 | 900 | 0 | 900 | 0 | 30 | 900 | 0 | 900 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 281 | 0 | 04 Apr 2022 | MURLIDHAR LIMBAJI KAMBLE | GH Travelling Allowance | Travelling allowance. | Day | 31 | 30 | 930 | 0 | 930 | 0 | 28 | 840 | 0 | 840 | 3 | 90 |  | 90.3226 |  | Dushant Gore | Swapnil Erande | construction open | 06 Apr 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 282 | 0 | 04 Apr 2022 | AQUARIUS VENTURES | MEDIA Event Expenses | Exhibition | No. | 1 | 107100 | 107100 | 19278 | 126378 | 0 | 1 | 107100 | 19278 | 126378 | 0 | 0 | WEST PUNE MEGA HOME BUYING FESTIVAL AT TIP TOP INTERNATIONAL , WAKAD DTD. 09 AND 10TH APRIL 2022 STALL SIZE AS 3X3 SQ MTR. STALL NO. 31 | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 07 Apr 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 283 | 0 | 04 Apr 2022 | DREAMTREE EXPERIENCE | PRINTING PRINTING-NO.-(NA) | Exhibition Expencess - Mkt | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 | WEST PUNE MEGA HOME BUYING FESTIVAL EXHIBITION AT WAKAD STALL SET UP EXPENCES. | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 18 Apr 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 284 | 0 | 05 Apr 2022 | FIRE CLOSURE SYSTEMS | Lab & Safety Equipments Site Safety Material | Fire Extinguisher refilling- SO | No. | 12 | 550 | 6600 | 1188 | 7788 | 0 | 10.9992 | 6049.56 | 1088.92 | 7138.48 | 1.0008 | 649.52 |  | 91.66 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 284 | 0 | 05 Apr 2022 | FIRE CLOSURE SYSTEMS | Lab & Safety Equipments Site Safety Material | Fire Extinguisher refilling- SO | No. | 2 | 550 | 1100 | 198 | 1298 | 0 | 2 | 1100 | 198 | 1298 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 284 | 0 | 05 Apr 2022 | FIRE CLOSURE SYSTEMS | Lab & Safety Equipments Site Safety Material | Fire Extinguisher refilling- SO | No. | 0 | 550 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 05 Apr 2022 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 05 Apr 2022
GANGA ASMI | 284 | 1 | 05 Apr 2022 | FIRE CLOSURE SYSTEMS | Lab & Safety Equipments Site Safety Material | Fire Extinguisher refilling- SO | No. | 2 | 550 | 1100 | 198 | 1298 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 05 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 285 | 0 | 06 Apr 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House (L) AMC for 30 KVA UPS System | AMC Charges | Month | 12 | 1218.75 | 14625 | 2632.5 | 17257.5 | 0 | 12 | 14625 | 2632.56 | 17257.56 | 0 | -0.06 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Apr 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 285 | 1 | 06 Apr 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House (L) AMC for 30 KVA UPS System | AMC Charges | Month | 12 | 1500 | 18000 | 3240 | 21240 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 06 Apr 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 285 | 0 | 06 Apr 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House Electrical Work | AMC Charges | Month | 0 | 1187.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 06 Apr 2022 |  | Admin. Indirect Expenses | Cancelled | ADITYA CHOUGULE | 06 Apr 2022
GANGA ASMI | 286 | 1 | 06 Apr 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House (L) AMC for 125 KVA Stabilizer | AMC Charges | Month | 12 | 1187.5 | 14250 | 2565 | 16815 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 06 Apr 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 286 | 2 | 06 Apr 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House (L) AMC for 125 KVA Stabilizer | AMC Charges | Month | 12 | 1416.66 | 16999.92 | 3059.98 | 20059.9 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Apr 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 286 | 0 | 06 Apr 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House (L) AMC for 125 KVA Stabilizer | AMC Charges | Month | 12 | 1187.5 | 14250 | 2565 | 16815 | 0 | 12 | 14250 | 2565.12 | 16815.12 | 0 | -0.12 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Apr 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 287 | 0 | 08 Apr 2022 | SHRUSTI FLORALS | Goel House Garden Maintenance work | Garden maintenance material-SMA | Month | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Apr 2022 |  | SOC. M. Maintenace of Aminitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Cut Point Channel installation (m+l) | No. | 2 | 1500 | 3000 | 540 | 3540 | 2.5 | 2 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Manual Change over MCB Type | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | 125 Amp 4 Pole MCCB Fixing | No. | 4 | 2000 | 8000 | 1440 | 9440 | 2.5 | 4 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Pole Fixing (M+L) | No. | 2 | 20000 | 40000 | 7200 | 47200 | 2.5 | 2 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | 6" Half round Hume Pipe laying | Mtrs | 250 | 30 | 7500 | 1350 | 8850 | 2.5 | 198 | 5940 | 1069.2 | 7009.2 | 52 | 1840.8 |  | 79.2 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Al. Arm. Cable laying 3.5C 185sqmm-UTI | Mtrs | 160 | 75 | 12000 | 2160 | 14160 | 2.5 | 160 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Cut Point Channel installation (m+l) | No. | 2 | 2000 | 4000 | 720 | 4720 | 2.5 | 2 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Earthing work - ULT | No. | 2 | 4000 | 8000 | 1440 | 9440 | 2.5 | 1 | 4000 | 720 | 4720 | 1 | 4720 |  | 50 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Cut Point Channel installation (m+l) | No. | 2 | 1500 | 3000 | 540 | 3540 | 2.5 | 2 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | End Termination 120 Sqmm - UTI | No. | 1 | 900 | 900 | 162 | 1062 | 2.5 | 1 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | 8 Gauge GI Wire | Mtrs | 20 | 9 | 180 | 32.4 | 212.4 | 2.5 | 20 | 180 | 32.4 | 212.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Al. Arm. Cable laying 3C 300sqmm-UTI | Mtrs | 160 | 140 | 22400 | 4032 | 26432 | 2.5 | 160 | 22400 | 4032 | 26432 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | HT Conductor Disconnection | Mtrs | 280 | 20 | 5600 | 1008 | 6608 | 2.5 | 269.9984 | 5399.97 | 972 | 6371.97 | 10.0016 | 236.03 |  | 96.428 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Jointing Kit 300sqmm OD (m+l) | No. | 2 | 6300 | 12600 | 2268 | 14868 | 2.5 | 2 | 12600 | 2268 | 14868 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Stay Pole (Wire Fixing) | No. | 2 | 1500 | 3000 | 540 | 3540 | 2.5 | 2 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | LT Conductor Disconnection | Mtrs | 360 | 10 | 3600 | 648 | 4248 | 2.5 | 360 | 3600 | 648 | 4248 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 288 | 0 | 08 Apr 2022 | LAXMI ELECTRICALS | Electrical Work HT/LT Line Underground | Pole Fixing (M+L) | No. | 0 | 2000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Cancelled | Dushant Gore | 08 Apr 2022
GANGA ASMI | 289 | 0 | 25 Mar 2022 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 38000 | 228000 | 41040 | 269040 | 0 | 5 | 190000 | 34200 | 224200 | 1 | 44840 | GANGA ASMI , WAKAD PROJECT DISPLAY BRANDING HOARDING DISPLAY CHARGES @ OPP. GANGA ASMI PROJECT FACING HINJEWADI SIZE AS 30X30 SQ FT AS ON 18.03.2022 TO 17.06.2022 238000/- + TAX. | 83.3333 |  | Tejas Raverkar | Tejas Raverkar | construction open | 17 Jun 2022 |  | MKT. Media | Approved | Tejas Raverkar | 1900-01-01
GANGA ASMI | 290 | 0 | 13 Apr 2022 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 45000 | 270000 | 48600 | 318600 | 0 | 6 | 270000 | 48600 | 318600 | 0 | 0 | GANGA ASMI WAKAD, PROJECT HOARDING DISPLAY BRANDING @ WAKAD PROJECT SIZE AS 30X42 BACK TO BACK BOTH SIDED HOARDING AS ON 01.04.2022 TO 30.09.2022 @45000/- + TAX PM. | 100 |  | Tejas Raverkar | Tejas Raverkar | construction open | 17 Jun 2022 |  | MKT. Media | Approved | TEJAS RAVERKAR | 14 Sep 2022
GANGA ASMI | 291 | 0 | 18 Apr 2022 | JAY GANESH ENTERPRISES | Goel House Department Work | Male Coolie | No. | 4 | 550 | 2200 | 0 | 2200 | 0 | 4 | 2200 | 0 | 2200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 291 | 0 | 18 Apr 2022 | JAY GANESH ENTERPRISES | Goel House Department Work | Plaster Mason - UDR | No. | 6 | 1050 | 6300 | 0 | 6300 | 0 | 6 | 6300 | 0 | 6300 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 291 | 1 | 18 Apr 2022 | JAY GANESH ENTERPRISES | GH Gym Room Jacuzzi BBM Work | Sand face Plaster- BC | Sq.Ft | 136.5 | 30 | 4095 | 0 | 4095 | 2.5 | 136.5 | 4095 | 0 | 4095 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Apr 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 291 | 0 | 18 Apr 2022 | JAY GANESH ENTERPRISES | Goel House Department Work | Female Coolie | No. | 3 | 350 | 1050 | 0 | 1050 | 0 | 3 | 1050 | 0 | 1050 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 291 | 1 | 18 Apr 2022 | JAY GANESH ENTERPRISES | GH Gym Room Jacuzzi BBM Work | Brickwork 18" BC | Sq.Ft | 71.74 | 60 | 4304.4 | 0 | 4304.4 | 2.5 | 71.74 | 4304.4 | 0 | 4304.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Apr 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 291 | 1 | 18 Apr 2022 | JAY GANESH ENTERPRISES | GH Gym Room Jacuzzi BBM Work | 9" Brick Work | Sq.Ft | 85.87 | 30 | 2576.1 | 0 | 2576.1 | 2.5 | 85.87 | 2576.1 | 0 | 2576.1 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Apr 2022 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 62 | 387.09 | 23999.58 | 0 | 23999.58 | 0 | 62 | 23999.58 | 0 | 23999.58 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 0 | 428.57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 25 Apr 2022
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 19 Apr 2022
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 62 | 387.09 | 23999.58 | 0 | 23999.58 | 0 | 62 | 23999.58 | 0 | 23999.58 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 62 | 387.09 | 23999.58 | 0 | 23999.58 | 0 | 59 | 22838.31 | 0 | 22838.31 | 3 | 1161.27 |  | 95.1613 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 56 | 428.57 | 23999.92 | 0 | 23999.92 | 0 | 56 | 23999.92 | 0 | 23999.92 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 60 | 400 | 24000 | 0 | 24000 | 0 | 59 | 23600 | 0 | 23600 | 1 | 400 |  | 98.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 0 | 387.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | ADITYA CHOUGULE | 19 Apr 2022
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 0 | 387.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 25 Apr 2022
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 62 | 387.09 | 23999.58 | 0 | 23999.58 | 0 | 57.0003 | 22064.25 | 0 | 22064.25 | 4.9997 | 1935.33 |  | 91.936 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 60 | 400 | 24000 | 0 | 24000 | 0 | 56 | 22400 | 0 | 22400 | 4 | 1600 |  | 93.3333 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 62 | 387.09 | 23999.58 | 0 | 23999.58 | 0 | 62 | 23999.58 | 0 | 23999.58 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 60 | 400 | 24000 | 0 | 24000 | 0 | 60 | 24000 | 4320 | 28320 | 0 | -4320 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 62 | 387.09 | 23999.58 | 0 | 23999.58 | 0 | 60.0005 | 23225.59 | 0 | 23225.59 | 1.9995 | 773.99 |  | 96.775 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 60 | 400 | 24000 | 0 | 24000 | 0 | 60 | 24000 | 0 | 24000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 62 | 387.09 | 23999.58 | 0 | 23999.58 | 0 | 62 | 23999.58 | 0 | 23999.58 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 292 | 0 | 19 Apr 2022 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance Work | Day | 0 | 387.09 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 15 LANDSCAPE & GARDEN WORK | Cancelled | skmishra | 25 Apr 2022
GANGA ASMI | 293 | 1 | 22 Apr 2022 | VIKAS GARADE | Site Infra Drainage Line Cleaning | Drainage Line Cleaning - UDR | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 29 Apr 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 293 | 2 | 22 Apr 2022 | VIKAS GARADE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 Apr 2022 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 293 | 0 | 22 Apr 2022 | VIKAS GARADE | Site Infra Septic Tank Cleaning | Septic Tank Cleaning services | No. | 4 | 1000 | 4000 | 0 | 4000 | 0 | 4 | 4000 | 720 | 4720 | 0 | -720 | 4 Times in Year. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Apr 2022 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 293 | 2 | 22 Apr 2022 | VIKAS GARADE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 Apr 2022 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 293 | 2 | 22 Apr 2022 | VIKAS GARADE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 29 Apr 2022 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 294 | 0 | 22 Apr 2022 | SAI NIRMAL COLOURS & TEXTURES | Goel House (L) Goel House External texture Painting Work | Texture Paint (L) | Sq.Ft | 2011.75 | 30 | 60352.5 | 10863.46 | 71215.96 | 2.5 | 2011.75 | 60352.5 | 10863.46 | 71215.96 | 0 | 0 | Bedroom 5,6 & Kitchen wall external texture paint. | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 295 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Control Cabling (M) | Mtrs | 40 | 84 | 3360 | 604.8 | 3964.8 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 295 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Drain Piping (M) | Mtrs | 30 | 50 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 295 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Refrigerant Piping (M) | Mtrs | 30 | 800 | 24000 | 4320 | 28320 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 295 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Stand for ODU unit (M) | No. | 2 | 500 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 296 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Control Cabling (L) | Mtrs | 40 | 20 | 800 | 144 | 944 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 296 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Dismentalling work-UTI | No. | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Cancelled | ADITYA CHOUGULE | 23 Apr 2022
GANGA ASMI | 296 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Installation of AC Machines (L) | No. | 2 | 1500 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 296 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Drain Piping (L) | Mtrs | 30 | 20 | 600 | 108 | 708 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 296 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Installation of AC Machines (L) | No. | 0 | 1500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Cancelled | ADITYA CHOUGULE | 23 Apr 2022
GANGA ASMI | 296 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Stand for ODU unit (L) | No. | 2 | 157 | 314 | 56.52 | 370.52 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 296 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | Goel House (L) AC Work | Refrigerant Piping (L) | Mtrs | 30 | 175 | 5250 | 945 | 6195 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 297 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | A9 11th Flr Renovation AC Work (L) | Dismantling work | No. | 5 | 600 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 297 | 0 | 23 Apr 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | A9 11th Flr Renovation AC Work (L) | Installation of AC Machines (L) | No. | 5 | 1500 | 7500 | 1350 | 8850 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 298 | 0 | 23 Apr 2022 | YOGESH BALU ICHAKE | Survey Work | Total Statiotn Survey | Day | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4 Days Before casting + 4 Days tie Beam+ Architect 2 Days+ 5Days Quality Person | 0 |  | ADITYA CHOUGULE |  | construction open | 25 Apr 2022 |  | Land Cost | Cancelled | skmishra | 25 Apr 2022
GANGA ASMI | 299 | 1 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey work (Wing 2) | Total Station Point marking. | No. | 350 | 100 | 35000 | 6300 | 41300 | 0 | 144 | 14400 | 2592 | 16992 | 206 | 24308 |  | 41.1429 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 2 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 2nd Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 1 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey work (Wing 2) | Total Station Point marking. | No. | 350 | 100 | 35000 | 6300 | 41300 | 0 | 349.0035 | 34900.35 | 6282.04 | 41182.39 | 0.9965 | 117.61 |  | 99.7153 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 2 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 3rd Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 1 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey work (Wing 2) | Total Station Point marking. | No. | 350 | 100 | 35000 | 6300 | 41300 | 0 | 330.0015 | 33000.15 | 5940.02 | 38940.17 | 19.9985 | 2359.83 |  | 94.2861 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 4 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 Ground Flr Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 0 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey Work | Total Statiotn Survey | Day | 10 | 4500 | 45000 | 8100 | 53100 | 0 | 10 | 45000 | 1620 | 46620 | 0 | 6480 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 29 Apr 2022 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 2 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 5th Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 26 | 2600 | 468 | 3068 | 74 | 8732 |  | 26 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 2 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 4th Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 96 | 9600 | 1728 | 11328 | 4 | 472 |  | 96 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 2 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 1st Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 29 Apr 2022 |  | DEV. Club House | Cancelled | Dushant Gore | 07 Nov 2022
GANGA ASMI | 299 | 3 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 Parking (Non Tower) Total Station point marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 1 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey work (Wing 2) | Total Station Point marking. | No. | 350 | 100 | 35000 | 6300 | 41300 | 0 | 349.9954 | 34999.54 | 6299.9 | 41299.44 | 0.0046 | 0.56 |  | 99.9987 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 2 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 1st Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 29 Apr 2022 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 299 | 1 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey Work | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 29 Apr 2022 |  | DEV. Club House | Cancelled | Dushant Gore | 17 Sep 2022
GANGA ASMI | 299 | 1 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey Work | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 29 Apr 2022 |  | DEV. Club House | Cancelled | Dushant Gore | 17 Sep 2022
GANGA ASMI | 299 | 1 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey Work | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 29 Apr 2022 |  | DEV. Club House | Cancelled | Dushant Gore | 17 Sep 2022
GANGA ASMI | 299 | 1 | 25 Apr 2022 | SP ENGINEERS AND LAND SURVEYORS | Survey Work | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 29 Apr 2022 |  | DEV. Club House | Cancelled | Dushant Gore | 17 Sep 2022
GANGA ASMI | 300 | 2 | 28 Apr 2022 | MEGAPOWER SOLUTION PVT LTD | GH AMC for 150 KVA DG Set | AMC Charges | No. | 1 | 10500 | 10500 | 1890 | 12390 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 28 Apr 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 300 | 1 | 28 Apr 2022 | MEGAPOWER SOLUTION PVT LTD | GH 180 KVA DG AMC Charges - 1 No. - 1 No. | AMC Charges | Month | 12 | 875 | 10500 | 1890 | 12390 | 0 | 11 | 9624.96 | 1732.5 | 11357.46 | 1 | 1032.54 | 1. Non Comprehensive Annual Maintenance Charges for DG Set- 180 KVA. 2. Period- MAY-2023 to APR-2024 | 91.6667 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 28 Apr 2022 |  | Admin. Indirect Expenses | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 300 | 0 | 28 Apr 2022 | MEGAPOWER SOLUTION PVT LTD | GH AMC for 150 KVA DG Set | AMC Charges | No. | 1 | 10500 | 10500 | 1890 | 12390 | 0 | 1 | 10500 | 1890.08 | 12390.08 | 0 | -0.08 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 28 Apr 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 301 | 0 | 04 May 2022 | PLANEDGE CONSULTANTS PVT LTD | Project Management Consultancy | Project Management Consultancy | Sq.Ft | 825000 | 30 | 24750000 | 4455000 | 29205000 | 0 | 59799.935 | 1793998.05 | 322919.62 | 2116917.67 | 765200.065 | 27088082.33 |  | 7.2485 |  | Dushant Gore | Swapnil Erande | consultancy | 23 May 2022 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Cancelled | skmishra | 30 May 2022
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Cancelled | skmishra | 30 May 2022
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Cancelled | skmishra | 30 May 2022
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Cancelled | skmishra | 30 May 2022
GANGA ASMI | 302 | 1 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 18 May 2022 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 1 | 30000 | 0 | 30000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 302 | 1 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 18 May 2022 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 30000 | 30000 | 0 | 30000 | 0 | 1 | 30000 | 0 | 30000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 302 | 1 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 18 May 2022 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Cancelled | skmishra | 30 May 2022
GANGA ASMI | 302 | 1 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 18 May 2022 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Cancelled | skmishra | 30 May 2022
GANGA ASMI | 302 | 1 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 18 May 2022 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 302 | 0 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 18 May 2022 |  | S OH Expenses | Cancelled | skmishra | 30 May 2022
GANGA ASMI | 302 | 1 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 18 May 2022 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 302 | 1 | 06 May 2022 | KRISHNA KUMAR | GH Site Expenses | Site Expenses -SO | Month | 1 | 50000 | 50000 | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore |  | construction open | 18 May 2022 |  | S OH Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 303 | 0 | 11 May 2022 | HASHTAG STUDIOS | 3D Views & Walkthrough Consultancy | Revision Cut Section & Floor Plan | Lumsum | 1 | 88000 | 88000 | 15840 | 103840 | 0 | 1 | 88000 | 15840 | 103840 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 10 Oct 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 303 | 0 | 11 May 2022 | HASHTAG STUDIOS | 3D Views & Walkthrough Consultancy | Walkthrough | No. | 4 | 150000 | 600000 | 108000 | 708000 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 10 Oct 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 303 | 0 | 11 May 2022 | HASHTAG STUDIOS | 3D Views & Walkthrough Consultancy | Floor Plan | No. | 2 | 20000 | 40000 | 7200 | 47200 | 0 | 2 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 10 Oct 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 303 | 0 | 11 May 2022 | HASHTAG STUDIOS | 3D Views & Walkthrough Consultancy | Interior Views | No. | 6 | 20000 | 120000 | 21600 | 141600 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 10 Oct 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 303 | 0 | 11 May 2022 | HASHTAG STUDIOS | 3D Views & Walkthrough Consultancy | Cut Section | No. | 4 | 18000 | 72000 | 12960 | 84960 | 0 | 4 | 72000 | 12960 | 84960 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 10 Oct 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 303 | 0 | 11 May 2022 | HASHTAG STUDIOS | 3D Views & Walkthrough Consultancy | Cut Section & Floor Plan | No. | 4 | 16000 | 64000 | 11520 | 75520 | 0 | 4 | 64000 | 11520 | 75520 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 10 Oct 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 303 | 0 | 11 May 2022 | HASHTAG STUDIOS | 3D Views & Walkthrough Consultancy | Aminity Views | No. | 6 | 20000 | 120000 | 21600 | 141600 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 10 Oct 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 303 | 0 | 11 May 2022 | HASHTAG STUDIOS | 3D Views & Walkthrough Consultancy | Exterior Views | No. | 15 | 20000 | 300000 | 54000 | 354000 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 10 Oct 2022 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Channel (M+L). | Kgs | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 May 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 13 May 2022
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | laser cutting panel | Sq.Ft | 0 | 244 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 May 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 16 May 2022
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Fabrication work (L) | Sq.Ft | 1294 | 66 | 85404 | 15372.72 | 100776.72 | 2.5 | 1294 | 85404 | 15372.72 | 100776.72 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 May 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Angle (M+L) | Kgs | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 May 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 13 May 2022
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Fabrication Work | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 May 2022 |  | B.C. Rework/Extrawork | Cancelled | ADITYA CHOUGULE | 16 May 2022
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Removing work.-SOS | No. | 0 | 220000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 May 2022 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 16 May 2022
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (L) | Sq.Ft | 1609.9 | 53 | 85324.7 | 15358.44 | 100683.14 | 2.5 | 1609.8868 | 85324 | 15358.32 | 100682.32 | 0.0132 | 0.82 |  | 99.9992 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 May 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Removing work.-SOS | No. | 1 | 220000 | 220000 | 39600 | 259600 | 0 | 1 | 220000 | 39600 | 259600 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 May 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Angle (M+L) | Kgs | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 May 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 16 May 2022
GANGA ASMI | 304 | 1 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (L) | Sq.Ft | 0 | 53 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 16 May 2022 |  | No category | Cancelled | DUSHANT GORE | 10 May 2023
GANGA ASMI | 304 | 1 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (M+L) - Sq.Ft | Sq.Ft | 135 | 550 | 74250 | 13365 | 87615 | 2.5 | 135 | 74250 | 13365 | 87615 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 16 May 2022 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 304 | 1 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Transportaion | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 16 May 2022 |  | B.C. Rework/Extrawork | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 304 | 1 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (L) | Sq.Ft | 0 | 97.6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 16 May 2022 |  | No category | Cancelled | DUSHANT GORE | 10 May 2023
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Channel. (L) | Kgs | 444.18 | 38 | 16878.84 | 3038.2 | 19917.04 | 2.5 | 444.18 | 16878.84 | 3038.2 | 19917.04 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 May 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | laser cutting panel | Sq.Ft | 0 | 485 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 May 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 16 May 2022
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Channel (M+L). | Kgs | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 16 May 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 16 May 2022
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Angle. (L) | Kgs | 231.12 | 38 | 8782.56 | 1580.86 | 10363.42 | 2.5 | 231.12 | 8782.56 | 1580.86 | 10363.42 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 May 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 304 | 0 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (L) | Sq.Ft | 210 | 97.6 | 20496 | 3689.28 | 24185.28 | 2.5 | 203.4221 | 19854 | 3508.02 | 23362.02 | 6.5779 | 823.26 |  | 96.8677 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 May 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 304 | 1 | 13 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (M+L) - Sq.Ft | Sq.Ft | 135 | 264 | 35640 | 6415.2 | 42055.2 | 2.5 | 135 | 35640 | 6415.2 | 42055.2 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 16 May 2022 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 305 | 1 | 17 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (M) | Sq.Ft | 0 | 432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT GORE | 10 May 2023
GANGA ASMI | 305 | 0 | 17 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (M) | Sq.Ft | 1609.9 | 432 | 695476.8 | 125185.82 | 820662.62 | 0 | 1609.8981 | 695475.98 | 125185.68 | 820661.66 | 0.0019 | 0.96 |  | 99.9999 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 305 | 0 | 17 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Fabrication work (M) | Sq.Ft | 1294 | 99 | 128106 | 23059.08 | 151165.08 | 0 | 1294 | 128106 | 23059.08 | 151165.08 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 305 | 0 | 17 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Fabrication work (M) | Sq.Ft | 0 | 99 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 17 May 2022
GANGA ASMI | 305 | 0 | 17 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Channel. (M) | Kgs | 444.18 | 57 | 25318.26 | 4557.28 | 29875.54 | 0 | 444.18 | 25318.26 | 4557.28 | 29875.54 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 305 | 0 | 17 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (M) | Sq.Ft | 210 | 146.4 | 30744 | 5533.92 | 36277.92 | 0 | 203.429 | 29782.01 | 5360.76 | 35142.77 | 6.571 | 1135.15 |  | 96.871 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 305 | 0 | 17 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Angle. (M) | Kgs | 231.12 | 57 | 13173.84 | 2371.3 | 15545.14 | 0 | 231.12 | 13173.84 | 2371.3 | 15545.14 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 305 | 1 | 17 May 2022 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Laser Cutting Panel (M) | Sq.Ft | 0 | 146.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT GORE | 10 May 2023
GANGA ASMI | 306 | 0 | 26 May 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | CP Lounge A.C. Servicing | Servicing of A.C. | No. | 2 | 1250 | 2500 | 450 | 2950 | 2.5 | 2 | 2500 | 450 | 2950 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 306 | 0 | 26 May 2022 | NEPTUNE ENGINEERS PRIVATE LIMITED | CP Lounge A.C. Servicing | Gas Charging. | Kgs | 1.4 | 1100 | 1540 | 277.2 | 1817.2 | 2.5 | 1.4 | 1540 | 277.2 | 1817.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 307 | 0 | 26 May 2022 | AKSHAY WATER SUPPLIERS | Water Tanker supply | Water Tanker | Trips | 5 | 2200 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | UTI. Water Supply | Approved | DUSHANT GORE | 11 May 2023
GANGA ASMI | 307 | 0 | 26 May 2022 | AKSHAY WATER SUPPLIERS | Water Tanker supply | Water Tanker | Trips | 50 | 750 | 37500 | 0 | 37500 | 0 | 32 | 24000 | 0 | 24000 | 18 | 13500 |  | 64 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | UTI. Water Supply | Approved | DUSHANT GORE | 11 May 2023
GANGA ASMI | 307 | 1 | 26 May 2022 | AKSHAY WATER SUPPLIERS | Water Tanker supply | Drinking Water supply-UWR | Trips | 10 | 2200 | 22000 | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 08 Jun 2022 |  | UTI. Water Supply | Approved | DUSHANT GORE | 11 May 2023
GANGA ASMI | 307 | 1 | 26 May 2022 | AKSHAY WATER SUPPLIERS | Water Tanker supply | Water Tanker | Trips | 50 | 750 | 37500 | 0 | 37500 | 0 | 0 | 0 | 0 | 0 | 50 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 08 Jun 2022 |  | UTI. Water Supply | Approved | DUSHANT GORE | 11 May 2023
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 13 | 150 | 1950 | 351 | 2301 | 2.5 | 13 | 1950 | 351 | 2301 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 56 | 50 | 2800 | 504 | 3304 | 2.5 | 56 | 2800 | 504 | 3304 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 3 | 285 | 855 | 153.9 | 1008.9 | 2.5 | 3 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 6 | 150 | 900 | 162 | 1062 | 2.5 | 6 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 78 | 15 | 1170 | 210.6 | 1380.6 | 2.5 | 78 | 1170 | 210.6 | 1380.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 192 | 50 | 9600 | 1728 | 11328 | 2.5 | 192 | 9600 | 1728 | 11328 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 90 | 15 | 1350 | 243 | 1593 | 2.5 | 90 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 32 | 150 | 4800 | 864 | 5664 | 2.5 | 32 | 4800 | 864 | 5664 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 6 | 150 | 900 | 162 | 1062 | 2.5 | 6 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA CHOUGULE | 27 May 2022
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | CAT 6 Cable- | R.Ft | 50 | 13 | 650 | 117 | 767 | 2.5 | 50 | 650 | 117 | 767 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 83 | 50 | 4150 | 747 | 4897 | 2.5 | 83 | 4150 | 747 | 4897 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 25 | 15 | 375 | 67.5 | 442.5 | 2.5 | 25 | 375 | 67.5 | 442.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 0.75 sqmm LED | R.Ft | 416 | 12 | 4992 | 898.56 | 5890.56 | 2.5 | 416 | 4992 | 898.56 | 5890.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 78 | 15 | 1170 | 210.6 | 1380.6 | 2.5 | 78 | 1170 | 210.6 | 1380.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Fixing | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 90 | 15 | 1350 | 243 | 1593 | 2.5 | 90 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | AC Point BC | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 1 | 425 | 76.5 | 501.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Testing & Driver Fixing | No. | 12 | 100 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 37 | 15 | 555 | 99.9 | 654.9 | 2.5 | 37 | 555 | 99.9 | 654.9 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 3 | 285 | 855 | 153.9 | 1008.9 | 2.5 | 3 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 16 AMP Plug Point - Mkt | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 1 | 425 | 76.5 | 501.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 14 | 15 | 210 | 37.8 | 247.8 | 2.5 | 14 | 210 | 37.8 | 247.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 39 | 50 | 1950 | 351 | 2301 | 2.5 | 39 | 1950 | 351 | 2301 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | AC Point BC | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 1 | 425 | 76.5 | 501.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 90 | 15 | 1350 | 243 | 1593 | 2.5 | 90 | 1350 | 243 | 1593 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 44 | 15 | 660 | 118.8 | 778.8 | 2.5 | 44 | 660 | 118.8 | 778.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 35 | 25 | 875 | 157.5 | 1032.5 | 2.5 | 35 | 875 | 157.5 | 1032.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 1 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 14 | 150 | 2100 | 378 | 2478 | 2.5 | 14 | 2100 | 378 | 2478 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 10 | 15 | 150 | 27 | 177 | 2.5 | 10 | 150 | 27 | 177 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 39 | 50 | 1950 | 351 | 2301 | 2.5 | 39 | 1950 | 351 | 2301 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 4 Sqmm Cable (L) | R.Ft | 12 | 25 | 300 | 54 | 354 | 2.5 | 12 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 1 | 150 | 150 | 27 | 177 | 2.5 | 1 | 150 | 27 | 177 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 180 | 15 | 2700 | 486 | 3186 | 2.5 | 180 | 2700 | 486 | 3186 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 45 | 20 | 900 | 162 | 1062 | 2.5 | 45 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 6 | 150 | 900 | 162 | 1062 | 2.5 | 6 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 32 | 100 | 3200 | 576 | 3776 | 2.5 | 32 | 3200 | 576 | 3776 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 1 | 285 | 285 | 51.3 | 336.3 | 2.5 | 1 | 285 | 51.3 | 336.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 33 | 20 | 660 | 118.8 | 778.8 | 2.5 | 33 | 660 | 118.8 | 778.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 4 Sqmm Cable (L) | R.Ft | 12 | 25 | 300 | 54 | 354 | 2.5 | 12 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Socket Fixing | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 4 | 350 | 1400 | 252 | 1652 | 2.5 | 4 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 16 | 210 | 3360 | 604.8 | 3964.8 | 2.5 | 16 | 3360 | 604.8 | 3964.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 24 | 285 | 6840 | 1231.2 | 8071.2 | 2.5 | 24 | 6840 | 1231.2 | 8071.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 45 | 20 | 900 | 162 | 1062 | 2.5 | 45 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 24 | 285 | 6840 | 1231.2 | 8071.2 | 2.5 | 24 | 6840 | 1231.2 | 8071.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 33 | 20 | 660 | 118.8 | 778.8 | 2.5 | 33 | 660 | 118.8 | 778.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 0.75 sqmm LED | R.Ft | 480 | 12 | 5760 | 1036.8 | 6796.8 | 2.5 | 480 | 5760 | 1036.8 | 6796.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 33 | 20 | 660 | 118.8 | 778.8 | 2.5 | 33 | 660 | 118.8 | 778.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 2.5 Sqmm Cable (L) | R.Ft | 20 | 20 | 400 | 72 | 472 | 2.5 | 20 | 400 | 72 | 472 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Fan Point | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 1 | 350 | 63 | 413 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 3 | 150 | 450 | 81 | 531 | 2.5 | 3 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 14 | 15 | 210 | 37.8 | 247.8 | 2.5 | 14 | 210 | 37.8 | 247.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 10 | 150 | 1500 | 270 | 1770 | 2.5 | 10 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 2 | 150 | 300 | 54 | 354 | 2.5 | 2 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 25 | 25 | 625 | 112.5 | 737.5 | 2.5 | 25 | 625 | 112.5 | 737.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA CHOUGULE | 03 Jun 2022
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 56 | 50 | 2800 | 504 | 3304 | 2.5 | 56 | 2800 | 504 | 3304 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 4 | 285 | 1140 | 205.2 | 1345.2 | 2.5 | 4 | 1140 | 205.2 | 1345.2 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 35 | 25 | 875 | 157.5 | 1032.5 | 2.5 | 35 | 875 | 157.5 | 1032.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 25 | 25 | 625 | 112.5 | 737.5 | 2.5 | 25 | 625 | 112.5 | 737.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Strip Fixing | R.Ft | 192 | 50 | 9600 | 1728 | 11328 | 2.5 | 182 | 9100 | 1638 | 10738 | 10 | 590 |  | 94.7917 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Two way Point - Mkt | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Curtain Point | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Curtain Point | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 2 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 3 | 350 | 1050 | 189 | 1239 | 2.5 | 3 | 1050 | 189 | 1239 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | AC Point BC | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 1 | 425 | 76.5 | 501.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 10 | 15 | 150 | 27 | 177 | 2.5 | 10 | 150 | 27 | 177 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 1 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 6 | 150 | 900 | 162 | 1062 | 2.5 | 6 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 13 Amp Plug Point | No. | 1 | 250 | 250 | 45 | 295 | 2.5 | 1 | 250 | 45 | 295 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 3 | 150 | 450 | 81 | 531 | 2.5 | 3 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 47 | 150 | 7050 | 1269 | 8319 | 2.5 | 47 | 7050 | 1269 | 8319 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Smoke Detector | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 1 | 300 | 54 | 354 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Secondary Light Point | No. | 32 | 150 | 4800 | 864 | 5664 | 2.5 | 32 | 4800 | 864 | 5664 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Inst. of Primary Light Point | No. | 3 | 285 | 855 | 153.9 | 1008.9 | 2.5 | 3 | 855 | 153.9 | 1008.9 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 32 | 100 | 3200 | 576 | 3776 | 2.5 | 32 | 3200 | 576 | 3776 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 17 | 100 | 1700 | 306 | 2006 | 2.5 | 17 | 1700 | 306 | 2006 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 49 | 100 | 4900 | 882 | 5782 | 2.5 | 49 | 4900 | 882 | 5782 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 14 | 100 | 1400 | 252 | 1652 | 2.5 | 14 | 1400 | 252 | 1652 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | Light Fitting Fixing | No. | 20 | 100 | 2000 | 360 | 2360 | 2.5 | 20 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 6 | 285 | 1710 | 307.8 | 2017.8 | 2.5 | 6 | 1710 | 307.8 | 2017.8 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | LED Point (L) | No. | 2 | 285 | 570 | 102.6 | 672.6 | 2.5 | 2 | 570 | 102.6 | 672.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | 1.5 Sqmm Cable (L) | R.Ft | 25 | 15 | 375 | 67.5 | 442.5 | 2.5 | 25 | 375 | 67.5 | 442.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 308 | 0 | 27 May 2022 | VAISHALI ELECTRICAL | Goel House Electrical Work | AC Point BC | No. | 1 | 425 | 425 | 76.5 | 501.5 | 2.5 | 1 | 425 | 76.5 | 501.5 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 309 | 0 | 30 May 2022 | TECHNOVISION ENERGY PVT.LTD. | Goel House (L) AMC for 125 KVA Stabilizer | AMC Charges | Month | 12 | 1187.5 | 14250 | 2565 | 16815 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | Sanket Patil |  | Construction | 30 May 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 310 | 0 | 30 May 2022 | SIDDHESH COMMUNICATIONS | BRANDING Event Expenses | Advertorial / Write Up / Articales | No. | 1 | 900000 | 900000 | 45000 | 945000 | 0 | 1 | 900000 | 45000 | 945000 | 0 | 0 | sakal maha brands - brand of maharashtra 2022 ( event, spl. suppliement one full page on maha brand feature, 22 min. episode on saam tv, micerosite hosted on www.esakal.om, coffee table book, additional - cricket league, talent hunt, fashion show etc) | 100 |  | Tejas Raverkar | TEJAS RAVERKAR | construction open | 30 Aug 2022 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 311 | 0 | 31 May 2022 | CHAITANYA TECHNICS | Wing 1 - RCC Retaining wall Rebaring work | Rebarring work 16mm dia- BC | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 31 May 2022 |  | B.C. RCC Substructure | Cancelled | Dushant Gore | 31 May 2022
GANGA ASMI | 311 | 0 | 31 May 2022 | CHAITANYA TECHNICS | Wing 1 - RCC Retaining wall Rebaring work | Rebarring work 8mm dia- BC | No. | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 31 May 2022 |  | B.C. RCC Substructure | Cancelled | Dushant Gore | 31 May 2022
GANGA ASMI | 311 | 0 | 31 May 2022 | CHAITANYA TECHNICS | Wing 1 - RCC Retaining wall Rebaring work | Rebaring work 20mm- cc | No. | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 31 May 2022 |  | B.C. Customer Changes | Cancelled | Dushant Gore | 31 May 2022
GANGA ASMI | 311 | 0 | 31 May 2022 | CHAITANYA TECHNICS | Wing 1 - RCC Retaining wall Rebaring work | Rebarring work 12mm dia- BC | No. | 0 | 120 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 31 May 2022 |  | B.C. RCC Substructure | Cancelled | Dushant Gore | 31 May 2022
GANGA ASMI | 312 | 4 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Revised Ramp & plinth Beam Rebaring | Rebaring work 12mm- cc | No. | 85 | 230 | 19550 | 3519 | 23069 | 0 | 63.0003 | 14490.07 | 2608.22 | 17098.29 | 21.9997 | 5970.71 |  | 74.118 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 0 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - RCC Retaining wall Rebaring work | Rebaring work 20mm- cc | No. | 20 | 800 | 16000 | 2880 | 18880 | 0 | 20 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 5 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | Rebaring work 8mm dia.- DTR | No. | 73 | 150 | 10950 | 1971 | 12921 | 2.5 | 73 | 10950 | 1971 | 12921 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Jun 2022 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 5 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | Rebaring work 20mm- cc | No. | 2 | 940 | 1880 | 338.4 | 2218.4 | 2.5 | 2 | 1880 | 338.4 | 2218.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 4 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Revised Ramp & plinth Beam Rebaring | Rebaring work 20mm- cc | No. | 0 | 800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Cancelled | ADITYA CHOUGULE | 25 Feb 2023
GANGA ASMI | 312 | 4 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Revised Ramp & plinth Beam Rebaring | Rebaring work 16mm- cc | No. | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Cancelled | ADITYA CHOUGULE | 25 Feb 2023
GANGA ASMI | 312 | 5 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | Rebaring work 16mm dia.- DTR | No. | 21 | 500 | 10500 | 1890 | 12390 | 2.5 | 21 | 10500 | 1890 | 12390 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Jun 2022 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 1 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - RCC Retaining wall Rebaring work | Rebarring work 16mm dia- BC | No. | 55 | 350 | 19250 | 3465 | 22715 | 0 | 55 | 19250 | 3465 | 22715 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 0 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - RCC Retaining wall Rebaring work | Rebarring work 12mm dia- BC | No. | 470 | 120 | 56400 | 10152 | 66552 | 0 | 470 | 56400 | 10152 | 66552 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 3 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - RCC Retaining wall Rebaring work | Rebarring Work 12mm dia.(Rate Diff) | No. | 470 | 20 | 9400 | 1692 | 11092 | 0 | 470 | 9400 | 1692 | 11092 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 08 Jun 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 0 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - RCC Retaining wall Rebaring work | Rebarring work 16mm dia- BC | No. | 85 | 350 | 29750 | 5355 | 35105 | 0 | 85 | 29750 | 5355 | 35105 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 3 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - RCC Retaining wall Rebaring work | Rebarring Work 8mm dia.(Rate Diff) | No. | 520 | 20 | 10400 | 1872 | 12272 | 0 | 347.0012 | 6940.02 | 1249.2 | 8189.22 | 172.9988 | 4082.78 |  | 66.731 |  | DUSHANT GORE | Swapnil Erande | construction open | 08 Jun 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 4 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Revised Ramp & plinth Beam Rebaring | Rebaring work 16mm- cc | No. | 30 | 450 | 13500 | 2430 | 15930 | 0 | 30 | 13500 | 2430 | 15930 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 5 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | Rebarring work 10mm dia- BC | No. | 1 | 200 | 200 | 36 | 236 | 2.5 | 1 | 200 | 36 | 236 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 0 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - RCC Retaining wall Rebaring work | Rebarring work 8mm dia- BC | No. | 520 | 120 | 62400 | 11232 | 73632 | 0 | 520 | 62400 | 11232 | 73632 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 4 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Revised Ramp & plinth Beam Rebaring | Rebaring work 20mm- cc | No. | 9 | 850 | 7650 | 1377 | 9027 | 0 | 9 | 7650 | 1377 | 9027 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 4 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Revised Ramp & plinth Beam Rebaring | Rebaring work 12mm- cc | No. | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Cancelled | ADITYA CHOUGULE | 25 Feb 2023
GANGA ASMI | 312 | 5 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Rebaring Work Wing 1 - 4th,5th,6th Slab Rebaring Work | Rebaring work 12mm- cc | No. | 11 | 260 | 2860 | 514.8 | 3374.8 | 2.5 | 11 | 2860 | 514.8 | 3374.8 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 4 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 Revised Ramp & plinth Beam Rebaring | Rebaring work 12mm- cc | No. | 0 | 140 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 08 Jun 2022 |  | B.C. Customer Changes | Cancelled | ADITYA CHOUGULE | 24 Feb 2023
GANGA ASMI | 312 | 2 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - Rebarring work Grade slab, Ramp & Plinth beam side | Rebarring work 12mm dia- BC | No. | 90 | 120 | 10800 | 1944 | 12744 | 0 | 90 | 10800 | 1944 | 12744 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 312 | 2 | 31 May 2022 | AVCON TECHNICS PVT LTD | Wing 1 - Rebarring work Grade slab, Ramp & Plinth beam side | Rebarring work 10mm dia- BC | No. | 230 | 120 | 27600 | 4968 | 32568 | 0 | 229.9044 | 27588.53 | 4965.92 | 32554.45 | 0.0956 | 13.55 |  | 99.9584 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 08 Jun 2022 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 313 | 0 | 01 Jun 2022 | SHRUSTI FLORALS | A9/B1 Garden maintenance | Garden Maintenance | Month | 1 | 7500 | 7500 | 0 | 7500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Un-Approved |  | 1900-01-01
GANGA ASMI | 314 | 0 | 03 Jun 2022 | AYAZ RAFIK SHAIKH | Liasoning Consultancy Professional fees for liaisoning | Liasoning Consultancy (Architectural) | Sq.Ft | 1482655.318 | 3 | 4447965.95 | 0 | 4447965.95 | 0 | 312098 | 936294 | 0 | 936294 | 1170557.318 | 3511671.95 |  | 21.0499 |  | Dushant Gore | chetan.jewalikar | consultancy | 25 Jun 2022 |  | Consultacy Architectural | Approved | chetan.jewalikar | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | UTI. Garbage Chute | Cancelled | ADITYA CHOUGULE | 06 Jun 2022
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 1 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 2 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Garbage Collection UGC | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Garbage Chute | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 315 | 0 | 06 Jun 2022 | VIKAS GARADE | Site Infra Misc Work | Maintanance Work - SMS | Month | 1 | 1000 | 1000 | 0 | 1000 | 0 | 1 | 1000 | 0 | 1000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 316 | 0 | 06 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Angle. (L) | Kgs | 726.74 | 18 | 13081.32 | 2354.64 | 15435.96 | 2.5 | 0 | 0 | 0 | 0 | 726.74 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 316 | 0 | 06 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Angle. (L) | Kgs | 93.08 | 18 | 1675.44 | 301.58 | 1977.02 | 2.5 | 0 | 0 | 0 | 0 | 93.08 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 316 | 0 | 06 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Angle. (L) | Kgs | 272.37 | 18 | 4902.66 | 882.48 | 5785.14 | 2.5 | 0 | 0 | 0 | 0 | 272.37 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 316 | 0 | 06 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Square Pipe (L) | Kgs | 233.896 | 18 | 4210.13 | 757.82 | 4967.95 | 2.5 | 105.9221 | 1906.6 | 343.18 | 2249.78 | 127.9739 | 2718.17 |  | 45.286 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 316 | 0 | 06 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Angle. (L) | Kgs | 451.08 | 18 | 8119.44 | 1461.5 | 9580.94 | 2.5 | 0 | 0 | 0 | 0 | 451.08 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 316 | 1 | 06 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Square pipe Rate Diff.(L) | Kgs | 233.896 | 10.85 | 2537.77 | 456.8 | 2994.57 | 2.5 | 105.9221 | 1149.25 | 206.86 | 1356.11 | 127.9739 | 1638.46 |  | 45.286 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 317 | 0 | 06 Jun 2022 | DREAMTREE EXPERIENCE | MEDIA Event Expenses | Event Expenses | No. | 1 | 19210 | 19210 | 0 | 19210 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | event expences - backdrop frame 8x8 sq ft, star flex, led parcans, t stands, cordless mics., jbl vrx + tops, batter les, + transport dtd. 04.06.2022- real rich event | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 318 | 0 | 07 Jun 2022 | SITARAM GANGADHAR AUTI | Garden Work | Misc. Garden work | No. | 1 | 21700 | 21700 | 0 | 21700 | 0 | 0.4465 | 9689.05 | 0 | 9689.05 | 0.5535 | 12010.95 |  | 44.65 |  | Dushant Gore | Swapnil Erande | construction open | 07 Jun 2022 |  | S OH Repair & Maintenance | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 318 | 0 | 07 Jun 2022 | SITARAM GANGADHAR AUTI | Garden Work | Misc. Garden work | No. | 0 | 21700 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 07 Jun 2022 |  | S OH Repair & Maintenance | Cancelled | Dushant Gore | 07 Jun 2022
GANGA ASMI | 319 | 0 | 07 Jun 2022 | AMAN ENTERPRISES | Wing-1 Substructure Murum Compaction work | Vibro Roller. | Month | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Jun 2022 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 07 Jun 2022
GANGA ASMI | 319 | 2 | 07 Jun 2022 | AMAN ENTERPRISES | Hiring of Machinery for Plinth Preparation (Wing 2) | Vibro Roller | Day | 60 | 2500 | 150000 | 0 | 150000 | 0 | 14.8401 | 37100.25 | 0 | 37100.25 | 45.1599 | 112899.75 |  | 24.7335 |  | Dushant Gore | Swapnil Erande | construction open | 07 Jun 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 319 | 0 | 07 Jun 2022 | AMAN ENTERPRISES | Wing-1 Substructure Murum Compaction work | Vibro Roller. | Month | 2 | 55000 | 110000 | 0 | 110000 | 0 | 2 | 110000 | 0 | 110000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 07 Jun 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Dushant Gore | 07 Nov 2022
GANGA ASMI | 319 | 1 | 07 Jun 2022 | AMAN ENTERPRISES | Substructure Murum Compaction Work Wing 1 & Wing 2 Partial | Vibro Roller. | Month | 3 | 55000 | 165000 | 0 | 165000 | 0 | 2.4132 | 132726 | 0 | 132726 | 0.5868 | 32274 |  | 80.44 |  | Dushant Gore | Swapnil Erande | construction open | 07 Jun 2022 |  | 01 EARTHWORK & ROADWORK | Approved | Dushant Gore | 07 Nov 2022
GANGA ASMI | 319 | 0 | 07 Jun 2022 | AMAN ENTERPRISES | Wing-1 Substructure Murum Compaction work | Vibro Roller. | Month | 0 | 55000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 07 Jun 2022 |  | 01 EARTHWORK & ROADWORK | Cancelled | ADITYA CHOUGULE | 07 Jun 2022
GANGA ASMI | 320 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Square Pipe (M) | Kgs | 233.896 | 68 | 15904.93 | 2862.88 | 18767.81 | 0 | 0 | 0 | 0 | 0 | 233.896 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 320 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Angle. (M) | Kgs | 93.08 | 60 | 5584.8 | 1005.26 | 6590.06 | 0 | 0 | 0 | 0 | 0 | 93.08 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 320 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Angle. (M) | Kgs | 726.74 | 60 | 43604.4 | 7848.8 | 51453.2 | 0 | 0 | 0 | 0 | 0 | 726.74 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 320 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Site Infra Fabrication Work | MS Angle. (M) | Kgs | 272.37 | 60 | 16342.2 | 2941.6 | 19283.8 | 0 | 0 | 0 | 0 | 0 | 272.37 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 321 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 42.35 | 54 | 2286.9 | 411.64 | 2698.54 | 0 | 37.5191 | 2026.03 | 364.68 | 2390.71 | 4.8309 | 307.83 |  | 88.5929 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 321 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Steel Cutting work | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | 02 RCC WORK | Cancelled | Dushant Gore | 08 Jun 2022
GANGA ASMI | 321 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Misc Work - AIE | No. | 3 | 300 | 900 | 162 | 1062 | 0 | 3 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 321 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Top Bearing Of Gate | No. | 2 | 80 | 160 | 28.8 | 188.8 | 0 | 2 | 160 | 28.8 | 188.8 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 321 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 37.38 | 54 | 2018.52 | 363.34 | 2381.86 | 0 | 37.38 | 2018.52 | 363.34 | 2381.86 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 321 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (M) | Kgs | 41.25 | 64 | 2640 | 475.2 | 3115.2 | 0 | 25.4232 | 1627.08 | 292.88 | 1919.96 | 15.8268 | 1195.24 |  | 61.632 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 322 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 37.38 | 18 | 672.84 | 121.12 | 793.96 | 2.5 | 37.38 | 672.84 | 121.12 | 793.96 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Jun 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 322 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | GI Sheet Fixing (L) | Sq.Ft | 404.54 | 5 | 2022.7 | 364.08 | 2386.78 | 2.5 | 404.54 | 2022.7 | 364.08 | 2386.78 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 24 Jun 2022 |  | UTI. Vermiculture | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 322 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 41.25 | 18 | 742.5 | 133.66 | 876.16 | 2.5 | 25.4232 | 457.62 | 82.38 | 540 | 15.8268 | 336.16 |  | 61.632 |  | Dushant Gore | Swapnil Erande | construction open | 24 Jun 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 322 | 0 | 07 Jun 2022 | SHRUSHTI GLASS & ALUMINIUM | Steel Cutting Yard Fabrication work | Fabrication work (L) | Kgs | 42.35 | 18 | 762.3 | 137.22 | 899.52 | 2.5 | 37.5191 | 675.34 | 121.56 | 796.9 | 4.8309 | 102.62 |  | 88.5929 |  | Dushant Gore | Swapnil Erande | construction open | 24 Jun 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 323 | 0 | 08 Jun 2022 | SOCKS N SHOES MEDIA | MEDIA Event Expenses | Photoshoot | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | PHOTO / VIDEO SHOOT EVENT- REAL RICH DTD. 04TH JUNE 2022 FOR PROJECT BRANDING, MARKETING AND SALES PROMOTION | 0 |  | Tejas Raverkar |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 324 | 0 | 27 Jun 2022 | NAYANSRUSHTI ENVIROCARE PRIVATE LIMITED | Legal consultancy for CGWA | Legal Consultancy.- | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 05 Jul 2022 |  | Consultancy Legal | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 325 | 0 | 27 Jun 2022 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | Website Maintainence - | Month | 12 | 2000 | 24000 | 4320 | 28320 | 0 | 6 | 11999.99 | 2160 | 14159.99 | 6 | 14160.01 | WWW.REALRICH.IN WEB SITE DEVELOPMENT AND MAINTENANCE CHARGES MONTHLY RS. 2000/- + TAX.AS ON 01ST JULY 2022 TO TILL 31ST MARCH 2023 | 50 |  | Tejas Raverkar | sunita shirolkar | construction open | 28 Jun 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 325 | 1 | 27 Jun 2022 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | Web Marketing | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 1 | 40000 | 7200 | 47200 | 0 | 0 | WEB SITE DEVELOPMENT CHARGES ONE TIME CHARGES RS. 40000 + TAX. WWW.REALRICH.IN | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 28 Jun 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 326 | 0 | 28 Jun 2022 | AQUARIUS WATERPROOFING | Wing-2 Substructure Lift Pit Waterproofing(Vertical) | Membrane Vertical Waterproofing (M) | Sq.Ft | 11292 | 40 | 451680 | 81302.4 | 532982.4 | 0 | 10614.1398 | 424565.59 | 76421.8 | 500987.39 | 677.8602 | 31995.01 |  | 93.997 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Jul 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 326 | 0 | 28 Jun 2022 | AQUARIUS WATERPROOFING | Wing-2 Substructure Lift Pit Waterproofing(Horizontal) | Membrane Horizontal Waterproofing (M) | Sq.Ft | 4238 | 34 | 144092 | 25936.56 | 170028.56 | 0 | 786.0219 | 26724.74 | 4810.46 | 31535.2 | 3451.9781 | 138493.36 |  | 18.547 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Jul 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 327 | 0 | 28 Jun 2022 | AQUARIUS WATERPROOFING | Wing-2 Substructure Lift Pit Waterproofing(Vertical) | Membrane Vertical Waterproofing (L) | Sq.Ft | 11292 | 15 | 169380 | 30488.4 | 199868.4 | 10 | 10614.1398 | 159212.1 | 28658.18 | 187870.28 | 677.8602 | 11998.12 | 1.B-C11 to B-C72 side vertical portion at raft. 2.B-C11 to B-C72 side horizontal portion at raft. 3.BC48,BC49,BC51,BC52,LW1,2,3,4,5,6 side vertical portion at shear wall. 4.BC58,BC59,BC42,BC43,LW7,8,9,10,11,12 side vertical portion at shear wall. | 93.997 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Jul 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 327 | 0 | 28 Jun 2022 | AQUARIUS WATERPROOFING | Wing-2 Substructure Lift Pit Waterproofing(Horizontal) | Membrane Horizontal Waterproofing (L) | Sq.Ft | 4238 | 13 | 55094 | 9916.92 | 65010.92 | 10 | 786.0219 | 10218.28 | 1839.3 | 12057.58 | 3451.9781 | 52953.34 | 1.B-C11 to B-C72 side horizontal area at PCC. 2.B-C7 to B-C64 side horizontal area at PCC. | 18.547 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 04 Jul 2022 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 328 | 0 | 28 Jun 2022 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Black Back Flex | Sq.Ft | 3420 | 10 | 34200 | 6156 | 40356 | 0 | 3420 | 34200 | 6156 | 40356 | 0 | 0 | NORMAL BLACK BACK FLEX PRINT WITH MOUNT FOR OUTDOOR HOARDING FLEX SIZE AS 30 X 42 SQ FT QTY. 02 AND SIZE AS 30 X 30 SQ FT QTY. 01 FOR GANGA ASMI WAKAD PROJECT HOARDING | 100 |  | Tejas Raverkar | sunita shirolkar | construction open | 05 Jul 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 329 | 0 | 30 Jun 2022 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 38000 | 228000 | 41040 | 269040 | 0 | 3.0012 | 114045.6 | 20528.2 | 134573.8 | 2.9988 | 134466.2 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES @ OPP. GANGA ASMI PROJECT FACING HINJEWADI SIZE AS 30 X 30 SQ FT. AS ON 18/06/2022 TO 17/12/2022 | 50.02 |  | Tejas Raverkar | sunita shirolkar | construction open | 22 Jul 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 22 | 170 | 3740 | 673.2 | 4413.2 | 2.5 | 15 | 2550 | 459 | 3009 | 7 | 1404.2 |  | 68.1818 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Substructure Rebar Coupling Base to P1 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.32mm Base to Tie Level- 22 Nos. 2.32mm Tie to P1 Level- 22 Nos. | 0 |  | ADITYA CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 04 Jul 2022
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P4 to P5 Level | Rebar Coupler- BC | No. | 24 | 100 | 2400 | 432 | 2832 | 2.5 | 0 | 0 | 0 | 0 | 24 | 0 | Wing-2 Rebar Coupler P4 to P5 level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 47 | 100 | 4700 | 846 | 5546 | 2.5 | 47 | 4700 | 846 | 5546 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P2 to P3 Level | Rebar Coupler- BC | No. | 12 | 170 | 2040 | 367.2 | 2407.2 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 | Wing-2 Rebar Coupler P2 to P3 level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 1 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 8 | 100 | 800 | 144 | 944 | 2.5 | 8 | 800 | 144 | 944 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P2 to P3 Level | Reducer Coupler | No. | 10 | 165 | 1650 | 297 | 1947 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 | Wing-2 Reducer Coupler P2 to P3 level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 9 | 100 | 900 | 162 | 1062 | 2.5 | 9 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P3 to P4 Level | Rebar Coupler- BC | No. | 12 | 170 | 2040 | 367.2 | 2407.2 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 | Wing-2 Rebar Coupler P3 to P4 level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 1 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling Tie to P1 Lvl. | Rebar Coupler- BC | No. | 122 | 100 | 12200 | 2196 | 14396 | 2.5 | 50 | 5000 | 900 | 5900 | 72 | 8496 |  | 40.9836 |  | Dushant Gore | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P4 to P5 Level | Reducer Coupler | No. | 12 | 165 | 1980 | 356.4 | 2336.4 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 | Wing-2 Reducer Coupler P4 to P5 level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | 02 RCC WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 05 Jul 2022
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P2 to P3 Level | Rebar Coupler- BC | No. | 35 | 100 | 3500 | 630 | 4130 | 2.5 | 0 | 0 | 0 | 0 | 35 | 0 | Wing-2 Rebar Coupler P2 to P3 level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P5to P6 Level | Rebar Coupler- BC | No. | 30 | 100 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 | Wing-2 Rebar Coupler P5 to P6 level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing -2 Parking Rebar Coupling Base to P1 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1.25mm Base to Tie Level- 560 Nos. 2.25mm Tie to P1 Level- 560 Nos. | 0 |  | ADITYA CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 04 Jul 2022
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Substructure Rebar Coupling Base to P1 Lvl. | Rebar Coupler- BC | No. | 94 | 100 | 9400 | 1692 | 11092 | 2.5 | 93.0003 | 9300.03 | 1674 | 10974.03 | 0.9997 | 117.97 | 1.25mm Base to Tie Level- 47 Nos. 2.25mm Tie to P1 Level- 47 Nos. | 98.9365 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 1 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling Base to Tie Lvl | Rebar Coupler- BC | No. | 122 | 100 | 12200 | 2196 | 14396 | 2.5 | 0 | 0 | 0 | 0 | 122 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 04 Jul 2022
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing -2 Parking Rebar Coupling Base to P1 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 01 Jul 2022
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Substructure Rebar Coupling Base to P1 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 01 Jul 2022
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Aditya Chougule |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 01 Jul 2022
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 1. Coupler for testing 32mm- 4 Nos. and 25mm- 9 Nos. | 0 |  | ADITYA CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Cancelled | ADITYA CHOUGULE | 04 Jul 2022
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing -2 Parking Rebar Coupling Base to P1 Lvl. | Rebar Coupler- BC | No. | 1120 | 100 | 112000 | 20160 | 132160 | 2.5 | 128.0003 | 12800.03 | 2304 | 15104.03 | 991.9997 | 117055.97 |  | 11.4286 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P6 to Podium Level | Rebar Coupler- BC | No. | 30 | 100 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 30 | 0 | Wing-2 Rebar Coupler P6 to Podium level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 2 | 30 Jun 2022 | POWER SPLICER | Wing 2 . Rebar Coupler P3 to P4 Level | Rebar Coupler- BC | No. | 33 | 100 | 3300 | 594 | 3894 | 2.5 | 0 | 0 | 0 | 0 | 33 | 0 | Wing-2 Rebar Coupler P3 to P4 level | 0 |  | ADITYA.CHOUGULE |  | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Substructure Rebar Coupling Base to P1 Lvl. | Rebar Coupler- BC | No. | 44 | 170 | 7480 | 1346.4 | 8826.4 | 2.5 | 44 | 7480 | 1346.4 | 8826.4 | 0 | 0 | 1.32mm Base to Tie Level- 22 Nos. 2.32mm Tie to P1 Level- 22 Nos. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 330 | 0 | 30 Jun 2022 | POWER SPLICER | Wing-2 Superstructure Rebar Coupling P1 to P2 Lvl. | Rebar Coupler- BC | No. | 4 | 170 | 680 | 122.4 | 802.4 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Jul 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 331 | 0 | 01 Jul 2022 | S.K. Fabrication | Site Infra Fabrication Work | Miscellaneous Expenses | No. | 1 | 4000 | 4000 | 0 | 4000 | 2.5 | 1 | 4000 | 0 | 4000 | 0 | 0 | 1. Partially material available on site rest material and labour should be supplied by contractor. 2. Structural work to be done with proper line level & Alignment. 3. Temporary support or frame if required then it is to be done by contractor. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Jul 2022 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 4403.272 | 24.4 | 107439.84 | 19339.18 | 126779.02 | 2.5 | 4403.272 | 107439.84 | 19339.18 | 126779.02 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 230 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Cancelled | Dushant Gore | 15 Nov 2022
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 0 | 23.56 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Cancelled | Dushant Gore | 15 Nov 2022
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 243 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 4403.272 | 6 | 26419.63 | 4755.54 | 31175.17 | 0 | 4403.272 | 26419.63 | 4755.54 | 31175.17 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 01 EARTHWORK & ROADWORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Parking plinth beam | RCC Beam | Sq.Ft | 8172.9352 | 55 | 449511.44 | 80912.06 | 530423.5 | 2.5 | 8172.9352 | 449511.44 | 80912.06 | 530423.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. BBM, Plaster, POP | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 243 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 190 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 260 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Cancelled | Dushant Gore | 15 Nov 2022
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 260 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Cancelled | Dushant Gore | 15 Nov 2022
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 190 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Cancelled | Dushant Gore | 15 Nov 2022
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Cancelled | Dushant Gore | 15 Nov 2022
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Parking Footing & Column | Footing & Column | Sq.Ft | 4403.272 | 65 | 286212.68 | 51518.28 | 337730.96 | 2.5 | 4403.272 | 286212.68 | 51518.28 | 337730.96 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Parking PCC Work | PCC | Sq.Ft | 4403.272 | 5 | 22016.36 | 3962.94 | 25979.3 | 2.5 | 4403.272 | 22016.36 | 3962.94 | 25979.3 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. Building Common Items | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 230 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Cancelled | Dushant Gore | 15 Nov 2022
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 332 | 0 | 08 Jul 2022 | OM CONSTRUCTION | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 19 Jul 2022 |  | 02 RCC WORK | Foreclose | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.1485 | 20919.64 | 3766.5 | 24686.14 | 0.8515 | 141544 |  | 14.85 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3767 | 53066.86 | 9552.6 | 62619.46 | 0.6233 | 103610.68 |  | 37.67 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3627 | 51094.64 | 9196.2 | 60290.84 | 0.6373 | 105939.3 |  | 36.27 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3772 | 53137.3 | 9565.2 | 62702.5 | 0.6228 | 103527.64 |  | 37.72 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.2945 | 41487.1 | 7467.66 | 48954.76 | 0.7055 | 117275.38 |  | 29.45 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 0 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.2989 | 42106.94 | 7579.08 | 49686.02 | 0.7011 | 116544.12 |  | 29.89 |  | Dushant Gore | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Dushant Gore | 08 Aug 2022
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.1485 | 20919.64 | 3766.5 | 24686.14 | 0.8515 | 141544 |  | 14.85 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 0 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3624 | 51052.38 | 9189.54 | 60241.92 | 0.6376 | 105988.22 |  | 36.24 |  | Dushant Gore | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Dushant Gore | 08 Aug 2022
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.1485 | 20919.64 | 3766.5 | 24686.14 | 0.8515 | 141544 |  | 14.85 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 0 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3132 | 44121.42 | 7941.06 | 52062.48 | 0.6868 | 114167.66 |  | 31.32 |  | Dushant Gore | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Dushant Gore | 08 Aug 2022
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3453 | 48643.45 | 8755.38 | 57398.83 | 0.6547 | 108831.31 |  | 34.53 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.2738 | 38571.03 | 6942.6 | 45513.63 | 0.7262 | 120716.51 |  | 27.38 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 0 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Dushant Gore | 08 Aug 2022
GANGA ASMI | 333 | 0 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3632 | 51165.07 | 9209.34 | 60374.41 | 0.6368 | 105855.73 |  | 36.32 |  | Dushant Gore | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Dushant Gore | 08 Aug 2022
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3363 | 47375.59 | 8528.22 | 55903.81 | 0.6637 | 110326.33 |  | 33.63 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.1485 | 20919.64 | 3766.5 | 24686.14 | 0.8515 | 141544 |  | 14.85 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.2929 | 41261.7 | 7428.24 | 48689.94 | 0.7071 | 117540.2 |  | 29.29 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3498 | 49277.38 | 8868.78 | 58146.16 | 0.6502 | 108083.98 |  | 34.98 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3079 | 43374.8 | 7807.14 | 51181.94 | 0.6921 | 115048.2 |  | 30.79 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 0 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.6614 | 93173.4 | 16771.68 | 109945.08 | 0.3386 | 56285.06 |  | 66.14 |  | Dushant Gore | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Dushant Gore | 08 Aug 2022
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3853 | 54278.37 | 9770.4 | 64048.77 | 0.6147 | 102181.37 |  | 38.53 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3811 | 53686.7 | 9663.12 | 63349.82 | 0.6189 | 102880.32 |  | 38.11 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3392 | 47784.12 | 8602.38 | 56386.5 | 0.6608 | 109843.64 |  | 33.92 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 1 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.2893 | 40754.56 | 7336.44 | 48091 | 0.7107 | 118139.14 |  | 28.93 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 333 | 2 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3853 | 54278.37 | 9770.4 | 64048.77 | 0.6147 | 102181.37 |  | 38.53 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | DUSHANT.GORE | 03 Feb 2024
GANGA ASMI | 333 | 0 | 09 Jul 2022 | SHREE GANESH SECURITY SERVICES | H.O. Admin Security Services | Security Services. | Month | 1 | 140873 | 140873 | 25357.14 | 166230.14 | 0 | 0.3572 | 50319.84 | 9057.24 | 59377.08 | 0.6428 | 106853.06 |  | 35.72 |  | Dushant Gore | Swapnil Erande | construction open | 12 Jul 2022 |  | S OH Site Staff | Approved | Dushant Gore | 08 Aug 2022
GANGA ASMI | 334 | 0 | 11 Jul 2022 | LAXMAN CHAVAN | Wing-2 Substructure Lift Pit Screeding Work | Screeding W/P-BCo | Sq.Ft | 4238.97 | 15 | 63584.55 | 0 | 63584.55 | 10 | 786.0322 | 11790.48 | 2122.28 | 13912.76 | 3452.9378 | 49671.79 |  | 18.543 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 19 Jul 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 335 | 0 | 13 Jul 2022 | NAVAY RENEWABLE PRIVATE LIMITED | Goel House Solar System work | 75 KW Solar System (M) | No. | 0 | 3562500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Solar PV Panel/Module=Capacity-75 KW on Grid,Brand-550 Wp Trina,Type-Monocrystalline with Half cut Technology,Generation per Day-260 KWh/Day,Panel Size-2.4x1.1 mtr,No. of Panels-138,Warranty- 28 Years. 2.Inverter;75 KW 3 Phase, ABB Brand, Warranty-7Yrs. | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Jul 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 13 Jul 2022
GANGA ASMI | 336 | 0 | 13 Jul 2022 | NAVAY RENEWABLES | Goel House Solar System work | 75 KW Solar System (M) | No. | 0 | 3562500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.Solar PV Panel/Module=Capacity-75 KW on Grid,Brand-550 Wp Trina,Type-Monocrystalline with Half cut Technology,Generation per Day-260 KWh/Day,Panel Size-2.4x1.1 mtr,No. of Panels-138,Warranty- 28 Years. 2.Inverter;75 KW 3 Phase, ABB Brand, Warranty-7Yrs. | 0 |  | ADITYA CHOUGULE |  | construction open | 13 Jul 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 19 Jul 2022
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Flat Patti- SO | Kgs | 116 | 18 | 2088 | 375.84 | 2463.84 | 2.5 | 72.8468 | 1311.24 | 236.02 | 1547.26 | 43.1532 | 916.58 |  | 62.799 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | ISMC 100 (L) | Kgs | 2599.28 | 18 | 46787.04 | 8421.66 | 55208.7 | 2.5 | 2392.1953 | 43059.52 | 7750.7 | 50810.22 | 207.0847 | 4398.48 |  | 92.033 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | M.S. Angle 50x50x5 (L)- BCo | Kgs | 2699.05 | 18 | 48582.9 | 8744.92 | 57327.82 | 2.5 | 2371.0614 | 42679.11 | 7682.24 | 50361.35 | 327.9886 | 6966.47 |  | 87.848 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Flat Patti- SO | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 16 Jul 2022 |  | S OH Infrastructure | Cancelled | Dushant Gore | 16 Jul 2022
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | MS Square Pipe (L) | Kgs | 54.39 | 18 | 979.02 | 176.22 | 1155.24 | 2.5 | 48.2689 | 868.84 | 156.4 | 1025.24 | 6.1211 | 130 |  | 88.7459 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | M.S. Angles (L)- SOSB | Kgs | 455.4 | 18 | 8197.2 | 1475.5 | 9672.7 | 2.5 | 408.3708 | 7350.67 | 1323.12 | 8673.79 | 47.0292 | 998.91 |  | 89.673 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | MS Square Pipe (L) | Kgs | 172.48 | 18 | 3104.64 | 558.84 | 3663.48 | 2.5 | 121.419 | 2185.54 | 393.4 | 2578.94 | 51.061 | 1084.54 |  | 70.396 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Flat Patti- SO | Kgs | 67.2 | 18 | 1209.6 | 217.72 | 1427.32 | 2.5 | 60.7165 | 1092.9 | 196.72 | 1289.62 | 6.4835 | 137.7 |  | 90.3519 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | MS Square Pipe (L) | Kgs | 94.08 | 18 | 1693.44 | 304.82 | 1998.26 | 2.5 | 94.08 | 1693.44 | 304.82 | 1998.26 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Deck Sheet Fixing | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 16 Jul 2022 |  | UTI. U.G.W.T | Cancelled | Dushant Gore | 18 Jul 2022
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | MS Square Pipe (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 16 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | Dushant Gore | 16 Jul 2022
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | ISMC 150 (L) | Kgs | 1719.3 | 18 | 30947.4 | 5570.54 | 36517.94 | 2.5 | 1719.025 | 30942.45 | 5569.64 | 36512.09 | 0.275 | 5.85 |  | 99.984 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | M.S. Angles (L)- SOSB | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 16 Jul 2022 |  | S OH Infrastructure | Cancelled | Dushant Gore | 16 Jul 2022
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Meta colour Sheet Fixing BC | Sq.Ft | 4600 | 6 | 27600 | 4968 | 32568 | 2.5 | 3482.43 | 20894.58 | 3761.02 | 24655.6 | 1117.57 | 7912.4 |  | 75.705 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Deck Sheet Fixing | Sq.Ft | 1040 | 7 | 7280 | 1310.4 | 8590.4 | 2.5 | 997.7448 | 6984.21 | 1257.16 | 8241.37 | 42.2552 | 349.03 |  | 95.937 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 337 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Door Frame making & Fixing work | No. | 16 | 800 | 12800 | 2304 | 15104 | 2.5 | 16 | 12800 | 2304 | 15104 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 16 Jul 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | MS Square Pipe (M) | Kgs | 172.48 | 69 | 11901.12 | 2142.2 | 14043.32 | 0 | 121.4207 | 8378.03 | 1508.04 | 9886.07 | 51.0593 | 4157.25 |  | 70.397 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | MS Square Pipe (M) | Kgs | 54 | 69 | 3726 | 670.68 | 4396.68 | 0 | 48.269 | 3330.56 | 599.5 | 3930.06 | 5.731 | 466.62 |  | 89.387 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | MS Square Pipe (M) | Kgs | 94.08 | 69 | 6491.52 | 1168.48 | 7660 | 0 | 94.08 | 6491.52 | 1168.48 | 7660 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | M.S. Angles (M)- SOSB | Kgs | 455.4 | 64 | 29145.6 | 5246.2 | 34391.8 | 0 | 408.3708 | 26135.73 | 4704.44 | 30840.17 | 47.0292 | 3551.63 |  | 89.673 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Flat Patti (M) | Kgs | 67.2 | 64 | 4300.8 | 774.14 | 5074.94 | 0 | 60.7172 | 3885.9 | 699.46 | 4585.36 | 6.4828 | 489.58 |  | 90.353 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | Flat Patti (M) | Kgs | 116 | 64 | 7424 | 1336.32 | 8760.32 | 0 | 72.848 | 4662.27 | 839.2 | 5501.47 | 43.152 | 3258.85 |  | 62.8 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | M.S. Angle 50x50x5 (M)- BCo | Kgs | 2699.05 | 64 | 172739.2 | 31093.06 | 203832.26 | 0 | 2371.0614 | 151747.93 | 27314.6 | 179062.53 | 327.9886 | 24769.73 |  | 87.848 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | ISMC 150 (M) | Kgs | 1719.3 | 64 | 110035.2 | 19806.34 | 129841.54 | 0 | 1719.025 | 110017.6 | 19803.16 | 129820.76 | 0.275 | 20.78 |  | 99.984 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 338 | 0 | 16 Jul 2022 | SHRUSHTI GLASS & ALUMINIUM | New Labour Camp | ISMC 100 (M)- Kgs | Kgs | 2599.28 | 64 | 166353.92 | 29943.7 | 196297.62 | 0 | 2392.1953 | 153100.5 | 27558.08 | 180658.58 | 207.0847 | 15639.04 |  | 92.033 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 339 | 0 | 18 Jul 2022 | PEST-O-CRUSH | Goel House (L) Fogging Work | Fogging work.- AIE | No. | 1 | 1000 | 1000 | 180 | 1180 | 0 | 1 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 25 Jul 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 1 | 18 Jul 2022 | PATILS FABRICATORS | Goel House Fabrication rennovation work | GI Sheet Fixing | Sq.Ft | 435 | 5 | 2175 | 391.5 | 2566.5 | 2.5 | 435 | 2175 | 391.5 | 2566.5 | 0 | 0 | 1. 7.5Ft x 30 Ft= 225 Sqft 2. 14Ft x 7.5Ft x 2Nos= 210 Sqft Total= 435 Sqft | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Jul 2022 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 0 | 18 Jul 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | Chemical Fastner fixing (L) | No. | 3 | 50 | 150 | 27 | 177 | 2.5 | 3 | 150 | 27 | 177 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 0 | 18 Jul 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Square Pipe (L) | Kgs | 144.12 | 20 | 2882.4 | 518.84 | 3401.24 | 2.5 | 144.12 | 2882.4 | 518.84 | 3401.24 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 1 | 18 Jul 2022 | PATILS FABRICATORS | Goel House Fabrication rennovation work | Fabrication work (L) | Kgs | 296 | 17 | 5032 | 905.76 | 5937.76 | 2.5 | 296 | 5032 | 905.76 | 5937.76 | 0 | 0 | 1.30 Ft x 4 Nos= 120 Ft 2.7.5 Ft x 6Nos= 45 Ft 3.14 Ft x 6Nos= 84 Ft 4. 7.5 Ft x 10Nos= 75 Ft Total= 324 Rft. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Jul 2022 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 0 | 18 Jul 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Square Pipe (L) | Kgs | 225.9 | 20 | 4518 | 813.24 | 5331.24 | 2.5 | 225.9 | 4518 | 813.24 | 5331.24 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 0 | 18 Jul 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Square Pipe (L) | Kgs | 536.33 | 20 | 10726.6 | 1930.78 | 12657.38 | 2.5 | 536.33 | 10726.6 | 1930.78 | 12657.38 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 0 | 18 Jul 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Square Pipe (L) | Kgs | 25.98 | 20 | 519.6 | 93.52 | 613.12 | 2.5 | 25.98 | 519.6 | 93.52 | 613.12 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 0 | 18 Jul 2022 | PATILS FABRICATORS | Goel House (L) Pooja Room Fabrication Work | MS Pipe (L) | Kgs | 34.95 | 20 | 699 | 125.82 | 824.82 | 2.5 | 17.75 | 355 | 63.9 | 418.9 | 17.2 | 405.92 |  | 50.7868 |  | Dushant Gore | Swapnil Erande | construction open | 21 Jul 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 340 | 2 | 18 Jul 2022 | PATILS FABRICATORS | Gym Room M.S. A/C Rack Work | Fabrication work (L) | Kgs | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Jul 2022 |  | Admin. Direct Expenses | Cancelled | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 341 | 0 | 22 Jul 2022 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | ARTICLE / WRITE UP / CONTENT / ONLINE - OFFILINE PR / ORM / | No. | 12 | 50000 | 600000 | 108000 | 708000 | 0 | 5.5 | 274998.9 | 49499.78 | 324498.68 | 6.5 | 383501.32 | PRESS RELEASE FOR GOEL GANGA GROUP + ATUL GOEL - ARTICALE, WRTITE UP, CONTENT ETC. WITH BRAND PROMOTION THROUGH PR - ONLINE / OFFLINE MEDIA AS ON 01ST APRIL 2022 TO 31ST MARCH 2023 @ 50000/- + TAX PER MONTH | 45.8333 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 23 Jul 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 341 | 1 | 22 Jul 2022 | CR TECHMEDIA PRIVETE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 12 | 50000 | 600000 | 108000 | 708000 | 0 | 9 | 449998.2 | 80999.64 | 530997.84 | 3 | 177002.16 | ONLINE REPUTATION MANAGEMENT SERVICES FOR GOEL GANGA GROUP + MR. ATUL GORL SIR BRAND, SALES PROMOTION WITH LEAD GENERATION AS ON 01ST APRIL 2022 TO TILL 31ST MARCH 2023 @50000 + TAX PER MONTH | 75 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 23 Jul 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 342 | 0 | 26 Jul 2022 | LAXMI FURNITURE | A9 11th Flr Renovation | Carpentary work -Mkt | No. | 1 | 26950 | 26950 | 0 | 26950 | 2.5 | 1 | 26950 | 0 | 26950 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 342 | 0 | 26 Jul 2022 | LAXMI FURNITURE | A9 11th Flr Renovation | Carpentary work -Mkt | No. | 1 | 155585 | 155585 | 0 | 155585 | 2.5 | 1 | 155585 | 0 | 155585 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Lumpsum work- DCW | No. | 1 | 4000 | 4000 | 0 | 4000 | 2.5 | 1 | 4000 | 0 | 4000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Edge Polish - Dld | R.Ft | 55.32 | 35 | 1936.2 | 0 | 1936.2 | 2.5 | 55.32 | 1936.2 | 0 | 1936.2 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Epoxy Grout Filling- | R.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Cancelled | Dushant Gore | 28 Jul 2022
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Epoxy Grout Filling | Sq.Ft | 90 | 25 | 2250 | 0 | 2250 | 2.5 | 90 | 2250 | 0 | 2250 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Edge Polish - Dld | R.Ft | 95.64 | 35 | 3347.4 | 0 | 3347.4 | 2.5 | 95.64 | 3347.4 | 0 | 3347.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Lumpsum work- DCW | No. | 1 | 2500 | 2500 | 0 | 2500 | 2.5 | 1 | 2500 | 0 | 2500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | V Groove - AIE | R.Ft | 74.48 | 80 | 5958.4 | 0 | 5958.4 | 2.5 | 74.48 | 5958.4 | 0 | 5958.4 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Lumpsum work- DCW | No. | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | DEV. Compound Wall | Cancelled | Dushant Gore | 05 Sep 2022
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Dado - AIE | Sq.Ft | 38.82 | 125 | 4852.5 | 0 | 4852.5 | 2.5 | 38.82 | 4852.5 | 0 | 4852.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Dado - AIE | Sq.Ft | 102.28 | 225 | 23013 | 0 | 23013 | 2.5 | 102.28 | 23013 | 0 | 23013 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Dado - AIE | Sq.Ft | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Cancelled | Dushant Gore | 29 Jul 2022
GANGA ASMI | 343 | 0 | 26 Jul 2022 | BACHHULAL ENTERPRISES | A9 1101 Tiling work | Dado - AIE | Sq.Ft | 147.94 | 125 | 18492.5 | 0 | 18492.5 | 2.5 | 147.94 | 18492.5 | 0 | 18492.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | M.R.False Ceiling work | Sq.Ft | 93 | 140 | 13020 | 0 | 13020 | 2.5 | 93 | 13020 | 0 | 13020 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Groove Making-DCH | R.Ft | 158.5 | 15 | 2377.5 | 0 | 2377.5 | 2.5 | 158.5 | 2377.5 | 0 | 2377.5 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | False Ceiling work- BCo | Sq.Ft | 104.75 | 125 | 13093.75 | 0 | 13093.75 | 2.5 | 104.75 | 13093.75 | 0 | 13093.75 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | POP Wall Mounting- AIE | Sq.Ft | 567 | 12 | 6804 | 0 | 6804 | 2.5 | 567 | 6804 | 0 | 6804 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Gypsum on Wall | Sq.Ft | 567 | 35 | 19845 | 0 | 19845 | 2.5 | 567 | 19845 | 0 | 19845 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Grid False Ceiling-DSP | Sq.Ft | 40 | 150 | 6000 | 0 | 6000 | 2.5 | 40 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Gypsum Ceiling - BC | Sq.Ft | 0 | 140 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | 05 GYPSUM & PLASTER | Cancelled | Dushant Gore | 28 Jul 2022
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Ceiling POP- ULT | Sq.Ft | 0 | 125 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Cancelled | Dushant Gore | 28 Jul 2022
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Light Gala Cutting-BC | No. | 15 | 60 | 900 | 0 | 900 | 2.5 | 15 | 900 | 0 | 900 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Lumpsum work- DCW | No. | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Lumpsum work- DCW | No. | 0 | 25000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | DEV. Compound Wall | Cancelled | Dushant Gore | 05 Sep 2022
GANGA ASMI | 344 | 0 | 27 Jul 2022 | NA DECORATES | A9 1101 Gypsum Work | Grid False Ceiling-DSP | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 1900-01-01 |  | DEV. Swimming Pool | Cancelled | Dushant Gore | 05 Sep 2022
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Royal Paint (Patta) | R.Ft | 191.36 | 27.6 | 5281.54 | 0 | 5281.54 | 2.5 | 191.36 | 5281.54 | 950.68 | 6232.22 | 0 | -950.68 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | P.U. Polish Patta-BC (m+l) | R.Ft | 111.5 | 101.2 | 11283.8 | 0 | 11283.8 | 2.5 | 111.5 | 11283.8 | 2031.08 | 13314.88 | 0 | -2031.08 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Apex Paint | Sq.Ft | 304.32 | 23 | 6999.36 | 0 | 6999.36 | 2.5 | 304.32 | 6999.36 | 1259.88 | 8259.24 | 0 | -1259.88 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine Lipping Polish - Mkt | R.Ft | 2971.18 | 36.8 | 109339.42 | 0 | 109339.42 | 2.5 | 2971.18 | 109339.42 | 19681.1 | 129020.52 | 0 | -19681.1 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Polish Work - BC | R.Ft | 54.74 | 87.4 | 4784.28 | 0 | 4784.28 | 2.5 | 54.74 | 4784.28 | 861.18 | 5645.46 | 0 | -861.18 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | French Polish | Sq.Ft | 81.06 | 32.2 | 2610.13 | 0 | 2610.13 | 2.5 | 81.06 | 2610.13 | 469.82 | 3079.95 | 0 | -469.82 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Satin Mat Paint | Sq.Ft | 2243.23 | 27.6 | 61913.15 | 0 | 61913.15 | 2.5 | 2243.23 | 61913.15 | 11144.36 | 73057.51 | 0 | -11144.36 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | P.U. Polish-AIE | Sq.Ft | 111.5 | 193.2 | 21541.8 | 0 | 21541.8 | 2.5 | 111.5 | 21541.8 | 3877.52 | 25419.32 | 0 | -3877.52 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Apex Paint | Sq.Ft | 4440.44 | 23 | 102130.12 | 0 | 102130.12 | 2.5 | 4440.44 | 102130.12 | 18383.42 | 120513.54 | 0 | -18383.42 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | French Polish | Sq.Ft | 49.24 | 32.2 | 1585.53 | 0 | 1585.53 | 2.5 | 49.24 | 1585.53 | 285.4 | 1870.93 | 0 | -285.4 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | ICA Colour P.U Groove | R.Ft | 4.99 | 82.8 | 413.17 | 0 | 413.17 | 2.5 | 4.99 | 413.17 | 74.38 | 487.55 | 0 | -74.38 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | ICA Colour P.U Patt | R.Ft | 100.03 | 142.6 | 14264.28 | 0 | 14264.28 | 2.5 | 100.03 | 14264.28 | 2567.58 | 16831.86 | 0 | -2567.58 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | ICA Colour P.U Patt | R.Ft | 121.98 | 142.6 | 17394.35 | 0 | 17394.35 | 2.5 | 121.98 | 17394.35 | 3130.98 | 20525.33 | 0 | -3130.98 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine Lipping Polish - Mkt | R.Ft | 2295.98 | 36.8 | 84492.06 | 0 | 84492.06 | 2.5 | 2295.98 | 84492.06 | 15208.58 | 99700.64 | 0 | -15208.58 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Primer,Lambi/Putty & 1 Coat Paint | Sq.Ft | 195.9 | 18.4 | 3604.56 | 648.82 | 4253.38 | 2.5 | 195.9 | 3604.56 | 648.82 | 4253.38 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | ICA Colour P.U Libbing | R.Ft | 256.53 | 142.6 | 36581.18 | 0 | 36581.18 | 2.5 | 256.53 | 36581.18 | 6584.62 | 43165.8 | 0 | -6584.62 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine Grove - Mkt | R.Ft | 151.23 | 27.6 | 4173.95 | 0 | 4173.95 | 2.5 | 151.23 | 4173.95 | 751.32 | 4925.27 | 0 | -751.32 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine 3" Patta - Mkt | R.Ft | 2112.58 | 46 | 97178.68 | 0 | 97178.68 | 2.5 | 2112.58 | 97178.68 | 17492.16 | 114670.84 | 0 | -17492.16 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Royale Paint | Sq.Ft | 3322.88 | 44.16 | 146738.38 | 0 | 146738.38 | 2.5 | 3322.88 | 146738.38 | 26412.9 | 173151.28 | 0 | -26412.9 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine 3" Patta - Mkt | R.Ft | 1496.67 | 46 | 68846.82 | 0 | 68846.82 | 2.5 | 1496.67 | 68846.82 | 12392.42 | 81239.24 | 0 | -12392.42 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Royale Paint | Sq.Ft | 3127.41 | 44.16 | 138106.43 | 0 | 138106.43 | 2.5 | 3127.41 | 138106.43 | 24859.16 | 162965.59 | 0 | -24859.16 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine Polish | Sq.Ft | 916.17 | 73.6 | 67430.11 | 0 | 67430.11 | 2.5 | 916.17 | 67430.11 | 12137.42 | 79567.53 | 0 | -12137.42 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Oil Paint | Sq.Ft | 1419.76 | 25.76 | 36573.02 | 0 | 36573.02 | 2.5 | 1419.76 | 36573.02 | 6583.14 | 43156.16 | 0 | -6583.14 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | UTI. Water treatment plant | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | ICA Colour P.U | Sq.Ft | 31.24 | 285.2 | 8909.65 | 0 | 8909.65 | 2.5 | 31.24 | 8909.65 | 1603.74 | 10513.39 | 0 | -1603.74 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine Grove - Mkt | R.Ft | 106.62 | 27.6 | 2942.71 | 0 | 2942.71 | 2.5 | 106.62 | 2942.71 | 529.68 | 3472.39 | 0 | -529.68 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | ICA Colour P.U | Sq.Ft | 234.04 | 285.2 | 66748.21 | 0 | 66748.21 | 2.5 | 234.04 | 66748.21 | 12014.68 | 78762.89 | 0 | -12014.68 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Royal Paint (Patta) | R.Ft | 388.26 | 27.6 | 10715.98 | 0 | 10715.98 | 2.5 | 388.26 | 10715.98 | 1928.88 | 12644.86 | 0 | -1928.88 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | ICA Colour P.U Libbing | R.Ft | 281.31 | 142.6 | 40114.81 | 0 | 40114.81 | 2.5 | 281.31 | 40114.81 | 7220.66 | 47335.47 | 0 | -7220.66 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine Polish | Sq.Ft | 547.08 | 73.6 | 40265.09 | 0 | 40265.09 | 2.5 | 547.08 | 40265.09 | 7247.72 | 47512.81 | 0 | -7247.72 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 345 | 0 | 27 Jul 2022 | UMESH YADAV | A9 1101 Painting | Melamine Polish | Sq.Ft | 1223.1 | 73.6 | 90020.16 | 0 | 90020.16 | 2.5 | 1223.1 | 90020.16 | 16203.62 | 106223.78 | 0 | -16203.62 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 01 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 346 | 1 | 03 Aug 2022 | NIRMAL AUTOMATION PVT.LTD. | Goel House (L) AMC Charges - Automation | AMC Charges | Month | 12 | 5833.33 | 69999.96 | 12600 | 82599.96 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | Sanket Patil | Swapnil Erande | construction open | 03 Aug 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 346 | 0 | 03 Aug 2022 | NIRMAL AUTOMATION PVT.LTD. | Goel House (L) AMC Charges - Automation | AMC Charges | Month | 12 | 5833.33 | 69999.96 | 12600 | 82599.96 | 0 | 12 | 69999.96 | 12600.02 | 82599.98 | 0 | -0.02 | ANNUAL MAINTENANCE CHARGES FOR AUTOMATION GATE TOTAL- 5 MOTORS. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 03 Aug 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 347 | 0 | 17 Aug 2022 | GREENSOL TECH | 500 KLD STP for Residential Towers | Sewage Treatment Plant (M) | No. | 0 | 2864000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.ALL SPECIFICATIONS AS PER QTN NO-22-23/248 R-1 DATED-17.08.2022 | 0 |  | ADITYA CHOUGULE |  | construction open | 30 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 30 Aug 2022
GANGA ASMI | 348 | 0 | 17 Aug 2022 | GREENSOL TECH | 500 KLD STP for Residential Towers | Sewage Treatment Plant (L) | No. | 0 | 716000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 30 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 30 Aug 2022
GANGA ASMI | 349 | 0 | 17 Aug 2022 | GREENSOL TECH | 60 KLD STP for MHADA | Sewage Treatment Plant (M) | No. | 0 | 648000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.ALL SPECIFICATIONS AS PER QTN NO-22-23/247 R-1 DATED-17.08.2022 | 0 |  | ADITYA CHOUGULE |  | construction open | 30 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 30 Aug 2022
GANGA ASMI | 350 | 0 | 17 Aug 2022 | GREENSOL TECH | 60 KLD STP for MHADA | Sewage Treatment Plant (L) | No. | 0 | 162000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 30 Aug 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 30 Aug 2022
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | PCC | Sq.Ft | 513.62 | 10 | 5136.2 | 0 | 5136.2 | 2.5 | 0 | 0 | 0 | 0 | 513.62 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Skirting Fixing - AIE | R.Ft | 50 | 140 | 7000 | 0 | 7000 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Zero Point | R.Ft | 32 | 180 | 5760 | 0 | 5760 | 2.5 | 0 | 0 | 0 | 0 | 32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Labour Lumpsum - SOS | No. | 0 | 37000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 06 Sep 2022 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 19 Nov 2022
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Top Fixing | Sq.Ft | 335.42 | 140 | 46958.8 | 0 | 46958.8 | 2.5 | 0 | 0 | 0 | 0 | 335.42 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Tile Fixing Work-DER | Sq.Ft | 56.55 | 140 | 7917 | 0 | 7917 | 2.5 | 0 | 0 | 0 | 0 | 56.55 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | DEV. Extrawork/Rework | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Marble Top Edge Polish | R.Ft | 91.5 | 35 | 3202.5 | 0 | 3202.5 | 2.5 | 0 | 0 | 0 | 0 | 91.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Edge Polish - BCE | R.Ft | 7 | 35 | 245 | 0 | 245 | 2.5 | 0 | 0 | 0 | 0 | 7 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Fixing -SOS | Sq.Ft | 103.16 | 125 | 12895 | 0 | 12895 | 2.5 | 0 | 0 | 0 | 0 | 103.16 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Epoxy Grout Filling- | R.Ft | 513.62 | 20 | 10272.4 | 0 | 10272.4 | 2.5 | 0 | 0 | 0 | 0 | 513.62 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | V Groove - AIE | R.Ft | 3.5 | 80 | 280 | 0 | 280 | 2.5 | 0 | 0 | 0 | 0 | 3.5 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Skirting Kani | R.Ft | 155.5 | 50 | 7775 | 0 | 7775 | 2.5 | 0 | 0 | 0 | 0 | 155.5 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Granite Edge Polish | R.Ft | 84.66 | 35 | 2963.1 | 0 | 2963.1 | 2.5 | 0 | 0 | 0 | 0 | 84.66 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Tile Fixing Work-DER | Sq.Ft | 656.74 | 140 | 91943.6 | 0 | 91943.6 | 2.5 | 0 | 0 | 0 | 0 | 656.74 | 0 | (RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | DEV. Extrawork/Rework | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 1 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Labour Lumpsum - SOS | No. | 1 | 37000 | 37000 | 0 | 37000 | 2.5 | 1 | 37000 | 0 | 37000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 351 | 0 | 19 Aug 2022 | BACHHULAL ENTERPRISES | Goel House Flooring Work | Labour Charges. | No. | 2 | 2500 | 5000 | 0 | 5000 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Old Kitchen Nhani Trap Jali cutting and Fixing work.(RA 17) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 06 Sep 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 3rd Slab (P4 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 0 | 10000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Cancelled | Dushant Gore | 22 Aug 2022
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Electrical Work (Labour) | No. | 1 | 6049 | 6049 | 0 | 6049 | 2.5 | 0.35 | 2117.15 | 0 | 2117.15 | 0.65 | 3931.85 | Bell Point-1,Light point-7,Fan Point-2,6A Plug Point-6,6Amp Half Plug Point-2,Exaust point-1,16Amp Power Point-2,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-1,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P4 Parking Electrical (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Fixing DB - Mkt | No. | 1 | 1200 | 1200 | 0 | 1200 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 5th Slab (P6 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 4th Slab (P5 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 0 | 10000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Cancelled | Dushant Gore | 22 Aug 2022
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Fixing DB - Mkt | No. | 1 | 1200 | 1200 | 0 | 1200 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 6th Slab (Podium Floor Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 0 | 10000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Cancelled | Dushant Gore | 22 Aug 2022
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P6 Parking Electrical (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Fixing DB - Mkt | No. | 1 | 1200 | 1200 | 0 | 1200 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P5 Parking Electrical (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing-1 P1 Parking Electrical (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P2 Parking Electrical (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Electrical Work (Labour) | No. | 1 | 7573 | 7573 | 0 | 7573 | 2.5 | 0.35 | 2650.55 | 0 | 2650.55 | 0.65 | 4922.45 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-4,6Amp Half Plug Point-4,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P2 Parking Electrical (L) | Light Point BC | No. | 30 | 225 | 6750 | 0 | 6750 | 2.5 | 30 | 6750 | 0 | 6750 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P2 Parking Electrical (L) | Tube Light Fixing BC | No. | 26 | 100 | 2600 | 0 | 2600 | 2.5 | 0 | 0 | 0 | 0 | 26 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P6 Parking Electrical (L) | Light Point BC | No. | 30 | 225 | 6750 | 0 | 6750 | 2.5 | 30 | 6750 | 0 | 6750 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 2nd Slab (P3 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 0 | 10000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Cancelled | Dushant Gore | 22 Aug 2022
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P4 Parking Electrical (L) | Light Point BC | No. | 30 | 225 | 6750 | 0 | 6750 | 2.5 | 30 | 6750 | 0 | 6750 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P3 Parking Electrical (L) | Light Point BC | No. | 30 | 225 | 6750 | 0 | 6750 | 2.5 | 30 | 6750 | 0 | 6750 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Electrical Work (Labour) | No. | 1 | 7573 | 7573 | 0 | 7573 | 2.5 | 0.35 | 2650.55 | 0 | 2650.55 | 0.65 | 4922.45 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-4,6Amp Half Plug Point-4,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 3rd Slab (P4 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 0.5 | 5000 | 900 | 5900 | 0.5 | 4100 |  | 50 |  | Dushant Gore | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Electrical Work (Labour) | No. | 1 | 7573 | 7573 | 0 | 7573 | 2.5 | 0.35 | 2650.55 | 0 | 2650.55 | 0.65 | 4922.45 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-4,6Amp Half Plug Point-4,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Electrical Work (Labour) | No. | 1 | 6049 | 6049 | 0 | 6049 | 2.5 | 0.35 | 2117.15 | 0 | 2117.15 | 0.65 | 3931.85 | Bell Point-1,Light point-7,Fan Point-2,6A Plug Point-6,6Amp Half Plug Point-2,Exaust point-1,16Amp Power Point-2,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-1,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Two way Point BC | No. | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 5th Slab (P6 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 0 | 10000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Cancelled | Dushant Gore | 22 Aug 2022
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P3 Parking Electrical (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Fixing DB - Mkt | No. | 1 | 1200 | 1200 | 0 | 1200 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Fixing DB - Mkt | No. | 1 | 1200 | 1200 | 0 | 1200 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Two way Point BC | No. | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing-1 P1 Parking Electrical (L) | Tube Light Fixing BC | No. | 26 | 100 | 2600 | 0 | 2600 | 2.5 | 0 | 0 | 0 | 0 | 26 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Heat Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P3 Parking Electrical (L) | Tube Light Fixing BC | No. | 26 | 100 | 2600 | 0 | 2600 | 2.5 | 0 | 0 | 0 | 0 | 26 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 6th Slab (Podium Floor Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 1st Slab (P2 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 1 | 10000 | 1800 | 11800 | 0 | -1800 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P4 Parking Electrical (L) | Tube Light Fixing BC | No. | 26 | 100 | 2600 | 0 | 2600 | 2.5 | 0 | 0 | 0 | 0 | 26 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P5 Parking Electrical (L) | Tube Light Fixing BC | No. | 26 | 100 | 2600 | 0 | 2600 | 2.5 | 0 | 0 | 0 | 0 | 26 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Exaust Point-mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | 6 AMP Plug Point - Mkt | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 103 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | Electrical Work (Labour) | No. | 1 | 7236 | 7236 | 0 | 7236 | 2.5 | 0.35 | 2532.6 | 0 | 2532.6 | 0.65 | 4703.4 | Bell Point-1,Light point-11,Fan Point-3,6A Plug Point-4,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Electrical Work (Labour) | No. | 1 | 7236 | 7236 | 0 | 7236 | 2.5 | 0.35 | 2532.6 | 0 | 2532.6 | 0.65 | 4703.4 | Bell Point-1,Light point-11,Fan Point-3,6A Plug Point-4,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 502 (MHADA) | Electrical Work (Labour) | No. | 1 | 7236 | 7236 | 0 | 7236 | 2.5 | 0.35 | 2532.6 | 0 | 2532.6 | 0.65 | 4703.4 | Bell Point-1,Light point-11,Fan Point-3,6A Plug Point-4,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Two way Point BC | No. | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P6 Parking Electrical (L) | Tube Light Fixing BC | No. | 26 | 100 | 2600 | 0 | 2600 | 2.5 | 0 | 0 | 0 | 0 | 26 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 4th Slab (P5 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 402 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 401 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing-1 P1 Parking Electrical (L) | Light Point BC | No. | 30 | 225 | 6750 | 0 | 6750 | 2.5 | 30 | 6750 | 0 | 6750 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 501 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | 6 AMP half plug point Mkt | No. | 0 | 112 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 2nd Slab (P3 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 1 | 10000 | 10000 | 0 | 10000 | 2.5 | 0.5 | 5000 | 900 | 5900 | 0.5 | 4100 |  | 50 |  | Dushant Gore | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 102 (MHADA) | Electrical Work (Labour) | No. | 1 | 7236 | 7236 | 0 | 7236 | 2.5 | 0.35 | 2532.6 | 0 | 2532.6 | 0.65 | 4703.4 | Bell Point-1,Light point-11,Fan Point-3,6A Plug Point-4,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 0 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing 1 - 1st Slab (P2 Lvl) Fire Sleeve Fixing Work | Sleeve Fixing Work | Floor | 0 | 10000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 22 Aug 2022 |  | B.C. RCC Superstructure | Cancelled | Dushant Gore | 22 Aug 2022
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Electrical Work (Labour) | No. | 1 | 7236 | 7236 | 0 | 7236 | 2.5 | 0.35 | 2532.6 | 0 | 2532.6 | 0.65 | 4703.4 | Bell Point-1,Light point-11,Fan Point-3,6A Plug Point-4,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 202 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 404 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Electrical Work (Labour) | No. | 1 | 6049 | 6049 | 0 | 6049 | 2.5 | 0.35 | 2117.15 | 0 | 2117.15 | 0.65 | 3931.85 | Bell Point-1,Light point-7,Fan Point-2,6A Plug Point-6,6Amp Half Plug Point-2,Exaust point-1,16Amp Power Point-2,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-1,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 505 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Electrical Work (Labour) | No. | 1 | 6049 | 6049 | 0 | 6049 | 2.5 | 0.35 | 2117.15 | 0 | 2117.15 | 0.65 | 3931.85 | Bell Point-1,Light point-7,Fan Point-2,6A Plug Point-6,6Amp Half Plug Point-2,Exaust point-1,16Amp Power Point-2,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-1,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Electrical Work (Labour) | No. | 1 | 7573 | 7573 | 0 | 7573 | 2.5 | 0.35 | 2650.55 | 0 | 2650.55 | 0.65 | 4922.45 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-4,6Amp Half Plug Point-4,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Power Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 105 (MHADA) | Two way Point BC | No. | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 303 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 305 (MHADA) | Two way Point BC | No. | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 203 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 304 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Telephone Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 403 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 301 (MHADA) | Electrical Work (Labour) | No. | 1 | 7573 | 7573 | 0 | 7573 | 2.5 | 0.35 | 2650.55 | 0 | 2650.55 | 0.65 | 4922.45 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-4,6Amp Half Plug Point-4,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 405 (MHADA) | Light Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 104 (MHADA) | Electrical Work (Labour) | No. | 1 | 7911 | 7911 | 0 | 7911 | 2.5 | 0.35 | 2768.85 | 0 | 2768.85 | 0.65 | 5142.15 | Bell Point-1,Light point-11,Fan Point-4,6A Plug Point-6,6Amp Half Plug Point-3,Exaust point-2,16Amp Power Point-3,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-2,Heat Detector-1 | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 302 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 204 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 205 (MHADA) | Electrical Work (Labour) | No. | 1 | 6049 | 6049 | 0 | 6049 | 2.5 | 0.35 | 2117.15 | 0 | 2117.15 | 0.65 | 3931.85 | Bell Point-1,Light point-7,Fan Point-2,6A Plug Point-6,6Amp Half Plug Point-2,Exaust point-1,16Amp Power Point-2,Gyser Point-1,TV Point-1,Telephone point-1,Smoke Detector-1,Heat Detector-1. | 35 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 201 (MHADA) | Gyser Point BC | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 2 | 22 Aug 2022 | LAXMI ELECTRICALS | Wing.1 P5 Parking Electrical (L) | Light Point BC | No. | 30 | 225 | 6750 | 0 | 6750 | 2.5 | 30 | 6750 | 0 | 6750 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 101 (MHADA) | Fan Point - BCo | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Smoke Detector | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | TV Point | No. | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 504 (MHADA) | Fixing DB - Mkt | No. | 1 | 1300 | 1300 | 0 | 1300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Aug 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 352 | 1 | 22 Aug 2022 | LAXMI ELECTRICALS | Internal Electrical - Wing 1 - Flat 503 (MHADA) | Bell Point BC | No. | 0 | 225 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 22 Aug 2022 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT GORE | 25 Mar 2023
GANGA ASMI | 353 | 0 | 30 Aug 2022 | AGILE VENTURES | 60 KLD STP for MHADA | Sewage Treatment Plant (M) | No. | 1 | 764122.04 | 764122.04 | 137541.96 | 901664 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1. ALL SPECIFICATIONS AS PER REF: AV/Q/22-23/146-R1 DATED- 29/08/2022 | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 354 | 0 | 30 Aug 2022 | AGILE VENTURES | 60 KLD STP for MHADA | Sewage Treatment Plant (L) | No. | 1 | 191030.51 | 191030.51 | 34385.5 | 225416.01 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 355 | 0 | 30 Aug 2022 | AGILE VENTURES | 500 KLD STP for Residential Towers | Sewage Treatment Plant (M) | No. | 1 | 2717322.04 | 2717322.04 | 489117.96 | 3206440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 1.ALL SPECIFICATIONS AS PER REF: AV/Q/22-23/149-R1 DATED- 29/08/2022 | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 356 | 0 | 30 Aug 2022 | AGILE VENTURES | 500 KLD STP for Residential Towers | Sewage Treatment Plant (L) | No. | 1 | 679330.51 | 679330.51 | 122279.5 | 801610.01 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 357 | 0 | 30 Aug 2022 | YOGESH R INGALE & ASSOCIATES | Professional Fees For Monthly Retainership Services | Professional Fees | Month | 12 | 1500 | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 03 CONSULTANCY | Un-Approved |  | 1900-01-01
GANGA ASMI | 357 | 0 | 30 Aug 2022 | YOGESH R INGALE & ASSOCIATES | Professional Fees For Annual Return & GST Audit Services | Professional Fees (Yrs) | Yearly | 1 | 12000 | 12000 | 0 | 12000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 358 | 0 | 07 Sep 2022 | NILIMA BHOSEKAR | Landscape Consul. - On Submission of Landscape concept plan | Landscape Consultancy. | No. | 1 | 220000 | 220000 | 39600 | 259600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 12 Oct 2022 |  | Consultacy Landscape | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 358 | 0 | 07 Sep 2022 | NILIMA BHOSEKAR | Landscape Consul. - On appointment as Landscape Architect | Landscape Consultancy. | No. | 1 | 110000 | 110000 | 19800 | 129800 | 0 | 1 | 110000 | 19800 | 129800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 12 Oct 2022 |  | Consultacy Landscape | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 358 | 0 | 07 Sep 2022 | NILIMA BHOSEKAR | Landscape Consul. - Remaining amount on Pro rata basis | Landscape Consultancy. | No. | 1 | 550000 | 550000 | 99000 | 649000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 12 Oct 2022 |  | Consultacy Landscape | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 358 | 0 | 07 Sep 2022 | NILIMA BHOSEKAR | Landscape Consul. - On completion of the project | Landscape Consultancy. | No. | 1 | 110000 | 110000 | 19800 | 129800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 12 Oct 2022 |  | Consultacy Landscape | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 358 | 0 | 07 Sep 2022 | NILIMA BHOSEKAR | Landscape Consul. - On Submission of plantation plan | Landscape Consultancy. | No. | 1 | 550000 | 550000 | 99000 | 649000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 12 Oct 2022 |  | Consultacy Landscape | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 358 | 0 | 07 Sep 2022 | NILIMA BHOSEKAR | Landscape Consul. - Environmental Clearance Charges | Landscape Consultancy. | No. | 1 | 110000 | 110000 | 19800 | 129800 | 0 | 1 | 110000 | 19800 | 129800 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 12 Oct 2022 |  | Consultacy Landscape | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 358 | 0 | 07 Sep 2022 | NILIMA BHOSEKAR | Landscape Consul. - On Submission of Landscape settingout pl | Landscape Consultancy. | No. | 1 | 550000 | 550000 | 99000 | 649000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | consultancy | 12 Oct 2022 |  | Consultacy Landscape | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 359 | 1 | 09 Sep 2022 | SAMSUNG INDIA ELECTRONICS PRIVATE LIMITED | Goel House (L) AMC Charges For AC | Annual Maintenance Charges | Hp | 80 | 3076 | 246080 | 44294.4 | 290374.4 | 0 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | Construction | 09 Sep 2022 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 359 | 0 | 09 Sep 2022 | SAMSUNG INDIA ELECTRONICS PRIVATE LIMITED | Goel House (L) AMC Charges For AC | Annual Maintenance Charges | Hp | 80 | 2987 | 238960 | 43012.8 | 281972.8 | 0 | 0 | 0 | 0 | 0 | 80 | 0 |  | 0 |  | Sanket Patil | Swapnil Erande | Construction | 09 Sep 2022 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 360 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | 1 Coat Primer (Water Base) (L) | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 2.5 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 360 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | 1st Coat OBD (L) | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 2.5 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 360 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | Scrapping with 1st Coat Putty | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 2.5 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 360 | 1 | 15 Sep 2022 | BABLI ANIL MAHTO | Sales Office Toilet Extension Gents Toilet Painting | OBD (M+L) BC | Sq.Ft | 67.3 | 9 | 605.7 | 0 | 605.7 | 2.5 | 0 | 0 | 0 | 0 | 67.3 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 26 Sep 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 360 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | 2nd Coat OBD (L) | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 2.5 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 360 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | Scrapping with 2nd Coat Putty | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 2.5 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 361 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | 1 Coat Primer (Water Base) (M) | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 0 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 361 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | 2nd Coat OBD (M) | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 0 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 361 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | Scrapping with 2nd Coat Putty (M) | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 0 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 361 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | Scrapping with 1st Coat Putty (M) | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 0 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 361 | 0 | 15 Sep 2022 | BABLI ANIL MAHTO | Sample flat walls painting (Old Sales office) | 1st Coat OBD (M) | Sq.Ft | 3600 | 1 | 3600 | 0 | 3600 | 0 | 3041.28 | 3041.28 | 547.44 | 3588.72 | 558.72 | 11.28 |  | 84.48 |  | Dushant Gore | Swapnil Erande | construction open | 26 Sep 2022 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 362 | 1 | 26 Sep 2022 | MUKUL CRANE SERVICES | Site Expenses Crane Charges for Steel Shifting | Crane Charges-SO | Hrs | 36.5 | 975 | 35587.5 | 0 | 35587.5 | 0 | 36.5 | 35587.5 | 0 | 35587.5 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 06 Oct 2022 |  | S OH Conveyance & Transport | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 362 | 0 | 26 Sep 2022 | MUKUL CRANE SERVICES | Erection of Front Arch, Septic Tank & Replantation | Crane Charges-BC | Hrs | 32 | 975 | 31200 | 0 | 31200 | 0 | 22.5002 | 21937.7 | 0 | 21937.7 | 9.4998 | 9262.31 |  | 70.3131 |  | Dushant Gore | Swapnil Erande | construction open | 06 Oct 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 363 | 0 | 27 Sep 2022 | KALPANA TASKAR | Landscape Development - MIYAWAKI Forest concept | Professional Fees. | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 18 Feb 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 364 | 0 | 02 Nov 2022 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 45000 | 270000 | 48600 | 318600 | 0 | 6 | 270000 | 48600 | 318600 | 0 | 0 | GANAG ASMI WAKAD PROJECT HOARDING DISPLAY CHARGES @ WAKAD CHOWK NEAR PROJECT SIZE AS 30X42 SQ FT BACK 2 BACK AS ON 01/10/2022 TO 31/03/2023 @ 45000/- + TAX | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 22 Nov 2022 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 365 | 0 | 07 Nov 2022 | SMITA ARTS | Sales Office & Sample Flat Signage Work - 1 No. | 3mm ACP with Vinyl Letters | No. | 14 | 216 | 3024 | 544.32 | 3568.32 | 2.5 | 14 | 3024 | 544.32 | 3568.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Nov 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 366 | 0 | 10 Nov 2022 | DREAM WORKS UNIVERSITY | BRANDING Event Expenses | Advertorial / Write Up / Articales | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 | FULL PAGE COLOUR PHOTO COVER PAGE + ONE FULL PAGE ADVT. ADVERTORIAL IN MAGAZINE | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 21 Nov 2022 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 367 | 0 | 17 Nov 2022 | WORLD WEB SOLUTIONS | ONLINE / DIGITAL Social / Digital Activity | Website Maintainence - | Month | 12 | 100000 | 1200000 | 216000 | 1416000 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | www.goelganga.com website monthly basis maintenance and updation. as on 01st april 2020 to 31st march 2021 @ Rs. 100000/- + tax per month | 0 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 22 Nov 2022 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 368 | 0 | 17 Nov 2022 | WORLD WEB SOLUTIONS | ONLINE / DIGITAL Social / Digital Activity | Website Maintainence - | Month | 16 | 40000 | 640000 | 115200 | 755200 | 0 | 12 | 480000 | 86400 | 566400 | 4 | 188800 | www.goelganga.com website maintenance monthly basis @ rs. 40000/- + tax as on 01st dec. 2022 to 31st march 2024 | 75 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 08 Dec 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 369 | 0 | 07 Dec 2022 | VAISHALI ELECTRICAL | A9 1101 Electrical Work | Electrical work lumpsum-SO | No. | 1 | 26000 | 26000 | 4680 | 30680 | 2.5 | 1 | 26000 | 4680 | 30680 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Dec 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 370 | 0 | 08 Dec 2022 | MARVEL ENTERPRISES | Safety Net fixing (Wing 1) | Safety Net Fixing- SO | Sq.Ft | 13400 | 2.7 | 36180 | 6512.4 | 42692.4 | 0 | 8392.8086 | 22660.58 | 4078.9 | 26739.48 | 5007.1914 | 15952.92 |  | 62.6329 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 370 | 0 | 08 Dec 2022 | MARVEL ENTERPRISES | Safety Net fixing (Wing 1) | Safety Net Removing- SO | Sq.Ft | 13400 | 1.35 | 18090 | 3256.2 | 21346.2 | 0 | 0 | 0 | 0 | 0 | 13400 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 371 | 0 | 10 Dec 2022 | RED TREE DESIGN STUDIO PRIVATE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 16 | 200000 | 3200000 | 576000 | 3776000 | 0 | 8 | 1600000 | 288000 | 1888000 | 8 | 1888000 | REAL RICH- Brand (Content Creation, conceptualization, 360 marketing planner and execution, Social + Digital online, offline ), ATUL GOEL Sir- Branding + Social Media Handles, Branding of Real Rich - of Goel Gnaga Deliverables as :- 2 Video per week, 3 short reels per week, 1 live per month, Deal Start as on 01st Dec. 2022 Rs. 200000/- + Tax | 50 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 21 Feb 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 21 Feb 2023
GANGA ASMI | 372 | 0 | 10 Dec 2022 | 99acres.com | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 600000 | 600000 | 108000 | 708000 | 0 | 0.5 | 300000 | 54000 | 354000 | 0.5 | 354000 | GANGA ASMI WAKAD PROJECT MARKETING WITH LEAD GENERATION ONLINE DIGITAL CAMPAIGN ACTIVITY THROUGH 99ACRES.COM FOR 6 MONTHS. COMMERCIAL RS. 6 LAC + GST (50% ADVANCE PAYMENT ) CPL- RS. 725 - RS. 775/- AND EXPECTED LEADS 825 + VALUE ADDITION AS 2 PROJECTS AT VALUE ADDITION FOR 30 DAYS EACH. DETAIL ATTACHED SHEET. | 50 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 13 Dec 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 373 | 2 | 13 Dec 2022 | MAHALAXMI FABRICATORS | Safety barrication on Slab | Safety Barrication | Kgs | 2415.89 | 12 | 28990.68 | 5218.32 | 34209 | 2.5 | 0 | 0 | 0 | 0 | 2415.89 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Dec 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 373 | 0 | 13 Dec 2022 | MAHALAXMI FABRICATORS | M.S. Ladder making | MS Square Pipe (L) | Kgs | 111.25 | 14 | 1557.5 | 280.36 | 1837.86 | 2.5 | 0 | 0 | 0 | 0 | 111.25 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 373 | 1 | 13 Dec 2022 | MAHALAXMI FABRICATORS | Technical Office, Store, Safety Induction Room making | Aluminium Sliding Window (M+L) | Sq.Ft | 0 | 260 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 21 Dec 2022 |  | No category | Cancelled | ADITYA CHOUGULE | 28 Dec 2022
GANGA ASMI | 373 | 1 | 13 Dec 2022 | MAHALAXMI FABRICATORS | Technical Office, Store, Safety Induction Room making | Meta colour Sheet Fixing BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 21 Dec 2022 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA CHOUGULE | 28 Dec 2022
GANGA ASMI | 373 | 1 | 13 Dec 2022 | MAHALAXMI FABRICATORS | Technical Office, Store, Safety Induction Room making | M.S Angle Fixing Work | Kgs | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 21 Dec 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 28 Dec 2022
GANGA ASMI | 373 | 1 | 13 Dec 2022 | MAHALAXMI FABRICATORS | Technical Office, Store, Safety Induction Room making | M.S Angle Fixing Work | Kgs | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 21 Dec 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 28 Dec 2022
GANGA ASMI | 373 | 1 | 13 Dec 2022 | MAHALAXMI FABRICATORS | Technical Office, Store, Safety Induction Room making | Door Shutter & Frame Fixing BC | No. | 0 | 800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 21 Dec 2022 |  | B.C. Internal Finishing Itmes | Cancelled | ADITYA CHOUGULE | 28 Dec 2022
GANGA ASMI | 373 | 0 | 13 Dec 2022 | MAHALAXMI FABRICATORS | M.S. Ladder making | M.S.Channel (L) | Kgs | 316.71 | 14 | 4433.94 | 798.1 | 5232.04 | 2.5 | 0 | 0 | 0 | 0 | 316.71 | 0 |  | 0 |  | Dushant Gore | Swapnil Erande | construction open | 21 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 373 | 1 | 13 Dec 2022 | MAHALAXMI FABRICATORS | Technical Office, Store, Safety Induction Room making | MS Pipe (L) | Kgs | 0 | 14 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 21 Dec 2022 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 28 Dec 2022
GANGA ASMI | 373 | 1 | 13 Dec 2022 | MAHALAXMI FABRICATORS | Technical Office, Store, Safety Induction Room making | Aluminium Sliding Window (m+l) - | No. | 0 | 260 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 21 Dec 2022 |  | MKT. Marketing Infrastructure | Cancelled | ADITYA CHOUGULE | 22 Dec 2022
GANGA ASMI | 374 | 0 | 15 Dec 2022 | PAPPU BAGELA | Sample Flat-Kitchen Otta | Granite Kitchen Otta - Mkt | R.Ft | 24.5 | 600 | 14700 | 0 | 14700 | 2.5 | 24.5 | 14700 | 0 | 14700 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Dec 2022 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 375 | 0 | 15 Dec 2022 | PAPPU BAGELA | Sample Flat-Kitchen Otta | Granite Vertical (M) | Sq.Ft | 27.417 | 110.7 | 3035.06 | 0 | 3035.06 | 0 | 27.417 | 3035.06 | 0 | 3035.06 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 375 | 0 | 15 Dec 2022 | PAPPU BAGELA | Sample Flat-Kitchen Otta | Facia Patti (M). | Sq.Ft | 1.2 | 110.7 | 132.84 | 0 | 132.84 | 0 | 1.2 | 132.84 | 0 | 132.84 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Dec 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 375 | 0 | 15 Dec 2022 | PAPPU BAGELA | Sample Flat-Kitchen Otta | Granite Umbra patti (M). | Sq.Ft | 2.389 | 110.7 | 264.46 | 0 | 264.46 | 0 | 2.389 | 264.46 | 0 | 264.46 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Dec 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 375 | 0 | 15 Dec 2022 | PAPPU BAGELA | Sample Flat-Kitchen Otta | Granite Skirting (M). | Sq.Ft | 8.042 | 110.7 | 890.25 | 0 | 890.25 | 0 | 8.042 | 890.25 | 0 | 890.25 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 22 Dec 2022 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 376 | 0 | 15 Dec 2022 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 38000 | 228000 | 41040 | 269040 | 0 | 5.4 | 205200 | 36936 | 242136 | 0.6 | 26904 | GANAG ASMI WAKAD PROJECT HOARDING DISPLAY CHARGES @ OPP. GANGA ASMI PROJECT FACING HINJEWADI SIZE AS 30 X 30 SQ FT. PERIOD AS ON 18/12/2022 TO 17/06/2022 @ 38000/- +TAX PER MONTH | 90 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 31 Dec 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 377 | 0 | 15 Dec 2022 | PUDHARI PUBLICATIONS PVT. LTD. | BRANDING Event Expenses | Advertisement Release- | No. | 1 | 300000 | 300000 | 15000 | 315000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 84TH ANNIVERSARY OF PUDHARI PUBLICATION- 400 SQ CM. COLOUR ADVT. ALL EDITION - MAHARASHTRA. COST RS. 3.00 LAC + TAX | 0 |  | TEJAS RAVERKAR |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 378 | 0 | 15 Dec 2022 | PUDHARI PUBLICATIONS PVT. LTD. | BRANDING Event Expenses | Advertisement Release- | No. | 1 | 300000 | 300000 | 15000 | 315000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | 84TH ANNIVERSARY OF PUDHARI PUBLICATION- 400 SQ CM. COLOUR DISPLAY ADVT. FOR ALL MAHARASHTRA EDITION COST RS. 3 LAC + TAX | 0 |  | TEJAS RAVERKAR |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 379 | 0 | 15 Dec 2022 | PUDHARI PUBLICATIONS PVT. LTD. | BRANDING Event Expenses | Advertisement Release- | No. | 1 | 300000 | 300000 | 15000 | 315000 | 0 | 1 | 300000 | 15000 | 315000 | 0 | 0 | 84TH ANNIVERSARY OF PUDHARI PUBLICATION- 400 SQ CM. COLOUR ADVT. ALL EDITION - MAHARASHTRA. COST RS. 3.00 LAC + TAX | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 31 Dec 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 380 | 0 | 17 Dec 2022 | IVIZ STUDIO | 3D View - 1 Job | 3 D Exterior | No. | 1 | 23750 | 23750 | 0 | 23750 | 0 | 1 | 23750 | 0 | 23750 | 0 | 0 | 3D Exterior- Podium View Cad Modeling,lighting,texturing,Rendering & Post production to Create final photo Realistic Hi-End images | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 380 | 0 | 17 Dec 2022 | IVIZ STUDIO | 3D View - 1 Job | 3 D Isometric View | No. | 1 | 7125 | 7125 | 0 | 7125 | 0 | 1 | 7125 | 0 | 7125 | 0 | 0 | 3D Isometric View- Flat 105 Cad Modeling,lighting,texturing,Rendering & Post production to Create final photo Realistic Hi-End images | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 380 | 0 | 17 Dec 2022 | IVIZ STUDIO | 3D View - 1 Job | 3D Floor Plan | No. | 1 | 19000 | 19000 | 0 | 19000 | 0 | 1 | 19000 | 0 | 19000 | 0 | 0 | 3D Floor Plan- Master Plan top Layout Cad Modeling,lighting,texturing,Rendering & Post production to Create final photo Realistic Hi-End images | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 380 | 0 | 17 Dec 2022 | IVIZ STUDIO | 3D View - 1 Job | 3D Floor Plan | No. | 1 | 14250 | 14250 | 0 | 14250 | 0 | 1 | 14250 | 0 | 14250 | 0 | 0 | 3D Floor Plan- Wing 2 Cad Modeling,lighting,texturing,Rendering & Post production to Create final photo Realistic Hi-End images | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 380 | 0 | 17 Dec 2022 | IVIZ STUDIO | 3D View - 1 Job | 3D Floor Plan | No. | 1 | 7125 | 7125 | 0 | 7125 | 0 | 1 | 7125 | 0 | 7125 | 0 | 0 | 3D Floor Plan - Flat 105 Cad Modeling,lighting,texturing,Rendering & Post production to Create final photo Realistic Hi-End images | 100 |  | Dushant Gore | Swapnil Erande | consultancy | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 381 | 0 | 19 Dec 2022 | DREAM WORKS UNIVERSITY | BRANDING Event Expenses | Advertisement Release- | No. | 6 | 12500 | 75000 | 13500 | 88500 | 0 | 6 | 75000 | 13500 | 88500 | 0 | 0 | ONE FULL PAGE COLOUR DISPLAY ADVERTISEMENT IN MAGAZINE - DREAMS PER SQUARE FEET E-MAGAZINE (ISSUE 3) + ONE FULL PAGE SIZE AS 8 INCH X 10.5 INCH (IN 6 EDITIONS) COST RS. 12500/- + TAX EVERY QUARTER (QUARTER ONE ISSUE MAGAZINE) TOTAL 6 QUARTER | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 31 Dec 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0.4334 | 8668 | 0 | 8668 | 0.5666 | 11332 |  | 43.34 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 0 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Dec 2022
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 382 | 1 | 24 Dec 2022 | RAHUL SHYAMKUMAR KHANDELWAL | Company Secretary | Company Secretary charges | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 26 Dec 2022 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 383 | 0 | 27 Dec 2022 | LOKMAT MEDIA PVT. LTD. | BRANDING Event Expenses | Event Expenses | No. | 1 | 50000 | 50000 | 9000 | 59000 | 0 | 1 | 50000 | 9000 | 59000 | 0 | 0 | LOKMAT MEDIA GROUP + JITO PUNE GROUP ORGANISED - FUN STREET AT GANGA DHAM CHOWK, BIBAVEWADI PUNE DTD. 11 DEC. 2022CO-SPONCERSHIP EVENT EXPENCES | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 31 Dec 2022 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 384 | 0 | 28 Dec 2022 | K B N FABRICATION | Technical Office, Store, Safety Induction Room making | MS Pipe (L) | Kgs | 1786.25 | 12 | 21435 | 0 | 21435 | 2.5 | 973.5063 | 11682.08 | 0 | 11682.08 | 812.7437 | 9752.92 |  | 54.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 384 | 0 | 28 Dec 2022 | K B N FABRICATION | Technical Office, Store, Safety Induction Room making | Door Shutter & Frame Fixing BC | No. | 15 | 800 | 12000 | 0 | 12000 | 2.5 | 5.0001 | 4000.08 | 0 | 4000.08 | 9.9999 | 7999.92 |  | 33.334 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 384 | 0 | 28 Dec 2022 | K B N FABRICATION | Technical Office, Store, Safety Induction Room making | M.S Angle Fixing Work | Kgs | 0 | 12 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 28 Dec 2022
GANGA ASMI | 384 | 0 | 28 Dec 2022 | K B N FABRICATION | Technical Office, Store, Safety Induction Room making | Aluminium Sliding Window (L) | Sq.Ft | 64 | 30 | 1920 | 0 | 1920 | 2.5 | 0 | 0 | 0 | 0 | 64 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 384 | 0 | 28 Dec 2022 | K B N FABRICATION | Technical Office, Store, Safety Induction Room making | Meta colour Sheet Fixing BC | Sq.Ft | 6200 | 5 | 31000 | 0 | 31000 | 2.5 | 1080.412 | 5402.06 | 0 | 5402.06 | 5119.588 | 25597.94 |  | 17.426 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 384 | 0 | 28 Dec 2022 | K B N FABRICATION | Technical Office, Store, Safety Induction Room making | M.S Angle Fixing Work | Kgs | 204.6 | 12 | 2455.2 | 0 | 2455.2 | 2.5 | 0 | 0 | 0 | 0 | 204.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 384 | 0 | 28 Dec 2022 | K B N FABRICATION | Technical Office, Store, Safety Induction Room making | M.S Angle Fixing Work | Kgs | 235.6 | 12 | 2827.2 | 0 | 2827.2 | 2.5 | 0 | 0 | 0 | 0 | 235.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 0 | 346942 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Dec 2022 |  | No category | Cancelled | DUSHANT.GORE | 29 Jul 2023
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 1 | 346942 | 62449.56 | 409391.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 1 | 346942 | 62449.56 | 409391.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 1 | 346942 | 62449.56 | 409391.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 1 | 346942 | 62449.56 | 409391.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 0 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 1 | 346942 | 62449.56 | 409391.56 | 0 | 0 |  | 100 |  | Dushant Gore | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 1 | 346942 | 62449.56 | 409391.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 1 | 346942 | 62449.56 | 409391.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 385 | 1 | 30 Dec 2022 | SBI GENERAL INSURANCE COMPANY LIMITED | Contractor All Risk (CAR) Policy Renewal | Insurance Policy | No. | 1 | 346942 | 346942 | 62449.56 | 409391.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 386 | 0 | 02 Jan 2023 | R.T.S. STEEL SERVICES | Experience Center Work | Experience Center | No. | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False Ceiling-Max other than light hole & condition,Alu. window-fixed glass 100%,Plywood-Max as per condition,Gypsum Board,Paint,Lights-100%,Wire/Cable-Maximum,DB-100%,Furniture-100%,TV-83"&63",LED Panel-100%,Lamp,Mat,Carpet-100%,Granite-as per condition. | 0 |  | ADITYA CHOUGULE |  | construction open | 02 Jan 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Jan 2023
GANGA ASMI | 386 | 0 | 02 Jan 2023 | R.T.S. STEEL SERVICES | Experience Center Work | Experience Center | No. | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Size of Experience center 40x70 ft, MS Vertical section-100% from Gr level, | 0 |  | ADITYA CHOUGULE |  | construction open | 02 Jan 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Jan 2023
GANGA ASMI | 386 | 0 | 02 Jan 2023 | R.T.S. STEEL SERVICES | Experience Center Work | Experience Center | No. | 1 | 10000000 | 10000000 | 1800000 | 11800000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | False Ceiling-Max other than light hole & condition,Alu. window-fixed glass 100%,Plywood-Max as per condition,Gypsum Board,Paint,Lights-100%,Wire/Cable-Maximum,DB-100%,Furniture-100%,TV-83"&63",LED Panel-100%,Lamp,Mat,Carpet-100%,Granite-as per condition. | 0 |  | ADITYA CHOUGULE |  | construction open | 02 Jan 2023 |  | No category | Un-Approved |  | 1900-01-01
GANGA ASMI | 386 | 0 | 02 Jan 2023 | R.T.S. STEEL SERVICES | Experience Center Work | Experience Center | No. | 0 | 10000000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | False Ceiling-Max other than light hole & condition,Alu. window-fixed glass 100%,Plywood-Max as per condition,Gypsum Board,Paint,Lights-100%,Wire/Cable-Maximum,DB-100%,Furniture-100%,TV-83"&63",LED Panel-100%,Lamp,Mat,Carpet-100%,Granite-as per condition. | 0 |  | ADITYA CHOUGULE |  | construction open | 02 Jan 2023 |  | No category | Cancelled | ADITYA CHOUGULE | 02 Jan 2023
GANGA ASMI | 387 | 0 | 07 Jan 2023 | LOKMAT MEDIA PVT. LTD. | MEDIA Event Expenses | Event Expenses | No. | 1 | 700000 | 700000 | 126000 | 826000 | 0 | 1 | 700000 | 126000 | 826000 | 0 | 0 | LOKMAT INFLUENCERS AWARDS COST RS. 7 LAC + TAX | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 10 Jan 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 387 | 2 | 07 Jan 2023 | LOKMAT MEDIA PVT. LTD. | MEDIA Event Expenses | Event Expenses | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 1 | 100000 | 18000 | 118000 | 0 | 0 | EVENT EXP. INFLUNCER WARDS EXP. COST RS. 1 LAC + TAX | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 10 Jan 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 387 | 1 | 07 Jan 2023 | LOKMAT MEDIA PVT. LTD. | MEDIA Event Expenses | Event Expenses | No. | 1 | 300000 | 300000 | 54000 | 354000 | 0 | 1 | 300000 | 54000 | 354000 | 0 | 0 | EVENT EXPENCES - DEEPTOTSAV BOOK ADVT.COST RS. 3 LAC + TAX | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 10 Jan 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 388 | 0 | 07 Jan 2023 | VIJAY MOHITE | Goel House Gym Work | RCC Work - DCH | No. | 1 | 190000 | 190000 | 0 | 190000 | 2.5 | 1 | 190000 | 0 | 190000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 388 | 0 | 07 Jan 2023 | VIJAY MOHITE | Goel House Gym Work | Swimming pool work | No. | 1 | 100000 | 100000 | 0 | 100000 | 2.5 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 388 | 0 | 07 Jan 2023 | VIJAY MOHITE | Goel House Gym Work | Swimming pool work | No. | 0 | 100000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT GORE | 09 Jan 2023
GANGA ASMI | 388 | 1 | 07 Jan 2023 | VIJAY MOHITE | GH Gym Room Bricks,Metal,sand,Rubble Shifting | Male Coolie | No. | 15 | 700 | 10500 | 0 | 10500 | 0 | 15 | 10500 | 0 | 10500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | SOC. M. Maintenace Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 388 | 0 | 07 Jan 2023 | VIJAY MOHITE | Goel House Gym Work | RCC Work - DCH | No. | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.368 | 1840 | 0 | 1840 | 0.632 | 3160 |  | 36.8 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.312 | 1560 | 0 | 1560 | 0.688 | 3440 |  | 31.2 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0.684 | 3420 | 0 | 3420 | 0.316 | 1580 |  | 68.4 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 389 | 0 | 09 Jan 2023 | KALYANRAO HANMANT KANE | GH Site Expenses | Site Expenses -SO | Month | 1 | 5000 | 5000 | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 16 Jan 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 390 | 1 | 11 Jan 2023 | VIKAS GARADE | Sales Office Grid Ceiling Repairing Work | Repairing work | Sq.Ft | 0 | 48.56 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Jan 2023 |  | 14 MISC WORK | Cancelled | MONALI CHAUDHAR | 27 Jun 2024
GANGA ASMI | 390 | 0 | 11 Jan 2023 | VIKAS GARADE | Marketing Expenses Diwali Decoration Lighting | Misc. Expenses-Mkt | No. | 1 | 8400 | 8400 | 0 | 8400 | 0 | 1 | 8400 | 0 | 8400 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Jan 2023 |  | MKT. Media | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 390 | 1 | 11 Jan 2023 | VIKAS GARADE | Sales Office Grid Ceiling Repairing Work | Labour Lumpsum | No. | 0 | 7000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 16 Jan 2023 |  | Land Cost | Cancelled | MONALI CHAUDHAR | 03 Jul 2024
GANGA ASMI | 391 | 0 | 12 Jan 2023 | RAJSAN ENTERPRISES | Goel House New Extension-roofing work | Tensile Canopy | Sq.Ft | 0 | 425 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 13 Jan 2023 |  | DEV. Swimming Pool | Cancelled | DUSHANT GORE | 13 Jan 2023
GANGA ASMI | 392 | 0 | 12 Jan 2023 | DAILY PRABHAT & POONA DAILY NEWS PVT. LTD. | BRANDING Event Expenses | Advertisement Release- | No. | 1 | 400000 | 400000 | 20000 | 420000 | 0 | 1 | 400000 | 20000 | 420000 | 0 | 0 | PRABHAT ANNIVERSARY DISPLAY ADVERTISEMENT FULL PAGE COLOUR SIZE AS 33 CM(W) X 50 CM(H) FRONT PAGE- FULL PAGE PUNE DISTRICT EDITION. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Feb 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 393 | 1 | 13 Jan 2023 | RAJSAN ENTERPRISES | Goel House Gym Work | Tensile Canopy | Sq.Ft | 80 | 425 | 34000 | 6120 | 40120 | 2.5 | 0 | 0 | 0 | 0 | 80 | 0 | FR 702 GSM with 12 years warranty. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 13 Jan 2023 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 393 | 0 | 13 Jan 2023 | RAJSAN ENTERPRISES | Goel House Gym Work | Tensile Canopy | Sq.Ft | 1610 | 425 | 684250 | 123165 | 807415 | 0 | 1520 | 646000 | 116280 | 762280 | 90 | 45135 |  | 94.4099 |  | Sanket Patil | Swapnil Erande | construction open | 13 Jan 2023 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 394 | 0 | 20 Jan 2023 | SPACE DESIGNERS SYNDICATE | Phase-A Wing-3 Architectural Consultancy | Architectural Consultancy | Sq.Ft | 152132 | 19 | 2890508 | 520291.44 | 3410799.44 | 0 | 0 | 0 | 0 | 0 | 152132 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 20 Jan 2023 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 394 | 0 | 20 Jan 2023 | SPACE DESIGNERS SYNDICATE | Phase-A PARKING AREA Architectural Consultancy | Architectural Consultancy | Sq.Ft | 204594 | 9.99 | 2043894.06 | 367900.94 | 2411795 | 0 | 0 | 0 | 0 | 0 | 204594 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 20 Jan 2023 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 394 | 0 | 20 Jan 2023 | SPACE DESIGNERS SYNDICATE | Phase-A COMM BLDG Architectural Consultancy | Architectural Consultancy | Sq.Ft | 1719 | 20 | 34380 | 6188.4 | 40568.4 | 0 | 0 | 0 | 0 | 0 | 1719 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 20 Jan 2023 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 394 | 0 | 20 Jan 2023 | SPACE DESIGNERS SYNDICATE | Phase-A Wing-1 Architectural Consultancy | Architectural Consultancy | Sq.Ft | 167053 | 17.8 | 2974011.15 | 535322 | 3509333.15 | 0 | 167052.5818 | 2974003.7 | 535320.66 | 3509324.36 | 0.4182 | 8.79 |  | 99.9997 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 20 Jan 2023 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 394 | 0 | 20 Jan 2023 | SPACE DESIGNERS SYNDICATE | Phase-A MAHADA Architectural Consultancy | Architectural Consultancy | Sq.Ft | 27728 | 19 | 526832 | 94829.76 | 621661.76 | 0 | 0 | 0 | 0 | 0 | 27728 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 20 Jan 2023 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 394 | 0 | 20 Jan 2023 | SPACE DESIGNERS SYNDICATE | Phase-A Wing-2 Architectural Consultancy | Architectural Consultancy | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 20 Jan 2023 |  | Consultacy Architectural | Cancelled | ADITYA CHOUGULE | 20 Jan 2023
GANGA ASMI | 394 | 0 | 20 Jan 2023 | SPACE DESIGNERS SYNDICATE | Phase-A Wing-2 Architectural Consultancy | Architectural Consultancy | Sq.Ft | 171601 | 19 | 3260419 | 586875.42 | 3847294.42 | 0 | 53999.7368 | 1025995 | 184679.1 | 1210674.1 | 117601.2632 | 2636620.32 |  | 31.4682 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 20 Jan 2023 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 394 | 0 | 20 Jan 2023 | SPACE DESIGNERS SYNDICATE | Phase-A Wing-1 Architectural Consultancy | Architectural Consultancy | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 20 Jan 2023 |  | Consultacy Architectural | Cancelled | ADITYA CHOUGULE | 20 Jan 2023
GANGA ASMI | 395 | 0 | 20 Jan 2023 | LOKMAT MEDIA PVT. LTD. | BRANDING Event Expenses | Advertisement Release- | No. | 1 | 250000 | 250000 | 12500 | 262500 | 0 | 1 | 250000 | 12500 | 262500 | 0 | 0 | 23RD LOKMAT- PUNE EDITION ANNIVERSARY ISSUE QUARTER PAGE 400 SQ CM COLOUR DISPLAY ADVT. IN HELLO PUNE & PCMC OR DISTRICT . COST RS. 250000/-+ TAX. | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 20 Jan 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 396 | 0 | 21 Jan 2023 | LEXICON BROADCASTING LLP | BRANDING Event Expenses | Advertisement Release- | No. | 1 | 95238 | 95238 | 4761.9 | 99999.9 | 0 | 1 | 95238 | 4761.9 | 99999.9 | 0 | 0 | DOUBLE SPREAD FULL PAGE COLOUR DISPLAY ADVT. - PUNE TIMES MIRROR COST RS. 1 LAC + GST- DIRECT DEAL | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Feb 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 397 | 0 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ISMB 150 (M) | Kgs | 1089.912 | 58 | 63214.9 | 11378.68 | 74593.58 | 0 | 1089.912 | 63214.9 | 11378.68 | 74593.58 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 397 | 0 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | MS Pipe (M) | Kgs | 960 | 72 | 69120 | 12441.6 | 81561.6 | 0 | 960 | 69120 | 12441.6 | 81561.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 397 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | MS Pipe (M) | Kgs | 103.907 | 72 | 7481.3 | 1346.64 | 8827.94 | 0 | 0 | 0 | 0 | 0 | 103.907 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 397 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ISMB 150 (M) | Kgs | 197.84 | 58 | 11474.72 | 2065.44 | 13540.16 | 0 | 0 | 0 | 0 | 0 | 197.84 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | MS Framing (L) | Sq.Ft | 562.602 | 10 | 5626.02 | 1012.68 | 6638.7 | 2.5 | 0 | 0 | 0 | 0 | 562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 0 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | Crane Charges - | No. | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Crane Charges - | No. | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 09 Feb 2023 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | MS Pipe (L) | Kgs | 356.81 | 25 | 8920.25 | 1605.64 | 10525.89 | 2.5 | 0 | 0 | 0 | 0 | 356.81 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Dismentalling work-UTI | No. | 1 | 300000 | 300000 | 54000 | 354000 | 2.5 | 1 | 300000 | 54000 | 354000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ISMC 150 (L) | Kgs | 651.45 | 25 | 16286.25 | 2931.52 | 19217.77 | 2.5 | 0 | 0 | 0 | 0 | 651.45 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 0 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | Fabrication Work (L) | Kgs | 2049.912 | 25.82 | 52933.85 | 9528.1 | 62461.95 | 2.5 | 2049.912 | 52933.85 | 9528.1 | 62461.95 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Dismentalling work-UTI | No. | 0 | 25000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 398 | 2 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | Fabrication Work (L) | Kgs | 301.74 | 25.82 | 7791.68 | 1402.5 | 9194.18 | 2.5 | 0 | 0 | 0 | 0 | 301.74 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 09 Feb 2023 |  | DEV. Ext Development | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 398 | 0 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | Lumpsum work- DCW | No. | 1 | 40000 | 40000 | 7200 | 47200 | 2.5 | 0.5 | 20000 | 3600 | 23600 | 0.5 | 23600 |  | 50 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 0 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ACP Cladding (M+L)- AIE | Sq.Ft | 3450 | 245 | 845250 | 152145 | 997395 | 2.5 | 3450 | 845250 | 152145 | 997395 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Dismentalling work-UTI | No. | 1 | 25000 | 25000 | 4500 | 29500 | 2.5 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | Fabrication work (L) | Sq.Ft | 1753 | 10 | 17530 | 3155.4 | 20685.4 | 2.5 | 0 | 0 | 0 | 0 | 1753 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | Fabrication work (M) | Kgs | 114.88 | 72 | 8271.36 | 1488.84 | 9760.2 | 0 | 0 | 0 | 0 | 0 | 114.88 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | MS Frame Refixing work | Sq.Ft | 562.6 | 10 | 5626 | 1012.68 | 6638.68 | 2.5 | 0 | 0 | 0 | 0 | 562.6 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 0 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ACP Cladding (M+L)- AIE | Sq.Ft | 0 | 220 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | skmishra | 20 Oct 2023
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | MS Frame Refixing work | Sq.Ft | 1553.002 | 10 | 15530.02 | 2795.4 | 18325.42 | 2.5 | 0 | 0 | 0 | 0 | 1553.002 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | Barricating Removing - UTI | Sq.Ft | 200 | 6 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 200 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Dismentalling work-UTI | No. | 0 | 200000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Dismentalling work-UTI | No. | 1 | 350000 | 350000 | 63000 | 413000 | 2.5 | 1 | 350000 | 63000 | 413000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 2 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | Scaffolding work | Sq.Ft | 386.97 | 10 | 3869.7 | 696.54 | 4566.24 | 2.5 | 0 | 0 | 0 | 0 | 386.97 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 09 Feb 2023 |  | B.C. RCC Superstructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 398 | 2 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ACP Cladding (M+L)- AIE | Sq.Ft | 180.667 | 245 | 44263.42 | 7967.42 | 52230.84 | 2.5 | 0 | 0 | 0 | 0 | 180.667 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 09 Feb 2023 |  | Admin. Indirect Expenses | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Crane Charges - | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 1 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Dismentalling work-UTI | No. | 1 | 200000 | 200000 | 36000 | 236000 | 2.5 | 1 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 0 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | Scaffolding work | Sq.Ft | 3612 | 10 | 36120 | 6501.6 | 42621.6 | 2.5 | 3612 | 36120 | 6501.6 | 42621.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 09 Feb 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | MS Frame Refixing work | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 13 Dec 2023
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | Frame Removing- MWB | Sq.Ft | 562.602 | 5 | 2813.01 | 506.34 | 3319.35 | 0 | 0 | 0 | 0 | 0 | 562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | MS Frame Refixing work | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 13 Dec 2023
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | MS Square Pipe (L) | Kgs | 441 | 23 | 10143 | 1825.74 | 11968.74 | 2.5 | 0 | 0 | 0 | 0 | 441 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 2 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ACP Sheet (L) | Sq.Ft | 368.305 | 50 | 18415.25 | 3314.74 | 21729.99 | 2.5 | 0 | 0 | 0 | 0 | 368.305 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 09 Feb 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Dismentalling work-UTI | No. | 0 | 350000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ACP sheet fixing rate diff. (M+L) | Sq.Ft | 368.3 | 72.5 | 26701.75 | 4806.32 | 31508.07 | 2.5 | 0 | 0 | 0 | 0 | 368.3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 398 | 1 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Sales Office, Sample Flat, Exp. Center Dismentaling | Dismentalling work-UTI | No. | 0 | 300000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 09 Feb 2023 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 28 Feb 2023
GANGA ASMI | 398 | 3 | 24 Jan 2023 | R.T.S. STEEL SERVICES | Media Frame Fabrication Work | Frame Removing- MWB | Sq.Ft | 1553 | 5 | 7765 | 1397.7 | 9162.7 | 2.5 | 0 | 0 | 0 | 0 | 1553 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 09 Feb 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 399 | 0 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 399 | 1 | 25 Jan 2023 | TALENTAX RENAISSANCE PRIVATE LIMITED | GST Consultancy | Professional Fees | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | ADITYA.CHOUGULE | construction open | 28 Mar 2023 |  | 03 CONSULTANCY | Approved | ADITYA.CHOUGULE | 1900-01-01
GANGA ASMI | 400 | 0 | 28 Jan 2023 | KALPATARU CREATIONS | MEDIA Event Expenses | Exhibition stall errection and decoratin | No. | 1 | 170625 | 170625 | 30712.5 | 201337.5 | 0 | 1 | 170625 | 30712.5 | 201337.5 | 0 | 0 | mega property exhibition - credai pune dtd. 16, 17 and 18th sept. 2022 stall fabrication, decoration, erracton, table, chair, display etc. charges | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 07 Feb 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 401 | 0 | 30 Jan 2023 | GOEL GANGA INDIA PRIVATE LIMITED | BRANDING Event Expenses | Exhibition Expencess - Mkt | No. | 1 | 512000 | 512000 | 92160 | 604160 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | MEGA PROPERTY EXHIBITION STALL CHARGES DTD. 16 TO 18 SEPT. 2022 @AGRICULTURE COLLEGE GROUND STALL SIZE AS 4 X 4 SQ MTR. ATY. 4 STALL | 0 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 07 Feb 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 402 | 0 | 01 Feb 2023 | JAIPRAKASH RAMRATAN BAJAARI | H.O. Admin Rental Charges | Rent Charges | Month | 12 | 166668 | 2000016 | 0 | 2000016 | 0 | 8 | 1333338.67 | 0 | 1333338.67 | 4 | 666677.33 |  | 66.6667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 402 | 0 | 01 Feb 2023 | JAIPRAKASH RAMRATAN BAJAARI | H.O. Admin Rental Charges | Rent Charges | Month | 12 | 166668 | 2000016 | 0 | 2000016 | 0 | 12 | 2000016 | 0 | 2000016 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 403 | 0 | 01 Feb 2023 | KAM FOUNDATION | Site Infra Septic Tank Cleaning | Septic Tank Cleaning services | No. | 20 | 1000 | 20000 | 3600 | 23600 | 0 | 20 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 403 | 1 | 01 Feb 2023 | KAM FOUNDATION | Site Infra Septic Tank Cleaning | Septic Tank Cleaning services | No. | 20 | 1500 | 30000 | 5400 | 35400 | 0 | 20 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 403 | 2 | 01 Feb 2023 | KAM FOUNDATION | Site Infra Septic Tank Cleaning | Septic Tank Cleaning services | No. | 40 | 1500 | 60000 | 10800 | 70800 | 0 | 3 | 4500 | 810 | 5310 | 37 | 65490 |  | 7.5 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Feb 2023 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0.8475 | 1000.05 | 180 | 1180.05 | 0.1525 | 212.35 |  | 84.75 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0.8475 | 1000.05 | 180 | 1180.05 | 0.1525 | 212.35 |  | 84.75 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0.8475 | 1000.05 | 180 | 1180.05 | 0.1525 | 212.35 |  | 84.75 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | H.O. Admin Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 0 | 1180 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 06 Feb 2023
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0.8475 | 1000.05 | 180 | 1180.05 | 0.1525 | 212.35 |  | 84.75 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 404 | 0 | 03 Feb 2023 | ANIKET ENTERPRISES | Sales Office - Tea Vending Machine Rent | Rent for Vending machine-AIE | Month | 1 | 1180 | 1180 | 212.4 | 1392.4 | 0 | 0.8475 | 1000.05 | 180 | 1180.05 | 0.1525 | 212.35 |  | 84.75 |  | DUSHANT GORE | Swapnil Erande | construction open | 06 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 405 | 0 | 04 Feb 2023 | K B N FABRICATION | Media Flex Fabrication Work for Media Work | Meta colour Sheet Fixing BC | Sq.Ft | 2634.62 | 5 | 13173.1 | 0 | 13173.1 | 2.5 | 391.891 | 1959.46 | 0 | 1959.46 | 2242.729 | 11213.65 |  | 14.8747 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 405 | 0 | 04 Feb 2023 | K B N FABRICATION | Media Flex Fabrication Work for Media Work | MS Pipe Fixing (L) | Kgs | 256 | 12 | 3072 | 0 | 3072 | 2.5 | 107.3152 | 1287.78 | 0 | 1287.78 | 148.6848 | 1784.22 |  | 41.92 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 405 | 0 | 04 Feb 2023 | K B N FABRICATION | Media Flex Fabrication Work for Media Work | Fabrication Work (L) | Kgs | 459 | 12 | 5508 | 0 | 5508 | 2.5 | 135.2122 | 1622.55 | 0 | 1622.55 | 323.7878 | 3885.45 |  | 29.458 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 405 | 0 | 04 Feb 2023 | K B N FABRICATION | Media Flex Fabrication Work for Media Work | MS Channel Fixing BCo | Kgs | 549.93 | 12 | 6599.16 | 1187.84 | 7787 | 2.5 | 129.602 | 1555.22 | 0 | 1555.22 | 420.328 | 6231.78 |  | 23.567 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 406 | 1 | 09 Feb 2023 | SUMIT SATISHCHANDRA SHARMA | Marketing Expenses | Marketing Operating Expenses | Month | 15 | 10000 | 150000 | 0 | 150000 | 0 | 5.6735 | 56735.33 | 0 | 56735.33 | 9.3265 | 93264.67 |  | 37.8233 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 21 Feb 2023 |  | MKT. Marketing Operating Expen | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 406 | 1 | 09 Feb 2023 | SUMIT SATISHCHANDRA SHARMA | Marketing Expenses | Marketing Operating Expenses | Month | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 21 Feb 2023 |  | MKT. Marketing Operating Expen | Cancelled | DUSHANT.GORE | 29 Jan 2024
GANGA ASMI | 406 | 0 | 09 Feb 2023 | SUMIT SATISHCHANDRA SHARMA | Marketing Expenses | Marketing Operating Expenses | Month | 12 | 10000 | 120000 | 0 | 120000 | 0 | 9.4216 | 94216.5 | 0 | 94216.5 | 2.5784 | 25783.5 |  | 78.5133 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | MKT. Marketing Operating Expen | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.9825 | 1965 | 353.7 | 2318.7 | 0.0175 | 41.3 |  | 98.25 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 360 | 2360 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0.95 | 1900 | 342 | 2242 | 0.05 | 118 |  | 95 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 407 | 0 | 09 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales office & Sample flat Housekeeping Material | Housekeeping (M) | Month | 1 | 2000 | 2000 | 360 | 2360 | 0 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 408 | 0 | 14 Feb 2023 | SAFIYA BHAIJAN SHAH | Sales office renovation - False Ceiling - 1 No. | False Ceiling (L)-BRE | Sq.Ft | 5806 | 20 | 116120 | 0 | 116120 | 2.5 | 5806 | 116120 | 0 | 116120 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 408 | 1 | 14 Feb 2023 | SAFIYA BHAIJAN SHAH | Sales office renovation - False Ceiling - 1 No. | False Ceiling (L)-BRE | Sq.Ft | 214 | 20 | 4280 | 0 | 4280 | 2.5 | 214 | 4280 | 0 | 4280 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 409 | 1 | 14 Feb 2023 | SAFIYA BHAIJAN SHAH | Sales office renovation - False Ceiling - 1 No. | False Ceiling (M)-BRE | Sq.Ft | 214 | 60 | 12840 | 0 | 12840 | 0 | 214 | 12840 | 0 | 12840 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 409 | 0 | 14 Feb 2023 | SAFIYA BHAIJAN SHAH | Sales office renovation - False Ceiling - 1 No. | False Ceiling (M)-BRE | Sq.Ft | 5806 | 60 | 348360 | 0 | 348360 | 0 | 5806 | 348360 | 0 | 348360 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 21 Feb 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 466.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 451.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 466.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 451.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 466.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 451.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 84 | 535.71 | 44999.98 | 8100 | 53099.98 | 0 | 84 | 44999.98 | 8100 | 53099.98 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 451.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 466.66 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 483.87 | 45000 | 8100 | 53100 | 0 | 57.8666 | 27999.97 | 5040 | 33039.97 | 35.1334 | 20060.03 |  | 62.2222 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 483.87 | 45000 | 8100 | 53100 | 0 | 92 | 44516.13 | 8012.9 | 52529.03 | 1 | 570.97 |  | 98.9247 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 451.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 483.87 | 45000 | 8100 | 53100 | 0 | 92.0002 | 44516.23 | 8012.92 | 52529.15 | 0.9998 | 570.85 |  | 98.9249 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 451.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 483.87 | 45000 | 8100 | 53100 | 0 | 92.0002 | 44516.23 | 8012.92 | 52529.15 | 0.9998 | 570.85 |  | 98.9249 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 451.61 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 483.87 | 45000 | 8100 | 53100 | 0 | 0 | 0 | 0 | 0 | 93 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 483.87 | 45000 | 8100 | 53100 | 0 | 89 | 43064.52 | 7751.62 | 50816.14 | 4 | 2283.86 |  | 95.6989 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 93 | 483.87 | 45000 | 8100 | 53100 | 0 | 86 | 41612.91 | 7490.32 | 49103.23 | 7 | 3996.78 |  | 92.4731 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 500 | 45000 | 8100 | 53100 | 0 | 86.0004 | 43000.2 | 7740.04 | 50740.24 | 3.9996 | 2359.76 |  | 95.556 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 500 | 45000 | 8100 | 53100 | 0 | 80 | 40000 | 7200 | 47200 | 10 | 5900 |  | 88.8889 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 0 | 500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Cancelled | DUSHANT GORE | 20 Feb 2023
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 500 | 45000 | 8100 | 53100 | 0 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 410 | 0 | 16 Feb 2023 | PROARCUS FACILITY MANAGEMENT INDIA PRIVATE LIMITED | Sales Office Housekeeping Work | Housekeeping Work- | Day | 90 | 500 | 45000 | 8100 | 53100 | 0 | 81 | 40500 | 7290 | 47790 | 9 | 5310 |  | 90 |  | DUSHANT GORE | Swapnil Erande | construction open | 20 Feb 2023 |  | 18. Maintenance & Repair Work | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 411 | 0 | 16 Feb 2023 | K B N FABRICATION | Safety barrication for Lift Shaft & Ducts | Safety Barrication | Kgs | 5133.41 | 12 | 61600.92 | 0 | 61600.92 | 2.5 | 2053.364 | 24640.37 | 0 | 24640.37 | 3080.046 | 36960.55 |  | 40 |  | DUSHANT GORE | Swapnil Erande | construction open | 16 Feb 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 412 | 0 | 17 Feb 2023 | SAKAL MEDIA PRIVATE LIMITED | Advertisement | Advertisement Release- | No. | 1 | 1714285 | 1714285 | 85714.26 | 1799999.26 | 0 | 0.8333 | 1428513.69 | 71425.68 | 1499939.37 | 0.1667 | 300059.89 |  | 83.33 |  | ADITYA CHOUGULE | tejas raverkar | construction open | 17 Feb 2023 |  | MKT. Media | Approved | tejas raverkar | 1900-01-01
GANGA ASMI | 412 | 0 | 17 Feb 2023 | SAKAL MEDIA PRIVATE LIMITED | Advertisement | Advertisement Release- | No. | 0 | 1710000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 17 Feb 2023 |  | MKT. Media | Cancelled | ADITYA CHOUGULE | 17 Feb 2023
GANGA ASMI | 413 | 0 | 18 Feb 2023 | SAKAL MEDIA PRIVATE LIMITED | BRANDING Event Expenses | Advertisement Release- | No. | 1 | 1428571 | 1428571 | 71428.56 | 1499999.56 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | HALF PAGE COLOUR DISPLAY ADVT. IN SAKAL- PUNE EDITION (SAKAL- TODAY ANY RHP) PUBLISH DTD. 18/02/2023 COST RS. 15 LAC (INCLUD. TAX) DIRECT DEAL PAYMENT AS PDC DTD. 05/03/2023 LESS TDS | 0 |  | TEJAS RAVERKAR |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Aluform Modification - Groove making | No. | 3000 | 6 | 18000 | 3240 | 21240 | 2.5 | 1488 | 8928 | 1607.04 | 10535.04 | 1512 | 10704.96 | Welding Machine, Gas cutter, Grinder, tools and tackles & all consumable Material in Contractors scope. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Labour Lumpsum | No. | 0 | 300000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Ext Development | Cancelled | ADITYA CHOUGULE | 20 Feb 2023
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Welding work for Aluform | R. Inch | 0 | 9.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | ADITYA CHOUGULE | 20 Feb 2023
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Labour Lumpsum | No. | 1 | 300000 | 300000 | 54000 | 354000 | 2.5 | 1 | 300000 | 54000 | 354000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Aluform Modification - Hole filling | No. | 3000 | 14 | 42000 | 7560 | 49560 | 2.5 | 565 | 7910 | 1423.8 | 9333.8 | 2435 | 40226.2 | Welding Machine, Gas cutter, Grinder, tools and tackles & all consumable Material in Contractors scope. | 27.9667 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Aluform Modification - Hole making | No. | 10000 | 6 | 60000 | 10800 | 70800 | 2.5 | 1879 | 11274 | 2029.32 | 13303.32 | 8121 | 57496.68 | Welding Machine, Gas cutter, Grinder, tools and tackles & all consumable Material in Contractors scope. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 414 | 1 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Welding work for Aluform | R. Inch | 150000 | 9.5 | 1425000 | 256500 | 1681500 | 2.5 | 149080 | 1416260 | 254926.82 | 1671186.82 | 920 | 10313.18 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 414 | 2 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Welding work for Aluform | R. Inch | 227664 | 9.5 | 2162808 | 389305.44 | 2552113.44 | 2.5 | 72353 | 687353.5 | 123723.64 | 811077.14 | 155311 | 1741036.3 |  | 93.9749 |  | DUSHANT.GORE | Chetan Jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Chetan Jewalikar | 1900-01-01
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Aluform Modification - Sorting work | Sq.m. | 4500 | 55 | 247500 | 44550 | 292050 | 2.5 | 1343.2259 | 73877.42 | 10030.94 | 83908.36 | 3156.7741 | 208141.64 | Welding Machine, Gas cutter, Grinder, tools and tackles & all consumable Material in Contractors scope. | 77.3841 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Cutting work for Aluform | R. Inch | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | ADITYA CHOUGULE | 20 Feb 2023
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Welding work for Aluform | R. Inch | 0 | 9.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | Admin. Direct Expenses | Cancelled | DUSHANT.GORE | 06 Jul 2023
GANGA ASMI | 414 | 2 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Cutting work for Aluform | R. Inch | 329537 | 2 | 659074 | 118633.32 | 777707.32 | 2.5 | 109751 | 219502 | 39510.36 | 259012.36 | 219786 | 518694.96 |  | 96.5376 |  | DUSHANT.GORE | Chetan Jewalikar | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Chetan Jewalikar | 1900-01-01
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Cutting work for Aluform | R. Inch | 30000 | 2 | 60000 | 10800 | 70800 | 2.5 | 28058 | 56116 | 10100.88 | 66216.88 | 1942 | 4583.12 | Welding Machine, Gas cutter, Grinder, tools and tackles & all consumable Material in Contractors scope. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 414 | 2 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Aluform Modification - Groove making | No. | 5000 | 6 | 30000 | 5400 | 35400 | 2.5 | 5000 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Chetan Jewalikar | construction open | 1900-01-01 |  | No category | Approved | Chetan Jewalikar | 1900-01-01
GANGA ASMI | 414 | 1 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Cutting work for Aluform | R. Inch | 350000 | 2 | 700000 | 126000 | 826000 | 2.5 | 270069 | 540138 | 97224.84 | 637362.84 | 79931 | 188637.16 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 414 | 2 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Aluform Modification - Hole making | No. | 40000 | 6 | 240000 | 43200 | 283200 | 2.5 | 40000 | 240000 | 43200 | 283200 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Chetan Jewalikar | construction open | 1900-01-01 |  | No category | Approved | Chetan Jewalikar | 1900-01-01
GANGA ASMI | 414 | 0 | 20 Feb 2023 | RAISING INFRATECH SERVICES | Aluform modification work | Welding work for Aluform | R. Inch | 30000 | 9.5 | 285000 | 51300 | 336300 | 2.5 | 29999.0526 | 284991 | 51298.38 | 336289.38 | 0.9474 | 10.62 | Welding Machine, Gas cutter, Grinder, tools and tackles & all consumable Material in Contractors scope. | 99.9968 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 2 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Work (L) | UGWT Labour | Ltrs | 570260.3 | 2.25 | 1283085.68 | 230955.42 | 1514041.1 | 2.5 | 233806.723 | 526065.13 | 94691.72 | 620756.85 | 336453.577 | 893284.25 | Quantity Differance Charges for UGWT RCC Work. | 41 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 2 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Work (L) | Concrete Work - UTI | Cu.Mtrs | 339.84 | 350 | 118944 | 21409.92 | 140353.92 | 2.5 | 263.904 | 92366.4 | 16625.96 | 108992.36 | 75.936 | 31361.56 |  | 77.6554 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 0 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Work (L) | UGWT Labour | Ltrs | 1024152.5 | 2.25 | 2304343.13 | 414781.76 | 2719124.89 | 2.5 | 419902.525 | 944780.68 | 170060.54 | 1114841.22 | 604249.975 | 1604283.66 |  | 41 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 4 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT & STP Plumbing Work | Plumbing work lumpsum- SOS | No. | 1 | 10000 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 01 Mar 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 2 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Work (L) | Reinforcement Work-Mkt | Kgs | 22797.45 | 8 | 182379.6 | 32828.32 | 215207.92 | 2.5 | 15000 | 120000 | 21600 | 141600 | 7797.45 | 73607.92 |  | 65.7968 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 2 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Work (L) | Shuttering Work-Mkt | Sq.m. | 1306.53 | 550 | 718591.5 | 129346.48 | 847937.98 | 2.5 | 933.6 | 513480 | 92426.4 | 605906.4 | 372.93 | 242031.58 |  | 71.4565 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 3 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Plum Concrete Above Raft (C60-R40) | Rate Diff.Plum Concrete | Cu.Mtrs | 633.6 | 100 | 63360 | 11404.8 | 74764.8 | 2.5 | 633.6 | 63360 | 11404.8 | 74764.8 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 1 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Plum Concrete Below Raft (C60-R40) | Plum Concrete | Cu.Mtrs | 129.6 | 300 | 38880 | 6998.4 | 45878.4 | 2.5 | 129.6 | 38880 | 6998.4 | 45878.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 2 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Work (L) | RCC Slab - Mkt | Sq.Ft | 2399.833 | 277.5 | 665953.66 | 119871.66 | 785825.32 | 2.5 | 0 | 0 | 0 | 0 | 2399.833 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 1 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Plum Concrete Above Raft (C60-R40) | Plum Concrete | Cu.Mtrs | 633.6 | 300 | 190080 | 34214.4 | 224294.4 | 2.5 | 450 | 135000 | 24300 | 159300 | 183.6 | 64994.4 |  | 71.0227 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 415 | 3 | 21 Feb 2023 | PURVA CONSTRUCTION | UGWT RCC Plum Concrete Below Raft (C60-R40) | Rate Diff.Plum Concrete | Cu.Mtrs | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 01 Mar 2023 |  | No category | Cancelled | DUSHANT.GORE | 14 Feb 2024
GANGA ASMI | 416 | 0 | 21 Feb 2023 | RAVINDRA AGARWAL | Aluform material shifting from GBT | Crane Charges - | No. | 8 | 7000 | 56000 | 0 | 56000 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 416 | 0 | 21 Feb 2023 | RAVINDRA AGARWAL | Aluform material shifting from GBT | Trailer vehical | Trips | 10 | 15000 | 150000 | 0 | 150000 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 417 | 0 | 21 Feb 2023 | ASHISH SHAMSUNDAR BHATTAD | Company Secretary | Company Secretary charges | Month | 0 | 183333.33 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 27 Feb 2023 |  | Admin. Indirect Expenses | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 418 | 1 | 21 Feb 2023 | TAJ SERVICES | BRANDING Event Expenses | T SHIRT / BAGS / PENS / DRESS - BRANDING | No. | 300 | 60 | 18000 | 3240 | 21240 | 0 | 300 | 18000 | 3240 | 21240 | 0 | 0 | GANGA ASMI MARKETING - SALES PROMOTION ( CHANEL PARTNER EVENT GIFT ITEM) METALIC PEN QTY. 300 @ 60/- + 18% GST EACH. | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 21 Feb 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 418 | 0 | 21 Feb 2023 | TAJ SERVICES | BRANDING Event Expenses | STAND (WWODEN / METALIC / M S STAND ETC/ ACRYLIC ETC.) | No. | 300 | 440 | 132000 | 23760 | 155760 | 0 | 300 | 132000 | 23760 | 155760 | 0 | 0 | GANGA ASMI MARKETING - SALES PROMOTION ( CHANEL PARTNER EVENT GIFT ITEM) WOODEN STAND FOR PEN QTY. 300 @ 440/- + 18% GST EACH | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 21 Feb 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 419 | 0 | 21 Feb 2023 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | PRINTING PRINTING-NO.-(NA) | LEAFLET PRINTING | No. | 2000 | 6 | 12000 | 1440 | 13440 | 0 | 2000 | 12000 | 1440 | 13440 | 0 | 0 | GANGA ASMI WAKAD (A-4 SIZE LEAFLET PRINT -CLOSE SIZE A-5 CENTRE FOLD, 350 GSM ART CARD PAPER F/B MULTICOLOUR PTINT QTY. 2000 @ 6/- + 12% GST | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 01 Mar 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 420 | 0 | 22 Feb 2023 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Misc. Development work | Poclain Charges - BC - | Hrs | 8 | 1800 | 14400 | 2592 | 16992 | 0 | 6 | 10800 | 1944 | 12744 | 2 | 4248 |  | 75 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 420 | 0 | 22 Feb 2023 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Misc. Development work | JCB Charges | Hrs | 30 | 900 | 27000 | 4860 | 31860 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 420 | 1 | 22 Feb 2023 | DRAUPADA EARTHMOVERS | Hiring of Machinery for Misc. Development work | Transport Charges | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 421 | 0 | 23 Feb 2023 | SPRINGTIME MAINTENANCE SERVICES PVT LTD | Head Office Expenses | Housekeeping -SM | Month | 0 | 4500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 23 Feb 2023 |  | SOC. M. Civil Work Maintenace | Cancelled | ADITYA CHOUGULE | 23 Feb 2023
GANGA ASMI | 421 | 1 | 23 Feb 2023 | SPRINGTIME MAINTENANCE SERVICES PVT LTD | Head Office Expenses | Housekeeping -SM | Month | 12 | 32500 | 390000 | 70200 | 460200 | 0 | 6.8169 | 221549.72 | 39878.96 | 261428.68 | 5.1831 | 198771.32 |  | 56.8075 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open | 23 Feb 2023 |  | SOC. M. Civil Work Maintenace | Approved | ADITYA.CHOUGULE | 23 Apr 2024
GANGA ASMI | 421 | 0 | 23 Feb 2023 | SPRINGTIME MAINTENANCE SERVICES PVT LTD | Head Office Expenses | Housekeeping -SM | Month | 12 | 32500 | 390000 | 70200 | 460200 | 0 | 11.6278 | 377904.26 | 68022.82 | 445927.08 | 0.3722 | 14272.92 |  | 96.8983 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 23 Feb 2023 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 422 | 1 | 23 Feb 2023 | SPRINGTIME MAINTENANCE SERVICES PVT LTD | Head Office Housekeeping | Housekeeping -SM | Month | 12 | 4500 | 54000 | 9720 | 63720 | 0 | 7 | 31499.87 | 5670 | 37169.87 | 5 | 26550.13 |  | 58.3333 |  | ADITYA.CHOUGULE | ADITYA.CHOUGULE | construction open | 25 Feb 2023 |  | SOC. M. Civil Work Maintenace | Approved | ADITYA.CHOUGULE | 23 Apr 2024
GANGA ASMI | 422 | 0 | 23 Feb 2023 | SPRINGTIME MAINTENANCE SERVICES PVT LTD | Head Office Housekeeping | Housekeeping -SM | Month | 12 | 4500 | 54000 | 9720 | 63720 | 0 | 12 | 54000 | 9720.04 | 63720.04 | 0 | -0.04 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Feb 2023 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 423 | 0 | 23 Feb 2023 | DREAMTREE EXPERIENCE | MEDIA Event Expenses | Event Expenses | No. | 1 | 340000 | 340000 | 61200 | 401200 | 0 | 1 | 340000 | 61200 | 401200 | 0 | 0 | GANGA ASMI (WAKAD) CHANEL PARTNER MEET DTD. 01ST MARCH 2023 @ TIP-TOP HOTEL WAKAD. VENUE BRANDING, EVENT SET UP, PRODUCTION , EXECUTION, TRANSPORT, COST RS. 340000/- + 18% GST | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 24 Feb 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 424 | 0 | 23 Feb 2023 | HOTEL TIPTOP INTERNATIONAL PVT LTD | MEDIA Event Expenses | Event Expenses | No. | 1 | 505000 | 505000 | 90900 | 595900 | 0 | 1 | 505000 | 90900 | 595900 | 0 | 0 | GANGA ASMI - WAKAD PROJECT SALES PROMOTION EVENT EXPENCES - CHANEL PARTNER MEET FOLLOWED BY DINNER DTD. 01ST MARCH 2023 @ HOTEL TIPTOP INTERNATION , WAKAD ( 3 VEG STARTERS, 03 CHEF CHOICE SALAD, 03 VEG MAIN COUSE, 01 DAL, 01 RICE PREPARATION, 03 ASSORTED INDIA BREADS, 02 DESSERT AND 01 ICE CREAM, PPC ETC. COST RS. 1500/- + 18% TAX AND COCKTAIL CHARGES - 03 VARIETIES OF CHAKANA, SODA, SOFT DRINKS, AND MOCKTAILS. ETC. COST RS. 400/- + 18% TAX (INCLUDING YOUR CROCKAGE CHARGES + LIQUOR LICENSE CHARGES RS. 30000/- + TAX. EXTRA. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 24 Feb 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 424 | 1 | 23 Feb 2023 | HOTEL TIPTOP INTERNATIONAL PVT LTD | MEDIA Event Expenses | Event Expenses | No. | 1 | 285000 | 285000 | 51300 | 336300 | 0 | 1 | 285000 | 51300 | 336300 | 0 | 0 | EXTRA DINNER WITH COCKTEL CHARGES RS. 1900/- EACH EXTRA PACKS QTY 150 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 24 Feb 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 425 | 0 | 24 Feb 2023 | SAIRAJ CONSTRUCTION | MS Staircase Tower | Dismentalling work-UTI | No. | 1 | 4000 | 4000 | 720 | 4720 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 425 | 0 | 24 Feb 2023 | SAIRAJ CONSTRUCTION | MS Staircase Tower | Erection Charges | No. | 1 | 6000 | 6000 | 1080 | 7080 | 2.5 | 0.8 | 4800 | 864 | 5664 | 0.2 | 1416 | Erection of MS Staircase from P1 to P6 floor. | 80 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 426 | 0 | 24 Feb 2023 | VINOD MANAGOBIND PRADHAN | Sales Office Carpentary & Plumbing work | Lumpsum work- DCW | No. | 1 | 10000 | 10000 | 0 | 10000 | 0 | 0.8 | 8000 | 0 | 8000 | 0.2 | 2000 | Floor Trap jali fixing, 3" PVC pipe line for urinal and kitchen line,4" PVC pipe line for SWR Sewage line,CP angle cock fixing,50mm PVC Pipe line work, Removing and Refixing of Old CP & Sanitory. | 80 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 427 | 0 | 24 Feb 2023 | K B N FABRICATION | Fabrication work for Misc. Items | Fabrication Work (L) | Kgs | 765 | 12 | 9180 | 0 | 9180 | 2.5 | 0 | 0 | 0 | 0 | 765 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 427 | 0 | 24 Feb 2023 | K B N FABRICATION | Fabrication work for Misc. Items | Meta colour Sheet Fixing BC | Sq.Ft | 765 | 5 | 3825 | 0 | 3825 | 2.5 | 0 | 0 | 0 | 0 | 765 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 427 | 0 | 24 Feb 2023 | K B N FABRICATION | Fabrication work for Misc. Items | Fabrication Work (L) | Kgs | 475 | 12 | 5700 | 0 | 5700 | 2.5 | 0 | 0 | 0 | 0 | 475 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 427 | 0 | 24 Feb 2023 | K B N FABRICATION | Fabrication work for Misc. Items | Fabrication Work (L) | Kgs | 697 | 12 | 8364 | 0 | 8364 | 2.5 | 0 | 0 | 0 | 0 | 697 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 427 | 0 | 24 Feb 2023 | K B N FABRICATION | Fabrication work for Misc. Items | Fabrication Work (L) | Kgs | 56 | 12 | 672 | 0 | 672 | 2.5 | 0 | 0 | 0 | 0 | 56 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 4 | 24 Feb 2023 | SATYAM TIWARI | Lab & Safety Equipments Site Safety Material | Fabrication work (L) No. | No. | 30 | 100 | 3000 | 0 | 3000 | 2.5 | 20 | 2000 | 0 | 2000 | 10 | 1000 |  | 66.6667 |  | DUSHANT GORE | chetan jewalikar | construction open | 01 Mar 2023 |  | B.C. Internal Finishing Itmes | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 428 | 5 | 24 Feb 2023 | SATYAM TIWARI | Temporary Structure DG Shed | Chainlink Fencing - UDG | Sq.Ft | 1756.03 | 5 | 8780.15 | 0 | 8780.15 | 2.5 | 0 | 0 | 0 | 0 | 1756.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | UTI. D.G.Set | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 2 | 24 Feb 2023 | SATYAM TIWARI | Fabrication work for labour colony in Wing01 - 1 Job | MS Door Fixing-UGB | No. | 15 | 600 | 9000 | 0 | 9000 | 2.5 | 13.0001 | 7800.06 | 0 | 7800.06 | 1.9999 | 1199.94 |  | 86.6673 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | UTI. Gas Bank | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 0 | 24 Feb 2023 | SATYAM TIWARI | Aluform Yard | Fabrication work (L) | Sq.Ft | 5170 | 13 | 67210 | 0 | 67210 | 2.5 | 5170 | 67210 | 0 | 67210 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 1 | 24 Feb 2023 | SATYAM TIWARI | Aluform modification & cutting yard work in wing 01 - 1 J | Fabrication work (L) | Sq.Ft | 762 | 13 | 9906 | 0 | 9906 | 2.5 | 740.0544 | 9620.71 | 0 | 9620.71 | 21.9456 | 285.29 |  | 97.12 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 3 | 24 Feb 2023 | SATYAM TIWARI | Site Office Site office at Wing 01 - P2 Parking area | Door Fixing (L) | No. | 5 | 600 | 3000 | 0 | 3000 | 2.5 | 2 | 1200 | 0 | 1200 | 3 | 1800 |  | 40 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 5 | 24 Feb 2023 | SATYAM TIWARI | Temporary Structure DG Shed | M.S. Angle 35x35x5-UGB | Kgs | 63.78 | 16 | 1020.48 | 0 | 1020.48 | 2.5 | 0 | 0 | 0 | 0 | 63.78 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | UTI. Gas Bank | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 5 | 24 Feb 2023 | SATYAM TIWARI | Temporary Structure DG Shed | Fabrication work (L) | Sq.Ft | 177.12 | 13 | 2302.56 | 0 | 2302.56 | 2.5 | 0 | 0 | 0 | 0 | 177.12 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 2 | 24 Feb 2023 | SATYAM TIWARI | Fabrication work for labour colony in Wing01 - 1 Job | Meta colour Sheet Fixing BC | Sq.Ft | 0 | 13 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 01 Mar 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA CHOUGULE | 14 Apr 2023
GANGA ASMI | 428 | 2 | 24 Feb 2023 | SATYAM TIWARI | Fabrication work for labour colony in Wing01 - 1 Job | Meta colour Sheet Fixing BC | Sq.Ft | 2641.65 | 13 | 34341.45 | 0 | 34341.45 | 2.5 | 2393.6519 | 31117.47 | 0 | 31117.47 | 247.9981 | 3223.98 |  | 90.612 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 428 | 3 | 24 Feb 2023 | SATYAM TIWARI | Site Office Site office at Wing 01 - P2 Parking area | Meta colour Sheet Fixing BC | Sq.Ft | 2000 | 13 | 26000 | 0 | 26000 | 2.5 | 1980 | 25740 | 0 | 25740 | 20 | 260 |  | 99 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 429 | 0 | 24 Feb 2023 | SATYAM TIWARI | Site Boundry Work Chainlink Barrication for Site & Green zon | Chain Link Fixing - Dld | Sq.Ft | 1476 | 17 | 25092 | 0 | 25092 | 2.5 | 0 | 0 | 0 | 0 | 1476 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 429 | 2 | 24 Feb 2023 | SATYAM TIWARI | Safety barrication on Slab | Safety Barrication | Kgs | 0 | 16 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 01 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA.CHOUGULE | 09 Aug 2023
GANGA ASMI | 429 | 3 | 24 Feb 2023 | SATYAM TIWARI | Safety barrication for Lift Shaft & Ducts | Fabrication Work (L) | Kgs | 933.8 | 16 | 14940.8 | 0 | 14940.8 | 2.5 | 933.8 | 14940.8 | 0 | 14940.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 429 | 1 | 24 Feb 2023 | SATYAM TIWARI | Aluform Yard | Fabrication work (L) | Sq.Ft | 1458 | 13 | 18954 | 0 | 18954 | 2.5 | 1458 | 18954 | 0 | 18954 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 429 | 2 | 24 Feb 2023 | SATYAM TIWARI | Safety barrication on Slab | Safety Barrication (L) | Sq.Ft | 19033.2 | 12 | 228398.4 | 0 | 228398.4 | 2.5 | 19033.2 | 228398.4 | 0 | 228398.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 429 | 2 | 24 Feb 2023 | SATYAM TIWARI | Aluform Store Making Work | MS Door (L) | No. | 3 | 600 | 1800 | 0 | 1800 | 2.5 | 3 | 1800 | 0 | 1800 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 429 | 2 | 24 Feb 2023 | SATYAM TIWARI | MS Racks Making For Steel Yard | M.S.Channel (L) | Kgs | 973 | 16 | 15568 | 0 | 15568 | 2.5 | 973 | 15568 | 0 | 15568 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 429 | 2 | 24 Feb 2023 | SATYAM TIWARI | Aluform Store Making Work | Meta colour Sheet Fixing BC | Sq.Ft | 1137.6 | 12 | 13651.2 | 0 | 13651.2 | 2.5 | 1137.6 | 13651.2 | 0 | 13651.2 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 429 | 2 | 24 Feb 2023 | SATYAM TIWARI | Aluform Store Making Work | Metacolur Sheet Removing - DER | Sq.Ft | 261 | 6 | 1566 | 0 | 1566 | 0 | 261 | 1566 | 0 | 1566 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Extrawork/Rework | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 430 | 0 | 24 Feb 2023 | DAMU RATHOD | Aluform material storage area civil work | Excavation & Concrete -DSP - | No. | 2 | 200 | 400 | 0 | 400 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 430 | 0 | 24 Feb 2023 | DAMU RATHOD | Aluform material storage area civil work | Excavation & Concrete -DSP - | No. | 15 | 200 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 431 | 0 | 25 Feb 2023 | DRAUPADA EARTHMOVERS | BC Soil excavation work (Wing 2 & 3 West side) | Excavation By Bucket (Shifting Outside) | Cu.Mtrs | 1317.28 | 150 | 197592 | 35566.56 | 233158.56 | 0 | 0 | 0 | 0 | 0 | 1317.28 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 432 | 0 | 27 Feb 2023 | REVANTI FURNITURE | Dismantling of Sample Flat at One Boat Club | Labour Lumpsum | No. | 1 | 175000 | 175000 | 0 | 175000 | 0 | 1 | 175000 | 27562.5 | 202562.5 | 0 | -27562.5 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 433 | 0 | 27 Feb 2023 | VENKAT RATHOD | Goel House Gym Work | Ghotai Plaster (Rate Diff.) | Sq.Ft | 700 | 5 | 3500 | 0 | 3500 | 10 | 700 | 3500 | 0 | 3500 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 01 Mar 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 434 | 0 | 27 Feb 2023 | SHIV BRAHAMA ENTERPRISES | Material shifting (From One Boat Club to Asmi) | Labour Lumpsum | No. | 1 | 78000 | 78000 | 14040 | 92040 | 0 | 1 | 78000 | 14040 | 92040 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 01 Mar 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing.2 Substructure RCC Work | Labour lumpsum | No. | 1 | 18250 | 18250 | 3285 | 21535 | 0 | 1 | 18250 | 3285 | 21535 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 0 | 34.9 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 281.1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 281.1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing.2 Substructure RCC Work | Steel Binding | Kgs | 25000 | 8 | 200000 | 36000 | 236000 | 0 | 25000 | 200000 | 36000 | 236000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing.2 Substructure RCC Work | Shuttering for Footing- BC | Sq.m. | 215.29 | 500 | 107645 | 19376.1 | 127021.1 | 0 | 215.29 | 107645 | 19376.1 | 127021.1 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing.2 Substructure RCC Work | Concreting Work | Cu.Mtrs | 56 | 300 | 16800 | 3024 | 19824 | 0 | 56 | 16800 | 3024 | 19824 | 0 | 0 | PCC (Plain cement concrete) with RMC with lift & lead upto 100 with proper shuttering, concreting with compaction, line level etc. Loading, shifting & unloading of estimated raw material from store to required place to be done by contractor. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 265 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Parking plinth beam | RCC Beam | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing.2 Substructure RCC Work | Concreting Work | Cu.Mtrs | 121 | 300 | 36300 | 6534 | 42834 | 0 | 121 | 36300 | 6534 | 42834 | 0 | 0 | PCC (Plain cement concrete) with RMC with lift & lead upto 100 with proper shuttering, concreting with compaction, line level etc. Loading, shifting & unloading of estimated raw material from store to required place to be done by contractor. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 265 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing.2 Substructure RCC Work | Departmental Labour | No. | 50 | 600 | 30000 | 5400 | 35400 | 0 | 50 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Parking PCC Work | PCC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 435 | 0 | 28 Feb 2023 | INDRA ASSOCIATES | Wing 2 - Parking Footing & Column | Footing & Column | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 30 May 2023
GANGA ASMI | 436 | 0 | 01 Mar 2023 | MEDIASSET HOLDINGS | MEDIA Event Expenses | Event Expenses | No. | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 | 14TH REALTY+ CONCLAVE AND EXCELLENCE AWARDS 2023 CONCLAVE PARTNER ( REALTY PLUS MAGAZINE) ON GROUND EVENT | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 17 Mar 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 03 Apr 2023
GANGA ASMI | 437 | 0 | 01 Mar 2023 | AMPLE IMPRESSIONS | PRINTING PRINTING-NO.-(NA) | print | No. | 2000 | 39 | 78000 | 9360 | 87360 | 0 | 2000 | 78000 | 9360 | 87360 | 0 | 0 | GANAG ASMI WAKAD PROJECT BROCHURE PRINT FOR SALES PROMOTION MARKETING BRANDING QTY. 2000 X @ 39/- + 12% TAX 350 GSM OPP ART CARD PAPER CLOSE SIZEAS A-4, BOTH SIDE PRINT FRONT/ BACK LAMMINATION WITH 170 GSM 7 INSERT | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 16 Mar 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 438 | 0 | 23 Feb 2023 | LOKMAT MEDIA PVT. LTD. | MEDIA Event Expenses | Event Expenses | No. | 1 | 250000 | 250000 | 45000 | 295000 | 0 | 1 | 250000 | 45000 | 295000 | 0 | 0 | LOKMAT - MEDIA GROUP- ORGANISED LOKMAT MAHAMARATHON AT BALEWADI STADIUM PUNE. EVENT SPONCERSHIP COST RS. 250000 + 18% TAX | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 16 Mar 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 439 | 0 | 02 Mar 2023 | AAKASH CONSTRUCTION | Sales Toilet extension Civil Works | Sand face Plaster- BC | Sq.Ft | 188 | 15 | 2820 | 0 | 2820 | 2.5 | 0 | 0 | 0 | 0 | 188 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 439 | 0 | 02 Mar 2023 | AAKASH CONSTRUCTION | Sales Toilet extension Civil Works | 6" Brick Work | Sq.Ft | 166 | 15 | 2490 | 0 | 2490 | 2.5 | 0 | 0 | 0 | 0 | 166 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 12 MASONARY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 439 | 0 | 02 Mar 2023 | AAKASH CONSTRUCTION | Sales Toilet extension Civil Works | Male Coolie | No. | 2 | 550 | 1100 | 0 | 1100 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 440 | 0 | 02 Mar 2023 | R.T.S. STEEL SERVICES | Sales Office Front elevation MS & ACP work | ACP Panel work | No. | 1 | 136392 | 136392 | 24550.56 | 160942.56 | 2.5 | 1 | 136392 | 24550.56 | 160942.56 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 441 | 3 | 03 Mar 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Eco Vinyal with Lamination | Sq.Ft | 996 | 105 | 104580 | 18824.4 | 123404.4 | 0 | 896.6367 | 94146.85 | 16946.42 | 111093.27 | 99.3633 | 12311.13 | GANGA ASMI WAKAD PROJECT SITE BRANDING WITH SALES PROMOTION ECO VINYAL PRINT ON 5 MM FOAM SHEET BOARD WITH PASTING, LAMINATION TOTAL AREA AS 996 SQ FT. RS. 105/- PER SQ FT. | 90.0238 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 19 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 441 | 4 | 03 Mar 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 3420 | 10 | 34200 | 6156 | 40356 | 0 | 3420 | 34200 | 6156 | 40356 | 0 | 0 | GANGA ASMI WAKAD HOARDING FLEX PRINTING WITH MOUNTING AT NEAR PROJECT SITE | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 19 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 441 | 1 | 03 Mar 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Black Back Flex | Sq.Ft | 2774 | 21 | 58254 | 10485.72 | 68739.72 | 0 | 2774 | 58254 | 10485.78 | 68739.78 | 0 | -0.06 | GANGA ASMI WAKAD PROJECT SITE - SAMPLE FLAT BRANDING STAR BLACK BACK FLEX PRINT WITH PAST ON MS FRAME | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 19 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 441 | 0 | 03 Mar 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Black Back Flex | Sq.Ft | 4190 | 21 | 87990 | 15838.2 | 103828.2 | 0 | 4190 | 87990 | 15838.14 | 103828.14 | 0 | 0.06 | GANGA ASMI WAKAD PROJECT SITE BRANDING FOR MARKETING WITH SALES PROMOTION STAR BLACK BACK FLEX PRINT WITH PAST ON MS FRAME. COST RS. 21/- PER SQ FT. TOTAL 9512 SQ FT AREA. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 19 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 441 | 2 | 03 Mar 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Black Back Flex | Sq.Ft | 2548 | 21 | 53508 | 9631.44 | 63139.44 | 0 | 2548 | 53508 | 9631.5 | 63139.5 | 0 | -0.06 | GANAG ASMI WAKAD PROJECT SITE- SALES OFFICE BRABNDING STAR BLACK BACK FLEX PRINT WITH PAST ON MS FRAME TOTAL 2548 SQ FT AREA RS. 21/- PER SQ FT. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 19 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 441 | 5 | 03 Mar 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Black Back Flex | Sq.Ft | 800 | 21 | 16800 | 3024 | 19824 | 0 | 800 | 16800 | 3024 | 19824 | 0 | 0 | GANGA ASMI WAKAD PROJECT MAIN ENTRANCE ARCH DISPLAY STAR FLEX PRINT WITH PAST ON MS FRAME AT SITESIZE AS 20 X 3 SQ FT. X 8 FRAMES FOR LEFT AND RIGHT SIDE , TOP SIDE SIZE AS 40 X2 SQ FT. QTY. 4 | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 19 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 442 | 0 | 03 Mar 2023 | RED TREE DESIGN STUDIO PRIVATE LIMITED | ONLINE / DIGITAL Social / Digital Activity | FaceBook Paid Campaign | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | GANGA ASMI WAKAD PROJECT SALES PROMOTION WITH MARKETING THROUGH ONLINE SOCIAL MEDIA - FACEBOOK PAID CAMPAIGN - REALRICH CAMPAIGN FOR THE MONTH OF MARCH 2023 COST RS. 25000/- + TAX | 0 |  | TEJAS RAVERKAR |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 443 | 0 | 04 Mar 2023 | PRITESH SURESH BANSAL | Professional Fees | Internal Audit Fees -AIE- | Month | 12 | 40000 | 480000 | 0 | 480000 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 04 Mar 2023 |  | Admin. Indirect Expenses | Un-Approved |  | 1900-01-01
GANGA ASMI | 444 | 0 | 13 Mar 2023 | ASSOCIATED POOLS | Goel House Gym Work | Installation Charges | No. | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | Sanket Patil | Swapnil Erande | construction open | 25 Apr 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 445 | 0 | 13 Mar 2023 | RAJSAN ENTERPRISES | Goel House Gym Work | Repairing work | Sq.Ft | 1670 | 24 | 40080 | 7214.4 | 47294.4 | 0 | 1520 | 36480 | 6566.4 | 43046.4 | 150 | 4248 |  | 91.018 |  | Sanket Patil | chetan jewalikar | construction open | 22 May 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Piling Work 300mm Dia. - BC | Mtrs | 34.8 | 2000 | 69600 | 12528 | 82128 | 2.5 | 0 | 0 | 0 | 0 | 34.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Piling Work 300mm Dia. - BC | Mtrs | 0 | 1800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 23 Apr 2024 |  | B.C. RCC Substructure | Cancelled | DUSHANT.GORE | 26 Apr 2024
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Chiseling work for Piling - DEn | Hrs | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 23 Apr 2024 |  | DEV. Entrance Gate | Cancelled | ADITYA.CHOUGULE | 23 Apr 2024
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Piling Work 300mm Dia. - BC | Mtrs | 429.2 | 1800 | 772560 | 139060.8 | 911620.8 | 2.5 | 0 | 0 | 0 | 0 | 429.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Piling work 400 mm. dia. SOS | Mtrs | 0 | 800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 23 Apr 2024 |  | S OH Infrastructure | Cancelled | ADITYA.CHOUGULE | 23 Apr 2024
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Reinforcement for Piling-BC | Mtrs | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 23 Apr 2024 |  | B.C. RCC Substructure | Cancelled | ADITYA.CHOUGULE | 23 Apr 2024
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Pile Concreting Work | Mtrs | 464 | 200 | 92800 | 16704 | 109504 | 2.5 | 0 | 0 | 0 | 0 | 464 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | 300mm Dia Casing Pipe | Kgs | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 23 Apr 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 23 Apr 2024
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Reinforcement for Piling-BC | Mtrs | 464 | 200 | 92800 | 16704 | 109504 | 2.5 | 0 | 0 | 0 | 0 | 464 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | 300mm Dia Casing Pipe | Kgs | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 23 Apr 2024 |  | No category | Cancelled | DUSHANT.GORE | 26 Apr 2024
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Mobilisation - DEn | No. | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Apr 2024 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Mobilisation - DEn | No. | 0 | 35000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 23 Apr 2024 |  | DEV. Entrance Gate | Cancelled | ADITYA.CHOUGULE | 23 Apr 2024
GANGA ASMI | 446 | 0 | 13 Mar 2023 | MASKE PILE FOUNDATION | Compound Wall Pile Foundation | Pile Concreting Work | Mtrs | 0 | 100 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 23 Apr 2024 |  | 02 RCC WORK | Cancelled | ADITYA.CHOUGULE | 23 Apr 2024
GANGA ASMI | 447 | 0 | 14 Mar 2023 | BAJRANG ENTERPRISES | Extra Work | Labour Lumpsum | No. | 0 | 265050 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 15 Mar 2023 |  | Land Cost | Cancelled | DUSHANT GORE | 15 Mar 2023
GANGA ASMI | 448 | 0 | 15 Mar 2023 | ASSOCIATED POOLS | Goel House Rennovation Supply & Installation of SKIMMER Ladd | S.S Ladders DSP | No. | 1 | 16000 | 16000 | 2880 | 18880 | 0 | 1 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 449 | 0 | 15 Mar 2023 | AARYA HOME ARTS | Extra Work | Labour Lumpsum | No. | 1 | 265050 | 265050 | 47709 | 312759 | 2.5 | 1 | 265050 | 47709 | 312759 | 0 | 0 |  | 100 |  | DUSHANT GORE | DUSHANT GORE | construction open | 15 Mar 2023 |  | Land Cost | Approved | DUSHANT GORE | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | Reinforcement for Piling-DSP | Mtrs | 201.6 | 100 | 20160 | 3628.8 | 23788.8 | 2.5 | 173.875 | 17387.5 | 3129.76 | 20517.26 | 27.725 | 3271.54 |  | 86.2475 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | Reinforcement for Piling-DSP | Mtrs | 78.4 | 100 | 7840 | 1411.2 | 9251.2 | 2.5 | 67.17 | 6717 | 1209.06 | 7926.06 | 11.23 | 1325.14 |  | 85.676 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Swimming Pool | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | MS Liner 6mm (L) | Kgs | 13968 | 35 | 488880 | 87998.4 | 576878.4 | 2.5 | 13506.11 | 472713.85 | 85088.5 | 557802.35 | 461.89 | 19076.05 |  | 96.6932 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 1 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing-1 Parking Non Tower Area Pile Breaking | Pile Breaking | Hrs | 50.3 | 500 | 25150 | 4527 | 29677 | 0 | 0 | 0 | 0 | 0 | 50.3 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 1900-01-01 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | MS Liner 6mm (L) | Kgs | 5432 | 35 | 190120 | 34221.6 | 224341.6 | 2.5 | 3259.2 | 114072 | 20532.96 | 134604.96 | 2172.8 | 89736.64 |  | 60 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | Pile Concreting work 600mm dia.- | Mtrs | 201.6 | 100 | 20160 | 3628.8 | 23788.8 | 2.5 | 201.595 | 20159.5 | 3628.72 | 23788.22 | 0.005 | 0.58 |  | 99.9975 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | Chiseling work for Piling - DEn | Hrs | 12 | 500 | 6000 | 1080 | 7080 | 0 | 12 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | MS Liner 5mm (L) | Kgs | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Cancelled | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 201.6 | 1000 | 201600 | 36288 | 237888 | 2.5 | 152.09 | 152090 | 27376.2 | 179466.2 | 49.51 | 58421.8 |  | 75.4415 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 78.4 | 1000 | 78400 | 14112 | 92512 | 2.5 | 55.18 | 55180 | 9932.4 | 65112.4 | 23.22 | 27399.6 |  | 70.3827 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | Chiseling work for Piling - DEn | Hrs | 13 | 500 | 6500 | 1170 | 7670 | 0 | 13 | 6500 | 1170 | 7670 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | Transport Charges | No. | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | MS Liner 5mm | Kgs | 0 | 105 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | Pile Concreting work 600mm dia.- | Mtrs | 78.4 | 100 | 7840 | 1411.2 | 9251.2 | 2.5 | 67.245 | 6724.5 | 1210.42 | 7934.92 | 11.155 | 1316.28 |  | 85.7717 |  | DUSHANT GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | MS Liner 5mm | Kgs | 0 | 105 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 04 Apr 2023
GANGA ASMI | 450 | 0 | 16 Mar 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | MS Liner 5mm (L) | Kgs | 0 | 35 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Cancelled | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 1 | 16000 | 0 | 16000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 1 | 16000 | 0 | 16000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 1 | 16000 | 0 | 16000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 1 | 16000 | 0 | 16000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 1 | 16000 | 0 | 16000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 451 | 0 | 17 Mar 2023 | GAYATRI KULKARNI | Site Staff Rent charges | Rent Charges- SO | Month | 1 | 16000 | 16000 | 0 | 16000 | 0 | 1 | 16000 | 0 | 16000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 17 Mar 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 452 | 3 | 17 Mar 2023 | MARK NEONS | Advertisement | Transport Charges- Med. | No. | 1 | 1800 | 1800 | 324 | 2124 | 0 | 1 | 1800 | 324 | 2124 | 0 | 0 | GANGA ASMI LOGO- TRANSPORT, INSTALLATION, FIXING CHARGES COST RS. 1800/- | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 29 Mar 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 452 | 0 | 17 Mar 2023 | MARK NEONS | Advertisement | ACRYLIC LETTER WORK | No. | 1 | 13500 | 13500 | 2430 | 15930 | 0 | 1 | 13500 | 2430 | 15930 | 0 | 0 | 3D ACRYLIC LETTERS WITH CAST GRADE ACRYLIC WITH 60MM DEEP EDGES WITH AL CLAMPS FOR FITTING ETC. "GANGA ASMI" @162/- PER SQ.INCHES | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 29 Mar 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 452 | 4 | 17 Mar 2023 | MARK NEONS | Advertisement | ACRYLIC LETTER WORK | No. | 1 | 9500 | 9500 | 1710 | 11210 | 0 | 1 | 9500 | 1710 | 11210 | 0 | 0 | GOEL GANGA GROUP ACRYLIC LETTER CUTTING INSTALLATION WITH VINYAL PRINTING , CUTTING, PASTING COST RS. 9500/- + TRANSPORT, LABOUR, INSTALLATION, FIXING CHARGES COST RS. 4500/-+ TAX | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 29 Mar 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 452 | 2 | 17 Mar 2023 | MARK NEONS | Advertisement | ACRYLIC LETTER WORK | No. | 1 | 18000 | 18000 | 3240 | 21240 | 0 | 1 | 18000 | 3240 | 21240 | 0 | 0 | GANGA ASMI LOGO- 2) 2D ACRYLIC AL PROFILE LETTERS WITH CAST GRADE ACRYLIC WITH 60MM DEEP EDGES WITH 1.5 WATT 35MD LED MODULES RAINPROOF DRIVER WITH INTERNAL WIRING IN FINOLEX MAKE LT CABLES COST RS. 18000/- + TRANSPORT, INSTALLATION, FIXING CHARGES COST RS. 1800/- | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 29 Mar 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 452 | 5 | 17 Mar 2023 | MARK NEONS | Advertisement | Transport Charges- Med. | No. | 1 | 4500 | 4500 | 810 | 5310 | 0 | 0.0889 | 400.05 | 72 | 472.05 | 0.9111 | 4837.95 | GOEL GANGA GROUP ACRYLIC LETTER CUTTING INSTALLATION WITH VINYAL PRINTING , CUTTING, PASTING TRANSPORT, LABOUR, INSTALLATION, FIXING CHARGES COST RS. 4500/-+ TAX | 8.89 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 29 Mar 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 452 | 1 | 17 Mar 2023 | MARK NEONS | Advertisement | Transport Charges- Med. | No. | 1 | 1800 | 1800 | 324 | 2124 | 0 | 1 | 1800 | 324 | 2124 | 0 | 0 | "GANGA ASMI" ACRYLIC LETTERS CUTTING, INSTALLATION WITH FIXING, CHARGES RS. 2800/- | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 29 Mar 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 453 | 1 | 17 Mar 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 65000 | 195000 | 35100 | 230100 | 0 | 2.5 | 162500.03 | 29250 | 191750.03 | 0.5 | 38349.97 | GANGA ASMI -WAKAD PROJECT OUT DOOR MEDIA HOSRDING DISPLAY CHARGES AT BHUMKAR CHOWK, NEAR OLYMPIA PROJECT, OPP. MAMTA NAGAR, WAKAD, FACING HINJEWADI IT PARK SIZE AS 60 X 30 SQ FT. COST RS. 65000/- +TAX PER MONTH | 83.3333 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 21 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 453 | 0 | 17 Mar 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 50000 | 150000 | 27000 | 177000 | 0 | 2.5 | 125000.03 | 22500.02 | 147500.05 | 0.5 | 29499.96 | GANGA ASMI -WAKAD PROJECT OUT DOOR MEDIA HOSRDING DISPLAY CHARGES AT HINJEWADI IT PARK ROAD, NEAR BANK OF MAHARASHTRA FACING WAKAD SIZE AS 35 X 42 SQ FT. PERIOD AS ON 21/03/2023TO 20/06/2023 COST RS. 50000/-+ TAX PER MONTH | 83.3333 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 21 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 454 | 1 | 17 Mar 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 75000 | 225000 | 40500 | 265500 | 0 | 3 | 225000 | 40499.98 | 265499.98 | 0 | 0.02 | 2) GANGA ASMI WAKAD PROJECT OUT DOOR HOARDING DISPLAY CHARGES AT HINJEWADI NEAR SHEL PETROL PUMP TRAFFIC FROM HINJEWADI TO PUNE SIZE AS 60 X 30 SQ FT. COST RS. 75000/- + TAX LIT PERIOD AS ON 21/03/2023 TO 20/06/2023 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 13 Apr 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 454 | 2 | 17 Mar 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 80000 | 240000 | 43200 | 283200 | 0 | 3 | 240000 | 43199.98 | 283199.98 | 0 | 0.02 | 3) GANGA ASMI WAKAD PROJECT OUT DOOR HOARDING DISPLAY CHARGES AT HINJEWADI BHUMKAR CHOWK ROAD, NEAR ORRITEL HOTEL, TRAFFIC FROM HINJEWADI TO BHUMKAR CHOWK SIZE AS 60 X 42 SQ FT. COST RS. 80000/- + TAX NON LIT PERIOD AS ON 21/03/2023 TO 20/06/2023 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 13 Apr 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 454 | 0 | 17 Mar 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 60000 | 180000 | 32400 | 212400 | 0 | 3 | 180000 | 32399.98 | 212399.98 | 0 | 0.02 | GANAG ASMI WAKAD PROJECT OUT DOOR HOARDING DISPLAY CHARGES AT PILPALE NILAKH NEAR KOLTE PATIL 24K PROJECT, TRAFFIC FROM WAKAD TO PUNE SIZE AS 30 X 30 SQ FT. COST RS. 60000/- + TAX NON LIT PERIOD AS ON 21/03/2023 TO 20/06/2023 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 13 Apr 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 454 | 3 | 17 Mar 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 20000 | 60000 | 10800 | 70800 | 0 | 3 | 60000 | 10800 | 70800 | 0 | 0 | 4) GANGA ASMI WAKAD PROJECT OUT DOOR HOARDING DISPLAY CHARGES AT MAHALUNGE AT GODREJ PROJECT ENTRANCE TRAFFIC FROM MAHALUNGE TO GODREJ SIZE AS 30 X 30 SQ FT. COST RS. 20000/- + TAX NON LIT PERIOD AS ON 21/03/2023 TO 20/06/2023 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 13 Apr 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 454 | 4 | 17 Mar 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 50000 | 150000 | 27000 | 177000 | 0 | 3 | 150000 | 27000.02 | 177000.02 | 0 | -0.02 | 5) GANGA ASMI WAKAD PROJECT OUT DOOR HOARDING DISPLAY CHARGES AT MAHALUNGE AT GODREJ PROJECT ENTRANCE TRAFFIC FROM GODREJ TO MAHALUNGE SIZE AS 40 X 42 SQ FT. COST RS. 50000/- + TAX NON LIT PERIOD AS ON 21/03/2023 TO 20/06/2023 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 13 Apr 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 454 | 6 | 17 Mar 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 40000 | 120000 | 21600 | 141600 | 0 | 3 | 120000 | 21600.02 | 141600.02 | 0 | -0.02 | 7) GANGA ASMI WAKAD PROJECT OUT DOOR HOARDING DISPLAY CHARGES AT WAKAD FLYOVER, TRAFFIC FROM PUNE TO HINJEWADI SIZE AS 30 X 30 SQ FT. COST RS. 40000/- + TAX NON LIT PERIOD AS ON 21/03/2023 TO 20/06/2023 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 13 Apr 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 454 | 5 | 17 Mar 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 60000 | 180000 | 32400 | 212400 | 0 | 3 | 180000 | 32399.98 | 212399.98 | 0 | 0.02 | 6) GANGA ASMI WAKAD PROJECT OUT DOOR HOARDING DISPLAY CHARGES AT HINJEWADI, WIPRO CHOWK, TRAFFIC FROM HINJEWADI TO PUNE SIZE AS 30 X 40 SQ FT. COST RS. 60000/- + TAX NON LIT PERIOD AS ON 21/03/2023 TO 20/06/2023 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 13 Apr 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 455 | 0 | 20 Mar 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 13170 | 10 | 131700 | 23706 | 155406 | 0 | 11194.5 | 111945 | 20150.12 | 132095.12 | 1975.5 | 23310.88 | FELX PRITING MOUNTING FOR HOARDINGS GANGA ASMI- WAKAD PROJECT | 85 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 19 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 456 | 0 | 23 Mar 2023 | ERA FAME MEDIA GROUP | Advertisement | Advertisement Release- | No. | 1 | 190476 | 190476 | 9523.8 | 199999.8 | 0 | 1 | 190476 | 9523.84 | 199999.84 | 0 | -0.04 | CONSTRUCTION AND ARCHITECTURE UPDATE MAGAZINE - REAL RICH BRANDING WITH PROJECT PROMOTION, MARKETING ADVERTISEMENT WITH ADVERTORIAL , INTERVIEW ETC. AS ON 01ST APRIL 2023 TO FEB. 2024 (TOTAL 6 MAGAZINE INSERTION COST RS. 200000/- (INCLUDING 5% GST) WITH 50% ADVANCE PAYMENT | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 28 Mar 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 457 | 0 | 24 Mar 2023 | STRESSTECH ENGINEERS PRIVATE LIMITED | Wing 2 -2nd (P3) slab Post Tensioning Work | Post Tensioning Work -BC | Metric Tonnes | 10.834 | 143000 | 1549262 | 278867.16 | 1828129.16 | 0 | 0 | 0 | 0 | 0 | 10.834 | 0 | Rate Variation Plus or Minus 3000 per Metric Tonne. | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 457 | 0 | 24 Mar 2023 | STRESSTECH ENGINEERS PRIVATE LIMITED | Wing 2 -1st (P2) slab Post Tensioning Work | Post Tensioning Work -BC | Metric Tonnes | 9.828 | 143000 | 1405404 | 252972.72 | 1658376.72 | 0 | 1.735 | 248105 | 44658.9 | 292763.9 | 8.093 | 1365612.82 | Rate Variation Plus or Minus 3000 per Metric Tonne. | 17.6536 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 457 | 0 | 24 Mar 2023 | STRESSTECH ENGINEERS PRIVATE LIMITED | Wing 2 -3rd (P4) slab Post Tensioning Work | Post Tensioning Work -BC | Metric Tonnes | 10.834 | 143000 | 1549262 | 278867.16 | 1828129.16 | 0 | 0 | 0 | 0 | 0 | 10.834 | 0 | Rate Variation Plus or Minus 3000 per Metric Tonne. | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 457 | 0 | 24 Mar 2023 | STRESSTECH ENGINEERS PRIVATE LIMITED | Wing 2 -4th (P5) slab Post Tensioning Work | Post Tensioning Work -BC | Metric Tonnes | 10.834 | 143000 | 1549262 | 278867.16 | 1828129.16 | 0 | 0 | 0 | 0 | 0 | 10.834 | 0 | Rate Variation Plus or Minus 3000 per Metric Tonne. | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 457 | 0 | 24 Mar 2023 | STRESSTECH ENGINEERS PRIVATE LIMITED | Wing 2 -5th (P6) slab Post Tensioning Work | Post Tensioning Work -BC | Metric Tonnes | 10.834 | 143000 | 1549262 | 278867.16 | 1828129.16 | 0 | 0 | 0 | 0 | 0 | 10.834 | 0 | Rate Variation Plus or Minus 3000 per Metric Tonne. | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 457 | 0 | 24 Mar 2023 | STRESSTECH ENGINEERS PRIVATE LIMITED | Wing 2 -6th (Podium) slab Post Tensioning Work | Post Tensioning Work -BC | Metric Tonnes | 10.834 | 143000 | 1549262 | 278867.16 | 1828129.16 | 0 | 0 | 0 | 0 | 0 | 10.834 | 0 | Rate Variation Plus or Minus 3000 per Metric Tonne. | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 05 Apr 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 458 | 0 | 24 Mar 2023 | ARENA EVENTS & PROMOTIONS | One Boat Club Sales office Hording fabrication work | ISMC 75 (M) | Kgs | 126.52 | 72 | 9109.44 | 1639.7 | 10749.14 | 0 | 126.52 | 9109.44 | 1639.7 | 10749.14 | 0 | 0 | ISMC 75 x 40mm | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 458 | 0 | 24 Mar 2023 | ARENA EVENTS & PROMOTIONS | One Boat Club Sales office Hording fabrication work | MS Pipe (M) | Kgs | 196.67 | 72 | 14160.24 | 2548.84 | 16709.08 | 0 | 196.67 | 14160.24 | 2548.84 | 16709.08 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 24 Mar 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 459 | 0 | 25 Mar 2023 | K.K.ENGINEERING | Goel House Gym Room Alu. Window Work | Al Window (m+l)-BCo- | Sq.Ft | 68.06 | 450 | 30627 | 5512.86 | 36139.86 | 2.5 | 0 | 0 | 0 | 0 | 68.06 | 0 | Aluminium of Euro series of T-6063 Grade,Orbita Make lock & MITI Brand bearing for Euro windos,Osaka make EPDM,Woolpile of technofitas brand,5mmClear toughned glass,Powder coating upto 55-60 microns. | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 459 | 0 | 25 Mar 2023 | K.K.ENGINEERING | Goel House Gym Room Alu. Window Work | Al Window (m+l)-BCo- | Sq.Ft | 247.5 | 349 | 86377.5 | 15547.96 | 101925.46 | 2.5 | 0 | 0 | 0 | 0 | 247.5 | 0 | Aluminium of Euro series of T-6063 Grade,Orbita Make lock & MITI Brand bearing for Euro windos,Osaka make EPDM,Woolpile of technofitas brand,5mmClear toughned glass,Powder coating upto 55-60 microns. | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 459 | 0 | 25 Mar 2023 | K.K.ENGINEERING | Goel House Gym Room Alu. Window Work | Al Window (m+l)-BCo- | Sq.Ft | 74.25 | 435 | 32298.75 | 5813.78 | 38112.53 | 2.5 | 0 | 0 | 0 | 0 | 74.25 | 0 | Aluminium of Euro series of T-6063 Grade,Orbita Make lock & MITI Brand bearing for Euro windos,Osaka make EPDM,Woolpile of technofitas brand,5mmClear toughned glass,Powder coating upto 55-60 microns. | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 460 | 0 | 25 Mar 2023 | K.RAZA ENTERPRISES | Goel House Gym Room Wall Punning - 1 No. | Wall Punning - ARW | Sq.Ft | 1345 | 25 | 33625 | 0 | 33625 | 2.5 | 1019.51 | 25487.75 | 0 | 25487.75 | 325.49 | 8137.25 |  | 75.8 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 460 | 0 | 25 Mar 2023 | K.RAZA ENTERPRISES | Goel House Gym Room Wall Punning - 1 No. | Acrylic False Ceiling- Dld | Sq.Ft | 60 | 140 | 8400 | 0 | 8400 | 2.5 | 54.096 | 7573.44 | 1363.22 | 8936.66 | 5.904 | -536.66 |  | 90.16 |  | DUSHANT GORE | Swapnil Erande | construction open | 30 Mar 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 461 | 0 | 28 Mar 2023 | AAJ KA ANAND PUBLICATIONS LLP | Advertisement | Advertisement Release- | No. | 1 | 50000 | 50000 | 2500 | 52500 | 0 | 1 | 50000 | 2500 | 52500 | 0 | 0 | AAJ KA ANAD - DAILY HINDI NEWS PAPER ANNIVERSARY ISSUE - PROJECT DISPLAY ADVERTIMENT SALES PROMOTION WITH MARKETING ADVT. SIZE AS 16 CM (W) X 25 CM(H) COLOUR ADVT. ANY RHP MAIN ISUUE PUNE EDITION | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 31 Mar 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 462 | 0 | 29 Mar 2023 | THREED SIGN | 3D Rendering & Brocher Design charges | Labour Lumpsum - BC | No. | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 1 | 70000 | 12600 | 82600 | 0 | 0 | Charges for 3D Rendering and Brochure design of (High Resolution 8k.) | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 18 Apr 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 463 | 0 | 30 Mar 2023 | PATILS FABRICATORS | Lashkar Police Station Work | Fabrication work (L) | Sq.Ft | 1020 | 18 | 18360 | 3304.8 | 21664.8 | 2.5 | 750 | 13500 | 2430 | 15930 | 270 | 5734.8 |  | 73.5294 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 464 | 0 | 31 Mar 2023 | RAJSAN ENTERPRISES | GH Supply & installation Tensile Canocopy structure - 1 N | Labour Lumsum | No. | 1 | 42372.88 | 42372.88 | 7627.12 | 50000 | 0 | 1 | 42372.88 | 7627.12 | 50000 | 0 | 0 |  | 100 |  | Sanket Patil | Chetan Jewalikar | construction open | 31 Mar 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Chetan Jewalikar | 1900-01-01
GANGA ASMI | 465 | 0 | 04 Apr 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | MS Liner 6mm (M) | Kgs | 13968 | 70 | 977760 | 175996.8 | 1153756.8 | 0 | 13500 | 945000 | 170100 | 1115100 | 468 | 38656.8 |  | 96.6495 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 465 | 0 | 04 Apr 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | MS Liner 5mm (M) | Kgs | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 07 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 465 | 0 | 04 Apr 2023 | MASKE PILE FOUNDATION | Wing 02 Piling work for Non Tower area | MS Liner 6mm (M) | Kgs | 5432 | 70 | 380240 | 68443.2 | 448683.2 | 0 | 3259.2 | 228144 | 41065.92 | 269209.92 | 2172.8 | 179473.28 |  | 60 |  | DUSHANT GORE | Swapnil Erande | construction open | 07 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 465 | 0 | 04 Apr 2023 | MASKE PILE FOUNDATION | Wing 01 Piling work for Non Tower area | MS Liner 5mm (M) | Kgs | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 07 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | DUSHANT GORE | 07 Apr 2023
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0.9 | 165000 | 29700 | 194700 | 0.1 | 21633.33 |  | 90 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 1 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 466 | 0 | 04 Apr 2023 | ASB AND ASSOCIATES | Company Secretary | Company Secretary charges | Month | 1 | 183333.33 | 183333.33 | 33000 | 216333.33 | 0 | 1 | 183333.33 | 33000 | 216333.33 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 467 | 0 | 06 Apr 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 45000 | 270000 | 48600 | 318600 | 0 | 1.3526 | 60866.01 | 10955.88 | 71821.89 | 4.6474 | 246778.11 | GANGA ASMI WAKAD PROJECT HOARDING DISPLAY CHARGES @ WAKAD CHOWK FRONT/BACK 2 SIDED HOADING SIZE AS 30 X 42 SQ FT. AS ON DTD. 01/04/2023 TO 30/06/2023 @ 45000/- PER MONTH + TAX | 22.5433 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 11 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 468 | 0 | 07 Apr 2023 | SITARAM GANGADHAR AUTI | Aluform material for unloading - 1 Lumsum | Labour Lumsum | No. | 1 | 5000 | 5000 | 0 | 5000 | 0 | 1 | 5000 | 0 | 5000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 11 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 469 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour Act Registration & Compliance | Registration of Company (RC) | No. | 293 | 350 | 102550 | 18459 | 121009 | 0 | 293 | 102550 | 18459 | 121009 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 469 | 0 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour Act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 1 | 20250 | 20250 | 3645 | 23895 | 0 | 1 | 20250 | 3645 | 23895 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 469 | 1 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour Act Registration & Compliance | B.O.C.W. Act Registration &Compliance. | No. | 293 | 350 | 102550 | 18459 | 121009 | 0 | 293 | 102550 | 18459 | 121009 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | Consultancy Labour act Regist. | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 469 | 0 | 07 Apr 2023 | NIKISHA CONSULTANCY SERVICES | Contract Labour Act Registration & Compliance | Registration of Company (RC) | No. | 1 | 54000 | 54000 | 9720 | 63720 | 0 | 1 | 54000 | 9720 | 63720 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 470 | 0 | 08 Apr 2023 | SURESH KUMAR MURALIDHAR | Demolish work at One Boat Club - | Contractor Profit-Mkt | No. | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 470 | 0 | 08 Apr 2023 | SURESH KUMAR MURALIDHAR | Demolish work at One Boat Club - | Department Labour-LC - No. | No. | 120 | 550 | 66000 | 0 | 66000 | 0 | 120 | 66000 | 0 | 66000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Apr 2023 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 470 | 0 | 08 Apr 2023 | SURESH KUMAR MURALIDHAR | Demolish work at One Boat Club - | Transportaion - No. | No. | 1 | 6000 | 6000 | 0 | 6000 | 0 | 1 | 6000 | 0 | 6000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 11 Apr 2023 |  | MKT. Media | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Anchor Fastener (L) | No. | 12 | 50 | 600 | 108 | 708 | 2.5 | 12 | 600 | 108 | 708 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Anchor Fastner (M+L) | No. | 0 | 395 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 10 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 30 Aug 2023
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Anchor Fastener (M) | No. | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 10 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 29 Aug 2023
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | M.S. Plate (M+L)-Mkt | Kgs | 23.52 | 75 | 1764 | 317.52 | 2081.52 | 2.5 | 23.52 | 1764 | 317.52 | 2081.52 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | M.S. Plate (M+L)-Mkt | Kgs | 14.7 | 75 | 1102.5 | 198.46 | 1300.96 | 2.5 | 14.7 | 1102.5 | 198.46 | 1300.96 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Wastage & Profite Cont. - UDR | No. | 0 | 15492 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 10 Apr 2023 |  | UTI. Drainage | Cancelled | DUSHANT.GORE | 29 Sep 2023
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | A1 Fencing Removing work | Sq.Ft | 45 | 10 | 450 | 81 | 531 | 0 | 45 | 450 | 81 | 531 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 1 | 08 Apr 2023 | R.T.S. STEEL SERVICES | One Boat Club-Labour Camp Slab Breaking Work | Labour Lumsum | No. | 1 | 50000 | 50000 | 9000 | 59000 | 0 | 1 | 50000 | 9000 | 59000 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 10 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Wastage & Profite Cont. - UDR | No. | 0 | 4106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 10 Apr 2023 |  | UTI. Drainage | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Pipe 40 x 40 x 2mm (L) | Kgs | 23.04 | 22 | 506.88 | 91.24 | 598.12 | 2.5 | 23.04 | 506.88 | 91.24 | 598.12 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Gusset Plate (M+L) | Kgs | 22.5 | 75 | 1687.5 | 303.76 | 1991.26 | 2.5 | 22.5 | 1687.5 | 303.76 | 1991.26 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 0 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Boat Club- Old Labour Camp Dismanteling Work | Labour Lumpsum | No. | 1 | 275000 | 275000 | 49500 | 324500 | 0 | 1 | 275000 | 49500 | 324500 | 0 | 0 | MS Structure removing, GI Sheet Removing,Deck Sheet Removing and concrete slab breaking work for old and new Labour camp. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 10 Apr 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | ISMC 75 (L) | Kgs | 61.63 | 22 | 1355.86 | 244.06 | 1599.92 | 2.5 | 61.63 | 1355.86 | 244.06 | 1599.92 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | ISMC 150 (L) | Kgs | 471 | 22 | 10362 | 1865.16 | 12227.16 | 2.5 | 471 | 10362 | 1865.16 | 12227.16 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Anchor Fastner (M+L) | No. | 16 | 325 | 5200 | 936 | 6136 | 2.5 | 16 | 5200 | 936 | 6136 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Weld mesh fixing(L) BC | Sq.Ft | 39 | 25 | 975 | 175.5 | 1150.5 | 2.5 | 39 | 975 | 175.5 | 1150.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Pipe 50 x 50 x 2mm | Kgs | 38.48 | 22 | 846.56 | 152.38 | 998.94 | 2.5 | 38.48 | 846.56 | 152.38 | 998.94 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Wastage & Profite Cont. - UDR | No. | 1 | 3856 | 3856 | 694.08 | 4550.08 | 0 | 1 | 3856 | 694.08 | 4550.08 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | UTI. Drainage | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 2 | 08 Apr 2023 | R.T.S. STEEL SERVICES | One Boat Club-Material Removing & Shifting Work | Transport Charges | No. | 1 | 233000 | 233000 | 41940 | 274940 | 2.5 | 1 | 233000 | 41940 | 274940 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | A1 Fence Work (L)- DCW | Sq.Ft | 45 | 15 | 675 | 121.5 | 796.5 | 2.5 | 45 | 675 | 121.5 | 796.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Chemical Fastner 12mm (M) | No. | 0 | 29 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 10 Apr 2023 |  | No category | Cancelled | DUSHANT.GORE | 30 Aug 2023
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Wastage & Profite Cont. - UDR | No. | 0 | 15975 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 10 Apr 2023 |  | UTI. Drainage | Cancelled | DUSHANT.GORE | 30 Aug 2023
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Angle. (M) | Kgs | 64.51 | 60 | 3870.6 | 696.7 | 4567.3 | 0 | 64.51 | 3870.6 | 696.7 | 4567.3 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 0 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Boat Club- Old Labour Camp Dismanteling Work | Labour Lumpsum | No. | 0 | 250000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MS Structure Removing, GI Sheet Removing, Deck Sheet Removing and Concrete slab breaking work for Old and New Labour camp. | 0 |  | ADITYA CHOUGULE |  | construction open | 10 Apr 2023 |  | DEV. Ext Development | Cancelled | ADITYA CHOUGULE | 10 Apr 2023
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | Castor Wheel Set on rent | Day | 38 | 200 | 7600 | 1368 | 8968 | 2.5 | 38 | 7600 | 1368 | 8968 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 471 | 3 | 08 Apr 2023 | R.T.S. STEEL SERVICES | Goel House Fabrication rennovation work | MS Angle 50 x 50 x 5mm | Kgs | 86.76 | 20 | 1735.2 | 312.34 | 2047.54 | 2.5 | 86.76 | 1735.2 | 312.34 | 2047.54 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 472 | 0 | 11 Apr 2023 | SATYAM TIWARI | MS Plate for Lift Cut Out for Tower Crane - 3rd Stage | Fabrication work (L) | Kgs | 268.44 | 32 | 8590.08 | 0 | 8590.08 | 2.5 | 0 | 0 | 0 | 0 | 268.44 | 0 | 1. 4 pockets 16 plates required at each stage of tower crane 1st to 9th floor. 2. At Top= 67.5 kg, at Bottom= 67.5 kg, Vertical Plate= 133.44 kg. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 472 | 0 | 11 Apr 2023 | SATYAM TIWARI | MS Plate for Lift Cut Out for Tower Crane - 1st Stage | Fabrication work (L) | Kgs | 268.44 | 32 | 8590.08 | 0 | 8590.08 | 2.5 | 268 | 8576 | 0 | 8576 | 0.44 | 14.08 | 1. 4 pockets 16 plates required at each stage of tower crane 1st to 9th floor. 2. At Top= 67.5 kg, at Bottom= 67.5 kg, Vertical Plate= 133.44 kg. | 99.8361 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 472 | 0 | 11 Apr 2023 | SATYAM TIWARI | MS Plate for Lift Cut Out for Tower Crane - 2nd Stage | Fabrication work (L) | Kgs | 268.44 | 32 | 8590.08 | 0 | 8590.08 | 2.5 | 268.44 | 8590.08 | 0 | 8590.08 | 0 | 0 | 1. 4 pockets 16 plates required at each stage of tower crane 1st to 9th floor. 2. At Top= 67.5 kg, at Bottom= 67.5 kg, Vertical Plate= 133.44 kg. | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 473 | 0 | 11 Apr 2023 | AAKAAR INDUSTRIES | Debris Chute System for Wing-1 | Debris Chute system (M+L) | Mtrs | 110 | 1925 | 211750 | 38115 | 249865 | 0 | 30.7601 | 59213.19 | 10658.38 | 69871.57 | 79.2399 | 179993.43 |  | 27.9637 |  | Sanket Patil | Swapnil Erande | construction open | 11 Apr 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 473 | 0 | 11 Apr 2023 | AAKAAR INDUSTRIES | Debris Chute System for Wing-1 | Transportaion - No. | No. | 1 | 3000 | 3000 | 540 | 3540 | 0 | 1 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | Sanket Patil | Swapnil Erande | construction open | 11 Apr 2023 |  | MKT. Media | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 473 | 0 | 11 Apr 2023 | AAKAAR INDUSTRIES | Debris Chute System for Wing-1 | Debris Chute system (M+L) | Mtrs | 0 | 1925 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Sanket Patil |  | construction open | 11 Apr 2023 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | ADITYA CHOUGULE | 11 Apr 2023
GANGA ASMI | 474 | 1 | 12 Apr 2023 | SATYAM TIWARI | Tower Crane Counter Weight Frame | Fabrication (L)-DEn | Kgs | 235.99 | 16 | 3775.84 | 0 | 3775.84 | 2.5 | 0 | 0 | 0 | 0 | 235.99 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 474 | 0 | 12 Apr 2023 | SATYAM TIWARI | Steel yard below ramp in wing 01 for Wing 01 - 1 Job | Fabrication work (L) | Kgs | 452.6 | 16 | 7241.6 | 0 | 7241.6 | 2.5 | 0 | 0 | 0 | 0 | 452.6 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Apr 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 474 | 0 | 12 Apr 2023 | SATYAM TIWARI | Steel yard near Experience centre for Wing 02 - 1 Job | Meta colour Sheet Fixing BC | Sq.Ft | 1291.67 | 13 | 16791.71 | 0 | 16791.71 | 2.5 | 1291.67 | 16791.71 | 0 | 16791.71 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Apr 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 474 | 1 | 12 Apr 2023 | SATYAM TIWARI | Steel Cutting Yard Making Rack For Steel | Fabrication (L)-DEn | Kgs | 0 | 12 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Entrance Gate | Cancelled | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ASMI | 474 | 1 | 12 Apr 2023 | SATYAM TIWARI | Tower Crane Counter Weight Frame | Fabrication (L)-DEn | Kgs | 0 | 12 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Entrance Gate | Cancelled | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ASMI | 474 | 0 | 12 Apr 2023 | SATYAM TIWARI | Steel yard below ramp in wing 01 for Wing 01 - 1 Job | Fabrication work (L) | Sq.Ft | 0 | 13 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 12 Apr 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | ADITYA CHOUGULE | 12 Apr 2023
GANGA ASMI | 474 | 1 | 12 Apr 2023 | SATYAM TIWARI | Tower Crane Counter Weight Frame | Fabrication (L)-DEn | Kgs | 0 | 12 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Entrance Gate | Cancelled | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ASMI | 474 | 1 | 12 Apr 2023 | SATYAM TIWARI | Tower Crane Counter Weight Frame | Fabrication (L)-DEn | Kgs | 35.43 | 16 | 566.88 | 0 | 566.88 | 2.5 | 0 | 0 | 0 | 0 | 35.43 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 474 | 1 | 12 Apr 2023 | SATYAM TIWARI | Tower Crane Counter Weight Frame | Fabrication (L)-DEn | Kgs | 0 | 12 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Entrance Gate | Cancelled | ADITYA.CHOUGULE | 06 Sep 2023
GANGA ASMI | 474 | 1 | 12 Apr 2023 | SATYAM TIWARI | Tower Crane Counter Weight Frame | Fabrication (L)-DEn | Kgs | 55.73 | 16 | 891.68 | 0 | 891.68 | 2.5 | 0 | 0 | 0 | 0 | 55.73 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 474 | 0 | 12 Apr 2023 | SATYAM TIWARI | Steel yard below ramp in wing 01 for Wing 01 - 1 Job | Meta colour Sheet Fixing BC | Sq.Ft | 1026.877 | 13 | 13349.4 | 0 | 13349.4 | 2.5 | 0 | 0 | 0 | 0 | 1026.877 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Apr 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 474 | 1 | 12 Apr 2023 | SATYAM TIWARI | Steel Cutting Yard Making Rack For Steel | Fabrication (L)-DEn | Kgs | 480 | 16 | 7680 | 0 | 7680 | 2.5 | 0 | 0 | 0 | 0 | 480 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Entrance Gate | Un-Approved |  | 1900-01-01
GANGA ASMI | 475 | 0 | 12 Apr 2023 | SURESH KUMAR MURALIDHAR | Goel House (L) Roof Slab Roof tile fixing work | Male Coolie | Day | 13.5 | 550 | 7425 | 0 | 7425 | 0 | 13.5 | 7425 | 0 | 7425 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Apr 2023 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 475 | 0 | 12 Apr 2023 | SURESH KUMAR MURALIDHAR | Goel House (L) Roof Slab Roof tile fixing work | Mason - DCW | No. | 0 | 900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 12 Apr 2023 |  | DEV. Compound Wall | Cancelled | ADITYA CHOUGULE | 12 Apr 2023
GANGA ASMI | 475 | 0 | 12 Apr 2023 | SURESH KUMAR MURALIDHAR | Goel House (L) Roof Slab Roof tile fixing work | Mason - SOS | Day | 9 | 900 | 8100 | 0 | 8100 | 0 | 9 | 8100 | 0 | 8100 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Apr 2023 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 475 | 0 | 12 Apr 2023 | SURESH KUMAR MURALIDHAR | Goel House (L) Roof Slab Roof tile fixing work | Contractor Profit-Mkt | No. | 1 | 1552 | 1552 | 0 | 1552 | 0 | 1 | 1552 | 0 | 1552 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Apr 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 475 | 0 | 12 Apr 2023 | SURESH KUMAR MURALIDHAR | Goel House (L) Roof Slab Roof tile fixing work | Transport Charges | No. | 1 | 1080 | 1080 | 0 | 1080 | 0 | 1 | 1080 | 0 | 1080 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 12 Apr 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | After Completion of all RCC Work of Bulding | RCC Work -Dld | No. | 0 | 1000000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | DEV. Landscape/Equipment | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | Sorting & Shifting mockup,checking & rework- 10179.655 Sq. | Sorting & Shifting Work | Sq.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 8th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 28th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 16th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 19th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 28th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 31st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 18th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 30th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT GORE | 13 Apr 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 27th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 24th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 28th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT GORE | 13 Apr 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | Shifting of shuttering material from last floor to G.F.(L)- | Sorting & Shifting Work | Sq.Ft | 0 | 47.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 28th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 9th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 17th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 25th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 33rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 34th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 11th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 17th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 35th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 33rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 22nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 32nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 23rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 34th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 25th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 21st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 29th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 25th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 27th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT GORE | 13 Apr 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 29th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT GORE | 13 Apr 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 30th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 27th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 34th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 7th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 23rd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 13th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 32nd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 35th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 15th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 33rd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 22nd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 31st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT GORE | 13 Apr 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 31st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT GORE | 13 Apr 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 12th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 30th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 17th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 31st Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 21st Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 29th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 185 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 20th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 30th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 26th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 29th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 24th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 22nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 32nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 20th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | Wing 1-OHWT Top Terrace LMR,OHWT | RCC Work -Dld | No. | 0 | 1251782 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | DEV. Landscape/Equipment | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 23rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 10th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 26th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 24th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 26th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 175 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 20th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 35th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 215 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 21st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 145 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 14th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 476 | 0 | 13 Apr 2023 | SAIRAJ CONSTRUCTION | 27th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 14 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 477 | 0 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Sales office renovation - Tree Trimming - 1 Lumsum | Tree cutting Work - Dld | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Cancelled | ADITYA.CHOUGULE | 09 May 2024
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 1 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 477 | 2 | 14 Apr 2023 | SITARAM GANGADHAR AUTI | Garden Work | Garden Maintenance | Month | 1 | 20000 | 20000 | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 478 | 0 | 14 Apr 2023 | INSTA POLLUTECH LABS | Goel House Water Testing (Insta pollutech Lab Test) - 1 | Water Testing report - SOS | No. | 1 | 1000 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Apr 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 479 | 0 | 14 Apr 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 2460 | 10 | 24600 | 4428 | 29028 | 0 | 2460 | 24600 | 4428 | 29028 | 0 | 0 | GANGA ASMI WAKAD PROJECT HOARDING FLEX PRNTING WITH MOUNTING @ 1) WIPRO CHOWK, HINJEWADI SIZE AS 30 X 42 SQ FT. & 2) HINJEWADI SIZE AS 30 X 40 SQ FT. (FLEX TORN- REPLACE) | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 20 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 480 | 0 | 14 Apr 2023 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | Weigh Bridge AMC Charges & Stamping Charges - 1 Job | Stamping Charges | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 480 | 0 | 14 Apr 2023 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | Weigh Bridge AMC Charges & Stamping Charges - 1 Job | AMC Charges | No. | 1 | 24000 | 24000 | 4320 | 28320 | 0 | 1 | 24000 | 4319.94 | 28319.94 | 0 | 0.06 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | Admin. Indirect Expenses | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 481 | 2 | 17 Apr 2023 | J K INTERIOR | GH Meeting Room 4 False Ceiling Work | Removing Work | Sq.Ft | 200 | 15 | 3000 | 540 | 3540 | 0 | 200 | 3000 | 540 | 3540 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 481 | 1 | 17 Apr 2023 | J K INTERIOR | Goel House VOX Facade for Gym Room - 1 No. | Cement Sheet fixing | Sq.Ft | 58.62 | 35 | 2051.7 | 369.3 | 2421 | 2.5 | 58 | 2030 | 365.4 | 2395.4 | 0.62 | 25.6 |  | 98.9423 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 481 | 0 | 17 Apr 2023 | J K INTERIOR | Goel House VOX Facade for Gym Room - 1 No. | Cement Sheet fixing | Sq.Ft | 250 | 35 | 8750 | 1575 | 10325 | 2.5 | 250 | 8750 | 1575 | 10325 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 481 | 2 | 17 Apr 2023 | J K INTERIOR | GH Meeting Room 4 False Ceiling Work | False Ceiling (m+l) - BRE | Sq.Ft | 200 | 50 | 10000 | 1800 | 11800 | 2.5 | 200 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 481 | 0 | 17 Apr 2023 | J K INTERIOR | Goel House VOX Facade for Gym Room - 1 No. | VOX PVC Sheet (M+L) | Sq.Ft | 720 | 250 | 180000 | 32400 | 212400 | 2.5 | 0 | 0 | 0 | 0 | 720 | 0 | Green VOX PVC Sheet Vertically VOX Infratop Code- Unicolour SV-07 Graphite. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 482 | 0 | 19 Apr 2023 | B.B. ROAD CONSTRUCTION | GH Main Road Space Making For Car Parking - 1 No. | Transportation - BRE | No. | 1 | 1000 | 1000 | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 482 | 0 | 19 Apr 2023 | B.B. ROAD CONSTRUCTION | GH Main Road Space Making For Car Parking - 1 No. | Aggregate Spreading | Sq.Ft | 6456 | 1 | 6456 | 0 | 6456 | 0 | 0 | 0 | 0 | 0 | 6456 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 482 | 0 | 19 Apr 2023 | B.B. ROAD CONSTRUCTION | GH Main Road Space Making For Car Parking - 1 No. | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 6456 | 2 | 12912 | 0 | 12912 | 0 | 0 | 0 | 0 | 0 | 6456 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 482 | 0 | 19 Apr 2023 | B.B. ROAD CONSTRUCTION | GH Main Road Space Making For Car Parking - 1 No. | Roller Hiring Charges (for Compaction) | Day | 2 | 3000 | 6000 | 0 | 6000 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 483 | 0 | 19 Apr 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 1680 | 10 | 16800 | 3024 | 19824 | 0 | 1680 | 16800 | 3024 | 19824 | 0 | 0 | GANGA ASMI WAKAD PROJECT (TORN FLEX CHANGE) HOARDING FLEX PRINTING & MOUNTING SIZE AS 40 X 42 SQ FT. @ MAHALUNGE | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 20 Apr 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 484 | 0 | 21 Apr 2023 | METTLE TECH SOLUTIONS | Tower Crane | Service Charges | No. | 3 | 100000 | 300000 | 54000 | 354000 | 0 | 3 | 300000 | 54000 | 354000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 25 Apr 2023 |  | S OH Repair & Maintenance | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 485 | 0 | 24 Apr 2023 | VATUGI FACILITY MANAGEMENT | Drain line cleaning,lifting,disposal by suction machine | Chamber Cleaning work (Rmt) - Mtrs | Mtrs | 700 | 10 | 7000 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 700 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | No category | Approved | ADITYA CHOUGULE | 24 Apr 2023
GANGA ASMI | 485 | 0 | 24 Apr 2023 | VATUGI FACILITY MANAGEMENT | Drain line cleaning,lifting,disposal by suction machine | Misc Work - AIE | No. | 32 | 250 | 8000 | 0 | 8000 | 2.5 | 0 | 0 | 0 | 0 | 32 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 25 Apr 2023 |  | Admin. Indirect Expenses | Approved | ADITYA CHOUGULE | 24 Apr 2023
GANGA ASMI | 486 | 0 | 29 Apr 2023 | LOKMAT MEDIA PVT. LTD. | BRANDING Event Expenses | Event Expenses | No. | 1 | 400000 | 400000 | 72000 | 472000 | 0 | 1 | 400000 | 72000 | 472000 | 0 | 0 | LOKMAT MEDIA ORGANISED- "KHEL MANDIYELA" - ADESH BANDEKAR + LOKMAT SAKHI MANCH EVENT SPONCERSHIP RS. 400000/- + TAX. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 01 May 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Bonus | No. | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0.5831 | 291550 | 52479.54 | 344029.54 | 0.4169 | 245970.46 |  | 58.31 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | S OH Site Staff | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 0 | 500000 | 0 | 90000 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 0 | 500000 | 0 | 90000 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 0 | 500000 | 0 | 90000 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 0 | 500000 | 0 | 90000 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 90000 | 590000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 1 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 03 May 2024
GANGA ASMI | 487 | 0 | 01 May 2023 | SUNITA S MISHRA | Professional Fees | Professional Fees | Month | 1 | 500000 | 500000 | 90000 | 590000 | 0 | 1 | 500000 | 0 | 500000 | 0 | 90000 |  | 100 |  | chetan jewalikar | chetan jewalikar | consultancy | 04 May 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 06 Dec 2023
GANGA ASMI | 488 | 1 | 02 May 2023 | SATHE RAJENDRA BANSILAL | GH Site Expenses | Site Expences | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 May 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 488 | 2 | 02 May 2023 | SATHE RAJENDRA BANSILAL | GH Site Expenses | Site Expences | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.6727 | 67270 | 0 | 67270 | 0.3273 | 32730 |  | 67.27 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 May 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 488 | 0 | 02 May 2023 | SATHE RAJENDRA BANSILAL | GH Site Expenses | Site Expences | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 1 | 100000 | 0 | 100000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 02 May 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 489 | 0 | 03 May 2023 | PEHELLWAAN WELLNESS PVT LTD | Gym Equipment Loading,Unloading Transportation | Leg press (L) | No. | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Cancelled | skmishra | 18 Jul 2023
GANGA ASMI | 489 | 0 | 03 May 2023 | PEHELLWAAN WELLNESS PVT LTD | Gym Equipment Loading,Unloading Transportation | Leg Extension curling (L) | No. | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Cancelled | skmishra | 18 Jul 2023
GANGA ASMI | 489 | 0 | 03 May 2023 | PEHELLWAAN WELLNESS PVT LTD | Gym Equipment Loading,Unloading Transportation | Loading, Unloading & Transport | No. | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Cancelled | skmishra | 18 Jul 2023
GANGA ASMI | 489 | 0 | 03 May 2023 | PEHELLWAAN WELLNESS PVT LTD | Gym Equipment Loading,Unloading Transportation | Bicep Tricep Pully (L) | No. | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Cancelled | skmishra | 18 Jul 2023
GANGA ASMI | 489 | 0 | 03 May 2023 | PEHELLWAAN WELLNESS PVT LTD | Gym Equipment Loading,Unloading Transportation | Peck Flies (L) | No. | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Cancelled | skmishra | 18 Jul 2023
GANGA ASMI | 489 | 0 | 03 May 2023 | PEHELLWAAN WELLNESS PVT LTD | Gym Equipment Loading,Unloading Transportation | Lat pull down (L) | No. | 0 | 22000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Cancelled | skmishra | 18 Jul 2023
GANGA ASMI | 490 | 0 | 06 May 2023 | SATYAM TIWARI | Technical Office, Store, Safety Induction Room making | Metacolur Sheet Removing - DER | Sq.Ft | 1080.411 | 2.5 | 2701.03 | 0 | 2701.03 | 0 | 1080.411 | 2701.03 | 0 | 2701.03 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | DEV. Extrawork/Rework | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | Murum filling Labour BC | Cu.Ft | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. RCC Substructure | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | 9" Brick Work | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | 12 MASONARY WORK | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | PCC | Sq.Ft | 0 | 8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Grade of PCC M-15 (1:2:4) | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. Building Common Items | Cancelled | DUSHANT GORE | 08 May 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | Dismentalling work-UTI | No. | 0 | 5000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | PCC | Sq.Ft | 0 | 8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | Pit Concrete work | No. | 0 | 1560 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | 02 RCC WORK | Cancelled | DUSHANT GORE | 08 May 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | Compaction, Levelling- BC | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. RCC Substructure | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | Tar Plaster-BC | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | External Plaster- BC | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | 6" Brick Work | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | 12 MASONARY WORK | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | Concreting Work-B.C. | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 125mm thick Deck slab | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | Pit Excavation - BC | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. RCC Substructure | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 491 | 0 | 06 May 2023 | VIJAY MOHITE | Tan. Civil Work | Reinforcement Work - BC | Sq.Ft | 0 | 7 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 30 Sep 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 30 Sep 2023
GANGA ASMI | 492 | 0 | 06 May 2023 | ABHIJIT PAWAR | Goel House Water leak detection work (L) | Water Leak Detection & Diagnosis | No. | 1 | 110000 | 110000 | 0 | 110000 | 0 | 1 | 110000 | 0 | 110000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 06 May 2023 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 492 | 0 | 06 May 2023 | ABHIJIT PAWAR | Goel House Water leak detection work (L) | Labour Lumpsum | No. | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Above final amount includes 3 attempt for the water leak detection survey,no any extra cost. | 0 |  | DUSHANT GORE |  | construction open | 06 May 2023 |  | DEV. Ext Development | Cancelled | ADITYA CHOUGULE | 06 May 2023
GANGA ASMI | 492 | 0 | 06 May 2023 | ABHIJIT PAWAR | Goel House Water leak detection work (L) | Labour Lumpsum | No. | 0 | 110000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 06 May 2023 |  | DEV. Ext Development | Cancelled | DUSHANT GORE | 06 May 2023
GANGA ASMI | 492 | 0 | 06 May 2023 | ABHIJIT PAWAR | Goel House Water leak detection work (L) | Labour Lumpsum | No. | 0 | 110000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Above final amount includes 3 attempt for the water leak detection survey,no any extra cost. | 0 |  | DUSHANT GORE |  | construction open | 06 May 2023 |  | DEV. Ext Development | Cancelled | DUSHANT GORE | 06 May 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | Reinforcement (M) | Kgs | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 02 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | Tar Plaster (M) | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | No category | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | 9" Brick Work (M) | Sq.Ft | 0 | 110 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | No category | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | Brickwork 6" (M) BC | Sq.Ft | 0 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | Reinforcement (M) | Kgs | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 14 Jun 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | Pit Concrete work | No. | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | Murum Filling (M) - UTI | Cu.Ft | 0 | 8.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Murum Supply from outside. | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | External Plaster (M)- BC | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | Murum Filling (M) - UTI | Cu.Ft | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | UTI. Electricity Infrastructur | Cancelled | DUSHANT GORE | 08 May 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | PCC (M) - DCW | Sq.Ft | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | DEV. Compound Wall | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 493 | 0 | 08 May 2023 | VIJAY MOHITE | Tan. Civil Work | Site Mix Concrete (M) | Sq.Ft | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 02 Oct 2023 |  | No category | Cancelled | DUSHANT.GORE | 02 Oct 2023
GANGA ASMI | 494 | 0 | 08 May 2023 | RED TREE DESIGN STUDIO PRIVATE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 12 | 200000 | 2400000 | 432000 | 2832000 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | MONTHLY ONLINE SOCIAL MEDIA BRANDING RETAINERSHIP CHARGES AS ON 01ST APRIL 2023 TO 31ST MARCH 2024 @ 200000/- + TAX PER MONTH | 0 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 09 May 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 495 | 0 | 08 May 2023 | TRIVIUM MEDIA GROUP | ONLINE / DIGITAL Social / Digital Activity | ARTICLE / WRITE UP / CONTENT / ONLINE - OFFILINE PR / ORM / | No. | 0 | 118644 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GOEL GANGA GROUP-MEDIA PR ACTIVITY (ARTICLE, WRITE UP, PROJECT INFORMATION, BRAND DEVELOPMENTS, EVENT COVERAGES, ETC PR MONTHLT MEDIA/ MARKETING RELATED ACTIVITY COST RS. 118644/-+ TAX.AS ON 05TH MAY 2023 TO 04TH JUNE 2023 | 0 |  | TEJAS RAVERKAR |  | construction open | 08 May 2023 |  | MKT. Media | Cancelled | sunita shirolkar | 08 May 2023
GANGA ASMI | 496 | 0 | 08 May 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 900 | 10 | 9000 | 1620 | 10620 | 0 | 900 | 9000 | 1620 | 10620 | 0 | 0 | TORN FLEX CHANGE FOR GANGA ASMI PROJECT OUTDOOR HOARDING DISPLAY SIZE AS 30 X 30 SQ FT. @ MUMBAI- BANGLORE HIGHWAY- WAKAD | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 09 May 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 497 | 0 | 08 May 2023 | TRIVIUM MEDIA GROUP | ONLINE / DIGITAL Social / Digital Activity | ARTICLE / WRITE UP / CONTENT / ONLINE - OFFILINE PR / ORM / | No. | 3 | 118644 | 355932 | 64067.76 | 419999.76 | 0 | 3 | 355932 | 64067.76 | 419999.76 | 0 | 0 | GOEL GANGA GROUP-MEDIA PR ACTIVITY (ARTICLE, WRITE UP, PROJECT INFORMATION, BRAND DEVELOPMENTS, EVENT COVERAGES, ETC PR MONTHLT MEDIA/ MARKETING RELATED ACTIVITY COST RS. 118644/-+ TAX.AS ON 05TH MAY 2023 TO 04TH AUGUST 2023 | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 09 May 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 21 Sep 2023
GANGA ASMI | 497 | 1 | 08 May 2023 | TRIVIUM MEDIA GROUP | ONLINE / DIGITAL Social / Digital Activity | ARTICLE / WRITE UP / CONTENT / ONLINE - OFFILINE PR / ORM / | No. | 2 | 118644 | 237288 | 42711.84 | 279999.84 | 0 | 2 | 237288 | 42711.84 | 279999.84 | 0 | 0 | ADDITIONAL MARKETING CAMPAIGN FOR 2 MONTH AS ON 05TH AUGUST 2023 TO 04TH OCTOBER 2023 @ 118644/- + TAX | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 09 May 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 21 Sep 2023
GANGA ASMI | 498 | 0 | 11 May 2023 | DUROCRETE ENGINEERING SERVICES PVT LTD | Tan. Civil Work | Soil Investigation work- SOS | No. | 0.6302 | 106000 | 66801.2 | 12024.22 | 78825.42 | 0 | 0.6302 | 66801.2 | 12024 | 78825.2 | 0 | 0.22 | Laboratory test-Dry Density, Specific Gravity, Water absorption, Porosity, Saturated Crushing strength/Point load.Setting & Shifting of Rig at borehole locations,Drilling,Conducting SPT,preservation & handing,Any other relevant geotechnical issues. | 100 |  | DUSHANT GORE | chetan jewalikar | consultancy | 13 May 2023 |  | S OH Infrastructure | Foreclose | ADITYA.CHOUGULE | 07 Sep 2023
GANGA ASMI | 499 | 0 | 12 May 2023 | SIDDHANT CLEANING SERVICES | Goel House Cleaning Work | Cleaning work lumpsum- BC | No. | 1 | 20000 | 20000 | 0 | 20000 | 0 | 1 | 20000 | 0 | 20000 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. RCC Substructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 500 | 0 | 13 May 2023 | SATYAM TIWARI | Site Barrication with GI Sheet | Metacolur Sheet Removing - DER | Sq.Ft | 2526.45 | 6 | 15158.7 | 0 | 15158.7 | 0 | 0 | 0 | 0 | 0 | 2526.45 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | DEV. Extrawork/Rework | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 500 | 0 | 13 May 2023 | SATYAM TIWARI | Media Frame Fabrication Work | Fabrication work (L) | Sq.Ft | 841 | 5 | 4205 | 0 | 4205 | 2.5 | 841 | 4205 | 0 | 4205 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 500 | 0 | 13 May 2023 | SATYAM TIWARI | Media Frame Fabrication Work | MS Square Pipe (L) | Kgs | 347 | 16 | 5552 | 0 | 5552 | 2.5 | 347 | 5552 | 0 | 5552 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 500 | 0 | 13 May 2023 | SATYAM TIWARI | Site Barrication with GI Sheet | Meta colour Sheet Fixing BC | Sq.Ft | 3047.925 | 13 | 39623.03 | 0 | 39623.03 | 2.5 | 3047.925 | 39623.03 | 0 | 39623.03 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 500 | 0 | 13 May 2023 | SATYAM TIWARI | Media Frame Fabrication Work | MS Square Pipe (L) | Kgs | 107.82 | 16 | 1725.12 | 0 | 1725.12 | 2.5 | 107.82 | 1725.12 | 0 | 1725.12 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 500 | 0 | 13 May 2023 | SATYAM TIWARI | Media Frame Fabrication Work | Fabrication (L) - Mkt | Kgs | 127.708 | 16 | 2043.33 | 0 | 2043.33 | 2.5 | 127.7 | 2043.2 | 0 | 2043.2 | 0.008 | 0.13 |  | 99.9937 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | MKT. Marketing Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 500 | 0 | 13 May 2023 | SATYAM TIWARI | Media Frame Fabrication Work | MS Frame Fixing | Sq.Ft | 1147.28 | 5 | 5736.4 | 0 | 5736.4 | 2.5 | 1147.28 | 5736.4 | 0 | 5736.4 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 500 | 0 | 13 May 2023 | SATYAM TIWARI | Media Frame Fabrication Work | MS Framing (L) | Sq.Ft | 543 | 10 | 5430 | 0 | 5430 | 2.5 | 543 | 5430 | 0 | 5430 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Sewage Water Analysis | No. | 8 | 1200 | 9600 | 1728 | 11328 | 0 | 3 | 3600 | 648 | 4248 | 5 | 7080 |  | 37.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | NOise Test Day SOS | No. | 40 | 100 | 4000 | 720 | 4720 | 0 | 9 | 900 | 162 | 1062 | 31 | 3658 |  | 22.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Stack Monitoring Report SOS | No. | 20 | 900 | 18000 | 3240 | 21240 | 0 | 4 | 3600 | 648 | 4248 | 16 | 16992 |  | 20 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Effluent Sample | No. | 8 | 1200 | 9600 | 1728 | 11328 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Water Testing report - SOS | No. | 48 | 1000 | 48000 | 8640 | 56640 | 0 | 7 | 7000 | 1260 | 8260 | 41 | 48380 |  | 14.5833 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Air Test SOS | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | ADITYA CHOUGULE | 24 May 2023
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Air Test SOS | No. | 20 | 1500 | 30000 | 5400 | 35400 | 0 | 9 | 13500 | 2430 | 15930 | 11 | 19470 |  | 45 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Soil Analysis Test- SOS | No. | 16 | 1500 | 24000 | 4320 | 28320 | 0 | 4 | 6000 | 1080 | 7080 | 12 | 21240 |  | 25 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 501 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Noise Test Night SOS | No. | 40 | 100 | 4000 | 720 | 4720 | 0 | 9 | 900 | 162 | 1062 | 31 | 3658 |  | 22.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Dado Fixing | Sq.Ft | 70.87 | 78.75 | 5581.01 | 1004.58 | 6585.59 | 2.5 | 70.87 | 5581.01 | 1004.58 | 6585.59 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Edge Polish - BCE | R.Ft | 183.96 | 36.75 | 6760.53 | 1216.9 | 7977.43 | 2.5 | 183.96 | 6760.53 | 1216.9 | 7977.43 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Elevation Features | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Tile Cutting work | R.Ft | 77.92 | 21 | 1636.32 | 294.54 | 1930.86 | 2.5 | 77.92 | 1636.32 | 294.54 | 1930.86 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Flooring work- cc | Sq.Ft | 34.59 | 36.75 | 1271.18 | 228.82 | 1500 | 2.5 | 34.59 | 1271.18 | 228.82 | 1500 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Customer Changes | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Granite Shelf (M+L) | R.Ft | 3.32 | 315 | 1045.8 | 188.24 | 1234.04 | 2.5 | 3.32 | 1045.8 | 188.24 | 1234.04 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Drill Hole | No. | 8 | 136.5 | 1092 | 196.56 | 1288.56 | 2.5 | 8 | 1092 | 196.56 | 1288.56 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Granite Jamb - BCo | R.Ft | 116.88 | 315 | 36817.2 | 6627.1 | 43444.3 | 2.5 | 116.88 | 36817.2 | 6627.1 | 43444.3 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Demolish Work | R.Ft | 98.16 | 35 | 3435.6 | 618.4 | 4054 | 2.5 | 98.16 | 3435.6 | 618.4 | 4054 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Champher-DCH | R.Ft | 131.18 | 89.25 | 11707.82 | 2107.4 | 13815.22 | 2.5 | 131.18 | 11707.82 | 2107.4 | 13815.22 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | DEV. Club House | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Zero Point Joint Making | R.Ft | 9.32 | 210 | 1957.2 | 352.3 | 2309.5 | 2.5 | 9.32 | 1957.2 | 352.3 | 2309.5 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Internal Finishing Itmes | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Granite Umbra Pattil (L) -BC | R.Ft | 5.66 | 36.75 | 208.01 | 37.44 | 245.45 | 2.5 | 5.66 | 208.01 | 37.44 | 245.45 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Internal Finishing Itmes | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Grout filling | Sq.Ft | 502.03 | 20 | 10040.6 | 1807.3 | 11847.9 | 2.5 | 502.03 | 10040.6 | 1807.3 | 11847.9 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Granite Shelf. | No. | 10 | 630 | 6300 | 1134 | 7434 | 2.5 | 10 | 6300 | 1134 | 7434 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Granite Border - DCH | R.Ft | 25.98 | 78.75 | 2045.93 | 368.26 | 2414.19 | 2.5 | 25.98 | 2045.93 | 368.26 | 2414.19 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | DEV. Club House | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Granite Grinding Rough making | Sq.Ft | 21.75 | 20 | 435 | 78.3 | 513.3 | 2.5 | 21.75 | 435 | 78.3 | 513.3 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Skirting Fixing - AIE | R.Ft | 18.24 | 36.75 | 670.32 | 120.66 | 790.98 | 2.5 | 18.24 | 670.32 | 120.66 | 790.98 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | Admin. Indirect Expenses | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 502 | 0 | 25 May 2023 | R K INTERIOR | Wanowadi Wetal sir home flooring work - 1 R.Ft - 1 R.F | Nahani Trap Jali- BCo | No. | 3 | 136.5 | 409.5 | 73.72 | 483.22 | 2.5 | 3 | 409.5 | 73.72 | 483.22 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Tile Fixing Work | No. | 1 | 900 | 900 | 162 | 1062 | 2.5 | 1 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Dado Fixing | Sq.Ft | 5.26 | 135 | 710.1 | 127.82 | 837.92 | 2.5 | 5.26 | 710.1 | 127.82 | 837.92 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Drill Hole | No. | 6 | 122.85 | 737.1 | 132.68 | 869.78 | 2.5 | 6 | 737.1 | 132.68 | 869.78 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Granite Basin Counter | R.Ft | 2.25 | 3150 | 7087.5 | 1275.76 | 8363.26 | 2.5 | 2.25 | 7087.5 | 1275.76 | 8363.26 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Champher-DCH | R.Ft | 38.81 | 80.32 | 3117.22 | 561.1 | 3678.32 | 2.5 | 38.81 | 3117.22 | 561.1 | 3678.32 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | DEV. Club House | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Tile Border | R.Ft | 3.5 | 135 | 472.5 | 85.06 | 557.56 | 2.5 | 3.5 | 472.5 | 85.06 | 557.56 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Granite Border Fixing- | R.Ft | 13.74 | 423 | 5812.02 | 1046.16 | 6858.18 | 2.5 | 13.74 | 5812.02 | 1046.16 | 6858.18 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Granite Grinding Rough making | Sq.Ft | 15.41 | 18 | 277.38 | 49.92 | 327.3 | 2.5 | 15.41 | 277.38 | 49.92 | 327.3 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Granite Table Top | Sq.Ft | 4.33 | 585 | 2533.05 | 455.94 | 2988.99 | 2.5 | 4.33 | 2533.05 | 455.94 | 2988.99 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Department Labour - Day | Day | 1.5 | 1134 | 1701 | 306.18 | 2007.18 | 0 | 1.5 | 1701 | 306.18 | 2007.18 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | SOC. M. Civil Work Maintenace | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Edge Polish - BCE | R.Ft | 38.81 | 33.07 | 1283.45 | 231.02 | 1514.47 | 2.5 | 38.81 | 1283.45 | 231.02 | 1514.47 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | B.C. Elevation Features | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Dado Fixing | Sq.Ft | 15.41 | 153 | 2357.73 | 424.4 | 2782.13 | 2.5 | 15.41 | 2357.73 | 424.4 | 2782.13 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 503 | 0 | 25 May 2023 | R K INTERIOR | Shivaji Nagar Salgavkar home flooring work | Granite Shelf | Sq.Ft | 14 | 180 | 2520 | 453.6 | 2973.6 | 2.5 | 14 | 2520 | 453.6 | 2973.6 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | 11 TILING WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 504 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | Wetal Sir Home-Bathroom Tile breaking &W/P work | Mason - DCW | No. | 2 | 1200 | 2400 | 0 | 2400 | 0 | 2 | 2400 | 0 | 2400 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 27 Jun 2023 |  | DEV. Compound Wall | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 504 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | Wetal Sir Home-Bathroom Tile breaking &W/P work | Transportaion | No. | 1 | 100 | 100 | 0 | 100 | 0 | 1 | 100 | 0 | 100 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 27 Jun 2023 |  | B.C. Rework/Extrawork | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 504 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | Wetal Sir Home-Bathroom Tile breaking &W/P work | Contractor Profit-Mkt | No. | 1 | 100 | 100 | 0 | 100 | 0 | 1 | 100 | 0 | 100 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 27 Jun 2023 |  | MKT. Marketing Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 504 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | Wetal Sir Home-Bathroom Tile breaking &W/P work | Breaking Work. | No. | 1 | 1300 | 1300 | 0 | 1300 | 0 | 1 | 1300 | 0 | 1300 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 27 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 504 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | Wetal Sir Home-Bathroom Tile breaking &W/P work | Male Coolie | No. | 2 | 550 | 1100 | 0 | 1100 | 0 | 2 | 1100 | 0 | 1100 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 27 Jun 2023 |  | DEV. Compound Wall | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 505 | 1 | 26 May 2023 | PRAKASH CONTRACTOR | Lashkar Police Station Work | Furniture Shifting work- AIE | No. | 4 | 650 | 2600 | 0 | 2600 | 0 | 4 | 2600 | 0 | 2600 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 505 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | One Boat Club-Dpt Labour Work | Male Coolie | No. | 29 | 550 | 15950 | 0 | 15950 | 0 | 29 | 15950 | 0 | 15950 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | DEV. Compound Wall | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 505 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | One Boat Club-Dpt Labour Work | Contractor Profit-Mkt | No. | 1 | 1450 | 1450 | 0 | 1450 | 0 | 1 | 1450 | 0 | 1450 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | MKT. Marketing Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 505 | 1 | 26 May 2023 | PRAKASH CONTRACTOR | Lashkar Police Station Work | Breaker with Operator | Day | 1 | 1300 | 1300 | 0 | 1300 | 0 | 1 | 1300 | 0 | 1300 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 505 | 1 | 26 May 2023 | PRAKASH CONTRACTOR | Lashkar Police Station Work | Furniture Shifting work- AIE | No. | 4 | 650 | 2600 | 0 | 2600 | 0 | 4 | 2600 | 0 | 2600 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 505 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | One Boat Club-Dpt Labour Work | Transport Charges | No. | 1 | 1450 | 1450 | 0 | 1450 | 0 | 1 | 1450 | 0 | 1450 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 505 | 1 | 26 May 2023 | PRAKASH CONTRACTOR | Lashkar Police Station Work | PCC | Sq.Ft | 99 | 6 | 594 | 0 | 594 | 2.5 | 99 | 594 | 0 | 594 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 505 | 1 | 26 May 2023 | PRAKASH CONTRACTOR | Lashkar Police Station Work | Tractor Trip - DCW | Trips | 1 | 1200 | 1200 | 0 | 1200 | 0 | 1 | 1200 | 0 | 1200 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 505 | 1 | 26 May 2023 | PRAKASH CONTRACTOR | Lashkar Police Station Work | IPS Flooring - ULT | Sq.Ft | 99 | 20 | 1980 | 0 | 1980 | 2.5 | 99 | 1980 | 0 | 1980 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 May 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 505 | 0 | 26 May 2023 | PRAKASH CONTRACTOR | One Boat Club-Dpt Labour Work | Breaking Work. | No. | 11 | 1300 | 14300 | 0 | 14300 | 0 | 11 | 14300 | 0 | 14300 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 30 May 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 506 | 0 | 27 May 2023 | SIDDHIVINAYAK ENTERPRISES | Goel House - AC Work | 410 A Gas (M) | Kgs | 15 | 950 | 14250 | 2565 | 16815 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 506 | 0 | 27 May 2023 | SIDDHIVINAYAK ENTERPRISES | Goel House - AC Work | Refrigerant Piping (L+M) | Mtrs | 6 | 800 | 4800 | 864 | 5664 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 506 | 0 | 27 May 2023 | SIDDHIVINAYAK ENTERPRISES | Goel House - AC Work | AC Installation & Commissioning (L) | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT GORE |  | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Un-Approved |  | 1900-01-01
GANGA ASMI | 507 | 0 | 30 May 2023 | VIJAY MOHITE | Tan. Civil Work | MS Barrication work (M+L) | Sq.Ft | 2400 | 225 | 540000 | 0 | 540000 | 2.5 | 2400 | 540000 | 0 | 540000 | 0 | 0 |  | 100 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 507 | 1 | 30 May 2023 | VIJAY MOHITE | Tan. Civil Work | MS Barrication work (M+L) | Sq.Ft | 1691 | 225 | 380475 | 0 | 380475 | 2.5 | 1691 | 380475 | 0 | 380475 | 0 | 0 |  | 100 |  | DUSHANT GORE | DUSHANT GORE | construction open | 30 May 2023 |  | No category | Approved | DUSHANT GORE | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 12622.46 | 5 | 63112.3 | 11360.22 | 74472.52 | 2.5 | 0 | 0 | 0 | 0 | 12622.46 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 12592.59 | 5 | 62962.95 | 11333.34 | 74296.29 | 2.5 | 0 | 0 | 0 | 0 | 12592.59 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Parking plinth beam | RCC Beam | Sq.Ft | 11008.18 | 55 | 605449.9 | 108980.98 | 714430.88 | 2.5 | 11008.158 | 605448.69 | 108980.76 | 714429.45 | 0.022 | 1.43 |  | 99.9998 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 11008.18 | 5 | 55040.9 | 9907.36 | 64948.26 | 2.5 | 0 | 0 | 0 | 0 | 11008.18 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 11008.18 | 41 | 451335.38 | 81240.36 | 532575.74 | 2.5 | 3632.6994 | 148940.68 | 26809.32 | 175750 | 7375.4806 | 356825.74 |  | 33 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Parking Dressing,Levelling & Cleaning | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 11008.18 | 6 | 66049.08 | 11888.84 | 77937.92 | 2.5 | 11008.18 | 66049.08 | 11888.84 | 77937.92 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 01 EARTHWORK & ROADWORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6311.23 | 164.16 | 1036019.96 | 186483.6 | 1222503.56 | 2.5 | 5364.5455 | 880616.97 | 158511.06 | 1039128.03 | 946.6845 | 183375.53 |  | 85 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6296.29 | 195.23 | 1229237.29 | 221262.72 | 1450500.01 | 2.5 | 5037.032 | 983389.83 | 177010.16 | 1160399.99 | 1259.258 | 290100.02 |  | 80 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6311.23 | 164.16 | 1036019.96 | 186483.6 | 1222503.56 | 2.5 | 5680.1 | 932416.82 | 167835.02 | 1100251.84 | 631.13 | 122251.73 |  | 89.9999 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6296.3 | 195.23 | 1229239.24 | 221263.06 | 1450502.3 | 2.5 | 5351.855 | 1044853.36 | 188073.6 | 1232926.96 | 944.445 | 217575.35 |  | 85 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6296.29 | 220 | 1385183.8 | 249333.08 | 1634516.88 | 2.5 | 0 | 0 | 0 | 0 | 6296.29 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P2 Lvl - 1sr RCC Slab Rate Diff. Due Height | RCC Rate Diferance BC | Sq.Ft | 3275.075 | 235 | 769642.63 | 138535.68 | 908178.31 | 2.5 | 3275.075 | 769642.63 | 138535.68 | 908178.31 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | B.C. RCC Superstructure | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6296.29 | 174.12 | 1096297.42 | 197333.54 | 1293630.96 | 2.5 | 4722.2175 | 822223.07 | 148000.16 | 970223.23 | 1574.0725 | 323407.74 |  | 75 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 12562.13 | 5 | 62810.65 | 11305.92 | 74116.57 | 2.5 | 0 | 0 | 0 | 0 | 12562.13 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 12592.59 | 5 | 62962.95 | 11333.34 | 74296.29 | 2.5 | 0 | 0 | 0 | 0 | 12592.59 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 11008.18 | 5 | 55040.9 | 9907.36 | 64948.26 | 2.5 | 0 | 0 | 0 | 0 | 11008.18 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5504.09 | 151.83 | 835696.99 | 150425.46 | 986122.45 | 2.5 | 4952.863 | 752003.1 | 135360.56 | 887363.66 | 551.227 | 98758.8 |  | 89.9851 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P5 Lvl - 4th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 12592.59 | 5 | 62962.95 | 11333.34 | 74296.29 | 2.5 | 0 | 0 | 0 | 0 | 12592.59 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6296.3 | 220 | 1385186 | 249333.48 | 1634519.48 | 2.5 | 0 | 0 | 0 | 0 | 6296.3 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 12592.59 | 5 | 62962.95 | 11333.34 | 74296.29 | 2.5 | 0 | 0 | 0 | 0 | 12592.59 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6296.3 | 174.12 | 1096299.16 | 197333.84 | 1293633 | 2.5 | 5666.67 | 986669.25 | 177600.46 | 1164269.71 | 629.63 | 129363.3 |  | 90 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 12562.13 | 5 | 62810.65 | 11305.92 | 74116.57 | 2.5 | 0 | 0 | 0 | 0 | 12562.13 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Parking PCC Work | PCC | Sq.Ft | 11008.18 | 5 | 55040.9 | 9907.36 | 64948.26 | 2.5 | 11008.18 | 55040.9 | 9907.36 | 64948.26 | 0 | 0 |  | 100 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | B.C. Building Common Items | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P4 Lvl - 3rd RCC Slab, beam, ST, Shear wall | Schedule- BC | Sq.Ft | 12592.59 | 5 | 62962.95 | 11333.34 | 74296.29 | 2.5 | 0 | 0 | 0 | 0 | 12592.59 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | B.C. BBM, Plaster, POP | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P2 Lvl - 1st RCC slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 5504.09 | 151.83 | 835696.99 | 150425.46 | 986122.45 | 2.5 | 4952.863 | 752003.1 | 135360.56 | 887363.66 | 551.227 | 98758.8 |  | 89.9851 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P6 Lvl - 5th RCC Slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 12592.59 | 5 | 62962.95 | 11333.34 | 74296.29 | 2.5 | 0 | 0 | 0 | 0 | 12592.59 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Parking Footing & Column | Footing & Column | Sq.Ft | 11008.18 | 50 | 550409 | 99073.62 | 649482.62 | 2.5 | 11007.726 | 550386.3 | 99069.54 | 649455.84 | 0.454 | 26.78 |  | 99.9959 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - P3 Lvl - 2nd RCC slab, beam, ST, Shear wall | Quality (BC) | Sq.Ft | 12622.46 | 5 | 63112.3 | 11360.22 | 74472.52 | 2.5 | 0 | 0 | 0 | 0 | 12622.46 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6281.06 | 240.98 | 1513609.84 | 272449.78 | 1786059.62 | 2.5 | 0 | 0 | 0 | 0 | 6281.06 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 508 | 0 | 30 May 2023 | KSHITEEJ ENTERPRISES | Wing 2 - Podium Flr - 6th RCC Slab, beam, ST, Shear wall | RCC Superstructure (B-up area) | Sq.Ft | 6281.07 | 240.98 | 1513612.25 | 272450.2 | 1786062.45 | 2.5 | 0 | 0 | 0 | 0 | 6281.07 | 0 |  | 0 |  | DUSHANT GORE | chetan jewalikar | construction open | 02 Jun 2023 |  | 02 RCC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 509 | 0 | 03 Jun 2023 | JAISAN | One Boat Club Rabit shifting work by tractor | Tractor Trips - SOS | No. | 36 | 500 | 18000 | 0 | 18000 | 0 | 36 | 18000 | 0 | 18000 | 0 | 0 |  | 100 |  | DUSHANT GORE | Swapnil Erande | construction open | 22 Jun 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 6300 | 41300 | 0 | -6300 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 6300 | 41300 | 0 | -6300 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 6300 | 41300 | 0 | -6300 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 6300 | 41300 | 0 | -6300 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 0 | 35000 | 0 | 6300 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 1 | 35000 | 6300 | 41300 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 1 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | DUSHANT.GORE | 05 Aug 2024
GANGA ASMI | 510 | 0 | 06 Jun 2023 | UMESH SHANTARAM VASTE | Legal Consultancy | Legal Consultancy | Month | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 6300 | 41300 | 0 | -6300 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Jun 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 511 | 1 | 10 Jun 2023 | A B SERVICES | Site Expenses 125 KVA DG Rent | DG Hiring Charges | Month | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Jun 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 511 | 0 | 10 Jun 2023 | A B SERVICES | Site Expenses 125 KVA DG Rent | DG Hiring Charges | Month | 1 | 25000 | 25000 | 4500 | 29500 | 0 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Jun 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 511 | 0 | 10 Jun 2023 | A B SERVICES | Site Expenses 125 KVA DG Rent | Transport Charges | No. | 1 | 7000 | 7000 | 1260 | 8260 | 0 | 1 | 7000 | 1260 | 8260 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 21 Jun 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 512 | 0 | 17 Jun 2023 | KUMPENNY SOLUTIONS | PRINTING PRINTING-NO.-(NA) | ARTICLE / WRITE UP / CONTENT / ONLINE - OFFILINE PR / ORM / | No. | 0 | 33000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | REAL RICH BOOKLET TRANSLET IN HINDI AND MARATHI (TOTAL 165 PAGES X @200/- PER PAGE + TAX. + 50% ADVANCE PAYMENT | 0 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 21 Jun 2023 |  | MKT. Media | Cancelled | sunita shirolkar | 02 Sep 2023
GANGA ASMI | 513 | 0 | 17 Jun 2023 | TRIVIUM MEDIA GROUP | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 3 | 80000 | 240000 | 43200 | 283200 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | MONTHLY SOCIAL MEDIA CHAEGES AS ON 01ST JULY 2023 TO 30TH SEPT. 2023 @ 80000/- + TAX (GOEL GANGA GROUP + REAL RICH + ATUL GOEL | 0 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 04 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 514 | 0 | 21 Jun 2023 | LAXMI ELECTRICALS ENTERPRISES | Earthing Work For DG,Crane,Steel Yard | GI Strip 25 x 5mm (M+L) | Mtrs | 0 | 132 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Jul 2023 |  | No category | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ASMI | 514 | 0 | 21 Jun 2023 | LAXMI ELECTRICALS ENTERPRISES | Earthing Work For DG,Crane,Steel Yard | Pit Excavation - BC | No. | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Jul 2023 |  | B.C. RCC Substructure | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ASMI | 514 | 0 | 21 Jun 2023 | LAXMI ELECTRICALS ENTERPRISES | Earthing Work For DG,Crane,Steel Yard | GI Strip fixing-(m+l)- BC | R.Ft | 0 | 132 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 03 Jul 2023 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 22 Jun 2023
GANGA ASMI | 514 | 0 | 21 Jun 2023 | LAXMI ELECTRICALS ENTERPRISES | Earthing Work For DG,Crane,Steel Yard | Earthing work(m+l)- BC | No. | 30 | 4400 | 132000 | 23760 | 155760 | 2.5 | 24 | 105600 | 19008 | 124608 | 6 | 31152 |  | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Jul 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 514 | 0 | 21 Jun 2023 | LAXMI ELECTRICALS ENTERPRISES | Earthing Work For DG,Crane,Steel Yard | Pit Excavation - BC | No. | 30 | 1100 | 33000 | 5940 | 38940 | 0 | 24 | 26400 | 4752 | 31152 | 6 | 7788 |  | 80 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Jul 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 514 | 0 | 21 Jun 2023 | LAXMI ELECTRICALS ENTERPRISES | Earthing Work For DG,Crane,Steel Yard | Earthing work(m+l)- BC | No. | 0 | 4800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Jul 2023 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 03 Jul 2023
GANGA ASMI | 514 | 0 | 21 Jun 2023 | LAXMI ELECTRICALS ENTERPRISES | Earthing Work For DG,Crane,Steel Yard | GI Strip 25 x 5mm (M+L) | Mtrs | 185 | 121 | 22385 | 4029.3 | 26414.3 | 2.5 | 163.5 | 19783.5 | 3561.04 | 23344.54 | 21.5 | 3069.76 |  | 88.3784 |  | DUSHANT.GORE | Swapnil Erande | construction open | 03 Jul 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 23 Jun 2023
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 350 | 280 | 98000 | 17640 | 115640 | 0 | 350 | 98000 | 17640 | 115640 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 23 Jun 2023
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 23 Jun 2023
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 410 | 280 | 114800 | 20664 | 135464 | 0 | 409 | 114520 | 20613.6 | 135133.6 | 1 | 330.4 |  | 99.7561 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 950 | 280 | 266000 | 47880 | 313880 | 0 | 884 | 247520 | 44553.6 | 292073.6 | 66 | 21806.4 |  | 93.0526 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 100 | 280 | 28000 | 5040 | 33040 | 0 | 100 | 28000 | 5040 | 33040 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 1 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 230 | 280 | 64400 | 11592 | 75992 | 0 | 99.75 | 27930 | 5027.4 | 32957.4 | 130.25 | 43034.6 |  | 43.3696 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 1 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 200 | 280 | 56000 | 10080 | 66080 | 0 | 200 | 56000 | 10080 | 66080 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 2 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 300 | 280 | 84000 | 15120 | 99120 | 0 | 0 | 0 | 0 | 0 | 300 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 2 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 20 | 280 | 5600 | 1008 | 6608 | 0 | 20 | 5600 | 1008 | 6608 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 30 | 280 | 8400 | 1512 | 9912 | 0 | 30 | 8400 | 1512 | 9912 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 1 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 270 | 280 | 75600 | 13608 | 89208 | 0 | 270 | 75600 | 13608 | 89208 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 23 Jun 2023
GANGA ASMI | 515 | 1 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 150 | 280 | 42000 | 7560 | 49560 | 0 | 150 | 42000 | 7560 | 49560 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 2 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 630 | 280 | 176400 | 31752 | 208152 | 0 | 339.38 | 95026.4 | 17104.74 | 112131.14 | 290.62 | 96020.86 |  | 53.8698 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 23 Jun 2023
GANGA ASMI | 515 | 2 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 667 | 280 | 186760 | 33616.8 | 220376.8 | 0 | 450 | 126000 | 22680 | 148680 | 217 | 71696.8 |  | 67.4663 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 441 | 280 | 123480 | 22226.4 | 145706.4 | 0 | 441 | 123480 | 22226.4 | 145706.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 515 | 0 | 23 Jun 2023 | RAISING INFRATECH SERVICES | Aluform Accessories | Aluform Accessories | Kgs | 0 | 280 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Jun 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Cancelled | DUSHANT.GORE | 23 Jun 2023
GANGA ASMI | 516 | 0 | 23 Jun 2023 | SITA DEVI MAGARAM JANGID | Sales Office Carpentary & Plumbing work | Panelling work (L) | R.Ft | 48 | 150 | 7200 | 0 | 7200 | 2.5 | 25.22 | 3783 | 0 | 3783 | 22.78 | 3417 |  | 52.5417 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 516 | 1 | 23 Jun 2023 | SITA DEVI MAGARAM JANGID | Sales Office Carpentary & Plumbing work | 3 inch MDF Partition(L) | Sq.Ft | 273.65 | 150 | 41047.5 | 0 | 41047.5 | 2.5 | 273.65 | 41047.5 | 0 | 41047.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 516 | 0 | 23 Jun 2023 | SITA DEVI MAGARAM JANGID | Sales Office Carpentary & Plumbing work | Glass Door fixing | No. | 5 | 3000 | 15000 | 0 | 15000 | 0 | 1 | 3000 | 0 | 3000 | 4 | 12000 |  | 20 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 516 | 0 | 23 Jun 2023 | SITA DEVI MAGARAM JANGID | Sales Office Carpentary & Plumbing work | Plywood Door (L) | No. | 2 | 3500 | 7000 | 0 | 7000 | 2.5 | 2 | 7000 | 0 | 7000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 516 | 0 | 23 Jun 2023 | SITA DEVI MAGARAM JANGID | Sales Office Carpentary & Plumbing work | 5" MDF Partition (L) | Sq.Ft | 1320 | 175 | 231000 | 0 | 231000 | 2.5 | 1320 | 231000 | 0 | 231000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 516 | 0 | 23 Jun 2023 | SITA DEVI MAGARAM JANGID | Sales Office Carpentary & Plumbing work | Glass Partition (L) | Sq.Ft | 229 | 100 | 22900 | 0 | 22900 | 2.5 | 195.41 | 19541 | 0 | 19541 | 33.59 | 3359 |  | 85.3319 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 516 | 1 | 23 Jun 2023 | SITA DEVI MAGARAM JANGID | Sales Office Carpentary & Plumbing work | 5" MDF Partition (L) | Sq.Ft | 417.42 | 175 | 73048.5 | 0 | 73048.5 | 2.5 | 417.42 | 73048.5 | 0 | 73048.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 516 | 0 | 23 Jun 2023 | SITA DEVI MAGARAM JANGID | Sales Office Carpentary & Plumbing work | 3" MDF Partition (L) | No. | 249 | 150 | 37350 | 0 | 37350 | 2.5 | 249 | 37350 | 0 | 37350 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Jun 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 517 | 0 | 24 Jun 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 21 | 60000 | 1260000 | 226800 | 1486800 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES AS PERIOD 21.06.2023 TO 20.09.2023 AT PIMPALE NILAKH, NEAR KOLTE PATIL 24 K PROJECT, TRAFFIC FROM WAKAD TO BANER SIZE AS 30 X 30 SQ FT. NONLIT @ 60000/- + TAX PER MONTH | 0 |  | TEJAS RAVERKAR |  | construction open | 1900-01-01 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 518 | 2 | 24 Jun 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 80000 | 240000 | 43200 | 283200 | 0 | 3 | 240000 | 43199.98 | 283199.98 | 0 | 0.02 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES AS PERIOD 21.06.2023 TO 20.09.2023 AT 1) HINJEWADI - BHUMKAR CHOWK ROAD, NEAR ORRITTEL HOTEL, TRAFFIC HINJEWADI TO BHUMKAR CHOWK SIZE AS 60 X 42 @ 80000/- + TAX PER MONTH | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 518 | 1 | 24 Jun 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 75000 | 225000 | 40500 | 265500 | 0 | 3 | 225000 | 40499.98 | 265499.98 | 0 | 0.02 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES AS PERIOD 21.06.2023 TO 20.09.2023 AT 1) HINJEWADI, NEAR SHEL PETROL PUMP, TRAFFIC FROM HINJEWADI TO PUNE SIZE AS 60 X 30 SQ FT. @ 75000/- + TAX PER MONTH | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 518 | 4 | 24 Jun 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 50000 | 150000 | 27000 | 177000 | 0 | 3 | 150000 | 27000.02 | 177000.02 | 0 | -0.02 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES AS PERIOD 21.06.2023 TO 20.09.2023 AT 1) MAHALUNGE AT GODREJ PROJECT ENTRANCE TRAFFIC FROM GODREJ TO MAHALUNGE SIZE AS 30 X 30 SQ FT @ 50000/- + TAX PER MONTH | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 518 | 3 | 24 Jun 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 20000 | 60000 | 10800 | 70800 | 0 | 3 | 60000 | 10800 | 70800 | 0 | 0 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES AS PERIOD 21.06.2023 TO 20.09.2023 AT 1) MAHALUNGE AT GODREJ PROJECT ENTRANCE TRAFFIC FROM MAHALUNGE TO GODREJ SIZE AS 30 X 30 SQ FT @ 20000/- + TAX PER MONTH | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 518 | 0 | 24 Jun 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 60000 | 180000 | 32400 | 212400 | 0 | 3 | 180000 | 32399.98 | 212399.98 | 0 | 0.02 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES AS PERIOD 21.06.2023 TO 20.09.2023 AT 1) PIMPALE NILAKH, NEAR KOLTE PATIL 24 K PROJECT, TRAFFIC FROM WAKAD TO BANER SIZE AS 30 X 30 SQ FT. NONLIT @ 60000/- + TAX PER MONTH, | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 518 | 5 | 24 Jun 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 60000 | 180000 | 32400 | 212400 | 0 | 3 | 180000 | 32399.98 | 212399.98 | 0 | 0.02 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES AS PERIOD 21.06.2023 TO 20.09.2023 AT 1) HINJEWADI WIPRO CHOWK TRAFFIC FROM HINJEWADI TO PUNE SIZE AS 40 X 40 SQ FT @ 60000/- + TAX PER MONTH | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 518 | 6 | 24 Jun 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 40000 | 120000 | 21600 | 141600 | 0 | 3 | 120000 | 21600 | 141600 | 0 | 0 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES AS PERIOD 21.06.2023 TO 20.09.2023 AT 1) WAKAD FLYOVER TRAFFIC FROM PUNE TO HINJEWADI SIZE AS 30 X 30 SQ FT @ 40000/- + TAX PER MONTH | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 519 | 1 | 26 Jun 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 65000 | 195000 | 35100 | 230100 | 0 | 3 | 195000 | 35099.98 | 230099.98 | 0 | 0.02 | GANGA ASMI WAKAD OUTDOOR HOARDING DISPLAY BRANDING MONTHLY BASIS CHARGES AT 1) @ BHUMKAR CHOWK, NEAR OLYMPLIA PROJECTS, OPP. MAMTA NAGAR, WAKAD, FACING HINJEWADI IT PARK SIZE AS 60 X 30 SQ FT. @ 65000/- + TAX PER MONTH PERIOD AS ON 21/06/2023 TO 20/09/2023 | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 519 | 0 | 26 Jun 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 50000 | 150000 | 27000 | 177000 | 0 | 3 | 150000 | 27000.02 | 177000.02 | 0 | -0.02 | GANGA ASMI WAKAD OUTDOOR HOARDING DISPLAY BRANDING MONTHLY BASIS CHARGES AT 1) HINJEWADI IT PARK ROAD, NEAR BANK OF MAHARASHTRA FACING WAKAD SIZE AS 35 X 42 SQ FT. @ 50000/- + TAX PERIOD AS ON 21/06/2023 TO 20/09/2023 | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 520 | 0 | 29 Jun 2023 | METAPHORS | Goel House Consultancy charges | Interior Designing Consultancy | Sq.Ft | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 04 Jul 2024 |  | Consultancy Interior Designing | Cancelled | DUSHANT.GORE | 20 Jul 2023
GANGA ASMI | 520 | 0 | 29 Jun 2023 | METAPHORS | Goel House Consultancy charges | Interior Designing Consultancy | Sq.Ft | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | consultancy | 04 Jul 2024 |  | Consultancy Interior Designing | Cancelled | DUSHANT.GORE | 29 Jun 2023
GANGA ASMI | 520 | 0 | 29 Jun 2023 | METAPHORS | Goel House Consultancy charges | Interior Designing Consultancy | Sq.Ft | 0 | 350 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | consultancy | 04 Jul 2024 |  | Consultancy Interior Designing | Cancelled | DUSHANT.GORE | 29 Jun 2023
GANGA ASMI | 520 | 0 | 29 Jun 2023 | METAPHORS | Goel House Consultancy charges | Refurbishment Consultancy | Sq.Ft | 0 | 200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | consultancy | 04 Jul 2024 |  | 03 CONSULTANCY | Cancelled | DUSHANT.GORE | 20 Jul 2023
GANGA ASMI | 520 | 1 | 29 Jun 2023 | METAPHORS | Goel House Consultancy charges | Architectural Consultancy (No.) | No. | 0 | 2500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | consultancy | 04 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 04 Jul 2024
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Denting,Painting repair,Maintenance charges | No. | 16 | 5000 | 80000 | 0 | 80000 | 0 | 6 | 30000 | 0 | 30000 | 10 | 50000 |  | 37.5 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 6 | 10800 | 0 | 10800 | 2 | 3600 |  | 75 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 6 | 10800 | 0 | 10800 | 2 | 3600 |  | 75 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 6 | 10800 | 0 | 10800 | 2 | 3600 |  | 75 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 6 | 10800 | 0 | 10800 | 2 | 3600 |  | 75 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 7 | 12600 | 0 | 12600 | 1 | 1800 |  | 87.5 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 6 | 10800 | 0 | 10800 | 2 | 3600 |  | 75 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 521 | 0 | 30 Jun 2023 | CRYSTAL CLEAR CLEANING CONCERN | Car Repair and Maintenance | Car Cleaning & Maintenance Charges | No. | 8 | 1800 | 14400 | 0 | 14400 | 0 | 6 | 10800 | 0 | 10800 | 2 | 3600 |  | 75 |  | ADITYA.CHOUGULE | chetan jewalikar | construction open | 30 Jun 2023 |  | 14 MISC WORK | Approved | chetan jewalikar | 1900-01-01
GANGA ASMI | 522 | 0 | 30 Jun 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 3 | 38000 | 114000 | 20520 | 134520 | 0 | 2.9 | 110198.73 | 19835.82 | 130034.55 | 0.1 | 4485.45 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING HOARDING DISPLAY CHARGES @ OPP. GANGA ASMI PROJECT FACING HINJEWADI SIZE AS 30 X 30 SQ FT @ RS. 38000/- + TAX PER MONTH AS ON 18/06/2023 TO 17/09/2023 | 96.6667 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 03 Jul 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 523 | 0 | 04 Jul 2023 | SWARAJ DASHARATH SHINDE | Morwadi Site Barigation | Barrication work (L) | Sq.Ft | 5000 | 20 | 100000 | 0 | 100000 | 2.5 | 5000 | 100000 | 0 | 100000 | 0 | 0 | Overheads,Supervision,loading,unloading,shifting,transportation,fabrication with all tools,equipments,accessories and contractor profit including. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jul 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 524 | 0 | 04 Jul 2023 | SWARAJ DASHARATH SHINDE | Morwadi Site Barigation | Barrication work (M) | Sq.Ft | 5000 | 90 | 450000 | 0 | 450000 | 0 | 5000 | 450000 | 0 | 450000 | 0 | 0 | Overheads,Supervision,loading,unloading,shifting,transportation,fabrication with all tools,equipments,accessories and contractor profit including. | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 12 Jul 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 525 | 0 | 07 Jul 2023 | EHS Matrix Private Limited | Morwadi Air, Noise, Water, Soil Test Report | Soil Analysis Test- SOS | No. | 16 | 1500 | 24000 | 4320 | 28320 | 0 | 4 | 6000 | 1080 | 7080 | 12 | 21240 |  | 25 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 525 | 0 | 07 Jul 2023 | EHS Matrix Private Limited | Morwadi Air, Noise, Water, Soil Test Report | Sewage Analysis-SOS | No. | 8 | 1200 | 9600 | 1728 | 11328 | 0 | 2 | 2400 | 432 | 2832 | 6 | 8496 |  | 25 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 525 | 0 | 07 Jul 2023 | EHS Matrix Private Limited | Morwadi Air, Noise, Water, Soil Test Report | Effluent Sample | No. | 8 | 1200 | 9600 | 1728 | 11328 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 525 | 0 | 07 Jul 2023 | EHS Matrix Private Limited | Morwadi Air, Noise, Water, Soil Test Report | Water Testing report - SOS | No. | 48 | 1000 | 48000 | 8640 | 56640 | 0 | 3 | 3000 | 540 | 3540 | 45 | 53100 |  | 6.25 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 525 | 0 | 07 Jul 2023 | EHS Matrix Private Limited | Morwadi Air, Noise, Water, Soil Test Report | NOise Test Day SOS | No. | 40 | 100 | 4000 | 720 | 4720 | 0 | 6 | 600 | 108 | 708 | 34 | 4012 |  | 15 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 525 | 0 | 07 Jul 2023 | EHS Matrix Private Limited | Morwadi Air, Noise, Water, Soil Test Report | Stack Monitoring Report SOS | No. | 20 | 900 | 18000 | 3240 | 21240 | 0 | 2 | 1800 | 324 | 2124 | 18 | 19116 |  | 10 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 525 | 0 | 07 Jul 2023 | EHS Matrix Private Limited | Morwadi Air, Noise, Water, Soil Test Report | Noise Test Night SOS | No. | 40 | 100 | 4000 | 720 | 4720 | 0 | 6 | 600 | 108 | 708 | 34 | 4012 |  | 15 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 525 | 0 | 07 Jul 2023 | EHS Matrix Private Limited | Morwadi Air, Noise, Water, Soil Test Report | Air Test SOS | No. | 20 | 1500 | 30000 | 5400 | 35400 | 0 | 6 | 9000 | 1620 | 10620 | 14 | 24780 |  | 30 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 526 | 0 | 11 Jul 2023 | PLANEDGE CONSULTANTS PVT LTD | Project Management Consultancy | Project Management Consultancy. | No. | 0 | 1312000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 11 Jul 2023 |  | No category | Cancelled | ADITYA.CHOUGULE | 11 Jul 2023
GANGA ASMI | 526 | 0 | 11 Jul 2023 | PLANEDGE CONSULTANTS PVT LTD | Project Management Consultancy | Project Management Consultancy. | No. | 1 | 1355932 | 1355932 | 244067.76 | 1599999.76 | 0 | 1 | 1355932 | 244067.76 | 1599999.76 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Jul 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 527 | 0 | 12 Jul 2023 | YASH AQUA DYNAMIC | GH Rennovation Heat Pump & Ozone generator for swimming Pool | Installation & Plumbing charges | No. | 1 | 30000 | 30000 | 5400 | 35400 | 0 | 1 | 30000 | 5400 | 35400 | 0 | 0 |  | 100 |  | Sanket Patil | Swapnil Erande | construction open | 12 Jul 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 527 | 0 | 12 Jul 2023 | YASH AQUA DYNAMIC | GH Rennovation Heat Pump & Ozone generator for swimming Pool | Transport Charges | No. | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | Sanket Patil | Swapnil Erande | construction open | 12 Jul 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 528 | 0 | 13 Jul 2023 | PRAKASH CONTRACTOR | Goel House (L) Gym Room- Dpt Labour Work | Breaker | Day | 9 | 1300 | 11700 | 0 | 11700 | 0 | 9 | 11700 | 0 | 11700 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 528 | 0 | 13 Jul 2023 | PRAKASH CONTRACTOR | Goel House (L) Gym Room- Dpt Labour Work | Transport Charges | No. | 1 | 3950 | 3950 | 0 | 3950 | 0 | 1 | 3950 | 0 | 3950 | 0 | 0 | 79 Nos x 50rs = 3950 /- | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 528 | 0 | 13 Jul 2023 | PRAKASH CONTRACTOR | Goel House (L) Gym Room- Dpt Labour Work | Departmental Labour | No. | 79 | 550 | 43450 | 0 | 43450 | 0 | 79 | 43450 | 0 | 43450 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 528 | 0 | 13 Jul 2023 | PRAKASH CONTRACTOR | Goel House (L) Gym Room- Dpt Labour Work | Breaker | Day | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 14 Jul 2023
GANGA ASMI | 528 | 0 | 13 Jul 2023 | PRAKASH CONTRACTOR | Goel House (L) Gym Room- Dpt Labour Work | Contractor Profit-Mkt | No. | 1 | 3950 | 3950 | 0 | 3950 | 0 | 1 | 3950 | 0 | 3950 | 0 | 0 | 79 Nos x 50rs = 3950 /- | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 529 | 0 | 18 Jul 2023 | R.T.S. STEEL SERVICES | GH Laser Jali Pannel Rust removal, Rustproofing,Recoating & | Galvanization work | Sq.Ft | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Including Transportation, Loading, Unloading, Scaffolding fixing and removing work. | 0 |  | ADITYA.CHOUGULE |  | construction open | 19 Jul 2023 |  | No category | Cancelled | ADITYA.CHOUGULE | 19 Jul 2023
GANGA ASMI | 529 | 0 | 18 Jul 2023 | R.T.S. STEEL SERVICES | GH Laser Jali Pannel Rust removal, Rustproofing,Recoating & | Galvanization work | Sq.Ft | 6228 | 250 | 1557000 | 280260 | 1837260 | 2.5 | 0 | 0 | 0 | 0 | 6228 | 0 | Including Transportation, Loading, Unloading, Scaffolding fixing & removing work. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 530 | 0 | 18 Jul 2023 | NAMANNA RATHOD | GH Rabbit Shifting Work | Rabbit Shifting - BRE | Trips | 11 | 1000 | 11000 | 0 | 11000 | 0 | 11 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jul 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 531 | 0 | 18 Jul 2023 | JAY GANESH ENTERPRISES | GH Gym Room Deck Slab Casting Work | PCC Work | Sq.Ft | 150 | 6 | 900 | 0 | 900 | 2.5 | 150 | 900 | 0 | 900 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 531 | 0 | 18 Jul 2023 | JAY GANESH ENTERPRISES | GH Gym Room Deck Slab Casting Work | Labour Lumpsum - DER | No. | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | DEV. Extrawork/Rework | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 532 | 0 | 18 Jul 2023 | J K INTERIOR | GH Meeting Room 4 False Ceiling Work | False Ceiling (m+l) - BRE | Sq.Ft | 0 | 75 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 31 Jul 2023 |  | B.C. Rework/Extrawork | Cancelled | ADITYA.CHOUGULE | 31 Jul 2023
GANGA ASMI | 533 | 0 | 20 Jul 2023 | VIJAY MOHITE | Talawade Barbed Wire Fencing & JCB Hiring for Plot Cleaning | Barbed Wire Fencing- SOSB | R.Ft | 2350 | 142 | 333700 | 0 | 333700 | 0 | 0 | 0 | 0 | 0 | 2350 | 0 | CC pole- 4" X 4" X 7Ft Height / pit Size 1.5ft x 1.5ft x 2ft/ concrete- 1:3:6/ Bared Wire- 12x14 Gauge- 5 Horizontal & 2 Vertical. | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 533 | 0 | 20 Jul 2023 | VIJAY MOHITE | Talawade Barbed Wire Fencing & JCB Hiring for Plot Cleaning | JCB Charges | Hrs | 40 | 750 | 30000 | 0 | 30000 | 0 | 0 | 0 | 0 | 0 | 40 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | UTI. Drainage | Un-Approved |  | 1900-01-01
GANGA ASMI | 534 | 0 | 21 Jul 2023 | OMKAR CRANES (I) PVT LTD | 180 tonnes crane hiring charges for tower crane extension | Crane Charges - | No. | 1 | 170000 | 170000 | 30600 | 200600 | 0 | 1 | 170000 | 30600 | 200600 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 28 Jul 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 535 | 0 | 24 Jul 2023 | NEELESH NANDKUMAR AGRAWAL | Project Management Consultancy | Project Management Consultancy. | No. | 9 | 100000 | 900000 | 0 | 900000 | 0 | 3 | 299999.7 | 0 | 299999.7 | 6 | 600000.3 |  | 33.3333 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 24 Jul 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 535 | 0 | 24 Jul 2023 | NEELESH NANDKUMAR AGRAWAL | Project Management Consultancy | Project Management Consultancy. | No. | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2023 |  | No category | Cancelled | ADITYA.CHOUGULE | 24 Jul 2023
GANGA ASMI | 536 | 0 | 25 Jul 2023 | SHRUSTI FLORALS | One Boat Club Plants Removing and Shifting | Removing Trees No. | No. | 0 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Cancelled | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 536 | 0 | 25 Jul 2023 | SHRUSTI FLORALS | One Boat Club Plants Removing and Shifting | Plants Removing | No. | 15 | 550 | 8250 | 0 | 8250 | 0 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 536 | 0 | 25 Jul 2023 | SHRUSTI FLORALS | One Boat Club Plants Removing and Shifting | Transportation | No. | 1 | 750 | 750 | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 537 | 0 | 25 Jul 2023 | PRAKASH CONTRACTOR | One Boat Club- Department Work | Contractor Profit-Mkt | No. | 1 | 750 | 750 | 0 | 750 | 0 | 1 | 750 | 0 | 750 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 537 | 0 | 25 Jul 2023 | PRAKASH CONTRACTOR | One Boat Club- Department Work | Transportation | No. | 1 | 750 | 750 | 0 | 750 | 0 | 1 | 750 | 0 | 750 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 537 | 0 | 25 Jul 2023 | PRAKASH CONTRACTOR | One Boat Club- Department Work | Departmental Labour - SO | No. | 15 | 550 | 8250 | 0 | 8250 | 0 | 15 | 8250 | 0 | 8250 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 537 | 0 | 25 Jul 2023 | PRAKASH CONTRACTOR | One Boat Club- Department Work | Breaker - SOS | Day | 0 | 1300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | S OH Site Staff | Cancelled | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 537 | 0 | 25 Jul 2023 | PRAKASH CONTRACTOR | One Boat Club- Department Work | Breaker - SOS | Day | 1 | 1300 | 1300 | 0 | 1300 | 0 | 1 | 1300 | 0 | 1300 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Site Staff | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 538 | 0 | 25 Jul 2023 | PATRA PLUMBING | GH Drinking and Bore Water Line Laying | Labour Lumsum | No. | 1 | 25000 | 25000 | 4500 | 29500 | 2.5 | 1 | 25000 | 4500 | 29500 | 0 | 0 | Including Transportation from Bavdhan to Goel House & return till work completion. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 539 | 0 | 25 Jul 2023 | PATILS FABRICATORS | Gym Room M.S. A/C Rack Work | Sheet Fixing - AIE | Sq.Ft | 180 | 6 | 1080 | 194.4 | 1274.4 | 2.5 | 180 | 1080 | 194.4 | 1274.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | Admin. Indirect Expenses | Approved | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 539 | 0 | 25 Jul 2023 | PATILS FABRICATORS | Gym Room M.S. A/C Rack Work | Fabrication work (L) | Kgs | 170 | 18 | 3060 | 550.8 | 3610.8 | 2.5 | 170 | 3060 | 550.8 | 3610.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | Admin. Direct Expenses | Approved | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 539 | 0 | 25 Jul 2023 | PATILS FABRICATORS | Gym Room M.S. A/C Rack Work | Jali fixing- AIE | Sq.Ft | 104 | 12 | 1248 | 224.64 | 1472.64 | 2.5 | 104 | 1248 | 224.64 | 1472.64 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | Admin. Indirect Expenses | Approved | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 539 | 0 | 25 Jul 2023 | PATILS FABRICATORS | Gym Room M.S. A/C Rack Work | Fabrication work (L) | Kgs | 435.57 | 18 | 7840.26 | 1411.24 | 9251.5 | 2.5 | 435.57 | 7840.26 | 1411.24 | 9251.5 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | Admin. Direct Expenses | Approved | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 539 | 0 | 25 Jul 2023 | PATILS FABRICATORS | Gym Room M.S. A/C Rack Work | Departmental work- SO | No. | 5 | 800 | 4000 | 720 | 4720 | 0 | 5 | 4000 | 720 | 4720 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | S OH Infrastructure | Approved | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 539 | 0 | 25 Jul 2023 | PATILS FABRICATORS | Gym Room M.S. A/C Rack Work | Sheet Removing - AIE | Sq.Ft | 180 | 4 | 720 | 129.6 | 849.6 | 0 | 180 | 720 | 129.6 | 849.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | Admin. Indirect Expenses | Approved | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 540 | 0 | 25 Jul 2023 | PATILS FABRICATORS | Gym Room M.S. A/C Rack Work | Jali Fixing (M) | Sq.Ft | 104 | 34 | 3536 | 636.48 | 4172.48 | 0 | 104 | 3536 | 636.48 | 4172.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 28 Jul 2023 |  | No category | Approved | ADITYA.CHOUGULE | 25 Jul 2023
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Top- ARW | Sq.Ft | 0 | 94.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Cancelled | ADITYA.CHOUGULE | 27 Jul 2023
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Tile Border | R.Ft | 7.4 | 126 | 932.4 | 167.84 | 1100.24 | 2.5 | 7.4 | 932.4 | 167.84 | 1100.24 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 1 | 26 Jul 2023 | R K INTERIOR | Goel House Flooring Work | Full Moulding- DWB | R.Ft | 9.75 | 115.5 | 1126.13 | 202.7 | 1328.83 | 2.5 | 9.75 | 1126.13 | 202.7 | 1328.83 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Water Body | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Demolish Work | R.Ft | 20.5 | 36.75 | 753.38 | 135.6 | 888.98 | 0 | 20.5 | 753.38 | 135.6 | 888.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Grout filling | Sq.Ft | 115.45 | 15.75 | 1818.34 | 327.3 | 2145.64 | 2.5 | 115.45 | 1818.34 | 327.3 | 2145.64 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Dado- ARW | Sq.Ft | 81.74 | 120.75 | 9870.11 | 1776.62 | 11646.73 | 2.5 | 81.74 | 9870.11 | 1776.62 | 11646.73 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Top- ARW | Sq.Ft | 42.06 | 94.5 | 3974.67 | 715.44 | 4690.11 | 2.5 | 42.06 | 3974.67 | 715.44 | 4690.11 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 1 | 26 Jul 2023 | R K INTERIOR | Goel House Flooring Work | Bull Nose Moulding | R.Ft | 6 | 89.25 | 535.5 | 96.4 | 631.9 | 2.5 | 6 | 535.5 | 96.4 | 631.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Zero Joint- Dld | R.Ft | 88.93 | 210 | 18675.3 | 3361.56 | 22036.86 | 2.5 | 88.93 | 18675.3 | 3361.56 | 22036.86 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 1 | 26 Jul 2023 | R K INTERIOR | Goel House Flooring Work | Zero Point Moulding - Mkt | R.Ft | 6 | 210 | 1260 | 226.8 | 1486.8 | 2.5 | 6 | 1260 | 226.8 | 1486.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 1 | 26 Jul 2023 | R K INTERIOR | Goel House Flooring Work | Drill Hole | No. | 100 | 136.5 | 13650 | 2457 | 16107 | 2.5 | 100 | 13650 | 2457 | 16107 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 1 | 26 Jul 2023 | R K INTERIOR | Goel House Flooring Work | Granite Round Border | R.Ft | 9.75 | 100 | 975 | 175.5 | 1150.5 | 2.5 | 0 | 0 | 0 | 0 | 9.75 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Bull Nose Moulding | R.Ft | 116.12 | 89.25 | 10363.71 | 1865.46 | 12229.17 | 2.5 | 116.12 | 10363.71 | 1865.46 | 12229.17 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Tile Top fixing | Sq.Ft | 33.02 | 52.5 | 1733.55 | 312.04 | 2045.59 | 2.5 | 33.02 | 1733.55 | 312.04 | 2045.59 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Moulding-mkt | R.Ft | 322.96 | 210 | 67821.6 | 12207.88 | 80029.48 | 2.5 | 322.96 | 67821.6 | 12207.88 | 80029.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Tile Border | R.Ft | 25.64 | 126 | 3230.64 | 581.52 | 3812.16 | 2.5 | 25.64 | 3230.64 | 581.52 | 3812.16 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Tappa-ULT | R.Ft | 12.45 | 94.5 | 1176.53 | 211.78 | 1388.31 | 2.5 | 11.45 | 1082.03 | 194.76 | 1276.79 | 1 | 111.52 |  | 91.9679 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 1 | 26 Jul 2023 | R K INTERIOR | Goel House Flooring Work | Granite Border - DCH | R.Ft | 328.66 | 94.5 | 31058.37 | 5590.5 | 36648.87 | 2.5 | 328.66 | 31058.37 | 5590.5 | 36648.87 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Window Jamb-ARW | R.Ft | 19.16 | 94.5 | 1810.62 | 325.92 | 2136.54 | 2.5 | 19.16 | 1810.62 | 325.92 | 2136.54 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 1 | 26 Jul 2023 | R K INTERIOR | Goel House Flooring Work | Wooden Tile Border | R.Ft | 108 | 126 | 13608 | 2449.44 | 16057.44 | 2.5 | 108 | 13608 | 2449.44 | 16057.44 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Demolish Work | R.Ft | 52.08 | 35 | 1822.8 | 328.1 | 2150.9 | 0 | 52.08 | 1822.8 | 328.1 | 2150.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Tappa/Riser BC | R.Ft | 0 | 94.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | ADITYA.CHOUGULE | 26 Jul 2023
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Tappa/Riser BC | R.Ft | 435.4 | 94.5 | 41145.3 | 7406.16 | 48551.46 | 2.5 | 435 | 41107.5 | 7399.36 | 48506.86 | 0.4 | 44.6 |  | 99.9081 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | L Groove - BCV | R.Ft | 9.25 | 157.5 | 1456.88 | 262.24 | 1719.12 | 2.5 | 9.25 | 1456.88 | 262.24 | 1719.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Half Moulding- ARW | R.Ft | 3.75 | 89.25 | 334.69 | 60.24 | 394.93 | 2.5 | 3.75 | 334.69 | 60.24 | 394.93 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Cutting & fixing (L) | R.Ft | 25 | 15.75 | 393.75 | 70.88 | 464.63 | 2.5 | 25 | 393.75 | 70.88 | 464.63 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Drill Hole | No. | 2 | 136.5 | 273 | 49.14 | 322.14 | 2.5 | 2 | 273 | 49.14 | 322.14 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Flooring - Dld | Sq.Ft | 14.13 | 94.5 | 1335.29 | 240.36 | 1575.65 | 2.5 | 14.13 | 1335.29 | 240.36 | 1575.65 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Champher-DCH | R.Ft | 45.08 | 89.25 | 4023.39 | 724.22 | 4747.61 | 2.5 | 45.08 | 4023.39 | 724.22 | 4747.61 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Full Moulding- DWB | R.Ft | 7.74 | 115.5 | 893.97 | 160.92 | 1054.89 | 2.5 | 7.74 | 893.97 | 160.92 | 1054.89 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Water Body | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Edge Polish- ARW | R.Ft | 109.95 | 36.75 | 4040.66 | 727.32 | 4767.98 | 2.5 | 109.95 | 4040.66 | 727.32 | 4767.98 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | Admin. Indirect Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Cobble fixing -Dld | Sq.Ft | 136.88 | 110.25 | 15091.02 | 2716.38 | 17807.4 | 2.5 | 136.88 | 15091.02 | 2716.38 | 17807.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Granite Moulding-mkt | R.Ft | 322.96 | 70 | 22607.2 | 4069.3 | 26676.5 | 2.5 | 98 | 6860 | 1234.8 | 8094.8 | 224.96 | 18581.7 |  | 30.3443 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 0 | 26 Jul 2023 | R K INTERIOR | Goel House (L) Gym Room- Tiling Work | Tile Border | R.Ft | 20.5 | 52.5 | 1076.25 | 193.72 | 1269.97 | 2.5 | 20.5 | 1076.25 | 193.72 | 1269.97 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 541 | 1 | 26 Jul 2023 | R K INTERIOR | Goel House Flooring Work | Edge Polish - BCE | R.Ft | 3.5 | 36.75 | 128.63 | 23.16 | 151.79 | 2.5 | 3.5 | 128.63 | 23.16 | 151.79 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Elevation Features | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 542 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Grid Ceiling making work (M+L) | Sq.Ft | 60 | 125 | 7500 | 1350 | 8850 | 2.5 | 60 | 7500 | 1350 | 8850 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 542 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Shetawood Patta (L) | R.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Cancelled | ADITYA.CHOUGULE | 27 Jul 2023
GANGA ASMI | 542 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Sherawood Patta (L) | R.Ft | 391 | 20 | 7820 | 1407.6 | 9227.6 | 2.5 | 391 | 7820 | 1407.6 | 9227.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 542 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Gypsum Patta Plaster (L) | R.Ft | 64 | 6 | 384 | 69.12 | 453.12 | 2.5 | 64 | 384 | 69.12 | 453.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 542 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Gypsum False Ceiling (M+L) - BC | Sq.Ft | 60 | 75 | 4500 | 810 | 5310 | 2.5 | 60 | 4500 | 810 | 5310 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 542 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Patra Finish (L) | Sq.Ft | 152 | 5 | 760 | 136.8 | 896.8 | 2.5 | 152 | 760 | 136.8 | 896.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 543 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Transportation | No. | 1 | 1500 | 1500 | 270 | 1770 | 0 | 1 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 543 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Patra Finish (M) | Sq.Ft | 152 | 5 | 760 | 136.8 | 896.8 | 0 | 152 | 760 | 136.8 | 896.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 543 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Sherawood Patta (M) | R.Ft | 391 | 60 | 23460 | 4222.8 | 27682.8 | 0 | 391 | 23460 | 4222.8 | 27682.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 543 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Shetawood Patta (M) | R.Ft | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Cancelled | ADITYA.CHOUGULE | 27 Jul 2023
GANGA ASMI | 543 | 0 | 27 Jul 2023 | J K INTERIOR | Gym Room Gypsum False Ceiling Work | Gypsum Patta Plaster (M) | R.Ft | 64 | 6 | 384 | 69.12 | 453.12 | 0 | 64 | 384 | 69.12 | 453.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 544 | 0 | 27 Jul 2023 | SAI PLUMBING WORKS | New Sales Office (Wing-1) - Pantry & Toilet | Plumbing work lumpsum- | No. | 1 | 25000 | 25000 | 4500 | 29500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | New Sales office (Wing-1) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 544 | 0 | 27 Jul 2023 | SAI PLUMBING WORKS | New Sales Office (Wing-1) - Pantry & Toilet | Core Cutting Work 8" BCE | No. | 1 | 500 | 500 | 90 | 590 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 544 | 0 | 27 Jul 2023 | SAI PLUMBING WORKS | New Sales Office (Wing-1) - Pantry & Toilet | Core Cutting Work 5" BCE | No. | 1 | 500 | 500 | 90 | 590 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 544 | 0 | 27 Jul 2023 | SAI PLUMBING WORKS | New Sales Office (Wing-1) - Pantry & Toilet | Core Cutting 4" -UTI | No. | 1 | 500 | 500 | 90 | 590 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 03 Aug 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 545 | 0 | 31 Jul 2023 | NANDLAL MAURYA | Tangewala Site Transit Camp Material | Plumbing work lumpsum- SM | No. | 1 | 25000 | 25000 | 0 | 25000 | 2.5 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 12 Aug 2023 |  | SOC. M. Civil Work Maintenace | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 546 | 0 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Granite Door Frame -BRE - | R.Ft | 105 | 50 | 5250 | 0 | 5250 | 2.5 | 97.15 | 4857.5 | 0 | 4857.5 | 7.85 | 392.5 |  | 92.5238 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 546 | 0 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Dado Fixing | Sq.Ft | 448 | 23 | 10304 | 0 | 10304 | 2.5 | 448 | 10304 | 0 | 10304 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 546 | 0 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Ceramic Flooring - BRE | Sq.Ft | 0 | 21 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 02 Aug 2023
GANGA ASMI | 546 | 0 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Vitrified Flooring 600 x 1200mm | Sq.Ft | 1750 | 23 | 40250 | 0 | 40250 | 2.5 | 1626 | 37398 | 0 | 37398 | 124 | 2852 |  | 92.9143 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 546 | 1 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Dado Fixing | Sq.Ft | 259.96 | 23 | 5979.08 | 0 | 5979.08 | 2.5 | 259.96 | 5979.08 | 0 | 5979.08 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 546 | 0 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Granite Door Frame -BRE - | R.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Cancelled | DUSHANT.GORE | 02 Aug 2023
GANGA ASMI | 546 | 0 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Kitchen Otta (L) | No. | 3 | 2500 | 7500 | 0 | 7500 | 2.5 | 3 | 7500 | 0 | 7500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 546 | 0 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Ceramic Flooring - BRE | Sq.Ft | 112 | 21 | 2352 | 0 | 2352 | 2.5 | 112 | 2352 | 0 | 2352 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 546 | 0 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Window Frame (L) | R.Ft | 32 | 50 | 1600 | 0 | 1600 | 2.5 | 32 | 1600 | 0 | 1600 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 11 TILING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 546 | 1 | 02 Aug 2023 | RAM NARESH | Tangewala Site Transit Camp Material | Ceramic Flooring - BRE | Sq.Ft | 16 | 21 | 336 | 0 | 336 | 2.5 | 16 | 336 | 0 | 336 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 547 | 0 | 02 Aug 2023 | AARYA HOME ARTS | GH Gym Room Carpentary Work | Pipe Covering Box | Sq.Ft | 225 | 180 | 40500 | 7290 | 47790 | 2.5 | 225 | 40500 | 7290 | 47790 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 547 | 0 | 02 Aug 2023 | AARYA HOME ARTS | GH Gym Room Carpentary Work | Aluminium Partition (L) | Sq.Ft | 1200 | 210 | 252000 | 45360 | 297360 | 2.5 | 1200 | 252000 | 45360 | 297360 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 547 | 0 | 02 Aug 2023 | AARYA HOME ARTS | GH Gym Room Carpentary Work | Rework | No. | 1 | 8000 | 8000 | 1440 | 9440 | 2.5 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 547 | 0 | 02 Aug 2023 | AARYA HOME ARTS | GH Gym Room Carpentary Work | Cement Sheet fixing | Sq.Ft | 260 | 30 | 7800 | 1404 | 9204 | 2.5 | 260 | 7800 | 1404 | 9204 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 547 | 0 | 02 Aug 2023 | AARYA HOME ARTS | GH Gym Room Carpentary Work | Mirror Panelling (L) | Sq.Ft | 90 | 125 | 11250 | 2025 | 13275 | 2.5 | 90 | 11250 | 2025 | 13275 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 547 | 0 | 02 Aug 2023 | AARYA HOME ARTS | GH Gym Room Carpentary Work | Ply with MDF Finish | R.Ft | 300 | 275 | 82500 | 14850 | 97350 | 2.5 | 300 | 82500 | 14850 | 97350 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 547 | 0 | 02 Aug 2023 | AARYA HOME ARTS | GH Gym Room Carpentary Work | Door Fixing (L) | No. | 5 | 1500 | 7500 | 1350 | 8850 | 2.5 | 5 | 7500 | 1350 | 8850 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 548 | 1 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Tikki Dhada (L) | Sq.Ft | 1577.64 | 11 | 17354.04 | 3123.72 | 20477.76 | 2.5 | 1577 | 17347 | 3122.46 | 20469.46 | 0.64 | 8.3 |  | 99.9594 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 548 | 0 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Tikki Dhada (L) | Sq.Ft | 359.6 | 11 | 3955.6 | 712 | 4667.6 | 2.5 | 359.6 | 3955.6 | 712 | 4667.6 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 548 | 0 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Patra Finish (L) | Sq.Ft | 137.73 | 5 | 688.65 | 123.96 | 812.61 | 2.5 | 137.73 | 688.65 | 123.96 | 812.61 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | 05 GYPSUM & PLASTER | Foreclose | DUSHANT.GORE | 23 Aug 2023
GANGA ASMI | 548 | 1 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Light Gala Cutting-BC | No. | 90 | 30 | 2700 | 486 | 3186 | 2.5 | 0 | 0 | 0 | 0 | 90 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 548 | 0 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Gypsum Board False Ceiling (L) | Sq.Ft | 2824.79 | 15 | 42371.85 | 7626.94 | 49998.79 | 2.5 | 2471.78 | 37076.7 | 6673.8 | 43750.5 | 353.01 | 6248.29 |  | 87.5031 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 549 | 1 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Tikki Dhada (M) | Sq.Ft | 1937.24 | 11 | 21309.64 | 3835.74 | 25145.38 | 0 | 1937.24 | 21309.64 | 3835.74 | 25145.38 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 549 | 0 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Gypsum Board False Ceiling (M) | Sq.Ft | 2824.79 | 60 | 169487.4 | 30507.74 | 199995.14 | 0 | 2824.79 | 169487.4 | 30507.72 | 199995.12 | 0 | 0.02 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 549 | 1 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Grid Ceiling making work (M+L) | Sq.Ft | 175.25 | 90 | 15772.5 | 2839.06 | 18611.56 | 0 | 175.25 | 15772.5 | 2839.06 | 18611.56 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 549 | 1 | 03 Aug 2023 | GUDIYA ENTERPRISES | New Sales Office (Wing-1) Gypsum Work | Patra Finish (M) | Sq.Ft | 137.73 | 3.5 | 482.06 | 86.78 | 568.84 | 0 | 137.73 | 482.06 | 86.78 | 568.84 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Aug 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 550 | 0 | 05 Aug 2023 | POOJA COMMUNICATIONS (INDIA) PVT LTD | Advertisement | Advertisement Release- | No. | 1 | 300960 | 300960 | 15048 | 316008 | 0 | 1 | 300960 | 15048 | 316008 | 0 | 0 | REAL RICH- BARNDING NEWS PAPER DISPLAY ADVERTISEMENT I TIMES OF INDIA + MAHARASHTRA TIME - PUNE EDITION ( 15TH AUGUST) SPL. SUPPLIMENT ANY RHP ADVT SIZE AS 32.9 CM (w) AND 52.5 CM (h) COLOUR ADVT. | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 08 Aug 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 551 | 0 | 16 Aug 2023 | ERA FAME MEDIA GROUP | PRINTING PRINTING-NO.-(NA) | ARTICLE / WRITE UP / CONTENT / ONLINE - OFFILINE PR / ORM / | No. | 1 | 200000 | 200000 | 10000 | 210000 | 0 | 1 | 200000 | 10000 | 210000 | 0 | 0 | MAGAZINE ADVT. IN CONSTRUCTION & ARCHITECTURE UPDATE MAGAZINE OCTOBER 2023 ISSUE ( SOLO COVER FULL PAGE- + EXCLUSIVE ADVERTORIAL OF 2 + 2 + 2 = 6 PAGES INTERVIEW +PROJECT BRANDING + 50 MAGAZINE COPIES OFFILE + ONLINE MAGAZINE MEDIA | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 09 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 552 | 0 | 16 Aug 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 15090 | 10 | 150900 | 27162 | 178062 | 0 | 11296.4653 | 112964.65 | 20333.66 | 133298.31 | 3793.5347 | 44763.69 | GANGA ASMI WAKAD PROJET HOARDING FLEX PRINT WITH MOUNT @10/- PER SQ FT. TOTAL 15090 SQ FT AREA. | 74.8606 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 28 Aug 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 26th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 3 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 2nd Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 22 Aug 2023 |  | DEV. Club House | Un-Approved |  | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 10th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 7th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 15th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 6th Slab | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 21st Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 2nd Slab | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Cancelled | DUSHANT.GORE | 06 Jun 2024
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 23rd Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 2nd Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 11th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 17th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 1 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Non Tower Area Point marking by total station | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 8th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 20th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 3rd Slab | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 5th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 37 | 3700 | 666 | 4366 | 63 | 7434 |  | 37 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 4th Slab | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 3 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 5th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 22 Aug 2023 |  | DEV. Club House | Un-Approved |  | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 2nd Slab | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 22nd Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 4th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 1st Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 200 | 100 | 20000 | 3600 | 23600 | 0 | 200 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 16th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Non Tower Area Point marking by total station | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 22 Aug 2023 |  | DEV. Club House | Cancelled | DUSHANT.GORE | 25 May 2024
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 12th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 3 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 3rd Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 22 Aug 2023 |  | DEV. Club House | Un-Approved |  | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 18th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 13th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 28th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 6th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 25th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 6th Slab | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Cancelled | DUSHANT.GORE | 06 Jun 2024
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 5th Slab | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Cancelled | DUSHANT.GORE | 06 Jun 2024
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 3rd Slab | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Cancelled | DUSHANT.GORE | 06 Jun 2024
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 5th Slab | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 3 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 Ground Flr Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 22 Aug 2023 |  | DEV. Club House | Un-Approved |  | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 1st Slab | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Cancelled | DUSHANT.GORE | 06 Jun 2024
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 1st Slab | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 24th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 27th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 19th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 3 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 4th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 22 Aug 2023 |  | DEV. Club House | Un-Approved |  | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 9th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 3rd Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 553 | 2 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Total Station Point Marking @ 4th Slab | Total Station Point marking. | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Cancelled | DUSHANT.GORE | 06 Jun 2024
GANGA ASMI | 553 | 0 | 22 Aug 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-1 14th Floor Total Station Survey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Aug 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 1 | 26 Aug 2023 | S.R.Enterprises | Goel House Anti Termite Treatment (Inside/Outside) | Anti-termite Treatment - No. | No. | 1 | 32500 | 32500 | 5850 | 38350 | 0 | 1 | 32500 | 5850 | 38350 | 0 | 0 | Chemical - Imidacloprid 30.5 % SC | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 1 | 26 Aug 2023 | S.R.Enterprises | Goel House Anti Termite Treatment (Inside/Outside) | Antitermite Treatment - BRE | Sq.Ft | 5000 | 4 | 20000 | 3600 | 23600 | 0 | 5000 | 20000 | 3600 | 23600 | 0 | 0 | Chemical - Imidacloprid 30.5 % SC | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 2 | 26 Aug 2023 | S.R.Enterprises | Goel House Anti Termite Treatment (Inside/Outside) | Anti-termite Treatment - No. | No. | 30 | 4000 | 120000 | 21600 | 141600 | 0 | 0 | 0 | 0 | 0 | 30 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.75 | 6000 | 1080 | 7080 | 0.25 | 2360 |  | 75 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.5 | 4000 | 720 | 4720 | 0.5 | 4720 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.875 | 7000 | 1260 | 8260 | 0.125 | 1180 |  | 87.5 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.625 | 5000 | 900 | 5900 | 0.375 | 3540 |  | 62.5 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.75 | 6000 | 1080 | 7080 | 0.25 | 2360 |  | 75 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 554 | 0 | 26 Aug 2023 | S.R.Enterprises | Goel House Pest Control | Pest Control | Month | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 0.375 | 3000 | 540 | 3540 | 0.625 | 5900 |  | 37.5 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 12mm dia- BC | No. | 40 | 140 | 5600 | 1008 | 6608 | 0 | 40 | 5600 | 1008 | 6608 | 0 | 0 | 12 mm TMT Bars rebarring work upto 150mm depth. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 10mm dia- BC | No. | 25 | 180 | 4500 | 810 | 5310 | 0 | 25 | 4500 | 810 | 5310 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 16mm dia- BC | No. | 18 | 450 | 8100 | 1458 | 9558 | 0 | 18 | 8100 | 1458 | 9558 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 25mm dia- BRE | No. | 0 | 1200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Cancelled | ADITYA.CHOUGULE | 28 Aug 2023
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 10mm dia- BC | No. | 54 | 180 | 9720 | 1749.6 | 11469.6 | 0 | 54 | 9720 | 1749.6 | 11469.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 20mm dia- BRE | No. | 25 | 850 | 21250 | 3825 | 25075 | 0 | 25 | 21250 | 3825 | 25075 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 12mm dia- BC | No. | 47 | 140 | 6580 | 1184.4 | 7764.4 | 0 | 47 | 6580 | 1184.4 | 7764.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 1 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing 1 Podium Floor Rebaring Work | Rebaring work 12mm- cc | No. | 56 | 125 | 7000 | 1260 | 8260 | 2.5 | 56 | 7000 | 1260 | 8260 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 12mm dia- BC | No. | 126 | 230 | 28980 | 5216.4 | 34196.4 | 0 | 126 | 28980 | 5216.4 | 34196.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 10mm dia- BC | No. | 15 | 140 | 2100 | 378 | 2478 | 0 | 15 | 2100 | 378 | 2478 | 0 | 0 | 10 mm TMT Bars rebarring work upto 150mm depth. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 1 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing 1 2nd Floor Rebaring Work | Rebaring work 12mm- cc | No. | 72 | 125 | 9000 | 1620 | 10620 | 2.5 | 40 | 5000 | 900 | 5900 | 32 | 4720 |  | 55.5556 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 1 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing 1 1st Floor Rebaring Work | Rebaring work 12mm- cc | No. | 72 | 125 | 9000 | 1620 | 10620 | 2.5 | 72 | 9000 | 1620 | 10620 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebaring work 8mm dia.- DTR | No. | 76 | 160 | 12160 | 2188.8 | 14348.8 | 0 | 76 | 12160 | 2188.8 | 14348.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 25mm dia- BRE | No. | 5 | 1200 | 6000 | 1080 | 7080 | 0 | 5 | 6000 | 1080 | 7080 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 16mm dia- BC | No. | 55 | 450 | 24750 | 4455 | 29205 | 0 | 55 | 24750 | 4455 | 29205 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 555 | 0 | 26 Aug 2023 | AVCON TECHNICS PVT LTD | Wing-1 Re-baring Work | Rebarring work 12mm dia- BC | No. | 96 | 230 | 22080 | 3974.4 | 26054.4 | 0 | 96 | 22080 | 3974.4 | 26054.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 2732.61 | 22 | 60117.42 | 10821.14 | 70938.56 | 2.5 | 0 | 0 | 0 | 0 | 2732.61 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 2840.79 | 22 | 62497.38 | 11249.52 | 73746.9 | 2.5 | 66.69 | 1467.18 | 264.1 | 1731.28 | 2774.1 | 72015.62 |  | 2.3476 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 1677.669 | 18 | 30198.04 | 5435.64 | 35633.68 | 2.5 | 0 | 0 | 0 | 0 | 1677.669 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 2840.79 | 22 | 62497.38 | 11249.52 | 73746.9 | 2.5 | 66.69 | 1467.18 | 264.1 | 1731.28 | 2774.1 | 72015.62 |  | 2.3476 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 2840.79 | 22 | 62497.38 | 11249.52 | 73746.9 | 2.5 | 66.69 | 1467.18 | 264.1 | 1731.28 | 2774.1 | 72015.62 |  | 2.3476 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | RCC Patli | R.Ft | 2723.69 | 40 | 108947.6 | 19610.56 | 128558.16 | 2.5 | 307.27 | 12290.8 | 2212.34 | 14503.14 | 2416.42 | 114055.02 |  | 11.2814 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | RCC Patli | R.Ft | 1256.96 | 40 | 50278.4 | 9050.12 | 59328.52 | 2.5 | 0 | 0 | 0 | 0 | 1256.96 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 1677.669 | 18 | 30198.04 | 5435.64 | 35633.68 | 2.5 | 30 | 540 | 97.2 | 637.2 | 1647.669 | 34996.48 |  | 1.7882 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 3197.11 | 22 | 70336.42 | 12660.56 | 82996.98 | 2.5 | 0 | 0 | 0 | 0 | 3197.11 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | RCC Patli | R.Ft | 2603.78 | 40 | 104151.2 | 18747.22 | 122898.42 | 2.5 | 0 | 0 | 0 | 0 | 2603.78 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 8699.25 | 20 | 173985 | 31317.3 | 205302.3 | 2.5 | 2551.62 | 51032.4 | 9185.84 | 60218.24 | 6147.63 | 145084.06 |  | 29.3315 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | RCC Patli | R.Ft | 2723.69 | 40 | 108947.6 | 19610.56 | 128558.16 | 2.5 | 307 | 12280 | 2210.4 | 14490.4 | 2416.69 | 114067.76 |  | 11.2715 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 2706.734 | 22 | 59548.15 | 10718.66 | 70266.81 | 2.5 | 0 | 0 | 0 | 0 | 2706.734 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | Blockwork 12'' | Sq.Ft | 429.22 | 25 | 10730.5 | 1931.5 | 12662 | 2.5 | 0 | 0 | 0 | 0 | 429.22 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | Blockwork 12'' | Sq.Ft | 429.22 | 25 | 10730.5 | 1931.5 | 12662 | 2.5 | 0 | 0 | 0 | 0 | 429.22 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 311.195 | 18 | 5601.51 | 1008.28 | 6609.79 | 2.5 | 0 | 0 | 0 | 0 | 311.195 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | Blockwork 12'' | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 1581.2397 | 18 | 28462.31 | 5123.22 | 33585.53 | 2.5 | 0 | 0 | 0 | 0 | 1581.2397 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 8527.81 | 20 | 170556.2 | 30700.12 | 201256.32 | 2.5 | 1501.63 | 30032.6 | 5405.86 | 35438.46 | 7026.18 | 165817.86 |  | 17.6086 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 8042.95 | 20 | 160859 | 28954.62 | 189813.62 | 2.5 | 0 | 0 | 0 | 0 | 8042.95 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | Blockwork 12'' | Sq.Ft | 429.22 | 25 | 10730.5 | 1931.5 | 12662 | 2.5 | 0 | 0 | 0 | 0 | 429.22 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | RCC Patli | R.Ft | 2748.3 | 40 | 109932 | 19787.76 | 129719.76 | 2.5 | 614 | 24560 | 4420.8 | 28980.8 | 2134.3 | 100738.96 |  | 22.3411 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 8699.25 | 20 | 173985 | 31317.3 | 205302.3 | 2.5 | 2551.62 | 51032.4 | 9185.84 | 60218.24 | 6147.63 | 145084.06 |  | 29.3315 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 1677.669 | 18 | 30198.04 | 5435.64 | 35633.68 | 2.5 | 30 | 540 | 97.2 | 637.2 | 1647.669 | 34996.48 |  | 1.7882 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | RCC Patli | R.Ft | 2723.7 | 40 | 108948 | 19610.64 | 128558.64 | 2.5 | 307.27 | 12290.8 | 2212.34 | 14503.14 | 2416.43 | 114055.5 |  | 11.2813 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | Blockwork 12'' | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | Blockwork 12'' | Sq.Ft | 429.22 | 25 | 10730.5 | 1931.5 | 12662 | 2.5 | 0 | 0 | 0 | 0 | 429.22 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | Blockwork 12'' | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 8699.25 | 20 | 173985 | 31317.3 | 205302.3 | 2.5 | 2551.62 | 51032.4 | 9185.84 | 60218.24 | 6147.63 | 145084.06 |  | 29.3315 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Second Floor (P3) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | Blockwork 8" - BC | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 1677.669 | 18 | 30198.04 | 5435.64 | 35633.68 | 2.5 | 516.93 | 9304.74 | 1674.86 | 10979.6 | 1160.739 | 24654.08 |  | 30.8124 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | Blockwork 12'' | Sq.Ft | 429.22 | 25 | 10730.5 | 1931.5 | 12662 | 2.5 | 0 | 0 | 0 | 0 | 429.22 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | Blockwork 4" - BC | Sq.Ft | 0 | 18 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fourth Floor (P5) Block Work (L) | Blockwork 12'' | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Third Floor (P4) Block Work (L) | Blockwork 12'' | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | Blockwork 12'' | Sq.Ft | 523.29 | 25 | 13082.25 | 2354.8 | 15437.05 | 2.5 | 0 | 0 | 0 | 0 | 523.29 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | Blockwork 12'' | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | No category | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Fifth Floor (P6) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA . First Floor (P2) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 17 Oct 2023
GANGA ASMI | 556 | 0 | 28 Aug 2023 | JAI SEVALAL CONSTRUCTION | MHADA - Ground Floor (P1) Block Work (L) | Blockwork 5" - BC - | Sq.Ft | 4613.92 | 20 | 92278.4 | 16610.12 | 108888.52 | 2.5 | 0 | 0 | 0 | 0 | 4613.92 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Sep 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Air Test SOS | No. | 0 | 1500 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 29 Aug 2023 |  | S OH Infrastructure | Cancelled | ADITYA.CHOUGULE | 29 Aug 2023
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | DG insertion loss Noise Monitoring | No. | 1 | 500 | 500 | 90 | 590 | 0 | 1 | 500 | 90 | 590 | 0 | 0 | Environmental Monitoring Report for One Boat Club Project. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | NOise Test Day SOS | No. | 4 | 100 | 400 | 72 | 472 | 0 | 4 | 400 | 72 | 472 | 0 | 0 | Environmental Monitoring Report for One Boat Club Project. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Aug 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Sewage Water Analysis | No. | 1 | 1200 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Environmental Monitoring Report for One Boat Club Project. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Air Test SOS | No. | 4 | 1500 | 6000 | 1080 | 7080 | 0 | 4 | 6000 | 1080 | 7080 | 0 | 0 | Environmental Monitoring Report for One Boat Club Project. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Aug 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Noise Test Night SOS | No. | 4 | 100 | 400 | 72 | 472 | 0 | 4 | 400 | 72 | 472 | 0 | 0 | Environmental Monitoring Report for One Boat Club Project. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Aug 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Stack Monitoring Report SOS | No. | 2 | 900 | 1800 | 324 | 2124 | 0 | 1 | 900 | 162 | 1062 | 1 | 1062 | Environmental Monitoring Report for One Boat Club Project. | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Aug 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | NOise Test Day SOS | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 29 Aug 2023 |  | S OH Infrastructure | Cancelled | ADITYA.CHOUGULE | 29 Aug 2023
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Soil Analysis Test- SOS | No. | 3 | 1500 | 4500 | 810 | 5310 | 0 | 3 | 4500 | 810 | 5310 | 0 | 0 | Environmental Monitoring Report for One Boat Club Project. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Aug 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Sewage Water Analysis | No. | 0 | 1000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 29 Aug 2023 |  | No category | Cancelled | ADITYA.CHOUGULE | 29 Aug 2023
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Noise Test Night SOS | No. | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 29 Aug 2023 |  | S OH Infrastructure | Cancelled | ADITYA.CHOUGULE | 29 Aug 2023
GANGA ASMI | 557 | 0 | 29 Aug 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water Test | Water Testing report - SOS | No. | 2 | 1000 | 2000 | 360 | 2360 | 0 | 2 | 2000 | 360 | 2360 | 0 | 0 | Environmental Monitoring Report for One Boat Club Project. | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Aug 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 558 | 0 | 29 Aug 2023 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | professional Consultancy Charges | Consultancy Charges | No. | 1 | 635000 | 635000 | 114300 | 749300 | 0 | 0.8 | 508000 | 91440 | 599440 | 0.2 | 149860 | Consultancy Charges for Project- One Boat Club. | 80 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 12 Sep 2023 |  | Consultacy Architectural | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 559 | 0 | 31 Aug 2023 | ANIMOTIONSZ | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 7 | 15000 | 105000 | 18900 | 123900 | 0 | 4 | 60000.05 | 10800.02 | 70800.07 | 3 | 53099.94 | MANAGING THE CAMPAIGN FOR INCREASING THE ROI + CREATION OF ADS +LANDING PAGE, + FACEBOOK PAID CAMPAIGN = MONITORING CHARGES PER MONTH RS. 15000/- + TAX AS ON 01ST SEPT. 2023 TO 31ST MARCH 2024 | 57.1429 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 07 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 560 | 0 | 02 Sep 2023 | RED TREE DESIGN STUDIO PRIVATE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 7 | 300000 | 2100000 | 378000 | 2478000 | 0 | 6 | 1800000.3 | 324000.02 | 2124000.32 | 1 | 353999.68 | GOEL GANGA GROUP +REAL RICH - ONLINE SOCIAL + DIGITAL MEDIA MONTHLY BASIS RETAINERSHIP CHARGES AS ON 01ST SEPT. 2023 TO TILL 31ST MARCH 2023 @ 300000/- +TAX PER MONTH (PROPOSAL AS PER ATTACHED DELIVERABLES) | 86.0714 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 16 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 560 | 0 | 02 Sep 2023 | RED TREE DESIGN STUDIO PRIVATE LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 300000 | 300000 | 54000 | 354000 | 0 | 1 | 300000 | 54000 | 354000 | 0 | 0 | RED TREE | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 16 Sep 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV | 1900-01-01
GANGA ASMI | 561 | 0 | 08 Sep 2023 | KENYT TECHONOLOGIES PRIVATE LIMITED | ONLINE / DIGITAL Social / Digital Activity | LEAD GENERATION - LIVE CHATS | No. | 1 | 210000 | 210000 | 37800 | 247800 | 0 | 1 | 210000 | 37800 | 247800 | 0 | 0 | lead generation chat (unlimited) period as on 04th may 2023 to 03rd may 2024 for 1 year | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 16 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 562 | 0 | 09 Sep 2023 | AMPLE IMPRESSIONS | PRINTING PRINTING-NO.-(NA) | Booklet / Notepad / Diary / Pocket Print | No. | 500 | 75 | 37500 | 4500 | 42000 | 0 | 500 | 37500 | 1875 | 39375 | 0 | 2625 | GANGA ASMI BROCHURE PRINT QTY. 500 2 75/-+ TAX ( 300 GSM ART PAPER BOTH SIDE PRINTING + MATT COATING SPOT UV, DOCKET WITH POCKET 6INSERT ON 130 GSM ART CARD MULTICOLOUR PRINT) | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 11 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 563 | 0 | 09 Sep 2023 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | PRINTING PRINTING-NO.-(NA) | Booklet / Notepad / Diary / Pocket Print | No. | 2000 | 5.5 | 11000 | 550 | 11550 | 0 | 2000 | 11000 | 550 | 11550 | 0 | 0 | AARATI BOOKLET POCKET SIZE AS 4 X 5.75 INCH QTY. 2000 @ 5.50/- +TAX 70 GSM ART PAPER COLOUR PRINT | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 11 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 564 | 0 | 13 Sep 2023 | RED TREE DESIGN STUDIO PRIVATE LIMITED | BRANDING Event Expenses | Advertorial / Write Up / Articales | No. | 1 | 300000 | 300000 | 54000 | 354000 | 0 | 1 | 300000 | 54000 | 354000 | 0 | 0 | GANGA ASMI + GOEL GANGA CONTENT CREATION FOR REAL RICH MONTH OF AUGUST 2023 | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 16 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 565 | 0 | 14 Sep 2023 | SHAH KHANDELWAL JAIN AND ASSOCIATES | Professional Fees | TAX CONSULTANCY | Month | 12 | 50000 | 600000 | 108000 | 708000 | 0 | 12 | 600000 | 108000 | 708000 | 0 | 0 | MONTHLY BASIS DIRECT TAX- RETAINERSHIP SERVICES @50000/- + TAX PER MONTH AS ON 01/04/2023 TO 31/03/2024 | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 21 Sep 2023 |  | Consultancy TAX | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 565 | 1 | 14 Sep 2023 | SHAH KHANDELWAL JAIN AND ASSOCIATES | Professional Fees | TAX CONSULTANCY | Month | 12 | 50000 | 600000 | 108000 | 708000 | 0 | 3.9998 | 199992 | 35998.56 | 235990.56 | 8.0002 | 472009.44 |  | 33.3317 |  | DUSHANT.GORE | Swapnil Erande | construction open | 21 Sep 2023 |  | Consultancy TAX | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 14 Sep 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 566 | 0 | 14 Sep 2023 | KSHITEEJ ENTERPRISES | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 07 Oct 2023
GANGA ASMI | 567 | 0 | 18 Sep 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 0 | 65000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING - HOARDING DISPLAY CHARGES AS PER MONTHLY BASIS. @ BHUMKAR CHOWK, NEAR OLYMPLIA PROJECTS OPP. MAMTA NAGAR, WAKAD FACING HINJEWADI IT PARK SIZE AS 60 X 30 SQ FT. @65000/- +TAX AS ON 21/09/2023 TO 20/03/2024 | 0 |  | TEJAS RAVERKAR |  | construction open | 18 Sep 2023 |  | MKT. Media | Cancelled | TEJAS RAVERKAR | 21 Sep 2023
GANGA ASMI | 567 | 1 | 18 Sep 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 0 | 38000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING - HOARDING DISPLAY CHARGES AS PER MONTHLY BASIS. @ OPP GANGA ASMI WAKAD PROJECT SITE SIZE AS 30 X 30 SQ FT. @38000/- +TAX AS ON 18/09/2023 TO 17/03/2024 | 0 |  | TEJAS RAVERKAR |  | construction open | 18 Sep 2023 |  | MKT. Media | Cancelled | TEJAS RAVERKAR | 21 Sep 2023
GANGA ASMI | 567 | 0 | 18 Sep 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING - HOARDING DISPLAY CHARGES AS PER MONTHLY BASIS. @ HINJEWADI IT PARK ROAD, NEAR BANK OF MAHARASHTRA FACING WAKAD, SIZE AS 35 X 42 SQ FT. @50000/- +TAX AS ON 21/09/2023 TO 20/03/2024 | 0 |  | TEJAS RAVERKAR |  | construction open | 18 Sep 2023 |  | MKT. Media | Cancelled | TEJAS RAVERKAR | 21 Sep 2023
GANGA ASMI | 568 | 6 | 18 Sep 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 40000 | 240000 | 43200 | 283200 | 0 | 6 | 240000 | 43200.04 | 283200.04 | 0 | -0.04 | GANGA ASMI WAKAD PROJECT OUTDORR BRANDING HOARDING DISPLAY CHARGES ON MANTHLY BASIS @WAKAD FLYOVER TRAFFIC FROM PUNE TO HINJEWADI SIZE AS 30 X 30 SQ FT. @40000/- +TAX AS ON 21/09/2023 TO 20/03/2024, | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 18 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 568 | 4 | 18 Sep 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 6 | 300000 | 53999.98 | 353999.98 | 0 | 0.02 | GANGA ASMI WAKAD PROJECT OUTDORR BRANDING HOARDING DISPLAY CHARGES ON MANTHLY BASIS @MAHALUNGE AT GODREJ PROJECT ENTRANCE TRAFFIC FROM GODREJ TO MAHALUNGE SIZE AS 30 X 30 SQ FT. @50000/- +TAX AS ON 21/09/2023 TO 20/03/2024, | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 18 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 568 | 1 | 18 Sep 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 75000 | 450000 | 81000 | 531000 | 0 | 3 | 224999.1 | 40499.82 | 265498.92 | 3 | 265501.08 | GANGA ASMI WAKAD PROJECT OUTDORR BRANDING HOARDING DISPLAY CHARGES ON MANTHLY BASIS @ HINJEWADI, NEAR SHEL PETROL PUMP, TRAFFIC FROM HINJEWADI TO PUNE , SIZE AS 60 X 30 SQ FT. @75000/- +TAX AS ON 21/09/2023 TO 20/03/2024, | 50 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 18 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 568 | 2 | 18 Sep 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 80000 | 480000 | 86400 | 566400 | 0 | 6 | 480000 | 86399.98 | 566399.98 | 0 | 0.02 | GANGA ASMI WAKAD PROJECT OUTDORR BRANDING HOARDING DISPLAY CHARGES ON MANTHLY BASIS @ HINJEWADI - BHUMKAR CHOWK ROAD, NEAR ORRITTEL HOTEL, TRAFFIC HINJEWADI TO BHUMKAR CHOWK SIZE AS 60 X 42 SQ FT. @80000/- +TAX AS ON 21/09/2023 TO 20/03/2024, | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 18 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 568 | 0 | 18 Sep 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 60000 | 360000 | 64800 | 424800 | 0 | 6 | 360000 | 64800.02 | 424800.02 | 0 | -0.02 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING - HOARDING DISPLAY CHARGES AS PER MONTHLY BASIS. @PIMPALE NILAKH, NEAR KOLTE PATIL 24 K PROJECT TRAFFIC FROM WAKAD TO BANER SIZE AS 30 X 30 SQ FT. @60000/- +TAX AS ON 21/09/2023 TO 20/03/2024 | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 18 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 568 | 5 | 18 Sep 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 60000 | 360000 | 64800 | 424800 | 0 | 6 | 360000 | 64800.02 | 424800.02 | 0 | -0.02 | GANGA ASMI WAKAD PROJECT OUTDORR BRANDING HOARDING DISPLAY CHARGES ON MANTHLY BASIS @HINJEWADI WIPRO CHOWK TRAFFIC FROM HINJEWADI TO PUNE SIZE AS 40 X 40 SQ FT. @60000/- +TAX AS ON 21/09/2023 TO 20/03/2024, | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 18 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 568 | 7 | 18 Sep 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 6420 | 2 | 12840 | 2311.2 | 15151.2 | 0 | 6420 | 12840 | 2311.2 | 15151.2 | 0 | 0 | FLEX MOUNTING CHARGES FOR THE GANGA ASMI TOTA SQFT 6420 @ 2RS PER SQFT | 100 |  | SWAPNIL JADHAV | SWAPNIL JADHAV | construction open | 18 Sep 2023 |  | MKT. Media | Approved | SWAPNIL JADHAV | 1900-01-01
GANGA ASMI | 568 | 3 | 18 Sep 2023 | SHUBHAM OUTDOOR ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 60000 | 360000 | 64800 | 424800 | 0 | 1 | 59999.76 | 10800 | 70799.76 | 5 | 354000.24 | GANGA ASMI WAKAD PROJECT OUTDORR BRANDING HOARDING DISPLAY CHARGES ON MANTHLY BASIS @ MAHALUNGE AT GODREJ PROJECT ENTRANCE TRAFFIC FROM MAHALUNGE TO GODREJ PROJECT SIZE AS 30 X 30 SQ FT. @20000/- +TAX AS ON 21/09/2023 TO 20/03/2024, | 16.6667 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 18 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 569 | 1 | 21 Sep 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 65000 | 390000 | 70200 | 460200 | 0 | 5.998 | 389869.74 | 70176.6 | 460046.34 | 0.002 | 153.66 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING - HOARDING DISPLAY CHARGES MONTHLY BASIS 2) @ BHUMKAR CHOWK, NEAR OLYMPIA PROJECTS, OPP. MAMTA NAGAR, WAKAD, FACING HINJEWADI IT PARK SIZE AS 60 X 30 SQ FT. @65000/- + TAX PERIOD AS ON 21/09/2023 TO 20/03/2024 | 99.9667 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 26 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 569 | 0 | 21 Sep 2023 | SHUBHANGI ADVERTISING | PRINTING PRINTING-NO.-(NA) | Hoarding Display Charges | No. | 6 | 50000 | 300000 | 54000 | 354000 | 0 | 5.998 | 299899.8 | 53982 | 353881.8 | 0.002 | 118.2 | GANGA ASMI WAKAD PROJECT OUTDOOR BRANDING - HOARDING DISPLAY CHARGES MONTHLY BASIS @ HINJEWADI IT PARK ROAD, NEAR BANK OF MAHARASHTRA FACING WAKAD, SIZE AS 35 X 42 SQ FT. @50000/- + TAX PERIOD AS ON 21/09/2023 TO 20/03/2024 | 99.9667 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 26 Sep 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 570 | 0 | 22 Sep 2023 | Liases Foras Real Estate Rating and Research Pvt Ltd | BRANDING Event Expenses | SURVEY / ANALYSIS / SERVICE REPORT | No. | 1 | 450000 | 450000 | 81000 | 531000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | GANGA ASMI WAKAD PROJECT OTHER PROJECT ANYALISYS, SURVEY, STUDY ETC. 1) REGIONAL CONTEXT OF PCMC, 2) RESIDENTIAL MARKET ASSESSMENT, 3) MARKET OUTLOOK ETC. TOTAL COST RS. 450000/- + TAX. | 0 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 22 Sep 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 571 | 0 | 25 Sep 2023 | CREDAI-Pune Metro | Advertisement | Advertisement Release- | No. | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | SOUVENIR - FULL PAGE BACK COVER FOR 1) BEST FACILITY AWARD COMPETITION 2023 & SAFETY COMPETITION AWARDS - DIRECTORY , 2) DIRECTORY ON BEST PRACTICES FOLLOWED ON CONSTRUCTION SITES FOR LABOUR CAMPS, AND SAFETY AT SITE RS. 25000/- + TAX EACH (CREDAI -PUNE METRO) | 0 |  | TEJAS RAVERKAR |  | construction open | 25 Sep 2023 |  | MKT. Media | Cancelled | TEJAS RAVERKAR | 25 Sep 2023
GANGA ASMI | 572 | 0 | 25 Sep 2023 | CREDAI-Pune Metro | Advertisement | Advertisement Release- | No. | 1 | 50000 | 50000 | 9000 | 59000 | 0 | 1 | 50000 | 9000 | 59000 | 0 | 0 | SOUVENIR - FULL PAGE BACK COVER FOR 1) BEST FACILITY AWARD COMPETITION 2023 & SAFETY COMPETITION AWARDS - DIRECTORY , 2) DIRECTORY ON BEST PRACTICES FOLLOWED ON CONSTRUCTION SITES FOR LABOUR CAMPS, AND SAFETY AT SITE RS. 25000/- + TAX EACH (CREDAI -PUNE METRO) 100% advance with gst | 100 |  | TEJAS RAVERKAR | TEJAS RAVERKAR | construction open | 25 Sep 2023 |  | MKT. Media | Approved | TEJAS RAVERKAR | 1900-01-01
GANGA ASMI | 573 | 0 | 27 Sep 2023 | A.S.INFOTECH SOLUTION | Goel House Cartridge Refilling | Cartridge refilling | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 0.9999 | 9999 | 1799.82 | 11798.82 | 0.0001 | 1.18 |  | 99.99 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 573 | 0 | 27 Sep 2023 | A.S.INFOTECH SOLUTION | Goel House Cartridge Refilling | Cartridge refilling | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 573 | 0 | 27 Sep 2023 | A.S.INFOTECH SOLUTION | Goel House Cartridge Refilling | Cartridge refilling | No. | 0 | 10000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Cancelled | ADITYA.CHOUGULE | 27 Sep 2023
GANGA ASMI | 573 | 0 | 27 Sep 2023 | A.S.INFOTECH SOLUTION | Goel House Cartridge Refilling | Cartridge refilling | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 573 | 0 | 27 Sep 2023 | A.S.INFOTECH SOLUTION | Goel House Cartridge Refilling | Cartridge refilling | No. | 1 | 10000 | 10000 | 1800 | 11800 | 0 | 1 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 574 | 0 | 03 Oct 2023 | UMESH YADAV | Goel House Bamboo Scaffolding Work Roof Tile painting | Scaffolding work | Sq.Ft | 5906 | 5 | 29530 | 5315.4 | 34845.4 | 0 | 5906 | 29530 | 5315.4 | 34845.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 16 Oct 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 29th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 26th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 24th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 28th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 24th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 21st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 28th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Wing 1-OHWT Top Terrace LMR,OHWT | RCC Work -Dld | No. | 0 | 1250000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | DEV. Landscape/Equipment | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 10th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 25th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 28th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 34th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 22nd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 21st Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 30th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Sorting & Shifting mockup,checking & rework- 10179.655 Sq. | Sorting & Shifting Work | Sq.Ft | 1513.606 | 95 | 143792.57 | 25882.66 | 169675.23 | 2.5 | 0 | 0 | 0 | 0 | 1513.606 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 24th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 25th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Top Terrace,LMR,OHWT,Parapet wall pergola (L) | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 4462.506 | 155 | 691688.43 | 124503.92 | 816192.35 | 2.5 | 4462.506 | 691688.43 | 124503.92 | 816192.35 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 35th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 17th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 26th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 11th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 14th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Wing 1-OHWT Top Terrace LMR,OHWT | RCC Work -Dld | No. | 0 | 1250000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | DEV. Landscape/Equipment | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 33rd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 17th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 4462.506 | 155 | 691688.43 | 124503.92 | 816192.35 | 2.5 | 4462.506 | 691688.43 | 124503.92 | 816192.35 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 26th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 20th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 14th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 33rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 22nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 35th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 200.1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 17th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 28th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 23rd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 17th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 32nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 12th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 32nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 24th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 27th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | After Completion of all RCC Work of Bulding | RCC Work -Dld | No. | 0 | 1000000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 23 Oct 2023 |  | DEV. Landscape/Equipment | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 15th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 33rd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 24th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 10th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 3174.075 | 200 | 634815 | 114266.7 | 749081.7 | 2.5 | 3174.075 | 634815 | 114266.7 | 749081.7 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 24th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 33rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 22nd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 33rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 17th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 26th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 20th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 25th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 22nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 32nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 13th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 35th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 200.1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 22nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 29th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 25th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 4462.506 | 155 | 691688.43 | 124503.92 | 816192.35 | 2.5 | 4462.506 | 691688.43 | 124503.92 | 816192.35 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 12th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 35th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 200.1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 27th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 538.295 | 200 | 107659 | 19378.62 | 127037.62 | 2.5 | 0 | 0 | 0 | 0 | 538.295 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 34th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 23rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 8th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 1513.606 | 155 | 234608.93 | 42229.6 | 276838.53 | 2.5 | 0 | 0 | 0 | 0 | 1513.606 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 27th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | After Completion of all RCC Work of Bulding | RCC Work -Dld | No. | 0 | 1000000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | DEV. Landscape/Equipment | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 14th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 35th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 200.1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 1513.606 | 155 | 234608.93 | 42229.6 | 276838.53 | 2.5 | 154.83 | 23998.65 | 0 | 23998.65 | 1358.776 | 252839.88 |  | 10.2292 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 32nd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Shifting of shuttering material from last floor to G.F.(L)- | Sorting & Shifting Work | Sq.Ft | 0 | 47.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 974.81 | 155 | 151095.55 | 27197.2 | 178292.75 | 2.5 | 0 | 0 | 0 | 0 | 974.81 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 4462.506 | 155 | 691688.43 | 124503.92 | 816192.35 | 2.5 | 4462.506 | 691688.43 | 124503.92 | 816192.35 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 32nd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Shifting of shuttering material from last floor to G.F.(L)- | Sorting & Shifting Work | Sq.Ft | 0 | 47.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 9th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 20th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 4462.506 | 155 | 691688.43 | 124503.92 | 816192.35 | 2.5 | 4462.506 | 691688.43 | 124503.92 | 816192.35 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 26th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 21st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 34th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 19th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 32nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 29th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 21st Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 16th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 19th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 28th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 9th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 20th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 29th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 20th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 17th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 31st Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 30th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 30th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 26th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 15th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 27th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 18th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 23rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 35th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 31st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 27th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 28th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 30th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 31st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 25th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 23rd Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 29th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 21st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 30th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 31st Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 22nd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 34th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 23rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | After Completion of all RCC Work of Bulding | RCC Work -Dld | No. | 0 | 981312 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | DEV. Landscape/Equipment | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 23rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 15th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Sorting & Shifting mockup,checking & rework- 10179.655 Sq. | Sorting & Shifting Work | Sq.Ft | 0 | 95 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 18th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | Sorting & Shifting mockup,checking & rework- 10179.655 Sq. | Sorting & Shifting Work | Sq.Ft | 8925.012 | 95 | 847876.14 | 152617.7 | 1000493.84 | 2.5 | 8925.012 | 847876.14 | 152617.72 | 1000493.86 | 0 | -0.02 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 31st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 8th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 34th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 5750.54 | 155 | 891333.7 | 160440.06 | 1051773.76 | 2.5 | 5750.54 | 891333.7 | 160440.06 | 1051773.76 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 31st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 8th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 4462.506 | 155 | 691688.43 | 124503.92 | 816192.35 | 2.5 | 4462.506 | 691688.43 | 124503.92 | 816192.35 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 11th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 08 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 29th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 13th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 27th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 21st Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 25th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 20th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 16th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 12th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 30th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 34th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 13th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 33rd Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 199 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 19th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 11th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 16th Slab RCC slab,beam,ST,Shear wall | Schedule & Quality | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 10th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 1513.606 | 155 | 234608.93 | 42229.6 | 276838.53 | 2.5 | 82.58 | 12799.9 | 0 | 12799.9 | 1431.026 | 264038.63 |  | 5.4558 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 7th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 9th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | ADITYA.CHOUGULE | 23 Oct 2023
GANGA ASMI | 575 | 0 | 07 Oct 2023 | VINAYAKA ASSOCIATE | 18th Slab RCC slab,beam,ST,Shear wall | RCC Mi-van Labour (B-up Basis)BC | Sq.Ft | 0 | 160 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 23 Oct 2023 |  | B.C. RCC Superstructure | Foreclose | DUSHANT.GORE | 01 Jun 2024
GANGA ASMI | 576 | 0 | 07 Oct 2023 | DUROCRETE ENGINEERING SERVICES PVT LTD | Pile Integrity Test | Integrity Test | No. | 25 | 666.66 | 16666.5 | 2999.98 | 19666.48 | 0 | 0 | 0 | 0 | 0 | 25 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | 16 Testing, Analysis & Reports | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 576 | 0 | 07 Oct 2023 | DUROCRETE ENGINEERING SERVICES PVT LTD | Pile Integrity Test | Travelling charges- SO | No. | 2 | 1500 | 3000 | 540 | 3540 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 577 | 0 | 09 Oct 2023 | Enviro Analysts & Engineers Pvt Ltd | One Boat Club Environmental Consultancy-No. | Env.Clearance Consultancy | No. | 1 | 280933 | 280933 | 50567.94 | 331500.94 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | 03 CONSULTANCY | Un-Approved |  | 1900-01-01
GANGA ASMI | 578 | 0 | 09 Oct 2023 | NILIMA BHOSEKAR | One Boat Club Landscape Consultancy-No. | Landscape Consultancy. | No. | 1 | 237000 | 237000 | 42660 | 279660 | 0 | 1 | 237000 | 42660 | 279660 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Dec 2023 |  | Consultacy Landscape | Approved | ADITYA.CHOUGULE | 09 Oct 2023
GANGA ASMI | 579 | 0 | 09 Oct 2023 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | One Boat Club Env. Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | No. | 1 | 22691 | 22691 | 4084.38 | 26775.38 | 0 | 1 | 22691 | 4084.38 | 26775.38 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 15 Dec 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 580 | 0 | 09 Oct 2023 | UNICORN M.E.P. CONSULTANTS PVT LTD | One Boat Club MEP Consultancy-No. | MEP Consultancy | Sq.Ft | 178467.25 | 8 | 1427738 | 256992.84 | 1684730.84 | 0 | 178467.25 | 1427738 | 256992.84 | 1684730.84 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 22 Dec 2023 |  | Consultancy MEP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 581 | 0 | 10 Oct 2023 | DREAMTREE EXPERIENCE | Advertisement | ACP Name Board Making - BCo | Sq.Ft | 0 | 950 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | sunita shirolkar | construction open | 10 Oct 2023 |  | B.C. Building Common Items | Cancelled | SWAPNIL JADHAV | 10 Jan 2024
GANGA ASMI | 581 | 0 | 10 Oct 2023 | DREAMTREE EXPERIENCE | Advertisement | Transport Charges- Med. | No. | 0 | 15000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | sunita shirolkar | construction open | 10 Oct 2023 |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 10 Jan 2024
GANGA ASMI | 582 | 0 | 10 Oct 2023 | BASAV ENTERPRISES | Wing 01 Piling work for Non Tower area | Pile Breaking on R.ft Basis | R.Ft | 45.39 | 350 | 15886.5 | 0 | 15886.5 | 0 | 45.39 | 15886.5 | 0 | 15886.5 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 582 | 0 | 10 Oct 2023 | BASAV ENTERPRISES | Wing 01 Piling work for Non Tower area | Pile Casing Cutting - No. | No. | 18 | 550 | 9900 | 0 | 9900 | 0 | 18 | 9900 | 0 | 9900 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 582 | 1 | 10 Oct 2023 | BASAV ENTERPRISES | NTA Superstructure (L) Slab breaking Parking Pile Brkng Cutt | Lumpsum work- DCW | No. | 1 | 35000 | 35000 | 0 | 35000 | 0 | 1 | 35000 | 0 | 35000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 583 | 0 | 12 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-2 2nd Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 583 | 0 | 12 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-2 4th Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 100 | 10000 | 1800 | 11800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 583 | 0 | 12 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-2 5th Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 583 | 0 | 12 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-2 3rd Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 55 | 5500 | 990 | 6490 | 45 | 5310 |  | 55 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 583 | 0 | 12 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-2 1st Slab Total Station Suvey Point Marking | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 97 | 9700 | 1746 | 11446 | 3 | 354 |  | 97 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 2nd Slab (P3 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 5th Slab (P6 Lvl) Building RCC Labour Work | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 6th Slab (Podium Floor Lvl) Building RCC Labour Wor | RCC Superstructure (B-up area) | Sq.Ft | 0 | 240.65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 Parking Dressing, Leveling & Cleaning (RCC Labour) | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 4th Slab (P5 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 1st Slab (P2 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 Parking Plinth Beam (RCC Labour) | RCC Beam | Sq.Ft | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 3rd Slab (P4 Lvl) Building RCC Labour Work | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 2nd Slab (P3 Lvl) Building RCC Labour Work | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 4th Slab (P5 Lvl) Building RCC Labour Work | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 5th Slab (P6 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 210 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 1st Slab (P2 Lvl) Building RCC Labour Work | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 3rd Slab (P4 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 190 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 Parking Soling & PCC Work (RCC Labour) | Soling & PCC | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 Parking PCC Work (RCC Labour) | PCC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 5th Slab (P6 Lvl) Building RCC Labour Work | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 1st Slab (P2 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 170 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 2nd Slab (P3 Lvl) Building RCC Labour Work | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 5th Slab (P6 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 210 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 4th Slab (P5 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 2nd Slab (P3 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 4th Slab (P5 Lvl) Building RCC Labour Work | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 Parking Footing & Column (RCC Labour) | Footing & Column | Sq.Ft | 0 | 45 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 3rd Slab (P4 Lvl) Building RCC Labour Work | RCC Superstructure (B-up area) | Sq.Ft | 0 | 190 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 6th Slab (Podium Floor Lvl) Building RCC Labour Wor | RCC Superstructure (B-up area) | Sq.Ft | 0 | 240.65 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 6th Slab (Podium Floor Lvl) Building RCC Labour Wor | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 3rd Slab (P4 Lvl) Building RCC Labour Work | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. RCC Superstructure | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 1st Slab (P2 Lvl) Building RCC Labour Work | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 Plinth Work (RCC Labour) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 115 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 584 | 0 | 12 Oct 2023 | KRISHNA CONSTRUCTION (Prop BHISE) | Wing-3 - 6th Slab (Podium Floor Lvl) Building RCC Labour Wor | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 27 Apr 2024
GANGA ASMI | 585 | 0 | 17 Oct 2023 | MONARCH PRINT ARTS (PROP. SHARAD DATTATRAY NARALE) | Work Safety permit Printing Work | print | No. | 10000 | 0.65 | 6500 | 780 | 7280 | 0 | 10000 | 6500 | 780 | 7280 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 23 Oct 2023 |  | MKT. Media | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 586 | 0 | 19 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-3 Substructure (L) Total Station Point Marking | Total Station Point marking. | No. | 350 | 100 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 350 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 586 | 0 | 19 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-3 Substructure (L) Total Station Point Marking | Total Station Point marking. | No. | 350 | 100 | 35000 | 6300 | 41300 | 0 | 4 | 400 | 72 | 472 | 346 | 40828 |  | 1.1429 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 586 | 0 | 19 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-3 Substructure (L) Total Station Point Marking | Total Station Point marking. | No. | 350 | 100 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 350 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 586 | 0 | 19 Oct 2023 | SP ENGINEERS AND LAND SURVEYORS | Wing-3 Substructure (L) Total Station Point Marking | Total Station Point marking. | No. | 350 | 100 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 350 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2401 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1207 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-109 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4609.15 | 0 | 4609.15 | 0.65 | 8559.85 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P6 (INDOOR GAMES) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-608 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-501 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2205 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1001 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-501 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-306 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2206 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-504 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1809 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-701 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1507 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-704 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2602 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1601 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1904 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2608 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2605 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-802 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2408 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-207 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5876.61 | 0 | 5876.61 | 0.65 | 10915.39 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-902 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-602 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1502 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-404 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1005 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-507 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-801 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1905 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2002 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1008 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-706 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1209 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-205 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4608.69 | 0 | 4608.69 | 0.65 | 8560.31 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2701 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1301 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2806 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-406 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1104 (2BHK) (Refuge Area) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-306 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1309 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1802 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-104 (2BHK) (Refuge Area) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4609.15 | 0 | 4609.15 | 0.65 | 8559.85 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1904 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1203 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-102 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5877.2 | 0 | 5877.2 | 0.65 | 10914.8 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-302 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1603 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-803 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-901 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2002 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P7 (INDOOR GAMES) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1906 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1506 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1202 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-204 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2705 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-506 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2801 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-905 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2805 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-207 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2102 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1406 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-303 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1901 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-701 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1302 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-206 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-606 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1801 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1401 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2503 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P4 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-502 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1006 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-505 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2704 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1907 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2801 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1508 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-104 (2BHK) (Refuge Area) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-707 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-303 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P8 (MEDITATION & YOGA ROOM) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-405 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-908 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-308 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2605 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2503 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2105 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-509 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1606 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2405 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1203 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2701 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1509 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1708 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2805 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2106 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1307 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-204 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4608.69 | 0 | 4608.69 | 0.65 | 8560.31 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1703 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2207 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2203 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-409 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-102 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1207 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1306 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2604 (2BHK) (Refuge Area) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-101 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2406 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1505 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2005 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1501 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-609 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1906 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-502 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1006 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2705 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-209 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2407 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-401 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1204 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P9 (MEDITATION & YOGA ROOM) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2307 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1107 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2504 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1604 (2BHK) (Refuge Area) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1702 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-602 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1103 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1402 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1707 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-702 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1007 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1708 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2106 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-206 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5876.61 | 0 | 5876.61 | 0.65 | 10915.39 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-802 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1407 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1706 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-402 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2606 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1005 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2802 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1309 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-607 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2006 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1009 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1908 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-907 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1603 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1902 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2108 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-806 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2807 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-905 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-109 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2301 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2502 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2306 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1404 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1901 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2607 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2409 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1208 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2506 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2709 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1807 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-209 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4608.69 | 0 | 4608.69 | 0.65 | 8560.31 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1206 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2608 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2309 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-305 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1101 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2402 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P2 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2603 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2407 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-503 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2204 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2305 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P8 (MEDITATION & YOGA ROOM) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-904 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-706 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2209 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-806 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-603 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1802 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1304 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2001 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1607 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2107 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P2 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5876.61 | 0 | 5876.61 | 0.65 | 10915.39 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-808 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2003 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2807 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2201 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2803 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-909 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2609 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-406 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2404 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2103 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-506 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-101 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5877.2 | 0 | 5877.2 | 0.65 | 10914.8 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1605 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2306 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-105 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4609.15 | 0 | 4609.15 | 0.65 | 8559.85 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2707 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-505 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1109 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1701 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-105 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1504 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2402 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-309 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2206 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-408 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P4 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4608.69 | 0 | 4608.69 | 0.65 | 8560.31 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1502 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-208 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1408 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2502 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-703 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1103 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1303 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1509 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-804 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2604 (2BHK) (Refuge Area) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-708 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-106 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5877.2 | 0 | 5877.2 | 0.65 | 10914.8 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2008 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-903 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2505 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1807 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1308 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2703 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2109 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1002 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1206 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1004 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1508 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-702 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1105 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2208 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1704 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-906 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1107 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1903 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-705 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1106 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2003 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2609 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-909 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2009 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-307 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-103 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1506 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1405 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1609 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1109 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1702 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2704 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1007 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-404 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-202 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5877.2 | 0 | 5877.2 | 0.65 | 10914.8 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2508 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1706 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2808 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2809 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2708 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2706 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1105 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1903 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1805 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1902 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2205 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1205 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-203 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-907 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1604 (2BHK) (Refuge Area) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2601 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1409 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-607 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1304 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-302 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-608 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-407 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-805 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-601 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-605 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1102 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2405 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1602 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1808 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1201 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-903 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2702 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2403 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2001 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2305 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2507 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-408 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-507 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1707 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2702 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1409 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-801 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1104 (2BHK) (Refuge Area) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-401 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1209 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1402 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1806 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1608 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2308 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-407 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1204 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1403 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1303 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2406 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2201 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-604 (2BHK) (Refuge Area) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1608 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-707 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1305 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-603 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-304 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-606 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2207 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1108 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2202 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2202 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2008 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-809 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-106 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2302 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2401 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-403 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-201 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1601 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P3 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-503 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2507 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1301 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1302 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-803 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1101 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1201 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2101 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1808 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-902 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-403 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1401 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-108 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4609.15 | 0 | 4609.15 | 0.65 | 8559.85 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1406 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-809 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1408 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1905 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1202 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-208 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4608.69 | 0 | 4608.69 | 0.65 | 8560.31 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-301 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2709 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1001 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P3 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4608.69 | 0 | 4608.69 | 0.65 | 8560.31 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1102 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2103 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1607 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1705 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1804 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-305 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2808 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-308 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2707 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1504 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2509 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2804 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2204 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2806 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1804 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2208 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1801 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1602 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1403 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-704 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2504 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-906 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-804 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-504 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1106 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2102 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1009 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-901 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2303 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-508 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-304 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.315 | 4148.24 | 0 | 4148.24 | 0.685 | 9020.77 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1404 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2606 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1609 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2105 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2203 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-405 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-509 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1308 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1803 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-402 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-703 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-904 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1809 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P7 (INDOOR GAMES) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-805 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1505 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1003 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2802 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2108 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1002 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2409 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2308 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2404 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2703 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1803 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2706 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1108 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P1 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2809 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1503 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1908 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P6 (INDOOR GAMES) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2602 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2607 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2501 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2007 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2301 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1305 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2107 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-808 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2007 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1307 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1008 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-107 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-604 (2BHK) (Refuge Area) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2403 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1909 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2005 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-205 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2307 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-508 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2601 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1205 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1507 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-409 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-908 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-609 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1606 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-605 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-705 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2304 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-307 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2508 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1709 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2304 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-807 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-108 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2803 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1605 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2501 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2109 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-601 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1705 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1407 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2603 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2408 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2505 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-301 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.315 | 5289.48 | 0 | 5289.48 | 0.685 | 11502.52 |  | 31.5 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1703 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P1 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5876.61 | 0 | 5876.61 | 0.65 | 10915.39 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2309 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2509 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-709 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-709 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1501 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2506 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-807 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1306 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2101 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-203 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4609.15 | 0 | 4609.15 | 0.65 | 8559.85 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-107 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5877.2 | 0 | 5877.2 | 0.65 | 10914.8 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2004 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2209 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-201 (3BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0.35 | 5877.2 | 0 | 5877.2 | 0.65 | 10914.8 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2804 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-202 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1704 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1805 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1208 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1004 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P9 (MEDITATION & YOGA ROOM) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 16792 | 16792 | 0 | 16792 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1709 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1907 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2006 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1806 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-309 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1701 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2004 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2302 (3BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1500 | 1500 | 0 | 1500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2303 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1405 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P5 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1003 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2708 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-708 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1503 (2BHK) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-1909 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-P5 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4608.69 | 0 | 4608.69 | 0.65 | 8560.31 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2104 (2BHK) (Refuge Area) Electrical Work (L) | Fixing DB - Mkt | No. | 1 | 1400 | 1400 | 0 | 1400 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2104 (2BHK) (Refuge Area) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-103 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0.35 | 4609.15 | 0 | 4609.15 | 0.65 | 8559.85 |  | 35 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 587 | 0 | 23 Oct 2023 | LAXMI ELECTRICALS | Flat No-2009 (2BHK) Electrical Work (L) | Electrical Work (Labour) | No. | 1 | 13169 | 13169 | 0 | 13169 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 25 Oct 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 588 | 0 | 24 Oct 2023 | DRAUPADA EARTHMOVERS | Labour Camp Work | Murum Supply- DTR | Cu.Ft | 5710.38 | 7 | 39972.66 | 7195.08 | 47167.74 | 0 | 0 | 0 | 0 | 0 | 5710.38 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 589 | 0 | 25 Oct 2023 | SAIRAJ CONSTRUCTION | Wing-3 Cover Block Making (L) | Cover Block making | No. | 300 | 15 | 4500 | 810 | 5310 | 0 | 300 | 4500 | 810 | 5310 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 2 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Hutment | Fabrication work (L) | Kgs | 6634.61 | 30 | 199038.3 | 35826.9 | 234865.2 | 2.5 | 0 | 0 | 0 | 0 | 6634.61 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 0 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Hutment | Deck Sheet Fixing | Sq.Ft | 5286 | 10 | 52860 | 9514.8 | 62374.8 | 2.5 | 4615.44 | 46154.4 | 8307.78 | 54462.18 | 670.56 | 7912.62 |  | 87.3144 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 1 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Hutment | Fabrication work (L) | Kgs | 3171.14 | 30 | 95134.2 | 17124.16 | 112258.36 | 2.5 | 3171.14 | 95134.2 | 17124.16 | 112258.36 | 0 | 0 | 1) 200 x 100mm C Channel 2) 100 x 50mm C Channel 3) Angle 35 x 35mm | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 02 Nov 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 0 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Hutment | Fabrication work (L) | Kgs | 5683.2 | 30 | 170496 | 30689.28 | 201185.28 | 2.5 | 5683.2 | 170496 | 23915.64 | 194411.64 | 0 | 6773.64 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 0 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Hutment | Fabrication work (L) | Kgs | 712.8 | 30 | 21384 | 3849.12 | 25233.12 | 2.5 | 712.8 | 21384 | 3849.12 | 25233.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 0 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Hutment | Fabrication work (L) | Kgs | 4101.24 | 30 | 123037.2 | 22146.7 | 145183.9 | 2.5 | 4101.24 | 123037.2 | 22146.7 | 145183.9 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 0 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Dismantling 32 Rooms | Dismantling work | No. | 1 | 95000 | 95000 | 17100 | 112100 | 0 | 1 | 95000 | 17100 | 112100 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 0 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Hutment | Fabrication work (L) | Kgs | 3326.4 | 30 | 99792 | 17962.56 | 117754.56 | 2.5 | 3326.4 | 99792 | 17962.56 | 117754.56 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 590 | 0 | 25 Oct 2023 | PATILS FABRICATORS | Labour Camp Hutment | GI Sheet Fixing (L) | Sq.Ft | 22960 | 6 | 137760 | 24796.8 | 162556.8 | 2.5 | 19520.85 | 117125.1 | 21082.52 | 138207.62 | 3439.15 | 24349.18 |  | 85.0211 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | UTI. Vermiculture | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 591 | 0 | 26 Oct 2023 | DAILY PRABHAT & POONA DAILY NEWS PVT. LTD. | Advertisement | Advertisement Release- | No. | 1 | 30000 | 30000 | 1500 | 31500 | 0 | 1 | 30000 | 1500 | 31500 | 0 | 0 | PRABHAT DIWALI ISSUE - ONE FULL PAGE COLOUR DISPLAY ADVT. IN DIPAWALI VISHESHANK 2023 (ADVT SIZE AS 24 CM(H) X 18 CM(W) COLOUR DIRECT RELEASES. COST RS. 30000+ 5% GST | 100 |  | TEJAS RAVERKAR | sunita shirolkar | construction open | 31 Oct 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 592 | 0 | 27 Oct 2023 | LAA GRAPHICS | Advertisement | ACRYLIC LETTER WORK | No. | 0 | 28800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | MS FABRICATION BOX 6FT x 3TF x 8INCH DEPTH WITH BASE LEG BOTH SIDE WITH LED BACKLIT. | 0 |  | SWAPNIL JADHAV |  | construction open | 27 Oct 2023 |  | MKT. Media | Cancelled | ADITYA.CHOUGULE | 27 Oct 2023
GANGA ASMI | 593 | 0 | 27 Oct 2023 | LAA GRAPHICS | Advertisement | ACRYLIC LETTER WORK | No. | 1 | 28800 | 28800 | 5184 | 33984 | 0 | 0.8681 | 25001.28 | 4500 | 29501.28 | 0.1319 | 4482.72 | MS FABRICATION BOX 6FT x 3TF x 8INCH DEPTH WITH BASE LEG BOTH SIDE WITH LED BACKLIT TOTAL 18 SQ FT @ 1600/-RS PER SQFT/- | 86.81 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 27 Oct 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 594 | 0 | 27 Oct 2023 | JALDIP DILIP SHAH | Goel House Meeting Room No 3 & 4 Renovation Supervision Char | Labour Lumsum | No. | 1 | 151000 | 151000 | 0 | 151000 | 0 | 1 | 151000 | 0 | 151000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 594 | 1 | 27 Oct 2023 | JALDIP DILIP SHAH | Goel House Meeting Room No 3 & 4 Renovation Supervision Char | Labour Lumsum | No. | 0 | 151000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | MONALI CHAUDHAR | 28 Mar 2024
GANGA ASMI | 594 | 1 | 27 Oct 2023 | JALDIP DILIP SHAH | Goel House Meeting Room No 3 & 4 Renovation Supervision Char | Labour Lumsum | No. | 1 | 151000 | 151000 | 0 | 151000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 595 | 0 | 27 Oct 2023 | N A DECORATORS | Goel House Meeting Room No 3 & 4 Gypsum False Ceiling work | Labour Lumsum | No. | 1 | 70000 | 70000 | 12600 | 82600 | 2.5 | 0.9464 | 66248 | 11924.64 | 78172.64 | 0.0536 | 4427.36 |  | 94.64 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 595 | 1 | 27 Oct 2023 | N A DECORATORS | Goel House Meeting Room No 3 & 4 Gypsum False Ceiling work | Labour Lumsum | No. | 0 | 70000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | MONALI CHAUDHAR | 28 Mar 2024
GANGA ASMI | 595 | 1 | 27 Oct 2023 | N A DECORATORS | Goel House Meeting Room No 3 & 4 Gypsum False Ceiling work | Labour Lumsum | No. | 1 | 70000 | 70000 | 12600 | 82600 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 596 | 0 | 27 Oct 2023 | KHUSHI CUSHIONS WORKS | Goel House Meeting Room No 3 & 4 Kushan work | Labour Lumsum | No. | 1 | 75000 | 75000 | 0 | 75000 | 0 | 0.98 | 73500 | 0 | 73500 | 0.02 | 1500 |  | 98 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 596 | 1 | 27 Oct 2023 | KHUSHI CUSHIONS WORKS | Goel House Meeting Room No 3 & 4 Kushan work | Labour Lumsum | No. | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | MONALI CHAUDHAR | 28 Mar 2024
GANGA ASMI | 596 | 1 | 27 Oct 2023 | KHUSHI CUSHIONS WORKS | Goel House Meeting Room No 3 & 4 Kushan work | Labour Lumsum | No. | 1 | 75000 | 75000 | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 597 | 0 | 27 Oct 2023 | UMESH YADAV | Goel House Meeting Room No 3 & 4 Painting and Polishing work | Labour Lumsum | No. | 1 | 600000 | 600000 | 108000 | 708000 | 0 | 0.3634 | 218040 | 39242.7 | 257282.7 | 0.6366 | 450717.3 |  | 36.34 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 597 | 1 | 27 Oct 2023 | UMESH YADAV | Goel House Meeting Room No 3 & 4 Painting and Polishing work | Labour Lumsum | No. | 1 | 600000 | 600000 | 108000 | 708000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 597 | 1 | 27 Oct 2023 | UMESH YADAV | Goel House Meeting Room No 3 & 4 Painting and Polishing work | Labour Lumsum | No. | 0 | 600000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | MONALI CHAUDHAR | 28 Mar 2024
GANGA ASMI | 598 | 1 | 27 Oct 2023 | BACHHULAL ENTERPRISES | Goel House Meeting Room No 3 & 4 Flooring Civil renovation w | Labour Lumsum | No. | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | MONALI CHAUDHAR | 28 Mar 2024
GANGA ASMI | 598 | 1 | 27 Oct 2023 | BACHHULAL ENTERPRISES | Goel House Meeting Room No 3 & 4 Flooring Civil renovation w | Labour Lumsum | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 598 | 0 | 27 Oct 2023 | BACHHULAL ENTERPRISES | Goel House Meeting Room No 3 & 4 Flooring Civil renovation w | Labour Lumsum | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.24 | 24000 | 0 | 24000 | 0.76 | 76000 |  | 24 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 3 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Carpentary Work | Door Closer Fixing Work -BCo | No. | 2 | 1400 | 2800 | 0 | 2800 | 2.5 | 2 | 2800 | 504 | 3304 | 0 | -504 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 06 Nov 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 3 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Carpentary Work | Mirror Fixing | No. | 3 | 1800 | 5400 | 0 | 5400 | 2.5 | 3 | 5400 | 972 | 6372 | 0 | -972 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 06 Nov 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 0 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Meeting Room No 3 & 4 Carpentry Renovation Work | Labour Lumsum | No. | 1 | 500000 | 500000 | 0 | 500000 | 2.5 | 1 | 500000 | 0 | 500000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 3 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Carpentary Work | Door Repairing Work | No. | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 1 | 1000 | 180 | 1180 | 0 | -180 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 06 Nov 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 3 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Carpentary Work | Channel Fixing - SOS | No. | 1 | 750 | 750 | 0 | 750 | 2.5 | 1 | 750 | 135 | 885 | 0 | -135 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 06 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 2 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Meeting Room No 3 & 4 Carpentry Renovation Work | Labour Lumsum | No. | 1 | 44000 | 44000 | 0 | 44000 | 2.5 | 1 | 44000 | 0 | 44000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 3 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Carpentary Work | Wall Panelling Work | No. | 1 | 5000 | 5000 | 900 | 5900 | 2.5 | 1 | 5000 | 900 | 5900 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 06 Nov 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 1 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Meeting Room No 3 & 4 Carpentry Renovation Work | Labour Lumsum | No. | 0 | 2000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 06 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | MONALI CHAUDHAR | 28 Mar 2024
GANGA ASMI | 599 | 3 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Carpentary Work | Door Repairing Work | No. | 1 | 500 | 500 | 0 | 500 | 2.5 | 1 | 500 | 90 | 590 | 0 | -90 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 06 Nov 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 1 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Meeting Room No 3 & 4 Carpentry Renovation Work | Labour Lumsum | No. | 1 | 500000 | 500000 | 0 | 500000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 06 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 599 | 1 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Meeting Room No 3 & 4 Carpentry Renovation Work | Labour Lumsum | No. | 0 | 500000 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 06 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Cancelled | MONALI CHAUDHAR | 28 Mar 2024
GANGA ASMI | 599 | 3 | 27 Oct 2023 | LAXMI FURNITURE | Goel House Carpentary Work | Door Fixing (L) | No. | 2 | 1800 | 3600 | 0 | 3600 | 2.5 | 2 | 3600 | 648 | 4248 | 0 | -648 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 06 Nov 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 600 | 0 | 28 Oct 2023 | ANIL MAHTO ENTERPRISES | Painting (M+L) (Wanowadi PI) | Oil Paint (L+M) DEn | Sq.Ft | 250 | 12 | 3000 | 540 | 3540 | 2.5 | 180.87 | 2170.44 | 390.68 | 2561.12 | 69.13 | 978.88 |  | 72.348 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 600 | 0 | 28 Oct 2023 | ANIL MAHTO ENTERPRISES | Painting (M+L) (Wanowadi PI) | Transport Charges-SO | No. | 1 | 2000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 600 | 0 | 28 Oct 2023 | ANIL MAHTO ENTERPRISES | Painting (M+L) (Wanowadi PI) | Luster Paint (m+l)- BCo | Sq.Ft | 600 | 24 | 14400 | 2592 | 16992 | 2.5 | 600 | 14400 | 2592 | 16992 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 600 | 0 | 28 Oct 2023 | ANIL MAHTO ENTERPRISES | Painting (M+L) (Wanowadi PI) | OBD (M+L) DCH | Sq.Ft | 100 | 12 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 100 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 600 | 1 | 28 Oct 2023 | ANIL MAHTO ENTERPRISES | Painting (M+L) (Wanowadi PI) | Luster Paint (m+l)- BCo | Sq.Ft | 300 | 24 | 7200 | 1296 | 8496 | 2.5 | 188.35 | 4520.4 | 813.68 | 5334.08 | 111.65 | 3161.92 |  | 62.7833 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 02 Nov 2023 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 601 | 0 | 30 Oct 2023 | JAIPRAKASH RAMRATAN BAJAARI | Legal Expenses | Legal Expenses-BC | No. | 1 | 500000 | 500000 | 0 | 500000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 30 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 602 | 0 | 30 Oct 2023 | NIRMAL AUTOMATION PVT.LTD. | Goel House Gate No 2 Repair/Maintenance | 2 Channel Remote | No. | 2 | 1455 | 2910 | 523.8 | 3433.8 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 602 | 0 | 30 Oct 2023 | NIRMAL AUTOMATION PVT.LTD. | Goel House Gate No 2 Repair/Maintenance | Installation Charges | No. | 1 | 1455 | 1455 | 261.9 | 1716.9 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 603 | 1 | 31 Oct 2023 | JAISAN | Goel House Dept Labour for Meeting Room 3 & 4 Work | Contractor Profit-Mkt | No. | 70 | 50 | 3500 | 0 | 3500 | 0 | 0 | 0 | 0 | 0 | 70 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 603 | 0 | 31 Oct 2023 | JAISAN | Goel House Dept Labour for Meeting Room 3 & 4 Work | Male Coolie BC | No. | 60 | 650 | 39000 | 0 | 39000 | 0 | 10 | 6500 | 0 | 6500 | 50 | 32500 |  | 16.6667 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 603 | 0 | 31 Oct 2023 | JAISAN | Goel House Dept Labour for Meeting Room 3 & 4 Work | Contractor Profit-Mkt | No. | 70 | 50 | 3500 | 0 | 3500 | 0 | 10 | 500 | 0 | 500 | 60 | 3000 |  | 14.2857 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 603 | 1 | 31 Oct 2023 | JAISAN | Goel House Dept Labour for Meeting Room 3 & 4 Work | Male Coolie BC | No. | 60 | 650 | 39000 | 0 | 39000 | 0 | 0 | 0 | 0 | 0 | 60 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 603 | 1 | 31 Oct 2023 | JAISAN | Goel House Dept Labour for Meeting Room 3 & 4 Work | Mason - DCW | No. | 10 | 1050 | 10500 | 0 | 10500 | 0 | 0 | 0 | 0 | 0 | 10 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Nov 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 603 | 0 | 31 Oct 2023 | JAISAN | Goel House Dept Labour for Meeting Room 3 & 4 Work | Mason - DCW | No. | 10 | 1050 | 10500 | 0 | 10500 | 0 | 2 | 2100 | 0 | 2100 | 8 | 8400 |  | 20 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Nov 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 604 | 0 | 31 Oct 2023 | ANIMOTIONSZ | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 75000 | 75000 | 13500 | 88500 | 0 | 1 | 75000 | 13500 | 88500 | 0 | 0 | MANAGING THE CAMPAIGN FOR INCREASING THE ROI + CREATION OF ADS + LANDING PAGE + FACEBOOK PAID CAMPAIGN = MONITORING CHARGES PER MONTH 15,000/-RS PER MONTH + TAX AS ON 1ST NOV.2023 TO 31ST MARCH 2024. | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 31 Oct 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 605 | 0 | 01 Nov 2023 | MAGICBRICKS REALTY SERVICES LIMITED | ONLINE / DIGITAL Social / Digital Activity | DIGITAL / ONLINE MARKETING - CAMPAIGN / ADVT. | No. | 1 | 350000 | 350000 | 63000 | 413000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Ganga Asmi Wakad- Impact Visibility campaign : 1) project Spotlight 2) Listings for Pune search page 3) Project Ms, through MagicBricks.com for 90days. | 0 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 01 Nov 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 606 | 0 | 08 Nov 2023 | ARYA CONSULTANCY | Electrical Work Project Meter & Permissions | Elect Meters Installation (L)-UTI | No. | 1093 | 2000 | 2186000 | 393480 | 2579480 | 0 | 0 | 0 | 0 | 0 | 1093 | 0 | 1 Phase Residential, commercial & 3 phase residential,commercial & Buildingwise common. | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 606 | 0 | 08 Nov 2023 | ARYA CONSULTANCY | Electrical Work Project Meter & Permissions | Highrise Perm UTI | No. | 3 | 75000 | 225000 | 40500 | 265500 | 0 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 606 | 0 | 08 Nov 2023 | ARYA CONSULTANCY | Electrical Work Project Meter & Permissions | Highrise Perm UTI | No. | 2 | 45000 | 90000 | 16200 | 106200 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 606 | 0 | 08 Nov 2023 | ARYA CONSULTANCY | Electrical Work Project Meter & Permissions | LT SPL CT Meter | No. | 1 | 40000 | 40000 | 7200 | 47200 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 606 | 0 | 08 Nov 2023 | ARYA CONSULTANCY | Electrical Work Project Meter & Permissions | Transformer Charging -UTI | No. | 4 | 75000 | 300000 | 54000 | 354000 | 0 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 606 | 0 | 08 Nov 2023 | ARYA CONSULTANCY | Electrical Work Project Meter & Permissions | Elect Meters UTI | No. | 1093 | 3000 | 3279000 | 590220 | 3869220 | 0 | 1038.35 | 3115050 | 560709 | 3675759 | 54.65 | 193461 | 1 Phase Residential, commercial & 3 phase residential,commercial & Buildingwise common. | 95 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 607 | 4 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Godown & Electric room Making - 1 No. | GI Sheet Fixing (L) | Sq.Ft | 1335.27 | 5 | 6676.35 | 0 | 6676.35 | 2.5 | 1335.27 | 6676.35 | 0 | 6676.35 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Nov 2023 |  | UTI. Vermiculture | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | Door Frame making & Fixing work | No. | 6 | 800 | 4800 | 0 | 4800 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | B.C. Internal Finishing Itmes | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | G.I. Sheet Fixing - BC | Sq.Ft | 1594.04 | 4 | 6376.16 | 0 | 6376.16 | 2.5 | 0 | 0 | 0 | 0 | 1594.04 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 2 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Yard | Lumpsum work- DCW | No. | 1 | 7000 | 7000 | 0 | 7000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 1 | 08 Nov 2023 | PARTH ENTERPRISES | MS Fabrication For Aluform | Hole Making | No. | 4276 | 15 | 64140 | 0 | 64140 | 2.5 | 4276 | 64140 | 0 | 64140 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Nov 2023 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 4 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Godown & Electric room Making - 1 No. | GI Sheet Fixing (L) | Sq.Ft | 268.02 | 5 | 1340.1 | 0 | 1340.1 | 2.5 | 268.02 | 1340.1 | 0 | 1340.1 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Nov 2023 |  | UTI. Vermiculture | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Tower Crane MS Platform Plank Modifictn | Plank Cutting | No. | 96 | 100 | 9600 | 0 | 9600 | 2.5 | 0 | 0 | 0 | 0 | 96 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 0 | 08 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Fabrication for Concrete Bucket & Meter | Fabrication work (L) | Kgs | 226.92 | 12 | 2723.04 | 0 | 2723.04 | 2.5 | 226.92 | 2723.04 | 0 | 2723.04 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | Admin. Direct Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | Hinges (L) | No. | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 11 Nov 2023 |  | No category | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | M.S. Angles (L)- SOSB | Kgs | 75.9 | 12 | 910.8 | 0 | 910.8 | 2.5 | 0 | 0 | 0 | 0 | 75.9 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 4 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Godown & Electric room Making - 1 No. | Door Fixing (L) | No. | 1 | 400 | 400 | 0 | 400 | 2.5 | 1 | 400 | 0 | 400 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Nov 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Tower Crane MS Platform Plank Modifictn | MS Plate (L) | Kgs | 272 | 12 | 3264 | 0 | 3264 | 2.5 | 0 | 0 | 0 | 0 | 272 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 5 | 08 Nov 2023 | PARTH ENTERPRISES | Wing 1 - Window hard barrication work (Typical - 10 Floor) | Safety Barrication | Kgs | 3086.6 | 12 | 37039.2 | 0 | 37039.2 | 2.5 | 0 | 0 | 0 | 0 | 3086.6 | 0 |  | 9.9981 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 4 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Godown & Electric room Making - 1 No. | MS Square Pipe (L) | Kgs | 324.219 | 12 | 3890.63 | 0 | 3890.63 | 2.5 | 324.219 | 3890.63 | 0 | 3890.63 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 4 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Godown & Electric room Making - 1 No. | Taping Screw- SOSB | No. | 500 | 2.5 | 1250 | 0 | 1250 | 2.5 | 500 | 1250 | 0 | 1250 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | MS Square Pipe (L) | Kgs | 1403.25 | 12 | 16839 | 0 | 16839 | 2.5 | 0 | 0 | 0 | 0 | 1403.25 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 0 | 08 Nov 2023 | PARTH ENTERPRISES | Safety barrication on Slab | Safety Barrication | Kgs | 1713.29 | 12 | 20559.48 | 0 | 20559.48 | 2.5 | 1713.29 | 20559.48 | 0 | 20559.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 607 | 4 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Godown & Electric room Making - 1 No. | MS Square Pipe (L) | Kgs | 97.161 | 12 | 1165.93 | 0 | 1165.93 | 2.5 | 97.161 | 1165.93 | 0 | 1165.93 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 4 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Godown & Electric room Making - 1 No. | Door Fixing (L) | No. | 1 | 400 | 400 | 0 | 400 | 2.5 | 1 | 400 | 0 | 400 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 11 Nov 2023 |  | 09 CARPENTRY WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Tower Crane MS Platform Plank Modifictn | Welding work- DEn | No. | 29 | 100 | 2900 | 0 | 2900 | 2.5 | 0 | 0 | 0 | 0 | 29 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 0 | 08 Nov 2023 | PARTH ENTERPRISES | Safety barrication for Lift Shaft & Ducts | Fabrication Work (L) | Kgs | 169.439 | 12 | 2033.27 | 0 | 2033.27 | 2.5 | 169.439 | 2033.27 | 0 | 2033.27 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | DEV. Ext Development | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 607 | 4 | 08 Nov 2023 | PARTH ENTERPRISES | Aluform Godown & Electric room Making - 1 No. | GI Sheet Fixing (L) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 11 Nov 2023 |  | UTI. Vermiculture | Cancelled | ADITYA.CHOUGULE | 24 Apr 2024
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | Hinges (L) | No. | 14 | 30 | 420 | 0 | 420 | 2.5 | 0 | 0 | 0 | 0 | 14 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 1 | 08 Nov 2023 | PARTH ENTERPRISES | MS Fabrication For Aluform | Fabrication work (L) | Kgs | 7375.51 | 12 | 88506.12 | 0 | 88506.12 | 2.5 | 7374.98 | 88499.76 | 0 | 88499.76 | 0.53 | 6.36 |  | 99.9928 |  | DUSHANT.GORE | Swapnil Erande | construction open | 11 Nov 2023 |  | Admin. Direct Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Safety barrication for Lift Shaft & Ducts | Fabrication Work (L) | Kgs | 293.12 | 12 | 3517.44 | 0 | 3517.44 | 2.5 | 0 | 0 | 0 | 0 | 293.12 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 0 | 08 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Fabrication for Concrete Bucket & Meter | Full Welding work (M+L) | R.Ft | 54.3334 | 100 | 5433.34 | 0 | 5433.34 | 2.5 | 54.3334 | 5433.34 | 0 | 5433.34 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 11 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Tower Crane MS Platform Plank Modifictn | M.S.Channel (L) | Kgs | 95.6 | 12 | 1147.2 | 0 | 1147.2 | 2.5 | 0 | 0 | 0 | 0 | 95.6 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Safety barrication for Lift Shaft & Ducts | Fabrication Work (L) | Kgs | 58.99 | 12 | 707.88 | 0 | 707.88 | 2.5 | 0 | 0 | 0 | 0 | 58.99 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | Hinges (L) | No. | 12 | 50 | 600 | 0 | 600 | 2.5 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Safety barrication for Lift Shaft & Ducts | Fabrication Work (L) | Kgs | 134.38 | 12 | 1612.56 | 0 | 1612.56 | 2.5 | 0 | 0 | 0 | 0 | 134.38 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | M.S.Channel (L) | Kgs | 58.32 | 12 | 699.84 | 0 | 699.84 | 2.5 | 0 | 0 | 0 | 0 | 58.32 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Safety barrication for Lift Shaft & Ducts | Fabrication Work (L) | Kgs | 5.31 | 12 | 63.72 | 0 | 63.72 | 2.5 | 0 | 0 | 0 | 0 | 5.31 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | New Labour Camp | Hinges (L) | No. | 0 | 50 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 11 Nov 2023 |  | No category | Cancelled | MONALI CHAUDHAR | 09 Mar 2024
GANGA ASMI | 607 | 3 | 08 Nov 2023 | PARTH ENTERPRISES | Safety barrication for Lift Shaft & Ducts | Fabrication Work (L) | Kgs | 149.265 | 12 | 1791.18 | 0 | 1791.18 | 2.5 | 0 | 0 | 0 | 0 | 149.265 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 11 Nov 2023 |  | DEV. Ext Development | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.P5 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 404 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2303 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 406 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2807 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1103 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 202 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2608 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 306 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 708 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1407 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2704 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2409 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.106 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 204 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1908 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P4 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 401 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 603 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2706 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1702 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1307 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.905 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1206 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2505 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2004 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 907 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1106 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2708 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2003 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 605 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1508 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2501 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 502 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 602 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2801 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.705 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1602 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1003 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2401 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1407 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 609 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1702 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1505 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1405 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1807 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2303 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 901 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1709 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 405 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2005 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 308 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 602 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2307 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1302 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1107 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2708 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 301 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P4 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2103 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1701 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1709 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2608 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2702 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1705 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 305 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1909 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 903 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 701 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 209 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1201 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2802 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2504 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2804 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1506 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2009 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2405 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1902 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1109 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2001 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 201 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1305 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 204 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2509 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 906 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1105 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 506 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1209 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 907 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2405 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1204 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2405 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1808 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2406 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1804 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1503 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 803 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1508 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1209 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2103 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 105 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1906 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2706 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1809 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2801 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 804 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2803 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1605 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1504 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2401 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1503 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 404 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2709 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1902 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1309 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 101 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1303 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2804 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2303 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2407 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1805 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 706 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2305 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1002 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2702 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2704 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 808 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2301 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2102 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2006 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2409 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 206 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.705 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 102 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2609 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2309 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P1 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1504 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1908 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1802 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 706 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1205 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2204 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1405 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1606 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1507 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1305 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1802 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.205 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2606 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1304 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1203 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1902 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 601 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2203 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 808 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2708 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 306 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2005 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 904 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2009 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2404 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1702 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 603 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2606 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 907 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1503 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 203 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1802 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2507 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2705 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.107 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2107 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1107 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1109 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1301 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 504 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2709 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1109 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 705 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2802 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1005 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 901 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 401 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 302 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1809 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2505 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 704 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2401 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2804 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1403 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2304 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1108 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1404 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 407 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 904 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 206 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2006 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2509 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2009 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1901 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 203 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 602 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1107 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 804 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 803 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 109 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2305 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 605 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 809 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 405 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 208 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1705 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1109 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1302 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1406 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 702 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2004 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1101 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1205 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2403 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1401 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2004 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2706 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 408 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 806 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 902 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2205 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 508 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 606 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1504 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2503 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 601 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1803 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1901 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 403 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1206 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1004 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1705 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1704 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2407 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2606 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 505 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2207 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 901 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2008 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1502 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1406 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2209 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 804 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2208 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 305 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1808 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 507 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2002 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2207 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 302 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1803 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1308 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 403 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1502 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1302 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1001 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2308 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1003 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2801 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 404 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2607 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 507 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2207 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2803 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1002 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 106 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 501 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 404 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1703 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 608 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1702 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 907 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2508 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 302 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1304 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2307 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2407 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1904 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2105 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2204 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P3 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 203 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 803 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 303 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 102 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.107 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2602 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1209 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1501 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 201 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1105 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 902 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.107 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 603 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 403 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 201 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 702 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 402 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2006 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 401 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1407 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 503 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1703 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1607 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1704 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 403 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1308 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1301 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1901 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 701 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 908 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1301 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 703 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 408 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 905 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2503 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1609 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 808 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2001 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2007 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P2 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2607 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2501 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 703 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 305 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1802 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 801 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2501 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1505 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 607 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2205 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 301 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1904 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 209 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1009 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 606 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1507 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2707 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2509 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1707 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2007 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 204 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2102 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2605 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1106 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 502 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2603 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 304 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1806 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 806 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 203 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 304 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1406 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2708 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2207 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 501 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1002 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 507 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1704 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 601 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 708 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2105 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1706 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2806 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1005 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.705 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2406 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2407 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1006 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2408 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 701 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1608 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 407 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2505 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 204 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1204 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1502 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 103 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2003 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1601 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 302 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1108 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1409 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 709 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 104 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1103 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1006 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P2 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1402 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2802 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2107 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2609 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 504 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1506 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2208 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2404 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1309 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 303 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1701 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2805 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2106 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2304 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1707 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 308 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 807 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1602 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1808 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2601 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1207 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1907 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 309 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 103 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2408 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2306 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1907 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2809 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2808 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1208 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 204 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1804 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 301 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 502 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1806 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1007 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2101 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 405 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2406 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 908 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2506 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1809 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1905 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2107 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2607 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 403 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 709 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1506 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1708 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 108 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2603 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 405 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2509 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2402 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2401 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2109 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.905 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 701 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2703 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P1 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1409 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1804 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1309 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 809 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 508 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2704 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 704 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 704 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 409 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 402 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1807 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 402 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1001 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1401 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1605 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2601 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2307 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2106 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1708 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1407 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2508 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 207 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P3 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1306 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2504 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1008 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 504 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 702 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1606 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 807 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2708 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1504 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 105 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 404 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2009 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1601 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2602 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1004 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1403 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1703 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1706 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1107 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 303 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 707 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 906 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 706 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2806 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1108 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1607 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1008 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 408 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 308 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1803 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1308 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2609 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1801 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2308 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 209 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 104 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 809 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1002 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 801 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1308 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.607 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1101 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 103 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1307 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P2 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1408 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2005 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1902 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 409 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2504 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 201 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 301 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1701 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2606 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1609 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 306 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1706 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2203 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1101 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 309 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2709 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2206 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.205 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2003 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1404 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2008 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 903 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 202 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 706 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 903 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1702 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1708 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 409 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 904 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 101 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 503 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2506 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2601 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 106 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1509 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2309 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 503 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1204 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 207 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 207 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2302 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1006 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2201 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2003 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2004 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 807 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 608 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 805 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1502 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2809 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1003 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 908 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2407 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1305 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2107 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1709 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1408 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 207 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2606 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 108 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2804 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 709 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 105 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1908 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 505 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2809 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P3 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2308 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2302 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 506 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2307 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 703 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1608 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 603 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2507 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 407 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2405 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 308 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 906 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1505 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1301 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1906 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2502 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2403 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2501 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2007 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2704 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2804 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1208 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1204 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1509 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 209 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 608 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1209 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1103 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 909 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 205 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2304 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1603 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2009 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1408 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 402 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P4 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1405 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 307 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2701 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 302 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1402 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1103 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 802 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 601 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2207 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 508 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2302 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2702 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2204 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1704 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 506 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1807 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2301 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1303 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1203 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 404 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1501 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1905 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2608 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2002 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 901 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2402 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2409 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1105 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2201 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1603 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1204 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 102 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 302 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2402 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 904 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2502 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1609 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2109 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1108 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1005 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1506 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2306 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 103 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2503 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 101 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1505 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1904 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 101 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 807 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 308 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 108 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1006 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1305 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1101 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2502 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 405 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 507 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 606 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 101 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 809 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2406 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2007 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1601 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1105 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 208 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1102 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1901 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P1 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1605 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1201 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1308 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1408 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 708 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P3 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 304 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 605 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 503 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 608 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1103 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 301 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1806 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 105 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 709 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2703 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 201 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 606 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1903 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2601 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2404 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1107 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 503 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1706 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 105 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1608 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2705 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1404 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 307 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 305 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2709 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 803 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 404 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 905 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2703 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 502 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2703 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 109 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 102 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2208 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 801 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2801 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2505 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 401 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 902 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 409 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2209 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1306 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 307 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2309 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2808 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 402 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1405 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 206 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1008 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 703 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2005 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 504 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1005 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 605 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2301 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 502 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1207 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1105 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 808 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1906 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 804 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2807 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1801 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 204 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1304 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2701 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1003 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 202 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 802 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 403 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 908 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 802 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2805 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 806 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2101 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2402 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 904 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1409 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 201 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1208 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1102 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P5 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2306 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1907 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 509 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P2 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 502 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2707 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 806 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 508 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1809 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1402 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 509 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1801 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2106 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2808 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1009 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2405 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 703 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 505 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2008 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 108 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2109 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 208 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2408 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.607 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 507 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1507 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2605 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.805 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1608 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1905 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2107 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 506 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1904 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 309 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 609 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2206 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2308 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 808 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1606 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2304 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2602 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 902 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 708 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2503 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1405 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1202 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2404 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 802 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 408 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1108 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 103 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 707 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1703 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 103 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P2 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2504 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2303 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1008 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 101 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1801 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1004 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2605 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1407 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 508 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1803 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2807 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.607 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 806 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 709 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.905 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1303 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1502 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 206 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 309 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1703 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 702 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2309 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1401 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2408 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 301 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 204 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2707 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 907 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 405 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 903 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2002 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 303 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1906 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2802 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1903 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 202 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1504 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1409 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 909 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2807 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2103 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2808 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1009 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2404 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2703 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1004 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 706 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 401 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1901 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2301 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2305 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2307 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 205 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1903 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2403 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1307 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 609 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2601 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 102 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2603 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2809 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 704 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.106 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2607 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2305 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2007 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1001 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 208 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2008 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1102 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2506 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1304 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 306 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2103 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 206 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1601 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1708 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P4 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2302 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 401 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1202 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P3 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1106 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2803 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1707 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2501 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1602 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2301 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2005 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 304 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1201 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1501 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1207 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 205 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2004 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2303 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1409 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1209 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 803 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1307 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1205 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1603 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2806 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 103 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 307 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1404 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 504 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 909 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 607 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 801 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1807 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P4 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1907 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 606 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 605 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 305 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1001 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2208 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2502 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 901 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1306 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 501 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1003 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1102 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2805 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 202 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.205 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.805 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1606 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 406 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 401 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 203 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1805 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 609 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1805 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1904 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2305 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 309 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2203 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2506 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2001 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1305 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1709 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1006 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1805 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.805 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1803 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2802 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1705 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2808 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2609 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1202 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2206 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 609 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2701 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 405 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2204 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1008 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1406 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 306 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2506 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 509 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2102 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1007 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 903 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 102 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 202 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1403 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.P5 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2701 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2504 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 702 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1303 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1903 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P5 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2201 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2409 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2608 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1909 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 506 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1201 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 301 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 407 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2603 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 503 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1402 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 406 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1805 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2203 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1808 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1607 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P1 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1007 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2609 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 303 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 105 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 802 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2707 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1506 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2106 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1301 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2101 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2707 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1508 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2508 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2108 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1205 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2001 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1202 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 504 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 909 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2209 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2608 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2705 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1005 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2101 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2204 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 707 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1701 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1608 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1205 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2402 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 704 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2602 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 902 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2102 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1709 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 307 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1801 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1403 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 303 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2704 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1908 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 207 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2705 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2701 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1501 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1909 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1903 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1203 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2805 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 409 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 203 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2206 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2201 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2605 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2702 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2709 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2002 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2408 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2706 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1509 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1208 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 501 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2108 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1106 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 509 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 909 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 107 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1806 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1306 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1601 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1907 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2409 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2105 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 707 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1602 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1605 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2502 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1807 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 501 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2205 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 402 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1508 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 302 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1206 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1302 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 805 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 304 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 305 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2803 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2103 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 505 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2202 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2209 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 501 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 203 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2308 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1403 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1603 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 406 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 105 Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 2000 | 2000 | 0 | 2000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2302 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1509 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1207 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2505 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1804 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2801 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 107 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2202 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2507 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1704 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1605 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 408 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1007 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1607 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2202 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2105 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 208 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2607 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1902 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.505 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2805 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 809 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1609 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1905 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 701 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 608 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1406 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2209 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1203 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.505 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 205 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2807 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 305 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2605 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 707 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2507 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1009 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1507 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1603 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 304 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2406 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 407 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 402 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2201 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1909 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1001 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2102 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2508 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 801 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1909 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 602 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2706 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1708 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 602 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 906 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2105 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 406 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2108 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1503 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.106 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2202 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2806 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2403 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.1106 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1404 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2205 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1804 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1802 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2202 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1505 2 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1402 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2108 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2304 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1401 (3BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1009 (2BHK) Internal Plumbing (L) | Int Plumbing CP & Sanitary Fittings | Per Flat | 1 | 3800 | 3800 | 0 | 3800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 201 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1908 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 109 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1206 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2401 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1302 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 109 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1306 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2806 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2508 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1906 3 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2206 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2003 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2002 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1707 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 705 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2507 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1207 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2603 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 603 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1309 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1707 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1304 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1503 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1101 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1002 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 708 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 109 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1706 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2809 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1401 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1507 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 108 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 503 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 403 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2006 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1201 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1809 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 303 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1004 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1408 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2008 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 101 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1705 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1501 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2306 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2503 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1609 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1303 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2006 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 504 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 102 Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2509 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2306 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 906 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2309 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 601 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 509 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2001 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 908 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1309 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1606 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2203 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1701 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2108 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 502 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.P5 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1109 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1208 2BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.2705 2 BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. P1 3BHK Core Cutting | Core Cutting Work 5" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2602 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1206 3 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No.505 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1508 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1602 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2205 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1607 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1509 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 804 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2803 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1806 3 BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2109 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 304 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2208 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2702 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1007 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1202 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 2101 3BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1808 2BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1905 2 BHK Core Cutting | Core Cutting 4" -UTI | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2109 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2106 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1307 (3BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2403 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 0 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 209 (2BHK) Internal Plumbing (L) | Int Plumbing PPRC Work | Per Flat | 1 | 5700 | 5700 | 1026 | 6726 | 2.5 | 1 | 5700 | 0 | 5700 | 0 | 1026 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 807 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1102 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 501 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 1203 2BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 608 | 1 | 08 Nov 2023 | PRASNA PLUMBING SERVICE | Flat No. 202 3BHK Core Cutting | Core Cutting Work 2" BCE | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 609 | 0 | 08 Nov 2023 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Backfilling | JCB Hiring | Hrs | 350 | 850 | 297500 | 53550 | 351050 | 0 | 232 | 197200 | 35496 | 232696 | 118 | 118354 |  | 66.2857 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 610 | 0 | 08 Nov 2023 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Backfilling | Hyva on Day Basis | Day | 20 | 9000 | 180000 | 32400 | 212400 | 0 | 0 | 0 | 0 | 0 | 20 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 610 | 1 | 08 Nov 2023 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Backfilling | Spreading & Levelling Work | Cu.Mtrs | 495 | 30 | 14850 | 2673 | 17523 | 0 | 0 | 0 | 0 | 0 | 495 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 610 | 0 | 08 Nov 2023 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Backfilling | Pocklain with Bucket-DTR | Hrs | 0 | 1800 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | DEV. Trimix Road | Cancelled | DUSHANT.GORE | 02 Dec 2023
GANGA ASMI | 610 | 0 | 08 Nov 2023 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Backfilling | Pocklain with Bucket-DTR | Hrs | 70 | 1800 | 126000 | 22680 | 148680 | 0 | 61 | 109800 | 19764 | 129564 | 9 | 19116 |  | 87.1429 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 610 | 1 | 08 Nov 2023 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Backfilling | Backfilling | Cu.Mtrs | 495 | 60 | 29700 | 5346 | 35046 | 0 | 190 | 11400 | 2052 | 13452 | 305 | 21594 |  | 38.3838 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 610 | 2 | 08 Nov 2023 | DRAUPADA EARTHMOVERS | Wing-2 Substructure Backfilling | Tractor Trips (Internal) DLT | Trips | 100 | 400 | 40000 | 7200 | 47200 | 0 | 72 | 28800 | 0 | 28800 | 28 | 18400 |  | 72 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Local Trips | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2807 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 204 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 402 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1202 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 207 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1207 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2505 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1805 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1803 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1509 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2303 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1105 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1204 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1107 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2407 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 409 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2205 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2706 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2203 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1304 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1308 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1404 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2402 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2709 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1408 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 907 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 408 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1102 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2009 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1307 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1908 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2609 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P2 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1705 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 806 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2006 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1609 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 209 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1209 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2609 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1309 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 301 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1406 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1405 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1108 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2804 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2506 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1101 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2008 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2001 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 801 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2306 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1201 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 306 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1006 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 605 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 404 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 102 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2204 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1305 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2202 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2705 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 705 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2601 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2303 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2204 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2301 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 706 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2704 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 101 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1701 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1404 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1901 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 501 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2301 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2603 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1206 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2009 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1401 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 903 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 107 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1702 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1204 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 507 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 506 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2201 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1903 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 503 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2403 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 203 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 203 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 307 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1909 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1603 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1602 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2308 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1201 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 104 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1708 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 302 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1702 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1904 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2101 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2202 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 608 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 401 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 205 (1RK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2809 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1205 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2403 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1005 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P4 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 307 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 502 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 209 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1803 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1105 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 403 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1904 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 702 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1805 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1102 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 804 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2608 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1802 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 603 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2804 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 108 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 305 (1RK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2203 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2302 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 309 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1704 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2706 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1607 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2106 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1102 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2005 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1007 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2705 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1402 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 906 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2502 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 908 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 405 (1RK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 305 (1RK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 306 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2505 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1903 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2802 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2503 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2605 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1809 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1309 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 905 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 704 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1701 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 908 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1203 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1901 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 301 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 403 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2109 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2702 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1009 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1004 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1501 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 609 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2601 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1704 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 606 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 404 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1001 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 401 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 402 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2407 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 101 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 104 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2307 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2707 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1407 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 902 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 606 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1304 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2505 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1103 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 406 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1002 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1407 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2803 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1107 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2101 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 804 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 102 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 701 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2703 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1109 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 703 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1807 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1305 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1301 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2501 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 801 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1906 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2709 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2803 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1905 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2002 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1008 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2207 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 807 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 504 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1002 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2607 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 404 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1306 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2503 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1905 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1602 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1302 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 209 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 101 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 303 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1407 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1202 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1004 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1407 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 502 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2106 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 106 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2007 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1309 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1507 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1301 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1803 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1207 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1805 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1802 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 608 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 801 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1003 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 303 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1403 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1603 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2807 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2409 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1608 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1201 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 104 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1308 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 705 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2109 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2402 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2203 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2405 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 201 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 309 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1409 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 401 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 704 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 207 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1506 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 508 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1508 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 608 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P3 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1506 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 608 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1202 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1902 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1806 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2504 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 504 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 703 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 102 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 301 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2109 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 205 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 407 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 707 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 204 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 704 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 906 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 403 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1804 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 105 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2103 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2108 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 303 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 207 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2803 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 206 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1306 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 806 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2605 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 601 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1303 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1708 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1105 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 107 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 906 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 307 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1103 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2206 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 302 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1903 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1001 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 202 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2608 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 907 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2601 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2803 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 105 (1RK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1707 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 501 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 101 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 908 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 809 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1706 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2708 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 101 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2501 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 408 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 206 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1706 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 206 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2605 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2309 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 306 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2702 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1004 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1004 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 103 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2702 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 103 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 901 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 503 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1608 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2802 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 806 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 704 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1007 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 401 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2807 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 201 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 802 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 701 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1106 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2409 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 303 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 402 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2801 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 205 (1RK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1907 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2709 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 903 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1806 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 302 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 203 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 102 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1304 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 405 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2401 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2105 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 902 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 405 (1RK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 504 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2002 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2003 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1507 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1207 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 706 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1209 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 901 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 407 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2205 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 503 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 304 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 304 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1706 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1908 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2602 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 303 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 304 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2007 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 109 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 206 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1503 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 801 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1005 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 705 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1608 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 702 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P5 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 501 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1306 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2701 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 807 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 505 (1RK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1206 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1607 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2205 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 205 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 101 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 302 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 404 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2306 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 501 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2004 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2605 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 103 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1407 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1606 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1804 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2406 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2207 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 709 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2103 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1508 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 603 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 306 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2207 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1708 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 201 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1906 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1207 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1605 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2501 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 105 (1RK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1909 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1709 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 908 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 307 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 201 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 205 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1001 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1403 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2202 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1509 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 803 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2007 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1703 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2702 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 708 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2206 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2305 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1705 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2806 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 904 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1206 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2403 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 602 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2508 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 905 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1906 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P3 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1404 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2403 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 609 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2609 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1102 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1806 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 209 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 606 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 501 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1105 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P2 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1706 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 208 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1409 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 101 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 802 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1506 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2409 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2706 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2504 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 507 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P2 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 501 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 106 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 507 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2108 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 804 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 408 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2504 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2708 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2506 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 405 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 401 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2005 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1606 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2402 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 401 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 703 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2202 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2606 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2307 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1208 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2704 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2204 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1101 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P5 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 202 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2807 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2405 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2603 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2809 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 505 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1408 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 201 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1108 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 702 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1401 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 901 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2507 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1208 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 206 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1806 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2102 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2501 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2402 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2403 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 307 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1901 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 901 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 303 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2502 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 305 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1606 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 903 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1401 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 602 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1801 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 502 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2709 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2009 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 809 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2705 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 503 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2401 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1506 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 804 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1609 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1709 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1702 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1809 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1507 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1607 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2103 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 203 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1309 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 708 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2307 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 905 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2508 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2107 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2708 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 607 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1501 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1707 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 605 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1409 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2008 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2304 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2405 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2108 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2502 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2006 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 702 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1906 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1106 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 503 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1909 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2606 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1709 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1806 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 508 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2308 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 109 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 303 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1106 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2407 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 203 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 302 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1404 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1502 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1907 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 103 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 504 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 707 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2701 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2405 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1707 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1102 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 208 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 404 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P1 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2202 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2507 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 105 (1RK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 701 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2303 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 402 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1101 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1808 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1906 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2509 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 405 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 503 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 305 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1001 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 905 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1302 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2709 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2802 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 503 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 107 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1603 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1502 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 907 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2708 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2805 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 305 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1008 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1505 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 902 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1307 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1009 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 302 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2801 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2805 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 505 (1RK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2603 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1305 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1008 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 505 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2208 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2706 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2603 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1608 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 102 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 304 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2809 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2607 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1203 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2602 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1706 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 102 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2605 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 708 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2508 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2209 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2703 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1204 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2808 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 204 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 909 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 801 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1809 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 409 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2302 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P3 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 701 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P1 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 503 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2406 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2602 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2506 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2006 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 304 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2509 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2408 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2509 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1205 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2009 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1207 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1303 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1904 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 307 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1202 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1303 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 204 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 708 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2509 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1703 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 205 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 607 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 202 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2308 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1505 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 608 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2301 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2408 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 304 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1609 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 302 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 205 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2607 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2607 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2208 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 507 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2002 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2302 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1107 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1208 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1902 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2706 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1502 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1009 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1606 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 607 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 308 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 804 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 105 (1RK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 206 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1008 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2008 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1003 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2809 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2607 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2201 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1609 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2801 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2405 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2304 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1007 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1705 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 607 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1403 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2601 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1007 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2707 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2506 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 502 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 207 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2206 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1407 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1807 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 602 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2107 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1809 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1006 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2309 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1503 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1601 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1508 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2608 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2805 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1606 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 902 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2001 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 502 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 504 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2005 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 203 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1006 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1108 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2602 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1709 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1307 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 401 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1108 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 903 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 807 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2508 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1508 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2506 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1708 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2508 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2406 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 501 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2703 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2608 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1704 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 403 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 404 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 205 (1RK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2601 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2705 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2404 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1601 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2102 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1807 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 202 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1801 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 109 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1806 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 603 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 203 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1605 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 501 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 105 (1RK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 404 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2809 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2102 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 705 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 402 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 108 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1807 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 204 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1301 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 702 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 506 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 503 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2707 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 601 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1304 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 501 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 203 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1403 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2701 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 204 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1906 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1409 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1303 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1509 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P5 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 403 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P5 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 308 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1703 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 107 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2309 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2308 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 303 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1102 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 806 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 306 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 205 (1RK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 909 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 609 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1608 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1804 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 808 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 305 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1306 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 201 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 405 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 607 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 509 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 809 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 103 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1503 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1903 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2304 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2801 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1908 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2004 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2209 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1503 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2501 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 407 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 407 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2608 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 705 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 404 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 603 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 609 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1705 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 609 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2506 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1008 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2105 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 301 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1109 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2307 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1301 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 103 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2002 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2703 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 106 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 304 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 403 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2704 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1203 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2304 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2706 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P5 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1607 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 405 (1RK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1805 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2208 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 505 (1RK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2004 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 203 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P1 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1001 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 302 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2207 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1406 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1708 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2102 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 409 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2603 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 301 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 402 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2501 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2004 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2306 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 703 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1801 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2007 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 406 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1605 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 401 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1106 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P2 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2602 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 303 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2105 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2202 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P4 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2508 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1406 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P3 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 108 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1201 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2401 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1202 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 904 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2008 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2507 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 305 (1RK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2802 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 602 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1509 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1401 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1302 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2208 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2107 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 304 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2701 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2201 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2502 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2503 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 707 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 802 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 408 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 504 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 609 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 909 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 904 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1302 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 908 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2606 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1703 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2808 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 209 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1003 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 402 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 108 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P4 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1901 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1801 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1108 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 405 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1209 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 302 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 809 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2802 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1608 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2402 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 504 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1206 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1308 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2807 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 305 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1905 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 504 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1301 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 606 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1904 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2203 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 406 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1909 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2808 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1808 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1607 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2102 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 207 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2001 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2203 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 805 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1507 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 502 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1103 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2404 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 406 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 404 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 106 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1305 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2001 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 706 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2406 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2105 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 101 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2101 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P3 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1702 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 202 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1704 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1306 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 906 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 108 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 109 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1103 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 409 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2505 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2204 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 301 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2004 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1708 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 203 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P4 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1601 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1902 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 803 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1109 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1603 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2001 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2704 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 403 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 905 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 503 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 606 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1304 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P2 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1306 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 902 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P1 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1904 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2801 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2008 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 605 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 709 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2606 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 703 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1504 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 401 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1809 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1606 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1103 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1803 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 103 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 601 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1107 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1506 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 202 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1204 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 406 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 208 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 101 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 104 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1603 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P1 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1109 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 201 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2302 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1003 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1409 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 908 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P2 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1507 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 902 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 407 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1507 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2708 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 805 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2806 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1905 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1702 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1002 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 401 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2109 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 901 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 808 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1402 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2209 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 202 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2804 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1602 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2308 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2007 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1201 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2208 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2003 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1406 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 707 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 301 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1006 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1401 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1902 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2503 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1908 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 101 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1005 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 608 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 808 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 904 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2803 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 402 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 805 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1908 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1505 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 501 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2504 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 507 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2509 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1301 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1209 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1905 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2002 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 803 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2701 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 309 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 709 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 803 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2806 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1405 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 803 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 303 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 301 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1309 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1602 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1704 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1402 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 305 (1RK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1501 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 508 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 105 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1209 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2708 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 403 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2605 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1308 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2805 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 405 (1RK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1808 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2503 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1701 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2804 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1302 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 509 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1402 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1308 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1404 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1208 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1901 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 907 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 607 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2408 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 909 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 401 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2302 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2003 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2607 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2609 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1909 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1802 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2703 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 505 (1RK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1005 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1607 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 105 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 502 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1204 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2305 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2602 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 201 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1101 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 505 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2808 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2404 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 602 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1804 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 805 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1205 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 102 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 809 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 103 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 308 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2504 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 201 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P3 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 904 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 706 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2005 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2809 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1203 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 704 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 105 (1RK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1106 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 708 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 808 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2802 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 402 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 205 (1RK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2302 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 907 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 207 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2803 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 509 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1902 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P4 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2406 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 409 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 805 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2106 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 909 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2502 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1602 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 109 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2609 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2306 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1406 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2102 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 107 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P4 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 308 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 205 (1RK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1008 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2305 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 102 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 305 (1RK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2009 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2209 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1903 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 104 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 403 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 408 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1504 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 409 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 304 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2309 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1504 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 709 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1709 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1909 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1009 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 109 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2408 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 203 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 605 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 102 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 708 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1804 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 201 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 403 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 204 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 504 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1001 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 305 (1RK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1805 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 603 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 405 (1RK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 502 (1BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1408 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 401 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2201 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 201 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 505 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2008 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 505 (1RK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 309 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 303 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 304 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1406 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 308 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2105 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 701 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 103 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 103 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1208 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 301 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1502 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2309 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 506 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 105 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 502 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2006 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2003 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 101 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 809 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1805 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 105 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2309 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 505 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1408 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 408 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 104 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 806 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1504 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1203 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1508 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2507 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 503 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1009 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 204 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1003 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 404 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1702 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1907 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 601 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1002 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1205 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 202 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 601 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1003 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1201 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1505 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2304 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 703 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 403 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 103 (1BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 500 | 500 | 0 | 500 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 802 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1803 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2305 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2107 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1703 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1706 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 805 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 602 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2209 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1801 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2203 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1209 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1005 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1808 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2301 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1007 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1202 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2404 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2705 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2207 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1308 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 508 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1505 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 208 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1802 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1509 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2507 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 102 (1BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 204 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2804 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2303 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 504 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 906 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2205 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1503 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 102 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2702 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1206 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2201 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 402 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2307 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2603 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 709 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 404 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2301 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1204 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 706 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 704 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1207 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1107 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 107 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1307 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2306 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2608 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 802 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 606 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2404 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2504 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 509 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 406 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2106 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 903 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1402 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2807 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2002 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2006 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 603 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 808 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1903 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1804 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 503 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1609 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2704 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1509 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2702 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1601 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1208 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2207 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2304 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2108 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1403 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 405 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 601 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1703 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1401 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2609 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 302 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 807 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1305 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2101 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 108 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1501 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1405 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1707 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 304 (1BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2505 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1309 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2707 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1006 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2109 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2306 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2005 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1605 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1105 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1107 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1709 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2105 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2206 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2001 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 706 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1902 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 804 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2808 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2408 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2409 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2805 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1007 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 707 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P5 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2402 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1908 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1302 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 203 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1303 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2409 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1203 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 504 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 202 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 201 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 202 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 208 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2801 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1205 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 205 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 301 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2707 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 202 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 508 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1802 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2209 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 905 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1701 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 302 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 808 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 204 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1802 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1808 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 605 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1307 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 506 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 304 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2704 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 402 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No P1 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2503 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 906 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2103 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1206 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 308 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 509 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 502 (1BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 701 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1505 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 502 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1704 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1808 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2606 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 803 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2401 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 402 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2106 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 903 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1701 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1605 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2208 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2201 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2502 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 505 (1RK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2301 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 405 (1RK) External Plumbing (L) | Duct Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2707 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2103 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1807 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2305 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1403 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 509 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 901 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2308 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1205 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 209 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2409 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2303 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1404 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1101 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2305 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 904 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2003 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2101 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2005 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2407 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1408 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1601 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1409 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2101 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 303 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 403 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1105 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2808 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2505 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 508 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2009 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2806 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1006 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 507 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2108 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2107 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 302 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 407 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1602 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2307 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 305 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1801 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1803 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2109 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 807 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1405 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1501 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2703 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1304 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 301 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1106 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2507 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1601 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2103 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2205 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1103 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2204 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2601 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 806 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 309 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1504 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 204 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1303 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 504 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1109 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 101 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1705 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1002 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 202 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1707 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 505 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1108 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1503 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1901 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1402 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1907 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1004 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2405 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1005 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1408 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 102 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2204 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 105 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1109 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2206 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2003 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1004 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1609 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1705 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 501 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 106 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1603 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1809 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1101 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 103 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 807 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2107 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 301 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2806 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1807 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1405 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1009 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2406 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2108 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 801 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1707 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 309 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2509 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 702 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 709 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2303 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2401 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1907 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1605 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1405 (2BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 605 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 306 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1701 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1504 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 502 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1501 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2606 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2805 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 909 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1305 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2705 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2205 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 106 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2407 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 506 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1307 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 907 (3BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1502 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2006 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 802 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2709 (2BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2206 (3BHK) External Plumbing (L) | Rainwater Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1508 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 404 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 707 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1502 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1506 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1002 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 506 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1907 (3BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2404 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2403 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1905 (2BHK) External Plumbing (L) | Gully Trap & Chamber | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2106 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 1904 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA- Flat No 501 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | MAHDA. Flat No 204 (1BHK) External Plumbing (L) | Rising Main Line | Flat | 1 | 1000 | 1000 | 0 | 1000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2007 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2401 (3BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 705 (2BHK) External Plumbing (L) | Duct Line | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2806 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2408 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2701 (3BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 208 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2804 (2BHK) External Plumbing (L) | OHWT Distribution | Flat | 1 | 1900 | 1900 | 0 | 1900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2004 (2BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 611 | 0 | 09 Nov 2023 | PRASNA PLUMBING SERVICE | Wing-1 Flat No 2407 (3BHK) External Plumbing (L) | Testing & Misc | Flat | 1 | 950 | 950 | 0 | 950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 08 PLUMBING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 612 | 0 | 09 Nov 2023 | NILESH POTE | Site Staff Misc. Expanses | Miscellaneous Expenses | No. | 1 | 10663 | 10663 | 0 | 10663 | 0 | 1 | 10663 | 0 | 10663 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 09 Nov 2023 |  | 14 MISC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 613 | 0 | 09 Nov 2023 | ATHARVA AIRCON SYSTEM | Goel House AC Repair work of Drain Pump at Dining area | PVC Drain Pipe 25mm | No. | 1 | 195 | 195 | 35.1 | 230.1 | 0 | 1 | 195 | 35.1 | 230.1 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 613 | 0 | 09 Nov 2023 | ATHARVA AIRCON SYSTEM | Goel House AC Repair work of Drain Pump at Dining area | Hi Wall Drain Pump | No. | 2 | 4652.5 | 9305 | 1674.9 | 10979.9 | 0 | 2 | 9305 | 1674.9 | 10979.9 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 613 | 0 | 09 Nov 2023 | ATHARVA AIRCON SYSTEM | Goel House AC Repair work of Drain Pump at Dining area | Installation Charges | No. | 2 | 500 | 1000 | 180 | 1180 | 0 | 2 | 1000 | 180 | 1180 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 614 | 3 | 16 Nov 2023 | VIKAS GARADE | Site Expenses for Hydra & Crane | Site Expenses -SO | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.4924 | 49240 | 0 | 49240 | 0.5076 | 50760 |  | 49.24 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 614 | 0 | 16 Nov 2023 | VIKAS GARADE | Pooja Expenses 18/09/2023 | Site Expenses -SO | No. | 1 | 16337 | 16337 | 0 | 16337 | 0 | 1 | 16337 | 0 | 16337 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 614 | 2 | 16 Nov 2023 | VIKAS GARADE | Labour Camp Gutter Cleaning Work | Labour Lumsum-DTR | No. | 1 | 2500 | 2500 | 0 | 2500 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | DEV. Trimix Road | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 614 | 1 | 16 Nov 2023 | VIKAS GARADE | Site Expenses for Hydra & Crane | Site Expenses -SO | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.8678 | 86780 | 0 | 86780 | 0.1322 | 13220 |  | 86.78 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 615 | 1 | 16 Nov 2023 | VIKAS GARADE | Sales Office Grid Ceiling Repairing Work | Lumpsum work- DCW | No. | 1 | 2324 | 2324 | 0 | 2324 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 27 Nov 2023 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 615 | 0 | 16 Nov 2023 | VIKAS GARADE | New Sales Office Electrical Work | Electrical work lumpsum-SO | No. | 1 | 23000 | 23000 | 0 | 23000 | 0 | 1 | 23000 | 0 | 23000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 615 | 1 | 16 Nov 2023 | VIKAS GARADE | Sales Office Grid Ceiling Repairing Work | Labour Lumpsum | No. | 1 | 7000 | 7000 | 0 | 7000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 27 Nov 2023 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 616 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | Wing.1 Parking Column/SW/Pardi Plaster P1 To P6 | Single Coat Plaster (L) | Sq.Ft | 2411.13 | 25 | 60278.25 | 10850.08 | 71128.33 | 2.5 | 0 | 0 | 0 | 0 | 2411.13 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 05 GYPSUM & PLASTER | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 616 | 1 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA External Plaster West Side External Plaster | External Plaster- BC | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 27 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 14 Feb 2024
GANGA ASMI | 616 | 1 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA External Plaster South Side External Plaster | External Plaster- BC | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 27 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 14 Feb 2024
GANGA ASMI | 616 | 1 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA External Plaster Internal Duct Plaster | External Plaster- BC | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 27 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 14 Feb 2024
GANGA ASMI | 616 | 1 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA External Plaster South Side External Plaster | External Plaster- BC | Sq.Ft | 0 | 30 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 27 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | MONALI CHAUDHAR | 12 Feb 2024
GANGA ASMI | 616 | 1 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA External Plaster Internal Duct Plaster | Double Coat Plaster work (L) | Sq.Ft | 4314.4 | 30 | 129432 | 23297.76 | 152729.76 | 2.5 | 0 | 0 | 0 | 0 | 4314.4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 616 | 1 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA External Plaster South Side External Plaster | Double Coat Plaster work (L) | Sq.Ft | 6397.1 | 30 | 191913 | 34544.34 | 226457.34 | 2.5 | 0 | 0 | 0 | 0 | 6397.1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 616 | 1 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA External Plaster West Side External Plaster | Double Coat Plaster work (L) | Sq.Ft | 7889.8 | 30 | 236694 | 42604.92 | 279298.92 | 2.5 | 0 | 0 | 0 | 0 | 7889.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | 05 GYPSUM & PLASTER | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | Wing.1 Parking Column/SW/Pardi Plaster P1 To P6 | Single Coat Plaster (L) | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA.CHOUGULE | 21 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 103 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 103 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 92.44 | 15 | 1386.6 | 249.58 | 1636.18 | 2.5 | 92.44 | 1386.6 | 249.58 | 1636.18 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 15.98 | 15 | 239.7 | 43.14 | 282.84 | 2.5 | 15.98 | 239.7 | 43.14 | 282.84 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 102 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 34.96 | 15 | 524.4 | 94.4 | 618.8 | 2.5 | 0 | 0 | 0 | 0 | 34.96 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 403 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 65.39 | 980.85 | 176.56 | 1157.41 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 148.14 | 15 | 2222.1 | 399.98 | 2622.08 | 2.5 | 0 | 0 | 0 | 0 | 148.14 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 143.3 | 15 | 2149.5 | 386.92 | 2536.42 | 2.5 | 143.3 | 2149.5 | 386.92 | 2536.42 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 302 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 504 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 302 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 121.5 | 15 | 1822.5 | 328.06 | 2150.56 | 2.5 | 121.5 | 1822.5 | 328.06 | 2150.56 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 402 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 101.72 | 15 | 1525.8 | 274.64 | 1800.44 | 2.5 | 101.72 | 1525.8 | 274.64 | 1800.44 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 101 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 111.08 | 15 | 1666.2 | 299.92 | 1966.12 | 2.5 | 0 | 0 | 0 | 0 | 111.08 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 102 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 148.14 | 15 | 2222.1 | 399.98 | 2622.08 | 2.5 | 148.14 | 2222.1 | 399.98 | 2622.08 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 204 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 402 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 15.98 | 15 | 239.7 | 43.14 | 282.84 | 2.5 | 15.98 | 239.7 | 43.14 | 282.84 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 105 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.45 | 15 | 441.75 | 79.52 | 521.27 | 2.5 | 29.45 | 441.75 | 79.52 | 521.27 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 30.14 | 15 | 452.1 | 81.38 | 533.48 | 2.5 | 0 | 0 | 0 | 0 | 30.14 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 102 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 303 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.76 | 15 | 446.4 | 80.36 | 526.76 | 2.5 | 29.76 | 446.4 | 80.36 | 526.76 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 103 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 502 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 503 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 0 | 0 | 0 | 0 | 65.39 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 503 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.76 | 15 | 446.4 | 80.36 | 526.76 | 2.5 | 0 | 0 | 0 | 0 | 29.76 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 304 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 302 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 105 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 103 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 104 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 203 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 302 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 502 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 101.72 | 15 | 1525.8 | 274.64 | 1800.44 | 2.5 | 0 | 0 | 0 | 0 | 101.72 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 501 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 143.3 | 15 | 2149.5 | 386.92 | 2536.42 | 2.5 | 0 | 0 | 0 | 0 | 143.3 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 202 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 504 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.45 | 15 | 441.75 | 79.52 | 521.27 | 2.5 | 29.45 | 441.75 | 79.52 | 521.27 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 502 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 105 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 404 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 402 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 121.5 | 15 | 1822.5 | 328.06 | 2150.56 | 2.5 | 121.5 | 1822.5 | 328.06 | 2150.56 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 402 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 105 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 501 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 143.3 | 15 | 2149.5 | 386.92 | 2536.42 | 2.5 | 0 | 0 | 0 | 0 | 143.3 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 105 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 105 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.45 | 15 | 441.75 | 79.52 | 521.27 | 2.5 | 0 | 0 | 0 | 0 | 29.45 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 501 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 102 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 101.72 | 15 | 1525.8 | 274.64 | 1800.44 | 2.5 | 0 | 0 | 0 | 0 | 101.72 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 503 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 22.28 | 15 | 334.2 | 60.16 | 394.36 | 2.5 | 22.28 | 334.2 | 60.16 | 394.36 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 402 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 503 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 111.08 | 15 | 1666.2 | 299.92 | 1966.12 | 2.5 | 111.08 | 1666.2 | 299.92 | 1966.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 202 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 121.5 | 15 | 1822.5 | 328.06 | 2150.56 | 2.5 | 121.5 | 1822.5 | 328.06 | 2150.56 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 501 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 22.28 | 15 | 334.2 | 60.16 | 394.36 | 2.5 | 0 | 0 | 0 | 0 | 22.28 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 10.9 | 163.5 | 29.44 | 192.94 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 203 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 65.39 | 980.85 | 176.56 | 1157.41 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 502 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 121.5 | 15 | 1822.5 | 328.06 | 2150.56 | 2.5 | 0 | 0 | 0 | 0 | 121.5 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | Wing.1 Parking Column/SW/Pardi Plaster P1 To P6 | Single Coat Plaster (L) | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA.CHOUGULE | 21 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 10.9 | 163.5 | 29.44 | 192.94 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 105 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 301 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 111.08 | 15 | 1666.2 | 299.92 | 1966.12 | 2.5 | 111.08 | 1666.2 | 299.92 | 1966.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 302 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 504 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 0 | 0 | 0 | 0 | 65.39 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 505 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 148.14 | 15 | 2222.1 | 399.98 | 2622.08 | 2.5 | 0 | 0 | 0 | 0 | 148.14 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | Wing.1 Parking Column/SW/Pardi Plaster P1 To P6 | Single Coat Plaster (L) | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA.CHOUGULE | 21 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 103 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 22.28 | 15 | 334.2 | 60.16 | 394.36 | 2.5 | 22.28 | 334.2 | 60.16 | 394.36 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 104 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 30.14 | 15 | 452.1 | 81.38 | 533.48 | 2.5 | 0 | 0 | 0 | 0 | 30.14 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 204 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 65.39 | 980.85 | 176.56 | 1157.41 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.45 | 15 | 441.75 | 79.52 | 521.27 | 2.5 | 0 | 0 | 0 | 0 | 29.45 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 99.71 | 15 | 1495.65 | 269.22 | 1764.87 | 2.5 | 99.71 | 1495.65 | 269.22 | 1764.87 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 15.98 | 15 | 239.7 | 43.14 | 282.84 | 2.5 | 0 | 0 | 0 | 0 | 15.98 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 22.28 | 15 | 334.2 | 60.16 | 394.36 | 2.5 | 22.28 | 334.2 | 60.16 | 394.36 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 403 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 102 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 121.5 | 15 | 1822.5 | 328.06 | 2150.56 | 2.5 | 0 | 0 | 0 | 0 | 121.5 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 104 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 0 | 0 | 0 | 0 | 65.39 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 203 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 92.44 | 15 | 1386.6 | 249.58 | 1636.18 | 2.5 | 92.44 | 1386.6 | 249.58 | 1636.18 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 103 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 92.44 | 15 | 1386.6 | 249.58 | 1636.18 | 2.5 | 0 | 0 | 0 | 0 | 92.44 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 303 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 65.39 | 980.85 | 176.56 | 1157.41 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 101 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 10.9 | 163.5 | 29.44 | 192.94 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 505 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 30.14 | 15 | 452.1 | 81.38 | 533.48 | 2.5 | 30.14 | 452.1 | 81.38 | 533.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 502 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 34.96 | 15 | 524.4 | 94.4 | 618.8 | 2.5 | 0 | 0 | 0 | 0 | 34.96 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 15.98 | 15 | 239.7 | 43.14 | 282.84 | 2.5 | 15.98 | 239.7 | 43.14 | 282.84 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 505 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.45 | 15 | 441.75 | 79.52 | 521.27 | 2.5 | 0 | 0 | 0 | 0 | 29.45 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 501 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 301 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 504 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 99.71 | 15 | 1495.65 | 269.22 | 1764.87 | 2.5 | 0 | 0 | 0 | 0 | 99.71 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 402 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 301 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 103 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 401 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | Wing.1 Parking Column/SW/Pardi Plaster P1 To P6 | Single Coat Plaster (L) | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA.CHOUGULE | 21 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 202 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 202 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 99.71 | 15 | 1495.65 | 269.22 | 1764.87 | 2.5 | 99.71 | 1495.65 | 269.22 | 1764.87 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 304 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 505 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 105 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 401 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 501 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 15.98 | 15 | 239.7 | 43.14 | 282.84 | 2.5 | 0 | 0 | 0 | 0 | 15.98 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 101 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 104 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 30.14 | 15 | 452.1 | 81.38 | 533.48 | 2.5 | 30.14 | 452.1 | 81.38 | 533.48 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 104 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 505 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 504 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 201 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 143.3 | 15 | 2149.5 | 386.92 | 2536.42 | 2.5 | 143 | 2145 | 386.1 | 2531.1 | 0.3 | 5.32 |  | 99.7906 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 302 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 505 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 104 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 102 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 301 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 504 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 103 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 0 | 0 | 0 | 0 | 65.39 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.76 | 15 | 446.4 | 80.36 | 526.76 | 2.5 | 29.76 | 446.4 | 80.36 | 526.76 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 402 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 34.96 | 15 | 524.4 | 94.4 | 618.8 | 2.5 | 34.96 | 524.4 | 94.4 | 618.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 102 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 104 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 102 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 148.14 | 15 | 2222.1 | 399.98 | 2622.08 | 2.5 | 148.14 | 2222.1 | 399.98 | 2622.08 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 304 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 65.39 | 980.85 | 176.56 | 1157.41 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 99.71 | 15 | 1495.65 | 269.22 | 1764.87 | 2.5 | 0 | 0 | 0 | 0 | 99.71 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 504 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 30.14 | 15 | 452.1 | 81.38 | 533.48 | 2.5 | 0 | 0 | 0 | 0 | 30.14 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 503 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 405 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 104 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 10.9 | 163.5 | 29.44 | 192.94 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 202 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 302 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 34.96 | 15 | 524.4 | 94.4 | 618.8 | 2.5 | 34.96 | 524.4 | 94.4 | 618.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 302 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 201 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 104 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 92.44 | 15 | 1386.6 | 249.58 | 1636.18 | 2.5 | 0 | 0 | 0 | 0 | 92.44 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 503 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 501 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 204 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 305 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 402 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 202 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | Wing.1 Parking Column/SW/Pardi Plaster P1 To P6 | Single Coat Plaster (L) | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | 05 GYPSUM & PLASTER | Cancelled | ADITYA.CHOUGULE | 21 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 404 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 65.39 | 15 | 980.85 | 176.56 | 1157.41 | 2.5 | 65.39 | 980.85 | 176.56 | 1157.41 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 201 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 143.3 | 15 | 2149.5 | 386.92 | 2536.42 | 2.5 | 143.3 | 2149.5 | 386.92 | 2536.42 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 404 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 104 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 403 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 503 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 92.44 | 15 | 1386.6 | 249.58 | 1636.18 | 2.5 | 0 | 0 | 0 | 0 | 92.44 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 104 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 0 | 0 | 0 | 0 | 10.9 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.76 | 15 | 446.4 | 80.36 | 526.76 | 2.5 | 29.76 | 446.4 | 80.36 | 526.76 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 103 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 29.76 | 15 | 446.4 | 80.36 | 526.76 | 2.5 | 0 | 0 | 0 | 0 | 29.76 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 401 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 111.08 | 15 | 1666.2 | 299.92 | 1966.12 | 2.5 | 111.08 | 1666.2 | 299.92 | 1966.12 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 205 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 105 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 148.14 | 15 | 2222.1 | 399.98 | 2622.08 | 2.5 | 0 | 0 | 0 | 0 | 148.14 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 302 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 101.72 | 15 | 1525.8 | 274.64 | 1800.44 | 2.5 | 101.72 | 1525.8 | 274.64 | 1800.44 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 503 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 101 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 22.28 | 15 | 334.2 | 60.16 | 394.36 | 2.5 | 0 | 0 | 0 | 0 | 22.28 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 202 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 101.72 | 15 | 1525.8 | 274.64 | 1800.44 | 2.5 | 101.72 | 1525.8 | 274.64 | 1800.44 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 10.9 | 163.5 | 29.44 | 192.94 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 501 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 111.08 | 15 | 1666.2 | 299.92 | 1966.12 | 2.5 | 0 | 0 | 0 | 0 | 111.08 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 103 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 102 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 202 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 34.96 | 15 | 524.4 | 94.4 | 618.8 | 2.5 | 34.96 | 524.4 | 94.4 | 618.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 504 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 103 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 104 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 99.71 | 15 | 1495.65 | 269.22 | 1764.87 | 2.5 | 0 | 0 | 0 | 0 | 99.71 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 103 Kitchen otta (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 403 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 203 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 204 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 303 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 201 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 15 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 303 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 10.9 | 15 | 163.5 | 29.44 | 192.94 | 2.5 | 10.9 | 163.5 | 29.44 | 192.94 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 404 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 401 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 304 WHB (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 202 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA.Flat No 402 Utility (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 617 | 0 | 16 Nov 2023 | JAI SEVALAL CONSTRUCTION | MHADA-Flat No 502 Toilet Rough (Tar) Plaster | Rough Plaster | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | Rough coat Plaster for Wing-1 Mhada Bldg. | 0 |  | ADITYA.CHOUGULE |  | construction open | 21 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | ADITYA.CHOUGULE | 22 Nov 2023
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 1 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 1 | 3000 | 3000 | 0 | 3000 | 0 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 618 | 0 | 17 Nov 2023 | AQUA CLEAN | Labour Camp Water Tank Cleaning | Cleaning Work - SO | No. | 4 | 3200 | 12800 | 2304 | 15104 | 0 | 4 | 12800 | 0 | 12800 | 0 | 2304 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 619 | 0 | 18 Nov 2023 | KARAN JAGRAM BALMIKI | Site Expenses Curing & House Keeping | Housekeeping-SMS | Month | 1 | 25000 | 25000 | 0 | 25000 | 0 | 1 | 25000 | 0 | 25000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | SOC. M. Maintenace Staff | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 620 | 0 | 18 Nov 2023 | SPEEDNET OPTICAL NETWORK PRIVATE LIMITED | Goel House- Internet Connection charges. | Speed Net connection | Month | 12 | 2250 | 27000 | 4860 | 31860 | 0 | 12 | 27000 | 4860.02 | 31860.02 | 0 | -0.02 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 621 | 0 | 18 Nov 2023 | SPEEDNET OPTICAL NETWORK PRIVATE LIMITED | Ganga Asmi - Internet Connection charges. | Speed Net connection | Month | 12 | 750 | 9000 | 1620 | 10620 | 0 | 0 | 0 | 0 | 0 | 12 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 622 | 0 | 18 Nov 2023 | PURVA CONSTRUCTION | Labour Camp Construction M-10 & M-20 | Steel Binding | Kgs | 1500 | 8 | 12000 | 2160 | 14160 | 2.5 | 1180.58 | 9444.64 | 1700.04 | 11144.68 | 319.42 | 3015.32 |  | 78.7053 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 02 RCC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 622 | 0 | 18 Nov 2023 | PURVA CONSTRUCTION | Labour Camp Construction M-10 & M-20 | Concreting Work-Dld | Sq.Ft | 3905.89 | 6 | 23435.34 | 4218.36 | 27653.7 | 2.5 | 3196.91 | 19181.46 | 3452.66 | 22634.12 | 708.98 | 5019.58 |  | 81.8484 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | DEV. Landscape/Equipment | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 622 | 0 | 18 Nov 2023 | PURVA CONSTRUCTION | Labour Camp Construction M-10 & M-20 | Plum Concrete | Cu.Mtrs | 30 | 600 | 18000 | 3240 | 21240 | 2.5 | 30 | 18000 | 3240 | 21240 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | DEV. Compound Wall | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 622 | 0 | 18 Nov 2023 | PURVA CONSTRUCTION | Labour Camp Pole Concrete 1:2:4 | Concrete Work - Bcp | No. | 62 | 200 | 12400 | 2232 | 14632 | 2.5 | 62 | 12400 | 2232 | 14632 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 622 | 0 | 18 Nov 2023 | PURVA CONSTRUCTION | Labour Camp Construction M-10 & M-20 | Concreting Work-Dld | Sq.Ft | 5799.64 | 4 | 23198.56 | 4175.74 | 27374.3 | 2.5 | 3706.91 | 14827.64 | 2668.98 | 17496.62 | 2092.73 | 9877.68 |  | 63.9162 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | DEV. Landscape/Equipment | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 623 | 0 | 20 Nov 2023 | RITU ENTERPRISES | Goel House (L) Tie Beam RCC work | Labour Lumsum | No. | 1 | 25000 | 25000 | 4500 | 29500 | 2.5 | 1 | 25000 | 4500 | 29500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 01 EARTHWORK & ROADWORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 624 | 0 | 20 Nov 2023 | HB POLYTECH INDUSTRIES | Wing.1 Parking Surface Grinding 4th Slab Top | Surface Grinding work | Sq.m. | 984.6 | 75 | 73845 | 13292.1 | 87137.1 | 2.5 | 338.71 | 25403.25 | 4572.58 | 29975.83 | 645.89 | 57161.27 | All tools,Equipments,Labour,Transport,Loading/Unloading,Maintenance,shifting,Consumables in Contractors Scope.Rate Final for Single/One Step Grinding work if Double/Two Step Grinding work done then no extra cost will be paid. | 34.4008 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 624 | 0 | 20 Nov 2023 | HB POLYTECH INDUSTRIES | Wing.1 Parking Surface Grinding 2nd Slab Top | Surface Grinding work | Sq.m. | 984.6 | 75 | 73845 | 13292.1 | 87137.1 | 2.5 | 338.71 | 25403.25 | 4572.58 | 29975.83 | 645.89 | 57161.27 | All tools,Equipments,Labour,Transport,Loading/Unloading,Maintenance,shifting,Consumables in Contractors Scope.Rate Final for Single/One Step Grinding work if Double/Two Step Grinding work done then no extra cost will be paid. | 34.4008 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 624 | 0 | 20 Nov 2023 | HB POLYTECH INDUSTRIES | Wing-1 Parking Surface Grinding 1st Slab Top | Surface Grinding work | Sq.m. | 984.6 | 75 | 73845 | 13292.1 | 87137.1 | 2.5 | 0 | 0 | 0 | 0 | 984.6 | 0 | All tools,Equipments,Labour,Transport,Loading/Unloading,Maintenance,shifting,Consumables in Contractors Scope.Rate Final for Single/One Step Grinding work if Double/Two Step Grinding work done then no extra cost will be paid. | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 624 | 0 | 20 Nov 2023 | HB POLYTECH INDUSTRIES | Wing.1 Parking Surface Grinding 5th Slab Top | Surface Grinding work | Sq.m. | 984.6 | 75 | 73845 | 13292.1 | 87137.1 | 2.5 | 0 | 0 | 0 | 0 | 984.6 | 0 | All tools,Equipments,Labour,Transport,Loading/Unloading,Maintenance,shifting,Consumables in Contractors Scope.Rate Final for Single/One Step Grinding work if Double/Two Step Grinding work done then no extra cost will be paid. | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 624 | 0 | 20 Nov 2023 | HB POLYTECH INDUSTRIES | Wing.1 Parking Surface Grinding 3rd Slab Top | Surface Grinding work | Sq.m. | 984.6 | 75 | 73845 | 13292.1 | 87137.1 | 2.5 | 338.71 | 25403.25 | 4572.58 | 29975.83 | 645.89 | 57161.27 | All tools,Equipments,Labour,Transport,Loading/Unloading,Maintenance,shifting,Consumables in Contractors Scope.Rate Final for Single/One Step Grinding work if Double/Two Step Grinding work done then no extra cost will be paid. | 34.4008 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 625 | 1 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Pile Concreting Work | Mtrs | 134.4 | 300 | 40320 | 7257.6 | 47577.6 | 2.5 | 11 | 3300 | 594 | 3894 | 123.4 | 43683.6 |  | 8.1845 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Non Tower Area NTA Piling | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 28.2 | 1800 | 50760 | 9136.8 | 59896.8 | 2.5 | 13.5 | 24300 | 4374 | 28674 | 14.7 | 31222.8 |  | 47.8723 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Mobilization | No. | 1 | 280000 | 280000 | 50400 | 330400 | 0 | 1 | 280000 | 50400 | 330400 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Non Tower Area NTA Piling | Pile Concreting Work | Mtrs | 33.6 | 300 | 10080 | 1814.4 | 11894.4 | 2.5 | 33.6 | 10080 | 1814.4 | 11894.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 1 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Reinforcement for Piling-BC | Mtrs | 134.4 | 250 | 33600 | 6048 | 39648 | 2.5 | 23.8 | 5950 | 1071 | 7021 | 110.6 | 32627 |  | 17.7083 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Pile Concreting Work | Mtrs | 201.6 | 300 | 60480 | 10886.4 | 71366.4 | 2.5 | 201.6 | 60480 | 10886.4 | 71366.4 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Non Tower Area NTA Piling | Reinforcement for Piling-BC | Mtrs | 33.6 | 250 | 8400 | 1512 | 9912 | 2.5 | 33.6 | 8400 | 1512 | 9912 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 2 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Pile Concreting Work | Mtrs | 0 | 300 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 22 Nov 2023 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 12 Feb 2024
GANGA ASMI | 625 | 1 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 21.6 | 2500 | 54000 | 9720 | 63720 | 2.5 | 21.6 | 54000 | 9720 | 63720 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Non Tower Area NTA Piling | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 5.4 | 2500 | 13500 | 2430 | 15930 | 2.5 | 5.4 | 13500 | 2430 | 15930 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 2 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 0 | 2500 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Cancelled | DUSHANT.GORE | 12 Feb 2024
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 169.2 | 1800 | 304560 | 54820.8 | 359380.8 | 2.5 | 95.7 | 172260 | 31006.8 | 203266.8 | 73.5 | 156114 |  | 56.5603 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 32.4 | 2500 | 81000 | 14580 | 95580 | 2.5 | 32.4 | 81000 | 14580 | 95580 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 1 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 112.8 | 1800 | 203040 | 36547.2 | 239587.2 | 2.5 | 0 | 0 | 0 | 0 | 112.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 2 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Piling work 600 mm. dia.(Machine Pile) | Mtrs | 77.6 | 2500 | 194000 | 34920 | 228920 | 2.5 | 77.6 | 194000 | 34920 | 228920 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 0 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Reinforcement for Piling-BC | Mtrs | 201.6 | 250 | 50400 | 9072 | 59472 | 2.5 | 201.6 | 50400 | 9072 | 59472 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 625 | 2 | 20 Nov 2023 | JACHAK PILING FOUNDATION | Wing-3 Parking NTA Piling | Reinforcement for Piling-BC | Mtrs | 0 | 250 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 22 Nov 2023 |  | B.C. RCC Substructure | Cancelled | DUSHANT.GORE | 12 Feb 2024
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 626 | 0 | 20 Nov 2023 | VITTHAL GANPAT SHEDGE | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 627 | 0 | 20 Nov 2023 | SHEDGE SATYAWAN JAYRAM | Labour Camp Land Rent 05/10/23 To 05/12/24 | Rent Charges | Month | 1 | 11000 | 11000 | 0 | 11000 | 0 | 1 | 11000 | 0 | 11000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 628 | 1 | 21 Nov 2023 | VITHAL DHARMA KAMBLE | Site Expenses for Hydra & Crane | Site Expenses -SO | No. | 0 | 100000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 27 Nov 2023 |  | S OH Expenses | Cancelled | DUSHANT.GORE | 15 Mar 2024
GANGA ASMI | 628 | 0 | 21 Nov 2023 | VITHAL DHARMA KAMBLE | Site Expenses for Hydra & Crane | Site Expenses -SO | No. | 1 | 100000 | 100000 | 0 | 100000 | 0 | 0.9921 | 99210 | 0 | 99210 | 0.0079 | 790 |  | 99.21 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 629 | 1 | 21 Nov 2023 | SP ENGINEERS AND LAND SURVEYORS | Survey Work | Visiting Charges-AIE | No. | 5 | 4500 | 22500 | 4050 | 26550 | 0 | 3 | 13500 | 2430 | 15930 | 2 | 10620 |  | 60 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 629 | 1 | 21 Nov 2023 | SP ENGINEERS AND LAND SURVEYORS | Survey Work | Total Station Point marking. | No. | 100 | 100 | 10000 | 1800 | 11800 | 0 | 84 | 8400 | 1512 | 9912 | 16 | 1888 |  | 84 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 27 Nov 2023 |  | DEV. Club House | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 629 | 0 | 21 Nov 2023 | SP ENGINEERS AND LAND SURVEYORS | Compound Wall Point marking by total station | Total Station Point marking. | No. | 60 | 100 | 6000 | 1080 | 7080 | 0 | 0 | 0 | 0 | 0 | 60 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | DEV. Club House | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 629 | 1 | 21 Nov 2023 | SP ENGINEERS AND LAND SURVEYORS | Survey Work | Visiting Charges-AIE | No. | 1 | 8000 | 8000 | 1440 | 9440 | 0 | 1 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | DUSHANT.GORE | construction open | 27 Nov 2023 |  | Admin. Indirect Expenses | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 630 | 1 | 21 Nov 2023 | SP ENGINEERS AND LAND SURVEYORS | UGWT RCC Point marking by total station | Total Statiotn Survey | Day | 3 | 4500 | 13500 | 2430 | 15930 | 0 | 1 | 4500 | 810 | 5310 | 2 | 10620 |  | 33.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | Land Cost | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 630 | 0 | 21 Nov 2023 | SP ENGINEERS AND LAND SURVEYORS | UGWT RCC Point marking by total station | Total Station Point marking. | No. | 160 | 100 | 16000 | 2880 | 18880 | 0 | 160 | 16000 | 2880 | 18880 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | DEV. Club House | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 631 | 0 | 22 Nov 2023 | KAIZEN DESIGN SOLUTIONS | ECBC Consultancy PMAY 2329 A | ECBC Compliance | No. | 1 | 70000 | 70000 | 12600 | 82600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Old Workorder no. 18.0 In Project PMAY 2329 A | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 29 Nov 2023 |  | 03 CONSULTANCY | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 631 | 0 | 22 Nov 2023 | KAIZEN DESIGN SOLUTIONS | ECBC Consultancy PMAY 2329 A | ECBC Compliance | No. | 0 | 75000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 29 Nov 2023 |  | 03 CONSULTANCY | Cancelled | ADITYA.CHOUGULE | 29 Nov 2023
GANGA ASMI | 632 | 0 | 22 Nov 2023 | VITHAL DHARMA KAMBLE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.8033 | 12049.5 | 0 | 12049.5 | 0.1967 | 2950.5 |  | 80.33 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 632 | 0 | 22 Nov 2023 | VITHAL DHARMA KAMBLE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 632 | 0 | 22 Nov 2023 | VITHAL DHARMA KAMBLE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.8966 | 13449 | 0 | 13449 | 0.1034 | 1551 |  | 89.66 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 632 | 0 | 22 Nov 2023 | VITHAL DHARMA KAMBLE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 0.8 | 12000 | 0 | 12000 | 0.2 | 3000 |  | 80 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 632 | 0 | 22 Nov 2023 | VITHAL DHARMA KAMBLE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 632 | 0 | 22 Nov 2023 | VITHAL DHARMA KAMBLE | Site Staff Misc. Expanses | Miscellaneous Expenses. - SO | Month | 1 | 15000 | 15000 | 0 | 15000 | 0 | 1 | 15000 | 0 | 15000 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 2 | 22 Nov 2023 | PARTH ENTERPRISES | Site Infra Store godown,site office & duct closing | MS Square Pipe (M+L) | Kgs | 0 | 12 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 27 Nov 2023 |  | No category | Cancelled | MONALI CHAUDHAR | 02 Mar 2024
GANGA ASMI | 633 | 2 | 22 Nov 2023 | PARTH ENTERPRISES | Site Infra Store godown,site office & duct closing | Meta colour Sheet Fixing BC | Sq.Ft | 1568.43 | 4 | 6273.72 | 0 | 6273.72 | 2.5 | 1568.43 | 6273.72 | 0 | 6273.72 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 1 | 22 Nov 2023 | PARTH ENTERPRISES | Steel Cutting Yard | G.I. Sheet Removing - SOI | Sq.Ft | 1814.8104 | 2.5 | 4537.03 | 0 | 4537.03 | 0 | 1814.81 | 4537.03 | 0 | 4537.03 | 0.0004 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 2 | 22 Nov 2023 | PARTH ENTERPRISES | Site Infra Store godown,site office & duct closing | Door making & fixing-SOSB | No. | 7 | 800 | 5600 | 0 | 5600 | 2.5 | 7 | 5600 | 0 | 5600 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 1 | 22 Nov 2023 | PARTH ENTERPRISES | Steel Cutting Yard | Labour lumpsum | No. | 1 | 500 | 500 | 0 | 500 | 0 | 1 | 500 | 0 | 500 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 2 | 22 Nov 2023 | PARTH ENTERPRISES | Site Infra Store godown,site office & duct closing | Meta colour Sheet Fixing BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 27 Nov 2023 |  | B.C. BBM, Plaster, POP | Cancelled | MONALI CHAUDHAR | 02 Mar 2024
GANGA ASMI | 633 | 2 | 22 Nov 2023 | PARTH ENTERPRISES | Site Infra Store godown,site office & duct closing | MS Square Pipe (L) | Kgs | 348.21 | 12 | 4178.52 | 0 | 4178.52 | 2.5 | 348.21 | 4178.52 | 0 | 4178.52 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 27 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 2 | 22 Nov 2023 | PARTH ENTERPRISES | Site Infra Store godown,site office & duct closing | Meta colour Sheet Fixing BC | Sq.Ft | 288 | 5 | 1440 | 0 | 1440 | 2.5 | 288 | 1440 | 0 | 1440 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 0 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Store, Steel Yard Fabrication | MS Channel. (L) | Kgs | 85.5 | 12 | 1026 | 0 | 1026 | 2.5 | 0 | 0 | 0 | 0 | 85.5 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | No category | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 633 | 0 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Store, Steel Yard Fabrication | Channel removing- SOSB | Kgs | 346.8 | 6 | 2080.8 | 0 | 2080.8 | 0 | 0 | 0 | 0 | 0 | 346.8 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 633 | 2 | 22 Nov 2023 | PARTH ENTERPRISES | Site Infra Store godown,site office & duct closing | Fabrication work - BCo | Kgs | 123.24 | 12 | 1478.88 | 0 | 1478.88 | 2.5 | 123.24 | 1478.88 | 0 | 1478.88 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 0 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Store, Steel Yard Fabrication | MS Pipe Removing | Kgs | 327.26 | 6 | 1963.56 | 0 | 1963.56 | 0 | 0 | 0 | 0 | 0 | 327.26 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 633 | 2 | 22 Nov 2023 | PARTH ENTERPRISES | Site Infra Store godown,site office & duct closing | Window Fixing | No. | 5 | 300 | 1500 | 0 | 1500 | 2.5 | 5 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 27 Nov 2023 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 1 | 22 Nov 2023 | PARTH ENTERPRISES | Steel Cutting Yard | Channel removing- SOSB | Kgs | 646 | 6 | 3876 | 0 | 3876 | 0 | 646 | 3876 | 0 | 3876 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 0 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Store, Steel Yard Fabrication | G.I. Sheet Fixing - SOI | Sq.Ft | 2045.16 | 5 | 10225.8 | 0 | 10225.8 | 2.5 | 0 | 0 | 0 | 0 | 2045.16 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 633 | 3 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Office,Store,Safety Office Room removing | GI Sheet removing-SO | Sq.Ft | 3171.33 | 2 | 6342.66 | 0 | 6342.66 | 0 | 3171.33 | 6342.66 | 0 | 6342.66 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Expenses | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 0 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Store, Steel Yard Fabrication | G.I. Sheet Removing - SOI | Sq.Ft | 749.1744 | 2.5 | 1872.94 | 0 | 1872.94 | 0 | 0 | 0 | 0 | 0 | 749.1744 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 633 | 1 | 22 Nov 2023 | PARTH ENTERPRISES | Steel Cutting Yard | MS Pipe Removing | Kgs | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 27 Nov 2023 |  | S OH Infrastructure | Cancelled | DUSHANT.GORE | 19 Dec 2023
GANGA ASMI | 633 | 0 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Store, Steel Yard Fabrication | MS Pipe Fixing (L) | Kgs | 186.7 | 12 | 2240.4 | 0 | 2240.4 | 2.5 | 0 | 0 | 0 | 0 | 186.7 | 0 |  | 0 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 27 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 633 | 1 | 22 Nov 2023 | PARTH ENTERPRISES | Steel Cutting Yard | MS Pipe Removing | Kgs | 746.35 | 6 | 4478.1 | 0 | 4478.1 | 0 | 746.35 | 4478.1 | 0 | 4478.1 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 27 Nov 2023 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 3 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Office,Store,Safety Office Room removing | M.S. Door removing | No. | 5 | 300 | 1500 | 0 | 1500 | 0 | 5 | 1500 | 0 | 1500 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 633 | 3 | 22 Nov 2023 | PARTH ENTERPRISES | Temporary Structure Office,Store,Safety Office Room removing | MS Square Pipe (L) | Kgs | 465.9 | 6 | 2795.4 | 0 | 2795.4 | 0 | 465.9 | 2795.4 | 0 | 2795.4 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 27 Nov 2023 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 634 | 0 | 25 Nov 2023 | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | Weigh Bridge AMC Charges & Stamping Charges - 1 Job | Miscellaneous Expenses | No. | 1 | 2000 | 2000 | 0 | 2000 | 0 | 1 | 2000 | 0 | 2000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 28 Nov 2023 |  | 14 MISC WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 635 | 0 | 28 Nov 2023 | A.S.INFOTECH SOLUTION | H.O. IT Expences | Laptop Repair | No. | 1 | 50000 | 50000 | 9000 | 59000 | 0 | 0.462 | 23100 | 4158 | 27258 | 0.538 | 31742 |  | 46.2 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 636 | 0 | 29 Nov 2023 | S.R.Enterprises | UGWT Antitermite Treatment | Antitermite Treatment - BC] | Sq.Ft | 13193.973 | 4 | 52775.89 | 9499.66 | 62275.55 | 0 | 7559.48 | 30237.92 | 5442.82 | 35680.74 | 5634.493 | 26594.81 |  | 57.2949 |  | DUSHANT.GORE | Swapnil Erande | construction open | 04 Dec 2023 |  | B.C. RCC Substructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | Scaffolding & Removing | Sq.Ft | 10789.03 | 0.5 | 5394.52 | 971.02 | 6365.54 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | Scaffolding & Removing | Sq.Ft | 10789.03 | 0.5 | 5394.52 | 971.02 | 6365.54 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (5th Slab) Ceiling(OBD) Painting | Primer Water Base- Ceiling | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (1st Slab) Ceiling(OBD) Painting | 2nd Coat OBD (L) | Sq.Ft | 8435.54 | 1.25 | 10544.43 | 1898 | 12442.43 | 2.5 | 0 | 0 | 0 | 0 | 8435.54 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (1st Slab) Ceiling(OBD) Painting | 1st Coat Ceiling Putty | Sq.Ft | 8435.54 | 1 | 8435.54 | 1518.4 | 9953.94 | 2.5 | 0 | 0 | 0 | 0 | 8435.54 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (5th Slab) Ceiling(OBD) Painting | Joint Filling with Putty | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (1st Slab) Ceiling(OBD) Painting | Primer Water Base- Ceiling | Sq.Ft | 8435.54 | 1 | 8435.54 | 1518.4 | 9953.94 | 2.5 | 0 | 0 | 0 | 0 | 8435.54 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (L) | Sq.Ft | 10789.03 | 1.5 | 16183.55 | 2913.04 | 19096.59 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (6th Slab) Ceiling(OBD) Painting | Primer Water Base- Ceiling | Sq.Ft | 8740.93 | 1 | 8740.93 | 1573.36 | 10314.29 | 2.5 | 0 | 0 | 0 | 0 | 8740.93 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (L) | Sq.Ft | 10789.03 | 1.75 | 18880.8 | 3398.54 | 22279.34 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | Scaffolding & Removing | Sq.Ft | 10789.03 | 0.5 | 5394.52 | 971.02 | 6365.54 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (5th Slab) Ceiling(OBD) Painting | 2nd Coat OBD (L) | Sq.Ft | 9383.38 | 1.25 | 11729.23 | 2111.26 | 13840.49 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (L) | Sq.Ft | 10789.03 | 1 | 10789.03 | 1942.02 | 12731.05 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (3rd Slab) Ceiling(OBD) Painting | Primer Water Base- Ceiling | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (4th Slab) Ceiling(OBD) Painting | Joint Filling with Putty | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (3rd Slab) Ceiling(OBD) Painting | 2nd Coat OBD (L) | Sq.Ft | 9383.38 | 1.25 | 11729.23 | 2111.26 | 13840.49 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (L) | Sq.Ft | 14264.64 | 1 | 14264.64 | 2567.64 | 16832.28 | 2.5 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (L) | Sq.Ft | 14264.64 | 1.5 | 21396.96 | 3851.46 | 25248.42 | 2.5 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (3rd Slab) Ceiling(OBD) Painting | 1st Coat Ceiling Putty | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (L) | Sq.Ft | 10789.03 | 1.75 | 18880.8 | 3398.54 | 22279.34 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (6th Slab) Ceiling(OBD) Painting | Joint Filling with Putty | Sq.Ft | 8740.93 | 1 | 8740.93 | 1573.36 | 10314.29 | 2.5 | 0 | 0 | 0 | 0 | 8740.93 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (L) | Sq.Ft | 10789.03 | 1.5 | 16183.55 | 2913.04 | 19096.59 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (2nd Slab) Ceiling(OBD) Painting | 1st Coat Ceiling Putty | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | Scaffolding & Removing | Sq.Ft | 14264.64 | 0.5 | 7132.32 | 1283.82 | 8416.14 | 2.5 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (L) | Sq.Ft | 10789.03 | 1 | 10789.03 | 1942.02 | 12731.05 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (6th Slab) Ceiling(OBD) Painting | 1st Coat OBD (L) | Sq.Ft | 8740.93 | 1 | 8740.93 | 1573.36 | 10314.29 | 2.5 | 0 | 0 | 0 | 0 | 8740.93 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (4th Slab) Ceiling(OBD) Painting | 1st Coat Ceiling Putty | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | Scaffolding & Removing | Sq.Ft | 10789.03 | 0.5 | 5394.52 | 971.02 | 6365.54 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (5th Slab) Ceiling(OBD) Painting | 1st Coat OBD (L) | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (2nd Slab) Ceiling(OBD) Painting | 1st Coat OBD (L) | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | Scaffolding & Removing | Sq.Ft | 10590.8 | 0.5 | 5295.4 | 953.18 | 6248.58 | 2.5 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | Texture Paint (L) | Sq.Ft | 10789.03 | 7.5 | 80917.73 | 14565.2 | 95482.93 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (3rd Slab) Ceiling(OBD) Painting | 1st Coat OBD (L) | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (1st Slab) Ceiling(OBD) Painting | 1st Coat OBD (L) | Sq.Ft | 8435.54 | 1 | 8435.54 | 1518.4 | 9953.94 | 2.5 | 0 | 0 | 0 | 0 | 8435.54 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (4th Slab) Ceiling(OBD) Painting | 1st Coat OBD (L) | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (2nd Slab) Ceiling(OBD) Painting | Primer Water Base- Ceiling | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (3rd Slab) Ceiling(OBD) Painting | Joint Filling with Putty | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 4500 | 4500 | 810 | 5310 | 4883.38 | 5762.38 |  | 47.9571 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | 1 Coat Primer (Water Base) (L) | Sq.Ft | 10590.8 | 1 | 10590.8 | 1906.34 | 12497.14 | 2.5 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | Final Cleaning & Housekeeping work (L) | Sq.Ft | 10789.03 | 0.5 | 5394.52 | 971.02 | 6365.54 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | Final Cleaning & Housekeeping work (L) | Sq.Ft | 10789.03 | 0.5 | 5394.52 | 971.02 | 6365.54 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (2nd Slab) Ceiling(OBD) Painting | Joint Filling with Putty | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 4500 | 4500 | 810 | 5310 | 4883.38 | 5762.38 |  | 47.9571 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | Final Cleaning & Housekeeping work (L) | Sq.Ft | 14264.64 | 0.5 | 7132.32 | 1283.82 | 8416.14 | 2.5 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (4th Slab) Ceiling(OBD) Painting | Primer Water Base- Ceiling | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | Texture Paint (L) | Sq.Ft | 10789.03 | 7.5 | 80917.73 | 14565.2 | 95482.93 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | Final Cleaning & Housekeeping work (L) | Sq.Ft | 10590.8 | 0.5 | 5295.4 | 953.18 | 6248.58 | 2.5 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | Final Cleaning & Housekeeping work (L) | Sq.Ft | 10789.03 | 0.5 | 5394.52 | 971.02 | 6365.54 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | Final Cleaning & Housekeeping work (L) | Sq.Ft | 10789.03 | 0.5 | 5394.52 | 971.02 | 6365.54 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | 1st Coat Acrylic Paint (L) | Sq.Ft | 10590.8 | 1.5 | 15886.2 | 2859.52 | 18745.72 | 2.5 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (1st Slab) Ceiling(OBD) Painting | Joint Filling with Putty | Sq.Ft | 8435.54 | 1 | 8435.54 | 1518.4 | 9953.94 | 2.5 | 0 | 0 | 0 | 0 | 8435.54 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (5th Slab) Ceiling(OBD) Painting | 1st Coat Ceiling Putty | Sq.Ft | 9383.38 | 1 | 9383.38 | 1689 | 11072.38 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (4th Slab) Ceiling(OBD) Painting | 2nd Coat OBD (L) | Sq.Ft | 9383.38 | 1.25 | 11729.23 | 2111.26 | 13840.49 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (2nd Slab) Ceiling(OBD) Painting | 2nd Coat OBD (L) | Sq.Ft | 9383.38 | 1.25 | 11729.23 | 2111.26 | 13840.49 | 2.5 | 0 | 0 | 0 | 0 | 9383.38 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | Texture Paint (L) | Sq.Ft | 10590.8 | 7.5 | 79431 | 14297.58 | 93728.58 | 2.5 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (L) | Sq.Ft | 10789.03 | 1 | 10789.03 | 1942.02 | 12731.05 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | Texture Paint (L) | Sq.Ft | 14264.64 | 7.5 | 106984.8 | 19257.26 | 126242.06 | 2.5 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (L) | Sq.Ft | 10789.03 | 1.5 | 16183.55 | 2913.04 | 19096.59 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | Texture Paint (L) | Sq.Ft | 10789.03 | 7.5 | 80917.73 | 14565.2 | 95482.93 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (L) | Sq.Ft | 10789.03 | 1.75 | 18880.8 | 3398.54 | 22279.34 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (6th Slab) Ceiling(OBD) Painting | 2nd Coat OBD (L) | Sq.Ft | 8740.93 | 1.25 | 10926.16 | 1966.7 | 12892.86 | 2.5 | 0 | 0 | 0 | 0 | 8740.93 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (L) | Sq.Ft | 10789.03 | 1 | 10789.03 | 1942.02 | 12731.05 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (L) | Sq.Ft | 10789.03 | 1.5 | 16183.55 | 2913.04 | 19096.59 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (6th Slab) Ceiling(OBD) Painting | 1st Coat Ceiling Putty | Sq.Ft | 8740.93 | 1 | 8740.93 | 1573.36 | 10314.29 | 2.5 | 0 | 0 | 0 | 0 | 8740.93 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (L) | Sq.Ft | 14264.64 | 1.75 | 24963.12 | 4493.36 | 29456.48 | 2.5 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (L) | Sq.Ft | 10789.03 | 1.75 | 18880.8 | 3398.54 | 22279.34 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | 2nd Coat Acrylic Paint (L) | Sq.Ft | 10590.8 | 1.75 | 18533.9 | 3336.1 | 21870 | 2.5 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 637 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | Texture Paint (L) | Sq.Ft | 10789.03 | 7.5 | 80917.73 | 14565.2 | 95482.93 | 2.5 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (M) | Sq.Ft | 10789.03 | 2.5 | 26972.58 | 4855.06 | 31827.64 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | Texture Paint (M) | Sq.Ft | 14264.64 | 8 | 114117.12 | 20541.08 | 134658.2 | 0 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (M) | Sq.Ft | 10789.03 | 2.5 | 26972.58 | 4855.06 | 31827.64 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | 1 Coat Primer (Water Base) (M) | Sq.Ft | 10590.8 | 1 | 10590.8 | 1906.34 | 12497.14 | 0 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (M) | Sq.Ft | 10789.03 | 1 | 10789.03 | 1942.02 | 12731.05 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | Texture Paint (M) | Sq.Ft | 10789.03 | 8 | 86312.24 | 15536.2 | 101848.44 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (M) | Sq.Ft | 10789.03 | 2.25 | 24275.32 | 4369.56 | 28644.88 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | 1st Coat Acrylic Paint (M) | Sq.Ft | 10590.8 | 2.25 | 23829.3 | 4289.28 | 28118.58 | 0 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (M) | Sq.Ft | 14264.64 | 2.5 | 35661.6 | 6419.08 | 42080.68 | 0 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | Texture Paint (M) | Sq.Ft | 10590.8 | 8 | 84726.4 | 15250.76 | 99977.16 | 0 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (M) | Sq.Ft | 10789.03 | 2.25 | 24275.32 | 4369.56 | 28644.88 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (M) | Sq.Ft | 10789.03 | 2.25 | 24275.32 | 4369.56 | 28644.88 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (M) | Sq.Ft | 10789.03 | 2.5 | 26972.58 | 4855.06 | 31827.64 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (M) | Sq.Ft | 14264.64 | 1 | 14264.64 | 2567.64 | 16832.28 | 0 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (M) | Sq.Ft | 10789.03 | 1 | 10789.03 | 1942.02 | 12731.05 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-2 (1st To 2nd Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (M) | Sq.Ft | 10789.03 | 1 | 10789.03 | 1942.02 | 12731.05 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-1 (Plinth To 1st Slab) Column/SW/Beam Texture | 2nd Coat Acrylic Paint (M) | Sq.Ft | 10590.8 | 2.5 | 26477 | 4765.86 | 31242.86 | 0 | 0 | 0 | 0 | 0 | 10590.8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (M) | Sq.Ft | 10789.03 | 2.25 | 24275.32 | 4369.56 | 28644.88 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | 1 Coat Primer (Water Base) (M) | Sq.Ft | 10789.03 | 1 | 10789.03 | 1942.02 | 12731.05 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-6 (5th To 6th Slab) Column/SW/Beam Texture+Pa | 1st Coat Acrylic Paint (M) | Sq.Ft | 14264.64 | 2.25 | 32095.44 | 5777.18 | 37872.62 | 0 | 0 | 0 | 0 | 0 | 14264.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | Texture Paint (M) | Sq.Ft | 10789.03 | 8 | 86312.24 | 15536.2 | 101848.44 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-4 (3rd To 4th Slab) Column/SW/Beam Texture+Pa | Texture Paint (M) | Sq.Ft | 10789.03 | 8 | 86312.24 | 15536.2 | 101848.44 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-3 (2nd To 3rd Slab) Column/SW/Beam Texture+Pa | Texture Paint (M) | Sq.Ft | 10789.03 | 8 | 86312.24 | 15536.2 | 101848.44 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 638 | 0 | 30 Nov 2023 | RAHUL PATIL | Wing-1 Parking-5 (4th To 5th Slab) Column/SW/Beam Texture+Pa | 2nd Coat Acrylic Paint (M) | Sq.Ft | 10789.03 | 2.5 | 26972.58 | 4855.06 | 31827.64 | 0 | 0 | 0 | 0 | 0 | 10789.03 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 02 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 639 | 0 | 30 Nov 2023 | GOOD OLD DELIGHT | ONLINE / DIGITAL Social / Digital Activity | Retainership for Digital Media - | Month | 5 | 40000 | 200000 | 36000 | 236000 | 0 | 5 | 200000 | 36000 | 236000 | 0 | 0 | MONTLY MEDIA ONLINE SOCIAL PLATFORM ACTIVITY, BRANDING, SALES PROMOTIN ETC | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 01 Dec 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 639 | 1 | 30 Nov 2023 | GOOD OLD DELIGHT | ONLINE / DIGITAL Social / Digital Activity | Retainership for Digital Media - | Month | 5 | 40000 | 200000 | 36000 | 236000 | 0 | 5 | 200000 | 36000 | 236000 | 0 | 0 | MONTLY MEDIA ONLINE SOCIAL PLATFORM MARKETING ACTIVITY, BRANDING, SALES PROMOTION ETC. | 100 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 01 Dec 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 640 | 0 | 30 Nov 2023 | VGA DIGITAL PRINTERS PRIVATE LIMITED | PRINTING PRINTING-NO.-(NA) | Flex Printing & Mounting for hoardings | Sq.Ft | 12390 | 10 | 123900 | 22302 | 146202 | 0 | 10531.5 | 105315 | 18956.7 | 124271.7 | 1858.5 | 21930.3 | GANGA ASMI FLEX PRINTING & MOUNTING FOR HOARDING | 85 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 07 Dec 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4821.3735 | 175 | 843740.36 | 151873.26 | 995613.62 | 2.5 | 0 | 0 | 0 | 0 | 4821.3735 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 190 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA-Substructure RCC Labour Parking PCC Work | PCC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4821.3735 | 209.87 | 1011837.55 | 182130.76 | 1193968.31 | 2.5 | 0 | 0 | 0 | 0 | 4821.3735 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 3818.9145 | 155 | 591931.75 | 106547.72 | 698479.47 | 2.5 | 0 | 0 | 0 | 0 | 3818.9145 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA-Substructure RCC Labour Parking Footing & Column | Footing & Column | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | Schedule- BC | Sq.Ft | 9642.747 | 5 | 48213.74 | 8678.48 | 56892.22 | 2.5 | 0 | 0 | 0 | 0 | 9642.747 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4821.3735 | 209.87 | 1011837.55 | 182130.76 | 1193968.31 | 2.5 | 0 | 0 | 0 | 0 | 4821.3735 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | Schedule- BC | Sq.Ft | 9642.747 | 5 | 48213.74 | 8678.48 | 56892.22 | 2.5 | 0 | 0 | 0 | 0 | 9642.747 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4821.3735 | 185 | 891954.1 | 160551.74 | 1052505.84 | 2.5 | 0 | 0 | 0 | 0 | 4821.3735 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4821.3735 | 175 | 843740.36 | 151873.26 | 995613.62 | 2.5 | 0 | 0 | 0 | 0 | 4821.3735 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 204 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | Quality (BC) | Sq.Ft | 7637.829 | 5 | 38189.15 | 6874.04 | 45063.19 | 2.5 | 0 | 0 | 0 | 0 | 7637.829 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 190 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | Quality (BC) | Sq.Ft | 9642.747 | 5 | 48213.74 | 8678.48 | 56892.22 | 2.5 | 0 | 0 | 0 | 0 | 9642.747 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 204 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4757.106 | 165 | 784922.49 | 141286.04 | 926208.53 | 2.5 | 0 | 0 | 0 | 0 | 4757.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 265 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | Quality (BC) | Sq.Ft | 9642.747 | 5 | 48213.74 | 8678.48 | 56892.22 | 2.5 | 0 | 0 | 0 | 0 | 9642.747 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | Schedule- BC | Sq.Ft | 9642.747 | 5 | 48213.74 | 8678.48 | 56892.22 | 2.5 | 0 | 0 | 0 | 0 | 9642.747 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA Substructure (L) RCC Lab Parking,soling,PB,PCC,Ftng,Colu | RCC Work - Mkt | Sq.Ft | 7637.829 | 60 | 458269.74 | 82488.56 | 540758.3 | 2.5 | 7637.829 | 458269.74 | 82488.56 | 540758.3 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | Quality (BC) | Sq.Ft | 9514.212 | 5 | 47571.06 | 8562.8 | 56133.86 | 2.5 | 0 | 0 | 0 | 0 | 9514.212 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4757.106 | 165 | 784922.49 | 141286.04 | 926208.53 | 2.5 | 0 | 0 | 0 | 0 | 4757.106 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | Schedule- BC | Sq.Ft | 7637.829 | 5 | 38189.15 | 6874.04 | 45063.19 | 2.5 | 0 | 0 | 0 | 0 | 7637.829 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 180 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4821.3735 | 185 | 891954.1 | 160551.74 | 1052505.84 | 2.5 | 0 | 0 | 0 | 0 | 4821.3735 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | RCC Rate diff for RCC Slab | Sq.Ft | 1920.41 | 100 | 192041 | 34567.38 | 226608.38 | 2.5 | 0 | 0 | 0 | 0 | 1920.41 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | Quality (BC) | Sq.Ft | 9642.747 | 5 | 48213.74 | 8678.48 | 56892.22 | 2.5 | 0 | 0 | 0 | 0 | 9642.747 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 165 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4821.3735 | 195 | 940167.83 | 169230.2 | 1109398.03 | 2.5 | 0 | 0 | 0 | 0 | 4821.3735 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | Schedule- BC | Sq.Ft | 9514.212 | 5 | 47571.06 | 8562.8 | 56133.86 | 2.5 | 0 | 0 | 0 | 0 | 9514.212 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 4821.3735 | 195 | 940167.83 | 169230.2 | 1109398.03 | 2.5 | 0 | 0 | 0 | 0 | 4821.3735 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 155 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 0 | 265 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 3818.9145 | 155 | 591931.75 | 106547.72 | 698479.47 | 2.5 | 0 | 0 | 0 | 0 | 3818.9145 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA-Substructure RCC Labour Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 0 | 35.82 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | Quality (BC) | Sq.Ft | 9642.747 | 5 | 48213.74 | 8678.48 | 56892.22 | 2.5 | 0 | 0 | 0 | 0 | 9642.747 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA-Substructure RCC Labour Parking Dressing, Leveling & Cle | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 01 EARTHWORK & ROADWORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA-Substructure RCC Labour Parking Plinth Beam | RCC Beam | Sq.Ft | 0 | 60 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | Quality (BC) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | 02 RCC WORK | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | Schedule- BC | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Cancelled | DUSHANT.GORE | 30 Jan 2024
GANGA ASMI | 641 | 0 | 30 Nov 2023 | SAIRAJ CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | Schedule- BC | Sq.Ft | 9642.747 | 5 | 48213.74 | 8678.48 | 56892.22 | 2.5 | 0 | 0 | 0 | 0 | 9642.747 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 30 Jan 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | Quality (BC) | Sq.Ft | 11212.19 | 5 | 56060.95 | 10090.98 | 66151.93 | 2.5 | 0 | 0 | 0 | 0 | 11212.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5606.093 | 155 | 868944.42 | 156410 | 1025354.42 | 2.5 | 0 | 0 | 0 | 0 | 5606.093 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | Schedule- BC | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | Schedule- BC | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | Schedule- BC | Sq.Ft | 11212.19 | 5 | 56060.95 | 10090.98 | 66151.93 | 2.5 | 0 | 0 | 0 | 0 | 11212.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | Quality (BC) | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | Quality (BC) | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | Schedule- BC | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA-Substructure RCC Labour Parking Dressing, Leveling & Cle | Dressing, Levelling & Cleaning (Sq.ft) | Sq.Ft | 11212.19 | 6 | 67273.14 | 12109.16 | 79382.3 | 2.5 | 0 | 0 | 0 | 0 | 11212.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 01 EARTHWORK & ROADWORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -1st Slab (Parking-2) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5606.093 | 155 | 868944.42 | 156410 | 1025354.42 | 2.5 | 0 | 0 | 0 | 0 | 5606.093 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA-Substructure RCC Labour Parking Soling & PCC Work | Soling & PCC | Sq.Ft | 11212.19 | 27.6 | 309456.44 | 55702.16 | 365158.6 | 2.5 | 0 | 0 | 0 | 0 | 11212.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | Schedule- BC | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 185 | 1029081.37 | 185234.64 | 1214316.01 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | Quality (BC) | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | Schedule- BC | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | B.C. BBM, Plaster, POP | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 207 | 1151458.61 | 207262.54 | 1358721.15 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 185 | 1029081.37 | 185234.64 | 1214316.01 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | Quality (BC) | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 220 | 1223772.44 | 220279.04 | 1444051.48 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA-Substructure RCC Labour Parking Footing & Column | Footing & Column | Sq.Ft | 11212.19 | 45 | 504548.55 | 90818.74 | 595367.29 | 2.5 | 0 | 0 | 0 | 0 | 11212.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 175 | 973455.35 | 175221.96 | 1148677.31 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 165 | 917829.33 | 165209.28 | 1083038.61 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -6th Slab (Podium) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 220 | 1223772.44 | 220279.04 | 1444051.48 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA-Substructure RCC Labour Parking Plinth Beam | RCC Beam | Sq.Ft | 11212.19 | 45 | 504548.55 | 90818.74 | 595367.29 | 2.5 | 0 | 0 | 0 | 0 | 11212.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -2nd Slab (Parking-3) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 165 | 917829.33 | 165209.28 | 1083038.61 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -5th Slab (Parking-6) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 207 | 1151458.61 | 207262.54 | 1358721.15 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -3rd Slab (Parking-4) RCC (L) | RCC Superstructure (B-up area) | Sq.Ft | 5562.602 | 175 | 973455.35 | 175221.96 | 1148677.31 | 2.5 | 0 | 0 | 0 | 0 | 5562.602 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA -4th Slab (Parking-5) RCC (L) | Quality (BC) | Sq.Ft | 11125.2 | 5 | 55626 | 10012.68 | 65638.68 | 2.5 | 0 | 0 | 0 | 0 | 11125.2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 642 | 0 | 30 Nov 2023 | PURVA CONSTRUCTION | NTA-Substructure RCC Labour Parking PCC Work | PCC | Sq.Ft | 11212.19 | 5 | 56060.95 | 10090.98 | 66151.93 | 2.5 | 0 | 0 | 0 | 0 | 11212.19 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Feb 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 643 | 0 | 06 Dec 2023 | KLAUS WORLD EQUIPMENT | Tower Crane Jumping | Tower Crane Jumping Charges | No. | 7 | 35000 | 245000 | 44100 | 289100 | 0 | 1 | 35000 | 6300 | 41300 | 6 | 247800 | After every 5 floor | 14.2857 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | S OH Conveyance & Transport | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 644 | 0 | 07 Dec 2023 | TAJ SERVICES | Stationary | Card Print | No. | 125 | 75 | 9375 | 0 | 9375 | 0 | 0 | 0 | 0 | 0 | 125 | 0 | IDENTY CARD+ LANYARD | 0 |  | SWAPNIL JADHAV |  | construction open | 07 Dec 2023 |  | MKT. Media | Un-Approved |  | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 33.91 | 16 | 542.56 | 0 | 542.56 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 503 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 509 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 416 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 511 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 305 (1RK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 33.91 | 16 | 542.56 | 0 | 542.56 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Bore Packing | 5" Bore Packing | No. | 2 | 200 | 400 | 0 | 400 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 312 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 404 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 54 | 354 | 100 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 408 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 312 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 409 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 407 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 313 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 309 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 204 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 116 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 515 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 1 | 1100 | 1100 | 0 | 1100 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 516 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 502 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 316 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 503 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 114 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 503 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 315 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 419.55 | 2 | 839.1 | 151.04 | 990.14 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 516 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 33.91 | 20 | 678.2 | 0 | 678.2 | 5 | 33.91 | 678.2 | 122.08 | 800.28 | 0 | -122.08 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 31.65 | 20 | 633 | 0 | 633 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 512 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 415 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 34.88 | 22 | 767.36 | 0 | 767.36 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 113 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 280.64 | 2.5 | 701.6 | 126.28 | 827.88 | 2.5 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 216 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 390.13 | 2.5 | 975.33 | 175.56 | 1150.89 | 2.5 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 111 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 213 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 191.8 | 1257.38 | 2.5 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 510 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 511 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 414 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 515 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 408 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 216 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 410 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 415 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 413 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 210 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 209 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 406 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 214 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 31.65 | 16 | 506.4 | 0 | 506.4 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 108 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 414 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 411 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 509 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 215 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 33.91 | 16 | 542.56 | 0 | 542.56 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 374.57 | 2 | 749.14 | 134.84 | 883.98 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 33.91 | 746.02 | 134.28 | 880.3 | 0 | -134.28 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 208 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 215 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 312 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 407 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 203 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 9 | 100 | 900 | 0 | 900 | 5 | 4 | 400 | 72 | 472 | 5 | 428 |  | 44.4444 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 390.13 | 2 | 780.26 | 140.44 | 920.7 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 116 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 207 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 214 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 203 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 2 | 400 | 72 | 472 | 3 | 528 |  | 40 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 513 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 410 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 40.37 | 22 | 888.14 | 0 | 888.14 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 308 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 308 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 216 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 311 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 208 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 374.57 | 2.5 | 936.43 | 168.56 | 1104.99 | 2.5 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 390.13 | 2.5 | 975.33 | 175.56 | 1150.89 | 2.5 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 416 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 316 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 108 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 33.91 | 20 | 678.2 | 0 | 678.2 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 312 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 209 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 206 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 202 (1BHK) Bore Packing | 5" Bore Packing | No. | 4 | 200 | 800 | 0 | 800 | 5 | 2 | 400 | 72 | 472 | 2 | 328 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 512 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 516 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 315 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 213 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 216 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 403 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 515 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 416 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 212 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 413 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 508 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 374.57 | 2 | 749.14 | 134.84 | 883.98 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 415 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 188.8 | 1237.68 | 2.5 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 415 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 207 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 115 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 205 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 0 | 300 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 110 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 112 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 111 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 107 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 215 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 38.75 | 852.5 | 153.46 | 1005.96 | 0 | -153.46 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 515 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 212 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 407 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 206 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 34.88 | 22 | 767.36 | 0 | 767.36 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 406 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) Toilet IPS W/P | IPS W/P | Sq.Ft | 33.91 | 16 | 542.56 | 0 | 542.56 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 401 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 374.57 | 2 | 749.14 | 134.84 | 883.98 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 110 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 211 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 34.88 | 22 | 767.36 | 0 | 767.36 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 310 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 514 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 415 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 415 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 511 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 516 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 409 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 311 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 374.57 | 2.5 | 936.43 | 168.56 | 1104.99 | 2.5 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 411 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 411 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 115 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 511 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 34.88 | 20 | 697.6 | 0 | 697.6 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 416 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 107 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 407 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 30.27 | 22 | 665.94 | 0 | 665.94 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 314 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 0 | 16 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 306 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 508 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 416 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 191.8 | 1257.38 | 2.5 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 209 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 115 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 211 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 390.13 | 2.5 | 975.33 | 175.56 | 1150.89 | 2.5 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 412 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 407 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 516 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 508 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 34.88 | 20 | 697.6 | 0 | 697.6 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 215 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 408 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 415 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 505 (1RK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 303 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 113 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 38.75 | 16 | 620 | 0 | 620 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 202 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 205 (1RK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 516 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 280.64 | 2 | 561.28 | 101.04 | 662.32 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 30.27 | 20 | 605.4 | 0 | 605.4 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 30.27 | 22 | 665.94 | 0 | 665.94 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 108 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 203 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 302 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 280.64 | 2.5 | 701.6 | 126.28 | 827.88 | 2.5 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 304 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 507 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 205 (1RK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 301 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 502 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 30.27 | 20 | 605.4 | 0 | 605.4 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 302 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 513 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 215 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 31.65 | 20 | 633 | 0 | 633 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 191.8 | 1257.38 | 2.5 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 503 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 508 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 507 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 33.91 | 20 | 678.2 | 0 | 678.2 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Bore Packing | 2" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 507 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 188.8 | 1237.68 | 2.5 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 107 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 414 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 211 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 408 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 311 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 215 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 33.91 | 20 | 678.2 | 0 | 678.2 | 5 | 33.91 | 678.2 | 122.08 | 800.28 | 0 | -122.08 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 188.8 | 1237.68 | 2.5 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 374.57 | 2.5 | 936.43 | 168.56 | 1104.99 | 2.5 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 34.88 | 20 | 697.6 | 0 | 697.6 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 0 | 300 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 510 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 505 (1RK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 204 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 1 | 200 | 36 | 236 | 2 | 364 |  | 33.3333 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 33.91 | 746.02 | 134.28 | 880.3 | 0 | -134.28 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 1 | 1100 | 1100 | 0 | 1100 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 403 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 4 | 100 | 400 | 72 | 472 | 100 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 416 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 203 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 280.64 | 2.5 | 701.6 | 126.28 | 827.88 | 2.5 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 280.64 | 2.5 | 701.6 | 126.28 | 827.88 | 2.5 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 33.91 | 20 | 678.2 | 0 | 678.2 | 5 | 33.91 | 678.2 | 122.08 | 800.28 | 0 | -122.08 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 504 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 401 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 304 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 501 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 310 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 110 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 501 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 310 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 410 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 205 (1RK) Bore Packing | 5" Bore Packing | No. | 2 | 200 | 400 | 0 | 400 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 112 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 404 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 201 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 210 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 506 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 112 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 511 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 507 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 315 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 213 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 305 (1RK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 426.23 | 2 | 852.46 | 153.44 | 1005.9 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 40.37 | 20 | 807.4 | 0 | 807.4 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 408 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 514 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 409 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 411 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 390.13 | 2 | 780.26 | 140.44 | 920.7 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 506 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 374.57 | 2 | 749.14 | 134.84 | 883.98 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 511 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 419.55 | 2 | 839.1 | 151.04 | 990.14 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 410 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 316 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 390.13 | 2 | 780.26 | 140.44 | 920.7 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 314 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 426.23 | 2 | 852.46 | 153.44 | 1005.9 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 304 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 54 | 354 | 100 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 303 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 4 | 100 | 400 | 72 | 472 | 100 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 419.55 | 2 | 839.1 | 151.04 | 990.14 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 409 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 116 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 502 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 419.55 | 2 | 839.1 | 151.04 | 990.14 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 280.64 | 2.5 | 701.6 | 126.28 | 827.88 | 2.5 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 301 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 30.27 | 22 | 665.94 | 0 | 665.94 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 203 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 4 | 100 | 400 | 72 | 472 | 100 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 501 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 114 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 113 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 38.75 | 852.5 | 153.46 | 1005.96 | 0 | -153.46 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 313 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 302 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 54 | 354 | 100 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 374.57 | 2.5 | 936.43 | 168.56 | 1104.99 | 2.5 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 307 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 212 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 508 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 301 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 505 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 0 | 300 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 502 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 30.27 | 22 | 665.94 | 0 | 665.94 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 405 (1RK) Bore Packing | 5" Bore Packing | No. | 2 | 200 | 400 | 0 | 400 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 504 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 116 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 40.37 | 22 | 888.14 | 0 | 888.14 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 404 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 210 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 505 (1RK) Bore Packing | 2" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 407 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 405 (1RK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 310 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 204 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 54 | 354 | 100 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 204 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 514 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 38.75 | 852.5 | 153.46 | 1005.96 | 0 | -153.46 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 316 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 313 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 216 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) Toilet IPS W/P | IPS W/P | Sq.Ft | 33.91 | 16 | 542.56 | 0 | 542.56 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 108 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 115 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 207 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 306 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 510 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 303 (1BHK) Bore Packing | 4" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 216 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 302 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 1 | 200 | 36 | 236 | 2 | 364 |  | 33.3333 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 40.37 | 22 | 888.14 | 0 | 888.14 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 413 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 111 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 404 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 1 | 200 | 36 | 236 | 2 | 364 |  | 33.3333 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Toilet IPS W/P | IPS W/P | Sq.Ft | 33.91 | 16 | 542.56 | 0 | 542.56 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 301 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 505 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 214 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 108 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 211 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 31.65 | 20 | 633 | 0 | 633 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 510 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 310 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 308 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0.5 | 600 | 108 | 708 | 0.5 | 492 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 403 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 9 | 100 | 900 | 0 | 900 | 5 | 4 | 400 | 72 | 472 | 5 | 428 |  | 44.4444 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 110 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 309 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 426.23 | 2 | 852.46 | 153.44 | 1005.9 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 374.57 | 2 | 749.14 | 134.84 | 883.98 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 280.64 | 2 | 561.28 | 101.04 | 662.32 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 280.64 | 2 | 561.28 | 101.04 | 662.32 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 411 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 215 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 307 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 304 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 3 | 300 | 54 | 354 | 5 | 446 |  | 37.5 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 513 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 108 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 512 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 113 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 34.88 | 20 | 697.6 | 0 | 697.6 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 208 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 308 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 115 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 315 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 402 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 7 | 100 | 700 | 0 | 700 | 5 | 3 | 300 | 54 | 354 | 4 | 346 |  | 42.8571 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 316 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 305 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 214 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 308 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 33.91 | 20 | 678.2 | 0 | 678.2 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 409 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 408 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 412 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 203 (1BHK) Bore Packing | 4" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 511 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 502 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 7 | 100 | 700 | 0 | 700 | 5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 406 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 208 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 412 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 216 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 303 (1BHK) Bore Packing | 4" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 504 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 407 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 515 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 38.75 | 775 | 139.5 | 914.5 | 0 | -139.5 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 107 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Bore Packing | 4" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 210 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 313 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 314 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 108 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 212 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 115 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 509 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 311 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 111 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 515 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 111 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 513 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 314 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 211 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 107 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 112 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 307 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 209 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 406 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 191.8 | 1257.38 | 2.5 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 306 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 512 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 207 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 114 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 30.27 | 20 | 605.4 | 0 | 605.4 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 514 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 1 | 1100 | 1100 | 0 | 1100 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 114 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 314 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 302 (1BHK) Bore Packing | 5" Bore Packing | No. | 4 | 200 | 800 | 0 | 800 | 5 | 2 | 400 | 72 | 472 | 2 | 328 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 306 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 308 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 40.37 | 20 | 807.4 | 0 | 807.4 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 413 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 315 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 211 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 311 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 390.13 | 2 | 780.26 | 140.44 | 920.7 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 413 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 402 (1BHK) Bore Packing | 5" Bore Packing | No. | 4 | 200 | 800 | 0 | 800 | 5 | 2 | 400 | 72 | 472 | 2 | 328 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 207 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 508 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 40.37 | 22 | 888.14 | 0 | 888.14 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 107 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 213 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 390.13 | 2.5 | 975.33 | 175.56 | 1150.89 | 2.5 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 111 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 513 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 111 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 33.91 | 746.02 | 134.28 | 880.3 | 0 | -134.28 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 280.64 | 2 | 561.28 | 101.04 | 662.32 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 41.37 | 22 | 910.14 | 0 | 910.14 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 206 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 40.37 | 22 | 888.14 | 0 | 888.14 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 309 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 188.8 | 1237.68 | 2.5 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 112 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 307 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 107 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 116 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 207 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0.5 | 600 | 108 | 708 | 0.5 | 492 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 508 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 40.37 | 20 | 807.4 | 0 | 807.4 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 402 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 501 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 307 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 514 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 115 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 208 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 7 | 100 | 700 | 0 | 700 | 5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 31.65 | 20 | 633 | 0 | 633 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 34.88 | 22 | 767.36 | 0 | 767.36 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 207 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 201 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 302 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 7 | 100 | 700 | 0 | 700 | 5 | 3 | 300 | 54 | 354 | 4 | 346 |  | 42.8571 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 303 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 9 | 100 | 900 | 0 | 900 | 5 | 4 | 400 | 72 | 472 | 5 | 428 |  | 44.4444 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 34.88 | 22 | 767.36 | 0 | 767.36 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 412 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 504 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 414 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 33.91 | 746.02 | 134.28 | 880.3 | 0 | -134.28 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 510 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 411 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 303 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 2 | 400 | 72 | 472 | 1 | 128 |  | 66.6667 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 31.65 | 22 | 696.3 | 0 | 696.3 | 5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 503 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 316 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 38.75 | 22 | 852.5 | 0 | 852.5 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 313 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) Toilet IPS W/P | IPS W/P | Sq.Ft | 33.91 | 16 | 542.56 | 0 | 542.56 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 416 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 212 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 316 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 412 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 303 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 402 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 307 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 405 (1RK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 202 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0.5 | 600 | 108 | 708 | 0.5 | 492 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 301 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 506 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 191.8 | 1257.38 | 2.5 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 113 (1RK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0.5 | 600 | 108 | 708 | 0.5 | 492 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 208 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 33.91 | 20 | 678.2 | 0 | 678.2 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 390.13 | 2.5 | 975.33 | 175.56 | 1150.89 | 2.5 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 408 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 308 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 309 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 211 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 201 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 507 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 402 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 54 | 354 | 100 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 188.8 | 1237.68 | 2.5 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 205 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 405 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 206 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 515 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 405 (1RK) Bore Packing | 2" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 210 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 201 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 201 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 30.27 | 22 | 665.94 | 0 | 665.94 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 204 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 2 | 400 | 72 | 472 | 3 | 528 |  | 40 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 404 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 2 | 400 | 72 | 472 | 3 | 528 |  | 40 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 502 (1BHK) Bore Packing | 5" Bore Packing | No. | 4 | 200 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 403 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 2 | 400 | 72 | 472 | 1 | 128 |  | 66.6667 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 304 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 1 | 200 | 36 | 236 | 2 | 364 |  | 33.3333 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 214 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 33.91 | 20 | 678.2 | 0 | 678.2 | 5 | 33.91 | 678.2 | 122.08 | 800.28 | 0 | -122.08 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 509 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 208 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 307 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 312 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 426.23 | 2 | 852.46 | 153.44 | 1005.9 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 306 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 403 (1BHK) Bore Packing | 4" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 203 (1BHK) Bore Packing | 4" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 203 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 2 | 400 | 72 | 472 | 1 | 128 |  | 66.6667 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 38.75 | 775 | 139.5 | 914.5 | 0 | -139.5 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 507 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Bore Packing | 4" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 403 (1BHK) Bore Packing | 4" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 204 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 3 | 300 | 54 | 354 | 5 | 446 |  | 37.5 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 405 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 0 | 300 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 401 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 305 (1RK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 0 | 300 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 401 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 202 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 1 | 200 | 36 | 236 | 2 | 364 |  | 33.3333 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 506 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 1 | 1100 | 1100 | 0 | 1100 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 304 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 2 | 400 | 72 | 472 | 3 | 528 |  | 40 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 213 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 309 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 34.88 | 20 | 697.6 | 0 | 697.6 | 5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 38.75 | 775 | 139.5 | 914.5 | 0 | -139.5 |  | 100 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 40.37 | 20 | 807.4 | 0 | 807.4 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 205 (1RK) Bore Packing | 2" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 402 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 1 | 200 | 36 | 236 | 2 | 364 |  | 33.3333 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 311 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0.5 | 600 | 108 | 708 | 0.5 | 492 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 410 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 38.75 | 20 | 775 | 0 | 775 | 5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 406 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 202 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 7 | 100 | 700 | 0 | 700 | 5 | 3 | 300 | 54 | 354 | 4 | 346 |  | 42.8571 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 426.23 | 2 | 852.46 | 153.44 | 1005.9 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 414 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 401 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 501 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 303 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 2 | 400 | 72 | 472 | 3 | 528 |  | 40 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 403 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 2 | 400 | 72 | 472 | 3 | 528 |  | 40 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 305 (1RK) Bore Packing | 5" Bore Packing | No. | 2 | 200 | 400 | 0 | 400 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 404 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 3 | 300 | 54 | 354 | 5 | 446 |  | 37.5 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 501 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 8 | 100 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0.5 | 600 | 108 | 708 | 0.5 | 492 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 374.57 | 2.5 | 936.43 | 168.56 | 1104.99 | 2.5 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 110 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 411 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 506 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 403 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 504 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 209 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 206 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 1 | 1100 | 1100 | 0 | 1100 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 512 (1RK) IPS Seal Pack at Toilet & Balcony Do | IPS Seal Pack | Flat | 0 | 1100 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Utility Brickbatt+Finish Coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 509 (1RK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 201 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 503 (1BHK) Bore Packing | 5" Bore Packing | No. | 5 | 200 | 1000 | 0 | 1000 | 5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Bore Packing | 5" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 505 (1RK) Bore Packing | 5" Bore Packing | No. | 2 | 200 | 400 | 0 | 400 | 5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 280.64 | 2 | 561.28 | 101.04 | 662.32 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 390.13 | 2 | 780.26 | 140.44 | 920.7 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 116 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 315 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Building Common Items | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Int Flat Chemical Grouting Work | Ghadai work- BCP | Sq.Ft | 419.55 | 2 | 839.1 | 151.04 | 990.14 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 507 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 33.91 | 22 | 746.02 | 0 | 746.02 | 5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 202 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 3 | 100 | 300 | 54 | 354 | 100 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 504 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 0 | 100 | 0 | 0 | 0 | 100 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Foreclose | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Bore Packing | Perma Eazee Coat W/P (M+L) | No. | 9 | 100 | 900 | 0 | 900 | 5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Bore Packing | 5" Bore Packing | No. | 4 | 200 | 800 | 0 | 800 | 5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 30.27 | 20 | 605.4 | 0 | 605.4 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 30.27 | 20 | 605.4 | 0 | 605.4 | 5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 315 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 1 | 1200 | 1200 | 0 | 1200 | 5 | 0.5 | 600 | 108 | 708 | 0.5 | 492 |  | 50 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) C. Toilet Brickbatt+Finish coat W/P | Brickbat W/P | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | it admin | 04 May 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Utility Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 301 (1BHK) Bore Packing | 2" Bore Packing | No. | 3 | 200 | 600 | 0 | 600 | 5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 401 (1BHK) Bore Packing | 2" Bore Packing | No. | 0 | 200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA.Flat No 305 (1RK) Bore Packing | 2" Bore Packing | No. | 1 | 200 | 200 | 0 | 200 | 5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 116 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 114 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (L) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 41.37 | 20 | 827.4 | 0 | 827.4 | 5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Balcony Brickbatt+Finish Coat | Brickbat W/P | Sq.Ft | 40.37 | 20 | 807.4 | 0 | 807.4 | 5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | DUSHANT.GORE | DUSHANT.GORE | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 516 (1BHK) IPS Seal Pack at Toilet & Balcony D | IPS Seal Pack | Flat | 0 | 1200 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 311 (1BHK) C. Toilet Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 645 | 0 | 07 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Balcony Chemical Coat W/P | Chemical W/P (L+M) | Sq.Ft | 0 | 22 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Internal Finishing Itmes | Cancelled | DUSHANT.GORE | 29 Apr 2024
GANGA ASMI | 646 | 0 | 08 Dec 2023 | WORLD WEB SOLUTIONS | ONLINE / DIGITAL Social / Digital Activity | Website Maintainence - | Month | 3 | 90000 | 270000 | 48600 | 318600 | 0 | 2.9998 | 269982 | 48596.76 | 318578.76 | 0.0002 | 21.24 |  | 99.9933 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 08 Dec 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 309 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 211 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 318 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 216 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 210 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 412 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 310 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 202 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 0 | 1048.88 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 313 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 417 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 115 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 114 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 418 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 515 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 212 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 416 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 314 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 305 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 280.64 | 2.5 | 701.6 | 0 | 701.6 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 508 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 217 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 407 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 112 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 208 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 206 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 215 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 408 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 509 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 201 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 0 | 1065.58 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 110 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 207 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 304 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 374.57 | 2.5 | 936.43 | 0 | 936.43 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 311 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 218 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 108 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 504 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 374.57 | 2.5 | 936.43 | 0 | 936.43 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 503 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 390.13 | 2.5 | 975.33 | 0 | 975.33 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 505 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 280.64 | 2.5 | 701.6 | 0 | 701.6 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 502 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 0 | 1048.88 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 203 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 390.13 | 2.5 | 975.33 | 0 | 975.33 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 517 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 516 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 301 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 0 | 1065.58 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 118 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 302 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 0 | 1048.88 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 402 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 0 | 1048.88 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 506 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 410 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 411 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 501 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 0 | 1065.58 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 214 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 104 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 374.57 | 2.5 | 936.43 | 0 | 936.43 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 510 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 308 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 307 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 103 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 390.13 | 2.5 | 975.33 | 0 | 975.33 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 205 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 280.64 | 2.5 | 701.6 | 0 | 701.6 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 405 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 280.64 | 2.5 | 701.6 | 0 | 701.6 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 111 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 518 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 303 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 390.13 | 2.5 | 975.33 | 0 | 975.33 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 415 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 409 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 404 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 374.57 | 2.5 | 936.43 | 0 | 936.43 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 102 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 419.55 | 2.5 | 1048.88 | 0 | 1048.88 | 0 | 0 | 0 | 0 | 0 | 419.55 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 401 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 0 | 1065.58 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 105 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 280.64 | 2.5 | 701.6 | 0 | 701.6 | 0 | 0 | 0 | 0 | 0 | 280.64 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 511 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 117 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 406 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 513 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 403 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 390.13 | 2.5 | 975.33 | 0 | 975.33 | 0 | 0 | 0 | 0 | 0 | 390.13 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 414 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 116 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 317 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 512 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 514 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 101 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 426.23 | 2.5 | 1065.58 | 0 | 1065.58 | 0 | 0 | 0 | 0 | 0 | 426.23 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 209 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 316 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 107 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 306 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 312 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 113 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 315 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 204 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 374.57 | 2.5 | 936.43 | 0 | 936.43 | 0 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 413 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 213 (1RK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 647 | 0 | 08 Dec 2023 | DEVI WATERPROOFING | MHADA-Flat No 507 (1BHK) Int Flat Chemical Grouting Work | Chemical Grouting (M) | Sq.Ft | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | 06 WATERPROOFING WORK | Cancelled | DUSHANT.GORE | 08 Dec 2023
GANGA ASMI | 648 | 0 | 08 Dec 2023 | WORLD WEB SOLUTIONS | ONLINE / DIGITAL Social / Digital Activity | Website Maintainence - | Month | 12 | 90000 | 1080000 | 194400 | 1274400 | 0 | 2 | 179999.28 | 32399.88 | 212399.16 | 10 | 1062000.84 | WEBSITE DEVELOPMENT & MAINTENANCE CHARGES | 16.6667 |  | SWAPNIL JADHAV | sunita shirolkar | construction open | 12 Dec 2023 |  | MKT. Media | Approved | sunita shirolkar | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 6th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 18th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 17th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 25th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 5th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 11th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 26th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 7th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 9th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 27th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing Podium Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0.5 | 10000 | 0 | 10000 | 0.5 | 10000 |  | 50 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 3rd Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0.9 | 18000 | 0 | 18000 | 0.1 | 2000 |  | 90 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 23rd Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 13th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 12th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 19th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 28th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 21st Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 8th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 16th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 22nd Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 1st Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0.9 | 18000 | 0 | 18000 | 0.1 | 2000 |  | 90 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 15th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 14th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 24th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 10th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 4th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 2nd Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0.9 | 18000 | 0 | 18000 | 0.1 | 2000 |  | 90 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 649 | 0 | 08 Dec 2023 | PRASNA PLUMBING SERVICE | Wing-1 Aluform Sleeve Fixing 20th Floor | Sleeve Fixing Work | Floor | 1 | 20000 | 20000 | 0 | 20000 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Dec 2023 |  | B.C. RCC Superstructure | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 650 | 0 | 09 Dec 2023 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Temporary Electrical Work DG Shifting & Earthing | Al. Arm. Cable laying 3.5C 150sqmm-UTI | Mtrs | 260 | 71.5 | 18590 | 0 | 18590 | 2.5 | 260 | 18590 | 0 | 18590 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Dec 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 650 | 0 | 09 Dec 2023 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Temporary Electrical Work DG Shifting & Earthing | Electrical Trench Excavation & Backfilling | Mtrs | 10 | 176 | 1760 | 0 | 1760 | 0 | 10 | 1760 | 0 | 1760 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 650 | 3 | 09 Dec 2023 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing.1 Industrial Panel Fixing | Panel Fixing (L) | No. | 17 | 600 | 10200 | 1836 | 12036 | 2.5 | 3 | 1800 | 0 | 1800 | 14 | 10236 |  | 17.6471 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 13 Dec 2023 |  | UTI. Electricity Infrastructur | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 650 | 3 | 09 Dec 2023 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Wing.1 Industrial Panel Fixing | Lumpsum work- DCW | No. | 1 | 2000 | 2000 | 360 | 2360 | 2.5 | 1 | 2000 | 0 | 2000 | 0 | 360 |  | 100 |  | ADITYA.CHOUGULE | DUSHANT.GORE | construction open | 13 Dec 2023 |  | DEV. Compound Wall | Approved | DUSHANT.GORE | 1900-01-01
GANGA ASMI | 650 | 0 | 09 Dec 2023 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Temporary Electrical Work DG Shifting & Earthing | Feeder Pillar fixing-ULT | No. | 1 | 2750 | 2750 | 0 | 2750 | 2.5 | 1 | 2750 | 0 | 2750 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Dec 2023 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 650 | 1 | 09 Dec 2023 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Asmi-CREDAI Audit-Labour Charges | Fitting & Removing | No. | 1 | 3000 | 3000 | 0 | 3000 | 2.5 | 1 | 3000 | 0 | 3000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 650 | 2 | 09 Dec 2023 | LAXMI ELECTRICALS (Prop.Mayur Raskar) | Site Illumination/ Temporary Electrical Work Industrial Pane | 10 Sqmm x 4C Cable (L) | Mtrs | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 13 Dec 2023 |  | 04 ELECTRICAL WORK | Cancelled | ADITYA.CHOUGULE | 03 Jul 2024
GANGA ASMI | 651 | 0 | 09 Dec 2023 | NITIN D PARDESHI | Site Electricity expenses | Electricity Bills | No. | 0 | 350000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | SOC. M. Maintenace Overheads | Cancelled | DUSHANT.GORE | 19 Dec 2023
GANGA ASMI | 651 | 0 | 09 Dec 2023 | NITIN D PARDESHI | Vehicle Fuel, Maintenance & Insurance | Vehical Service & Repair | Month | 12 | 25000 | 300000 | 0 | 300000 | 0 | 0.6552 | 16380 | 0 | 16380 | 11.3448 | 283620 | From DEC-2023 to NOV-2024 | 5.46 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 651 | 0 | 09 Dec 2023 | NITIN D PARDESHI | Vehicle Fuel, Maintenance & Insurance | Insurance Renewal | No. | 0 | 50000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 19 Dec 2023
GANGA ASMI | 651 | 0 | 09 Dec 2023 | NITIN D PARDESHI | Photocopy-Xerox Machine Rental Charges. | Rental Charges. | Month | 0 | 20000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | MKT. Marketing Infrastructure | Cancelled | DUSHANT.GORE | 19 Dec 2023
GANGA ASMI | 652 | 0 | 09 Dec 2023 | NITIN D PARDESHI | Goel House Electricity expenses | Electricity Bills | No. | 12 | 75000 | 900000 | 0 | 900000 | 0 | 4.4283 | 332122.5 | 0 | 332122.5 | 7.5717 | 567877.5 | From DEC-2023 to NOV-2024 | 36.9025 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 20 Jan 2024 |  | SOC. M. Maintenace Overheads | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 653 | 0 | 09 Dec 2023 | AQUARIUS WATERPROOFING | UGWT Waterproofing Membrane W/P (Vertical) | Membrane Vertical Waterproofing (L) | Sq.Ft | 8029.59 | 15 | 120443.85 | 21679.9 | 142123.75 | 10 | 3613.3155 | 54199.73 | 9755.96 | 63955.69 | 4416.2745 | 78168.06 |  | 45 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Dec 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 653 | 0 | 09 Dec 2023 | AQUARIUS WATERPROOFING | UGWT Waterproofing Membrane W/P (Horizontal) | Membrane Horizontal Waterproofing (L) | Sq.Ft | 6796.2 | 13 | 88350.6 | 15903.1 | 104253.7 | 10 | 6796.2 | 88350.6 | 15903.1 | 104253.7 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Dec 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 653 | 1 | 09 Dec 2023 | AQUARIUS WATERPROOFING | UGWT Waterproofing Membrane W/P (Horizontal) | Membrane Horizontal Waterproofing (L) | Sq.Ft | 836.8 | 13 | 10878.4 | 1958.12 | 12836.52 | 10 | 836.8 | 10878.4 | 1958.12 | 12836.52 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 13 Dec 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 654 | 1 | 09 Dec 2023 | AQUARIUS WATERPROOFING | UGWT Waterproofing Membrane W/P (Horizontal) | Membrane Horizontal Waterproofing (M) | Sq.Ft | 836.8 | 34 | 28451.2 | 5121.22 | 33572.42 | 0 | 836.8 | 28451.2 | 5121.22 | 33572.42 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 13 Dec 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 654 | 0 | 09 Dec 2023 | AQUARIUS WATERPROOFING | UGWT Waterproofing Membrane W/P (Vertical) | Membrane Vertical Waterproofing (M) | Sq.Ft | 8029.59 | 30 | 240887.7 | 43359.78 | 284247.48 | 0 | 0 | 0 | 0 | 0 | 8029.59 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Dec 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 654 | 1 | 09 Dec 2023 | AQUARIUS WATERPROOFING | UGWT Waterproofing Membrane W/P (Horizontal) | Membrane Horizontal Waterproofing (M) | Sq.Ft | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 13 Dec 2023 |  | 06 WATERPROOFING WORK | Cancelled | MONALI CHAUDHAR | 02 Feb 2024
GANGA ASMI | 654 | 0 | 09 Dec 2023 | AQUARIUS WATERPROOFING | UGWT Waterproofing Membrane W/P (Horizontal) | Membrane Horizontal Waterproofing (M) | Sq.Ft | 6796.2 | 34 | 231070.8 | 41592.74 | 272663.54 | 0 | 6796.2 | 231070.8 | 41592.74 | 272663.54 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 13 Dec 2023 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 655 | 0 | 09 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Wall Painting | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 09 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 09 Dec 2023
GANGA ASMI | 655 | 0 | 09 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Wall Painting | 2nd Coat OBD (L) | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 09 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 655 | 0 | 09 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Wall Painting | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 09 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 655 | 0 | 09 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Ceiling Painting | 2nd Coat Putty (L) | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 09 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 655 | 0 | 09 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Ceiling Painting | 1 Coat Primer (Water Base) (L) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 09 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 655 | 0 | 09 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Wall Painting | 2nd Coat Putty (L) | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 09 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 655 | 0 | 09 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Ceiling Painting | 2nd Coat OBD (L) | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 09 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 656 | 0 | 11 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Wall Painting | 2nd Coat OBD (M) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 11 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 656 | 0 | 11 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Ceiling Painting | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 11 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 656 | 0 | 11 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Wall Painting | 2nd Coat Putty (M) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 11 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 656 | 0 | 11 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Wall Painting | 1 Coat Primer (Water Base) (M) | Sq.Ft | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 11 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 656 | 0 | 11 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Ceiling Painting | 2nd Coat Putty (M) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 11 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 656 | 0 | 11 Dec 2023 | ANIL MAHTO | New Sales Office (Wing-1) Ceiling Painting | 2nd Coat OBD (M) | Sq.Ft | 0 | 1.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 11 Dec 2023 |  | 10 PAINTING WORK | Cancelled | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 404 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 302 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 104 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 103 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 402 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 204 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 305 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 302 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 104 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 404 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 302 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 403 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 105 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 201 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 401 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 101 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 301 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 402 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 405 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 103 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 101 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 205 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 103 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 102 Core Cutting | Vertical Core Cutting 125mm | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 0 | 0 | 0 | 0 | 4 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 105 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 202 Core Cutting | Vertical Core Cutting 125mm | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 4 | 700 | 0 | 700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 204 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 403 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 405 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 405 Core Cutting | Vertical Core Cutting 125mm | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 2 | 350 | 0 | 350 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 403 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 102 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 205 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 303 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 101 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 103 Core Cutting | Vertical Core Cutting 100mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 104 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 105 Core Cutting | Vertical Core Cutting 125mm | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 303 Core Cutting | Vertical Core Cutting 100mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 102 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 101 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 205 Core Cutting | Vertical Core Cutting 125mm | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 2 | 350 | 0 | 350 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 402 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 305 Core Cutting | Vertical Core Cutting 50mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 1 | 175 | 0 | 175 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 203 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 105 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 404 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 301 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 204 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 304 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 402 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 205 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 103 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 202 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 303 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 303 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 505 Core Cutting | Vertical Core Cutting 125mm | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 2 | 350 | 0 | 350 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 401 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 202 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 305 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 201 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 401 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 304 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 202 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 304 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 104 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 305 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 204 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 403 Core Cutting | Horizontal Core Cutting 125mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 501 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 102 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 404 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 301 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 301 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 302 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 402 Core Cutting | Vertical Core Cutting 125mm | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 4 | 700 | 0 | 700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 203 Core Cutting | Vertical Core Cutting 100mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 404 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 1 | 175 | 0 | 175 | 2 | 350 |  | 33.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 501 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 403 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 502 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 204 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 1 | 175 | 0 | 175 | 2 | 350 |  | 33.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 301 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 304 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 1 | 175 | 0 | 175 | 2 | 350 |  | 33.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 102 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 403 Core Cutting | Vertical Core Cutting 100mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 203 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 302 Core Cutting | Vertical Core Cutting 125mm | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 4 | 700 | 0 | 700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 504 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 201 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 503 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 205 Core Cutting | Vertical Core Cutting 50mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 1 | 175 | 0 | 175 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 405 Core Cutting | Vertical Core Cutting 50mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 1 | 175 | 0 | 175 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 303 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 203 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 401 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 203 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 103 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 504 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 1 | 175 | 0 | 175 | 2 | 350 |  | 33.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 304 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 201 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 401 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 303 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 202 Core Cutting | Horizontal Core Cutting 100mm | No. | 1 | 265 | 265 | 0 | 265 | 2.5 | 1 | 265 | 0 | 265 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 405 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 101 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 105 Core Cutting | Vertical Core Cutting 50mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 505 Core Cutting | Vertical Core Cutting 50mm | No. | 1 | 175 | 175 | 0 | 175 | 2.5 | 1 | 175 | 0 | 175 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 201 Core Cutting | Vertical Core Cutting 50mm | No. | 3 | 175 | 525 | 0 | 525 | 2.5 | 3 | 525 | 0 | 525 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 104 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 305 Core Cutting | Vertical Core Cutting 125mm | No. | 2 | 175 | 350 | 0 | 350 | 2.5 | 2 | 350 | 0 | 350 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 502 Core Cutting | Vertical Core Cutting 125mm | No. | 4 | 175 | 700 | 0 | 700 | 2.5 | 4 | 700 | 0 | 700 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 503 Core Cutting | Vertical Core Cutting 125mm | No. | 5 | 175 | 875 | 0 | 875 | 2.5 | 5 | 875 | 0 | 875 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 657 | 0 | 11 Dec 2023 | PRASNA PLUMBING SERVICE | MHADA-Flat No 203 Core Cutting | Horizontal Core Cutting 50mm | No. | 3 | 265 | 795 | 0 | 795 | 2.5 | 3 | 795 | 0 | 795 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 26 Dec 2023 |  | 08 PLUMBING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 658 | 1 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Wall Painting | 1 Coat Primer (Water Base) (L) | Sq.Ft | 4229.57 | 1 | 4229.57 | 761.32 | 4990.89 | 2.5 | 4229.57 | 4229.57 | 761.32 | 4990.89 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 658 | 1 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Ceiling Painting | 2nd Coat OBD (L) | Sq.Ft | 2682.32 | 2 | 5364.64 | 965.64 | 6330.28 | 2.5 | 0 | 0 | 0 | 0 | 2682.32 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 658 | 1 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Ceiling Painting | 2nd Coat Putty (L) | Sq.Ft | 2682.32 | 2 | 5364.64 | 965.64 | 6330.28 | 2.5 | 2682.32 | 5364.64 | 965.64 | 6330.28 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 658 | 1 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Ceiling Painting | 1 Coat Primer (Water Base) (L) | Sq.Ft | 2682.32 | 1 | 2682.32 | 482.82 | 3165.14 | 2.5 | 2682.32 | 2682.32 | 482.82 | 3165.14 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 658 | 1 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Wall Painting | 2nd Coat Putty (L) | Sq.Ft | 4229.57 | 2 | 8459.14 | 1522.64 | 9981.78 | 2.5 | 4229.57 | 8459.14 | 1522.64 | 9981.78 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 658 | 1 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Wall Painting | 2nd Coat OBD (L) | Sq.Ft | 4229.57 | 2 | 8459.14 | 1522.64 | 9981.78 | 2.5 | 0 | 0 | 0 | 0 | 4229.57 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | MONALI CHAUDHAR | 12 Dec 2023
GANGA ASMI | 659 | 0 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Ceiling Painting | 2nd Coat OBD (M) | Sq.Ft | 2682.32 | 1.5 | 4023.48 | 724.22 | 4747.7 | 0 | 0 | 0 | 0 | 0 | 2682.32 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 659 | 0 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Ceiling Painting | 2nd Coat Putty (M) | Sq.Ft | 2682.32 | 1.5 | 4023.48 | 724.22 | 4747.7 | 0 | 2682.32 | 4023.48 | 724.22 | 4747.7 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 659 | 0 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Wall Painting | 2nd Coat OBD (M) | Sq.Ft | 4229.57 | 1.5 | 6344.36 | 1141.98 | 7486.34 | 0 | 0 | 0 | 0 | 0 | 4229.57 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 659 | 0 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Ceiling Painting | 1 Coat Primer (Water Base) (M) | Sq.Ft | 2682.32 | 1 | 2682.32 | 482.82 | 3165.14 | 0 | 2682.32 | 2682.32 | 482.82 | 3165.14 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 659 | 0 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Wall Painting | 1 Coat Primer (Water Base) (M) | Sq.Ft | 4229.57 | 1 | 4229.57 | 761.32 | 4990.89 | 0 | 4229.57 | 4229.57 | 761.32 | 4990.89 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 659 | 0 | 12 Dec 2023 | ANIL MAHTO ENTERPRISES | New Sales Office (Wing-1) Wall Painting | 2nd Coat Putty (M) | Sq.Ft | 4229.57 | 1.5 | 6344.36 | 1141.98 | 7486.34 | 0 | 4229.57 | 6344.36 | 1141.98 | 7486.34 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Dec 2023 |  | 10 PAINTING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ASMI | 661 | 0 | 12 Dec 2023 | TAJ SERVICES | BRANDING Event Expenses | T SHIRT / BAGS / PENS / DRESS - BRANDING | No. | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SWAPNIL JADHAV |  | construction open | 12 Dec 2023 |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 16 Dec 2023
GANGA ASMI | 661 | 1 | 12 Dec 2023 | TAJ SERVICES | BRANDING Event Expenses | T SHIRT / BAGS / PENS / DRESS - BRANDING | No. | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SWAPNIL JADHAV |  | construction open | 12 Dec 2023 |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 16 Dec 2023
GANGA ASMI | 661 | 2 | 12 Dec 2023 | TAJ SERVICES | BRANDING Event Expenses | T SHIRT / BAGS / PENS / DRESS - BRANDING | No. | 0 | 750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | SWAPNIL JADHAV |  | construction open | 12 Dec 2023 |  | MKT. Media | Cancelled | SWAPNIL JADHAV | 16 Dec 2023
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 36.17 | 19 | 687.23 | 123.7 | 810.93 | 2.5 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Flat Flooring | Schedule & Quality | Sq.Ft | 424.61 | 2 | 849.22 | 152.86 | 1002.08 | 2.5 | 0 | 0 | 0 | 0 | 424.61 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Toilet Dado | Dado Fixing | Sq.Ft | 157.83 | 25 | 3945.75 | 710.24 | 4655.99 | 2.5 | 0 | 0 | 0 | 0 | 157.83 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19 | 662.72 | 119.28 | 782 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 31.65 | 19 | 601.35 | 108.24 | 709.59 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Flat Skirting | Vitrified Skirting work | R.Ft | 75.79 | 24 | 1818.96 | 327.42 | 2146.38 | 2.5 | 0 | 0 | 0 | 0 | 75.79 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Balcony Skirting | Ceramic Skirting work | R.Ft | 17.06 | 23 | 392.38 | 70.62 | 463 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 38.75 | 19 | 736.25 | 132.52 | 868.77 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Toilet Dado | Dado Fixing | Sq.Ft | 157.83 | 25 | 3945.75 | 710.24 | 4655.99 | 2.5 | 0 | 0 | 0 | 0 | 157.83 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Utility Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 33.91 | 19 | 644.29 | 115.98 | 760.27 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 374.57 | 20 | 7491.4 | 1348.46 | 8839.86 | 2.5 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Toilet Flooring | Schedule & Quality | Sq.Ft | 31.65 | 2 | 63.3 | 11.4 | 74.7 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19 | 662.72 | 119.28 | 782 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19 | 662.72 | 119.28 | 782 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Balcony Skirting | Ceramic Skirting work | R.Ft | 20.51 | 23 | 471.73 | 84.92 | 556.65 | 2.5 | 0 | 0 | 0 | 0 | 20.51 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Balcony Flooring | Schedule & Quality | Sq.Ft | 41.37 | 2 | 82.74 | 14.9 | 97.64 | 2.5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Utility Flooring | Schedule & Quality | Sq.Ft | 34.88 | 2 | 69.76 | 12.56 | 82.32 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19 | 662.72 | 119.28 | 782 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 38.75 | 19 | 736.25 | 132.52 | 868.77 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 37.14 | 19 | 705.66 | 127.02 | 832.68 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Flooring | Schedule & Quality | Sq.Ft | 41.37 | 2 | 82.74 | 14.9 | 97.64 | 2.5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Schedule & Quality | Sq.Ft | 33.91 | 2 | 67.82 | 12.2 | 80.02 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Balcony Skirting | Ceramic Skirting work | R.Ft | 20.51 | 23 | 471.73 | 84.92 | 556.65 | 2.5 | 0 | 0 | 0 | 0 | 20.51 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Dado | Dado Fixing | Sq.Ft | 157.83 | 25 | 3945.75 | 710.24 | 4655.99 | 2.5 | 0 | 0 | 0 | 0 | 157.83 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Balcony Flooring | Schedule & Quality | Sq.Ft | 30.27 | 2 | 60.54 | 10.9 | 71.44 | 2.5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 34.88 | 19 | 662.72 | 119.28 | 782 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 14.54 | 95.28 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Flat Skirting | Vitrified Skirting work | R.Ft | 75.79 | 24 | 1818.96 | 327.42 | 2146.38 | 2.5 | 0 | 0 | 0 | 0 | 75.79 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 38.75 | 19 | 736.25 | 132.52 | 868.77 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Balcony Skirting | Ceramic Skirting work | R.Ft | 17.06 | 23 | 392.38 | 70.62 | 463 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 30.27 | 19 | 575.13 | 103.52 | 678.65 | 2.5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Toilet Dado | Dado Fixing | Sq.Ft | 157.83 | 25 | 3945.75 | 710.24 | 4655.99 | 2.5 | 0 | 0 | 0 | 0 | 157.83 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Balcony Flooring | Schedule & Quality | Sq.Ft | 30.27 | 2 | 60.54 | 10.9 | 71.44 | 2.5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Utility Flooring | Schedule & Quality | Sq.Ft | 38.75 | 2 | 77.5 | 13.96 | 91.46 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Flat Skirting | Vitrified Skirting work | R.Ft | 116.02 | 24 | 2784.48 | 501.2 | 3285.68 | 2.5 | 0 | 0 | 0 | 0 | 116.02 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Flat Flooring | Vitrified Flooring work | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 15 Dec 2023
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 278.46 | 20 | 5569.2 | 1002.46 | 6571.66 | 2.5 | 0 | 0 | 0 | 0 | 278.46 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Utility Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Toilet Flooring | Schedule & Quality | Sq.Ft | 31.65 | 2 | 63.3 | 11.4 | 74.7 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Flat Skirting | Vitrified Skirting work | R.Ft | 75.79 | 24 | 1818.96 | 327.42 | 2146.38 | 2.5 | 0 | 0 | 0 | 0 | 75.79 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Flat Skirting | Vitrified Skirting work | R.Ft | 96.82 | 24 | 2323.68 | 418.26 | 2741.94 | 2.5 | 0 | 0 | 0 | 0 | 96.82 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 31.65 | 2 | 63.3 | 11.4 | 74.7 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 33.91 | 19 | 644.29 | 115.98 | 760.27 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Toilet Flooring | Schedule & Quality | Sq.Ft | 31.65 | 2 | 63.3 | 11.4 | 74.7 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 417.78 | 20 | 8355.6 | 1504 | 9859.6 | 2.5 | 0 | 0 | 0 | 0 | 417.78 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 38.75 | 2 | 77.5 | 13.96 | 91.46 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 37.14 | 19 | 705.66 | 127.02 | 832.68 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Flat Skirting | Vitrified Skirting work | R.Ft | 108.47 | 24 | 2603.28 | 468.6 | 3071.88 | 2.5 | 0 | 0 | 0 | 0 | 108.47 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 40.37 | 2 | 80.74 | 14.54 | 95.28 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Utility Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Flat Flooring | Schedule & Quality | Sq.Ft | 388.35 | 2 | 776.7 | 139.8 | 916.5 | 2.5 | 0 | 0 | 0 | 0 | 388.35 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Skirting | Ceramic Skirting work | R.Ft | 20.51 | 23 | 471.73 | 84.92 | 556.65 | 2.5 | 0 | 0 | 0 | 0 | 20.51 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Balcony Flooring | Schedule & Quality | Sq.Ft | 40.37 | 2 | 80.74 | 14.54 | 95.28 | 2.5 | 0 | 0 | 0 | 0 | 40.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Flat Flooring | Schedule & Quality | Sq.Ft | 417.78 | 2 | 835.56 | 150.4 | 985.96 | 2.5 | 0 | 0 | 0 | 0 | 417.78 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 417.78 | 20 | 8355.6 | 1504 | 9859.6 | 2.5 | 0 | 0 | 0 | 0 | 417.78 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Toilet Dado | Dado Fixing | Sq.Ft | 148.14 | 25 | 3703.5 | 666.64 | 4370.14 | 2.5 | 0 | 0 | 0 | 0 | 148.14 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Flooring | Schedule & Quality | Sq.Ft | 37.14 | 2 | 74.28 | 13.38 | 87.66 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 374.57 | 20 | 7491.4 | 1348.46 | 8839.86 | 2.5 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 388.35 | 20 | 7767 | 1398.06 | 9165.06 | 2.5 | 0 | 0 | 0 | 0 | 388.35 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Utility Flooring | Schedule & Quality | Sq.Ft | 38.75 | 2 | 77.5 | 13.96 | 91.46 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 278.46 | 20 | 5569.2 | 1002.46 | 6571.66 | 2.5 | 0 | 0 | 0 | 0 | 278.46 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 37.14 | 2 | 74.28 | 13.38 | 87.66 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 37.14 | 2 | 74.28 | 13.38 | 87.66 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Balcony Skirting | Ceramic Skirting work | R.Ft | 17.06 | 23 | 392.38 | 70.62 | 463 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 33.91 | 2 | 67.82 | 12.2 | 80.02 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Balcony Flooring | Schedule & Quality | Sq.Ft | 41.37 | 2 | 82.74 | 14.9 | 97.64 | 2.5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 374.57 | 20 | 7491.4 | 1348.46 | 8839.86 | 2.5 | 0 | 0 | 0 | 0 | 374.57 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 41.37 | 2 | 82.74 | 14.9 | 97.64 | 2.5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Balcony Skirting | Ceramic Skirting work | R.Ft | 20.51 | 23 | 471.73 | 84.92 | 556.65 | 2.5 | 0 | 0 | 0 | 0 | 20.51 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Toilet Flooring | Schedule & Quality | Sq.Ft | 33.91 | 2 | 67.82 | 12.2 | 80.02 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Toilet Flooring | Schedule & Quality | Sq.Ft | 31.65 | 2 | 63.3 | 11.4 | 74.7 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Balcony Skirting | Ceramic Skirting work | R.Ft | 17.06 | 23 | 392.38 | 70.62 | 463 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 34.88 | 2 | 69.76 | 12.56 | 82.32 | 2.5 | 0 | 0 | 0 | 0 | 34.88 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Balcony Skirting | Ceramic Skirting work | R.Ft | 20.01 | 23 | 460.23 | 82.84 | 543.07 | 2.5 | 0 | 0 | 0 | 0 | 20.01 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 41.37 | 19 | 786.03 | 141.48 | 927.51 | 2.5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Balcony Skirting | Ceramic Skirting work | R.Ft | 17.06 | 23 | 392.38 | 70.62 | 463 | 2.5 | 0 | 0 | 0 | 0 | 17.06 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Toilet Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 41.37 | 2 | 82.74 | 14.9 | 97.64 | 2.5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 31.65 | 2 | 63.3 | 11.4 | 74.7 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Utility Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Balcony Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 388.35 | 20 | 7767 | 1398.06 | 9165.06 | 2.5 | 0 | 0 | 0 | 0 | 388.35 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 41.37 | 2 | 82.74 | 14.9 | 97.64 | 2.5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 31.65 | 2 | 63.3 | 11.4 | 74.7 | 2.5 | 0 | 0 | 0 | 0 | 31.65 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Toilet Dado | Dado Fixing | Sq.Ft | 157.83 | 25 | 3945.75 | 710.24 | 4655.99 | 2.5 | 0 | 0 | 0 | 0 | 157.83 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 33.91 | 2 | 67.82 | 12.2 | 80.02 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 205 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Utility Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Flat Flooring | Vitrified Flooring work | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 15 Dec 2023
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 33.91 | 2 | 67.82 | 12.2 | 80.02 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 30.27 | 2 | 60.54 | 10.9 | 71.44 | 2.5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Flooring | Schedule & Quality | Sq.Ft | 417.78 | 2 | 835.56 | 150.4 | 985.96 | 2.5 | 0 | 0 | 0 | 0 | 417.78 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Flat Skirting | Vitrified Skirting work | R.Ft | 116.02 | 24 | 2784.48 | 501.2 | 3285.68 | 2.5 | 0 | 0 | 0 | 0 | 116.02 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 37.14 | 2 | 74.28 | 13.38 | 87.66 | 2.5 | 0 | 0 | 0 | 0 | 37.14 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Utility Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 417.78 | 2 | 835.56 | 150.4 | 985.96 | 2.5 | 0 | 0 | 0 | 0 | 417.78 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Flat Flooring | Vitrified Flooring work | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 15 Dec 2023
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 36.17 | 2 | 72.34 | 13.02 | 85.36 | 2.5 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Toilet Flooring | Schedule & Quality | Sq.Ft | 36.17 | 2 | 72.34 | 13.02 | 85.36 | 2.5 | 0 | 0 | 0 | 0 | 36.17 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Toilet Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Flat Flooring | Vitrified Flooring work | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 15 Dec 2023
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 30.27 | 2 | 60.54 | 10.9 | 71.44 | 2.5 | 0 | 0 | 0 | 0 | 30.27 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Balcony Skirting | Ceramic Skirting work | R.Ft | 20.51 | 23 | 471.73 | 84.92 | 556.65 | 2.5 | 0 | 0 | 0 | 0 | 20.51 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 201 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 105 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Flooring | Schedule & Quality | Sq.Ft | 41.37 | 2 | 82.74 | 14.9 | 97.64 | 2.5 | 0 | 0 | 0 | 0 | 41.37 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Flat Flooring | Vitrified Flooring work | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 15 Dec 2023
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Flat Skirting | Vitrified Skirting work | R.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 102 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 103 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 503 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 504 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 305 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 278.46 | 2 | 556.92 | 100.24 | 657.16 | 2.5 | 0 | 0 | 0 | 0 | 278.46 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 204 Balcony Flooring | Ceramic Flooring work | Sq.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Flat Flooring | Vitrified Flooring work | Sq.Ft | 0 | 24 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | DUSHANT.GORE | 15 Dec 2023
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Toilet Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 405 Toilet Flooring | Schedule & Quality | Sq.Ft | 33.91 | 2 | 67.82 | 12.2 | 80.02 | 2.5 | 0 | 0 | 0 | 0 | 33.91 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 101 Toilet Dado | Dado Fixing | Sq.Ft | 0 | 25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 203 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 404 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 304 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 401 Utility Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 104 Toilet Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 501 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 301 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 302 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 202 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 12 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Balcony Flooring | Ceramic Flooring & Floor Guard Laying | Sq.Ft | 0 | 19 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 38.75 | 2 | 77.5 | 13.96 | 91.46 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 303 Balcony Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 11 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 505 Flat Flooring | Vitrified Flooring & Floor Guard Laying | Sq.Ft | 0 | 20 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 08 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 402 Flat Flooring | Schedule & Quality | Sq.Ft | 0 | 2 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | B.C. RCC Superstructure | Cancelled | MONALI CHAUDHAR | 09 Jan 2024
GANGA ASMI | 662 | 1 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 502 Utility Flooring | Floor Guard Removing & Acid Wash | Sq.Ft | 38.75 | 2 | 77.5 | 13.96 | 91.46 | 2.5 | 0 | 0 | 0 | 0 | 38.75 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 08 Jan 2024 |  | 11 TILING WORK | Un-Approved |  | 1900-01-01
GANGA ASMI | 662 | 0 | 14 Dec 2023 | NITIN ENTERPRISES | MHADA-Flat No 403 Balcony Skirting | Ceramic Skirting work | R.Ft | 0 | 23 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 08 Jan 2024 |  | B.C. Internal Finishing Itmes | Cancelled | MONALI CHAUDHAR | 06 Jan 2024