## Project_Work_Order6385925985717
Project Work Order
From 01 Jan 2018 To 31 Jul 2024
Page 1 of 1
Total Records: 43 Records 1 To 43
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ARCADIA - A BUILDING | 3 | 0 | 26 Mar 2021 | PUNDLIK P MAHAJAN | Misc Expenses | Miscellaneous Expenses | No. | 1 | 50000 | 50000 | 0 | 50000 | 0 | 1 | 50000 | 0 | 50000 | 0 | 0 |  | 100 |  | tausif | tausif | construction open | 05 Apr 2021 |  | 14 MISC WORK | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 2 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | GI Sheet Removing & fixing Work-Retaining Wall Side | GI Sheet Fixing (L) | Sq.Ft | 300 | 5 | 1500 | 270 | 1770 | 2.5 | 300 | 1500 | 270 | 1770 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 08 Jun 2021 |  | UTI. Vermiculture | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 2 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | GI Sheet Removing & fixing Work-Retaining Wall Side | G.I. Sheet Removing - SOI | Sq.Ft | 300 | 3 | 900 | 162 | 1062 | 0 | 300 | 900 | 162 | 1062 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 08 Jun 2021 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 1 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | Old Material cutting & Frame work | Frame work | Sq.Ft | 1200 | 10 | 12000 | 2160 | 14160 | 2.5 | 1200 | 12000 | 2160 | 14160 | 0 | 0 |  | 100 |  | chetan.jewalikar | chetan.jewalikar | construction open | 08 Jun 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 0 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | MS Box GI barrication work | Fabrication work (L) | Kgs | 1638.966 | 17 | 27862.42 | 5015.24 | 32877.66 | 2.5 | 1638.966 | 27862.42 | 5015.24 | 32877.66 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 08 Jun 2021 |  | Admin. Direct Expenses | Approved | chetan.jawalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 0 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | MS Box GI barrication work | Tapping Screw- Den | No. | 350 | 2.5 | 875 | 157.5 | 1032.5 | 0 | 350 | 875 | 157.5 | 1032.5 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 08 Jun 2021 |  | DEV. Entrance Gate | Approved | chetan.jawalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 2 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | GI Sheet Removing & fixing Work-Retaining Wall Side | MS Square Pipe (L) | Kgs | 42.08 | 15 | 631.2 | 113.62 | 744.82 | 2.5 | 42.08 | 631.2 | 113.62 | 744.82 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 08 Jun 2021 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 0 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | MS Box GI barrication work | Fabrication work (L) | Kgs | 298.584 | 22 | 6568.85 | 1182.4 | 7751.25 | 2.5 | 298.584 | 6568.85 | 1182.4 | 7751.25 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 08 Jun 2021 |  | Admin. Direct Expenses | Approved | chetan.jawalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 0 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | MS Box GI barrication work | GI Sheet Fixing | Sq.Ft | 1682 | 5 | 8410 | 1513.8 | 9923.8 | 2.5 | 1682 | 8410 | 1513.8 | 9923.8 | 0 | 0 |  | 100 |  | tausif | chetan.jawalikar | construction open | 08 Jun 2021 |  | DEV. Entrance Gate | Approved | chetan.jawalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 5 | 2 | 03 May 2021 | GURUDATTA KRUPA ENTERPRISES | GI Sheet Removing & fixing Work-Retaining Wall Side | MS Angle Fixing | Kgs | 84.99 | 15 | 1274.85 | 229.48 | 1504.33 | 2.5 | 84.99 | 1274.85 | 229.48 | 1504.33 | 0 | 0 |  | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 08 Jun 2021 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 10 | 0 | 28 Jul 2021 | DRAUPADA EARTHMOVERS | JCB Work on site | JCB Charges | Hrs | 18 | 800 | 14400 | 2592 | 16992 | 0 | 18 | 14400 | 2592 | 16992 | 0 | 0 |  | 100 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 28 Jul 2021 |  | UTI. Drainage | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 13 | 0 | 09 Dec 2021 | R.T.S. STEEL SERVICES | Fabrication Work for site barrication | Fabrication work (M) | Kgs | 806.34 | 64 | 51605.76 | 9289.04 | 60894.8 | 0 | 0 | 0 | 0 | 0 | 806.34 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 14 | 0 | 09 Dec 2021 | R.T.S. STEEL SERVICES | Fabrication Work for site barrication | Fabrication work (L) | Kgs | 807 | 17 | 13719 | 2469.42 | 16188.42 | 2.5 | 0 | 0 | 0 | 0 | 807 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | Admin. Direct Expenses | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 14 | 0 | 09 Dec 2021 | R.T.S. STEEL SERVICES | Fabrication Work for site barrication | GI Sheet Fixing (L) | Sq.Ft | 672 | 5 | 3360 | 604.8 | 3964.8 | 2.5 | 0 | 0 | 0 | 0 | 672 | 0 |  | 0 |  | Avinash Padmanabha | chetan.jewalikar | construction open | 24 Dec 2021 |  | UTI. Vermiculture | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 15 | 0 | 29 Dec 2021 | VNE INFRA PROJECTS P LTD | Barrication Work (L) | Department Labour-Dev | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 1 | 20000 | 3600 | 23600 | 0 | 0 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Murum Filling | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 15 | 0 | 29 Dec 2021 | VNE INFRA PROJECTS P LTD | Barrication Work (L) | Department Labour-Dev | No. | 20 | 600 | 12000 | 2160 | 14160 | 0 | 20 | 12000 | 0 | 12000 | 0 | 2160 |  | 100 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Murum Filling | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 15 | 0 | 29 Dec 2021 | VNE INFRA PROJECTS P LTD | Barrication Work (L) | Department Labour-Dev | No. | 50 | 600 | 30000 | 5400 | 35400 | 0 | 35 | 21000 | 3780 | 24780 | 15 | 10620 |  | 70 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Murum Filling | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 15 | 0 | 29 Dec 2021 | VNE INFRA PROJECTS P LTD | Barrication Work (L) | Department Labour-Dev | No. | 2 | 800 | 1600 | 288 | 1888 | 0 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | Aniket Mohite | chetan.jewalikar | construction open | 13 Jan 2022 |  | DEV. Murum Filling | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 17 | 0 | 19 Jan 2022 | RAHUL TECHNICAL SEVICES | Fabrication Work for site barrication | Fabrication Work | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 29 Jan 2022 |  | B.C. Rework/Extrawork | Cancelled | skmishra | 29 Jan 2022
GANGA ARCADIA - A BUILDING | 18 | 0 | 29 Jan 2022 | R.T.S. STEEL SERVICES | Fabrication Work for site barrication | Fabrication Work | Sq.Ft | 800 | 10 | 8000 | 1440 | 9440 | 2.5 | 800 | 8000 | 1440 | 9440 | 0 | 0 |  | 100 |  | dushant gore | chetan.jewalikar | construction open | 29 Jan 2022 |  | B.C. Rework/Extrawork | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 19 | 0 | 14 Feb 2022 | VIKAS GARADE | Compound wall-video shooting | Labour Lumpsum - SOS | No. | 1 | 10000 | 10000 | 0 | 10000 | 0 | 1 | 10000 | 0 | 10000 | 0 | 0 |  | 100 |  | Dushant Gore | chetan.jewalikar | construction open | 21 Feb 2022 |  | S OH Infrastructure | Approved | chetan.jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 28 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | Sewage Water Analysis | No. | 8 | 1200 | 9600 | 1728 | 11328 | 0 | 3 | 3600 | 648 | 4248 | 5 | 7080 |  | 37.5 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | No category | Approved | chetan jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 28 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | NOise Test Day SOS | No. | 40 | 100 | 4000 | 720 | 4720 | 0 | 15 | 1500 | 270 | 1770 | 25 | 2950 |  | 37.5 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 28 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | Soil Analysis Test- SOS | No. | 16 | 1500 | 24000 | 4320 | 28320 | 0 | 4 | 6000 | 1080 | 7080 | 12 | 21240 |  | 25 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 28 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | Noise Test Night SOS | No. | 40 | 100 | 4000 | 720 | 4720 | 0 | 15 | 1500 | 270 | 1770 | 25 | 2950 |  | 37.5 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 28 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | Stack Monitoring Report SOS | No. | 20 | 900 | 18000 | 3240 | 21240 | 0 | 4 | 3600 | 648 | 4248 | 16 | 16992 |  | 20 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 28 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | Air Test SOS | No. | 20 | 1500 | 30000 | 5400 | 35400 | 0 | 12 | 18000 | 3240 | 21240 | 8 | 14160 |  | 60 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 28 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | Effluent Sample | No. | 8 | 1200 | 9600 | 1728 | 11328 | 0 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 28 | 0 | 24 May 2023 | EHS Matrix Private Limited | Tests-Air,Soil,Mannure,Noise,Effluent,Water test | Water Testing report - SOS | No. | 48 | 1000 | 48000 | 8640 | 56640 | 0 | 5 | 5000 | 900 | 5900 | 43 | 50740 |  | 10.4167 |  | ADITYA CHOUGULE | chetan jewalikar | construction open | 30 May 2023 |  | S OH Infrastructure | Approved | chetan jewalikar | 1900-01-01
GANGA ARCADIA - A BUILDING | 58 | 0 | 09 Dec 2023 | NITIN D PARDESHI | Arcadia- Electricity Bill | Electricity Bills | No. | 12 | 45000 | 540000 | 0 | 540000 | 0 | 2.9743 | 133843.5 | 0 | 133843.5 | 9.0257 | 406156.5 |  | 24.7858 |  | ADITYA.CHOUGULE | SWAPNIL JADHAV | construction open | 21 Feb 2024 |  | SOC. M. Maintenace Overheads | Approved | SWAPNIL JADHAV | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 1 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | Fabrication Work for Partition between A&B Bldg. | M.S.Channel (L) | Kgs | 204.4 | 12 | 2452.8 | 0 | 2452.8 | 2.5 | 204 | 2448 | 0 | 2448 | 0.4 | 4.8 |  | 99.8043 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 1 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | Fabrication Work for Partition between A&B Bldg. | GI Sheet Removing - DCW | Sq.Ft | 300 | 2.5 | 750 | 0 | 750 | 0 | 300 | 750 | 0 | 750 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 1 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | Fabrication Work for Partition between A&B Bldg. | GI Sheet Fixing (L) | Sq.Ft | 360 | 5 | 1800 | 0 | 1800 | 2.5 | 360 | 1800 | 0 | 1800 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | UTI. Vermiculture | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 0 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | GI Sheet Removing & fixing Work-Retaining Wall Side | Channel removing- SOSB | Kgs | 58.2 | 6 | 349.2 | 0 | 349.2 | 0 | 58.2 | 349.2 | 0 | 349.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 1 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | Fabrication Work for Partition between A&B Bldg. | MS Pipe 40 x 40 x 2mm (L) | Kgs | 146.9 | 12 | 1762.8 | 0 | 1762.8 | 2.5 | 146.9 | 1762.8 | 0 | 1762.8 | 0 | 0 | For MS Ladder Making work | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 1 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | Fabrication Work for Partition between A&B Bldg. | MS Angle 50 x 50 x 5mm | Kgs | 126.8 | 12 | 1521.6 | 0 | 1521.6 | 2.5 | 126.8 | 1521.6 | 0 | 1521.6 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 0 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | GI Sheet Removing & fixing Work-Retaining Wall Side | MS Channel Fixing BCo | Kgs | 173.6 | 12 | 2083.2 | 0 | 2083.2 | 2.5 | 173.6 | 2083.2 | 0 | 2083.2 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 1 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | Fabrication Work for Partition between A&B Bldg. | MS Angle Removing | Kgs | 126.8 | 6 | 760.8 | 0 | 760.8 | 0 | 126.8 | 760.8 | 0 | 760.8 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 0 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | GI Sheet Removing & fixing Work-Retaining Wall Side | G.I. Sheet Removing - SOI | Sq.Ft | 1040 | 3 | 3120 | 0 | 3120 | 0 | 1040 | 3120 | 0 | 3120 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 0 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | GI Sheet Removing & fixing Work-Retaining Wall Side | MS Angle Fixing | Kgs | 541.5 | 12 | 6498 | 0 | 6498 | 2.5 | 541.5 | 6498 | 0 | 6498 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 67 | 0 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | GI Sheet Removing & fixing Work-Retaining Wall Side | G.I. Sheet Removing - SOI | Sq.Ft | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 1900-01-01 |  | S OH Infrastructure | Cancelled | ADITYA.CHOUGULE | 31 Jan 2024
GANGA ARCADIA - A BUILDING | 67 | 1 | 30 Jan 2024 | SURESH RANGNATH SHITOLE | Fabrication Work for Partition between A&B Bldg. | Channel removing- SOSB | Kgs | 204.4 | 6 | 1226.4 | 0 | 1226.4 | 0 | 204 | 1224 | 0 | 1224 | 0.4 | 2.4 |  | 99.8043 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 1900-01-01 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 89 | 0 | 06 Jul 2024 | DURGARAM CHANDURAM BHATEE | Drainage line checkup & chamber cleaning | Chamber Cleaning Work | No. | 6 | 3000 | 18000 | 0 | 18000 | 0 | 0 | 0 | 0 | 0 | 6 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 12 Jul 2024 |  | SOC. M. Maintenace of Utilitie | Approved | Swapnil Erande | 1900-01-01