## Project_Work_Order6385926000231
Project Work Order
From 01 Jan 2018 To 31 Jul 2024
Page 1 of 1
Total Records: 29 Records 1 To 29
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ARCADIA - A BUILDING | 2 | 0 | 22 Mar 2021 | SHINDE PLUMBING CONTRACTOR | Drainage Line Work (Temporary) | Chamber 24" x 36" (3ft Ht) - UTI | No. | 5 | 1000 | 5000 | 900 | 5900 | 2.5 | 2 | 2000 | 360 | 2360 | 3 | 3540 |  | 40 |  | tausif | tausif | construction open | 06 Apr 2021 |  | UTI. Electricity Infrastructur | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 2 | 0 | 22 Mar 2021 | SHINDE PLUMBING CONTRACTOR | Drainage Line Work (Temporary) | 12" Dia Derex Pipe line | R.Ft | 170 | 12 | 2040 | 367.2 | 2407.2 | 2.5 | 120 | 1440 | 259.2 | 1699.2 | 50 | 708 |  | 70.5882 |  | tausif | tausif | construction open | 06 Apr 2021 |  | 08 PLUMBING WORK | Approved | tausif | 1900-01-01
GANGA ARCADIA - A BUILDING | 54 | 0 | 10 Nov 2023 | AGILE VENTURES | Arcadia-STP-170KLD | Sewage Treatment Plant (M) | No. | 1 | 1605400 | 1605400 | 288972 | 1894372 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | AKSHADA MAHAJAN | DUSHANT.GORE | construction open | 10 Nov 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | DUSHANT.GORE | 1900-01-01
GANGA ARCADIA - A BUILDING | 73 | 0 | 22 Feb 2024 | ARYA CONSULTANCY | A-Electrical Work-HT & LT line shifting | H.T. & L.T. Line Shifting- UTI | No. | 1 | 100000 | 100000 | 18000 | 118000 | 0 | 0.5 | 50000 | 9000 | 59000 | 0.5 | 59000 |  | 50 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Mar 2024 |  | UTI. Electricity Infrastructur | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 75 | 0 | 04 Mar 2024 | DEFIANT RENEWABLES PRIVATE LIMITED | OWC System | OWC Inst. Test & Commissioning | No. | 0 | 800307.2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 04 Mar 2024 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 07 Mar 2024
GANGA ARCADIA - A BUILDING | 75 | 0 | 04 Mar 2024 | DEFIANT RENEWABLES PRIVATE LIMITED | OWC System | OWC Inst. Test & Commissioning | No. | 0 | 909440 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 04 Mar 2024 |  | 14 MISC WORK | Cancelled | ADITYA.CHOUGULE | 07 Mar 2024
GANGA ARCADIA - A BUILDING | 75 | 0 | 04 Mar 2024 | DEFIANT RENEWABLES PRIVATE LIMITED | OWC System | OWC Inst. Test & Commissioning | No. | 1 | 812000 | 812000 | 97440 | 909440 | 0 | 0.7 | 568400 | 68208 | 636608 | 0.3 | 272832 | 1. 1 Year Fully Comprehensive AMC Free of cost & after 1 Year 5% charges on Contract Value for fully Comprehensive AMC. 2. AMC Includes Oil Changing, Greasing, 1 coat PU Paint (Red oxide). | 70 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 04 Mar 2024 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 84 | 0 | 27 May 2024 | HOLE ENTERPRISES | Pump Room - RCC Work (L) | RCC Pardi -DPo | Sq.Ft | 0 | 150 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 27 May 2024 |  | DEV. Podium | Cancelled | ADITYA.CHOUGULE | 27 May 2024
GANGA ARCADIA - A BUILDING | 84 | 0 | 27 May 2024 | HOLE ENTERPRISES | STP-170KLD-RCC Work (L) | RCC Work STP | Ltrs | 0 | 4.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 27 May 2024 |  | UTI. S.T.P | Cancelled | ADITYA.CHOUGULE | 27 May 2024
GANGA ARCADIA - A BUILDING | 84 | 0 | 27 May 2024 | HOLE ENTERPRISES | Pump Room - RCC Work (L) | RCC Slab- cc | Sq.Ft | 0 | 190 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 27 May 2024 |  | B.C. Customer Changes | Cancelled | ADITYA.CHOUGULE | 27 May 2024
GANGA ARCADIA - A BUILDING | 84 | 0 | 27 May 2024 | HOLE ENTERPRISES | Pump Room - RCC Work (L) | PCC - SO | Sq.Ft | 0 | 8 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 27 May 2024 |  | S OH Infrastructure | Cancelled | ADITYA.CHOUGULE | 27 May 2024
GANGA ARCADIA - A BUILDING | 84 | 0 | 27 May 2024 | HOLE ENTERPRISES | Pump Room - RCC Work (L) | RCC Raft - DCW | Sq.Ft | 0 | 85 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 27 May 2024 |  | DEV. Compound Wall | Cancelled | ADITYA.CHOUGULE | 27 May 2024
GANGA ARCADIA - A BUILDING | 84 | 0 | 27 May 2024 | HOLE ENTERPRISES | UGWT- RCC Work (L) | UGWT Labour | Ltrs | 0 | 4.25 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 27 May 2024 |  | UTI. U.G.W.T | Cancelled | ADITYA.CHOUGULE | 27 May 2024
GANGA ARCADIA - A BUILDING | 85 | 0 | 27 May 2024 | ROHIT CONSTRUCTION | Pump Room - RCC Work (L) | PCC - SO | Sq.Ft | 1878.96 | 8 | 15031.68 | 2705.7 | 17737.38 | 2.5 | 1320 | 10560 | 1900.8 | 12460.8 | 558.96 | 5276.58 |  | 70.2516 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 85 | 0 | 27 May 2024 | ROHIT CONSTRUCTION | Pump Room - RCC Work (L) | RCC Slab- cc | Sq.Ft | 1622.67 | 190 | 308307.3 | 55495.32 | 363802.62 | 2.5 | 0 | 0 | 0 | 0 | 1622.67 | 0 |  | 16.5776 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | B.C. Customer Changes | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 85 | 0 | 27 May 2024 | ROHIT CONSTRUCTION | Pump Room - RCC Work (L) | RCC Pardi -DPo | Sq.Ft | 1504.674 | 150 | 225701.1 | 40626.2 | 266327.3 | 2.5 | 0 | 0 | 0 | 0 | 1504.674 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | DEV. Podium | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 85 | 0 | 27 May 2024 | ROHIT CONSTRUCTION | Pump Room - RCC Work (L) | RCC Raft - DCW | Sq.Ft | 1842.04 | 85 | 156573.4 | 28183.22 | 184756.62 | 2.5 | 1321.2924 | 112309.85 | 20215.78 | 132525.63 | 520.7476 | 52230.99 |  | 71.7298 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 85 | 0 | 27 May 2024 | ROHIT CONSTRUCTION | UGWT- RCC Work (L) | UGWT Labour | Ltrs | 267772 | 4.25 | 1138031 | 204845.58 | 1342876.58 | 2.5 | 113803.1 | 483663.18 | 87059.38 | 570722.56 | 153968.9 | 772154.03 | Charges for UGWT RCC Work as per Dwg. including Shuttering, Reinforcement & Concreting. | 60 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 85 | 0 | 27 May 2024 | ROHIT CONSTRUCTION | STP-170KLD-RCC Work (L) | RCC Work STP | Ltrs | 221129.68 | 4.25 | 939801.14 | 169164.2 | 1108965.34 | 2.5 | 210073.196 | 892811.08 | 160706.02 | 1053517.1 | 11056.484 | 55448.24 | Charges for STP RCC Work as per Dwg. including Shuttering, Reinforcement & Concreting. | 95 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | UTI. S.T.P | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 86 | 0 | 01 Jun 2024 | AQUARIUS WATERPROOFING | A-STP-170KLD,UGWT,Pumproom-External Waterproofing Work | Membrane Horizontal Waterproofing (L) | Sq.Ft | 5190.5 | 13 | 67476.5 | 12145.78 | 79622.28 | 10 | 2791 | 36283 | 6530.94 | 42813.94 | 2399.5 | 36808.34 |  | 53.7713 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 86 | 0 | 01 Jun 2024 | AQUARIUS WATERPROOFING | A-STP-170KLD,UGWT,Pumproom-External Waterproofing Work | Membrane Vertical Waterproofing (L) | Sq.Ft | 4246.61 | 15 | 63699.15 | 11465.84 | 75164.99 | 10 | 0 | 0 | 0 | 0 | 4246.61 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 87 | 0 | 01 Jun 2024 | AQUARIUS WATERPROOFING | A-STP-170KLD,UGWT,Pumproom-External Waterproofing Work | Membrane Vertical Waterproofing (M) | Sq.Ft | 4246.61 | 40 | 169864.4 | 30575.6 | 200440 | 0 | 0 | 0 | 0 | 0 | 4246.61 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 87 | 0 | 01 Jun 2024 | AQUARIUS WATERPROOFING | A-STP-170KLD,UGWT,Pumproom-External Waterproofing Work | Membrane Horizontal Waterproofing (M) | Sq.Ft | 5190.5 | 34 | 176477 | 31765.86 | 208242.86 | 0 | 2791 | 94894 | 17080.92 | 111974.92 | 2399.5 | 96267.94 |  | 53.7713 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 08 Jun 2024 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 91 | 0 | 10 Jul 2024 | PRABHURAM VERMA | UGWT -Internal Waterproofing Work | Chemical Waterproofing (M+L).Sq.ft | Sq.Ft | 3944.93 | 22 | 86788.46 | 0 | 86788.46 | 5 | 0 | 0 | 0 | 0 | 3944.93 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 19 Jul 2024 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 91 | 0 | 10 Jul 2024 | PRABHURAM VERMA | UGWT -Internal Waterproofing Work | IPS W/P | Sq.Ft | 1107.52 | 15 | 16612.8 | 0 | 16612.8 | 5 | 0 | 0 | 0 | 0 | 1107.52 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 19 Jul 2024 |  | 06 WATERPROOFING WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 91 | 0 | 10 Jul 2024 | PRABHURAM VERMA | UGWT -Internal Waterproofing Work | Cement Ghotai - DCH | Sq.Ft | 2837.41 | 15 | 42561.15 | 0 | 42561.15 | 5 | 0 | 0 | 0 | 0 | 2837.41 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 19 Jul 2024 |  | DEV. Club House | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 92 | 0 | 11 Jul 2024 | GANGAPRASAD K VARMA | STP -Internal Waterproofing Work | IPS W/P - DEn | Sq.Ft | 1195.95 | 15 | 17939.25 | 3229.06 | 21168.31 | 10 | 0 | 0 | 0 | 0 | 1195.95 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | DEV. Entrance Gate | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 92 | 0 | 11 Jul 2024 | GANGAPRASAD K VARMA | STP -Internal Waterproofing Work | Chemical W/ P (M+L)- SO | Sq.Ft | 5095.02 | 22 | 112090.44 | 20176.28 | 132266.72 | 10 | 0 | 0 | 0 | 0 | 5095.02 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ARCADIA - A BUILDING | 92 | 0 | 11 Jul 2024 | GANGAPRASAD K VARMA | STP -Internal Waterproofing Work | Cement Ghotai | Sq.Ft | 3899.07 | 15 | 58486.05 | 10527.48 | 69013.53 | 10 | 0 | 0 | 0 | 0 | 3899.07 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 19 Jul 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01