## Project_Work_Order6385986553421
Project Work Order
From 01 Jul 2022 To 22 Aug 2024
Page 1 of 1
Total Records: 651 Records 1 To 651
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 9 | 1200 | 10800 | 1944 | 12744 | 0 | 6.3 | 7560 | 1360.8 | 8920.8 | 2.7 | 3823.2 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 440 | 2550 | 1122000 | 201960 | 1323960 | 0 | 308 | 785400 | 141372 | 926772 | 132 | 397188 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 9 | 1000 | 9000 | 1620 | 10620 | 0 | 6.3 | 6300 | 1134 | 7434 | 2.7 | 3186 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Butterfly Valve 150mm -(M) | No. | 4 | 3400 | 13600 | 2448 | 16048 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Hydrant Valve 63mm (M). | set | 8 | 18500 | 148000 | 26640 | 174640 | 0 | 5.6 | 103600 | 18648 | 122248 | 2.4 | 52392 | Supplying of Hydrants a) Single headed (Type A) hydrant valve made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet, gunmetal blank caps, chain and hand wheels etc. b) 2 lengths of 15 mtr long , 63mm dia RRL hose. Brand-KARTAR | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Orifice Plate (M) | No. | 8 | 1100 | 8800 | 1584 | 10384 | 0 | 5.6 | 6160 | 1108.8 | 7268.8 | 2.4 | 3115.2 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(M) | No. | 3 | 5800 | 17400 | 3132 | 20532 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers CO2 type fire extinguishers of 4.5 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc.Brand-Marcury | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket (M) | No. | 3 | 3280 | 9840 | 1771.2 | 11611.2 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 13 | 6500 | 84500 | 15210 | 99710 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand-Kartar/Quinn. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 12 | 275 | 3300 | 594 | 3894 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 12 | 270 | 3240 | 583.2 | 3823.2 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 12 | 270 | 3240 | 583.2 | 3823.2 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (M) | No. | 12 | 270 | 3240 | 583.2 | 3823.2 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 12 | 2200 | 26400 | 4752 | 31152 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc.Brand-Marcury | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (M) | No. | 1616 | 380 | 614080 | 110534.4 | 724614.4 | 0 | 685.8 | 260604 | 46908.72 | 307512.72 | 930.2 | 417101.68 | Supply of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002 Brand- HD Fire | 42.4381 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (M) | No. | 57 | 450 | 25650 | 4617 | 30267 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | Supply of Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. Brand- HD Fire | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Upright Sprinkler (M) | No. | 398 | 450 | 179100 | 32238 | 211338 | 0 | 282.2 | 126990 | 22858.2 | 149848.2 | 115.8 | 61489.8 | Supply of Early Suppression Fast Response Upright sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. Brand- HD Fire | 70.9045 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Hydraulic Sprinkler 150mm.(M) | set | 7 | 56500 | 395500 | 71190 | 466690 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | Supply of Hydraulically operated sprinkler alarm valve 15mm with all accesories; 2 nos of pressure guages,2 nos isolation valves, 1 no of angle valve, 1 no of strainer, 1 no of non return valve, 1 no of alarm control valve, 1 no of alarm test valve etc.Brand-HD Fire | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 1 | 7540 | 7540 | 1357.2 | 8897.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of Vane type water flow switch in 100 mm size with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 12 | 8500 | 102000 | 18360 | 120360 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Supply of Vane type water flow switch in 150 mm size with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 857 | 1450 | 1242650 | 223677 | 1466327 | 0 | 666.5504 | 966498.01 | 173969.64 | 1140467.65 | 190.4497 | 325859.35 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 77.7772 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 1366 | 2100 | 2868600 | 516348 | 3384948 | 0 | 596.3105 | 1252252.03 | 225405.36 | 1477657.39 | 769.6895 | 1907290.61 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 43.6538 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 32mm (M) | No. | 21 | 1450 | 30450 | 5481 | 35931 | 0 | 20.7 | 30015 | 5402.7 | 35417.7 | 0.3 | 513.3 | Supply of brass Ball valve 32mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 98.5714 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 8 | 1850 | 14800 | 2664 | 17464 | 0 | 7.7005 | 14246.01 | 2564.28 | 16810.29 | 0.2995 | 653.71 | Supply of brass Ball valve 40mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 96.2563 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 100mm-(M) | No. | 1 | 3600 | 3600 | 648 | 4248 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 150mm -(M) | No. | 18 | 3800 | 68400 | 12312 | 80712 | 0 | 8.4 | 31920 | 5745.6 | 37665.6 | 9.6 | 43046.4 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Quinn/Kartar | 46.6667 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 3401 | 350 | 1190350 | 214263 | 1404613 | 0 | 1821.9429 | 637680 | 114782.4 | 752462.4 | 1579.0571 | 652150.6 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 53.5708 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 1508 | 450 | 678600 | 122148 | 800748 | 0 | 1018.6489 | 458392 | 82510.56 | 540902.56 | 489.3511 | 259845.44 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 67.5497 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 370 | 500 | 185000 | 33300 | 218300 | 0 | 113.618 | 56809 | 10225.62 | 67034.62 | 256.382 | 151265.38 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 30.7076 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 223 | 650 | 144950 | 26091 | 171041 | 0 | 140.8215 | 91534 | 16476.12 | 108010.12 | 82.1785 | 63030.88 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 63.1487 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 65mm Dia. Heavy Grade Pipe (M) | Mtrs | 153 | 800 | 122400 | 22032 | 144432 | 0 | 115.22 | 92176 | 16591.68 | 108767.68 | 37.78 | 35664.32 | Supply of 65mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 75.3072 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 40 | 1000 | 40000 | 7200 | 47200 | 0 | 28 | 28000 | 5040 | 33040 | 12 | 14160 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 80mm-(M) | No. | 14 | 3200 | 44800 | 8064 | 52864 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Supply of C.I. butterfly valves 80 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 150mm -(M) | No. | 3 | 3800 | 11400 | 2052 | 13452 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Double Hydrant Valve (M) | set | 12 | 33000 | 396000 | 71280 | 467280 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Supply of landing Hydrants a) Double headed (Type B) hydrant valve made of stainless steel with 63mm dia outlets & 80mm/100 mm dia flanged inlet,gunmetal blank caps,chain and hand wheels b) 2 L of 15 mtr long,63mm dia RRL hose. Brand-Essel/Mercury. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Orifice Plate (M) | No. | 14 | 1200 | 16800 | 3024 | 19824 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Supply of stainless steel single stage single hole restriction 80 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Orifice Plate (M) | No. | 12 | 1400 | 16800 | 3024 | 19824 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Hydrant Valve 63mm (M). | set | 14 | 19500 | 273000 | 49140 | 322140 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Supplying of Hydrants a) Single headed (Type A) hydrant valve made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet, gunmetal blank caps, chain and hand wheels etc. b) 2 lengths of 15 mtr long , 63mm dia RRL hose. Brand-Essel/Mercury. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Butterfly Valve 100mm-(M) | No. | 25 | 3600 | 90000 | 16200 | 106200 | 0 | 17.5 | 63000 | 11340 | 74340 | 7.5 | 31860 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Zoloto/Kartar | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Butterfly Valve 100mm-(M) | No. | 25 | 3600 | 90000 | 16200 | 106200 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of C.I. butterfly valves 100 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Zoloto/Kartar | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 24 | 350 | 8400 | 1512 | 9912 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 373 | 1000 | 373000 | 67140 | 440140 | 0 | 273.4 | 273400 | 49212 | 322612 | 99.6 | 117528 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 73.2976 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 13 | 1450 | 18850 | 3393 | 22243 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 466 | 2100 | 978600 | 176148 | 1154748 | 0 | 0 | 0 | 0 | 0 | 466 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor. This sign shall be used to Indicate all exits which can be used in the event of an emergency. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "FIRE EXTINGUISHER" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 26 | 275 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Air Release Valve 25mm (M) | No. | 3 | 1750 | 5250 | 945 | 6195 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand -Kartar/Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Air Release Valve 25mm (M) | No. | 3 | 1750 | 5250 | 945 | 6195 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand -Kartar/Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 26 | 2010 | 52260 | 9406.8 | 61666.8 | 0 | 17.5 | 35175 | 6331.5 | 41506.5 | 8.5 | 20160.3 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc.Brand- Mercury | 67.3077 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (M) | No. | 26 | 2010 | 52260 | 9406.8 | 61666.8 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Supplying, installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. capacity, with discharge nozzle, bend & horn, wal mounting bracket etc.Brand- Mercury | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 25 | 275 | 6875 | 1237.5 | 8112.5 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (M) | No. | 25 | 275 | 6875 | 1237.5 | 8112.5 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Providing and fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location. The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 200 | 340 | 68000 | 12240 | 80240 | 0 | 107.8 | 36652 | 6597.36 | 43249.36 | 92.2 | 36990.64 | Supply of Brand HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 53.9 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 200 | 340 | 68000 | 12240 | 80240 | 0 | 140 | 47600 | 8568 | 56168 | 60 | 24072 | Supply of Brand HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 25 | 7500 | 187500 | 33750 | 221250 | 0 | 17.5 | 131250 | 23625 | 154875 | 7.5 | 66375 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Vane Type Water Flow (M) | No. | 25 | 7500 | 187500 | 33750 | 221250 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of Vane type water flow switch in following sizes with accesories etc. complete. The flow switch shall be UL Listed / FM approved. Brand-Honeywell | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 25 | 4500 | 112500 | 20250 | 132750 | 0 | 17.5 | 78750 | 14175 | 92925 | 7.5 | 39825 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand- Zoloto/Kartar. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Drain Valve 25 mm (M) | No. | 25 | 4500 | 112500 | 20250 | 132750 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings; made of brass in following sizes, with unions etc. Brand- Zoloto/Kartar. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 100 | 2400 | 240000 | 43200 | 283200 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Supply of brass Ball valve 40mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Brass Ball Valve 40mm (M) | No. | 100 | 2400 | 240000 | 43200 | 283200 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Supply of brass Ball valve 40mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Brass Ball Valve 50mm (M) | No. | 100 | 2650 | 265000 | 47700 | 312700 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Supply of brass Ball valve 50mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Brass Ball Valve 50mm (M) | No. | 100 | 2650 | 265000 | 47700 | 312700 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | Supply of brass Ball valve 50mm with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. Brand-Kartar/Quinn | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 1340 | 350 | 469000 | 84420 | 553420 | 0 | 567 | 198450 | 35721 | 234171 | 773 | 319249 | Supply of Brand HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 42.3134 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Side Wall Sprinkler (M) | No. | 1340 | 350 | 469000 | 84420 | 553420 | 0 | 350 | 122500 | 22050 | 144550 | 990 | 408870 | Supply of Brand HD Fire Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 26.1194 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 302 | 650 | 196300 | 35334 | 231634 | 0 | 180.6 | 117390 | 21130.2 | 138520.2 | 121.4 | 93113.8 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 59.8013 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe (M) | Mtrs | 302 | 650 | 196300 | 35334 | 231634 | 0 | 210 | 136500 | 24570 | 161070 | 92 | 70564 | Supply of 50mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 69.5364 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 1027 | 1450 | 1489150 | 268047 | 1757197 | 0 | 426.2304 | 618034.01 | 111246.12 | 729280.13 | 600.7697 | 1027916.87 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 41.5025 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 1027 | 1450 | 1489150 | 268047 | 1757197 | 0 | 0 | 0 | 0 | 0 | 1027 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 260 | 2100 | 546000 | 98280 | 644280 | 0 | 177.8 | 373380 | 67208.4 | 440588.4 | 82.2 | 203691.6 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 68.3846 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 260 | 2100 | 546000 | 98280 | 644280 | 0 | 70 | 147000 | 26460 | 173460 | 190 | 470820 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 26.9231 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 1788 | 350 | 625800 | 112644 | 738444 | 0 | 714 | 249900 | 44982 | 294882 | 1074 | 443562 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 39.9329 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe (M) | Mtrs | 1788 | 350 | 625800 | 112644 | 738444 | 0 | 420 | 147000 | 26460 | 173460 | 1368 | 564984 | Supply of 25mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 23.4899 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 357 | 450 | 160650 | 28917 | 189567 | 0 | 249.9 | 112455 | 20241.9 | 132696.9 | 107.1 | 56870.1 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe (M) | Mtrs | 357 | 450 | 160650 | 28917 | 189567 | 0 | 6.3 | 2835 | 510.3 | 3345.3 | 350.7 | 186221.7 | Supply of 32mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 1.7647 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 1536 | 500 | 768000 | 138240 | 906240 | 0 | 999.6 | 499800 | 89964 | 589764 | 536.4 | 316476 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 65.0781 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe (M) | Mtrs | 1536 | 500 | 768000 | 138240 | 906240 | 0 | 420 | 210000 | 37800 | 247800 | 1116 | 658440 | Supply of 40mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 27.3438 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 79 | 2100 | 165900 | 29862 | 195762 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 79 | 2100 | 165900 | 29862 | 195762 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | Double Hydrant Valve (M) | set | 25 | 33000 | 825000 | 148500 | 973500 | 0 | 17.5 | 577500 | 103950 | 681450 | 7.5 | 292050 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-Essel | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | Double Hydrant Valve (M) | set | 25 | 33000 | 825000 | 148500 | 973500 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of C.I. 150mm butterfly valves of approved makes as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. Brand-Essel | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | Orifice Plate (M) | No. | 25 | 1400 | 35000 | 6300 | 41300 | 0 | 17.5 | 24500 | 4410 | 28910 | 7.5 | 12390 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | Orifice Plate (M) | No. | 25 | 1400 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Supply of stainless steel single stage single hole restriction 100 mm orifice plate at the inlet of landing valves.The sizing of orifice area must be calculated for straight edge section.The installation must be carried out as per the standard procedure | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Strainer "Y" (M) | No. | 1 | 7263 | 7263 | 1307.34 | 8570.34 | 0 | 0.7 | 5084.1 | 915.14 | 5999.24 | 0.3 | 2571.1 | Supply of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. Brand- Zoloto / KARTAR | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Strainer "Y" (M) | No. | 1 | 7263 | 7263 | 1307.34 | 8570.34 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. Brand- Zoloto / KARTAR | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Air Release Valve 25mm (M) | No. | 1 | 1750 | 1750 | 315 | 2065 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand-Kartar/ Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Air Release Valve 25mm (M) | No. | 1 | 1750 | 1750 | 315 | 2065 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supplying 25mm dia Automatic air release valve of approved makes with unions etc. complete.Brand-Kartar/ Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 27 | 1450 | 39150 | 7047 | 46197 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 27 | 1450 | 39150 | 7047 | 46197 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 20 | 1450 | 29000 | 5220 | 34220 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe (M) | Mtrs | 20 | 1450 | 29000 | 5220 | 34220 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Supply of 100mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo/Jindal | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Non Return Valve 100mm (M) | No. | 1 | 3200 | 3200 | 576 | 3776 | 0 | 0.7 | 2240 | 403.2 | 2643.2 | 0.3 | 1132.8 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand -Kartar/Zoloto | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Non Return Valve 100mm (M) | No. | 1 | 3200 | 3200 | 576 | 3776 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply, of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I.Brand -Kartar/Zoloto | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(M) | No. | 2 | 3600 | 7200 | 1296 | 8496 | 0 | 1.4 | 5040 | 907.2 | 5947.2 | 0.6 | 2548.8 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Zoloto/Kartar | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(M) | No. | 2 | 3600 | 7200 | 1296 | 8496 | 0 | 1.4 | 5040 | 907.2 | 5947.2 | 0.6 | 2548.8 | Supply of C.I. butterfly valves 150 mm as per I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. brand- Zoloto/Kartar | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm Cable (M) | Mtrs | 175 | 350 | 61250 | 11025 | 72275 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand- Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm Cable (M) | Mtrs | 175 | 350 | 61250 | 11025 | 72275 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand- Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 3C x 1.5sqmm (M) | Mtrs | 120 | 230 | 27600 | 4968 | 32568 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand- Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket Stand (M) | No. | 3 | 995 | 2985 | 537.3 | 3522.3 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Providing and fixing of "BREAK TO OBTAIN ACCESS" signage where it is necessary to break open a panel to create an exit or gain access to keys of an exit. The lettering / symbol shall be in white colour with green colour back ground. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 360 | 2550 | 918000 | 165240 | 1083240 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | Supply of 150mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 58.3333 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 18 | 1000 | 18000 | 3240 | 21240 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 3C x 1.5sqmm (M) | Mtrs | 120 | 230 | 27600 | 4968 | 32568 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | Supply of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands.Brand- Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (M) | Mtrs | 40 | 160 | 6400 | 1152 | 7552 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | Supply earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. Brand -Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (M) | Mtrs | 40 | 160 | 6400 | 1152 | 7552 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | Supply earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. Brand -Polycab | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | 2 Way 63mm,Fire Service inlet (M) | No. | 1 | 5000 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3.Brand -Essel/Mercry | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | 4 Way 63mm,Fire Service inlet (M) | No. | 3 | 7200 | 21600 | 3888 | 25488 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | Supply of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3.Brand -Essel/Mercry | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket (M) | No. | 4 | 3000 | 12000 | 2160 | 14160 | 0 | 2.8 | 8400 | 1512 | 9912 | 1.2 | 4248 | Supplying and installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket Stand (M) | No. | 1 | 639 | 639 | 115.02 | 754.02 | 0 | 0.7 | 447.3 | 80.52 | 527.82 | 0.3 | 226.2 | Supplying and installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Start/Stop push button station (M) | No. | 1 | 6640 | 6640 | 1195.2 | 7835.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of emergency start / stop push button station weather proof type for Booster pump | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Start/Stop push button station (M) | No. | 1 | 6640 | 6640 | 1195.2 | 7835.2 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of emergency start / stop push button station weather proof type for Booster pump | 0 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 0 | 600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | Dushant Gore |  | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | Dushant Gore | 14 Dec 2022
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 1027 | 550 | 564850 | 101673 | 666523 | 0 | 0 | 0 | 0 | 0 | 1027 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 260 | 600 | 156000 | 28080 | 184080 | 0 | 138.6 | 83160 | 14968.8 | 98128.8 | 121.4 | 85951.2 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 53.3077 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 260 | 600 | 156000 | 28080 | 184080 | 0 | 0 | 0 | 0 | 0 | 260 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 1788 | 200 | 357600 | 64368 | 421968 | 0 | 1002.4 | 200480 | 36086.4 | 236566.4 | 785.6 | 185401.6 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 56.0626 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 1788 | 200 | 357600 | 64368 | 421968 | 0 | 0 | 0 | 0 | 0 | 1788 | 0 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 357 | 250 | 89250 | 16065 | 105315 | 0 | 249.9 | 62475 | 11245.5 | 73720.5 | 107.1 | 31594.5 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 357 | 250 | 89250 | 16065 | 105315 | 0 | 0 | 0 | 0 | 0 | 357 | 0 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 1536 | 300 | 460800 | 82944 | 543744 | 0 | 945 | 283500 | 51030 | 334530 | 591 | 209214 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 61.5234 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 1536 | 300 | 460800 | 82944 | 543744 | 0 | 0 | 0 | 0 | 0 | 1536 | 0 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 79 | 600 | 47400 | 8532 | 55932 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | Brand-Jindal/Apollo.ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 79 | 600 | 47400 | 8532 | 55932 | 0 | 0 | 0 | 0 | 0 | 79 | 0 | Brand-Jindal/Apollo.ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | Double Hydrant Valve (L) | set | 25 | 1500 | 37500 | 6750 | 44250 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC of Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | Double Hydrant Valve (L) | set | 25 | 1500 | 37500 | 6750 | 44250 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC of Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | Orifice Plate (L) | No. | 25 | 200 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | Orifice Plate (L) | No. | 25 | 200 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Strainer "Y" (L) | No. | 1 | 450 | 450 | 81 | 531 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.ITC of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Strainer "Y" (L) | No. | 1 | 450 | 450 | 81 | 531 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.ITC of C.I.flanges "Y" type strainer with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Air Release Valve 25mm (L) | No. | 1 | 200 | 200 | 36 | 236 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete.The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Air Release Valve 25mm (L) | No. | 1 | 200 | 200 | 36 | 236 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete.The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 27 | 550 | 14850 | 2673 | 17523 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | Brand-Jindal/Apollo.ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Internal Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 27 | 550 | 14850 | 2673 | 17523 | 0 | 0 | 0 | 0 | 0 | 27 | 0 | Brand-Jindal/Apollo.ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 20 | 550 | 11000 | 1980 | 12980 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Brand-Jindal/Apollo.ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 20 | 550 | 11000 | 1980 | 12980 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Brand-Jindal/Apollo.ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Non Return Valve 100mm (L) | No. | 1 | 350 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.ITC of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I,of size and pressure rating as indicated below, with required flanges, nuts, bolts.The installation must be carried out as per the standard procedure of EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Non Return Valve 100mm (L) | No. | 1 | 350 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand-Zoloto/Kartar.ITC of swing check type non-return valves of approved makes confirming to IS:5312-2004 Part I,of size and pressure rating as indicated below, with required flanges, nuts, bolts.The installation must be carried out as per the standard procedure of EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(L) | No. | 2 | 350 | 700 | 126 | 826 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Brand-Zoloto/Kartar.ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Butterfly Valve 100mm-(L) | No. | 2 | 350 | 700 | 126 | 826 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Brand-Zoloto/Kartar.ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm.Cable. (L) | Mtrs | 175 | 55 | 9625 | 1732.5 | 11357.5 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | Brand-Polycab.ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 4C x 6 Sqmm Cu Arm.Cable. (L) | Mtrs | 175 | 55 | 9625 | 1732.5 | 11357.5 | 0 | 0 | 0 | 0 | 0 | 175 | 0 | Brand-Polycab.ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 3C x 1.5sqmm (L) | Mtrs | 120 | 45 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | Brand-Polycab.ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 3C x 1.5sqmm (L) | Mtrs | 120 | 45 | 5400 | 972 | 6372 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | Brand-Polycab.ITC of FRLS, PVC outer sheated steel armoured, aluminium / copper conductor, 1100v grade power cables with glands | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (L) | Mtrs | 40 | 45 | 1800 | 324 | 2124 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | ITC earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. The strip shall run on floor / ceiling / walls ,from the equipment to the nearest earth pit with neccessory accessories as require | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | 1C x 4 sqmm Cu FRLS (L) | Mtrs | 40 | 45 | 1800 | 324 | 2124 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | ITC earth wire of size 1C X 4 sq.mm Cu.FRLS of approved makes confirming to I.S. The strip shall run on floor / ceiling / walls ,from the equipment to the nearest earth pit with neccessory accessories as require | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | 2 Way 63mm,Fire Service inlet (L) | No. | 1 | 250 | 250 | 45 | 295 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | 4 way 63mm,Fire service inlet | No. | 3 | 250 | 750 | 135 | 885 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | ITC of fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves confirming to BS 5041:1975 Part 3. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | UTI Fire fight. (underground) | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket (L) | No. | 4 | 350 | 1400 | 252 | 1652 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Extinguishers - 1 No. | Fire Bucket Stand (L) | No. | 1 | 320 | 320 | 57.6 | 377.6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Pump Room Equipment | Start/Stop push button station (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Erection of emergency start / stop push button station weather proof type for Booster pump. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Pump Room Equipment | Start/Stop push button station (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Erection of emergency start / stop push button station weather proof type for Booster pump. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 9 | 600 | 5400 | 972 | 6372 | 0 | 3.64 | 2184 | 393.12 | 2577.12 | 5.36 | 3794.88 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 40.4444 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 440 | 750 | 330000 | 59400 | 389400 | 0 | 303.0307 | 227273.03 | 40909.14 | 268182.17 | 136.9693 | 121217.84 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 68.8706 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 9 | 450 | 4050 | 729 | 4779 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Butterfly Valve 150mm -(L) | No. | 4 | 300 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Hydrant Valve 63mm (L). | set | 8 | 1100 | 8800 | 1584 | 10384 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | Single headed (Type A) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet , gunmetal blank caps, chain and hand wheels etc complete. The installation must be carried out as per the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | Orifice Plate (L) | No. | 8 | 150 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | Design,installation,testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 13 | 850 | 11050 | 1989 | 13039 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass, with unions etc. complete. The installation must be carried out as per EIC | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 12 | 100 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 12 | 100 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 12 | 100 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Signage Board (L) | No. | 12 | 100 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 12 | 200 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Installation, testing, and commissioning portable Fire extinguisers ABC type fire extinguishers of 6 Kgs.Complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (L) | No. | 1616 | 200 | 323200 | 58176 | 381376 | 0 | 96.9 | 19380 | 3488.4 | 22868.4 | 1519.1 | 358507.6 | ITC Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 5.9963 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Pendent Sprinkler (L) | No. | 57 | 350 | 19950 | 3591 | 23541 | 0 | 0 | 0 | 0 | 0 | 57 | 0 | ITC Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Upright Sprinkler (L) | No. | 398 | 350 | 139300 | 25074 | 164374 | 0 | 11.4 | 3990 | 718.2 | 4708.2 | 386.6 | 159665.8 | ITC Early Suppression Fast Response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. | 2.8643 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Hydraulic Sprinkler 150mm (L) | No. | 7 | 2500 | 17500 | 3150 | 20650 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | ITC of Hydraulically operated sprinkler alarm valve with accesories; 2 nos of pressure guages,2 nos isolation valves.The installation must be carried out as per the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 1 | 350 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 12 | 350 | 4200 | 756 | 4956 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | ITC 150mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 857 | 550 | 471350 | 84843 | 556193 | 0 | 211.28 | 116204 | 20916.72 | 137120.72 | 645.72 | 419072.28 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 24.6534 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 1366 | 600 | 819600 | 147528 | 967128 | 0 | 205.515 | 123309 | 22195.62 | 145504.62 | 1160.485 | 821623.38 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 15.045 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 32mm (L) | No. | 21 | 200 | 4200 | 756 | 4956 | 0 | 19 | 3800 | 684 | 4484 | 2 | 472 | ITC 32mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 90.4762 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(L) | No. | 3 | 200 | 600 | 108 | 708 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | ITC portable fire extinguisers CO2 type fire extinguishers 4.5 KG.Fitted with gun metal union, high pressure CO2 gas cartridge & wall mounting bracket etc.complete. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket (L) | No. | 3 | 350 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | installation of Fire buckets round bottom type enamel painted ,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl - Fire Extinguisher & Signages | Fire Bucket Stand (L) | No. | 3 | 350 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | installation Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 360 | 750 | 270000 | 48600 | 318600 | 0 | 0 | 0 | 0 | 0 | 360 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 18 | 450 | 8100 | 1458 | 9558 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 8 | 200 | 1600 | 288 | 1888 | 0 | 6.65 | 1330 | 239.4 | 1569.4 | 1.35 | 318.6 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 83.125 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 100mm-(L) | No. | 1 | 350 | 350 | 63 | 413 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | Butterfly Valve 150mm -(L) | No. | 18 | 350 | 6300 | 1134 | 7434 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 3401 | 200 | 680200 | 122436 | 802636 | 0 | 269.25 | 53850 | 9693 | 63543 | 3131.75 | 739093 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 7.9168 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 32mm Dia. Heavy Grade Pipe | Mtrs | 1508 | 250 | 377000 | 67860 | 444860 | 0 | 250.952 | 62738 | 11292.84 | 74030.84 | 1257.048 | 370829.16 | ITC 32mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 16.6414 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 40mm Dia. Heavy Grade Pipe | Mtrs | 370 | 300 | 111000 | 19980 | 130980 | 0 | 76.05 | 22815.01 | 4106.7 | 26921.71 | 293.95 | 104058.29 | ITC 40mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 20.5541 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 223 | 400 | 89200 | 16056 | 105256 | 0 | 63.03 | 25212 | 4538.16 | 29750.16 | 159.97 | 75505.84 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 28.2646 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 65mm Dia. Heavy Grade Pipe | Mtrs | 153 | 450 | 68850 | 12393 | 81243 | 0 | 47.5311 | 21389 | 3850.02 | 25239.02 | 105.4689 | 56003.99 | ITC 65mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 31.0661 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 40 | 500 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 80mm-(L) | No. | 14 | 350 | 4900 | 882 | 5782 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Butterfly Valve 150mm -(L) | No. | 3 | 350 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | ITC of C.I. butterfly valves of approved makes as per I.S. 13095:1991,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Double Hydrant Valve (L) | set | 12 | 1500 | 18000 | 3240 | 21240 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Double headed (Type B) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm / 100 mm dia flanged inlet | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Hydrant Valve 63mm (L). | set | 14 | 1250 | 17500 | 3150 | 20650 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | ITC Single headed (Type A) hydrant valve as per IS 5290:1993, made of stainless steel with 63mm dia outlets & 80mm dia flanged inlet , gunmetal blank caps, chain and hand wheels etc.complete.The installation must be carried out as per EIC | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Orifice Plate (L) | No. | 14 | 200 | 2800 | 504 | 3304 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 80mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | Orifice Plate (L) | No. | 12 | 200 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 12 | 0 | Design,installation, testing and commissioning of stainless steel single stage single hole restriction 100mm orifice plate at the inlet of landing valves confirming to ASME B16.The installation must be carried out as per EIC | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 16.1 | 5635 | 1014.3 | 6649.3 | 8.9 | 3675.7 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass,with unions etc. complete. The installation must be carried out as per EIC. | 64.4 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Drain Valve 25 mm (L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Test and drain valve assembly with K factor 5.6 unless otherwise mentioned in the drawings;made of brass,with unions etc. complete. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 25mm Dia. Heavy Grade Pipe | Mtrs | 24 | 200 | 4800 | 864 | 5664 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | ITC 25mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 373 | 500 | 186500 | 33570 | 220070 | 0 | 176.15 | 88075 | 15853.5 | 103928.5 | 196.85 | 116141.5 | ITC 80mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 47.2252 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 13 | 550 | 7150 | 1287 | 8437 | 0 | 0 | 0 | 0 | 0 | 13 | 0 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 466 | 600 | 279600 | 50328 | 329928 | 0 | 0 | 0 | 0 | 0 | 466 | 0 | ITC 150mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "BREAK TO OBTAIN ACCESS" signage confirming to I.S. 12349:1988.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 25 | 100 | 2500 | 450 | 2950 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 25 | 100 | 2500 | 450 | 2950 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Fixing of "FIRE HOSE REEL" signage confirming to I.S. 12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground. Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "FIRE EXTINGUISHER" signage confirming to I.S.12349:1988 at each landing valve location.The symbol size shall be 7.5 cm in white colour with red colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Air Release Valve 25mm (L) | No. | 3 | 220 | 660 | 118.8 | 778.8 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Air Release Valve 25mm (L) | No. | 3 | 220 | 660 | 118.8 | 778.8 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | installation, testing, and commissioning 25mm dia Automatic air release valve with unions etc. complete. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 26 | 215 | 5590 | 1006.2 | 6596.2 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | ITC portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Fire Extinguisher ABC 6Kg (L) | No. | 26 | 215 | 5590 | 1006.2 | 6596.2 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | ITC portable Fire extinguisers ABC type fire extinguishers of 6 Kgs. complete, confirming to (IS:13849.discontinued and replaced with I.S. 15683:2006) | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Fire Extinguisher & Signages | Signage Board (L) | No. | 26 | 100 | 2600 | 468 | 3068 | 0 | 0 | 0 | 0 | 0 | 26 | 0 | Fixing of "EMERGENCY EXIT" signage confirming to I.S. 12349:1988 at each fire stair enclosure on every floor.The lettering / symbol shall be in white colour with green colour back ground.Signage shall be square size. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 1340 | 200 | 268000 | 48240 | 316240 | 0 | 844.2 | 168840 | 30391.2 | 199231.2 | 495.8 | 117008.8 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 63 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 1340 | 200 | 268000 | 48240 | 316240 | 0 | 0 | 0 | 0 | 0 | 1340 | 0 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 68° C temperature rating K80.The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 200 | 200 | 40000 | 7200 | 47200 | 0 | 128.8 | 25760 | 4636.8 | 30396.8 | 71.2 | 16803.2 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 64.4 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Side Wall Sprinkler (L) | No. | 200 | 200 | 40000 | 7200 | 47200 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | ITC of Standard response sprinkler quartzoid bulb type with screwed end connection with 79° C temperature rating K80. The sprinkler heads shall confirm to I.S. 9972:2002. The installation must be carried out as per EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Vane Type Water Flow (L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC 100mm Vane type water flow.The Flow shall be UL Listed,The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 100 | 200 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Brass Ball Valve 40mm (L) | No. | 100 | 200 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | ITC 40mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Brass Ball Valve 50mm (L) | No. | 100 | 200 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | ITC 50mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Brass Ball Valve 50mm (L) | No. | 100 | 200 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 100 | 0 | ITC 50mm Brass Ball Valve standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness. The installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | Butterfly Valve 100mm-(L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 16.1 | 5635 | 1014.3 | 6649.3 | 8.9 | 3675.7 | ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC | 64.4 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | Butterfly Valve 100mm-(L) | No. | 25 | 350 | 8750 | 1575 | 10325 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | ITC of C.I. butterfly valves of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts. The installation must be carried out as per the standard procedure as directed by the EIC | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 302 | 400 | 120800 | 21744 | 142544 | 0 | 211.4 | 84560 | 15220.8 | 99780.8 | 90.6 | 42763.2 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 70 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Building Automatic Sprinkler System | SITC GI- 50mm Dia. Heavy Grade Pipe | Mtrs | 302 | 400 | 120800 | 21744 | 142544 | 0 | 0 | 0 | 0 | 0 | 302 | 0 | ITC 50mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 0 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 591 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Building Automatic Sprinkler System | SITC GI- 100mm Dia. Heavy Grade Pipe | Mtrs | 1027 | 550 | 564850 | 101673 | 666523 | 0 | 544.2819 | 299355.02 | 53430.3 | 352785.32 | 482.7182 | 313737.68 | ITC 100mm of G.I.heavy grade pipes and fittings including painting with Fire Red colour confirming to I.S.5:1978 for piping in sprinkler application.installation must be carried out as per the standard procedure as directed by the EIC. | 52.9973 |  | Dushant Gore | Swapnil Erande | construction open | 14 Dec 2022 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Electrical Motor Driven Pump (M) | No. | 2 | 1375000 | 2750000 | 495000 | 3245000 | 0 | 1.4 | 1925000 | 346500 | 2271500 | 0.6 | 973500 | Electrical motor driven main pump of approved makes & horizontal centrifugal multi stage multi outlet type and capable to deliver from 1st Take off 171Cum/Hr at 106mwc and 171 Cum/Hr at 150 mwc from 2nd take off (Make-Lubi/KSB/Kirlosakar) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 25mm (M) | No. | 4 | 1250 | 5000 | 900 | 5900 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Ball valve 25mm PN 16 rating of approved makes confirming to I.S. 9890:1981 standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness (make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 50mm (M) | No. | 10 | 1550 | 15500 | 2790 | 18290 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Ball valve 50mm PN 16 rating of approved makes confirming to I.S. 9890:1981 standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness (make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Switch (M) | No. | 10 | 2350 | 23500 | 4230 | 27730 | 0 | 7 | 16450 | 2961 | 19411 | 3 | 8319 | Pressure switches of approved makes of suitable range for pumpsets. The quoted rates shall include needle valves, fittings like unions / collars / reducers etc. (Make- Danfors) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 150mm (M) | No. | 6 | 10000 | 60000 | 10800 | 70800 | 0 | 4.2 | 42000 | 7560 | 49560 | 1.8 | 21240 | Swing check type non-return valves 150mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 200mm (M) | No. | 2 | 16500 | 33000 | 5940 | 38940 | 0 | 1.4 | 23100 | 4158 | 27258 | 0.6 | 11682 | Swing check type non-return valves 200mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 80mm-(M) | No. | 2 | 7000 | 14000 | 2520 | 16520 | 0 | 0.95 | 6650 | 1197 | 7847 | 1.05 | 8673 | C.I. butterfly valves 80mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 47.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(M) | No. | 6 | 7500 | 45000 | 8100 | 53100 | 0 | 6 | 45000 | 8100 | 53100 | 0 | 0 | C.I. butterfly valves 100mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 100 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(M) | No. | 14 | 12000 | 168000 | 30240 | 198240 | 0 | 9.8 | 117600 | 21168 | 138768 | 4.2 | 59472 | C.I. butterfly valves 150mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 200mm (M) | No. | 2 | 25500 | 51000 | 9180 | 60180 | 0 | 1.4 | 35700 | 6426 | 42126 | 0.6 | 18054 | C.I. butterfly valves 200mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 21 | 2200 | 46200 | 8316 | 54516 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 150mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe (M) | Mtrs | 29 | 3400 | 98600 | 17748 | 116348 | 0 | 20.3 | 69020 | 12423.6 | 81443.6 | 8.7 | 34904.4 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 200mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI Pipe C Class 250mm dia-(M) | Mtrs | 10 | 4400 | 44000 | 7920 | 51920 | 0 | 7 | 30800 | 5544 | 36344 | 3 | 15576 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 250mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Relief Valve (M) | No. | 1 | 2300 | 2300 | 414 | 2714 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Pressure relief valve 20mm dia. UL / FM approved, with required threaded adaptors, nuts, bolts. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Foot Valve 150 mm (M) | No. | 1 | 17500 | 17500 | 3150 | 20650 | 0 | 0.7 | 12250 | 2205 | 14455 | 0.3 | 6195 | Foot valves 150mm with strainer of approved makes confirming to IS:4038-1986, reaffirmed 2005, with required flanges, nuts, bolts. | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 100mm (M) | No. | 4 | 6500 | 26000 | 4680 | 30680 | 0 | 3.1 | 20150 | 3627 | 23777 | 0.9 | 6903 | Swing check type non-return valves 100mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 77.5 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables (M) | Mtrs | 20 | 350 | 7000 | 1260 | 8260 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 12Cx1.5sq.mm for Diesel Engine Panel ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 150 x 50mm (M) | Mtrs | 20 | 650 | 13000 | 2340 | 15340 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports,anchor fasteners etc. complete.Maximum height of suspension shall not exceed 500 mm.Size of the tray shall be 150 mm x 50 mm | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 20 x 3mm GI Strip (M) | Mtrs | 30 | 400 | 12000 | 2160 | 14160 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | GI earthing strips of size 20mmx3mm of approved makes confirming to I.S. 3043:1987. The strip shall run on floor / ceiling / walls , from the equipment to the nearest earth pit with neccessory accessories as required | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 25 NB-(M) | Mtrs | 7 | 350 | 2450 | 441 | 2891 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 25mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 14 | 1000 | 14000 | 2520 | 16520 | 0 | 9.8 | 9800 | 1764 | 11564 | 4.2 | 4956 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 80mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 100 NB-(M) | Mtrs | 14 | 1500 | 21000 | 3780 | 24780 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 100mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Diesel Engine Driven Pump (M) | No. | 1 | 1717410 | 1717410 | 309133.8 | 2026543.8 | 0 | 0.7 | 1202187 | 216393.66 | 1418580.66 | 0.3 | 607963.14 | Diesel engine driven stand-by pump of approved makes & horizontal centrifugal multi stage multi outlet type pump and capable to deliver from 1st Take off 171Cum/Hr at 106 mwc and 171 Cum/Hr at 150 mwc from 2nd take off.(Make-Lubi/KSB/Kirlosakar) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Jockey Pump (M) | No. | 2 | 205000 | 410000 | 73800 | 483800 | 0 | 1.4 | 287000 | 51660 | 338660 | 0.6 | 145140 | Electrical motor driven main pump of approved makes & horizontal centrifugal multi stage multi outlet type pump and capable to deliver from 1st Take off 10.8Cum/Hr at 106 mwc and 10.8 Cum/Hr at 150 mwc from 2nd take off.(Hydrant Jockey + Sprinkler Jockey) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Control Panel (M) | No. | 1 | 410000 | 410000 | 73800 | 483800 | 0 | 0.7 | 287000 | 51660 | 338660 | 0.3 | 145140 | Main compartmentalised common control panel for electrical motor driven pumps and diesel engine driven pumps. | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables (M) | Mtrs | 40 | 2950 | 118000 | 21240 | 139240 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx70 sq.mm for main pumps ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables (M) | Mtrs | 40 | 1150 | 46000 | 8280 | 54280 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx10sq.mm jockey pump (Alu. Armoured) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables (M) | Mtrs | 50 | 95 | 4750 | 855 | 5605 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 2Cx1.5sq.mm for instrumentation ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 100 NB-(M) | Mtrs | 16 | 1500 | 24000 | 4320 | 28320 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 100mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe (M) | Mtrs | 15 | 2200 | 33000 | 5940 | 38940 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 150mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe (M) | Mtrs | 1 | 3400 | 3400 | 612 | 4012 | 0 | 0.7 | 2380 | 428.4 | 2808.4 | 0.3 | 1203.6 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 200mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI Pipe C Class 250mm dia-(M) | Mtrs | 2 | 4400 | 8800 | 1584 | 10384 | 0 | 1.4 | 6160 | 1108.8 | 7268.8 | 0.6 | 3115.2 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 250mm dia (Make-Apollo/Jindal) | 70 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(M) | No. | 4 | 7500 | 30000 | 5400 | 35400 | 0 | 2.8 | 21000 | 3780 | 24780 | 1.2 | 10620 | C.I. butterfly valves 100mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 70 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(M) | No. | 4 | 12000 | 48000 | 8640 | 56640 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | C.I. butterfly valves 150mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Sprinkler Alarm Valve 150mm dia (M) | set | 7 | 43500 | 304500 | 54810 | 359310 | 0 | 2.1 | 91350 | 16443 | 107793 | 4.9 | 251517 | Hydraulically operated sprinkler alarm valve with accesories | 30 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Rate Diff. Control Panel (M) | No. | 1 | 290000 | 290000 | 52200 | 342200 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Main compartmentalised common control panel for electrical motor driven pumps and diesel engine driven pumps. | 70 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables (M) | Mtrs | 10 | 2950 | 29500 | 5310 | 34810 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 3.5Cx70 sq.mm for main pumps ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables (M) | Mtrs | 40 | 1150 | 46000 | 8280 | 54280 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx10sq.mm jockey pump (Alu. Armoured) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables (M) | Mtrs | 150 | 95 | 14250 | 2565 | 16815 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 2Cx1.5sq.mm for instrumentation ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables (M) | Mtrs | 10 | 350 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 12Cx1.5sq.mm for Diesel Engine Panel ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Poly | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Service Inlet Connection (M) | set | 6 | 5200 | 31200 | 5616 | 36816 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Fire service inlet connection of 3 way with 3 nos. 63mm dia instantaneous coupling with built in non return valves(Make-Essel/Mercurry). | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Air Release Valve 25mm (M) | No. | 2 | 1450 | 2900 | 522 | 3422 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 25mm dia Automatic air release valve of approved makes with unions etc. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Signage Board (M) | No. | 10 | 225 | 2250 | 405 | 2655 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | This sign shall be used to Indicate the system for which pipe is used. It shall be accompanied: by an arrow.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Extinguisher (M) | No. | 1 | 6700 | 6700 | 1206 | 7906 | 0 | 0.7 | 4690 | 844.2 | 5534.2 | 0.3 | 2371.8 | Portable fire extinguisers Mechanical foam type fire extinguishers 50 Lts. capacity with intial filling in brand new cylinder with powder coated finish, fitted with gun metal union, high pressure CO2 gas cartridge,etc | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Bucket (M) | No. | 4 | 1000 | 4000 | 720 | 4720 | 0 | 2.8 | 2800 | 504 | 3304 | 1.2 | 1416 | Fire buckets round bottom type enamel painted,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Bucket Stand (M) | No. | 1 | 2500 | 2500 | 450 | 2950 | 0 | 0.7 | 1750 | 315 | 2065 | 0.3 | 885 | Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Guage 100mm (M) | No. | 20 | 3200 | 64000 | 11520 | 75520 | 0 | 9.8 | 31360 | 5644.8 | 37004.8 | 10.2 | 38515.2 | Glyserene filled pressure gauges of approved makes and of 0-25 bar range , dial size 100 mm accuracy class 1.6, IP 65 class include isolation valves, siphon tubes, needle valves with inlet connections of required sizes, with unions, washers, gaskets etc.(H Guru) | 49 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (M). | Mtrs | 24 | 2400 | 57600 | 10368 | 67968 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | Exhaust pipe 100mm for Diesel engine of M.S. medium grade with mineral wool insulation and aluminum sheet for protection | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Air Vessel (M) | No. | 2 | 27000 | 54000 | 9720 | 63720 | 0 | 1.4 | 37800 | 6804 | 44604 | 0.6 | 19116 | Air Vessel with required standard connections & required it supports,anchor fastners & nut bolts etc.(Dia 300 x 1200mm Height) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Rotameter (M) | No. | 1 | 10500 | 10500 | 1890 | 12390 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Rotameter of approved make of flow range 2.5 to 40000 lph of approved make etc complete | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 2 Way 63mm,Fire Service inlet (M) | No. | 1 | 4200 | 4200 | 756 | 4956 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves (Make-Essel/Mercurry) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 4 Way 63mm,Fire Service inlet (M) | No. | 2 | 7200 | 14400 | 2592 | 16992 | 0 | 1.4 | 10080 | 1814.4 | 11894.4 | 0.6 | 5097.6 | Fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves (Make-Essel/Mercurry). | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | CI Strainer 150 mm (M) | No. | 3 | 8900 | 26700 | 4806 | 31506 | 0 | 2.1 | 18690 | 3364.2 | 22054.2 | 0.9 | 9451.8 | C.I. "Basket" type strainer 150mm nominal dia with SS mesh of approved makes, confirming to ASME 31 with suitable flanges, nuts, bolts, gaskets etc.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Strainer "Y" (M) | No. | 2 | 5900 | 11800 | 2124 | 13924 | 0 | 1.4 | 8260 | 1486.8 | 9746.8 | 0.6 | 4177.2 | C.I.flanges "Y" type strainer 100mm with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 635 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | C.I.Basket Strainer 200mm (M) | No. | 2 | 29200 | 58400 | 10512 | 68912 | 0 | 1.4 | 40880 | 7358.4 | 48238.4 | 0.6 | 20673.6 | Sluice valves 200mm of approved makes rating confirming to IS:14846:2000, for suction side of the pumps and rising spindle type with flanges, bolts, nuts washers, gaskets etc.(make-Kartar/Quinn) | 70 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 100 NB-(L) | Mtrs | 16 | 500 | 8000 | 1440 | 9440 | 0 | 0 | 0 | 0 | 0 | 16 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 100mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 15 | 600 | 9000 | 1620 | 10620 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 150mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe | Mtrs | 1 | 800 | 800 | 144 | 944 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 200mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI Pipe C Class 250mm dia-(L) | Mtrs | 2 | 1000 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 250mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(L) | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | C.I. butterfly valves 100mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(L) | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | C.I. butterfly valves 150mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Bucket Stand (L) | No. | 1 | 450 | 450 | 81 | 531 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Fire bucket stand fabricated by MS angles to install 4 Nos. of buckets. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Sprinkler Alarm Valve 150mm dia (L) | set | 7 | 1500 | 10500 | 1890 | 12390 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | Hydraulically operated sprinkler alarm valve with accesories | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables | Mtrs | 10 | 50 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 3.5Cx70 sq.mm for main pumps ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables | Mtrs | 40 | 50 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx10sq.mm jockey pump (Alu. Armoured) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables | Mtrs | 150 | 50 | 7500 | 1350 | 8850 | 0 | 0 | 0 | 0 | 0 | 150 | 0 | 2Cx1.5sq.mm for instrumentation ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 1 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables | Mtrs | 10 | 50 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | 12Cx1.5sq.mm for Diesel Engine Panel ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Poly | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 4 way 63mm,Fire service inlet | No. | 2 | 250 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Fire service inlet connection of 4 way with 4 nos. 63mm dia instantaneous coupling with built in non return valves (Make-Essel/Mercurry). | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | UTI Fire fight. (underground) | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Service Inlet Connection (L) | set | 6 | 250 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Fire service inlet connection of 3 way with 3 nos. 63mm dia instantaneous coupling with built in non return valves(Make-Essel/Mercurry). | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Air Release Valve 25mm (L) | No. | 2 | 150 | 300 | 54 | 354 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 25mm dia Automatic air release valve of approved makes with unions etc. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Signage Board (L) | No. | 10 | 100 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | This sign shall be used to Indicate the system for which pipe is used. It shall be accompanied: by an arrow.The lettering / symbol shall be in white colour with green colour back ground. Signage shall be square size. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Exstingusher (L) | No. | 1 | 150 | 150 | 27 | 177 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Portable fire extinguisers Mechanical foam type fire extinguishers 50 Lts. capacity with intial filling in brand new cylinder with powder coated finish, fitted with gun metal union, high pressure CO2 gas cartridge,etc | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Fire Bucket (L) | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Fire buckets round bottom type enamel painted,white inside & red out side Letter "FIRE" in black out side and handle with mounting bracket. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Switch (L) | No. | 10 | 120 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Pressure switches of approved makes of suitable range for pumpsets. The quoted rates shall include needle valves, fittings like unions / collars / reducers etc. (Make- Danfors) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Guage 100mm (L) | No. | 20 | 120 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | Glyserene filled pressure gauges of approved makes and of 0-25 bar range , dial size 100 mm accuracy class 1.6, IP 65 class include isolation valves, siphon tubes, needle valves with inlet connections of required sizes, with unions, washers, gaskets etc.(H Guru) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Exhaust Pipe 100mm (L). | Mtrs | 24 | 600 | 14400 | 2592 | 16992 | 0 | 0 | 0 | 0 | 0 | 24 | 0 | Exhaust pipe 100mm for Diesel engine of M.S. medium grade with mineral wool insulation and aluminum sheet for protection | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Air Vessel (L) | No. | 2 | 1100 | 2200 | 396 | 2596 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Air Vessel with required standard connections & required it supports,anchor fastners & nut bolts etc.(Dia 300 x 1200mm Height) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Rotameter | No. | 1 | 1500 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Rotameter of approved make of flow range 2.5 to 40000 lph of approved make etc complete | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 2 Way 63mm,Fire Service inlet (L) | No. | 1 | 250 | 250 | 45 | 295 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Fire service inlet connection of 2 way with 2 nos. 63mm dia instantaneous coupling with built in non return valves (Make-Essel/Mercurry). | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 200mm (L) | No. | 2 | 250 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | C.I. butterfly valves 200mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | CI Strainer 150 mm (L) | No. | 3 | 320 | 960 | 172.8 | 1132.8 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | C.I. "Basket" type strainer 150mm nominal dia with SS mesh of approved makes, confirming to ASME 31 with suitable flanges, nuts, bolts, gaskets etc.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Strainer "Y" (L) | No. | 2 | 320 | 640 | 115.2 | 755.2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | C.I.flanges "Y" type strainer 100mm with SS mesh of approved makes, confirming to ASME 31 with suitable flanges nuts, bolts, gaskets etc.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | C.I.Basket Strainer 200mm (L) | No. | 2 | 320 | 640 | 115.2 | 755.2 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Sluice valves 200mm of approved makes rating confirming to IS:14846:2000, for suction side of the pumps and rising spindle type with flanges, bolts, nuts washers, gaskets etc.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 25mm (L) | No. | 4 | 120 | 480 | 86.4 | 566.4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Ball valve 25mm PN 16 rating of approved makes confirming to I.S. 9890:1981 standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness (make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Brass Ball Valve 50mm (L) | No. | 10 | 120 | 1200 | 216 | 1416 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Ball valve 50mm PN 16 rating of approved makes confirming to I.S. 9890:1981 standards with all required accessories & jointing material like threaded adaptors, unions and pressure testing for water tightness (make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 100mm (L) | No. | 4 | 250 | 1000 | 180 | 1180 | 0 | 0.952 | 238 | 42.84 | 280.84 | 3.048 | 899.16 | Swing check type non-return valves 100mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 23.8 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 150mm (L) | No. | 6 | 250 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Swing check type non-return valves 150mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Non Return Valve 200mm (L) | No. | 2 | 250 | 500 | 90 | 590 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Swing check type non-return valves 200mm of approved makes confirming to IS:5312-2004 Part I, of sizes and pressure rating as indicated below, with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 80mm-(L) | No. | 2 | 250 | 500 | 90 | 590 | 0 | 0.952 | 238 | 42.84 | 280.84 | 1.048 | 309.16 | C.I. butterfly valves 80mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 47.6 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 100mm-(L) | No. | 6 | 250 | 1500 | 270 | 1770 | 0 | 5.7 | 1425 | 256.5 | 1681.5 | 0.3 | 88.5 | C.I. butterfly valves 100mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 95 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Butterfly Valve 150mm -(L) | No. | 14 | 250 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | C.I. butterfly valves 150mm of approved makes confirming to I.S. 13095:1991, slim seal standard lever operated type with required flanges, nuts, bolts.(make-Kartar/Quinn) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 100 NB-(L) | Mtrs | 14 | 500 | 7000 | 1260 | 8260 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 100mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 150mm Dia. Heavy Grade Pipe | Mtrs | 21 | 600 | 12600 | 2268 | 14868 | 0 | 0 | 0 | 0 | 0 | 21 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 150mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 200mm Dia. Heavy Grade Pipe | Mtrs | 29 | 800 | 23200 | 4176 | 27376 | 0 | 0 | 0 | 0 | 0 | 29 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 200mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI Pipe C Class 250mm dia-(L) | Mtrs | 10 | 1000 | 10000 | 1800 | 11800 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 250mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Pressure Relief Valve (L) | No. | 1 | 250 | 250 | 45 | 295 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Pressure relief valve 20mm dia. UL / FM approved, with required threaded adaptors, nuts, bolts. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Foot Valve 150 mm (L) | No. | 1 | 320 | 320 | 57.6 | 377.6 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Foot valves 150mm with strainer of approved makes confirming to IS:4038-1986, reaffirmed 2005, with required flanges, nuts, bolts. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 2 C X 1.5 sqmm Cables | Mtrs | 50 | 50 | 2500 | 450 | 2950 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | 2Cx1.5sq.mm for instrumentation ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 12 C X 1.5 sqmm Cables | Mtrs | 20 | 50 | 1000 | 180 | 1180 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | 12Cx1.5sq.mm for Diesel Engine Panel ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | G.I.Cable tray 150 x 50mm (L) | Mtrs | 20 | 120 | 2400 | 432 | 2832 | 0 | 0 | 0 | 0 | 0 | 20 | 0 | G.I. sheet cable tray of approved makes with neccessory angle iron suspension supports,anchor fasteners etc. complete.Maximum height of suspension shall not exceed 500 mm.Size of the tray shall be 150 mm x 50 mm | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | 20 x 3mm GI Strip (L) | Mtrs | 30 | 120 | 3600 | 648 | 4248 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | GI earthing strips of size 20mmx3mm of approved makes confirming to I.S. 3043:1987. The strip shall run on floor / ceiling / walls , from the equipment to the nearest earth pit with neccessory accessories as required | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | GI Pipe C Class 25 NB-(L) | Mtrs | 7 | 150 | 1050 | 189 | 1239 | 0 | 0 | 0 | 0 | 0 | 7 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 25mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe | Mtrs | 14 | 425 | 5950 | 1071 | 7021 | 0 | 0 | 0 | 0 | 0 | 14 | 0 | G.I. heavy grade pipes and fittings confirming to IS 1239:2004 Pt -I & I.S. 1239:2011 Pt-II respectively of approved makes including painting with Fire Red colour confirming to I.S. 5:1978 in following sizes 80mm dia (Make-Apollo/Jindal) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Electrical Motor Driven Pump (L) | No. | 2 | 30000 | 60000 | 10800 | 70800 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Electrical motor driven main pump of approved makes & horizontal centrifugal multi stage multi outlet type and capable to deliver from 1st Take off 171Cum/Hr at 106mwc and 171 Cum/Hr at 150 mwc from 2nd take off (Make-Lubi/KSB/Kirlosakar) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Diesel Engine Driven Pump | No. | 1 | 35000 | 35000 | 6300 | 41300 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Diesel engine driven stand-by pump of approved makes & horizontal centrifugal multi stage multi outlet type pump and capable to deliver from 1st Take off 171Cum/Hr at 106 mwc and 171 Cum/Hr at 150 mwc from 2nd take off.(Make-Lubi/KSB/Kirlosakar) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SITC Jockey Pump (L) | No. | 2 | 15000 | 30000 | 5400 | 35400 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Electrical motor driven main pump of approved makes & horizontal centrifugal multi stage multi outlet type pump and capable to deliver from 1st Take off 10.8Cum/Hr at 106 mwc and 10.8 Cum/Hr at 150 mwc from 2nd take off.(Hydrant Jockey + Sprinkler Jockey) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | Control Panel (L) | No. | 1 | 20000 | 20000 | 3600 | 23600 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Main compartmentalised common control panel for electrical motor driven pumps and diesel engine driven pumps. | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 70 sqmm Cables | Mtrs | 40 | 50 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx70 sq.mm for main pumps ( Copper) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 636 | 0 | 10 Mar 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Pumproom Fire Equipment - 1 No. | SLTC- PVC-FRLS- 3.5 C X 10 sqmm Cables | Mtrs | 40 | 50 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | 3.5Cx10sq.mm jockey pump (Alu. Armoured) FRLS, PVC outer sheated steel armoured, aluminium/copper conductor,1100v grade power cables with glands of approved makes.The cables shall be laid in tray/hume pipe /in trenches/on walls/floor etc.(make- Polycab) | 0 |  | ADITYA CHOUGULE | Swapnil Erande | construction open | 17 Mar 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Digital Signal Based Voice Alarm Controller (L) | No. | 1 | 15000 | 15000 | 2700 | 17700 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of 8 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 8 zone paging station) Local Control Panel is 8 speaker circuit digital voice alarm controller.Make- Ravel,Model-Escape-250W | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Digital Amplifier (L) | No. | 1 | 12500 | 12500 | 2250 | 14750 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of 480W Power Amplifier with Rated output wattage - 480W Make- Ravel,Model-RE-250 | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 6W Ceiling Speakers (L) | No. | 17 | 350 | 5950 | 1071 | 7021 | 2.5 | 0 | 0 | 0 | 0 | 17 | 0 | ITC of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps Make- Ravel,Model-RE-LS 6C | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Back Box (L) | No. | 17 | 100 | 1700 | 306 | 2006 | 2.5 | 0 | 0 | 0 | 0 | 17 | 0 | ITC of back box for 6 Watt Ceiling Speakers.Make- STD | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Manual call point (L) | No. | 5 | 300 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 | ITC of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool. Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 M | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Conventional Sounder cum Strobe (L) | No. | 5 | 300 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 | ITC of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool. Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 M | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm cable for PA System (L) | Mtrs | 1508 | 40 | 60320 | 10857.6 | 71177.6 | 2.5 | 660.45 | 26418 | 4755.24 | 31173.24 | 847.55 | 40004.36 | Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval.Make-Ploycab | 43.7964 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 50 | 40 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 50 | 0 | Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated armoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval.Make-Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Talkback Panel (L) | No. | 1 | 12000 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of 8 Zone Talkback Panel.Make- Ravel,Model-EK 740 | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Talk Back System (L) | No. | 10 | 250 | 2500 | 450 | 2950 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 | ITC of Fire Fighter (talk back) jack module.Make- Ravel,Model-EK 750J | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Fire Alarm Panel (L) | No. | 1 | 20000 | 20000 | 3600 | 23600 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC Flush or Surface Mounting Modularized Panel with 4 loops.Having inbuilt 1 loops,Maximum 4 Loops (4 with Network ),Max Capacity with 4 Loops =1524 Addressable Devices. Make-Ravel ,Model-Avani-LCS | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Fire Repeater Panel (L) | No. | 1 | 5000 | 5000 | 900 | 5900 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of Network Active Repeater with Full Control, SemiFlush or Wall Mounting, Includes RS485 Class A Network Card (LPCB / UL, FM Approved).Make- Ravel,Model-RE-517 RP | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable smoke detector (L) | No. | 105 | 300 | 31500 | 5670 | 37170 | 2.5 | 0 | 0 | 0 | 0 | 105 | 0 | ITC of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor (LPCB / UL, FM Approved).Make- Ravel,Model-RE-317D SL | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Heat Detector (L) | No. | 5 | 300 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 5 | 0 | ITC of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor (LPCB / UL, FM Approved).Make- Ravel,Model-RE-317D HL | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Fault Isolator Base / Module (L) | No. | 10 | 300 | 3000 | 540 | 3540 | 2.5 | 0 | 0 | 0 | 0 | 10 | 0 | ITC of Zonal Short Circuit Loop Isolator, (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 MI | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Control Module (L) | No. | 1 | 300 | 300 | 54 | 354 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power.active Modes - Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 MC | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 32 NB | Mtrs | 60 | 352.5 | 21150 | 3807 | 24957 | 0 | 52.6298 | 18552 | 3339.36 | 21891.36 | 7.3702 | 3065.64 | Installation And Removing G.I.Pipe 32 mm for Rework | 87.7163 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 25 NB | Mtrs | 300 | 282 | 84600 | 15228 | 99828 | 0 | 280.1525 | 79003 | 14220.54 | 93223.54 | 19.8475 | 6604.46 | Installation And Removing G.I.Pipe 25 mm for Rework | 93.3842 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 80mm-(L) | No. | 2 | 350 | 700 | 126 | 826 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | C.I.Butterfly Valve 80 mm- Kartar | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 40mm (L) | No. | 6 | 300 | 1800 | 324 | 2124 | 0 | 4.75 | 1425 | 256.5 | 1681.5 | 1.25 | 442.5 | C.I.Butterfly Valve 40 mm- Kartar | 79.1667 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Non Return Valve 100mm (L) | No. | 2 | 350 | 700 | 126 | 826 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Installation And Removing G.I.Pipe 100 mm for Rework | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 100 NB | Mtrs | 90 | 775.5 | 69795 | 12563.1 | 82358.1 | 0 | 80.1805 | 62179.97 | 11192.4 | 73372.37 | 9.8195 | 8985.73 | Sprinkler Alarm Valve 150 mm dia- HD | 89.0894 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 50 NB | Mtrs | 30 | 564 | 16920 | 3045.6 | 19965.6 | 0 | 21.8493 | 12323.01 | 2218.14 | 14541.15 | 8.1507 | 5424.45 | Installation And Removing G.I.Pipe 50 mm for Rework | 72.831 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Removing & Refixing GI Pipe 40 NB | Mtrs | 12 | 423 | 5076 | 913.68 | 5989.68 | 0 | 8.7399 | 3697 | 665.46 | 4362.46 | 3.2601 | 1627.22 | Installation And Removing G.I.Pipe 40 mm for Rework | 72.8325 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Signage Fire Hose Reel (L) | No. | 5 | 329 | 1645 | 296.1 | 1941.1 | 0 | 3.7994 | 1249.99 | 225 | 1474.99 | 1.2006 | 466.11 | Fire Hose Reel with 30 mtrs rubber hose- Essel/Padma | 75.988 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Fire Extinguisher ABC 4Kg (L) | No. | 6 | 188 | 1128 | 203.04 | 1331.04 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | ABC Type Fire Extinguisher 4 Kg- Mercury | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(L) | No. | 2 | 200 | 400 | 72 | 472 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | CO2 Type Extinguisher 4.5 kg- Mercury | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Air Release Valve 25mm (L) | No. | 2 | 200 | 400 | 72 | 472 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Air Release Valve- STD | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 150mm -(L) | No. | 6 | 300 | 1800 | 324 | 2124 | 0 | 0.95 | 285 | 51.3 | 336.3 | 5.05 | 1787.7 | C.I.Butterfly Valve 150 mm - Kartar | 15.8333 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 100mm-(L) | No. | 6 | 350 | 2100 | 378 | 2478 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | C.I.Butterfly Valve 100 mm- Kartar | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Upright (L) | No. | 30 | 350 | 10500 | 1890 | 12390 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Upright Sprinkler 68 Deg- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Side wall (L) | No. | 10 | 200 | 2000 | 360 | 2360 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Sidewall Sprinkler 68 Deg - Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Rossete Plate (L) | No. | 370 | 45 | 16650 | 2997 | 19647 | 0 | 204.2667 | 9192 | 1654.56 | 10846.56 | 165.7333 | 8800.44 | Rossete plate- STD | 55.2072 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler Alarm Valve 150mm dia (L) | set | 1 | 1500 | 1500 | 270 | 1770 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Sprinkler Alarm Valve 150 mm dia- HD | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Signage Fire Hose Reel (L) | No. | 0 | 1034 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 10 Aug 2023 |  | No category | Cancelled | MONALI CHAUDHAR | 24 Jan 2024
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | GI Single Fire Hose Box (L) | No. | 5 | 1034 | 5170 | 930.6 | 6100.6 | 0 | 4.75 | 4911.5 | 884.08 | 5795.58 | 0.25 | 305.02 | S.S.Fire Hydrant Valve single headed,Fire Hose Box with powder coating ,Fire Hose Pipe 63 mm dia 15mtr long,Branch Pipe Nozzel- Essel/Padma | 95 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 32mm dia.(L) | Mtrs | 380 | 250 | 95000 | 17100 | 112100 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | G.I.Pipe 32mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 25mm dia-(L) | Mtrs | 660 | 200 | 132000 | 23760 | 155760 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | G.I.Pipe 25mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 1500 mm with Bushing (L) | No. | 30 | 188 | 5640 | 1015.2 | 6655.2 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Flexible Hose Pipe 1500 mm- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 25mm Dia (1.2mtr length) (L) | No. | 30 | 188 | 5640 | 1015.2 | 6655.2 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Flexible Hose Pipe 1200 mm- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 25mm Dia (1mtr length) (L) | No. | 370 | 188 | 69560 | 12520.8 | 82080.8 | 0 | 204.25 | 38399 | 6911.82 | 45310.82 | 165.75 | 36769.98 | Flexible Hose Pipe 1000 mm- Newage /Hd | 55.2027 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Pendent (L) | No. | 440 | 200 | 88000 | 15840 | 103840 | 0 | 123.5 | 24700 | 4446 | 29146 | 316.5 | 74694 | Pendent Sprinkler 68 Deg- Newage /Hd | 28.0682 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 150mm dia.(L) | Mtrs | 90 | 600 | 54000 | 9720 | 63720 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | G.I.Pipe 150 mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI C Class Pipe 100mm dia.(L) | Mtrs | 264 | 550 | 145200 | 26136 | 171336 | 0 | 0 | 0 | 0 | 0 | 264 | 0 | G.I.Pipe 100 mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 80mm dia.(L) | Mtrs | 60 | 450 | 27000 | 4860 | 31860 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | G.I.Pipe 80mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 65mm dia.(L) | Mtrs | 60 | 375 | 22500 | 4050 | 26550 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | G.I.Pipe 65mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 50mm dia.(L) | Mtrs | 90 | 400 | 36000 | 6480 | 42480 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | G.I.Pipe 50mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 40mm dia.(L) | Mtrs | 120 | 300 | 36000 | 6480 | 42480 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | G.I.Pipe 40mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Handheld Microphone (L) | No. | 1 | 350 | 350 | 63 | 413 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of Handheld Microphone with stand and cable of Microphone (corded).(Freq. response: 20Hz to 18kHz S/N: 1.6mV-4.5mV. Model-Goose Neck Microphone | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Rack 6 U (L) | No. | 1 | 2500 | 2500 | 450 | 2950 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of 6U Wall mount Rack with Front Glass Door, Fan Tray on Top, Perforated Rear Doors, Openable Entry at the Bottom for the Cable entry, Cable Basket for Cable Dressing & Vertical Power Strip with all necessary accessories & hardware.Make-STD | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 294 | 40 | 11760 | 2116.8 | 13876.8 | 2.5 | 0 | 0 | 0 | 0 | 294 | 0 | Laying of 2 Core x 1.5 Sq.mm,Multistrand Copper,Shielded,Twisted pair,FRLS PVC insulated UnArmoured cable, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.5 meters interval.Make Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | 7.5 HP Booster Pump- (L) | No. | 1 | 3290 | 3290 | 592.2 | 3882.2 | 0 | 0.95 | 3125.5 | 562.6 | 3688.1 | 0.05 | 194.1 | Booster Pump 7.5 Hp- CRI/Kirlosakar | 95 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Electrical Starter (L) | No. | 1 | 1410 | 1410 | 253.8 | 1663.8 | 0 | 0.95 | 1339.5 | 241.12 | 1580.62 | 0.05 | 83.18 | Electrical Starter-STD | 95 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Cable 2.5 sqmm (L) | Mtrs | 70 | 42.3 | 2961 | 532.98 | 3493.98 | 0 | 37.9906 | 1607 | 289.26 | 1896.26 | 32.0095 | 1597.72 | Cable 2.5sqr mm X 4 core- Polycab | 54.2723 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Telephone Jack/Receiver (L) | No. | 1 | 150 | 150 | 27 | 177 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | ITC of Fire Fighter (talk back) Telephone handset.Make- Ravel,Model-EK705H | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 687 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm cable for PA System (L) | Mtrs | 350 | 40 | 14000 | 2520 | 16520 | 2.5 | 0 | 0 | 0 | 0 | 350 | 0 | Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated UnArmoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval (Red in Colour)(Only LPCB approved) Make Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Signage Fire Hose Reel (M) | No. | 5 | 6392 | 31960 | 5752.8 | 37712.8 | 0 | 4 | 25568.03 | 4602.24 | 30170.27 | 1 | 7542.53 | Fire Hose Reel with 30 mtrs rubber hose- Essel/Padma | 80 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Fire Extinguisher ABC 4Kg (M) | No. | 6 | 1645 | 9870 | 1776.6 | 11646.6 | 0 | 4.2 | 6909 | 1243.62 | 8152.62 | 1.8 | 3493.98 | ABC Type Fire Extinguisher 4 Kg- Mercury | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Fire Extinguisher 4.5Kg CO2 (IS15683:2006(M) | No. | 2 | 5800 | 11600 | 2088 | 13688 | 0 | 1.4 | 8120 | 1461.6 | 9581.6 | 0.6 | 4106.4 | CO2 Type Extinguisher 4.5 kg- Mercury | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Air Release Valve 25mm (M) | No. | 2 | 1750 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Air Release Valve- STD | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 150mm -(M) | No. | 6 | 3800 | 22800 | 4104 | 26904 | 0 | 1 | 3800 | 684 | 4484 | 5 | 22420 | C.I.Butterfly Valve 150 mm - Kartar | 16.6667 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 100mm-(M) | No. | 6 | 3600 | 21600 | 3888 | 25488 | 0 | 4.2 | 15120 | 2721.6 | 17841.6 | 1.8 | 7646.4 | C.I.Butterfly Valve 100 mm- Kartar | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 25mm Dia (1mtr length) (M) | No. | 370 | 1034 | 382580 | 68864.4 | 451444.4 | 0 | 271.001 | 280214.99 | 50438.7 | 330653.69 | 98.999 | 120790.71 | Flexible Hose Pipe 1000 mm- Newage /Hd | 73.2435 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Pendent (M) | No. | 440 | 380 | 167200 | 30096 | 197296 | 0 | 186 | 70680 | 12722.4 | 83402.4 | 254 | 113893.6 | Pendent Sprinkler 68 Deg- Newage /Hd | 42.2727 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Upright (M) | No. | 30 | 450 | 13500 | 2430 | 15930 | 0 | 21 | 9450 | 1701 | 11151 | 9 | 4779 | Upright Sprinkler 68 Deg- Newage /Hd | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler 15mm 68 dg Side wall (M) | No. | 10 | 350 | 3500 | 630 | 4130 | 0 | 0 | 0 | 0 | 0 | 10 | 0 | Sidewall Sprinkler 68 Deg - Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Rossete Plate (M) | No. | 370 | 90 | 33300 | 5994 | 39294 | 0 | 271.0111 | 24391 | 4390.38 | 28781.38 | 98.9889 | 10512.62 | Rossete plate- STD | 73.2462 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | GI Single Fire Hose Box (M) | No. | 5 | 17930 | 89650 | 16137 | 105787 | 0 | 5 | 89650 | 16137.02 | 105787.02 | 0 | -0.02 | S.S.Fire Hydrant Valve single headed,Fire Hose Box with powder coating ,Fire Hose Pipe 63 mm dia 15mtr long,Branch Pipe Nozzel- Essel/Padma | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 50mm dia.(M) | Mtrs | 90 | 650 | 58500 | 10530 | 69030 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | G.I.Pipe 50mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 40mm dia.(M) | Mtrs | 120 | 500 | 60000 | 10800 | 70800 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | G.I.Pipe 40mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 32mm dia.(M) | Mtrs | 380 | 450 | 171000 | 30780 | 201780 | 0 | 0 | 0 | 0 | 0 | 380 | 0 | G.I.Pipe 32mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 25mm dia.(M) | Mtrs | 660 | 350 | 231000 | 41580 | 272580 | 0 | 0 | 0 | 0 | 0 | 660 | 0 | G.I.Pipe 25mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 1500 mm with Bushing (M) | No. | 30 | 1504 | 45120 | 8121.6 | 53241.6 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Flexible Hose Pipe 1500 mm- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Flexible Hose Pipe 25mm Dia (1.2mtr length) (M) | No. | 30 | 1222 | 36660 | 6598.8 | 43258.8 | 0 | 0 | 0 | 0 | 0 | 30 | 0 | Flexible Hose Pipe 1200 mm- Newage /Hd | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Electrical Starter (M) | No. | 1 | 6241 | 6241 | 1123.38 | 7364.38 | 0 | 1 | 6241 | 1123.36 | 7364.36 | 0 | 0.02 | Electrical Starter-STD | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Cable 2.5 sqmm (M) | Mtrs | 70 | 122 | 8540 | 1537.2 | 10077.2 | 0 | 40 | 4880 | 878.4 | 5758.4 | 30 | 4318.8 | Cable 2.5sqr mm X 4 core- Polycab | 57.1429 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 04 ELECTRICAL WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 150mm dia.(M) | Mtrs | 90 | 2100 | 189000 | 34020 | 223020 | 0 | 0 | 0 | 0 | 0 | 90 | 0 | G.I.Pipe 150 mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI C Class Pipe 100mm dia.(M) | Mtrs | 0 | 1450 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Cancelled | DUSHANT.GORE | 25 Jan 2024
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 80mm dia.(M) | Mtrs | 60 | 1000 | 60000 | 10800 | 70800 | 0 | 24.5 | 24500 | 4410 | 28910 | 35.5 | 41890 | G.I.Pipe 80mm dia- Apollo | 40.8333 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 65mm dia.(M) | Mtrs | 60 | 800 | 48000 | 8640 | 56640 | 0 | 0 | 0 | 0 | 0 | 60 | 0 | G.I.Pipe 65mm dia- Apollo | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 6W Ceiling Speakers (M) | No. | 17 | 1250 | 21250 | 3825 | 25075 | 0 | 10.5 | 13125 | 2362.5 | 15487.5 | 6.5 | 9587.5 | Supply of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps Make- Ravel,Model-RE-LS 6C | 61.7647 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 04 ELECTRICAL WORK | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Back Box (M) | No. | 17 | 350 | 5950 | 1071 | 7021 | 0 | 0 | 0 | 0 | 0 | 17 | 0 | Supply of back box for 6 Watt Ceiling Speakers.Make- STD | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Handheld Microphone (M) | No. | 1 | 2150 | 2150 | 387 | 2537 | 0 | 0.7 | 1505 | 270.9 | 1775.9 | 0.3 | 761.1 | Supply of Handheld Microphone with stand and cable of Microphone (corded).(Freq. response: 20Hz to 18kHz S/N: 1.6mV-4.5mV. Model-Goose Neck Microphone | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Rack 6 U (M) | No. | 1 | 17059 | 17059 | 3070.62 | 20129.62 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of 6U Wall mount Rack with Front Glass Door, Fan Tray on Top, Perforated Rear Doors, Openable Entry at the Bottom for the Cable entry, Cable Basket for Cable Dressing & Vertical Power Strip with all necessary accessories & hardware.Make-STD | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 294 | 80 | 23520 | 4233.6 | 27753.6 | 0 | 0 | 0 | 0 | 0 | 294 | 0 | Supply of 2 Core x 1.5 Sq.mm,Multistrand Copper,Shielded,Twisted pair,FRLS PVC insulated UnArmoured cable, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.5 meters interval.Make Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | 7.5 HP Booster Pump- (M) | No. | 1 | 45590 | 45590 | 8206.2 | 53796.2 | 0 | 1 | 45590 | 8206.22 | 53796.22 | 0 | -0.02 | Booster Pump 7.5 Hp- CRI/Kirlosakar | 100 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Talkback Panel (M) | No. | 1 | 66504 | 66504 | 11970.72 | 78474.72 | 0 | 0.7 | 46552.8 | 8379.5 | 54932.3 | 0.3 | 23542.42 | Supply of 8 Zone Talkback Panel.Make- Ravel,Model-EK 740 | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Talk Back System (M) | No. | 10 | 800 | 8000 | 1440 | 9440 | 0 | 2.8 | 2240 | 403.2 | 2643.2 | 7.2 | 6796.8 | Supply of Fire Fighter (talk back) jack module.Make- Ravel,Model-EK 750J | 28 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Telephone Jack/Receiver (M) | No. | 1 | 5500 | 5500 | 990 | 6490 | 0 | 0.7 | 3850 | 693 | 4543 | 0.3 | 1947 | Supply of Fire Fighter (talk back) Telephone handset.Make- Ravel,Model-EK705H | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm cable for PA System (M) | Mtrs | 350 | 80 | 28000 | 5040 | 33040 | 0 | 0 | 0 | 0 | 0 | 350 | 0 | Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated UnArmoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval (Red in Colour)(Only LPCB approved) Make Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Digital Signal Based Voice Alarm Controller (M) | No. | 1 | 51653 | 51653 | 9297.54 | 60950.54 | 0 | 0.7 | 36157.1 | 6508.28 | 42665.38 | 0.3 | 18285.16 | Supply of 8 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 8 zone paging station) Local Control Panel is 8 speaker circuit digital voice alarm controller.Make- Ravel,Model-Escape-250W | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Digital Amplifier (M) | No. | 1 | 38000 | 38000 | 6840 | 44840 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of 480W Power Amplifier with Rated output wattage - 480W Make- Ravel,Model-RE-250 | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Fault Isolator Base / Module (M) | No. | 10 | 2500 | 25000 | 4500 | 29500 | 0 | 2.8 | 7000 | 1260 | 8260 | 7.2 | 21240 | Supply of Zonal Short Circuit Loop Isolator, (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 MI | 28 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Control Module (M) | No. | 1 | 3300 | 3300 | 594 | 3894 | 0 | 0.7 | 2310 | 415.8 | 2725.8 | 0.3 | 1168.2 | Supply of Addressable Control Module for activating the Notification application devices. Shall have supervisory facility to supervise the auxillary power.active Modes - Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 MC | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Manual call point (M) | No. | 5 | 2850 | 14250 | 2565 | 16815 | 0 | 0.7 | 1995 | 359.1 | 2354.1 | 4.3 | 14460.9 | Supply of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool. Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-717 M | 14 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Conventional Sounder cum Strobe (M) | No. | 5 | 1900 | 9500 | 1710 | 11210 | 0 | 3.5 | 6650 | 1197 | 7847 | 1.5 | 3363 | Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, Approval: (LPCB / UL, FM Approved).Make- Ravel,Model-RE-25 SS | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm cable for PA System (M) | Mtrs | 1508 | 80 | 120640 | 21715.2 | 142355.2 | 0 | 917.7 | 73416 | 13214.88 | 86630.88 | 590.3 | 55724.32 | Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval.Make-Ploycab | 60.8554 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 50 | 80 | 4000 | 720 | 4720 | 0 | 0 | 0 | 0 | 0 | 50 | 0 | Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Unshielded, FRLS PVC insulated armoured cable, RED in colour, laid on wall/ slab or structure with necessary GI saddles & spacer at 0.4 meters interval.Make-Polycab | 0 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Fire Alarm Panel (M) | No. | 1 | 215000 | 215000 | 38700 | 253700 | 0 | 0.7 | 150500 | 27090 | 177590 | 0.3 | 76110 | Supply Flush or Surface Mounting Modularized Panel with 4 loops.Having inbuilt 1 loops,Maximum 4 Loops (4 with Network ),Max Capacity with 4 Loops =1524 Addressable Devices. Make-Ravel ,Model-Avani-LCS | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Fire Repeater Panel (M) | No. | 1 | 45000 | 45000 | 8100 | 53100 | 0 | 0.7 | 31500 | 5670 | 37170 | 0.3 | 15930 | Supply of Network Active Repeater with Full Control, SemiFlush or Wall Mounting, Includes RS485 Class A Network Card (LPCB / UL, FM Approved).Make- Ravel,Model-RE-517 RP | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable smoke detector (M) | No. | 105 | 2400 | 252000 | 45360 | 297360 | 0 | 73.5 | 176400 | 31752 | 208152 | 31.5 | 89208 | Supply of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor (LPCB / UL, FM Approved).Make- Ravel,Model-RE-317D SL | 70 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 0 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Building Fire Alarm System Work | Addressable Heat Detector (M) | No. | 5 | 2350 | 11750 | 2115 | 13865 | 0 | 0.7 | 1645 | 296.1 | 1941.1 | 4.3 | 11923.9 | Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor (LPCB / UL, FM Approved).Make- Ravel,Model-RE-317D HL | 14 |  | DUSHANT GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | ADITYA.CHOUGULE | 11 Dec 2023
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 80mm-(M) | No. | 2 | 3200 | 6400 | 1152 | 7552 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | C.I.Butterfly Valve 80 mm- Kartar | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Butterfly Valve 40mm (M) | No. | 6 | 2650 | 15900 | 2862 | 18762 | 0 | 5.0004 | 13251.03 | 2385.18 | 15636.21 | 0.9996 | 3125.79 | C.I.Butterfly Valve 40 mm- Kartar | 83.34 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Non Return Valve 100mm (M) | No. | 2 | 3200 | 6400 | 1152 | 7552 | 0 | 0.7 | 2240 | 403.2 | 2643.2 | 1.3 | 4908.8 | C.I.NRV 100 mm- Kartar | 35 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | Sprinkler Alarm Valve 150mm dia (M) | set | 1 | 43500 | 43500 | 7830 | 51330 | 0 | 0.7 | 30450 | 5481 | 35931 | 0.3 | 15399 | Sprinkler Alarm Valve 150 mm dia- HD | 70 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI C Class Pipe 100mm dia.(M) | Mtrs | 264 | 1439.83 | 380115.12 | 68420.72 | 448535.84 | 0 | 0 | 0 | 0 | 0 | 264 | 0 | G.I.Pipe 100mm Dia-Brand-Apollo | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 783 | 0 | 26 Sep 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Wing F . L.G. Floor Fire Door | Fire Door Installation (L) | No. | 4 | 1200 | 4800 | 864 | 5664 | 2.5 | 4 | 4800 | 864 | 5664 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 783 | 0 | 26 Sep 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Wing F - Stilt Floor Staircase Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 783 | 0 | 26 Sep 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Wing F - Ground Floor Staircase Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 783 | 0 | 26 Sep 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Wing F - First Floor Staircase Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 783 | 0 | 26 Sep 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Wing F - Second Floor Staircase Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 783 | 0 | 26 Sep 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Wing F - Third Floor Staircase Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 16 Oct 2023 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | Pressure Relief Dampers (M) | No. | 1 | 6526 | 6526 | 1174.68 | 7700.68 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand- Air Product.Pressure relief dampers set to operate at 60Pa. (max) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | 8 SWG GI Wire (M). | Mtrs | 34 | 51 | 1734 | 312.12 | 2046.12 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 8 SWG GI wire (for fan body earthing only) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | 14 SWG GI Perforated cable tray 100 wide (M) | Mtrs | 34 | 950 | 32300 | 5814 | 38114 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | "14 SWG GI perforated cable trays 100mm wide with cover for laying power & control cables between panel boards & equipment; including hardware, accessories like bends, tee’s, supports, etc. " | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | 14 SWG GI Perforated cable tray 100 wide (M) | Mtrs | 34 | 950 | 32300 | 5814 | 38114 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | "14 SWG GI perforated cable trays 100mm wide with cover for laying power & control cables between panel boards & equipment; including hardware, accessories like bends, tee’s, supports, etc. " | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | 14 SWG GI Perforated cable tray 100 wide (M) | Mtrs | 9 | 950 | 8550 | 1539 | 10089 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | "14 SWG GI perforated cable trays 100mm wide with cover for laying power & control cables between panel boards & equipment; including hardware, accessories like bends, tee’s, supports, etc. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | GSS Ducting 22 Gauge (M) | Sq.m. | 8 | 1650 | 13200 | 2376 | 15576 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | Supply of Site fabricated GSS Ducting 22 Guage Class VIII 120 GSM as per IS-277 with GI slotted C channel support, GI full threaded rod, double check nut washers system | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | GSS Ducting 22 Gauge (M) | Sq.m. | 8 | 1650 | 13200 | 2376 | 15576 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | Supply of Site fabricated GSS Ducting 22 Guage Class VIII 120 GSM as per IS-277 with GI slotted C channel support, GI full threaded rod, double check nut washers system | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | 4C x 6sqmm- XLPE Armoured cable (M) | Mtrs | 34 | 650 | 22100 | 3978 | 26078 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | Supply of 4Core X 6 Sqmm - XLPE Armoured cable (for fan motor) including terminations.All Cables should be XLPE type. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | 4C x 6sqmm- XLPE Armoured cable (M) | Mtrs | 34 | 650 | 22100 | 3978 | 26078 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | Supply of 4Core X 6 Sqmm - XLPE Armoured cable (for fan motor) including terminations.All Cables should be XLPE type. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | 8 SWG GI Wire (M). | Mtrs | 34 | 51 | 1734 | 312.12 | 2046.12 | 0 | 0 | 0 | 0 | 0 | 34 | 0 | 8 SWG GI wire (for fan body earthing only) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | Star Delta Starter Panel (M) | No. | 1 | 110000 | 110000 | 19800 | 129800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of Star delta starter panel with on off push button, on/off/trip indicators,NO/NC potential free contacts for BMS/integration with building Fire Fighting system, manual reset overload relays. Note: Panel should be IP-65 rating | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | 4C x 6sqmm- XLPE Armoured cable (M) | Mtrs | 9 | 850 | 7650 | 1377 | 9027 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | Brand- Polycab.Supply of 4Core X 6 Sqmm - XLPE Armoured cable (for fan motor) including terminations. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | 4C x 6sqmm- XLPE Armoured cable (M) | Mtrs | 9 | 850 | 7650 | 1377 | 9027 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | Brand- Polycab.Supply of 4Core X 6 Sqmm - XLPE Armoured cable (for fan motor) including terminations. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | 8 SWG GI Wire (M). | Mtrs | 9 | 51 | 459 | 82.62 | 541.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 8 SWG GI wire (for fan body earthing only) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | 8 SWG GI Wire (M). | Mtrs | 9 | 51 | 459 | 82.62 | 541.62 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | 8 SWG GI wire (for fan body earthing only) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | 14 SWG GI Perforated cable tray 100 wide (M) | Mtrs | 9 | 950 | 8550 | 1539 | 10089 | 0 | 0 | 0 | 0 | 0 | 9 | 0 | "14 SWG GI perforated cable trays 100mm wide with cover for laying power & control cables between panel boards & equipment; including hardware, accessories like bends, tee’s, supports, etc. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | Pressure Relief Dampers (M) | No. | 1 | 6526 | 6526 | 1174.68 | 7700.68 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Brand- Air Product.Pressure relief dampers set to operate at 60Pa. (max) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | GSS Ducting 22 Gauge (M) | Sq.m. | 15 | 1450 | 21750 | 3915 | 25665 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | Brand- Jindal.Supply of Site fabricated GSS Ducting 22 Guage Class VIII 120 GSM as per IS-277 with GI slotted C channel support, GI full threaded rod, double check nut washers system | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | GSS Ducting 22 Gauge (M) | Sq.m. | 15 | 1450 | 21750 | 3915 | 25665 | 0 | 0 | 0 | 0 | 0 | 15 | 0 | Brand- Jindal.Supply of Site fabricated GSS Ducting 22 Guage Class VIII 120 GSM as per IS-277 with GI slotted C channel support, GI full threaded rod, double check nut washers system | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | Al. Powder coated Grills (450x450mm) (M) | Sq.m. | 7.21 | 15600 | 112476 | 20245.68 | 132721.68 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | Brand- Air Product.Supply of Extruded Al. Powder coated Grilles with Damper for supply as per following specification & approved sample by Client / Architect /Consultant.Size - 450 X 450 mm | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | Al. Powder coated Grills (450x450mm) (M) | Sq.m. | 7.21 | 15600 | 112476 | 20245.68 | 132721.68 | 0 | 0 | 0 | 0 | 0 | 7.21 | 0 | Brand- Air Product.Supply of Extruded Al. Powder coated Grilles with Damper for supply as per following specification & approved sample by Client / Architect /Consultant.Size - 450 X 450 mm | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 831 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | Star Delta Starter Panel (M) | No. | 1 | 110000 | 110000 | 19800 | 129800 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Supply of Star delta starter panel with on off push button, on/off/trip indicators,NO/NC potential free contacts for BMS/integration with building Fire Fighting system, manual reset overload relays. Note: Panel should be IP-65 rating | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Dec 2023 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | GSS Ducting 22 Gauge (L) | Sq.m. | 8 | 500 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | 4C x 6sqmm- XLPE Armoured cable (L) | Mtrs | 34 | 200 | 6800 | 1224 | 8024 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | 4C x 6sqmm- XLPE Armoured cable (L) | Mtrs | 34 | 200 | 6800 | 1224 | 8024 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | 8 SWG GI Wire (L). | Mtrs | 34 | 40 | 1360 | 244.8 | 1604.8 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | 8 SWG GI Wire (L). | Mtrs | 34 | 40 | 1360 | 244.8 | 1604.8 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | 14 SWG GI Perforated cable tray 100 wide (L) | Mtrs | 34 | 450 | 15300 | 2754 | 18054 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | Axial Flow fan 25156 CFM/40 MMWC (L) | No. | 0 | 15800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 01 Dec 2023
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | Axial Flow fan 25156 CFM/40 MMWC (L) | No. | 1 | 15800 | 15800 | 2844 | 18644 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | Axial Flow fan 25156 CFM/40 MMWC (L) | No. | 1 | 15800 | 15800 | 2844 | 18644 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | Axial flow fan 25586 CFM/40 MMWC (L) | No. | 1 | 15800 | 15800 | 2844 | 18644 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | Axial flow fan 25586 CFM/40 MMWC (L) | No. | 1 | 15800 | 15800 | 2844 | 18644 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Lift Well Pressurization System | GSS Ducting 22 Gauge (L) | Sq.m. | 8 | 500 | 4000 | 720 | 4720 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | 4C x 6sqmm- XLPE Armoured cable (L) | Mtrs | 9 | 250 | 2250 | 405 | 2655 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | 8 SWG GI Wire (L). | Mtrs | 9 | 40 | 360 | 64.8 | 424.8 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | 8 SWG GI Wire (L). | Mtrs | 9 | 40 | 360 | 64.8 | 424.8 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | 14 SWG GI Perforated cable tray 100 wide (L) | Mtrs | 9 | 450 | 4050 | 729 | 4779 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | 14 SWG GI Perforated cable tray 100 wide (L) | Mtrs | 9 | 450 | 4050 | 729 | 4779 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | Axial Flow fan 25156 CFM/40 MMWC (L) | No. | 0 | 15800 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 01 Dec 2023
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | GSS Ducting 22 Gauge (L) | Sq.m. | 15 | 400 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | Al. Powder coated Grills (450x450mm) (L) | Sq.m. | 7.21 | 3500 | 25235 | 4542.3 | 29777.3 | 2.5 | 0 | 0 | 0 | 0 | 7.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | Al. Powder coated Grills (450x450mm) (L) | Sq.m. | 7.21 | 3500 | 25235 | 4542.3 | 29777.3 | 2.5 | 0 | 0 | 0 | 0 | 7.21 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | Star Delta Starter Panel (L) | No. | 1 | 14500 | 14500 | 2610 | 17110 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | Star Delta Starter Panel (L) | No. | 1 | 14500 | 14500 | 2610 | 17110 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | 4C x 6sqmm- XLPE Armoured cable (L) | Mtrs | 9 | 250 | 2250 | 405 | 2655 | 2.5 | 0 | 0 | 0 | 0 | 9 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | Pressure Relief Dampers (L) | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Staircase Pressurization System | Pressure Relief Dampers (L) | No. | 1 | 1800 | 1800 | 324 | 2124 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-Staircase Pressurization System-No. | GSS Ducting 22 Gauge (L) | Sq.m. | 15 | 400 | 6000 | 1080 | 7080 | 2.5 | 0 | 0 | 0 | 0 | 15 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 832 | 0 | 01 Dec 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-Lift Well Pressurization System | 14 SWG GI Perforated cable tray 100 wide (L) | Mtrs | 34 | 450 | 15300 | 2754 | 18054 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 |  | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 906 | 0 | 13 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Fire Fighting Misc.Work - F Bulding | Misc Work DCW | No. | 1 | 150000 | 150000 | 27000 | 177000 | 0 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 18 Jan 2024 |  | DEV. Compound Wall | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Surface Mounting Modularized Panel (M) | No. | 2 | 325000 | 650000 | 117000 | 767000 | 0 | 1.4 | 455000 | 81900 | 536900 | 0.6 | 230100 | Model No-Aaral x8.Make-Ravel.Supply of New Flush or Surface Mounting Modularized Panel with 8 loops.Having inbuilt 2 loops , Maximum 8 Loops ( 8 with Network ) , Max Capacity with 8 Loops = 1680 Addressable Devices, 140 Zone Indication, Big Screen, 2 Bell Circuit, Integrated PSU with Battery Charger. (LPCB Approved) and Dual Loop card for IFP8, 484 Addressable Devices Capacity (LPCB Approved) | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Network Active Repeater (M) | No. | 1 | 42500 | 42500 | 7650 | 50150 | 0 | 0.7 | 29750 | 5355 | 35105 | 0.3 | 15045 | Make-Ravel.Supply of Network Active Repeater with Full Control, SemiFlush or Wall Mounting, Includes RS485 Class A Network Card. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable smoke detector (M) | No. | 857 | 2340 | 2005380 | 360968.4 | 2366348.4 | 0 | 599.9 | 1403766 | 252677.88 | 1656443.88 | 257.1 | 709904.52 | Model NoAR-LC.Make-Ravel.Supply of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Heat Detector (M) | No. | 207 | 2300 | 476100 | 85698 | 561798 | 0 | 144.9 | 333270 | 59988.6 | 393258.6 | 62.1 | 168539.4 | Model No-RE357S.Make-Ravel.Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 20 Watt Cabinet Speakers (M) | No. | 76 | 2500 | 190000 | 34200 | 224200 | 0 | 53.2 | 133000 | 23940 | 156940 | 22.8 | 67260 | Model no-RE-LS20W.Supply of 20 Watt Cabinet Speakers with High impact and fire resistant ABS material and Rated Power 10W. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 1 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Relay Module (M) | No. | 4 | 3135 | 12540 | 2257.2 | 14797.2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Relay Module (RE 757R) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 1 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 1C x 1sqmm Wire (M) | Mtrs | 10000 | 33.25 | 332500 | 59850 | 392350 | 0 | 7000 | 232750 | 41895 | 274645 | 3000 | 117705 | 1 Sqmm x 1 Core Copper wire | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 1 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Monitor Module (M) | No. | 25 | 3135 | 78375 | 14107.5 | 92482.5 | 0 | 17.5 | 54862.5 | 9875.26 | 64737.76 | 7.5 | 27744.74 | Monitor Module (RE 757M) | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | 2 Core x 1.5 Sqmm FRLS Armd. cable (M) | Mtrs | 600 | 75 | 45000 | 8100 | 53100 | 0 | 31.5 | 2362.5 | 425.26 | 2787.76 | 568.5 | 50312.24 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 5.25 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 6 zone Voice Alarm controller (M) | No. | 2 | 165000 | 330000 | 59400 | 389400 | 0 | 1.4 | 231000 | 41580 | 272580 | 0.6 | 116820 | Model No-RE-2AS.Supply of 6 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 6 zone paging station).Local Control Panel is 8 speaker circuit digital voice alarm controller which includes a digital signal processor, audio storage for pre-recorded messages, audio matrix, and control, fire alarm input, loudspeaker output connection terminals and audio source connection ports for auxiliary inputs. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Battery update & activation card (M) | No. | 2 | 42000 | 84000 | 15120 | 99120 | 0 | 1.4 | 58800 | 10584 | 69384 | 0.6 | 29736 | Model No-RE-2AS BC.Supply of the Battery update and activation card EN54-4 certified for RE-2AS. Once activated, the card becomes a keyfor the charger to work permanently.Package dimensions (W x H x D) : 190 x 20 x 140 mm . | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Push to talk Microphone (M) | No. | 2 | 16500 | 33000 | 5940 | 38940 | 0 | 1.4 | 23100 | 4158 | 27258 | 0.6 | 11682 | Model No-RE-2AS-PTT.Supply of Push to Talk microphone. Make:RAVEL | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Wall Mounting Kit (M) | No. | 2 | 3200 | 6400 | 1152 | 7552 | 0 | 1.4 | 4480 | 806.4 | 5286.4 | 0.6 | 2265.6 | Model No-RE-2AS WMK.Supply of the Wall mounting kit allows to install a PAVA unit on wall. It should be made of 1.5 mm galvanized sheet. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Signal initiating devices (M) | No. | 112 | 750 | 84000 | 15120 | 99120 | 0 | 78.4 | 58800 | 10584 | 69384 | 33.6 | 29736 | Model No-RE-LS6C.Supply & Installation of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (M) | Mtrs | 10638 | 45 | 478710 | 86167.8 | 564877.8 | 0 | 7420 | 333900 | 60102 | 394002 | 3218 | 170875.8 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 69.75 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 2083 | 75 | 156225 | 28120.5 | 184345.5 | 0 | 1400 | 105000 | 18900 | 123900 | 683 | 60445.5 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, Twisted pair, FRLS PVC insulated Armoured cable, laid on wall / slab or structure with necessary GI saddles & spacer at 0.5 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. | 67.2108 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 2 Core x 1.5 Sqmm FRLS Armd. cable (M) | Mtrs | 955 | 75 | 71625 | 12892.5 | 84517.5 | 0 | 668.5 | 50137.5 | 9024.76 | 59162.26 | 286.5 | 25355.24 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | 8 Zone FFT Panel (M) | No. | 1 | 68915 | 68915 | 12404.7 | 81319.7 | 0 | 0.7 | 48240.5 | 8683.3 | 56923.8 | 0.3 | 24395.9 | Model No-EK - 740.Make- Ravel.Supply of 8 Zone FFT Panel. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | SITC Fireman's Phone Jack (M) | No. | 34 | 3300 | 112200 | 20196 | 132396 | 0 | 23.8 | 78540 | 14137.2 | 92677.2 | 10.2 | 39718.8 | Model No-EK-751J(For Aaral).Make- Ravel.Supply of Fire Fighter (talk back) jack module | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | Telephone Jack/Receiver (M) | No. | 2 | 5200 | 10400 | 1872 | 12272 | 0 | 1.4 | 7280 | 1310.4 | 8590.4 | 0.6 | 3681.6 | Model No-EK- 750 H.Make- Ravel.Supply of Fire Fighter (talk back) Telephone handset. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Gas Leakage Detector (M) | No. | 200 | 3600 | 720000 | 129600 | 849600 | 0 | 140 | 504000 | 90720 | 594720 | 60 | 254880 | Model No-RE357HMake-Ravel.Supply of Gas Leak Detector with Power Supply(standalone system) | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Zone Module (M) | No. | 200 | 3600 | 720000 | 129600 | 849600 | 0 | 140 | 504000 | 90720 | 594720 | 60 | 254880 | Model No-RE - 386LP.Make Ravel.Supply of an alog Addressable Zone Module with built in fault isolat or Interface Module for monitoring the field Conventional devices.Shall have Binary Coding Setting Dip Switch,Shall have an Tricolor LED indiaction for normal and Active Modes,IP-40- - Approval: UL Listed, | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Manual call point (M) | No. | 34 | 5000 | 170000 | 30600 | 200600 | 0 | 23.8 | 119000 | 21420 | 140420 | 10.2 | 60180 | Model No-RE-557PS.Make Ravel.Supply of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Combined sounder (M) | No. | 34 | 4200 | 142800 | 25704 | 168504 | 0 | 23.8 | 99960 | 17992.8 | 117952.8 | 10.2 | 50551.2 | Model No-RE-658SS.Make Ravel.Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Fault Isolator Base / Module (M) | No. | 52 | 3100 | 161200 | 29016 | 190216 | 0 | 36.4 | 112840 | 20311.2 | 133151.2 | 15.6 | 57064.8 | Model No-RE-757I.Make Ravel.Supply ofFault Isolator Module capable of monitoring short on SLCl oop circuit also isolate wire-to-wire short circuits on an loop of type Class Aan dau to maticallyrestore communications when shorte dconditions are corrected.The fault isolator module and its mounting shall be as per technical specification,IP-40, | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 913 | 0 | 20 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Power Supply unit (M) | No. | 6 | 8500 | 51000 | 9180 | 60180 | 0 | 4.2 | 35700 | 6426 | 42126 | 1.8 | 18054 | Model No-RE-5APS.Make-Ravel.Supply of power supply unit operting on 120-220VAC,60/50HZ + 10%, Battery backup with built in charging and up to 14 Ah batteries.Output 30VDC@ 5A Max, shall provide the supplies to Beam detector/Conventional Sounders/Strobe,etc. Shall have LED indications for Power supply ON, battery Fail, Battery Charging etc.,IP -50,Dimension (350 W x 400 H x 100 D (mm),IP -50. | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Surface Mounting Modularized Panel (L) | No. | 2 | 35000 | 70000 | 12600 | 82600 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Make-Ravel.Installation of New Flush or Surface Mounting Modularized Panel with 8 loops.Having inbuilt 2 loops , Maximum 8 Loops ( 8 with Network ) , Max Capacity with 8 Loops = 1680 Addressable Devices, 140 Zone Indication, Big Screen, 2 Bell Circuit, Integrated PSU with Battery Charger. (LPCB Approved) and Dual Loop card for IFP8, 484 Addressable Devices Capacity (LPCB Approved) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Network Active Repeater (L) | No. | 1 | 1500 | 1500 | 270 | 1770 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | Make-Ravel.Installation of Network Active Repeater with Full Control, SemiFlush or Wall Mounting, Includes RS485 Class A Network Card. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Power Supply unit (L) | No. | 6 | 180 | 1080 | 194.4 | 1274.4 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 | Make-Ravel.Installation of power supply unit operting on 120-220VAC,60/50HZ + 10%, Battery backup with built in charging and up to 14 Ah batteries.Output 30VDC@ 5A Max, shall provide the supplies to Beam detector/Conventional Sounders/Strobe,etc. Shall have LED indications for Power supply ON, battery Fail, Battery Charging etc.,IP -50,Dimension (350 W x 400 H x 100 D (mm),IP -50. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (L) | Mtrs | 10638 | 35 | 372330 | 67019.4 | 439349.4 | 2.5 | 0 | 0 | 0 | 0 | 10638 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 2 Core x 1.5 Sqmm FRLS Armd. cable (L) | Mtrs | 955 | 35 | 33425 | 6016.5 | 39441.5 | 2.5 | 0 | 0 | 0 | 0 | 955 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | 8 Zone FFT Panel (L) | No. | 1 | 10000 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | Make- Ravel.Installation of 8 Zone FFT Panel. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | SITC Fireman's Phone Jack (L) | No. | 34 | 250 | 8500 | 1530 | 10030 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 | Make- Ravel.Installation of Fire Fighter (talk back) jack module | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable smoke detector (L) | No. | 857 | 300 | 257100 | 46278 | 303378 | 0 | 0 | 0 | 0 | 0 | 857 | 0 | Make-Ravel.Installation of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Heat Detector (L) | No. | 207 | 300 | 62100 | 11178 | 73278 | 2.5 | 0 | 0 | 0 | 0 | 207 | 0 | Make-Ravel.Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Gas Leakage Detector (L) | No. | 200 | 250 | 50000 | 9000 | 59000 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 | Make-Ravel.Installation of Gas Leak Detector with Power Supply(standalone system) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Zone Module (L) | No. | 200 | 300 | 60000 | 10800 | 70800 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 | Make Ravel.Installation of an alog Addressable Zone Module with built in fault isolat or Interface Module for monitoring the field Conventional devices.Shall have Binary Coding Setting Dip Switch,Shall have an Tricolor LED indiaction for normal and Active Modes,IP-40- - Approval: UL Listed, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Manual call point (L) | No. | 34 | 300 | 10200 | 1836 | 12036 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 | Make Ravel.Instalation of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Combined sounder (L) | No. | 34 | 300 | 10200 | 1836 | 12036 | 2.5 | 0 | 0 | 0 | 0 | 34 | 0 | Make Ravel.Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Signal initiating devices (L) | No. | 112 | 200 | 22400 | 4032 | 26432 | 2.5 | 0 | 0 | 0 | 0 | 112 | 0 | Installation of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 20 Watt Cabinet Speakers (L) | No. | 76 | 300 | 22800 | 4104 | 26904 | 2.5 | 0 | 0 | 0 | 0 | 76 | 0 | Installation of 20 Watt Cabinet Speakers with High impact and fire resistant ABS material and Rated Power 10W. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 2083 | 35 | 72905 | 13122.9 | 86027.9 | 2.5 | 0 | 0 | 0 | 0 | 2083 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 1 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Relay Module (L) | No. | 4 | 332.5 | 1330 | 239.4 | 1569.4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Relay Module (RE 757R) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 1 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | 1C x 1sqmm Wire (L) | Mtrs | 10000 | 23.75 | 237500 | 42750 | 280250 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 Sqmm x 1 Core Copper wire | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 1 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Addressable Monitor Module (L) | No. | 25 | 332.5 | 8312.5 | 1496.26 | 9808.76 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Monitor Module (RE 757M) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | Telephone Jack/Receiver (L) | No. | 2 | 1000 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Make- Ravel.Installation of Fire Fighter (talk back) Telephone handset. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FFT System | 2 Core x 1.5 Sqmm FRLS Armd. cable (L) | Mtrs | 600 | 35 | 21000 | 3780 | 24780 | 2.5 | 0 | 0 | 0 | 0 | 600 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | 6 zone Voice Alarm controller (L) | No. | 2 | 23500 | 47000 | 8460 | 55460 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of 6 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 6 zone paging station) Local Control Panel is 8 speaker circuit digital voice alarm controller which includes a digital signal processor, audio storage for pre-recorded messages, audio matrix, and control, fire alarm input, loudspeaker output connection terminals and audio source connection ports for auxiliary inputs. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Battery update & activation card (L) | No. | 2 | 12000 | 24000 | 4320 | 28320 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of the Battery update and activation card EN54-4 certified for RE-2AS. Once activated, the card becomes a keyfor the charger to work permanently.Package dimensions (W x H x D) : 190 x 20 x 140 mm . | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Push to talk Microphone (L) | No. | 2 | 4200 | 8400 | 1512 | 9912 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of Push to Talk microphone. Make:RAVEL | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-PA System | Wall Mounting Kit (L) | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of the Wall mounting kit allows to install a PAVA unit on wall. It should be made of 1.5 mm galvanized sheet. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 915 | 0 | 25 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D Bldg.-FAS System | Fault Isolator Base / Module (L) | No. | 52 | 300 | 15600 | 2808 | 18408 | 2.5 | 0 | 0 | 0 | 0 | 52 | 0 | Make Ravel.Installation of Fault Isolator Module capable of monitoring short on SLCl oop circuit also isolate wire-to-wire short circuits on an loop of type Class Aan dau to maticallyrestore communications when shorte dconditions are corrected.The fault isolator module and its mounting shall be as per technical specification,IP-40, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Wall Mounting Kit (M) | No. | 2 | 3200 | 6400 | 1152 | 7552 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-RE-2AS WMK.Supply of the Wall mounting kit allows to install a PAVA unit on wall. It should be made of 1.5 mm galvanized sheet. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Signal initiating devices (M) | No. | 112 | 750 | 84000 | 15120 | 99120 | 0 | 0 | 0 | 0 | 0 | 112 | 0 | Model No-RE-LS6C.Supply & Installation of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 20 Watt Cabinet Speakers (M) | No. | 49 | 2500 | 122500 | 22050 | 144550 | 0 | 1.4 | 3500 | 630 | 4130 | 47.6 | 140420 | Model no-RE-LS20W.Supply of 20 Watt Cabinet Speakers with High impact and fire resistant ABS material and Rated Power 10W. | 2.8571 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 2 core x 1.5 sqmm Armoured cable (M) | Mtrs | 2610 | 75 | 195750 | 35235 | 230985 | 0 | 0 | 0 | 0 | 0 | 2610 | 0 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Relay Module (M) | No. | 4 | 3135 | 12540 | 2257.2 | 14797.2 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Relay Module (RE 757R) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 1C x 1sqmm Wire (M) | Mtrs | 10000 | 33.25 | 332500 | 59850 | 392350 | 0 | 1680 | 55860 | 10054.8 | 65914.8 | 8320 | 326435.2 | 1 Sqmm x 1 Core Copper wire | 16.8 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | 8 Zone FFT Panel (M) | No. | 1 | 68915 | 68915 | 12404.7 | 81319.7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Model No-EK - 740.Make- Ravel.Supply of 8 Zone FFT Panel. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | SITC Fireman's Phone Jack (M) | No. | 39 | 3300 | 128700 | 23166 | 151866 | 0 | 0 | 0 | 0 | 0 | 39 | 0 | Model No-EK-751J(For Aaral).Make- Ravel.Supply of Fire Fighter (talk back) jack module | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | Telephone Jack/Receiver (M) | No. | 2 | 5200 | 10400 | 1872 | 12272 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-EK- 750 H.Make- Ravel.Supply of Fire Fighter (talk back) Telephone handset. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 6 zone Voice Alarm controller (M) | No. | 2 | 165000 | 330000 | 59400 | 389400 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-RE-2AS.Supply of 6 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 6 zone paging station).Local Control Panel is 8 speaker circuit digital voice alarm controller which includes a digital signal processor, audio storage for pre-recorded messages, audio matrix, and control, fire alarm input, loudspeaker output connection terminals and audio source connection ports for auxiliary inputs. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Battery update & activation card (M) | No. | 2 | 42000 | 84000 | 15120 | 99120 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-RE-2AS BC.Supply of the Battery update and activation card EN54-4 certified for RE-2AS. Once activated, the card becomes a keyfor the charger to work permanently.Package dimensions (W x H x D) : 190 x 20 x 140 mm . | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Push to talk Microphone (M) | No. | 2 | 16500 | 33000 | 5940 | 38940 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-RE-2AS-PTT.Supply of Push to Talk microphone. Make:RAVEL | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Combined sounder (M) | No. | 40 | 4200 | 168000 | 30240 | 198240 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | Model No-RE-658SS.Make Ravel.Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Fault Isolator Base / Module (M) | No. | 54 | 3100 | 167400 | 30132 | 197532 | 0 | 0 | 0 | 0 | 0 | 54 | 0 | Model No-RE-757I.Make Ravel.Supply ofFault Isolator Module capable of monitoring short on SLCl oop circuit also isolate wire-to-wire short circuits on an loop of type Class Aan dau to maticallyrestore communications when shorte dconditions are corrected.The fault isolator module and its mounting shall be as per technical specification,IP-40, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Power Supply unit (M) | No. | 6 | 8500 | 51000 | 9180 | 60180 | 0 | 0 | 0 | 0 | 0 | 6 | 0 | Model No-RE-5APS.Make-Ravel.Supply of power supply unit operting on 120-220VAC,60/50HZ + 10%, Battery backup with built in charging and up to 14 Ah batteries.Output 30VDC@ 5A Max, shall provide the supplies to Beam detector/Conventional Sounders/Strobe,etc. Shall have LED indications for Power supply ON, battery Fail, Battery Charging etc.,IP -50,Dimension (350 W x 400 H x 100 D (mm),IP -50. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (M) | Mtrs | 10134 | 45 | 456030 | 82085.4 | 538115.4 | 0 | 3500 | 157500 | 28350 | 185850 | 6634 | 352265.4 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 34.5372 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 2 Core x 1.5 Sqmm FRLS Armd. cable (M) | Mtrs | 820 | 75 | 61500 | 11070 | 72570 | 0 | 0 | 0 | 0 | 0 | 820 | 0 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | 2 Core x 1.5 Sqmm FRLS Armd. cable (M) | Mtrs | 610 | 75 | 45750 | 8235 | 53985 | 0 | 0 | 0 | 0 | 0 | 610 | 0 | Make-Polycab.Supply of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Surface Mounting Modularized Panel (M) | No. | 2 | 325000 | 650000 | 117000 | 767000 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | Model No-Aaral x8.Make-Ravel.Supply of New Flush or Surface Mounting Modularized Panel with 8 loops.Having inbuilt 2 loops , Maximum 8 Loops ( 8 with Network ) , Max Capacity with 8 Loops = 1680 Addressable Devices, 140 Zone Indication, Big Screen, 2 Bell Circuit, Integrated PSU with Battery Charger. (LPCB Approved) and Dual Loop card for IFP8, 484 Addressable Devices Capacity (LPCB Approved) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable smoke detector (M) | No. | 866 | 2340 | 2026440 | 364759.2 | 2391199.2 | 0 | 0 | 0 | 0 | 0 | 866 | 0 | Model NoAR-LC.Make-Ravel.Supply of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Heat Detector (M) | No. | 216 | 2300 | 496800 | 89424 | 586224 | 0 | 0 | 0 | 0 | 0 | 216 | 0 | Model No-RE357S.Make-Ravel.Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Gas Leakage Detector (M) | No. | 200 | 3600 | 720000 | 129600 | 849600 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | Model No-RE357HMake-Ravel.Supply of Gas Leak Detector with Power Supply(standalone system) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Zone Module (M) | No. | 200 | 3600 | 720000 | 129600 | 849600 | 0 | 0 | 0 | 0 | 0 | 200 | 0 | Model No-RE - 386LP.Make Ravel.Supply of an alog Addressable Zone Module with built in fault isolat or Interface Module for monitoring the field Conventional devices.Shall have Binary Coding Setting Dip Switch,Shall have an Tricolor LED indiaction for normal and Active Modes,IP-40- - Approval: UL Listed, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Manual call point (M) | No. | 40 | 5000 | 200000 | 36000 | 236000 | 0 | 0 | 0 | 0 | 0 | 40 | 0 | Model No-RE-557PS.Make Ravel.Supply of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 916 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Monitor Module (M) | No. | 25 | 3135 | 78375 | 14107.5 | 92482.5 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Monitor Module (RE 757M) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 08 Apr 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Surface Mounting Modularized Panel (L) | No. | 2 | 35000 | 70000 | 12600 | 82600 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Make-Ravel.Installation of New Flush or Surface Mounting Modularized Panel with 8 loops.Having inbuilt 2 loops , Maximum 8 Loops ( 8 with Network ) , Max Capacity with 8 Loops = 1680 Addressable Devices, 140 Zone Indication, Big Screen, 2 Bell Circuit, Integrated PSU with Battery Charger. (LPCB Approved) and Dual Loop card for IFP8, 484 Addressable Devices Capacity (LPCB Approved) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable smoke detector (L) | No. | 866 | 300 | 259800 | 46764 | 306564 | 2.5 | 0 | 0 | 0 | 0 | 866 | 0 | Make-Ravel.Installation of Addressable Smoke detector Intelligent Optical Detector, Drift Compensation, Sensitivity Adjustment, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Heat Detector (L) | No. | 216 | 300 | 64800 | 11664 | 76464 | 2.5 | 0 | 0 | 0 | 0 | 216 | 0 | Make-Ravel.Supply of Heat Detector Intelligent Fixed Temperature and Rate of Rise Heat Detector, 8 Bit Processor. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Gas Leakage Detector (L) | No. | 200 | 250 | 50000 | 9000 | 59000 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 | Make-Ravel.Installation of Gas Leak Detector with Power Supply(standalone system) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Zone Module (L) | No. | 200 | 300 | 60000 | 10800 | 70800 | 2.5 | 0 | 0 | 0 | 0 | 200 | 0 | Make Ravel.Installation of an alog Addressable Zone Module with built in fault isolat or Interface Module for monitoring the field Conventional devices.Shall have Binary Coding Setting Dip Switch,Shall have an Tricolor LED indiaction for normal and Active Modes,IP-40- - Approval: UL Listed, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Battery update & activation card (L) | No. | 2 | 12000 | 24000 | 4320 | 28320 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of the Battery update and activation card EN54-4 certified for RE-2AS. Once activated, the card becomes a keyfor the charger to work permanently.Package dimensions (W x H x D) : 190 x 20 x 140 mm . | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Push to talk Microphone (L) | No. | 2 | 4200 | 8400 | 1512 | 9912 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of Push to Talk microphone. Make:RAVEL | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Wall Mounting Kit (L) | No. | 2 | 300 | 600 | 108 | 708 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of the Wall mounting kit allows to install a PAVA unit on wall. It should be made of 1.5 mm galvanized sheet. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 20 Watt Cabinet Speakers (L) | No. | 49 | 300 | 14700 | 2646 | 17346 | 2.5 | 0 | 0 | 0 | 0 | 49 | 0 | Installation of 20 Watt Cabinet Speakers with High impact and fire resistant ABS material and Rated Power 10W. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 2 core x 1.5 sqmm Armoured cable (L) | Mtrs | 2610 | 35 | 91350 | 16443 | 107793 | 2.5 | 0 | 0 | 0 | 0 | 2610 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | Signal initiating devices (L) | No. | 112 | 200 | 22400 | 4032 | 26432 | 2.5 | 0 | 0 | 0 | 0 | 112 | 0 | Installation of signal initiating devices complete with galvanised steel. 6 Watt Ceiling Mounted Speakers (wattage must be suitable for delivering of required sound level as per NFPA72) with multi taps | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 2 Core x 1.5 Sqmm FRLS Armd. cable (L) | Mtrs | 820 | 35 | 28700 | 5166 | 33866 | 2.5 | 0 | 0 | 0 | 0 | 820 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | 2 Core x 1.5 Sqmm FRLS Armd. cable (L) | Mtrs | 610 | 35 | 21350 | 3843 | 25193 | 2.5 | 0 | 0 | 0 | 0 | 610 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Armoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | 8 Zone FFT Panel (L) | No. | 1 | 10000 | 10000 | 1800 | 11800 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 | Make- Ravel.Installation of 8 Zone FFT Panel. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | SITC Fireman's Phone Jack (L) | No. | 39 | 250 | 9750 | 1755 | 11505 | 2.5 | 0 | 0 | 0 | 0 | 39 | 0 | Make- Ravel.Installation of Fire Fighter (talk back) jack module | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FFT System | Telephone Jack/Receiver (L) | No. | 2 | 1000 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Make- Ravel.Installation of Fire Fighter (talk back) Telephone handset. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-PA System | 6 zone Voice Alarm controller (L) | No. | 2 | 23500 | 47000 | 8460 | 55460 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 | Installation of 6 Zone, Voice Alarm controller with built-in USB, MP3, AM/FM player (with 6 zone paging station) Local Control Panel is 8 speaker circuit digital voice alarm controller which includes a digital signal processor, audio storage for pre-recorded messages, audio matrix, and control, fire alarm input, loudspeaker output connection terminals and audio source connection ports for auxiliary inputs. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Manual call point (L) | No. | 0 | 300 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | DUSHANT.GORE |  | construction open | 1900-01-01 |  | No category | Cancelled | DUSHANT.GORE | 27 Jan 2024
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Combined sounder (L) | No. | 40 | 300 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 | Make Ravel.Supply of Addressable Combined Sounder and Strobe, Loop Powered and 24VDC, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Manual call point (L) | No. | 40 | 300 | 12000 | 2160 | 14160 | 2.5 | 0 | 0 | 0 | 0 | 40 | 0 | Make Ravel.Instalation of Addressable Manual Call Point Semi FlushMounting Re-settable,Supplied with Special Reset Tool | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Fault Isolator Base / Module (L) | No. | 54 | 300 | 16200 | 2916 | 19116 | 2.5 | 0 | 0 | 0 | 0 | 54 | 0 | Make Ravel.Installation of Fault Isolator Module capable of monitoring short on SLCl oop circuit also isolate wire-to-wire short circuits on an loop of type Class Aan dau to maticallyrestore communications when shorte dconditions are corrected.The fault isolator module and its mounting shall be as per technical specification,IP-40, | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Power Supply unit (L) | No. | 6 | 180 | 1080 | 194.4 | 1274.4 | 2.5 | 0 | 0 | 0 | 0 | 6 | 0 | Make-Ravel.Installation of power supply unit operting on 120-220VAC,60/50HZ + 10%, Battery backup with built in charging and up to 14 Ah batteries.Output 30VDC@ 5A Max, shall provide the supplies to Beam detector/Conventional Sounders/Strobe,etc. Shall have LED indications for Power supply ON, battery Fail, Battery Charging etc.,IP -50,Dimension (350 W x 400 H x 100 D (mm),IP -50. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 0 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 2C x 1.5 Sqmm FRLS Copper unarmoured Cabel (L) | Mtrs | 10134 | 35 | 354690 | 63844.2 | 418534.2 | 2.5 | 0 | 0 | 0 | 0 | 10134 | 0 | Make-Polycab.Laying of 2 Core x 1.5 Sq.mm, Multistrand Copper, Shielded, FRLS PVC insulated Unarmoured cable, RED in colour, laid on wall / slab or structure with necessary GI saddles & spacer at 0.4 meters interval. complete with Lugs, Cable Compression Glands, Cable tags and ferruling. scope shall also include required end termination using gland, lugs & required accessories. (Red in Colour) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Relay Module (L) | No. | 4 | 332.5 | 1330 | 239.4 | 1569.4 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | Relay Module (RE 757R) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | 1C x 1sqmm Wire (L) | Mtrs | 10000 | 23.75 | 237500 | 42750 | 280250 | 0 | 0 | 0 | 0 | 0 | 10000 | 0 | 1 Sqmm x 1 Core Copper wire | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 918 | 1 | 27 Jan 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E Bldg.-FAS System | Addressable Monitor Module (L) | No. | 25 | 332.5 | 8312.5 | 1496.26 | 9808.76 | 0 | 0 | 0 | 0 | 0 | 25 | 0 | Monitor Module (RE 757M) | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 1900-01-01 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1000 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | 12.5 Hp Booster Pump (L) | No. | 1 | 6045 | 6045 | 1088.1 | 7133.1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Booster Pump 12.5 HP.Brand- CRI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1000 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | Electrical Starter (L) | No. | 1 | 2325 | 2325 | 418.5 | 2743.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Starter 12.5 HP.Brand- L & T | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1000 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | 6 Sqmm x 4C Copper Flexible Cable (L) - Mtrs | Mtrs | 120 | 42 | 5040 | 907.2 | 5947.2 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 6 sq. mm X 4 C Copper flexible cable.Brand- Polycab. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1001 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | 12.5 Hp Booster Pump (M) | No. | 1 | 63705 | 63705 | 11466.9 | 75171.9 | 0 | 0.7 | 44593.5 | 8026.84 | 52620.34 | 0.3 | 22551.56 | Booster Pump 12.5 HP.Brand- CRI | 70 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1001 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | Electrical Starter (M) | No. | 1 | 9765 | 9765 | 1757.7 | 11522.7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Starter 12.5 HP.Brand- L & T | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1001 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Booster Pump Supply & Installation | 6 Sqmm x 4C Copper Flexible Cable (M) - Mtrs | Mtrs | 120 | 289 | 34680 | 6242.4 | 40922.4 | 0 | 70 | 20230 | 3641.4 | 23871.4 | 50 | 17051 | 6 sq. mm X 4 C Copper flexible cable.Brand- Polycab. | 58.3333 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1002 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | 12.5 Hp Booster Pump (L) | No. | 1 | 6045 | 6045 | 1088.1 | 7133.1 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Booster Pump 12.5 HP.Brand- CRI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1002 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | Electrical Starter (L) | No. | 1 | 2325 | 2325 | 418.5 | 2743.5 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Starter 12.5 HP.Brand- L & T | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1002 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | 6 Sqmm x 4C Copper Flexible Cable (L) - Mtrs | Mtrs | 120 | 42 | 5040 | 907.2 | 5947.2 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 6 sq. mm X 4 C Copper flexible cable.Brand- Polycab. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1003 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | 12.5 Hp Booster Pump (M) | No. | 1 | 63705 | 63705 | 11466.9 | 75171.9 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Booster Pump 12.5 HP.Brand- CRI | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1003 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | Electrical Starter (M) | No. | 1 | 9765 | 9765 | 1757.7 | 11522.7 | 0 | 0 | 0 | 0 | 0 | 1 | 0 | Starter 12.5 HP.Brand- L & T | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1003 | 0 | 31 May 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | E-Terrace Booster Pump Supply & Installation | 6 Sqmm x 4C Copper Flexible Cable (M) - Mtrs | Mtrs | 120 | 289 | 34680 | 6242.4 | 40922.4 | 0 | 0 | 0 | 0 | 0 | 120 | 0 | 6 sq. mm X 4 C Copper flexible cable.Brand- Polycab. | 0 |  | DUSHANT.GORE | Swapnil Erande | construction open | 17 Jun 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-L.G. Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Ground Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Parking-P1 Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-21st Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-22nd Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-23rd Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-24th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Terrace Floor-Fire Door | Fire Door Installation (L) | No. | 2 | 1200 | 2400 | 432 | 2832 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-15th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-16th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-17th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-18th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-19th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-20th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-9th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-10th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-11th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-12th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-13th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-14th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-3rd Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-4th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-5th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-6th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-7th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-8th Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Parking-P2 Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Parking-P3 Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Parking-P5 Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Stilt Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-1st Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-2nd Floor-Fire Door | Fire Door Installation (L) | No. | 1 | 1200 | 1200 | 216 | 1416 | 2.5 | 1 | 1200 | 216 | 1416 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1022 | 0 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Meter Room-Fire Door | Fire Door Installation (L) | No. | 0 | 1200 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Foreclose | ADITYA.CHOUGULE | 23 Jul 2024
GANGA ALTUS | 1022 | 1 | 15 Jun 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | D-Meter Room-Fire Door | Fire Door Installation (L) | No. | 1 | 2400 | 2400 | 432 | 2832 | 2.5 | 1 | 2400 | 432 | 2832 | 0 | 0 |  | 100 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 06 Jul 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1068 | 0 | 07 Aug 2024 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Fire Fighting Misc.Work - F Bulding | Miscellaneous Expenses | No. | 1 | 175000 | 175000 | 0 | 175000 | 0 | 1 | 175000 | 0 | 175000 | 0 | 0 |  | 100 |  | DUSHANT.GORE | Swapnil Erande | construction open | 07 Aug 2024 |  | 14 MISC WORK | Approved | Swapnil Erande | 1900-01-01