## Project_Work_Order6385986776855
Project Work Order
From 26 Jun 2024 To 22 Aug 2024
Page 1 of 1
Total Records: 8 Records 1 To 8
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | PCC Work | Sq.Ft | 0 | 10 | 0 | 0 | 0 | 2.5 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | MONALI CHAUDHAR |  | construction open | 26 Jun 2024 |  | 02 RCC WORK | Cancelled | MONALI CHAUDHAR | 26 Jun 2024
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | PCC Work | Sq.Ft | 67.79 | 10 | 677.9 | 122.02 | 799.92 | 2.5 | 0 | 0 | 0 | 0 | 67.79 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | 02 RCC WORK | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Raft -UWT | Sq.Ft | 49.07 | 120 | 5888.4 | 1059.92 | 6948.32 | 2.5 | 0 | 0 | 0 | 0 | 49.07 | 0 | Including Reinforcement, Shuttering & Casting | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | UTI. U.G.W.T | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Retaining Wall - Dld | Sq.Ft | 79.62 | 160 | 12739.2 | 2293.06 | 15032.26 | 2.5 | 0 | 0 | 0 | 0 | 79.62 | 0 | Including Reinforcement, Shuttering & Casting | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Beam - BRE | R.Ft | 92 | 250 | 23000 | 4140 | 27140 | 2.5 | 0 | 0 | 0 | 0 | 92 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | B.C. Rework/Extrawork | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Work - Mkt | Sq.Ft | 434.7 | 160 | 69552 | 12519.36 | 82071.36 | 2.5 | 0 | 0 | 0 | 0 | 434.7 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Retaining Wall - Dld | Sq.Ft | 385.1 | 160 | 61616 | 11090.88 | 72706.88 | 2.5 | 0 | 0 | 0 | 0 | 385.1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | DEV. Landscape/Equipment | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1028 | 0 | 26 Jun 2024 | UPRISEN CONSTRUCTION | RCC Work in 265KLD STP | RCC Slab | Sq.Ft | 140.1 | 200 | 28020 | 5043.6 | 33063.6 | 2.5 | 0 | 0 | 0 | 0 | 140.1 | 0 |  | 0 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 26 Jun 2024 |  | S OH Infrastructure | Approved | Swapnil Erande | 1900-01-01