## Project_Work_Order6386002876361
Project Work Order
From 01 Jul 2006 To 24 Aug 2024
Page 1 of 1
Total Records: 5 Records 1 To 5
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 9 | 1200 | 10800 | 1944 | 12744 | 0 | 6.3 | 7560 | 1360.8 | 8920.8 | 2.7 | 3823.2 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 9 | 1000 | 9000 | 1620 | 10620 | 0 | 6.3 | 6300 | 1134 | 7434 | 2.7 | 3186 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Fire Hydrant System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 373 | 1000 | 373000 | 67140 | 440140 | 0 | 273.4 | 273400 | 49212 | 322612 | 99.6 | 117528 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 73.2976 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 0 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Parking Parking Fl -Automatic Sprinkler System | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 40 | 1000 | 40000 | 7200 | 47200 | 0 | 28 | 28000 | 5040 | 33040 | 12 | 14160 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 70 |  | Dushant Gore | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 590 | 1 | 14 Dec 2022 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | Infra Work- Fire Hydrant System - 1 No. | SITC GI- 80mm Dia. Heavy Grade Pipe (M) | Mtrs | 18 | 1000 | 18000 | 3240 | 21240 | 0 | 0 | 0 | 0 | 0 | 18 | 0 | Supply of 80mm G.I.heavy grade pipes and fittings including painting with Fire Red colour suitable type of supports with anchor fasteners,bolts nuts ,clamps,"U" bolts Including cutting, welding, fixing in/ on walls etc Brand- Apollo | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 02 Jan 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01