## Project_Work_Order6386002930935
Project Work Order
From 01 Jul 2005 To 24 Aug 2024
Page 1 of 1
Total Records: 1 Records 1 To 1
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 688 | 1 | 02 Jun 2023 | SFS FIRE PROTECTION INDIA PRIVATE LIMITED | F-Supply & Installation of Fire Hydrant System | SITC GI Pipe C Class 80mm dia.(M) | Mtrs | 60 | 1000 | 60000 | 10800 | 70800 | 0 | 24.5 | 24500 | 4410 | 28910 | 35.5 | 41890 | G.I.Pipe 80mm dia- Apollo | 40.8333 |  | MONALI CHAUDHAR | Swapnil Erande | construction open | 10 Aug 2023 |  | 13 Lift,Firefightng,Mech Equip | Approved | Swapnil Erande | 1900-01-01