## Project_Work_Order6386012583830
Project Work Order
From 25 Jul 2024 To 25 Aug 2024
Page 1 of 1
Total Records: 12 Records 1 To 12
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | 12mm Toughned Glass work (L) | Sq.Ft | 183 | 50 | 9150 | 1647 | 10797 | 2.5 | 0 | 0 | 0 | 0 | 183 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | First Floor F Bldg. Sensor Door | Automatic Sensor Door (M+L) | No. | 1 | 135000 | 135000 | 24300 | 159300 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | 12mm Toughned Glass work (M) | Sq.Ft | 183 | 155 | 28365 | 5105.7 | 33470.7 | 0 | 0 | 0 | 0 | 0 | 183 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | B.C. Building Common Items | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Hole Making | No. | 11 | 50 | 550 | 99 | 649 | 2.5 | 0 | 0 | 0 | 0 | 11 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Hole Making | No. | 3 | 100 | 300 | 54 | 354 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | MKT. Marketing Infrastructure | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Cutout | No. | 7 | 150 | 1050 | 189 | 1239 | 2.5 | 0 | 0 | 0 | 0 | 7 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Twin Pro section 10ft. (M+L) | No. | 3 | 1500 | 4500 | 810 | 5310 | 2.5 | 0 | 0 | 0 | 0 | 3 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Doorset FH 943 (M+L) | No. | 2 | 10200 | 20400 | 3672 | 24072 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Handle hole to Hole 600mm | No. | 2 | 1900 | 3800 | 684 | 4484 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | EPF 703P Overpanel Patch | No. | 1 | 2035 | 2035 | 366.3 | 2401.3 | 2.5 | 0 | 0 | 0 | 0 | 1 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | ESH 412 | No. | 2 | 429 | 858 | 154.44 | 1012.44 | 2.5 | 0 | 0 | 0 | 0 | 2 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | No category | Approved | Swapnil Erande | 1900-01-01
GANGA ALTUS | 1063 | 0 | 26 Jul 2024 | NAMOH GLASSES | F-Entrance Gate Glass Work | Silicon | No. | 8 | 250 | 2000 | 360 | 2360 | 2.5 | 0 | 0 | 0 | 0 | 8 | 0 |  | 0 |  | ADITYA.CHOUGULE | Swapnil Erande | construction open | 10 Aug 2024 |  | 07 Aluminium, M.S. & S.S. WORK | Approved | Swapnil Erande | 1900-01-01