## Project_Work_Order6386018870167
Project Work Order
From 24 Jul 2024 To 26 Aug 2024
Page 1 of 1
Total Records: 6 Records 1 To 6
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Rolling,Compaction,Levelling | Sq.Ft | 3238.56 | 3 | 9715.68 | 0 | 9715.68 | 0 | 0 | 0 | 0 | 0 | 3238.56 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 1st Layer (L) | Sq.Ft | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Cancelled | ADITYA.CHOUGULE | 13 Aug 2024
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Dry Lean Concrete (L) | Sq.Ft | 8958.28 | 5.11 | 45776.81 | 8239.82 | 54016.63 | 2.5 | 0 | 0 | 0 | 0 | 8958.28 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Reinforcement Work - BC | Sq.Ft | 7889.42 | 7 | 55225.94 | 9940.66 | 65166.6 | 2.5 | 0 | 0 | 0 | 0 | 7889.42 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | Pavement Quality Concrete (L) | Sq.Ft | 7889.42 | 16 | 126230.72 | 22721.52 | 148952.24 | 2.5 | 0 | 0 | 0 | 0 | 7889.42 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 994 | 0 | 25 May 2024 | HOLE ENTERPRISES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 1st Layer (L) | Sq.Ft | 1200 | 5 | 6000 | 1080 | 7080 | 0 | 0 | 0 | 0 | 0 | 1200 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 24 Jul 2024 |  | No category | Un-Approved |  | 1900-01-01