## Project_Work_Order6386018940733
Project Work Order
From 24 Jul 2024 To 26 Aug 2024
Page 1 of 1
Total Records: 7 Records 1 To 7
Project | WO No | Revision | Wo_Date | Contrator | Task Name | Labour Name | Unit_Name | Qty | Rate | Amount | TaxAmt | Total_amount | Retaintion% | Bill Qty | Bill Amount | Bill_Tax_Amount | Total_Bill_Amount | Bal.Bill Qty | Bal.Bill Amount | Specification | Completed_Per | User_Category | PreparedBy | Approved_By | WO_Type | WO_Creation_Date | WO_Type2 | TaskCategory_Name | WODetail_Status | User_Name | Status_Date
GANGA ALTUS | 773 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | D,E,F-Bldg Side- PQC Road Work(Main Road | Rolling,Compaction,Levelling | Sq.Ft | 13347.86 | 4 | 53391.44 | 9610.46 | 63001.9 | 0 | 0 | 0 | 0 | 0 | 13347.86 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 773 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 1st Layer (L) | Sq.Ft | 23209.11 | 5.11 | 118598.55 | 21347.74 | 139946.29 | 0 | 0 | 0 | 0 | 0 | 23209.11 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 773 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | D,E,F-Bldg Side- PQC Road Work(Main Road | GSB 2nd Layer (L) | Sq.Ft | 23209.11 | 5.11 | 118598.55 | 21347.74 | 139946.29 | 0 | 0 | 0 | 0 | 0 | 23209.11 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 773 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | D,E,F-Bldg Side- PQC Road Work(Main Road | Wet Mix Macadam (L) | Sq.Ft | 17670.74 | 5.11 | 90297.48 | 16253.54 | 106551.02 | 0 | 0 | 0 | 0 | 0 | 17670.74 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 773 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | D,E,F-Bldg Side- PQC Road Work(Main Road | Dry Lean Concrete (L) | Sq.Ft | 4775.66 | 5.11 | 24403.62 | 4392.66 | 28796.28 | 2.5 | 0 | 0 | 0 | 0 | 4775.66 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Un-Approved |  | 1900-01-01
GANGA ALTUS | 773 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | D,E,F-Bldg Side- PQC Road Work(Main Road | Reinforcement Work - BC | Sq.Ft | 15016.26 | 7 | 105113.82 | 18920.48 | 124034.3 | 2.5 | 0 | 0 | 0 | 0 | 15016.26 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | B.C. RCC Superstructure | Un-Approved |  | 1900-01-01
GANGA ALTUS | 773 | 0 | 14 Sep 2023 | AMAN ASSOCIATES | D,E,F-Bldg Side- PQC Road Work(Main Road | Pavement Quality Concrete (L) | Sq.Ft | 15016.26 | 16 | 240260.16 | 43246.82 | 283506.98 | 2.5 | 0 | 0 | 0 | 0 | 15016.26 | 0 |  | 0 |  | ADITYA.CHOUGULE |  | construction open | 07 Nov 2023 |  | No category | Un-Approved |  | 1900-01-01