## RABillBrowse_Contwise6385787273
Contractor RA Bill
GANGA ASMI
Page 1 of 1
Total Records: 9 Records 1 To 9
Contractor | WO NO | RA Bill | RA Bill Date | Project | Labour_Name | TASK | Revision | Qty | Unit | Rate | Payment Schedule | PS % | Retaintion | Retention_amt | WC_Amount | Tax_Scheme_Name | Tax Amount | Amount with Tax | Net Amount | Status
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 201 (3BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 202 (3BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 203 (2BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 204 (2BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 205 (2BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 206 (3BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 207 (3BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 208 (2BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved
PRASNA PLUMBING SERVICE | 608 | 109357 | 2024-07-29 | GANGA ASMI | Int Plumbing PPRC Work | Wing-1 Flat No 209 (2BHK) Internal Plumbing (L) | 0 | 1 | Per Flat | 5700 | Labour Charges for- Fixing of Internal Plumbing work.PPRC, ASTM, PVC Pipe work. | 100 | 142.5 | 1282.5 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5557.5 | Unapproved