GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1103 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | CGST 0% URD I/P | 0 | 4182.48 | 4182.48 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1101 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | CGST 0% URD I/P | 0 | 5188.92 | 5188.92 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1105 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | CGST 0% URD I/P | 0 | 5188.92 | 5188.92 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1104 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | CGST 0% URD I/P | 0 | 4182.48 | 4182.48 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1102 Rough Plaster | Rough Plaster | 326.7 | Sq.Ft | 12 | 100 | 98.01 | 0 | 3920.4 | CGST 0% URD I/P | 0 | 3920.4 | 3920.4 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 492 | 94698 | 07 May 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 255 | D Building 1103 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | CGST 0% URD I/P | 0 | 1152.75 | 1152.75 | Approved | 0 | 0 | 293 | 07 May 2022
GANGA DHAM TOWERS | 1256 | 94696 | 07 May 2022 |  | SADAF CONSTRUCTION | JAY BHAVANI ENTERPRISES | EV - 516 | B 2002 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 38.9571 | Sq.Ft | 140 | 100 | 136.35 | 0 | 5454 | CGST 0% URD I/P | 0 | 5454 | 5454 | Approved | 0 | 0 | 55 | 07 May 2022
GANGA DHAM TOWERS | 1052 | 94684 | 06 May 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 85 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | CGST 0% URD I/P | 0 | 29988 | 29988 | Approved | 0 | 0 | 2999 | 06 May 2022
GANGA DHAM TOWERS | 927 | 94666 | 05 May 2022 |  | VENKAT RATHOD | JAY BHAVANI ENTERPRISES | EV - 189 | A 11th Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 40 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 1804 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 66.3 | Sq.Ft | 55 | 100 | 91.16 | 0 | 3646.5 | C+S GST 0% I/P RD | 0 | 3646.5 | 3646.5 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 2503 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 95 | Sq.Ft | 55 | 100 | 130.63 | 0 | 5225 | C+S GST 0% I/P RD | 0 | 5225 | 5225 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 2504 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 132.6 | Sq.Ft | 55 | 100 | 182.33 | 0 | 7293 | C+S GST 0% I/P RD | 0 | 7293 | 7293 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 1603 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 95 | Sq.Ft | 55 | 100 | 130.63 | 0 | 5225 | C+S GST 0% I/P RD | 0 | 5225 | 5225 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 2104 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 132.6 | Sq.Ft | 55 | 100 | 182.33 | 0 | 7293 | C+S GST 0% I/P RD | 0 | 7293 | 7293 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 2502 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 174 | Sq.Ft | 55 | 100 | 239.25 | 0 | 9570 | C+S GST 0% I/P RD | 0 | 9570 | 9570 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 1501 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 135.68 | Sq.Ft | 55 | 100 | 186.56 | 0 | 7462.4 | C+S GST 0% I/P RD | 0 | 7462.4 | 7462.4 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 2404 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 75 | Sq.Ft | 55 | 100 | 103.13 | 0 | 4125 | C+S GST 0% I/P RD | 0 | 4125 | 4125 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 2501 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 75 | Sq.Ft | 55 | 100 | 103.13 | 0 | 4125 | C+S GST 0% I/P RD | 0 | 4125 | 4125 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 1803 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 95 | Sq.Ft | 55 | 100 | 130.63 | 0 | 5225 | C+S GST 0% I/P RD | 0 | 5225 | 5225 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 2201 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 169 | Sq.Ft | 55 | 100 | 232.38 | 0 | 9295 | C+S GST 0% I/P RD | 0 | 9295 | 9295 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 1261 | 94665 | 05 May 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 188 | A 2403 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 95 | Sq.Ft | 55 | 100 | 130.63 | 0 | 5225 | C+S GST 0% I/P RD | 0 | 5225 | 5225 | Approved | 0 | 0 | 737 | 05 May 2022
GANGA DHAM TOWERS | 407 | 94658 | 04 May 2022 |  | SHANKAR VILAS GAIKWAD | PRAKASH CONTRACTOR | EV - 145 | Fire Fighting Line Excavation & Filling | Excavation (manually)- Dld | 771.4286 | Cu.Ft | 7 | 100 | 0 | 0 | 5400 | CGST 0% URD I/P | 0 | 5400 | 5400 | Approved | 0 | 0 | 54 | 04 May 2022
GANGA DHAM TOWERS | 1309 | 94657 | 04 May 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 182 | Tower C Electrical Pipe Laying work - | 12" RCC Pipe Laying-USL | 393.4737 | R.Ft | 19 | 100 | 186.9 | 0 | 7476 | CGST 0% URD I/P | 0 | 7476 | 7476 | Approved | 0 | 0 | 285 | 04 May 2022
GANGA DHAM TOWERS | 1309 | 94657 | 04 May 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 182 | Tower C Electrical Pipe Laying work - | Square Chamber 1.2m x 1.2m(D= Upto 1.2m) - No. | 6 | No. | 3500 | 100 | 525 | 0 | 21000 | CGST 0% URD I/P | 0 | 21000 | 21000 | Approved | 0 | 0 | 285 | 04 May 2022
GANGA DHAM TOWERS | 1308 | 94656 | 04 May 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 183 | Tower C Electrical Pipe Laying work - | Excavation | 1947.6923 | Cu.Ft | 6.5 | 100 | 0 | 0 | 12660 | C+S GST 0% I/P RD | 0 | 12660 | 12660 | Approved | 0 | 0 | 196 | 04 May 2022
GANGA DHAM TOWERS | 1308 | 94656 | 04 May 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 183 | Tower C Electrical Pipe Laying work - | Backfilling - UDR | 1983.1429 | Cu.Ft | 3.5 | 100 | 0 | 0 | 6941 | C+S GST 0% I/P RD | 0 | 6941 | 6941 | Approved | 0 | 0 | 196 | 04 May 2022
GANGA DHAM TOWERS | 957 | 94655 | 04 May 2022 |  | LAXMI ELECTRICALS | PRAKASH CONTRACTOR | EV - 436 | Electricity Infrastructure-Trnsformer,HT,LT Work | Excavation work.- UTI | 30 | Mtrs | 160 | 100 | 0 | 0 | 4800 | CGST 0% URD I/P | 0 | 4800 | 4800 | Approved | 0 | 0 | 48 | 04 May 2022
GANGA DHAM TOWERS | 237 | 94653 | 04 May 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 447 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.9333 | Month | 7000 | 100 | 0 | 0 | 6533 | C+S GST 0% I/P RD | 0 | 6533 | 6533 | Approved | 0 | 0 | 49 | 04 May 2022
GANGA DHAM TOWERS | 258 | 94652 | 04 May 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 446 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.9 | Month | 2500 | 100 | 0 | 0 | 2250 | C+S GST 0% I/P RD | 0 | 2250 | 2250 | Approved | 0 | 0 | 17 | 04 May 2022
GANGA DHAM TOWERS | 1162 | 94651 | 04 May 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 178 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 0.9666 | Month | 5000 | 100 | 0 | 0 | 4833 | CGST 0% URD I/P | 0 | 4833 | 4833 | Approved | 0 | 0 | 48 | 04 May 2022
GANGA DHAM TOWERS | 1363 | 94650 | 04 May 2022 |  | DEEP MAN ENTERPRISES | DEEP MAN ENTERPRISES | EV - 504 | Borewell work | Casing Caping For Bore well | 70 | R.Ft | 350 | 100 | 0 | 0 | 24500 | CGST 0% URD I/P | 0 | 24500 | 24500 | Approved | 0 | 0 | 855 | 04 May 2022
GANGA DHAM TOWERS | 1363 | 94650 | 04 May 2022 |  | DEEP MAN ENTERPRISES | DEEP MAN ENTERPRISES | EV - 504 | Borewell work | Bore Survey - UWR | 1 | No. | 4000 | 100 | 0 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 855 | 04 May 2022
GANGA DHAM TOWERS | 1363 | 94650 | 04 May 2022 |  | DEEP MAN ENTERPRISES | DEEP MAN ENTERPRISES | EV - 504 | Borewell work | 6" Bore Well | 600 | R.Ft | 95 | 100 | 0 | 0 | 57000 | CGST 0% URD I/P | 0 | 57000 | 57000 | Approved | 0 | 0 | 855 | 04 May 2022
GANGA DHAM TOWERS | 413 | 94624 | 02 May 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 264 | Sales office Garden Maintenance | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 10 | 02 May 2022
GANGA DHAM TOWERS | 178 | 94623 | 02 May 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 265 | Sales office Garden Maintenance | Garden work. | 58.995 | Day | 420.83 | 100 | 0 | 0 | 24826.87 | C+S GST 18% I/P RD | 4468.84 | 29295.71 | 29295.71 | Approved | 0 | 0 | 248 | 02 May 2022
GANGA DHAM TOWERS | 1297 | 94622 | 02 May 2022 |  | MANALI HEMANT PHARATE | MANALI HEMANT PHARATE | EV - 123 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 1 | Month | 1000 | 100 | 0 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 0 | 02 May 2022
GANGA DHAM TOWERS | 455 | 94621 | 02 May 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 190 | A Bldg Flat No. 1104 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.6667 | No. | 1200 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 20 | 02 May 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 3rd floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 4th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 14th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 11th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 13th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 14th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 16th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 11th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 14th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 20th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 2nd floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 16th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 20th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 5th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 6th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 5th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 22nd floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 18th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 24th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 12th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 10th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 1st floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 4th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 6th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside1st floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 12th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 15th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 24th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 23rd floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 2nd floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 16th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 18th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 13th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 6th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 21st floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 1st floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 9th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 11th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 20th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 7th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 3rd floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 2nd floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 18th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 5th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 8th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 17th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 19th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 10th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 17th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 12th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 4th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 21st floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 22nd floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 7th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 9th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 10th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 8th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 23rd floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 3rd floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 19th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 17th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 19th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 21st floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 24th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 13th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 7th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 23rd floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 8th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Eastside 9th floor External Texture Painting | Texture Paint (M) | 520.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 15th floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A South side 22nd floor External Texture Painting | Texture Paint (M) | 264 | Sq.Ft | 7.25 | 100 | 0 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 845 | 94615 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 410 | A Northside 15th floor External Texture Painting | Texture Paint (M) | 279.0345 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 0 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 13th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 10th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 12th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 14th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 8th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 17th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 7th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 18th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 16th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 17th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 5th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 6th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 5th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 6th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 4th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 5th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 9th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 22nd floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 14th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 15th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 13th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 8th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 19th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 23rd floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 24th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 3rd floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 11th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 17th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 2nd floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 23rd floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 2nd floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 20th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 1st floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 3rd floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 19th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 1st floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 10th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 15th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 24th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside1st floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 9th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 18th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 16th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 23rd floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 13th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 16th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 14th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 15th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 10th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 12th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 21st floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 9th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 3rd floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 19th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 7th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 7th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 22nd floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 20th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 22nd floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 6th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 24th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 11th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 12th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 2nd floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 11th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 20th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 4th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 8th floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 21st floor External Texture Painting | Scaffolding/Gondola work | 521.1429 | Sq.Ft | 3.5 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 4th floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 21st floor External Texture Painting | Scaffolding/Gondola work | 264 | Sq.Ft | 3.5 | 100 | 23.1 | 0 | 924 | C+S GST 18% I/P RD | 166.32 | 1090.32 | 1090.32 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 18th floor External Texture Painting | Scaffolding/Gondola work | 279.1429 | Sq.Ft | 3.5 | 100 | 24.43 | 0 | 977 | C+S GST 18% I/P RD | 175.86 | 1152.86 | 1152.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 12th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 18th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 18th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 10th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 8th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 17th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 13th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 8th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 9th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 3rd floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 19th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 19th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 11th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 22nd floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside1st floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 17th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 1st floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 10th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 17th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 24th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 15th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 1st floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 2nd floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 4th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 9th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 16th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 16th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 19th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 7th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 23rd floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 18th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 16th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 5th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 22nd floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 12th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 8th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 6th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 13th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 11th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 15th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 6th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 22nd floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 24th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 20th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 3rd floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 14th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 2nd floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 9th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 2nd floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 21st floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 13th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 14th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 15th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 20th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 3rd floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 4th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 6th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 21st floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 5th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 7th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 12th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 5th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 23rd floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 23rd floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 7th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 4th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 20th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 21st floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Northside 24th floor External Texture Painting | Texture Paint (L) | 279.0345 | Sq.Ft | 7.25 | 100 | 50.58 | 0 | 2023 | C+S GST 18% I/P RD | 364.14 | 2387.14 | 2387.14 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 14th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A South side 10th floor External Texture Painting | Texture Paint (L) | 264 | Sq.Ft | 7.25 | 100 | 47.85 | 0 | 1914 | C+S GST 18% I/P RD | 344.52 | 2258.52 | 2258.52 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 844 | 94614 | 30 Apr 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 355 | A Eastside 11th floor External Texture Painting | Texture Paint (L) | 520.9655 | Sq.Ft | 7.25 | 100 | 94.42 | 0 | 3777 | C+S GST 18% I/P RD | 679.86 | 4456.86 | 4456.86 | Approved | 0 | 0 | 2745 | 30 Apr 2022
GANGA DHAM TOWERS | 1248 | 94592 | 29 Apr 2022 |  | AVCON TECHNICS PVT LTD | JAY BHAVANI ENTERPRISES | EV - 192 | B 201 NOC | Blockwork 4" - BC | 53.38 | Sq.Ft | 24 | 100 | 32.03 | 0 | 1281.12 | CGST 0% URD I/P | 0 | 1281.12 | 1281.12 | Approved | 0 | 0 | 13 | 29 Apr 2022
GANGA DHAM TOWERS | 1287 | 94591 | 29 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 140 | B 2302 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 259.3091 | Sq.Ft | 55 | 100 | 356.55 | 0 | 14262 | CGST 0% URD I/P | 0 | 14262 | 14262 | Approved | 0 | 0 | 1065 | 29 Apr 2022
GANGA DHAM TOWERS | 1287 | 94591 | 29 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 140 | B 502 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 259.3091 | Sq.Ft | 55 | 100 | 356.55 | 0 | 14262 | CGST 0% URD I/P | 0 | 14262 | 14262 | Approved | 0 | 0 | 1065 | 29 Apr 2022
GANGA DHAM TOWERS | 1287 | 94591 | 29 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 140 | B 2401 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 233.3091 | Sq.Ft | 55 | 100 | 320.8 | 0 | 12832 | CGST 0% URD I/P | 0 | 12832 | 12832 | Approved | 0 | 0 | 1065 | 29 Apr 2022
GANGA DHAM TOWERS | 1287 | 94591 | 29 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 140 | B 601 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 247.9636 | Sq.Ft | 55 | 100 | 340.95 | 0 | 13638 | CGST 0% URD I/P | 0 | 13638 | 13638 | Approved | 0 | 0 | 1065 | 29 Apr 2022
GANGA DHAM TOWERS | 1287 | 94591 | 29 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 140 | B 2502 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 178.2727 | Sq.Ft | 55 | 100 | 245.12 | 0 | 9805 | CGST 0% URD I/P | 0 | 9805 | 9805 | Approved | 0 | 0 | 1065 | 29 Apr 2022
GANGA DHAM TOWERS | 1287 | 94591 | 29 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 140 | B 702 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 259.3091 | Sq.Ft | 55 | 100 | 356.55 | 0 | 14262 | CGST 0% URD I/P | 0 | 14262 | 14262 | Approved | 0 | 0 | 1065 | 29 Apr 2022
GANGA DHAM TOWERS | 1287 | 94591 | 29 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 140 | B 602 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 259.3091 | Sq.Ft | 55 | 100 | 356.55 | 0 | 14262 | CGST 0% URD I/P | 0 | 14262 | 14262 | Approved | 0 | 0 | 1065 | 29 Apr 2022
GANGA DHAM TOWERS | 1287 | 94591 | 29 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 140 | B 2402 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 240.0545 | Sq.Ft | 55 | 100 | 330.07 | 0 | 13203 | CGST 0% URD I/P | 0 | 13203 | 13203 | Approved | 0 | 0 | 1065 | 29 Apr 2022
GANGA DHAM TOWERS | 1170 | 94590 | 29 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 184 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 50mm dia.(L) | 10.85 | Mtrs | 200 | 100 | 54.25 | 0 | 2170 | C+S GST 18% I/P RD | 390.6 | 2560.6 | 2560.6 | Approved | 0 | 0 | 1653 | 29 Apr 2022
GANGA DHAM TOWERS | 1170 | 94590 | 29 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 184 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 40mm dia.(L) | 140 | Mtrs | 165 | 100 | 577.5 | 0 | 23100 | C+S GST 18% I/P RD | 4158 | 27258 | 27258 | Approved | 0 | 0 | 1653 | 29 Apr 2022
GANGA DHAM TOWERS | 1170 | 94590 | 29 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 184 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 25mm dia-(L) | 284 | Mtrs | 110 | 100 | 781 | 0 | 31240 | C+S GST 18% I/P RD | 5623.2 | 36863.2 | 36863.2 | Approved | 0 | 0 | 1653 | 29 Apr 2022
GANGA DHAM TOWERS | 1170 | 94590 | 29 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 184 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 80mm dia.(L) | 15.3 | Mtrs | 270 | 100 | 103.28 | 0 | 4131 | C+S GST 18% I/P RD | 743.58 | 4874.58 | 4874.58 | Approved | 0 | 0 | 1653 | 29 Apr 2022
GANGA DHAM TOWERS | 1170 | 94590 | 29 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 184 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 65mm dia.(L) | 62.4489 | Mtrs | 225 | 100 | 0 | 0 | 14051 | C+S GST 18% I/P RD | 2529.18 | 16580.18 | 16580.18 | Approved | 0 | 0 | 1653 | 29 Apr 2022
GANGA DHAM TOWERS | 1170 | 94590 | 29 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 184 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 32mm dia.(L) | 57 | Mtrs | 140 | 100 | 199.5 | 0 | 7980 | C+S GST 18% I/P RD | 1436.4 | 9416.4 | 9416.4 | Approved | 0 | 0 | 1653 | 29 Apr 2022
GANGA DHAM TOWERS | 1089 | 94582 | 28 Apr 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 678 | Lt Substation Built-up Area (L) | RCC Superstructure (B-up area) | 121.3091 | Sq.Ft | 220 | 100 | 0 | 0 | 26688 | C+S GST 18% I/P RD | 4803.84 | 31491.84 | 31491.84 | Approved | 0 | 0 | 267 | 28 Apr 2022
GANGA DHAM TOWERS | 982 | 94562 | 27 Apr 2022 |  | S J INDUSTRIES | S J INDUSTRIES | EV - 356 | D H Frame Scaffolding for Platser Work | M.S. Planks | 25 | No. | 1350 | 100 | 0 | 0 | 33750 | C+S GST 18% I/P RD | 6075 | 39825 | 39825 | Approved | 0 | 0 | 0 | 27 Apr 2022
GANGA DHAM TOWERS | 982 | 94562 | 27 Apr 2022 |  | S J INDUSTRIES | S J INDUSTRIES | EV - 356 | D H Frame Scaffolding for Platser Work | H Frame & Cross Bracing | 150 | set | 5800 | 100 | 0 | 0 | 870000 | C+S GST 18% I/P RD | 156600 | 1026600 | 1026600 | Approved | 0 | 0 | 0 | 27 Apr 2022
GANGA DHAM TOWERS | 1228 | 94561 | 31 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | KIRAN TUKARAM DHANAWADE | EV - 2339 | Site Expenses | Site Expenses -SO | 0.1463 | Month | 15000 | 100 | 0 | 0 | 2195 | C+S GST 0% I/P RD | 0 | 2195 | 2195 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 1228 | 94561 | 31 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | KIRAN TUKARAM DHANAWADE | EV - 2339 | Site Expenses | Site Expenses -SO | 0.09 | Month | 15000 | 100 | 0 | 0 | 1350 | C+S GST 0% I/P RD | 0 | 1350 | 1350 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 1228 | 94561 | 31 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | KIRAN TUKARAM DHANAWADE | EV - 2339 | Site Expenses | Site Expenses -SO | 0.2453 | Month | 15000 | 100 | 0 | 0 | 3680 | C+S GST 0% I/P RD | 0 | 3680 | 3680 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 389 | 94544 | 25 Apr 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 74 | Loading / Unloading Expenses | Unloading work-SO | 3 | No. | 1000 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 0 | 25 Apr 2022
GANGA DHAM TOWERS | 389 | 94544 | 25 Apr 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 74 | Loading / Unloading Expenses | Unloading of AAC Blocks | 4798 | No. | 2 | 100 | 0 | 0 | 9596 | CGST 0% URD I/P | 0 | 9596 | 9596 | Approved | 0 | 0 | 0 | 25 Apr 2022
GANGA DHAM TOWERS | 1228 | 94530 | 22 Apr 2022 |  | KIRAN TUKARAM DHANAWADE | KIRAN TUKARAM DHANAWADE | EV - 122 | Site Expenses | Site Expenses -SO | 0.2159 | Month | 15000 | 100 | 0 | 0 | 3239 | C+S GST 0% I/P RD | 0 | 3239 | 3239 | Approved | 0 | 0 | 0 | 22 Apr 2022
GANGA DHAM TOWERS | 258 | 94529 | 22 Apr 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 124 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.786 | Month | 2500 | 100 | 0 | 0 | 1965 | C+S GST 0% I/P RD | 0 | 1965 | 1965 | Approved | 0 | 0 | 39 | 22 Apr 2022
GANGA DHAM TOWERS | 258 | 94529 | 22 Apr 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 124 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.774 | Month | 2500 | 100 | 0 | 0 | 1935 | C+S GST 0% I/P RD | 0 | 1935 | 1935 | Approved | 0 | 0 | 39 | 22 Apr 2022
GANGA DHAM TOWERS | 237 | 94528 | 22 Apr 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 125 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.7857 | Month | 7000 | 100 | 0 | 0 | 5500 | C+S GST 0% I/P RD | 0 | 5500 | 5500 | Approved | 0 | 0 | 109 | 22 Apr 2022
GANGA DHAM TOWERS | 237 | 94528 | 22 Apr 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 125 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.7743 | Month | 7000 | 100 | 0 | 0 | 5420 | C+S GST 0% I/P RD | 0 | 5420 | 5420 | Approved | 0 | 0 | 109 | 22 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1401 Chemical & IPS Waterproofing | IPS W/P | 220 | Sq.Ft | 11 | 100 | 242 | 0 | 2420 | CGST 0% URD I/P | 0 | 2420 | 2420 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1104 Chemical & IPS Waterproofing | IPS W/P | 289 | Sq.Ft | 11 | 100 | 317.9 | 0 | 3179 | CGST 0% URD I/P | 0 | 3179 | 3179 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1103 Chemical & IPS Waterproofing | IPS W/P | 230 | Sq.Ft | 11 | 100 | 253 | 0 | 2530 | CGST 0% URD I/P | 0 | 2530 | 2530 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1404 Chemical & IPS Waterproofing | IPS W/P | 268 | Sq.Ft | 11 | 100 | 294.8 | 0 | 2948 | CGST 0% URD I/P | 0 | 2948 | 2948 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2202 Chemical & IPS Waterproofing | IPS W/P | 307 | Sq.Ft | 11 | 100 | 337.7 | 0 | 3377 | CGST 0% URD I/P | 0 | 3377 | 3377 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2202 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2202 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1104 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1104 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1604 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1604 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2003 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 14 | No. | 70 | 100 | 98 | 0 | 980 | CGST 0% URD I/P | 0 | 980 | 980 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2003 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1103 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 14 | No. | 70 | 100 | 98 | 0 | 980 | CGST 0% URD I/P | 0 | 980 | 980 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1103 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1604 Chemical & IPS Waterproofing | IPS W/P | 248 | Sq.Ft | 11 | 100 | 272.8 | 0 | 2728 | CGST 0% URD I/P | 0 | 2728 | 2728 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1202 Chemical & IPS Waterproofing | IPS W/P | 237 | Sq.Ft | 11 | 100 | 260.7 | 0 | 2607 | CGST 0% URD I/P | 0 | 2607 | 2607 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2003 Chemical & IPS Waterproofing | IPS W/P | 190 | Sq.Ft | 11 | 100 | 209 | 0 | 2090 | CGST 0% URD I/P | 0 | 2090 | 2090 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2003 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1104 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1401 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1404 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1604 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1103 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2202 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1202 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 237 | Sq.Ft | 19 | 100 | 450.3 | 0 | 4503 | CGST 0% URD I/P | 0 | 4503 | 4503 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1401 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 220 | Sq.Ft | 19 | 100 | 418 | 0 | 4180 | CGST 0% URD I/P | 0 | 4180 | 4180 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1404 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 268 | Sq.Ft | 19 | 100 | 509.2 | 0 | 5092 | CGST 0% URD I/P | 0 | 5092 | 5092 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2202 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 307 | Sq.Ft | 19 | 100 | 583.3 | 0 | 5833 | CGST 0% URD I/P | 0 | 5833 | 5833 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2003 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 190 | Sq.Ft | 19 | 100 | 361 | 0 | 3610 | CGST 0% URD I/P | 0 | 3610 | 3610 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1604 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 248 | Sq.Ft | 19 | 100 | 471.2 | 0 | 4712 | CGST 0% URD I/P | 0 | 4712 | 4712 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1103 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 230.5263 | Sq.Ft | 19 | 100 | 438 | 0 | 4380 | CGST 0% URD I/P | 0 | 4380 | 4380 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1404 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1404 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1401 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1401 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1401 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1604 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1103 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1104 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2202 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1404 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 2003 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 401 | 94492 | 20 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 170 | A 1104 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 289 | Sq.Ft | 19 | 100 | 549.1 | 0 | 5491 | CGST 0% URD I/P | 0 | 5491 | 5491 | Approved | 0 | 0 | 907 | 20 Apr 2022
GANGA DHAM TOWERS | 413 | 94483 | 19 Apr 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 44 | Sales office Garden Maintenance | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 10 | 19 Apr 2022
GANGA DHAM TOWERS | 1228 | 94481 | 19 Apr 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 45 | R & D Purpose | R & D Purpose | 0.1932 | No. | 100000 | 100 | 0 | 0 | 19320 | C+S GST 18% I/P RD | 3477.6 | 22797.6 | 22797.6 | Approved | 0 | 0 | 386 | 19 Apr 2022
GANGA DHAM TOWERS | 1060 | 94480 | 19 Apr 2022 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 46 | D Building Steel Test | Travelling charges- SO | 1 | No. | 1120 | 100 | 0 | 0 | 1120 | C+S GST 18% I/P RD | 201.6 | 1321.6 | 1321.6 | Approved | 0 | 0 | 456 | 19 Apr 2022
GANGA DHAM TOWERS | 1060 | 94480 | 19 Apr 2022 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 46 | D Building Steel Test | Pull Out Test | 1 | No. | 4550 | 100 | 0 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 456 | 19 Apr 2022
GANGA DHAM TOWERS | 1060 | 94480 | 19 Apr 2022 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 46 | D Building Steel Test | Pull Out Test | 7 | No. | 2450 | 100 | 0 | 0 | 17150 | C+S GST 18% I/P RD | 3087 | 20237 | 20237 | Approved | 0 | 0 | 456 | 19 Apr 2022
GANGA DHAM TOWERS | 126 | 94476 | 31 Mar 2022 |  | SANDIP VAMANRAO RUPNAWAR | PUNDLIK P MAHAJAN | EV - 2341 | Site Expenses | Site Expenses -SO | 0.0881 | Month | 15000 | 100 | 0 | 0 | 1322 | CGST 0% URD I/P | 0 | 1322 | 1322 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 1228 | 94474 | 31 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 2340 | Site Expenses | Site Expenses -SO | 0.22 | Month | 15000 | 100 | 0 | 0 | 3300 | C+S GST 0% I/P RD | 0 | 3300 | 3300 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 1228 | 94474 | 31 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 2340 | Site Expenses | Site Expenses -SO | 0.582 | Month | 15000 | 100 | 0 | 0 | 8730 | C+S GST 0% I/P RD | 0 | 8730 | 8730 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 1228 | 94474 | 31 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | PUNDLIK P MAHAJAN | EV - 2340 | Site Expenses | Site Expenses -SO | 0.0421 | Month | 15000 | 100 | 0 | 0 | 631 | C+S GST 0% I/P RD | 0 | 631 | 631 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 1089 | 94473 | 19 Apr 2022 |  | UNIQUE ENTERPRISES | AJAY KUMAR GUPTA | EV - 169 | Lt Substation Built-up Area (L) | RCC Superstructure (B-up area) | 51.2727 | Sq.Ft | 220 | 100 | 0 | 0 | 11280 | CGST 0% URD I/P | 0 | 11280 | 11280 | Approved | 0 | 0 | 113 | 19 Apr 2022
GANGA DHAM TOWERS | 1089 | 94472 | 19 Apr 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 912 | Lt Substation Built-up Area (L) | RCC Superstructure (B-up area) | 1448.1818 | Sq.Ft | 220 | 100 | 0 | 0 | 318600 | C+S GST 18% I/P RD | 57348 | 375948 | 375948 | Approved | 0 | 0 | 3186 | 19 Apr 2022
GANGA DHAM TOWERS | 1225 | 94470 | 19 Apr 2022 |  | AJAY KUMAR GUPTA | AJAY KUMAR GUPTA | EV - 505 | terrace brick bat Waterproofing | Brickbat W/P 6" Sunk | 1498 | Sq.Ft | 15 | 100 | 2247 | 0 | 22470 | CGST 0% URD I/P | 0 | 22470 | 22470 | Approved | 0 | 0 | 404 | 19 Apr 2022
GANGA DHAM TOWERS | 1225 | 94470 | 19 Apr 2022 |  | AJAY KUMAR GUPTA | AJAY KUMAR GUPTA | EV - 505 | Substation Internal IPS Flooring ( Horizontal Area ) | IPS Flooring- BC | 1498 | Sq.Ft | 12 | 100 | 1797.6 | 0 | 17976 | CGST 0% URD I/P | 0 | 17976 | 17976 | Approved | 0 | 0 | 404 | 19 Apr 2022
GANGA DHAM TOWERS | 372 | 94468 | 18 Apr 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 439 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 62 | Sq.Ft | 150 | 100 | 0 | 0 | 9300 | C+S GST 18% I/P RD | 1674 | 10974 | 10974 | Approved | 0 | 0 | 930 | 18 Apr 2022
GANGA DHAM TOWERS | 372 | 94468 | 18 Apr 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 439 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 62 | Sq.Ft | 150 | 100 | 0 | 0 | 9300 | C+S GST 18% I/P RD | 1674 | 10974 | 10974 | Approved | 0 | 0 | 930 | 18 Apr 2022
GANGA DHAM TOWERS | 372 | 94468 | 18 Apr 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 439 | B Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 60 | Sq.Ft | 155 | 100 | 0 | 0 | 9300 | C+S GST 18% I/P RD | 1674 | 10974 | 10974 | Approved | 0 | 0 | 930 | 18 Apr 2022
GANGA DHAM TOWERS | 372 | 94468 | 18 Apr 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 439 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 60 | Sq.Ft | 155 | 100 | 0 | 0 | 9300 | C+S GST 18% I/P RD | 1674 | 10974 | 10974 | Approved | 0 | 0 | 930 | 18 Apr 2022
GANGA DHAM TOWERS | 372 | 94468 | 18 Apr 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 439 | B Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 60 | Sq.Ft | 155 | 100 | 0 | 0 | 9300 | C+S GST 18% I/P RD | 1674 | 10974 | 10974 | Approved | 0 | 0 | 930 | 18 Apr 2022
GANGA DHAM TOWERS | 1180 | 94467 | 18 Apr 2022 |  | M.S. CONSTRUCTION | M.S. CONSTRUCTION | EV - 128 | A Terrace Scaffolding Work | Scaffolding work | 9876.7273 | Sq.Ft | 5.5 | 100 | 1358.05 | 0 | 54322 | IGST 18% I/P RD | 9777.96 | 64099.96 | 64099.96 | Approved | 0 | 0 | 543 | 18 Apr 2022
GANGA DHAM TOWERS | 698 | 94466 | 18 Apr 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 121 | D 1105 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.072 | Sq.Ft | 9 | 100 | 206.12 | 0 | 8244.65 | C+S GST 18% I/P RD | 1484.04 | 9728.69 | 9728.69 | Approved | 0 | 0 | 142 | 18 Apr 2022
GANGA DHAM TOWERS | 698 | 94466 | 18 Apr 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 121 | D 802 (Refuge area) Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 660.928 | Sq.Ft | 9 | 100 | 148.71 | 0 | 5948.35 | C+S GST 18% I/P RD | 1070.7 | 7019.05 | 7019.05 | Approved | 0 | 0 | 142 | 18 Apr 2022
GANGA DHAM TOWERS | 1337 | 94463 | 31 Mar 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2326 | HO Expensess (L) | Printer Repairing- | 6 | Month | 8000 | 8.33 | 0 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 40 | 31 Mar 2022
GANGA DHAM TOWERS | 1337 | 94462 | 31 Mar 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2329 | HO Expensess (L) | Printer Repairing- | 5.925 | Month | 8000 | 8.33 | 0 | 0 | 3950 | C+S GST 18% I/P RD | 711 | 4661 | 4661 | Approved | 0 | 0 | 40 | 31 Mar 2022
GANGA DHAM TOWERS | 1337 | 94461 | 31 Mar 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2328 | HO Expensess (L) | Printer Repairing- | 5.925 | Month | 8000 | 8.33 | 0 | 0 | 3950 | C+S GST 18% I/P RD | 711 | 4661 | 4661 | Approved | 0 | 0 | 40 | 31 Mar 2022
GANGA DHAM TOWERS | 1337 | 94460 | 31 Mar 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2325 | HO Expensess (L) | Printer Repairing- | 6 | Month | 8000 | 8.33 | 0 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 40 | 31 Mar 2022
GANGA DHAM TOWERS | 1337 | 94459 | 31 Mar 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2324 | HO Expensess (L) | Printer Repairing- | 6 | Month | 8000 | 8.33 | 0 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 40 | 31 Mar 2022
GANGA DHAM TOWERS | 1337 | 94457 | 31 Mar 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 2323 | HO Expensess (L) | Printer Repairing- | 5.925 | Month | 8000 | 8.33 | 0 | 0 | 3950 | C+S GST 18% I/P RD | 711 | 4661 | 4661 | Approved | 0 | 0 | 40 | 31 Mar 2022
GANGA DHAM TOWERS | 1338 | 94456 | 18 Apr 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 64 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 18 Apr 2022
GANGA DHAM TOWERS | 1338 | 94455 | 18 Apr 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 65 | HO Expensess (L) | Toner refilling | 11.88 | Month | 4000 | 8.33 | 0 | 0 | 3960 | CGST 0% URD I/P | 0 | 3960 | 3960 | Approved | 0 | 0 | 40 | 18 Apr 2022
GANGA DHAM TOWERS | 1338 | 94454 | 18 Apr 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 63 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 18 Apr 2022
GANGA DHAM TOWERS | 1338 | 94453 | 18 Apr 2022 |  | SHREE VARAD ENTERPRISES | SHREE VARAD ENTERPRISES | EV - 62 | HO Expensess (L) | Toner refilling | 11.997 | Month | 4000 | 8.33 | 0 | 0 | 3999 | CGST 0% URD I/P | 0 | 3999 | 3999 | Approved | 0 | 0 | 40 | 18 Apr 2022
GANGA DHAM TOWERS | 1337 | 94452 | 18 Apr 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 67 | HO Expensess (L) | Printer Repairing- | 5.775 | Month | 8000 | 8.33 | 0 | 0 | 3850 | C+S GST 18% I/P RD | 693 | 4543 | 4543 | Approved | 0 | 0 | 39 | 18 Apr 2022
GANGA DHAM TOWERS | 1337 | 94451 | 18 Apr 2022 |  | A.S.INFOTECH SOLUTION | A.S.INFOTECH SOLUTION | EV - 66 | HO Expensess (L) | Printer Repairing- | 5.925 | Month | 8000 | 8.33 | 0 | 0 | 3950 | C+S GST 18% I/P RD | 711 | 4661 | 4661 | Approved | 0 | 0 | 40 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2302 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 60 | 100 | 308.39 | 0 | 12335.4 | C+S GST 18% I/P RD | 2220.38 | 14555.78 | 14555.78 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2302 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 60 | 100 | 989.34 | 0 | 39573.6 | C+S GST 18% I/P RD | 7123.24 | 46696.84 | 46696.84 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2302 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 60 | 100 | 404.13 | 0 | 16165.2 | C+S GST 18% I/P RD | 2909.74 | 19074.94 | 19074.94 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2302 Ceramic Tiling | Ceramic Flooring work | 153 | Sq.Ft | 21 | 100 | 80.33 | 0 | 3213 | C+S GST 18% I/P RD | 578.34 | 3791.34 | 3791.34 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2101 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 50.283 | Sq.Ft | 24 | 100 | 30.17 | 0 | 1206.79 | C+S GST 18% I/P RD | 217.22 | 1424.01 | 1424.01 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1602 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 20.1225 | R.Ft | 50 | 100 | 25.15 | 0 | 1006.13 | C+S GST 18% I/P RD | 181.1 | 1187.23 | 1187.23 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1302 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 16.995 | R.Ft | 50 | 100 | 21.24 | 0 | 849.75 | C+S GST 18% I/P RD | 152.96 | 1002.71 | 1002.71 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1401 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 50 | 100 | 24.6 | 0 | 984 | C+S GST 18% I/P RD | 177.12 | 1161.12 | 1161.12 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1501 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 50 | 100 | 24.61 | 0 | 984.38 | C+S GST 18% I/P RD | 177.18 | 1161.56 | 1161.56 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1701 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 50 | 100 | 24.61 | 0 | 984.38 | C+S GST 18% I/P RD | 177.18 | 1161.56 | 1161.56 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1301 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 50 | 100 | 24.61 | 0 | 984.38 | C+S GST 18% I/P RD | 177.18 | 1161.56 | 1161.56 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1601 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 36.6375 | R.Ft | 50 | 100 | 45.8 | 0 | 1831.88 | C+S GST 18% I/P RD | 329.74 | 2161.62 | 2161.62 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1801 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 50 | 100 | 24.6 | 0 | 984 | C+S GST 18% I/P RD | 177.12 | 1161.12 | 1161.12 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1602 Dry Balcony Dado - 1 No. | Dado BC | 73.242 | Sq.Ft | 22 | 100 | 40.28 | 0 | 1611.32 | C+S GST 18% I/P RD | 290.04 | 1901.36 | 1901.36 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1002 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 20.1225 | R.Ft | 45 | 100 | 22.64 | 0 | 905.51 | C+S GST 18% I/P RD | 163 | 1068.51 | 1068.51 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 701 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 45 | 100 | 22.15 | 0 | 885.94 | C+S GST 18% I/P RD | 159.46 | 1045.4 | 1045.4 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1101 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 36.6375 | R.Ft | 45 | 100 | 41.22 | 0 | 1648.69 | C+S GST 18% I/P RD | 296.76 | 1945.45 | 1945.45 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 902 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 16.995 | R.Ft | 45 | 100 | 19.12 | 0 | 764.78 | C+S GST 18% I/P RD | 137.66 | 902.44 | 902.44 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1201 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 45 | 100 | 22.14 | 0 | 885.6 | C+S GST 18% I/P RD | 159.4 | 1045 | 1045 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1202 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 20.1225 | R.Ft | 45 | 100 | 22.64 | 0 | 905.51 | C+S GST 18% I/P RD | 163 | 1068.51 | 1068.51 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 901 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 45 | 100 | 22.15 | 0 | 885.94 | C+S GST 18% I/P RD | 159.46 | 1045.4 | 1045.4 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 801 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 45 | 100 | 22.14 | 0 | 885.6 | C+S GST 18% I/P RD | 159.4 | 1045 | 1045 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1001 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 45 | 100 | 22.14 | 0 | 885.6 | C+S GST 18% I/P RD | 159.4 | 1045 | 1045 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1602 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 55.512 | Sq.Ft | 21 | 100 | 29.14 | 0 | 1165.75 | C+S GST 18% I/P RD | 209.84 | 1375.59 | 1375.59 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1602 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20.052 | Sq.Ft | 21 | 100 | 10.53 | 0 | 421.09 | C+S GST 18% I/P RD | 75.8 | 496.89 | 496.89 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1602 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 46.206 | Sq.Ft | 21 | 100 | 24.26 | 0 | 970.33 | C+S GST 18% I/P RD | 174.66 | 1144.99 | 1144.99 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2501 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 73 | 100 | 35.93 | 0 | 1437.19 | C+S GST 18% I/P RD | 258.7 | 1695.89 | 1695.89 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1901 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 55 | 100 | 27.07 | 0 | 1082.81 | C+S GST 18% I/P RD | 194.9 | 1277.71 | 1277.71 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2001 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 55 | 100 | 27.06 | 0 | 1082.4 | C+S GST 18% I/P RD | 194.84 | 1277.24 | 1277.24 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2201 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 55 | 100 | 27.06 | 0 | 1082.4 | C+S GST 18% I/P RD | 194.84 | 1277.24 | 1277.24 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2301 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 55 | 100 | 27.07 | 0 | 1082.81 | C+S GST 18% I/P RD | 194.9 | 1277.71 | 1277.71 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2401 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 55 | 100 | 27.06 | 0 | 1082.4 | C+S GST 18% I/P RD | 194.84 | 1277.24 | 1277.24 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2101 Terrace Parapet Top Granite - 1 No. | Granite Sill-BCo | 36.6375 | R.Ft | 55 | 100 | 50.38 | 0 | 2015.06 | C+S GST 18% I/P RD | 362.72 | 2377.78 | 2377.78 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 2102 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 148.707 | Sq.Ft | 28 | 100 | 104.09 | 0 | 4163.8 | C+S GST 18% I/P RD | 749.48 | 4913.28 | 4913.28 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1902 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 148.707 | Sq.Ft | 28 | 100 | 104.09 | 0 | 4163.8 | C+S GST 18% I/P RD | 749.48 | 4913.28 | 4913.28 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 401 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 40 | 100 | 19.68 | 0 | 787.2 | C+S GST 18% I/P RD | 141.7 | 928.9 | 928.9 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 402 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 20.1225 | R.Ft | 40 | 100 | 20.12 | 0 | 804.9 | C+S GST 18% I/P RD | 144.88 | 949.78 | 949.78 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 101 Terrace Parapet Top Granite | Granite Sill-BCo | 19.6875 | R.Ft | 40 | 100 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 201 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.68 | R.Ft | 40 | 100 | 19.68 | 0 | 787.2 | C+S GST 18% I/P RD | 141.7 | 928.9 | 928.9 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 602 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 20.1225 | R.Ft | 40 | 100 | 20.12 | 0 | 804.9 | C+S GST 18% I/P RD | 144.88 | 949.78 | 949.78 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 601 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 36.6375 | R.Ft | 40 | 100 | 36.64 | 0 | 1465.5 | C+S GST 18% I/P RD | 263.8 | 1729.3 | 1729.3 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 501 Terrace Parapet Top Granite - - 1 No. | Granite Sill-BCo | 19.6875 | R.Ft | 40 | 100 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 758 | 94444 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 127 | B 1602 Store Vitrified Flooring | Vitrified Flooring -BC | 42.48 | Sq.Ft | 21 | 100 | 22.3 | 0 | 892.08 | C+S GST 18% I/P RD | 160.58 | 1052.66 | 1052.66 | Approved | 0 | 0 | 1182 | 18 Apr 2022
GANGA DHAM TOWERS | 1146 | 94443 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 141 | B 102 NOC | Italian Marble Flooring- cc | 153.16 | Sq.Ft | 55 | 100 | 210.6 | 0 | 8423.8 | C+S GST 18% I/P RD | 1516.28 | 9940.08 | 9940.08 | Approved | 0 | 0 | 111 | 18 Apr 2022
GANGA DHAM TOWERS | 1146 | 94443 | 18 Apr 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 141 | B 102 NOC | Vitrified Flooring -cc | 180.315 | Sq.Ft | 15 | 100 | 67.62 | 0 | 2704.73 | C+S GST 18% I/P RD | 486.86 | 3191.59 | 3191.59 | Approved | 0 | 0 | 111 | 18 Apr 2022
GANGA DHAM TOWERS | 1002 | 94441 | 18 Apr 2022 |  | AVCON TECHNICS PVT LTD | Kishan Enterprises | EV - 443 | A 2002 NOC | Dado -cc | 194.49 | Sq.Ft | 22 | 100 | 106.97 | 0 | 4278.78 | C+S GST 18% I/P RD | 770.18 | 5048.96 | 5048.96 | Approved | 0 | 0 | 43 | 18 Apr 2022
GANGA DHAM TOWERS | 551 | 94437 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 187 | A 1604 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 131.173 | Sq.Ft | 55 | 100 | 180.36 | 0 | 7214.52 | C+S GST 18% I/P RD | 1298.62 | 8513.14 | 8513.14 | Approved | 0 | 0 | 596 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94437 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 187 | A 1604 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 590.89 | Sq.Ft | 55 | 100 | 812.47 | 0 | 32498.95 | C+S GST 18% I/P RD | 5849.82 | 38348.77 | 38348.77 | Approved | 0 | 0 | 596 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94437 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 187 | A 1604 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.99 | Sq.Ft | 55 | 100 | 208.99 | 0 | 8359.45 | C+S GST 18% I/P RD | 1504.7 | 9864.15 | 9864.15 | Approved | 0 | 0 | 596 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94437 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 187 | A 1604 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.44 | Sq.Ft | 55 | 100 | 289.36 | 0 | 11574.2 | C+S GST 18% I/P RD | 2083.36 | 13657.56 | 13657.56 | Approved | 0 | 0 | 596 | 16 Apr 2022
GANGA DHAM TOWERS | 372 | 94429 | 16 Apr 2022 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 263 | B Bldg 6th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20.8333 | Sq.Ft | 120 | 100 | 0 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 25 | 16 Apr 2022
GANGA DHAM TOWERS | 1287 | 94428 | 16 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | PRAKASH CONTRACTOR | EV - 147 | B 1101 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 45.4545 | Sq.Ft | 55 | 100 | 62.5 | 0 | 2500 | C+S GST 0% I/P RD | 0 | 2500 | 2500 | Approved | 0 | 0 | 25 | 16 Apr 2022
GANGA DHAM TOWERS | 1248 | 94427 | 16 Apr 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 360 | B 201 NOC | Concrete wall Crushing work | 1.125 | Cu.Mtrs | 7200 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 1301 | 16 Apr 2022
GANGA DHAM TOWERS | 1248 | 94427 | 16 Apr 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 360 | B 201 NOC | Concrete Cutting Work | 108.501 | R.Ft | 525 | 100 | 0 | 0 | 56963.01 | C+S GST 18% I/P RD | 10253.34 | 67216.35 | 67216.35 | Approved | 0 | 0 | 1301 | 16 Apr 2022
GANGA DHAM TOWERS | 1250 | 94426 | 16 Apr 2022 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 438 | B 1901 NOC | Concrete Cutting Work | 31.4286 | R.Ft | 525 | 100 | 0 | 0 | 16500 | CGST 0% URD I/P | 0 | 16500 | 16500 | Approved | 0 | 0 | 165 | 16 Apr 2022
GANGA DHAM TOWERS | 1250 | 94425 | 16 Apr 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 348 | B 1901 NOC | Concrete Cutting Work | 513.96 | R.Ft | 525 | 100 | 0 | 0 | 269829 | C+S GST 18% I/P RD | 48569.22 | 318398.22 | 318398.22 | Approved | 0 | 0 | 6173 | 16 Apr 2022
GANGA DHAM TOWERS | 1250 | 94425 | 16 Apr 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 348 | B 1901 NOC | Concrete Cutting Work | 9.1886 | R.Ft | 525 | 100 | 0 | 0 | 4824.01 | C+S GST 18% I/P RD | 868.32 | 5692.33 | 5692.33 | Approved | 0 | 0 | 6173 | 16 Apr 2022
GANGA DHAM TOWERS | 1250 | 94425 | 16 Apr 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 348 | B 1901 NOC | Concrete wall Crushing work | 4.72 | Cu.Mtrs | 7200 | 100 | 0 | 0 | 33984 | C+S GST 18% I/P RD | 6117.12 | 40101.12 | 40101.12 | Approved | 0 | 0 | 6173 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 103 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 50.775 | R.Ft | 45 | 100 | 57.12 | 0 | 2284.88 | C+S GST 18% I/P RD | 411.28 | 2696.16 | 2696.16 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 103 Master Bed Marble Flooring | Italian Marble Champher & Polish | 23.445 | R.Ft | 45 | 100 | 26.38 | 0 | 1055.03 | C+S GST 18% I/P RD | 189.9 | 1244.93 | 1244.93 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 103 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 20.835 | R.Ft | 45 | 100 | 23.44 | 0 | 937.58 | C+S GST 18% I/P RD | 168.76 | 1106.34 | 1106.34 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 901 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 50 | 100 | 41.01 | 0 | 1640.5 | C+S GST 18% I/P RD | 295.3 | 1935.8 | 1935.8 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 901 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 50 | 100 | 38.96 | 0 | 1558.5 | C+S GST 18% I/P RD | 280.54 | 1839.04 | 1839.04 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 801 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 15.79 | R.Ft | 50 | 100 | 19.74 | 0 | 789.5 | C+S GST 18% I/P RD | 142.12 | 931.62 | 931.62 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 801 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 50 | 100 | 41.01 | 0 | 1640.5 | C+S GST 18% I/P RD | 295.3 | 1935.8 | 1935.8 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 901 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 15.79 | R.Ft | 50 | 100 | 19.74 | 0 | 789.5 | C+S GST 18% I/P RD | 142.12 | 931.62 | 931.62 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 801 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 50 | 100 | 73.46 | 0 | 2938.5 | C+S GST 18% I/P RD | 528.94 | 3467.44 | 3467.44 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 801 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 50 | 100 | 38.96 | 0 | 1558.5 | C+S GST 18% I/P RD | 280.54 | 1839.04 | 1839.04 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 901 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 50 | 100 | 73.46 | 0 | 2938.5 | C+S GST 18% I/P RD | 528.94 | 3467.44 | 3467.44 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2204 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 15.79 | R.Ft | 60 | 100 | 23.69 | 0 | 947.4 | C+S GST 18% I/P RD | 170.54 | 1117.94 | 1117.94 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2302 Master Bed Marble Flooring | Italian Marble Champher & Polish | 33.45 | R.Ft | 60 | 100 | 50.18 | 0 | 2007 | C+S GST 18% I/P RD | 361.26 | 2368.26 | 2368.26 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2101 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 60 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2201 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 60 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2201 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 15.79 | R.Ft | 60 | 100 | 23.69 | 0 | 947.4 | C+S GST 18% I/P RD | 170.54 | 1117.94 | 1117.94 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2302 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 15.79 | R.Ft | 60 | 100 | 23.69 | 0 | 947.4 | C+S GST 18% I/P RD | 170.54 | 1117.94 | 1117.94 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2201 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 60 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2302 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 57.295 | R.Ft | 60 | 100 | 85.94 | 0 | 3437.7 | C+S GST 18% I/P RD | 618.78 | 4056.48 | 4056.48 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2204 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.13 | R.Ft | 60 | 100 | 87.2 | 0 | 3487.8 | C+S GST 18% I/P RD | 627.8 | 4115.6 | 4115.6 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2204 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 21.49 | R.Ft | 60 | 100 | 32.24 | 0 | 1289.4 | C+S GST 18% I/P RD | 232.1 | 1521.5 | 1521.5 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2303 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 50.775 | R.Ft | 60 | 100 | 76.16 | 0 | 3046.5 | C+S GST 18% I/P RD | 548.38 | 3594.88 | 3594.88 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2201 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 60 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2204 Master Bed Marble Flooring | Italian Marble Champher & Polish | 28.71 | R.Ft | 60 | 100 | 43.07 | 0 | 1722.6 | C+S GST 18% I/P RD | 310.06 | 2032.66 | 2032.66 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2302 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 24.835 | R.Ft | 60 | 100 | 37.25 | 0 | 1490.1 | C+S GST 18% I/P RD | 268.22 | 1758.32 | 1758.32 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2303 Master Bed Marble Flooring | Italian Marble Champher & Polish | 23.445 | R.Ft | 60 | 100 | 35.17 | 0 | 1406.7 | C+S GST 18% I/P RD | 253.2 | 1659.9 | 1659.9 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2101 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 15.79 | R.Ft | 60 | 100 | 23.69 | 0 | 947.4 | C+S GST 18% I/P RD | 170.54 | 1117.94 | 1117.94 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2303 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 20.835 | R.Ft | 60 | 100 | 31.25 | 0 | 1250.1 | C+S GST 18% I/P RD | 225.02 | 1475.12 | 1475.12 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2101 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 60 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 641 | 94421 | 16 Apr 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 193 | A 2101 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 60 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 558 | 16 Apr 2022
GANGA DHAM TOWERS | 1356 | 94418 | 16 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 143 | D Build. 1203 Blockwork 8" | Blockwork 8" - BC | 77.5 | Sq.Ft | 24 | 100 | 46.5 | 0 | 1860 | CGST 0% URD I/P | 0 | 1860 | 1860 | Approved | 0 | 0 | 1331 | 16 Apr 2022
GANGA DHAM TOWERS | 1356 | 94418 | 16 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 143 | D Build. 1205 Blockwork 8" | Blockwork 8" - BC | 204.0833 | Sq.Ft | 24 | 100 | 122.45 | 0 | 4898 | CGST 0% URD I/P | 0 | 4898 | 4898 | Approved | 0 | 0 | 1331 | 16 Apr 2022
GANGA DHAM TOWERS | 1356 | 94418 | 16 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 143 | D Build. 1201 Blockwork 8" | Blockwork 8" - BC | 62 | Sq.Ft | 24 | 100 | 37.2 | 0 | 1488 | CGST 0% URD I/P | 0 | 1488 | 1488 | Approved | 0 | 0 | 1331 | 16 Apr 2022
GANGA DHAM TOWERS | 1356 | 94418 | 16 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 143 | D Build. 1204 Blockwork 8" | Blockwork 8" - BC | 206.6667 | Sq.Ft | 24 | 100 | 124 | 0 | 4960 | CGST 0% URD I/P | 0 | 4960 | 4960 | Approved | 0 | 0 | 1331 | 16 Apr 2022
GANGA DHAM TOWERS | 1356 | 94418 | 16 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 143 | D Bldg Blockwork Rate Diff From 1 to 11 Floor - 1 No. | 8" Blockwork Rate Diff. | 7230.6667 | Sq.Ft | 3 | 100 | 542.3 | 0 | 21692 | CGST 0% URD I/P | 0 | 21692 | 21692 | Approved | 0 | 0 | 1331 | 16 Apr 2022
GANGA DHAM TOWERS | 1356 | 94418 | 16 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 143 | D Bldg Blockwork Rate Diff From 1 to 11 Floor - 1 No. | 5'' Blockwork Rate Diff. | 49101.8 | Sq.Ft | 2 | 100 | 2455.09 | 0 | 98203.6 | CGST 0% URD I/P | 0 | 98203.6 | 98203.6 | Approved | 0 | 0 | 1331 | 16 Apr 2022
GANGA DHAM TOWERS | 493 | 94417 | 16 Apr 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 177 | D Bldg Duct External Plaster | External Plaster- BC | 987.7143 | Sq.Ft | 28 | 100 | 691.4 | 0 | 27656 | C+S GST 18% I/P RD | 4978.08 | 32634.08 | 32634.08 | Approved | 0 | 0 | 277 | 16 Apr 2022
GANGA DHAM TOWERS | 522 | 94416 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 129 | B Bldg 1502 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 1250 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 75 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 104 Terrace Vitrified Flooring | Vitrified Skirting BC | 32.382 | R.Ft | 15 | 100 | 12.14 | 0 | 485.73 | C+S GST 18% I/P RD | 87.44 | 573.17 | 573.17 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 2204 Terrace Vitrified Flooring | Vitrified Skirting BC | 38.286 | R.Ft | 28 | 100 | 26.8 | 0 | 1072.01 | C+S GST 18% I/P RD | 192.96 | 1264.97 | 1264.97 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 104 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 145.746 | Sq.Ft | 15 | 100 | 54.65 | 0 | 2186.19 | C+S GST 18% I/P RD | 393.52 | 2579.71 | 2579.71 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 104 Terrace Vitrified Flooring | Vitrified Flooring -BC | 140.472 | Sq.Ft | 15 | 100 | 52.68 | 0 | 2107.08 | C+S GST 18% I/P RD | 379.28 | 2486.36 | 2486.36 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 2004 Staff Room Vitrified Flooring | Vitrified Skirting BC | 14.168 | R.Ft | 24 | 100 | 8.5 | 0 | 340.03 | C+S GST 18% I/P RD | 61.2 | 401.23 | 401.23 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 2003 Staff Room Vitrified Flooring | Vitrified Skirting BC | 28.044 | R.Ft | 24 | 100 | 16.83 | 0 | 673.06 | C+S GST 18% I/P RD | 121.16 | 794.22 | 794.22 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 2204 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 28 | 100 | 111.89 | 0 | 4475.77 | C+S GST 18% I/P RD | 805.64 | 5281.41 | 5281.41 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 2003 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 103.896 | Sq.Ft | 28 | 100 | 72.73 | 0 | 2909.09 | C+S GST 18% I/P RD | 523.64 | 3432.73 | 3432.73 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 2004 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 41.265 | Sq.Ft | 24 | 100 | 24.76 | 0 | 990.36 | C+S GST 18% I/P RD | 178.26 | 1168.62 | 1168.62 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 551 | 94415 | 16 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 253 | A 2003 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 64.521 | Sq.Ft | 24 | 100 | 38.71 | 0 | 1548.5 | C+S GST 18% I/P RD | 278.74 | 1827.24 | 1827.24 | Approved | 0 | 0 | 168 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 802 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2102 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1902 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2002 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1001 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2302 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 601 Chemical Grouting | Chemical Grouting.- BC | 2330.62 | Sq.Ft | 2 | 100 | 466.12 | 0 | 4661.24 | CGST 0% URD I/P | 0 | 4661.24 | 4661.24 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 501 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 601 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 201 Chemical Grouting | Chemical Grouting.- BC | 2535 | Sq.Ft | 2 | 100 | 507 | 0 | 5070 | CGST 0% URD I/P | 0 | 5070 | 5070 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 802 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 601 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 501 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2002 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1001 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2002 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 802 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1001 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2102 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2002 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 27 | No. | 70 | 100 | 189 | 0 | 1890 | CGST 0% URD I/P | 0 | 1890 | 1890 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 601 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 29 | No. | 70 | 100 | 203 | 0 | 2030 | CGST 0% URD I/P | 0 | 2030 | 2030 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1001 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 29 | No. | 70 | 100 | 203 | 0 | 2030 | CGST 0% URD I/P | 0 | 2030 | 2030 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 802 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 27 | No. | 70 | 100 | 189 | 0 | 1890 | CGST 0% URD I/P | 0 | 1890 | 1890 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 501 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 29 | No. | 70 | 100 | 203 | 0 | 2030 | CGST 0% URD I/P | 0 | 2030 | 2030 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1001 Chemical & IPS Waterproofing | IPS W/P | 301 | Sq.Ft | 11 | 100 | 331.1 | 0 | 3311 | CGST 0% URD I/P | 0 | 3311 | 3311 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2002 Chemical & IPS Waterproofing | IPS W/P | 468.45 | Sq.Ft | 11 | 100 | 515.3 | 0 | 5152.95 | CGST 0% URD I/P | 0 | 5152.95 | 5152.95 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 802 Chemical & IPS Waterproofing | IPS W/P | 468.45 | Sq.Ft | 11 | 100 | 515.3 | 0 | 5152.95 | CGST 0% URD I/P | 0 | 5152.95 | 5152.95 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1902 Chemical & IPS Waterproofing - | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 601 Chemical & IPS Waterproofing | IPS W/P | 400 | Sq.Ft | 11 | 100 | 440 | 0 | 4400 | CGST 0% URD I/P | 0 | 4400 | 4400 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 501 Chemical & IPS Waterproofing | IPS W/P | 388 | Sq.Ft | 11 | 100 | 426.8 | 0 | 4268 | CGST 0% URD I/P | 0 | 4268 | 4268 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2102 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2102 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1902 Chemical & IPS Waterproofing - | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 802 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 424.6316 | Sq.Ft | 19 | 100 | 806.8 | 0 | 8068 | CGST 0% URD I/P | 0 | 8068 | 8068 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 501 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 388.7895 | Sq.Ft | 19 | 100 | 738.7 | 0 | 7387 | CGST 0% URD I/P | 0 | 7387 | 7387 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 2002 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 424.6316 | Sq.Ft | 19 | 100 | 806.8 | 0 | 8068 | CGST 0% URD I/P | 0 | 8068 | 8068 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 601 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 400 | Sq.Ft | 19 | 100 | 760 | 0 | 7600 | CGST 0% URD I/P | 0 | 7600 | 7600 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 498 | 94414 | 16 Apr 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 144 | B 1001 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 388.7895 | Sq.Ft | 19 | 100 | 738.7 | 0 | 7387 | CGST 0% URD I/P | 0 | 7387 | 7387 | Approved | 0 | 0 | 1153 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2301 Terrace Vitrified Flooring | Vitrified Skirting BC | 32.382 | R.Ft | 28 | 100 | 22.67 | 0 | 906.7 | C+S GST 18% I/P RD | 163.2 | 1069.9 | 1069.9 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2201 Terrace Vitrified Flooring | Vitrified Skirting BC | 39.177 | R.Ft | 28 | 100 | 27.42 | 0 | 1096.96 | C+S GST 18% I/P RD | 197.46 | 1294.42 | 1294.42 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2001 Terrace Vitrified Flooring | Vitrified Skirting BC | 39.177 | R.Ft | 28 | 100 | 27.42 | 0 | 1096.96 | C+S GST 18% I/P RD | 197.46 | 1294.42 | 1294.42 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2302 Terrace Vitrified Flooring | Vitrified Skirting BC | 32.382 | R.Ft | 28 | 100 | 22.67 | 0 | 906.7 | C+S GST 18% I/P RD | 163.2 | 1069.9 | 1069.9 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2001 Staff Room Vitrified Flooring | Vitrified Skirting BC | 13.648 | R.Ft | 24 | 100 | 8.19 | 0 | 327.55 | C+S GST 18% I/P RD | 58.96 | 386.51 | 386.51 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 1802 Terrace Vitrified Flooring | Vitrified Skirting BC | 38.286 | R.Ft | 24 | 100 | 22.97 | 0 | 918.86 | C+S GST 18% I/P RD | 165.4 | 1084.26 | 1084.26 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 1801 Terrace Vitrified Flooring | Vitrified Skirting BC | 39.177 | R.Ft | 24 | 100 | 23.51 | 0 | 940.25 | C+S GST 18% I/P RD | 169.24 | 1109.49 | 1109.49 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2001 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 28 | 100 | 111.89 | 0 | 4475.77 | C+S GST 18% I/P RD | 805.64 | 5281.41 | 5281.41 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2201 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 28 | 100 | 111.89 | 0 | 4475.77 | C+S GST 18% I/P RD | 805.64 | 5281.41 | 5281.41 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2302 Terrace Vitrified Flooring | Vitrified Flooring -BC | 140.472 | Sq.Ft | 28 | 100 | 98.33 | 0 | 3933.22 | C+S GST 18% I/P RD | 707.98 | 4641.2 | 4641.2 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 1801 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 24 | 100 | 95.91 | 0 | 3836.38 | C+S GST 18% I/P RD | 690.54 | 4526.92 | 4526.92 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2001 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 39.645 | Sq.Ft | 24 | 100 | 23.79 | 0 | 951.48 | C+S GST 18% I/P RD | 171.26 | 1122.74 | 1122.74 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 1802 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 24 | 100 | 95.91 | 0 | 3836.38 | C+S GST 18% I/P RD | 690.54 | 4526.92 | 4526.92 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2002 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 40.617 | Sq.Ft | 24 | 100 | 24.37 | 0 | 974.81 | C+S GST 18% I/P RD | 175.46 | 1150.27 | 1150.27 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2002 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.726 | Sq.Ft | 24 | 100 | 13.04 | 0 | 521.42 | C+S GST 18% I/P RD | 93.86 | 615.28 | 615.28 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 2002 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 38.754 | Sq.Ft | 24 | 100 | 23.25 | 0 | 930.1 | C+S GST 18% I/P RD | 167.42 | 1097.52 | 1097.52 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 537 | 94413 | 16 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 196 | A 901 Terrace Vitrified Flooring | Vitrified Skirting BC | 32.382 | R.Ft | 20 | 100 | 16.19 | 0 | 647.64 | C+S GST 18% I/P RD | 116.58 | 764.22 | 764.22 | Approved | 0 | 0 | 308 | 16 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1802 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1801 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1601 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1801 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 3 | No. | 150 | 100 | 45 | 0 | 450 | CGST 0% URD I/P | 0 | 450 | 450 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2201 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2402 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1903 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2002 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2004 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1904 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2001 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2002 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2201 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2402 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1802 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2004 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1903 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1601 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2001 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2401 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2401 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2201 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2402 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1801 Chemical & IPS Waterproofing | IPS W/P | 161 | Sq.Ft | 11 | 100 | 177.1 | 0 | 1771 | CGST 0% URD I/P | 0 | 1771 | 1771 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1601 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2002 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2004 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1802 Chemical & IPS Waterproofing | IPS W/P | 177 | Sq.Ft | 11 | 100 | 194.7 | 0 | 1947 | CGST 0% URD I/P | 0 | 1947 | 1947 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1104 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1604 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1503 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1504 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2104 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2202 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1103 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1904 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1904 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 223 | Sq.Ft | 19 | 100 | 423.7 | 0 | 4237 | CGST 0% URD I/P | 0 | 4237 | 4237 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2004 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1801 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 161 | Sq.Ft | 19 | 100 | 305.9 | 0 | 3059 | CGST 0% URD I/P | 0 | 3059 | 3059 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2201 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2402 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1802 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2002 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1601 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2401 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 177 | Sq.Ft | 19 | 100 | 336.3 | 0 | 3363 | CGST 0% URD I/P | 0 | 3363 | 3363 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1103 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1503 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1104 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1504 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1401 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2104 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 2202 Chemical Grouting Work | Chemical Grouting.- BC | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1604 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 401 | 94400 | 15 Apr 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 142 | A 1404 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 767 | 15 Apr 2022
GANGA DHAM TOWERS | 1184 | 94397 | 15 Apr 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 205 | D Parking to 1st Floor Staircase 1 & 2 Riser Plaster - 1 | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 120 | 15 Apr 2022
GANGA DHAM TOWERS | 1184 | 94397 | 15 Apr 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 205 | D 8th to 9th Floor Staircase 1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 120 | 15 Apr 2022
GANGA DHAM TOWERS | 1184 | 94397 | 15 Apr 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 205 | D 9th to 10th Floor Staircase1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 120 | 15 Apr 2022
GANGA DHAM TOWERS | 551 | 94396 | 15 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 191 | A 2204 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 93.008 | R.Ft | 60 | 100 | 139.51 | 0 | 5580.48 | C+S GST 18% I/P RD | 1004.48 | 6584.96 | 6584.96 | Approved | 0 | 0 | 104 | 15 Apr 2022
GANGA DHAM TOWERS | 551 | 94396 | 15 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 191 | A 2204 Master Bed Marble Flooring | Italian marble Skirting - BCo | 45.936 | R.Ft | 60 | 100 | 68.9 | 0 | 2756.16 | C+S GST 18% I/P RD | 496.1 | 3252.26 | 3252.26 | Approved | 0 | 0 | 104 | 15 Apr 2022
GANGA DHAM TOWERS | 551 | 94396 | 15 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 191 | A 2204 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 34.384 | R.Ft | 60 | 100 | 51.58 | 0 | 2063.04 | C+S GST 18% I/P RD | 371.34 | 2434.38 | 2434.38 | Approved | 0 | 0 | 104 | 15 Apr 2022
GANGA DHAM TOWERS | 1296 | 94395 | 31 Mar 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 2315 | Miscellaneous expenses | Marketing Operating Expenses | 6.1772 | Month | 25000 | 8.33 | 0 | 0 | 12864 | C+S GST 0% I/P RD | 0 | 12864 | 12864 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 1296 | 94395 | 31 Mar 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 2315 | Miscellaneous expenses | Marketing Operating Expenses | 2.6103 | Month | 25000 | 8.33 | 0 | 0 | 5436 | C+S GST 0% I/P RD | 0 | 5436 | 5436 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1401 Terrace Vitrified Flooring | Vitrified Flooring -BC | 41.6667 | Sq.Ft | 24 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1301 Terrace Vitrified Flooring | Vitrified Flooring -BC | 39 | Sq.Ft | 24 | 100 | 23.4 | 0 | 936 | C+S GST 18% I/P RD | 168.48 | 1104.48 | 1104.48 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1402 Terrace Vitrified Flooring | Vitrified Flooring -BC | 67 | Sq.Ft | 24 | 100 | 40.2 | 0 | 1608 | C+S GST 18% I/P RD | 289.44 | 1897.44 | 1897.44 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1702 Terrace Vitrified Flooring | Vitrified Flooring -BC | 39 | Sq.Ft | 24 | 100 | 23.4 | 0 | 936 | C+S GST 18% I/P RD | 168.48 | 1104.48 | 1104.48 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1602 Terrace Vitrified Flooring | Vitrified Flooring -BC | 43 | Sq.Ft | 24 | 100 | 25.8 | 0 | 1032 | C+S GST 18% I/P RD | 185.76 | 1217.76 | 1217.76 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 602 Terrace Vitrified Flooring | Vitrified Flooring -BC | 66.6667 | Sq.Ft | 15 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1901 Terrace Vitrified Flooring | Vitrified Flooring -BC | 16 | Sq.Ft | 28 | 100 | 11.2 | 0 | 448 | C+S GST 18% I/P RD | 80.64 | 528.64 | 528.64 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 2301 Terrace Vitrified Flooring | Vitrified Flooring -BC | 134.2288 | Sq.Ft | 28 | 100 | 93.96 | 0 | 3758.41 | C+S GST 18% I/P RD | 676.52 | 4434.93 | 4434.93 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1902 Terrace Vitrified Flooring | Vitrified Flooring -BC | 16 | Sq.Ft | 28 | 100 | 11.2 | 0 | 448 | C+S GST 18% I/P RD | 80.64 | 528.64 | 528.64 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 101 Terrace Vitrified Flooring | Vitrified Flooring -BC | 66.6667 | Sq.Ft | 15 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 501 Terrace Vitrified Flooring | Vitrified Flooring -BC | 66.6667 | Sq.Ft | 15 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 2201 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 94.032 | R.Ft | 60 | 100 | 141.05 | 0 | 5641.92 | C+S GST 18% I/P RD | 1015.54 | 6657.46 | 6657.46 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 2201 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 60 | 100 | 74.81 | 0 | 2992.32 | C+S GST 18% I/P RD | 538.62 | 3530.94 | 3530.94 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 2302 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 91.672 | R.Ft | 60 | 100 | 137.51 | 0 | 5500.32 | C+S GST 18% I/P RD | 990.06 | 6490.38 | 6490.38 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 2302 Master Bed Marble Flooring | Italian marble Skirting - BCo | 53.52 | R.Ft | 60 | 100 | 80.28 | 0 | 3211.2 | C+S GST 18% I/P RD | 578.02 | 3789.22 | 3789.22 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 2302 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 39.736 | R.Ft | 60 | 100 | 59.6 | 0 | 2384.16 | C+S GST 18% I/P RD | 429.14 | 2813.3 | 2813.3 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 2201 Master Bed Marble Flooring | Italian marble Skirting - BCo | 52.496 | R.Ft | 60 | 100 | 78.74 | 0 | 3149.76 | C+S GST 18% I/P RD | 566.96 | 3716.72 | 3716.72 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1002 Terrace Vitrified Flooring | Vitrified Flooring -BC | 10 | Sq.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 902 Terrace Vitrified Flooring | Vitrified Flooring -BC | 46 | Sq.Ft | 20 | 100 | 23 | 0 | 920 | C+S GST 18% I/P RD | 165.6 | 1085.6 | 1085.6 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 801 Terrace Vitrified Flooring | Vitrified Flooring -BC | 50 | Sq.Ft | 20 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 901 Terrace Vitrified Flooring | Vitrified Flooring -BC | 46 | Sq.Ft | 20 | 100 | 23 | 0 | 920 | C+S GST 18% I/P RD | 165.6 | 1085.6 | 1085.6 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1001 Terrace Vitrified Flooring | Vitrified Flooring -BC | 10 | Sq.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1201 Terrace Vitrified Flooring | Vitrified Flooring -BC | 39 | Sq.Ft | 20 | 100 | 19.5 | 0 | 780 | C+S GST 18% I/P RD | 140.4 | 920.4 | 920.4 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 537 | 94394 | 15 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 194 | A 1201 Terrace Vitrified Flooring | Vitrified Flooring -BC | 20 | Sq.Ft | 20 | 100 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 405 | 15 Apr 2022
GANGA DHAM TOWERS | 1172 | 94372 | 13 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 181 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 150mm dia.(L) | 197 | Mtrs | 540 | 100 | 2659.5 | 0 | 106380 | C+S GST 18% I/P RD | 19148.4 | 125528.4 | 125528.4 | Approved | 0 | 0 | 2892 | 13 Apr 2022
GANGA DHAM TOWERS | 1172 | 94372 | 13 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 181 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 25mm dia-(L) | 192.5 | Mtrs | 110 | 100 | 529.38 | 0 | 21175 | C+S GST 18% I/P RD | 3811.5 | 24986.5 | 24986.5 | Approved | 0 | 0 | 2892 | 13 Apr 2022
GANGA DHAM TOWERS | 1172 | 94372 | 13 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 181 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 40mm dia.(L) | 46.8 | Mtrs | 165 | 100 | 193.05 | 0 | 7722 | C+S GST 18% I/P RD | 1389.96 | 9111.96 | 9111.96 | Approved | 0 | 0 | 2892 | 13 Apr 2022
GANGA DHAM TOWERS | 1172 | 94372 | 13 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 181 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 32mm dia.(L) | 66.5 | Mtrs | 140 | 100 | 232.75 | 0 | 9310 | C+S GST 18% I/P RD | 1675.8 | 10985.8 | 10985.8 | Approved | 0 | 0 | 2892 | 13 Apr 2022
GANGA DHAM TOWERS | 1174 | 94371 | 13 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 185 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 25mm dia-(L) | 136.2 | Mtrs | 110 | 100 | 374.55 | 0 | 14982 | C+S GST 18% I/P RD | 2696.76 | 17678.76 | 17678.76 | Approved | 0 | 0 | 4455 | 13 Apr 2022
GANGA DHAM TOWERS | 1174 | 94371 | 13 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 185 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 40mm dia.(L) | 43 | Mtrs | 165 | 100 | 177.38 | 0 | 7095 | C+S GST 18% I/P RD | 1277.1 | 8372.1 | 8372.1 | Approved | 0 | 0 | 4455 | 13 Apr 2022
GANGA DHAM TOWERS | 1174 | 94371 | 13 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 185 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 150mm dia.(L) | 359 | Mtrs | 540 | 100 | 4846.5 | 0 | 193860 | C+S GST 18% I/P RD | 34894.8 | 228754.8 | 228754.8 | Approved | 0 | 0 | 4455 | 13 Apr 2022
GANGA DHAM TOWERS | 1174 | 94371 | 13 Apr 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 185 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 32mm dia.(L) | 48.7214 | Mtrs | 140 | 100 | 170.52 | 0 | 6821 | C+S GST 18% I/P RD | 1227.78 | 8048.78 | 8048.78 | Approved | 0 | 0 | 4455 | 13 Apr 2022
GANGA DHAM TOWERS | 1119 | 94369 | 13 Apr 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 29 | C Bldg 2nd RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 6033.74 | Sq.Ft | 175 | 100 | 26397.61 | 0 | 1055904.5 | C+S GST 18% I/P RD | 190062.82 | 1245967.32 | 1245967.32 | Approved | 0 | 847457 | 21118 | 13 Apr 2022
GANGA DHAM TOWERS | 1119 | 94369 | 13 Apr 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 29 | C Bldg 2nd RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 6033.73 | Sq.Ft | 175 | 100 | 26397.57 | 0 | 1055902.75 | C+S GST 18% I/P RD | 190062.5 | 1245965.25 | 1245965.25 | Approved | 0 | 847457 | 21118 | 13 Apr 2022
GANGA DHAM TOWERS | 384 | 94367 | 13 Apr 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 220 | A Stru. Wall Core Cutting | Core Cutting Work 8" BCE | 23 | No. | 300 | 100 | 172.5 | 0 | 6900 | CGST 0% URD I/P | 0 | 6900 | 6900 | Approved | 0 | 0 | 69 | 13 Apr 2022
GANGA DHAM TOWERS | 983 | 94366 | 13 Apr 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 167 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 146 | No. | 210 | 100 | 766.5 | 0 | 30660 | CGST 0% URD I/P | 0 | 30660 | 30660 | Approved | 0 | 0 | 307 | 13 Apr 2022
GANGA DHAM TOWERS | 1287 | 94362 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | PRAKASH CONTRACTOR | EV - 139 | B 1001 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 334 | Sq.Ft | 55 | 100 | 459.25 | 0 | 18370 | C+S GST 0% I/P RD | 0 | 18370 | 18370 | Approved | 0 | 0 | 367 | 13 Apr 2022
GANGA DHAM TOWERS | 1287 | 94362 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | PRAKASH CONTRACTOR | EV - 139 | B 201 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 334 | Sq.Ft | 55 | 100 | 459.25 | 0 | 18370 | C+S GST 0% I/P RD | 0 | 18370 | 18370 | Approved | 0 | 0 | 367 | 13 Apr 2022
GANGA DHAM TOWERS | 1356 | 94361 | 13 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 176 | D Build. 1204 Blockwork 5" | Blockwork 5" - BC - | 813.08 | Sq.Ft | 21 | 100 | 426.87 | 0 | 17074.68 | CGST 0% URD I/P | 0 | 17074.68 | 17074.68 | Approved | 0 | 0 | 937 | 13 Apr 2022
GANGA DHAM TOWERS | 1356 | 94361 | 13 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 176 | D Build. 1203 Blockwork 5" | Blockwork 5" - BC - | 644.19 | Sq.Ft | 21 | 100 | 338.2 | 0 | 13527.99 | CGST 0% URD I/P | 0 | 13527.99 | 13527.99 | Approved | 0 | 0 | 937 | 13 Apr 2022
GANGA DHAM TOWERS | 1356 | 94361 | 13 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 176 | D Build. 1201 Blockwork 5" | Blockwork 5" - BC - | 986.46 | Sq.Ft | 21 | 100 | 517.89 | 0 | 20715.66 | CGST 0% URD I/P | 0 | 20715.66 | 20715.66 | Approved | 0 | 0 | 937 | 13 Apr 2022
GANGA DHAM TOWERS | 1356 | 94361 | 13 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 176 | D Build. 1202 Blockwork 5" | Blockwork 5" - BC - | 849.8571 | Sq.Ft | 21 | 100 | 446.17 | 0 | 17847 | CGST 0% URD I/P | 0 | 17847 | 17847 | Approved | 0 | 0 | 937 | 13 Apr 2022
GANGA DHAM TOWERS | 1356 | 94361 | 13 Apr 2022 |  | JAY GANESH ENTERPRISES | JAY GANESH ENTERPRISES | EV - 176 | D Build. 1205 Blockwork 5" | Blockwork 5" - BC - | 1169.49 | Sq.Ft | 21 | 100 | 613.98 | 0 | 24559.29 | CGST 0% URD I/P | 0 | 24559.29 | 24559.29 | Approved | 0 | 0 | 937 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2302 Tiling Below Wooden Flooring | Ceramic Flooring work | 100 | Sq.Ft | 21 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2201 Tiling Below Wooden Flooring | Ceramic Flooring work | 169.5474 | Sq.Ft | 21 | 100 | 89.01 | 0 | 3560.5 | C+S GST 18% I/P RD | 640.9 | 4201.4 | 4201.4 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2201 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 227 | Sq.Ft | 60 | 100 | 340.5 | 0 | 13620 | C+S GST 18% I/P RD | 2451.6 | 16071.6 | 16071.6 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2302 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151 | Sq.Ft | 60 | 100 | 226.5 | 0 | 9060 | C+S GST 18% I/P RD | 1630.8 | 10690.8 | 10690.8 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2201 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 209 | Sq.Ft | 60 | 100 | 313.5 | 0 | 12540 | C+S GST 18% I/P RD | 2257.2 | 14797.2 | 14797.2 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2302 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 60 | 100 | 859.22 | 0 | 34368.6 | C+S GST 18% I/P RD | 6186.34 | 40554.94 | 40554.94 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2302 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 122 | Sq.Ft | 60 | 100 | 183 | 0 | 7320 | C+S GST 18% I/P RD | 1317.6 | 8637.6 | 8637.6 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2302 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 209 | Sq.Ft | 60 | 100 | 313.5 | 0 | 12540 | C+S GST 18% I/P RD | 2257.2 | 14797.2 | 14797.2 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2201 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 561.246 | Sq.Ft | 60 | 100 | 841.87 | 0 | 33674.76 | C+S GST 18% I/P RD | 6061.46 | 39736.22 | 39736.22 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2201 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 131.173 | Sq.Ft | 60 | 100 | 196.76 | 0 | 7870.38 | C+S GST 18% I/P RD | 1416.66 | 9287.04 | 9287.04 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2201 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 161.84 | Sq.Ft | 28 | 100 | 113.29 | 0 | 4531.52 | C+S GST 18% I/P RD | 815.68 | 5347.2 | 5347.2 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 537 | 94360 | 13 Apr 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 201 | A 2302 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 150.97 | Sq.Ft | 28 | 100 | 105.68 | 0 | 4227.16 | C+S GST 18% I/P RD | 760.88 | 4988.04 | 4988.04 | Approved | 0 | 0 | 1454 | 13 Apr 2022
GANGA DHAM TOWERS | 551 | 94359 | 13 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 186 | A 2204 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 107.08 | Sq.Ft | 60 | 100 | 160.62 | 0 | 6424.8 | C+S GST 18% I/P RD | 1156.46 | 7581.26 | 7581.26 | Approved | 0 | 0 | 628 | 13 Apr 2022
GANGA DHAM TOWERS | 551 | 94359 | 13 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 186 | A 2204 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.99 | Sq.Ft | 60 | 100 | 227.99 | 0 | 9119.4 | C+S GST 18% I/P RD | 1641.5 | 10760.9 | 10760.9 | Approved | 0 | 0 | 628 | 13 Apr 2022
GANGA DHAM TOWERS | 551 | 94359 | 13 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 186 | A 2204 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 208.3356 | Sq.Ft | 60 | 100 | 312.5 | 0 | 12500.14 | C+S GST 18% I/P RD | 2250.02 | 14750.16 | 14750.16 | Approved | 0 | 0 | 628 | 13 Apr 2022
GANGA DHAM TOWERS | 551 | 94359 | 13 Apr 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 186 | A 2204 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 579.0722 | Sq.Ft | 60 | 100 | 868.61 | 0 | 34744.33 | C+S GST 18% I/P RD | 6253.98 | 40998.31 | 40998.31 | Approved | 0 | 0 | 628 | 13 Apr 2022
GANGA DHAM TOWERS | 1251 | 94358 | 13 Apr 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 173 | A 2301 NOC | Italian Marble Cutting & Shifting | 535 | Sq.Ft | 25 | 100 | 0 | 0 | 13375 | C+S GST 18% I/P RD | 2407.5 | 15782.5 | 15782.5 | Approved | 0 | 0 | 276 | 13 Apr 2022
GANGA DHAM TOWERS | 1251 | 94358 | 13 Apr 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 173 | A 2304 NOC | PCC Work-BC | 126 | Sq.Ft | 6 | 100 | 18.9 | 0 | 756 | C+S GST 18% I/P RD | 136.08 | 892.08 | 892.08 | Approved | 0 | 0 | 276 | 13 Apr 2022
GANGA DHAM TOWERS | 1251 | 94358 | 13 Apr 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 173 | A 2304 NOC | Italian Marble Cutting & Shifting | 290 | Sq.Ft | 25 | 100 | 0 | 0 | 7250 | C+S GST 18% I/P RD | 1305 | 8555 | 8555 | Approved | 0 | 0 | 276 | 13 Apr 2022
GANGA DHAM TOWERS | 1251 | 94358 | 13 Apr 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 173 | A 803 NOC | Italian Marble Cutting & Shifting | 250 | Sq.Ft | 25 | 100 | 0 | 0 | 6250 | C+S GST 18% I/P RD | 1125 | 7375 | 7375 | Approved | 0 | 0 | 276 | 13 Apr 2022
GANGA DHAM TOWERS | 1249 | 94357 | 13 Apr 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 168 | A 801 NOC | Italian Marble Flooring - BCo | 163 | Sq.Ft | 50 | 100 | 203.75 | 0 | 8150 | C+S GST 18% I/P RD | 1467 | 9617 | 9617 | Approved | 0 | 0 | 82 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 201 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 9 | Mtrs | 700 | 100 | 0 | 0 | 6300 | C+S GST 18% I/P RD | 1134 | 7434 | 7434 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 701 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 9 | Mtrs | 700 | 100 | 0 | 0 | 6300 | C+S GST 18% I/P RD | 1134 | 7434 | 7434 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 1601 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 8 | Mtrs | 700 | 100 | 0 | 0 | 5600 | C+S GST 18% I/P RD | 1008 | 6608 | 6608 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 1501 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 9 | Mtrs | 700 | 100 | 0 | 0 | 6300 | C+S GST 18% I/P RD | 1134 | 7434 | 7434 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 1601 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 38.1 | Mtrs | 700 | 100 | 0 | 0 | 26670 | C+S GST 18% I/P RD | 4800.6 | 31470.6 | 31470.6 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 1501 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 40.38 | Mtrs | 700 | 100 | 0 | 0 | 28266 | C+S GST 18% I/P RD | 5087.88 | 33353.88 | 33353.88 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 201 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 40.38 | Mtrs | 700 | 100 | 0 | 0 | 28266 | C+S GST 18% I/P RD | 5087.88 | 33353.88 | 33353.88 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 701 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 40.38 | Mtrs | 700 | 100 | 0 | 0 | 28266 | C+S GST 18% I/P RD | 5087.88 | 33353.88 | 33353.88 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 701 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 78 | 100 | 0 | 0 | 4368 | C+S GST 18% I/P RD | 786.24 | 5154.24 | 5154.24 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 1601 (Refuge) AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 48.8 | Mtrs | 78 | 100 | 0 | 0 | 3806.4 | C+S GST 18% I/P RD | 685.16 | 4491.56 | 4491.56 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 201 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 78 | 100 | 0 | 0 | 4368 | C+S GST 18% I/P RD | 786.24 | 5154.24 | 5154.24 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 1501 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 78 | 100 | 0 | 0 | 4368 | C+S GST 18% I/P RD | 786.24 | 5154.24 | 5154.24 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 201 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 39.0139 | Mtrs | 72 | 100 | 0 | 0 | 2809 | C+S GST 18% I/P RD | 505.62 | 3314.62 | 3314.62 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 701 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 39.0139 | Mtrs | 72 | 100 | 0 | 0 | 2809 | C+S GST 18% I/P RD | 505.62 | 3314.62 | 3314.62 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 1501 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 39.0139 | Mtrs | 72 | 100 | 0 | 0 | 2809 | C+S GST 18% I/P RD | 505.62 | 3314.62 | 3314.62 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1277 | 94344 | 13 Apr 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 138 | Tower B 1601 (Refuge) AC Installation & Commissioning | Drain Pipe with Insulation (M) | 46.9444 | Mtrs | 72 | 100 | 0 | 0 | 3380 | C+S GST 18% I/P RD | 608.4 | 3988.4 | 3988.4 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 272 | 94334 | 13 Apr 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 146 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 52.0124 | Sq.Ft | 161.5 | 100 | 0 | 0 | 8400 | CGST 0% URD I/P | 0 | 8400 | 8400 | Approved | 0 | 0 | 84 | 13 Apr 2022
GANGA DHAM TOWERS | 1322 | 94333 | 13 Apr 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 172 | Tower C Steel Yard Fabrication Work - 1 No. | Fabrication Work (L) - BCo | 156.39 | Kgs | 12 | 100 | 46.92 | 0 | 1876.68 | CGST 0% URD I/P | 0 | 1876.68 | 1876.68 | Approved | 0 | 0 | 89 | 13 Apr 2022
GANGA DHAM TOWERS | 1322 | 94333 | 13 Apr 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 172 | Tower C Steel Yard Fabrication Work - 1 No. | Fabrication Work (L) - BCo | 182.28 | Kgs | 12 | 100 | 54.68 | 0 | 2187.36 | CGST 0% URD I/P | 0 | 2187.36 | 2187.36 | Approved | 0 | 0 | 89 | 13 Apr 2022
GANGA DHAM TOWERS | 1322 | 94333 | 13 Apr 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 172 | Tower C Steel Yard Fabrication Work - 1 No. | GI Sheet Fixing (L) | 1220.39 | Sq.Ft | 4 | 100 | 122.04 | 0 | 4881.56 | CGST 0% URD I/P | 0 | 4881.56 | 4881.56 | Approved | 0 | 0 | 89 | 13 Apr 2022
GANGA DHAM TOWERS | 1261 | 94332 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 441 | A 2203 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 105 | Sq.Ft | 55 | 100 | 144.38 | 0 | 5775 | C+S GST 0% I/P RD | 0 | 5775 | 5775 | Approved | 0 | 0 | 587 | 13 Apr 2022
GANGA DHAM TOWERS | 1261 | 94332 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 441 | A 2301 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 166.208 | Sq.Ft | 55 | 100 | 228.54 | 0 | 9141.44 | C+S GST 0% I/P RD | 0 | 9141.44 | 9141.44 | Approved | 0 | 0 | 587 | 13 Apr 2022
GANGA DHAM TOWERS | 1261 | 94332 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 441 | A 2103 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 105 | Sq.Ft | 55 | 100 | 144.38 | 0 | 5775 | C+S GST 0% I/P RD | 0 | 5775 | 5775 | Approved | 0 | 0 | 587 | 13 Apr 2022
GANGA DHAM TOWERS | 1261 | 94332 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 441 | A 2204 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 106 | Sq.Ft | 55 | 100 | 145.75 | 0 | 5830 | C+S GST 0% I/P RD | 0 | 5830 | 5830 | Approved | 0 | 0 | 587 | 13 Apr 2022
GANGA DHAM TOWERS | 1261 | 94332 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 441 | A 2303 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 105 | Sq.Ft | 55 | 100 | 144.38 | 0 | 5775 | C+S GST 0% I/P RD | 0 | 5775 | 5775 | Approved | 0 | 0 | 587 | 13 Apr 2022
GANGA DHAM TOWERS | 1261 | 94332 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 441 | A 1404 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 132.6 | Sq.Ft | 55 | 100 | 182.33 | 0 | 7293 | C+S GST 0% I/P RD | 0 | 7293 | 7293 | Approved | 0 | 0 | 587 | 13 Apr 2022
GANGA DHAM TOWERS | 1261 | 94332 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 441 | A 2202 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 174.9 | Sq.Ft | 55 | 100 | 240.49 | 0 | 9619.5 | C+S GST 0% I/P RD | 0 | 9619.5 | 9619.5 | Approved | 0 | 0 | 587 | 13 Apr 2022
GANGA DHAM TOWERS | 1261 | 94332 | 13 Apr 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 441 | A 2302 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 173.151 | Sq.Ft | 55 | 100 | 238.08 | 0 | 9523.31 | C+S GST 0% I/P RD | 0 | 9523.31 | 9523.31 | Approved | 0 | 0 | 587 | 13 Apr 2022
GANGA DHAM TOWERS | 632 | 94331 | 13 Apr 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 174 | A 1404 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 320 | 13 Apr 2022
GANGA DHAM TOWERS | 632 | 94331 | 13 Apr 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 174 | A 1404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 320 | 13 Apr 2022
GANGA DHAM TOWERS | 632 | 94331 | 13 Apr 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 174 | A 804 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 400 | Sq.Ft | 20 | 100 | 200 | 0 | 8000 | C+S GST 18% I/P RD | 1440 | 9440 | 9440 | Approved | 0 | 0 | 320 | 13 Apr 2022
GANGA DHAM TOWERS | 629 | 94330 | 13 Apr 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 175 | A 1404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 629 | 94330 | 13 Apr 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 175 | A 1404 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 201 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 40.3833 | Mtrs | 120 | 100 | 121.15 | 0 | 4846 | CGST 0% URD I/P | 0 | 4846 | 4846 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 201 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 9 | Mtrs | 120 | 100 | 27 | 0 | 1080 | CGST 0% URD I/P | 0 | 1080 | 1080 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 701 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 9 | Mtrs | 120 | 100 | 27 | 0 | 1080 | CGST 0% URD I/P | 0 | 1080 | 1080 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 1501 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 9 | Mtrs | 120 | 100 | 27 | 0 | 1080 | CGST 0% URD I/P | 0 | 1080 | 1080 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 1601 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 8 | Mtrs | 120 | 100 | 24 | 0 | 960 | CGST 0% URD I/P | 0 | 960 | 960 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 701 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 18 | 100 | 25.2 | 0 | 1008 | CGST 0% URD I/P | 0 | 1008 | 1008 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 1501 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 18 | 100 | 25.2 | 0 | 1008 | CGST 0% URD I/P | 0 | 1008 | 1008 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 201 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 18 | 100 | 25.2 | 0 | 1008 | CGST 0% URD I/P | 0 | 1008 | 1008 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 1601 (Refuge) AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 48.8 | Mtrs | 18 | 100 | 21.96 | 0 | 878.4 | CGST 0% URD I/P | 0 | 878.4 | 878.4 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 1501 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 40.3833 | Mtrs | 120 | 100 | 121.15 | 0 | 4846 | CGST 0% URD I/P | 0 | 4846 | 4846 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 1601 (Refuge) AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 38.1 | Mtrs | 120 | 100 | 114.3 | 0 | 4572 | CGST 0% URD I/P | 0 | 4572 | 4572 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 701 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 40.3833 | Mtrs | 120 | 100 | 121.15 | 0 | 4846 | CGST 0% URD I/P | 0 | 4846 | 4846 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 1601 (Refuge) AC Installation & Commissioning | Drain Pipe with Insulation (L) | 46.95 | Mtrs | 20 | 100 | 23.48 | 0 | 939 | CGST 0% URD I/P | 0 | 939 | 939 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 1501 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 39 | Mtrs | 20 | 100 | 19.5 | 0 | 780 | CGST 0% URD I/P | 0 | 780 | 780 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 201 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 39 | Mtrs | 20 | 100 | 19.5 | 0 | 780 | CGST 0% URD I/P | 0 | 780 | 780 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1278 | 94329 | 13 Apr 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 137 | Tower B 701 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 39 | Mtrs | 20 | 100 | 19.5 | 0 | 780 | CGST 0% URD I/P | 0 | 780 | 780 | Approved | 0 | 0 | 305 | 13 Apr 2022
GANGA DHAM TOWERS | 1330 | 94326 | 11 Apr 2022 |  | NIKISHA CONSULTANCY SERVICES | NIKISHA CONSULTANCY SERVICES | EV - 11 | Contract Labour Act Registration & Compliace | B.O.C.W. Act Registration &Compliance. | 1 | No. | 64000 | 100 | 0 | 0 | 64000 | C+S GST 18% I/P RD | 11520 | 75520 | 75520 | Approved | 0 | 0 | 1655 | 11 Apr 2022
GANGA DHAM TOWERS | 1330 | 94326 | 11 Apr 2022 |  | NIKISHA CONSULTANCY SERVICES | NIKISHA CONSULTANCY SERVICES | EV - 11 | Contract Labour Act Registration & Compliace | Registration Charges | 1 | No. | 5000 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 1655 | 11 Apr 2022
GANGA DHAM TOWERS | 1330 | 94326 | 11 Apr 2022 |  | NIKISHA CONSULTANCY SERVICES | NIKISHA CONSULTANCY SERVICES | EV - 11 | Contract Labour Act Registration & Compliace | Registration of Company (RC) | 1 | No. | 95500 | 100 | 0 | 0 | 95500 | C+S GST 18% I/P RD | 17190 | 112690 | 112690 | Approved | 0 | 0 | 1655 | 11 Apr 2022
GANGA DHAM TOWERS | 1330 | 94326 | 11 Apr 2022 |  | NIKISHA CONSULTANCY SERVICES | NIKISHA CONSULTANCY SERVICES | EV - 11 | Contract Labour Act Registration & Compliace | Registration Charges | 1 | No. | 1000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 1655 | 11 Apr 2022
GANGA DHAM TOWERS | 149 | 94315 | 31 Mar 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 2285 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3734 | No. | 4 | 100 | 0 | 0 | 14936 | CGST 0% URD I/P | 0 | 14936 | 14936 | Approved | 0 | 0 | 0 | 31 Mar 2022
GANGA DHAM TOWERS | 1340 | 94313 | 31 Mar 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 2287 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 31 Mar 2022
GANGA DHAM TOWERS | 1340 | 94312 | 31 Mar 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 2288 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 31 Mar 2022
GANGA DHAM TOWERS | 1340 | 94311 | 31 Mar 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 2286 | HO Expensess (L) | Security Services. | 12 | Month | 26000 | 8.33 | 0 | 0 | 25999.9 | C+S GST 18% RCM | 4679.98 | 30679.88 | 30679.88 | Approved | 0 | 0 | 260 | 31 Mar 2022
GANGA DHAM TOWERS | 1052 | 94298 | 31 Mar 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 2289 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | C+S GST 0% I/P RD | 0 | 29988 | 29988 | Approved | 0 | 0 | 2999 | 31 Mar 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1703 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1503 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 903 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 803 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1603 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-2003 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1903 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1303 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1803 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1003 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1403 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1203 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1103 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1301 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1604 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1704 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1901 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 903 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1202 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1803 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1602 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1802 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-2001 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 902 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1502 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1503 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1801 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1902 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-2002 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-2003 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1201 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1702 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1101 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1701 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1804 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1303 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1601 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 803 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1302 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-2101 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1903 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-2102 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 802 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1504 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1703 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-2004 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1102 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1403 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1204 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1402 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1002 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1003 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 904 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1404 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1904 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1304 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 801 Internal Electrical Work | Smoke Detector | 2.2171 | No. | 250 | 35 | 4.85 | 0 | 194 | C+S GST 18% I/P RD | 34.92 | 228.92 | 228.92 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 901 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1401 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1603 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1001 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1103 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1104 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1004 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1501 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No. 804 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 359 | 94269 | 09 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 126 | A Bldg Flat No.-1203 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 466 | 09 Apr 2022
GANGA DHAM TOWERS | 940 | 94211 | 06 Apr 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 16 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 165 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 301 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 604 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 404 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 302 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 703 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 202 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 402 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 101 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 502 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 603 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 303 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 403 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 203 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 703 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 103 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 503 Internal Electrical Work | Smoke Detector | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 304 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 201 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 601 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 104 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 503 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 702 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 602 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 303 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 401 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 501 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 704 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 103 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 701 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 203 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 204 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 801 Internal Electrical Work | Smoke Detector | 6.58 | No. | 250 | 35 | 14.39 | 0 | 575.75 | C+S GST 18% I/P RD | 103.64 | 679.39 | 679.39 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 102 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 403 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 504 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 359 | 94210 | 06 Apr 2022 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | VAISHALI ELECTRICAL | EV - 157 | A Bldg Flat No. 603 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 251 | 06 Apr 2022
GANGA DHAM TOWERS | 776 | 94209 | 06 Apr 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 347 | C Murum Filling & Compaction | Murum Filling (avail earth in site) | 3000 | Cu.Mtrs | 90 | 100 | 6750 | 0 | 270000 | C+S GST 18% I/P RD | 48600 | 318600 | 318600 | Approved | 0 | 0 | 2700 | 06 Apr 2022
GANGA DHAM TOWERS | 1056 | 94207 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 213 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1056 | 94207 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 213 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1056 | 94207 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 213 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1056 | 94207 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 213 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1056 | 94207 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 213 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1056 | 94207 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 213 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1055 | 94206 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 212 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1055 | 94206 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 212 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1055 | 94206 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 212 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1055 | 94206 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 212 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1055 | 94206 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 212 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1055 | 94206 | 06 Apr 2022 |  | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 212 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 105 | 06 Apr 2022
GANGA DHAM TOWERS | 1162 | 94205 | 06 Apr 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 35 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 06 Apr 2022
GANGA DHAM TOWERS | 413 | 94201 | 06 Apr 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 215 | Sales office Garden Maintenance | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 10 | 06 Apr 2022
GANGA DHAM TOWERS | 1297 | 94195 | 06 Apr 2022 |  | MANALI HEMANT PHARATE | MANALI HEMANT PHARATE | EV - 24 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 1 | Month | 1000 | 100 | 0 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 0 | 06 Apr 2022
GANGA DHAM TOWERS | 178 | 94194 | 06 Apr 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 27 | Sales office Garden Maintenance | Garden work. | 88 | Day | 407.25 | 100 | 0 | 0 | 35838 | C+S GST 18% I/P RD | 6450.84 | 42288.84 | 42288.84 | Approved | 0 | 0 | 358 | 06 Apr 2022
GANGA DHAM TOWERS | 698 | 94134 | 02 Apr 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 36 | D 1102 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 783.376 | Sq.Ft | 9 | 100 | 176.26 | 0 | 7050.38 | CGST 0% URD I/P | 0 | 7050.38 | 7050.38 | Approved | 0 | 0 | 267 | 02 Apr 2022
GANGA DHAM TOWERS | 698 | 94134 | 02 Apr 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 36 | D 1103 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.328 | Sq.Ft | 9 | 100 | 142.72 | 0 | 5708.95 | CGST 0% URD I/P | 0 | 5708.95 | 5708.95 | Approved | 0 | 0 | 267 | 02 Apr 2022
GANGA DHAM TOWERS | 698 | 94134 | 02 Apr 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 36 | D 1104 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.328 | Sq.Ft | 9 | 100 | 142.72 | 0 | 5708.95 | CGST 0% URD I/P | 0 | 5708.95 | 5708.95 | Approved | 0 | 0 | 267 | 02 Apr 2022
GANGA DHAM TOWERS | 698 | 94134 | 02 Apr 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 36 | D 1101 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.072 | Sq.Ft | 9 | 100 | 206.12 | 0 | 8244.65 | CGST 0% URD I/P | 0 | 8244.65 | 8244.65 | Approved | 0 | 0 | 267 | 02 Apr 2022
GANGA DHAM TOWERS | 258 | 94088 | 01 Apr 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 10 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.774 | Month | 2500 | 100 | 0 | 0 | 1935 | CGST 0% URD I/P | 0 | 1935 | 1935 | Approved | 0 | 0 | 19 | 01 Apr 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1701 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1801 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2301 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 601 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2101 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2201 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2501 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 501 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1201 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2001 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 201 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1001 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1901 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 702 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 802 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1001 Chemical Grouting | Chemical Grouting.- BC | 2535 | Sq.Ft | 2 | 100 | 507 | 0 | 5070 | CGST 0% URD I/P | 0 | 5070 | 5070 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1701 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2501 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2301 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2401 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1901 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1201 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 175 | Sq.Ft | 19 | 100 | 332.5 | 0 | 3325 | CGST 0% URD I/P | 0 | 3325 | 3325 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2001 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1801 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2101 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2201 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1801 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1201 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2501 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 601 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2301 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1901 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2001 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1701 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 501 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 201 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2101 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2401 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2201 Chemical & IPS Waterproofing | IPS W/P | 193 | Sq.Ft | 11 | 100 | 212.3 | 0 | 2123 | CGST 0% URD I/P | 0 | 2123 | 2123 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1901 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2301 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 601 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2201 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1801 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1701 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1001 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2001 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2501 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 2401 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 501 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 498 | 94082 | 31 Mar 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2284 | B 1201 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 819 | 31 Mar 2022
GANGA DHAM TOWERS | 194 | 94073 | 30 Mar 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 2259 | A Bldg 5th Slab PT Slab Work | Post Tensioning Work Rate diff. | 7.87 | Metric Tonnes | 10000 | 100 | 1967.5 | 0 | 78700 | C+S GST 18% I/P RD | 14166 | 92866 | 92866 | Approved | 0 | 44000 | 4765 | 30 Mar 2022
GANGA DHAM TOWERS | 194 | 94073 | 30 Mar 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 2259 | P3 Parking Floor (108.00 Level) PT Slab Work | Post Tensioning Work Rate diff. | 4.2771 | Metric Tonnes | 10000 | 100 | 1069.28 | 0 | 42771 | C+S GST 18% I/P RD | 7698.78 | 50469.78 | 50469.78 | Approved | 0 | 44000 | 4765 | 30 Mar 2022
GANGA DHAM TOWERS | 194 | 94073 | 30 Mar 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 2259 | Stilt Floor (102 Level) PT Slab Work | Post Tensioning Work Rate diff. | 3.56 | Metric Tonnes | 10000 | 100 | 890 | 0 | 35600 | C+S GST 18% I/P RD | 6408 | 42008 | 42008 | Approved | 0 | 44000 | 4765 | 30 Mar 2022
GANGA DHAM TOWERS | 194 | 94073 | 30 Mar 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 2259 | P1 Parking Floor (105 Level) PT Slab Work | Post Tensioning Work Rate diff. | 3.51 | Metric Tonnes | 10000 | 100 | 877.5 | 0 | 35100 | C+S GST 18% I/P RD | 6318 | 41418 | 41418 | Approved | 0 | 44000 | 4765 | 30 Mar 2022
GANGA DHAM TOWERS | 194 | 94073 | 30 Mar 2022 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 2259 | P2 Parking Floor (108 Level) PT Slab Work | Post Tensioning Work Rate diff. | 4.61 | Metric Tonnes | 10000 | 100 | 1152.5 | 0 | 46100 | C+S GST 18% I/P RD | 8298 | 54398 | 54398 | Approved | 0 | 44000 | 4765 | 30 Mar 2022
GANGA DHAM TOWERS | 1169 | 94063 | 29 Mar 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2225 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 32mm dia.(M) | 38 | Mtrs | 494 | 100 | 0 | 0 | 18772 | C+S GST 18% I/P RD | 3378.96 | 22150.96 | 22150.96 | Approved | 0 | 139580 | 0 | 29 Mar 2022
GANGA DHAM TOWERS | 1169 | 94063 | 29 Mar 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2225 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 40mm dia.(M) | 44.0493 | Mtrs | 568 | 100 | 0 | 0 | 25020 | C+S GST 18% I/P RD | 4503.6 | 29523.6 | 29523.6 | Approved | 0 | 139580 | 0 | 29 Mar 2022
GANGA DHAM TOWERS | 1169 | 94063 | 29 Mar 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2225 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 50mm dia.(M) | 60 | Mtrs | 729 | 100 | 0 | 0 | 43740 | C+S GST 18% I/P RD | 7873.2 | 51613.2 | 51613.2 | Approved | 0 | 139580 | 0 | 29 Mar 2022
GANGA DHAM TOWERS | 1169 | 94063 | 29 Mar 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2225 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 25mm dia.(M) | 400.399 | Mtrs | 386 | 100 | 0 | 0 | 154554 | C+S GST 18% I/P RD | 27819.72 | 182373.72 | 182373.72 | Approved | 0 | 139580 | 0 | 29 Mar 2022
GANGA DHAM TOWERS | 1169 | 94062 | 29 Mar 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2224 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 65mm dia.(M) | 222.0001 | Mtrs | 952.4905 | 100 | 0 | 0 | 211453 | C+S GST 18% I/P RD | 38061.54 | 249514.54 | 249514.54 | Approved | 0 | 62546 | 0 | 29 Mar 2022
GANGA DHAM TOWERS | 1169 | 94062 | 29 Mar 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2224 | A Fire Fighting 14 Floors | Drain Valve 50mm (M) | 36 | No. | 2500 | 100 | 0 | 0 | 90000 | C+S GST 18% I/P RD | 16200 | 106200 | 106200 | Approved | 0 | 62546 | 0 | 29 Mar 2022
GANGA DHAM TOWERS | 843 | 94052 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2229 | A North Side 11th to 15th Floor | Glazing / Facad Work (M) | 87.7542 | Sq.Ft | 537 | 100 | 0 | 0 | 47124 | IGST 18% I/P RD | 8482.32 | 55606.32 | 55606.32 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94052 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2229 | A North Side 1 to 5th Floor | Glazing / Facad Work (M) | 4153 | Sq.Ft | 537 | 100 | 0 | 0 | 2230161 | IGST 18% I/P RD | 401428.98 | 2631589.98 | 2631589.98 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94051 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2231 | A East Side 16th to 20th Floor | Glazing / Facad Work (M) | 2148.5568 | Sq.Ft | 537 | 100 | 0 | 0 | 1153775 | IGST 18% I/P RD | 207679.5 | 1361454.5 | 1361454.5 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94051 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2231 | A East Side 11th to 15th Floor | Glazing / Facad Work (M) | 3925.25 | Sq.Ft | 537 | 100 | 0 | 0 | 2107859.25 | IGST 18% I/P RD | 379414.67 | 2487273.92 | 2487273.92 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94050 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2233 | A East Side 1 to 5th Floor | Glazing / Facad Work (M) | 3865.2235 | Sq.Ft | 537 | 100 | 0 | 0 | 2075625 | IGST 18% I/P RD | 373612.5 | 2449237.5 | 2449237.5 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94049 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2232 | A North Side 21st to 26th Floor | Glazing / Facad Work (M) | 1049.3482 | Sq.Ft | 537 | 100 | 0 | 0 | 563500 | IGST 18% I/P RD | 101430 | 664930 | 664930 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94044 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2230 | A North Side 21st to 26th Floor | Glazing / Facad Work (M) | 80.7542 | Sq.Ft | 537 | 100 | 0 | 0 | 43365 | IGST 18% I/P RD | 7805.7 | 51170.7 | 51170.7 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94044 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2230 | A North Side 16th to 20th Floor | Glazing / Facad Work (M) | 4160 | Sq.Ft | 537 | 100 | 0 | 0 | 2233920 | IGST 18% I/P RD | 402105.6 | 2636025.6 | 2636025.6 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94042 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2227 | A East Side 21st to 26th Floor | Glazing / Facad Work (M) | 4727.25 | Sq.Ft | 537 | 100 | 0 | 0 | 2538533.25 | IGST 18% I/P RD | 456935.99 | 2995469.24 | 2995469.24 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94042 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2227 | A East Side 16th to 20th Floor | Glazing / Facad Work (M) | 1804 | Sq.Ft | 537 | 100 | 0 | 0 | 968748 | IGST 18% I/P RD | 174374.64 | 1143122.64 | 1143122.64 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94042 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2227 | A East Side 6th to 10th Floor | Glazing / Facad Work (M) | 1615.8641 | Sq.Ft | 537 | 100 | 0 | 0 | 867719 | IGST 18% I/P RD | 156189.42 | 1023908.42 | 1023908.42 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94041 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2228 | A North Side 6th to 10th Floor | Glazing / Facad Work (M) | 4159 | Sq.Ft | 537 | 100 | 0 | 0 | 2233383 | IGST 18% I/P RD | 402008.94 | 2635391.94 | 2635391.94 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94041 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2228 | A North Side 11th to 15th Floor | Glazing / Facad Work (M) | 3987.1136 | Sq.Ft | 537 | 100 | 0 | 0 | 2141080 | IGST 18% I/P RD | 385394.4 | 2526474.4 | 2526474.4 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 843 | 94041 | 28 Mar 2022 |  | THERMALINE ALUMINIUM PRIVATE LIMITED | THERMALINE ALUMINIUM PRIVATE LIMITED | EV - 2228 | A North Side 11th to 15th Floor | Glazing / Facad Work (M) | 1 | Sq.Ft | 537 | 100 | 0 | 0 | 537 | IGST 18% I/P RD | 96.66 | 633.66 | 633.66 | Approved | 0 | 0 | 0 | 28 Mar 2022
GANGA DHAM TOWERS | 985 | 94032 | 28 Mar 2022 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 |  | 0 | 0 | 126 | 28 Mar 2022
GANGA DHAM TOWERS | 985 | 94032 | 28 Mar 2022 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 |  | 0 | 0 | 126 | 28 Mar 2022
GANGA DHAM TOWERS | 985 | 94032 | 28 Mar 2022 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4199.63 | C+S GST 18% I/P RD | 755.94 | 4955.57 | 4955.57 |  | 0 | 0 | 126 | 28 Mar 2022
GANGA DHAM TOWERS | 145 | 94007 | 23 Mar 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 2199 | Fogging Work | Fogging work-SO | 0.75 | Month | 6000 | 100 | 0 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 105 | 23 Mar 2022
GANGA DHAM TOWERS | 145 | 94007 | 23 Mar 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 2199 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 105 | 23 Mar 2022
GANGA DHAM TOWERS | 971 | 93992 | 22 Mar 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 2184 | B-Bldg Core cutting work for AC & Fire fighting | Core Cutting Work 3" BCE | 229 | No. | 300 | 100 | 1717.5 | 0 | 68700 | C+S GST 18% I/P URD | 12366 | 81066 | 81066 | Approved | 0 | 0 | 687 | 22 Mar 2022
GANGA DHAM TOWERS | 1180 | 93989 | 22 Mar 2022 |  | M.S. CONSTRUCTION | M.S. CONSTRUCTION | EV - 2156 | A Terrace Scaffolding Work | Scaffolding work | 5807.6364 | Sq.Ft | 5.5 | 100 | 798.55 | 0 | 31942 | IGST 18% I/P RD | 5749.56 | 37691.56 | 37691.56 | Approved | 0 | 0 | 319 | 22 Mar 2022
GANGA DHAM TOWERS | 1161 | 93985 | 22 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | M.S. CONSTRUCTION | EV - 2157 | A Facade Scaffolding Fixing & Removing Work (304 Flat No) | Scaffolding & Removing | 862 | Sq.Ft | 5 | 100 | 107.75 | 0 | 4310 | IGST 18% I/P RD | 775.8 | 5085.8 | 5085.8 | Approved | 0 | 0 | 43 | 22 Mar 2022
GANGA DHAM TOWERS | 1261 | 93972 | 21 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 2166 | A 1503 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 95 | Sq.Ft | 55 | 100 | 130.63 | 0 | 5225 | C+S GST 0% I/P RD | 0 | 5225 | 5225 | Approved | 0 | 0 | 464 | 21 Mar 2022
GANGA DHAM TOWERS | 1261 | 93972 | 21 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 2166 | A 501 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 101.76 | Sq.Ft | 55 | 100 | 139.92 | 0 | 5596.8 | C+S GST 0% I/P RD | 0 | 5596.8 | 5596.8 | Approved | 0 | 0 | 464 | 21 Mar 2022
GANGA DHAM TOWERS | 1261 | 93972 | 21 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 2166 | A 2401 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 169.6 | Sq.Ft | 55 | 100 | 233.2 | 0 | 9328 | C+S GST 0% I/P RD | 0 | 9328 | 9328 | Approved | 0 | 0 | 464 | 21 Mar 2022
GANGA DHAM TOWERS | 1261 | 93972 | 21 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 2166 | A 2402 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 174.9 | Sq.Ft | 55 | 100 | 240.49 | 0 | 9619.5 | C+S GST 0% I/P RD | 0 | 9619.5 | 9619.5 | Approved | 0 | 0 | 464 | 21 Mar 2022
GANGA DHAM TOWERS | 1261 | 93972 | 21 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 2166 | A 1401 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 169.6 | Sq.Ft | 55 | 100 | 233.2 | 0 | 9328 | C+S GST 0% I/P RD | 0 | 9328 | 9328 | Approved | 0 | 0 | 464 | 21 Mar 2022
GANGA DHAM TOWERS | 1261 | 93972 | 21 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | JAY BHAVANI ENTERPRISES | EV - 2166 | A 1604 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 132.6 | Sq.Ft | 55 | 100 | 182.33 | 0 | 7293 | C+S GST 0% I/P RD | 0 | 7293 | 7293 | Approved | 0 | 0 | 464 | 21 Mar 2022
GANGA DHAM TOWERS | 1229 | 93971 | 21 Mar 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2161 | B Fire Fighting 11 to 31 floor OUSTFIRE | Sprinkler 15mm 68 dg Pendent (M+L) | 144 | No. | 319 | 100 | 1148.4 | 0 | 45936 | C+S GST 18% I/P RD | 8268.48 | 54204.48 | 54204.48 | Approved | 0 | 0 | 12846 | 21 Mar 2022
GANGA DHAM TOWERS | 1229 | 93971 | 21 Mar 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2161 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 32mm dia.(M+L) | 52.8 | Mtrs | 660 | 100 | 871.2 | 0 | 34848 | C+S GST 18% I/P RD | 6272.64 | 41120.64 | 41120.64 | Approved | 0 | 0 | 12846 | 21 Mar 2022
GANGA DHAM TOWERS | 1229 | 93971 | 21 Mar 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2161 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 80mm dia.(M+L) | 28.8 | Mtrs | 1400 | 100 | 1008 | 0 | 40320 | C+S GST 18% I/P RD | 7257.6 | 47577.6 | 47577.6 | Approved | 0 | 0 | 12846 | 21 Mar 2022
GANGA DHAM TOWERS | 1229 | 93971 | 21 Mar 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2161 | B Fire Fighting 11 to 31 floor OUSTFIRE | Sprinkler 15mm 93 dg Pendent (M+L) | 8 | No. | 690 | 100 | 138 | 0 | 5520 | C+S GST 18% I/P RD | 993.6 | 6513.6 | 6513.6 | Approved | 0 | 0 | 12846 | 21 Mar 2022
GANGA DHAM TOWERS | 1229 | 93971 | 21 Mar 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2161 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 40mm dia.(M+L) | 168 | Mtrs | 760 | 100 | 3192 | 0 | 127680 | C+S GST 18% I/P URD | 22982.4 | 150662.4 | 150662.4 | Approved | 0 | 0 | 12846 | 21 Mar 2022
GANGA DHAM TOWERS | 1229 | 93971 | 21 Mar 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2161 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 65mm dia.(M+L) | 14.4 | Mtrs | 1170 | 100 | 421.2 | 0 | 16848 | C+S GST 18% I/P RD | 3032.64 | 19880.64 | 19880.64 | Approved | 0 | 0 | 12846 | 21 Mar 2022
GANGA DHAM TOWERS | 1229 | 93971 | 21 Mar 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2161 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 25mm dia.(M+L) | 355.2 | Mtrs | 510 | 100 | 4528.8 | 0 | 181152 | C+S GST 18% I/P RD | 32607.36 | 213759.36 | 213759.36 | Approved | 0 | 0 | 12846 | 21 Mar 2022
GANGA DHAM TOWERS | 1229 | 93971 | 21 Mar 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 2161 | B Fire Fighting 11 to 31 floor OUSTFIRE | Flexible hose pipe 25mm dia (1.2m length) (M+L) | 152 | No. | 1250 | 100 | 0 | 0 | 190000 | C+S GST 18% I/P RD | 34200 | 224200 | 224200 | Approved | 0 | 0 | 12846 | 21 Mar 2022
GANGA DHAM TOWERS | 1278 | 93955 | 21 Mar 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 2168 | Tower B 101 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 45 | Mtrs | 120 | 100 | 135 | 0 | 5400 | CGST 0% URD I/P | 0 | 5400 | 5400 | Approved | 0 | 0 | 81 | 21 Mar 2022
GANGA DHAM TOWERS | 1278 | 93955 | 21 Mar 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 2168 | Tower B 101 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 8 | Mtrs | 120 | 100 | 24 | 0 | 960 | CGST 0% URD I/P | 0 | 960 | 960 | Approved | 0 | 0 | 81 | 21 Mar 2022
GANGA DHAM TOWERS | 1278 | 93955 | 21 Mar 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 2168 | Tower B 101 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 18 | 100 | 25.2 | 0 | 1008 | CGST 0% URD I/P | 0 | 1008 | 1008 | Approved | 0 | 0 | 81 | 21 Mar 2022
GANGA DHAM TOWERS | 1278 | 93955 | 21 Mar 2022 |  | PRAKASH BHAGWAN BHAGWAT | PRAKASH BHAGWAN BHAGWAT | EV - 2168 | Tower B 101 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 35.35 | Mtrs | 20 | 100 | 17.68 | 0 | 707 | CGST 0% URD I/P | 0 | 707 | 707 | Approved | 0 | 0 | 81 | 21 Mar 2022
GANGA DHAM TOWERS | 983 | 93948 | 19 Mar 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 2113 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting 6" BCE | 89 | No. | 210 | 100 | 467.25 | 0 | 18690 | CGST 0% URD I/P | 0 | 18690 | 18690 | Approved | 0 | 0 | 187 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93946 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2134 | D 4th to 5th Floor Staircase 1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 280 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93946 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2134 | D 1st to 2nd Floor Staircase 1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 280 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93946 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2134 | D 2nd to 3rd Floor Staircase 1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 280 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93946 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2134 | D 3rd to 4th Floor Staircase 1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 280 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93946 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2134 | D 6th to 7th Floor Staircase 1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 280 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93946 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2134 | D 5th to 6th Floor Staircase 1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 280 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93946 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2134 | D 7th to 8th Floor Staircase 1 & 2 Riser Plaster - 1 No. | Tappa Plaster | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 280 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93944 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2141 | A Ground Floor External Sand Face Plaster | External Plaster- BC | 980 | Sq.Ft | 20 | 100 | 490 | 0 | 19600 | CGST 0% URD I/P | 0 | 19600 | 19600 | Approved | 0 | 0 | 800 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93944 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2141 | A Podium Floor External Sand Face Plaster | External Plaster- BC | 1020 | Sq.Ft | 20 | 100 | 510 | 0 | 20400 | CGST 0% URD I/P | 0 | 20400 | 20400 | Approved | 0 | 0 | 800 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93944 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2141 | A P3 Floor External Sand Face Plaster | External Plaster- BC | 1100 | Sq.Ft | 20 | 100 | 550 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 800 | 19 Mar 2022
GANGA DHAM TOWERS | 1184 | 93944 | 19 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2141 | A P2 Floor External Sand Face Plaster | External Plaster- BC | 900 | Sq.Ft | 20 | 100 | 450 | 0 | 18000 | CGST 0% URD I/P | 0 | 18000 | 18000 | Approved | 0 | 0 | 800 | 19 Mar 2022
GANGA DHAM TOWERS | 1224 | 93940 | 18 Mar 2022 |  | DURGARAM CHANDURAM BHATEE | DURGARAM CHANDURAM BHATEE | EV - 2142 | Housekeeping work at sample flat,parking,road | Housekeeping Work- | 31 | Day | 500 | 100 | 0 | 0 | 15500 | CGST 0% URD I/P | 0 | 15500 | 15500 | Approved | 0 | 0 | 421 | 18 Mar 2022
GANGA DHAM TOWERS | 1224 | 93940 | 18 Mar 2022 |  | DURGARAM CHANDURAM BHATEE | DURGARAM CHANDURAM BHATEE | EV - 2142 | Housekeeping work at sample flat,parking,road | Housekeeping Work- | 11.9992 | Day | 451.613 | 100 | 0 | 0 | 5419 | CGST 0% URD I/P | 0 | 5419 | 5419 | Approved | 0 | 0 | 421 | 18 Mar 2022
GANGA DHAM TOWERS | 1224 | 93940 | 18 Mar 2022 |  | DURGARAM CHANDURAM BHATEE | DURGARAM CHANDURAM BHATEE | EV - 2142 | Housekeeping work at sample flat,parking,road | Housekeeping Work- | 47.0004 | Day | 451.613 | 100 | 0 | 0 | 21226 | CGST 0% URD I/P | 0 | 21226 | 21226 | Approved | 0 | 0 | 421 | 18 Mar 2022
GANGA DHAM TOWERS | 774 | 93938 | 18 Mar 2022 |  | MUKESH CONSTRUCTIONS | JAI SAIRAM CONSTRUCTION | EV - 2165 | B Parking Floor 1 Trimix work | Trimix Work - BC | 16190 | Sq.Ft | 9 | 100 | 3642.75 | 0 | 145710 | C+S GST 18% I/P RD | 26227.8 | 171937.8 | 171937.8 | Approved | 0 | 0 | 1619 | 18 Mar 2022
GANGA DHAM TOWERS | 774 | 93938 | 18 Mar 2022 |  | MUKESH CONSTRUCTIONS | JAI SAIRAM CONSTRUCTION | EV - 2165 | B Parking Floor 1 Trimix work | Weld mesh fixing(L) BCo | 16190 | Sq.Ft | 1 | 100 | 404.75 | 0 | 16190 | C+S GST 18% I/P RD | 2914.2 | 19104.2 | 19104.2 | Approved | 0 | 0 | 1619 | 18 Mar 2022
GANGA DHAM TOWERS | 272 | 93937 | 18 Mar 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 2342 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 30.9598 | Sq.Ft | 161.5 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 18 Mar 2022
GANGA DHAM TOWERS | 1228 | 93917 | 17 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2218 | R & D Purpose | R & D Purpose | 0.0762 | No. | 100000 | 100 | 0 | 0 | 7620 | C+S GST 18% I/P RD | 1371.6 | 8991.6 | 8991.6 | Approved | 0 | 0 | 152 | 17 Mar 2022
GANGA DHAM TOWERS | 1228 | 93916 | 17 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2219 | R & D Purpose | R & D Purpose | 0.0852 | No. | 100000 | 100 | 0 | 0 | 8520 | C+S GST 18% I/P RD | 1533.6 | 10053.6 | 10053.6 | Approved | 0 | 0 | 170 | 17 Mar 2022
GANGA DHAM TOWERS | 1282 | 93912 | 17 Mar 2022 |  | Kishan Enterprises | RAHUL ENTERPRISES (Prop Laburi) | EV - 2187 | B 1001 NOC | Italian Marble Flooring - BCo | 330.94 | Sq.Ft | 50 | 100 | 413.68 | 0 | 16547 | C+S GST 18% I/P RD | 2978.46 | 19525.46 | 19525.46 | Approved | 0 | 0 | 270 | 17 Mar 2022
GANGA DHAM TOWERS | 1282 | 93912 | 17 Mar 2022 |  | Kishan Enterprises | RAHUL ENTERPRISES (Prop Laburi) | EV - 2187 | B 1001 NOC | Italian Marble Flooring - BCo | 209.86 | Sq.Ft | 50 | 100 | 262.33 | 0 | 10493 | C+S GST 18% I/P RD | 1888.74 | 12381.74 | 12381.74 | Approved | 0 | 0 | 270 | 17 Mar 2022
GANGA DHAM TOWERS | 1252 | 93911 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2170 | B 601 NOC | Italian Marble Flooring - BCo | 259.3818 | Sq.Ft | 55 | 100 | 356.65 | 0 | 14266 | C+S GST 18% I/P RD | 2567.88 | 16833.88 | 16833.88 | Approved | 0 | 0 | 143 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 501 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 222 | Sq.Ft | 45 | 100 | 249.75 | 0 | 9990 | C+S GST 18% I/P RD | 1798.2 | 11788.2 | 11788.2 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 501 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1038 | Sq.Ft | 45 | 100 | 1167.75 | 0 | 46710 | C+S GST 18% I/P RD | 8407.8 | 55117.8 | 55117.8 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 601 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 221.0222 | Sq.Ft | 45 | 100 | 248.65 | 0 | 9946 | C+S GST 18% I/P RD | 1790.28 | 11736.28 | 11736.28 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 501 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 274.5778 | Sq.Ft | 45 | 100 | 308.9 | 0 | 12356 | C+S GST 18% I/P RD | 2224.08 | 14580.08 | 14580.08 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 501 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 174.5556 | Sq.Ft | 45 | 100 | 196.38 | 0 | 7855 | C+S GST 18% I/P RD | 1413.9 | 9268.9 | 9268.9 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 601 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 274.5778 | Sq.Ft | 45 | 100 | 308.9 | 0 | 12356 | C+S GST 18% I/P RD | 2224.08 | 14580.08 | 14580.08 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 601 Living,Dining,Ent.Lobby | Italian Marble Flooring - BCo | 1038 | Sq.Ft | 45 | 100 | 1167.75 | 0 | 46710 | C+S GST 18% I/P RD | 8407.8 | 55117.8 | 55117.8 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1701 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 221.0182 | Sq.Ft | 55 | 100 | 303.9 | 0 | 12156 | C+S GST 18% I/P RD | 2188.08 | 14344.08 | 14344.08 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1701 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1038 | Sq.Ft | 55 | 100 | 1427.25 | 0 | 57090 | C+S GST 18% I/P RD | 10276.2 | 67366.2 | 67366.2 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1701 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 174.5455 | Sq.Ft | 55 | 100 | 240 | 0 | 9600 | C+S GST 18% I/P RD | 1728 | 11328 | 11328 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1001 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 221.02 | Sq.Ft | 50 | 100 | 276.28 | 0 | 11051 | C+S GST 18% I/P RD | 1989.18 | 13040.18 | 13040.18 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1001 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 274.58 | Sq.Ft | 50 | 100 | 343.23 | 0 | 13729 | C+S GST 18% I/P RD | 2471.22 | 16200.22 | 16200.22 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1001 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 174.54 | Sq.Ft | 50 | 100 | 218.18 | 0 | 8727 | C+S GST 18% I/P RD | 1570.86 | 10297.86 | 10297.86 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1001 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1038 | Sq.Ft | 50 | 100 | 1297.5 | 0 | 51900 | C+S GST 18% I/P RD | 9342 | 61242 | 61242 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1701 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 274.5818 | Sq.Ft | 55 | 100 | 377.55 | 0 | 15102 | C+S GST 18% I/P RD | 2718.36 | 17820.36 | 17820.36 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 1701 Living Terrace Vitr.Flooring | Vitrified Flooring -BC | 173.875 | Sq.Ft | 24 | 100 | 104.33 | 0 | 4173 | C+S GST 18% I/P RD | 751.14 | 4924.14 | 4924.14 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 2401 Living Terrace Vitr.Flooring | Vitrified Flooring -BC | 173.8929 | Sq.Ft | 28 | 100 | 121.73 | 0 | 4869 | C+S GST 18% I/P RD | 876.42 | 5745.42 | 5745.42 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 758 | 93910 | 17 Mar 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2174 | B 2101 Living Terrace Vitrified Flooring | Vitrified Flooring -BC | 173.8929 | Sq.Ft | 28 | 100 | 121.73 | 0 | 4869 | C+S GST 18% I/P RD | 876.42 | 5745.42 | 5745.42 | Approved | 0 | 0 | 3392 | 17 Mar 2022
GANGA DHAM TOWERS | 1261 | 93906 | 17 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 2140 | A 2102 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 174.9 | Sq.Ft | 55 | 100 | 240.49 | 0 | 9619.5 | CGST 0% URD I/P | 0 | 9619.5 | 9619.5 | Approved | 0 | 0 | 96 | 17 Mar 2022
GANGA DHAM TOWERS | 927 | 93905 | 17 Mar 2022 |  | VENKAT RATHOD | JAY GANESH ENTERPRISES | EV - 2145 | A 19th Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 40 | 17 Mar 2022
GANGA DHAM TOWERS | 957 | 93900 | 16 Mar 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2192 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU Touch proof joint 95 sqmm | 3 | No. | 2500 | 100 | 187.5 | 0 | 7500 | C+S GST 18% I/P RD | 1350 | 8850 | 8850 | Approved | 0 | 0 | 510 | 16 Mar 2022
GANGA DHAM TOWERS | 957 | 93900 | 16 Mar 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2192 | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU Touch proof joint 300 sqmm - No. | 5 | No. | 2500 | 100 | 312.5 | 0 | 12500 | C+S GST 18% I/P RD | 2250 | 14750 | 14750 | Approved | 0 | 0 | 510 | 16 Mar 2022
GANGA DHAM TOWERS | 957 | 93900 | 16 Mar 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2192 | Electricity Infrastructure-Trnsformer,HT,LT Work | Feeder Pillar fixing (L)-LC | 2 | No. | 3000 | 100 | 150 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 510 | 16 Mar 2022
GANGA DHAM TOWERS | 957 | 93900 | 16 Mar 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2192 | Electricity Infrastructure-Trnsformer,HT,LT Work | Earthing work(m+l)- BC | 3 | No. | 4000 | 100 | 300 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 510 | 16 Mar 2022
GANGA DHAM TOWERS | 957 | 93900 | 16 Mar 2022 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2192 | Electricity Infrastructure-Trnsformer,HT,LT Work | Excavation work.- UTI | 81.25 | Mtrs | 160 | 100 | 0 | 0 | 13000 | C+S GST 18% I/P RD | 2340 | 15340 | 15340 | Approved | 0 | 0 | 510 | 16 Mar 2022
GANGA DHAM TOWERS | 1309 | 93899 | 16 Mar 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 2133 | Tower C Electrical Pipe Laying work - | 12" RCC Pipe Laying-USL | 475.5263 | R.Ft | 19 | 100 | 225.87 | 0 | 9035 | CGST 0% URD I/P | 0 | 9035 | 9035 | Approved | 0 | 0 | 160 | 16 Mar 2022
GANGA DHAM TOWERS | 1309 | 93899 | 16 Mar 2022 |  | SHREE GURUDATTA ENTERPRISES | PRAKASH CONTRACTOR | EV - 2133 | Tower C Electrical Pipe Laying work - | Square Chamber 1.2m x 1.2m(D= Upto 1.2m) - No. | 2 | No. | 3500 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 160 | 16 Mar 2022
GANGA DHAM TOWERS | 1308 | 93898 | 16 Mar 2022 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 2137 | Tower C Electrical Pipe Laying work - | Excavation | 1033.0769 | Cu.Ft | 6.5 | 100 | 0 | 0 | 6715 | CGST 0% URD I/P | 0 | 6715 | 6715 | Approved | 0 | 0 | 67 | 16 Mar 2022
GANGA DHAM TOWERS | 1088 | 93897 | 16 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2176 | Club House Earthing work For Solar Panel - 3 No. | Earthing Work-UTI | 3 | No. | 4000 | 100 | 300 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 400 | 16 Mar 2022
GANGA DHAM TOWERS | 1088 | 93897 | 16 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2176 | Steel Godown/ Yard Earthing Work | Earthing work(m+l)- BC | 2 | No. | 4000 | 100 | 0 | 0 | 8000 | C+S GST 18% I/P RD | 1440 | 9440 | 9440 | Approved | 0 | 0 | 400 | 16 Mar 2022
GANGA DHAM TOWERS | 909 | 93896 | 16 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | PRAKASH CONTRACTOR | EV - 2138 | DG New Loaction Earthing Work | Excavation work- BC. | 10 | No. | 500 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 16 Mar 2022
GANGA DHAM TOWERS | 909 | 93895 | 16 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2177 | DG New Loaction Earthing Work | Earthing work(m+l)- BC | 10 | No. | 4000 | 100 | 1000 | 0 | 40000 | C+S GST 18% I/P RD | 7200 | 47200 | 47200 | Approved | 0 | 0 | 800 | 16 Mar 2022
GANGA DHAM TOWERS | 1235 | 93894 | 16 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2186 | Substation Ground Floor Electrical Work (L) | Power Point BC | 5 | No. | 250 | 100 | 0 | 0 | 1250 | C+S GST 18% I/P RD | 225 | 1475 | 1475 | Approved | 0 | 0 | 99 | 16 Mar 2022
GANGA DHAM TOWERS | 1235 | 93894 | 16 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2186 | Substation Ground Floor Electrical Work (L) | DB Box Fiting work-DPo | 1 | No. | 1000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 99 | 16 Mar 2022
GANGA DHAM TOWERS | 1235 | 93894 | 16 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2186 | Substation Ground Floor Electrical Work (L) | LIght Point - Mkt | 12 | No. | 225 | 100 | 0 | 0 | 2700 | C+S GST 18% I/P RD | 486 | 3186 | 3186 | Approved | 0 | 0 | 99 | 16 Mar 2022
GANGA DHAM TOWERS | 407 | 93893 | 16 Mar 2022 |  | SHANKAR VILAS GAIKWAD | PRAKASH CONTRACTOR | EV - 2201 | Fire Fighting Line Excavation & Filling | Excavation (manually)- Dld | 428.5714 | Cu.Ft | 7 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 111 | 16 Mar 2022
GANGA DHAM TOWERS | 407 | 93893 | 16 Mar 2022 |  | SHANKAR VILAS GAIKWAD | PRAKASH CONTRACTOR | EV - 2201 | Electrical LT Line Excavation & Filling work | Excavation (manually)- Dld | 1160.2857 | Cu.Ft | 7 | 100 | 0 | 0 | 8122 | CGST 0% URD I/P | 0 | 8122 | 8122 | Approved | 0 | 0 | 111 | 16 Mar 2022
GANGA DHAM TOWERS | 1261 | 93892 | 16 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2160 | A 1801 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 153 | Sq.Ft | 55 | 100 | 210.38 | 0 | 8415 | CGST 0% URD I/P | 0 | 8415 | 8415 | Approved | 0 | 0 | 130 | 16 Mar 2022
GANGA DHAM TOWERS | 1261 | 93892 | 16 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2160 | A 1802 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 84 | Sq.Ft | 55 | 100 | 115.5 | 0 | 4620 | CGST 0% URD I/P | 0 | 4620 | 4620 | Approved | 0 | 0 | 130 | 16 Mar 2022
GANGA DHAM TOWERS | 1113 | 93872 | 15 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2314 | A 201 Walls Satin Matt Paint | Oil base Primer-BC | 2277.21 | Sq.Ft | 1 | 100 | 56.93 | 0 | 2277.21 | CGST 0% URD I/P | 0 | 2277.21 | 2277.21 | Approved | 0 | 0 | 72 | 15 Mar 2022
GANGA DHAM TOWERS | 1113 | 93872 | 15 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2314 | A 202 Walls Satin Matt Painting | Oil base Primer-BC | 2204.55 | Sq.Ft | 1 | 100 | 55.11 | 0 | 2204.55 | CGST 0% URD I/P | 0 | 2204.55 | 2204.55 | Approved | 0 | 0 | 72 | 15 Mar 2022
GANGA DHAM TOWERS | 1113 | 93872 | 15 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2314 | A 502 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2204.55 | Sq.Ft | 1.25 | 100 | 68.89 | 0 | 2755.69 | CGST 0% URD I/P | 0 | 2755.69 | 2755.69 | Approved | 0 | 0 | 72 | 15 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 1602 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 2101 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 94.032 | R.Ft | 60 | 100 | 141.05 | 0 | 5641.92 | C+S GST 18% I/P RD | 1015.54 | 6657.46 | 6657.46 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 2101 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 60 | 100 | 74.81 | 0 | 2992.32 | C+S GST 18% I/P RD | 538.62 | 3530.94 | 3530.94 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 2101 Master Bed Marble Flooring | Italian marble Skirting - BCo | 52.496 | R.Ft | 60 | 100 | 78.74 | 0 | 3149.76 | C+S GST 18% I/P RD | 566.96 | 3716.72 | 3716.72 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 901 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 50 | 100 | 62.34 | 0 | 2493.6 | C+S GST 18% I/P RD | 448.84 | 2942.44 | 2942.44 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 801 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 94.032 | R.Ft | 50 | 100 | 117.54 | 0 | 4701.6 | C+S GST 18% I/P RD | 846.28 | 5547.88 | 5547.88 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 901 Master Bed Marble Flooring | Italian marble Skirting - BCo | 52.496 | R.Ft | 50 | 100 | 65.62 | 0 | 2624.8 | C+S GST 18% I/P RD | 472.46 | 3097.26 | 3097.26 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 901 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 94.032 | R.Ft | 50 | 100 | 117.54 | 0 | 4701.6 | C+S GST 18% I/P RD | 846.28 | 5547.88 | 5547.88 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93863 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2194 | A 1002 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 282 | 14 Mar 2022
GANGA DHAM TOWERS | 551 | 93861 | 14 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2135 | A 2303 Master Bed Marble Flooring | Italian marble Skirting - BCo | 37.512 | R.Ft | 60 | 100 | 56.27 | 0 | 2250.72 | C+S GST 18% I/P RD | 405.12 | 2655.84 | 2655.84 | Approved | 0 | 0 | 160 | 14 Mar 2022
GANGA DHAM TOWERS | 551 | 93861 | 14 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2135 | A 2303 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81.24 | R.Ft | 60 | 100 | 121.86 | 0 | 4874.4 | C+S GST 18% I/P RD | 877.4 | 5751.8 | 5751.8 | Approved | 0 | 0 | 160 | 14 Mar 2022
GANGA DHAM TOWERS | 551 | 93861 | 14 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2135 | A 2303 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 33.336 | R.Ft | 60 | 100 | 50 | 0 | 2000.16 | C+S GST 18% I/P RD | 360.02 | 2360.18 | 2360.18 | Approved | 0 | 0 | 160 | 14 Mar 2022
GANGA DHAM TOWERS | 551 | 93861 | 14 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2135 | A 103 Master Bed Marble Flooring | Italian marble Skirting - BCo | 37.512 | R.Ft | 45 | 100 | 42.2 | 0 | 1688.04 | C+S GST 18% I/P RD | 303.84 | 1991.88 | 1991.88 | Approved | 0 | 0 | 160 | 14 Mar 2022
GANGA DHAM TOWERS | 551 | 93861 | 14 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2135 | A 103 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81.24 | R.Ft | 45 | 100 | 91.4 | 0 | 3655.8 | C+S GST 18% I/P RD | 658.04 | 4313.84 | 4313.84 | Approved | 0 | 0 | 160 | 14 Mar 2022
GANGA DHAM TOWERS | 551 | 93861 | 14 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2135 | A 103 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 33.336 | R.Ft | 45 | 100 | 37.5 | 0 | 1500.12 | C+S GST 18% I/P RD | 270.02 | 1770.14 | 1770.14 | Approved | 0 | 0 | 160 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 1101 Granite Kitchen Otta | Granite Kitchen Otta BC | 13.6892 | R.Ft | 325 | 100 | 111.22 | 0 | 4449 | C+S GST 18% I/P RD | 800.82 | 5249.82 | 5249.82 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 1502 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.9714 | R.Ft | 350 | 100 | 148.5 | 0 | 5940 | C+S GST 18% I/P RD | 1069.2 | 7009.2 | 7009.2 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 701 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 902 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 802 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 702 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 801 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 2002 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 2402 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 2001 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 2201 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 2301 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 2401 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 2202 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 537 | 93859 | 14 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2132 | A 102 Terrace Parapet Top Granite | Granite Sill-BCo | 20.425 | R.Ft | 40 | 100 | 20.43 | 0 | 817 | C+S GST 18% I/P RD | 147.06 | 964.06 | 964.06 | Approved | 0 | 0 | 237 | 14 Mar 2022
GANGA DHAM TOWERS | 371 | 93851 | 14 Mar 2022 |  | CONSTROGENESIS | PRAKASH CONTRACTOR | EV - 2312 | EWS Bldg RCC 12th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 38 | Sq.Ft | 160 | 100 | 152 | 0 | 6080 | C+S GST 18% I/P RD | 1094.4 | 7174.4 | 7174.4 | Approved | 0 | 0 | 122 | 14 Mar 2022
GANGA DHAM TOWERS | 1277 | 93844 | 14 Mar 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 2167 | Tower B 101 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 8 | Mtrs | 700 | 100 | 0 | 0 | 5600 | C+S GST 18% I/P RD | 1008 | 6608 | 6608 | Approved | 0 | 0 | 440 | 14 Mar 2022
GANGA DHAM TOWERS | 1277 | 93844 | 14 Mar 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 2167 | Tower B 101 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 45 | Mtrs | 700 | 100 | 0 | 0 | 31500 | C+S GST 18% I/P RD | 5670 | 37170 | 37170 | Approved | 0 | 0 | 440 | 14 Mar 2022
GANGA DHAM TOWERS | 1277 | 93844 | 14 Mar 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 2167 | Tower B 101 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 78 | 100 | 0 | 0 | 4368 | C+S GST 18% I/P RD | 786.24 | 5154.24 | 5154.24 | Approved | 0 | 0 | 440 | 14 Mar 2022
GANGA DHAM TOWERS | 1277 | 93844 | 14 Mar 2022 |  | S D ENTERPRISES | S D ENTERPRISES | EV - 2167 | Tower B 101 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 35.3611 | Mtrs | 72 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 440 | 14 Mar 2022
GANGA DHAM TOWERS | 1287 | 93839 | 14 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | PRAKASH CONTRACTOR | EV - 2139 | B 1101 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 310.6182 | Sq.Ft | 55 | 100 | 427.1 | 0 | 17084 | C+S GST 0% I/P RD | 0 | 17084 | 17084 | Approved | 0 | 0 | 171 | 14 Mar 2022
GANGA DHAM TOWERS | 1251 | 93831 | 14 Mar 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 2195 | A 2002 NOC | Italian Marble Flooring - BCo | 181.41 | Sq.Ft | 55 | 100 | 249.44 | 0 | 9977.55 | C+S GST 18% I/P RD | 1795.96 | 11773.51 | 11773.51 | Approved | 0 | 0 | 151 | 14 Mar 2022
GANGA DHAM TOWERS | 1251 | 93831 | 14 Mar 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 2195 | A 2002 NOC | Italian Marble Flooring - BCo | 114.55 | Sq.Ft | 45 | 100 | 128.87 | 0 | 5154.75 | C+S GST 18% I/P RD | 927.86 | 6082.61 | 6082.61 | Approved | 0 | 0 | 151 | 14 Mar 2022
GANGA DHAM TOWERS | 1296 | 93830 | 12 Mar 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 2088 | Miscellaneous expenses | Marketing Operating Expenses | 3.5198 | Month | 25000 | 8.33 | 0 | 0 | 7330 | CGST 0% URD I/P | 0 | 7330 | 7330 | Approved | 0 | 0 | 171 | 12 Mar 2022
GANGA DHAM TOWERS | 1296 | 93830 | 12 Mar 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 2088 | Miscellaneous expenses | Marketing Operating Expenses | 4.6896 | Month | 25000 | 8.33 | 0 | 0 | 9766 | CGST 0% URD I/P | 0 | 9766 | 9766 | Approved | 0 | 0 | 171 | 12 Mar 2022
GANGA DHAM TOWERS | 1228 | 93809 | 12 Mar 2022 |  | KIRAN TUKARAM DHANAWADE | OM ENGINEERING & SCIENTIFIC EQUIPMENTS | EV - 2120 | R & D Purpose | R & D Purpose | 0.0622 | No. | 100000 | 100 | 0 | 0 | 6225 | C+S GST 18% I/P RD | 1120.5 | 7345.5 | 7345.5 | Approved | 0 | 0 | 62 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 201 Walls Satin Matt Paint | Scrapping with 2nd Coat Putty | 2125.396 | Sq.Ft | 1.25 | 100 | 66.42 | 0 | 2656.75 | CGST 0% URD I/P | 0 | 2656.75 | 2656.75 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 1003 Walls Satin Matt Painting | Scrapping with 2nd Coat Putty | 1933.68 | Sq.Ft | 1.25 | 100 | 60.43 | 0 | 2417.1 | CGST 0% URD I/P | 0 | 2417.1 | 2417.1 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 902 Walls Satin Matt Painting | Scrapping with 2nd Coat Putty | 2057.58 | Sq.Ft | 1.25 | 100 | 64.3 | 0 | 2571.98 | CGST 0% URD I/P | 0 | 2571.98 | 2571.98 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 703 Walls Satin Matt Painting | Scrapping with 2nd Coat Putty | 1933.68 | Sq.Ft | 1.25 | 100 | 60.43 | 0 | 2417.1 | CGST 0% URD I/P | 0 | 2417.1 | 2417.1 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 703 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 1933.68 | Sq.Ft | 1.25 | 100 | 60.43 | 0 | 2417.1 | CGST 0% URD I/P | 0 | 2417.1 | 2417.1 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 204 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 1942.304 | Sq.Ft | 1.25 | 100 | 60.7 | 0 | 2427.88 | CGST 0% URD I/P | 0 | 2427.88 | 2427.88 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 1703 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 1933.68 | Sq.Ft | 1.25 | 100 | 60.43 | 0 | 2417.1 | CGST 0% URD I/P | 0 | 2417.1 | 2417.1 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 202 Walls Satin Matt Painting | Scrapping with 2nd Coat Putty | 2057.58 | Sq.Ft | 1.25 | 100 | 64.3 | 0 | 2571.98 | CGST 0% URD I/P | 0 | 2571.98 | 2571.98 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 1113 | 93808 | 12 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2206 | A 1101 Walls Satin Matt Paint | Scrapping with 2nd Coat Putty | 2125.396 | Sq.Ft | 1.25 | 100 | 66.42 | 0 | 2656.75 | CGST 0% URD I/P | 0 | 2656.75 | 2656.75 | Approved | 0 | 0 | 226 | 12 Mar 2022
GANGA DHAM TOWERS | 149 | 93800 | 12 Mar 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 2147 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3314 | No. | 4 | 100 | 0 | 0 | 13256 | CGST 0% URD I/P | 0 | 13256 | 13256 | Approved | 0 | 0 | 270 | 12 Mar 2022
GANGA DHAM TOWERS | 149 | 93800 | 12 Mar 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 2147 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3448 | No. | 4 | 100 | 0 | 0 | 13792 | CGST 0% URD I/P | 0 | 13792 | 13792 | Approved | 0 | 0 | 270 | 12 Mar 2022
GANGA DHAM TOWERS | 237 | 93796 | 12 Mar 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 2283 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.7741 | Month | 7000 | 100 | 0 | 0 | 5419 | CGST 0% URD I/P | 0 | 5419 | 5419 | Approved | 0 | 0 | 54 | 12 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 10th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 5th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 8th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 12th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 9th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 15th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 2nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 9th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 18th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 13th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 11th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 20th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 23rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside1st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 4th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 22nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 21st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 5th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 24th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 7th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 16th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 10th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 20th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 18th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 1st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 24th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 13th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 15th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 8th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 19th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 19th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 6th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 12th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 17th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 4th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 6th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 11th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 14th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 14th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 16th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 17th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 17th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 1st floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 4th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 4th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 21st floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 5th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 23rd floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 19th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 20th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 9th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 12th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 14th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 12th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 15th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 6th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 2nd floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 3rd floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 5th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside1st floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 8th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 11th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 16th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 8th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 21st floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 24th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 2nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 3rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 7th floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 22nd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 23rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 3rd floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 21st floor External Texture Painting | 1st Coat Acrylic Paint (M) | 540 | Sq.Ft | 2 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 2nd floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 10th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 13th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 9th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 7th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 18th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 19th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 14th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 16th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 3rd floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 10th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 22nd floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 11th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 13th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 6th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 20th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 7th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 23rd floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 18th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 22nd floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 15th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 24th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 15th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 20th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 12th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 17th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 4th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 6th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 21st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 5th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 21st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 7th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 24th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 18th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 13th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 18th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 17th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 24th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 9th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 20th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 12th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 19th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 1st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 14th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 15th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 10th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 6th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 7th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside1st floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 4th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 9th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 5th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 19th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 8th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 11th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 13th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 16th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 10th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 11th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 14th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 16th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Northside 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 8th floor External Texture Painting | 2nd Coat Acrylic Paint (M) | 540 | Sq.Ft | 2.5 | 100 | 0 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1295 | 93789 | 11 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2068 | A Eastside 17th floor External Texture Painting | Water Base Primer (M) | 540 | Sq.Ft | 1 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 42373 | 1426 | 11 Mar 2022
GANGA DHAM TOWERS | 1129 | 93785 | 11 Mar 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2069 | D 3rd Floor Lobby Flooring | Vitrified Flooring -Bco | 210.708 | Sq.Ft | 20 | 100 | 105.35 | 0 | 4214.16 | CGST 0% URD I/P | 0 | 4214.16 | 4214.16 | Approved | 0 | 10000 | 126 | 11 Mar 2022
GANGA DHAM TOWERS | 1129 | 93785 | 11 Mar 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2069 | D 4th Floor Lobby Flooring | Vitrified Flooring -Bco | 210.708 | Sq.Ft | 20 | 100 | 105.35 | 0 | 4214.16 | CGST 0% URD I/P | 0 | 4214.16 | 4214.16 | Approved | 0 | 10000 | 126 | 11 Mar 2022
GANGA DHAM TOWERS | 1129 | 93785 | 11 Mar 2022 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2069 | D 2nd Floor Lobby Flooring | Vitrified Flooring -Bco | 210.708 | Sq.Ft | 20 | 100 | 105.35 | 0 | 4214.16 | CGST 0% URD I/P | 0 | 4214.16 | 4214.16 | Approved | 0 | 10000 | 126 | 11 Mar 2022
GANGA DHAM TOWERS | 371 | 93784 | 11 Mar 2022 |  | CONSTROGENESIS | CONSTROGENESIS | EV - 2071 | EWS Bldg LMR, OHWT, Parapet Built-up Area (L) | RCC Superstructure (B-up area) | 500.0025 | Sq.Ft | 200.665 | 100 | 2508.33 | 0 | 100333 | C+S GST 18% I/P RD | 18059.94 | 118392.94 | 118392.94 | Approved | 0 | 100000 | 8727 | 11 Mar 2022
GANGA DHAM TOWERS | 371 | 93784 | 11 Mar 2022 |  | CONSTROGENESIS | CONSTROGENESIS | EV - 2071 | EWS Bldg RCC 12th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 1400 | Sq.Ft | 160 | 100 | 5600 | 0 | 224000 | C+S GST 18% I/P RD | 40320 | 264320 | 264320 | Approved | 0 | 100000 | 8727 | 11 Mar 2022
GANGA DHAM TOWERS | 371 | 93784 | 11 Mar 2022 |  | CONSTROGENESIS | CONSTROGENESIS | EV - 2071 | EWS Bldg RCC 12th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 700 | Sq.Ft | 160 | 100 | 2800 | 0 | 112000 | C+S GST 18% I/P RD | 20160 | 132160 | 132160 | Approved | 0 | 100000 | 8727 | 11 Mar 2022
GANGA DHAM TOWERS | 778 | 93783 | 11 Mar 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2058 | D Build. 11th Floor RCC Patli (L) | Patli (Band)- BC | 674 | R.Ft | 12 | 100 | 202.2 | 0 | 8088 | C+S GST 0% I/P RD | 0 | 8088 | 8088 | Approved | 0 | 0 | 81 | 11 Mar 2022
GANGA DHAM TOWERS | 389 | 93782 | 11 Mar 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2091 | Loading / Unloading Expenses | Unloading of AAC Blocks | 1778 | No. | 2 | 100 | 0 | 0 | 3556 | CGST 0% URD I/P | 0 | 3556 | 3556 | Approved | 0 | 0 | 0 | 11 Mar 2022
GANGA DHAM TOWERS | 389 | 93782 | 11 Mar 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2091 | Loading / Unloading Expenses | Unloading of GYpsum- | 10 | Metric Tonnes | 200 | 100 | 0 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 0 | 11 Mar 2022
GANGA DHAM TOWERS | 389 | 93782 | 11 Mar 2022 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2091 | Loading / Unloading Expenses | Unloading of tiles. | 41 | Metric Tonnes | 260 | 100 | 0 | 0 | 10660 | CGST 0% URD I/P | 0 | 10660 | 10660 | Approved | 0 | 0 | 0 | 11 Mar 2022
GANGA DHAM TOWERS | 1114 | 93781 | 11 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2090 | B 1302 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2726.381 | Sq.Ft | 1.25 | 100 | 85.2 | 0 | 3407.98 | C+S GST 0% I/P RD | 0 | 3407.98 | 3407.98 | Approved | 0 | 0 | 68 | 11 Mar 2022
GANGA DHAM TOWERS | 1114 | 93781 | 11 Mar 2022 |  | HINDUSTAN MAINTENANCE COMPANY | A S ENTERPRISES | EV - 2090 | B 1202 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2726.381 | Sq.Ft | 1.25 | 100 | 85.2 | 0 | 3407.98 | C+S GST 0% I/P RD | 0 | 3407.98 | 3407.98 | Approved | 0 | 0 | 68 | 11 Mar 2022
GANGA DHAM TOWERS | 1283 | 93780 | 10 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS | P. L. VISHWAKARAMA | EV - 2151 | B-Bldg Extra electrical conduit box fixing (L) | 2 Module Box Fixing (Concealed Box) | 25 | Flat | 300 | 100 | 187.5 | 0 | 7500 | C+S GST 0% I/P RD | 0 | 7500 | 7500 | Approved | 0 | 0 | 75 | 10 Mar 2022
GANGA DHAM TOWERS | 1274 | 93779 | 10 Mar 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2111 | A Safety Jali Fabrication Work | M.S. Jali- DPo | 437 | Sq.Ft | 11 | 100 | 120.18 | 0 | 4807 | C+S GST 0% I/P RD | 0 | 4807 | 4807 | Approved | 0 | 0 | 48 | 10 Mar 2022
GANGA DHAM TOWERS | 940 | 93777 | 10 Mar 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 2107 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 330 | 10 Mar 2022
GANGA DHAM TOWERS | 940 | 93777 | 10 Mar 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 2107 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | C+S GST 0% I/P RD | 0 | 22000 | 22000 | Approved | 0 | 0 | 330 | 10 Mar 2022
GANGA DHAM TOWERS | 1250 | 93776 | 10 Mar 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2105 | B 802 NOC | Concrete wall Crushing work | 1.79 | Cu.Mtrs | 7200 | 100 | 0 | 0 | 12888 | C+S GST 18% I/P RD | 2319.84 | 15207.84 | 15207.84 | Approved | 0 | 0 | 2422 | 10 Mar 2022
GANGA DHAM TOWERS | 1250 | 93776 | 10 Mar 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2105 | B 802 NOC | Concrete Cutting Work | 206.12 | R.Ft | 525 | 100 | 0 | 0 | 108213 | C+S GST 18% I/P RD | 19478.34 | 127691.34 | 127691.34 | Approved | 0 | 0 | 2422 | 10 Mar 2022
GANGA DHAM TOWERS | 1275 | 93775 | 10 Mar 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2110 | B Bldg Safety Jali Work | M.S. Jali- DPo | 268.5455 | Sq.Ft | 11 | 100 | 73.85 | 0 | 2954 | C+S GST 0% I/P RD | 0 | 2954 | 2954 | Approved | 0 | 0 | 30 | 10 Mar 2022
GANGA DHAM TOWERS | 1273 | 93774 | 10 Mar 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 2112 | LT Substation Cable Trench Ms Jali Work | Fabrication Work (L) - BCo | 2793.26 | Kgs | 12 | 100 | 837.98 | 0 | 33519.12 | C+S GST 0% I/P RD | 0 | 33519.12 | 33519.12 | Approved | 0 | 0 | 335 | 10 Mar 2022
GANGA DHAM TOWERS | 1253 | 93773 | 10 Mar 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 2103 | LT Substation rolling shutter work | Transport charges-SOS | 1 | No. | 2200 | 100 | 0 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 1375 | 10 Mar 2022
GANGA DHAM TOWERS | 1253 | 93773 | 10 Mar 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 2103 | LT Substation rolling shutter work | Gear Box (M) | 4 | No. | 3600 | 100 | 0 | 0 | 14400 | C+S GST 18% I/P RD | 2592 | 16992 | 16992 | Approved | 0 | 0 | 1375 | 10 Mar 2022
GANGA DHAM TOWERS | 1253 | 93773 | 10 Mar 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 2103 | LT Substation rolling shutter work | Rolling Shutter (M) | 719.91 | Sq.Ft | 168 | 100 | 0 | 0 | 120944.88 | C+S GST 18% I/P RD | 21770.08 | 142714.96 | 142714.96 | Approved | 0 | 0 | 1375 | 10 Mar 2022
GANGA DHAM TOWERS | 1254 | 93772 | 10 Mar 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 2104 | LT Substation rolling shutter work | Rolling Shutter (L) | 719.91 | Sq.Ft | 72 | 100 | 1295.84 | 0 | 51833.52 | C+S GST 18% I/P RD | 9330.04 | 61163.56 | 61163.56 | Approved | 0 | 0 | 534 | 10 Mar 2022
GANGA DHAM TOWERS | 1254 | 93772 | 10 Mar 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 2104 | LT Substation rolling shutter work | Gear Box (L) | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 534 | 10 Mar 2022
GANGA DHAM TOWERS | 178 | 93770 | 09 Mar 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2214 | Sales Oiifce Landscape Area . | Garden work. | 88 | Day | 407.25 | 100 | 0 | 0 | 35838 | C+S GST 18% I/P RD | 6450.84 | 42288.84 | 42288.84 | Approved | 0 | 0 | 358 | 09 Mar 2022
GANGA DHAM TOWERS | 1052 | 93759 | 08 Mar 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 2034 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | CGST 0% URD I/P | 0 | 29988 | 29988 | Approved | 0 | 0 | 2999 | 08 Mar 2022
GANGA DHAM TOWERS | 1297 | 93751 | 07 Mar 2022 |  | MANALI HEMANT PHARATE | MANALI HEMANT PHARATE | EV - 2097 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 1 | Month | 1000 | 100 | 0 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 20 | 07 Mar 2022
GANGA DHAM TOWERS | 1297 | 93751 | 07 Mar 2022 |  | MANALI HEMANT PHARATE | MANALI HEMANT PHARATE | EV - 2097 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 1 | Month | 1000 | 100 | 0 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 20 | 07 Mar 2022
GANGA DHAM TOWERS | 1283 | 93727 | 05 Mar 2022 |  | P.L. VISHWAKARMA ELECTRICALS | P. L. VISHWAKARAMA | EV - 2150 | B-Bldg Extra electrical conduit box fixing (L) | 2 Module Box Fixing (Concealed Box) | 27 | Flat | 300 | 100 | 202.5 | 0 | 8100 | CGST 0% URD I/P | 0 | 8100 | 8100 | Approved | 0 | 0 | 81 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 17th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 23rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 8th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 22nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 15th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 20th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 3rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 2nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 10th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 12th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 13th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 20th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 13th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 14th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 7th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 3rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 10th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 21st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 24th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 8th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 7th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 9th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 9th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 11th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside1st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 17th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 24th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 19th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 2nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 18th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 14th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 18th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 19th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 11th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 16th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 15th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 4th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 22nd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 4th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 5th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 6th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 16th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 6th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 23rd floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 24th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 19th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 10th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 2nd floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 13th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 3rd floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 17th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 5th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 14th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 11th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 21st floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 4th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 22nd floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 12th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 3rd floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside1st floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 14th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 18th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 5th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 21st floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 2nd floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 19th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 13th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 20th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 7th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 20th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 15th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 8th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 18th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 12th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 7th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 9th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 15th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 16th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 17th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 1st floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 8th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 24th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 10th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 4th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 11th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 22nd floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 6th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 6th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 23rd floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 9th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 1st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 5th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 12th floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 21st floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 23rd floor External Texture Painting | 1st Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 11th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 5th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 5th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 7th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 11th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 14th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 10th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 13th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 14th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside1st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 16th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 19th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 12th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 21st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 13th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 6th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 24th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 3rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 17th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 4th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 1st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 17th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 18th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 20th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 12th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 21st floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 23rd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 7th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 8th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 10th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 9th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 19th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 15th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 20th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 22nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 6th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 4th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 2nd floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 9th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 18th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 24th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 8th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 15th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 16th floor External Texture Painting | 2nd Coat Acrylic Paint (L) | 540 | Sq.Ft | 1.5 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 2nd floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 20th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 8th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 13th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 14th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside1st floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 10th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 15th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 17th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 15th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 16th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 6th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 21st floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 22nd floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 5th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 6th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 22nd floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 23rd floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 24th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 12th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 14th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 11th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 12th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 21st floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 2nd floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 7th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 16th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 4th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 11th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 9th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 10th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 19th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 20th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 23rd floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 1st floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 5th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 8th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 19th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 24th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 13th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 18th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 17th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 18th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 3rd floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 4th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 7th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 9th floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Northside 3rd floor External Texture Painting | Cleaning Work - Bco | 540 | Sq.Ft | 0.5 | 100 | 0 | 0 | 270 | C+S GST 18% I/P RD | 48.6 | 318.6 | 318.6 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1292 | 93725 | 05 Mar 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2126 | A Eastside 16th floor External Texture Painting | Water Base Primer (L) | 540 | Sq.Ft | 1 | 100 | 13.5 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 1166 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1101 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 901 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1301 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1401 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1601 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 601 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 201 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 2501 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 301 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1701 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1001 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1201 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 2201 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 2301 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1501 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 501 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 701 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 801 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 2001 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 401 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1801 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 2601 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 2101 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 2401 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 1901 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 1260 | 93724 | 05 Mar 2022 |  | P. L. VISHWAKARAMA | P. L. VISHWAKARAMA | EV - 2149 | B 101 5 Bhk AC Location shifting work | Wiring Work | 1 | No. | 250 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 65 | 05 Mar 2022
GANGA DHAM TOWERS | 480 | 93716 | 04 Mar 2022 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2016 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 29.499 | Day | 466.66 | 100 | 0 | 0 | 13766 | C+S GST 18% I/P RD | 2477.88 | 16243.88 | 16243.88 | Approved | 0 | 8475 | 138 | 04 Mar 2022
GANGA DHAM TOWERS | 745 | 93714 | 04 Mar 2022 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2017 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 25.998 | Day | 466.66 | 100 | 0 | 0 | 12132.23 | C+S GST 18% I/P RD | 2183.8 | 14316.03 | 14316.03 | Approved | 0 | 4238 | 121 | 04 Mar 2022
GANGA DHAM TOWERS | 186 | 93712 | 04 Mar 2022 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2024 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 152.4828 | Day | 451.613 | 100 | 0 | 0 | 68863.21 | C+S GST 18% I/P RD | 12395.38 | 81258.59 | 81258.59 | Approved | 0 | 72034 | 869 | 04 Mar 2022
GANGA DHAM TOWERS | 186 | 93712 | 04 Mar 2022 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2024 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 31 | Day | 580.645 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 72034 | 869 | 04 Mar 2022
GANGA DHAM TOWERS | 1003 | 93705 | 04 Mar 2022 |  | KUMAWAT ENTERPRISES | Kishan Enterprises |  | A 901 NOC | Ceramic Flooring work | 45 | Sq.Ft | 20 | 100 | 0 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 |  | 0 | 0 | 9 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 901 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 227 | Sq.Ft | 50 | 100 | 283.75 | 0 | 11350 | C+S GST 18% I/P RD | 2043 | 13393 | 13393 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 901 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 567 | Sq.Ft | 50 | 100 | 708.75 | 0 | 28350 | C+S GST 18% I/P RD | 5103 | 33453 | 33453 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1401 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1802 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1601 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1801 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1501 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1402 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1901 Terrace Vitrified Flooring | Vitrified Flooring -BC | 140 | Sq.Ft | 28 | 100 | 98 | 0 | 3920 | C+S GST 18% I/P RD | 705.6 | 4625.6 | 4625.6 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 901 Tiling Below Wooden Flooring | Ceramic Flooring work | 171.26 | Sq.Ft | 16 | 100 | 68.5 | 0 | 2740.16 | C+S GST 18% I/P RD | 493.22 | 3233.38 | 3233.38 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1902 Terrace Vitrified Flooring | Vitrified Flooring -BC | 140 | Sq.Ft | 28 | 100 | 98 | 0 | 3920 | C+S GST 18% I/P RD | 705.6 | 4625.6 | 4625.6 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1901 Terrace Vitrified Flooring | Vitrified Skirting BC | 34.3214 | R.Ft | 28 | 100 | 24.02 | 0 | 961 | C+S GST 18% I/P RD | 172.98 | 1133.98 | 1133.98 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1902 Terrace Vitrified Flooring | Vitrified Skirting BC | 34.3214 | R.Ft | 28 | 100 | 24.02 | 0 | 961 | C+S GST 18% I/P RD | 172.98 | 1133.98 | 1133.98 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 901 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 125.34 | Sq.Ft | 50 | 100 | 156.68 | 0 | 6267 | C+S GST 18% I/P RD | 1128.06 | 7395.06 | 7395.06 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 901 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 172 | Sq.Ft | 50 | 100 | 215 | 0 | 8600 | C+S GST 18% I/P RD | 1548 | 10148 | 10148 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 901 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1102 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 1202 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4222 | R.Ft | 45 | 100 | 22.97 | 0 | 919 | C+S GST 18% I/P RD | 165.42 | 1084.42 | 1084.42 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 2501 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4267 | R.Ft | 75 | 100 | 38.3 | 0 | 1532 | C+S GST 18% I/P RD | 275.76 | 1807.76 | 1807.76 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 2502 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4267 | R.Ft | 75 | 100 | 38.3 | 0 | 1532 | C+S GST 18% I/P RD | 275.76 | 1807.76 | 1807.76 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 101 Terrace Parapet Top Granite | Granite Sill-BCo | 20.425 | R.Ft | 40 | 100 | 20.43 | 0 | 817 | C+S GST 18% I/P RD | 147.06 | 964.06 | 964.06 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 537 | 93704 | 04 Mar 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2064 | A 2302 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 810 | 04 Mar 2022
GANGA DHAM TOWERS | 551 | 93703 | 04 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2065 | A 2303 Tiling Below Wooden Flooring | Ceramic Flooring work | 171.58 | Sq.Ft | 21 | 100 | 90.08 | 0 | 3603.18 | C+S GST 18% I/P RD | 648.58 | 4251.76 | 4251.76 | Approved | 0 | 0 | 932 | 04 Mar 2022
GANGA DHAM TOWERS | 551 | 93703 | 04 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2065 | A 103 Tiling Below Wooden Flooring | Ceramic Flooring work | 171.58 | Sq.Ft | 13 | 100 | 55.76 | 0 | 2230.54 | C+S GST 18% I/P RD | 401.5 | 2632.04 | 2632.04 | Approved | 0 | 0 | 932 | 04 Mar 2022
GANGA DHAM TOWERS | 551 | 93703 | 04 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2065 | A 2303 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 487.99 | Sq.Ft | 60 | 100 | 731.99 | 0 | 29279.4 | C+S GST 18% I/P RD | 5270.3 | 34549.7 | 34549.7 | Approved | 0 | 0 | 932 | 04 Mar 2022
GANGA DHAM TOWERS | 551 | 93703 | 04 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2065 | A 2303 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 200.32 | Sq.Ft | 60 | 100 | 300.48 | 0 | 12019.2 | C+S GST 18% I/P RD | 2163.46 | 14182.66 | 14182.66 | Approved | 0 | 0 | 932 | 04 Mar 2022
GANGA DHAM TOWERS | 551 | 93703 | 04 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2065 | A 2303 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144.08 | Sq.Ft | 60 | 100 | 216.12 | 0 | 8644.8 | C+S GST 18% I/P RD | 1556.06 | 10200.86 | 10200.86 | Approved | 0 | 0 | 932 | 04 Mar 2022
GANGA DHAM TOWERS | 551 | 93703 | 04 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2065 | A 103 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 487.99 | Sq.Ft | 45 | 100 | 548.99 | 0 | 21959.55 | C+S GST 18% I/P RD | 3952.72 | 25912.27 | 25912.27 | Approved | 0 | 0 | 932 | 04 Mar 2022
GANGA DHAM TOWERS | 551 | 93703 | 04 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2065 | A 103 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 200.32 | Sq.Ft | 45 | 100 | 225.36 | 0 | 9014.4 | C+S GST 18% I/P RD | 1622.6 | 10637 | 10637 | Approved | 0 | 0 | 932 | 04 Mar 2022
GANGA DHAM TOWERS | 551 | 93703 | 04 Mar 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 2065 | A 103 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144.08 | Sq.Ft | 45 | 100 | 162.09 | 0 | 6483.6 | C+S GST 18% I/P RD | 1167.04 | 7650.64 | 7650.64 | Approved | 0 | 0 | 932 | 04 Mar 2022
GANGA DHAM TOWERS | 1162 | 93679 | 02 Mar 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 2010 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 02 Mar 2022
GANGA DHAM TOWERS | 1257 | 93678 | 02 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2060 | Ground Floor Trench Rough plaster | Rough Plaster - Dld | 2343 | Sq.Ft | 12 | 100 | 702.9 | 0 | 28116 | C+S GST 0% I/P RD | 0 | 28116 | 28116 | Approved | 0 | 0 | 281 | 02 Mar 2022
GANGA DHAM TOWERS | 1226 | 93677 | 02 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2162 | Lt Substation Ground Floor BBM/ Plaster (L) | Sanla Plaster- BC | 1637 | Sq.Ft | 20 | 100 | 818.5 | 0 | 32740 | CGST 0% URD I/P | 0 | 32740 | 32740 | Approved | 0 | 0 | 1239 | 02 Mar 2022
GANGA DHAM TOWERS | 1226 | 93677 | 02 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2162 | Lt Substation Ground Floor BBM/ Plaster (L) | Scaffolding work | 1812.2 | Sq.Ft | 3 | 100 | 135.92 | 0 | 5436.6 | CGST 0% URD I/P | 0 | 5436.6 | 5436.6 | Approved | 0 | 0 | 1239 | 02 Mar 2022
GANGA DHAM TOWERS | 1226 | 93677 | 02 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2162 | Lt Substation Ground Floor BBM/ Plaster (L) | Blockwork 8" - BC | 635.9333 | Sq.Ft | 15 | 100 | 238.47 | 0 | 9539 | CGST 0% URD I/P | 0 | 9539 | 9539 | Approved | 0 | 0 | 1239 | 02 Mar 2022
GANGA DHAM TOWERS | 1226 | 93677 | 02 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2162 | Lt Substation Trench Excavation | Excavation & Shifting-BC | 43.26 | Cu.Mtrs | 75 | 100 | 81.11 | 0 | 3244.5 | CGST 0% URD I/P | 0 | 3244.5 | 3244.5 | Approved | 0 | 0 | 1239 | 02 Mar 2022
GANGA DHAM TOWERS | 1226 | 93677 | 02 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2162 | Lt Substation Ground Floor BBM/ Plaster (L) | Sand Face Plaster DLd | 3203 | Sq.Ft | 22 | 100 | 1761.65 | 0 | 70466 | CGST 0% URD I/P | 0 | 70466 | 70466 | Approved | 0 | 0 | 1239 | 02 Mar 2022
GANGA DHAM TOWERS | 1226 | 93677 | 02 Mar 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2162 | Lt Substation Ground Floor Pcc Work | PCC Work | 623 | Sq.Ft | 4 | 100 | 62.3 | 0 | 2492 | CGST 0% URD I/P | 0 | 2492 | 2492 | Approved | 0 | 0 | 1239 | 02 Mar 2022
GANGA DHAM TOWERS | 384 | 93676 | 02 Mar 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 2011 | A Bldg Fire Fight,AC & Drain lines Core Cutting | Core Cutting Work 8" BCE | 22 | No. | 500 | 100 | 275 | 0 | 11000 | CGST 0% URD I/P | 0 | 11000 | 11000 | Approved | 0 | 0 | 110 | 02 Mar 2022
GANGA DHAM TOWERS | 978 | 93650 | 01 Mar 2022 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1976 | 52 Years Safety Week 2022 | Health Check up Camp | 100 | No. | 60 | 100 | 0 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 0 | 01 Mar 2022
GANGA DHAM TOWERS | 978 | 93650 | 01 Mar 2022 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1976 | 52 Years Safety Week 2022 | Safety Banner | 1 | No. | 500 | 100 | 0 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 0 | 01 Mar 2022
GANGA DHAM TOWERS | 978 | 93650 | 01 Mar 2022 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1976 | 52 Years Safety Week 2022 | Flag | 1 | No. | 300 | 100 | 0 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 0 | 01 Mar 2022
GANGA DHAM TOWERS | 978 | 93650 | 01 Mar 2022 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 1976 | 52 Years Safety Week 2022 | Food Expenses | 600 | No. | 30 | 100 | 0 | 0 | 18000 | CGST 0% URD I/P | 0 | 18000 | 18000 | Approved | 0 | 0 | 0 | 01 Mar 2022
GANGA DHAM TOWERS | 372 | 93626 | 01 Mar 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 2216 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 66.6667 | Sq.Ft | 150 | 100 | 0 | 0 | 10000 | IGST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 1410 | 01 Mar 2022
GANGA DHAM TOWERS | 372 | 93626 | 01 Mar 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 2216 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 70 | Sq.Ft | 150 | 100 | 0 | 0 | 10500 | IGST 18% I/P RD | 1890 | 12390 | 12390 | Approved | 0 | 0 | 1410 | 01 Mar 2022
GANGA DHAM TOWERS | 372 | 93626 | 01 Mar 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 2216 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 66.6667 | Sq.Ft | 150 | 100 | 0 | 0 | 10000 | IGST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 1410 | 01 Mar 2022
GANGA DHAM TOWERS | 372 | 93626 | 01 Mar 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 2216 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 66.6667 | Sq.Ft | 150 | 100 | 0 | 0 | 10000 | IGST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 1410 | 01 Mar 2022
GANGA DHAM TOWERS | 372 | 93626 | 01 Mar 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 2216 | B Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 64.5161 | Sq.Ft | 155 | 100 | 0 | 0 | 10000 | IGST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 1410 | 01 Mar 2022
GANGA DHAM TOWERS | 372 | 93626 | 01 Mar 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 2216 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 64.5161 | Sq.Ft | 155 | 100 | 0 | 0 | 10000 | IGST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 1410 | 01 Mar 2022
GANGA DHAM TOWERS | 372 | 93626 | 01 Mar 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 2216 | B Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 64.5161 | Sq.Ft | 155 | 100 | 0 | 0 | 10000 | IGST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 1410 | 01 Mar 2022
GANGA DHAM TOWERS | 272 | 93624 | 01 Mar 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2213 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 50 | Sq.Ft | 152 | 100 | 0 | 0 | 7600 | C+S GST 18% I/P RD | 1368 | 8968 | 8968 | Approved | 0 | 0 | 576 | 01 Mar 2022
GANGA DHAM TOWERS | 272 | 93624 | 01 Mar 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2213 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 65.7895 | Sq.Ft | 152 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 576 | 01 Mar 2022
GANGA DHAM TOWERS | 272 | 93624 | 01 Mar 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2213 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 65.7895 | Sq.Ft | 152 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 576 | 01 Mar 2022
GANGA DHAM TOWERS | 272 | 93624 | 01 Mar 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2213 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 61.9195 | Sq.Ft | 161.5 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 576 | 01 Mar 2022
GANGA DHAM TOWERS | 272 | 93624 | 01 Mar 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2213 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 61.9195 | Sq.Ft | 161.5 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 576 | 01 Mar 2022
GANGA DHAM TOWERS | 272 | 93624 | 01 Mar 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2213 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 61.9195 | Sq.Ft | 161.5 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 576 | 01 Mar 2022
GANGA DHAM TOWERS | 523 | 93606 | 26 Feb 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2006 | B Bldg External Plumbing Rainwater Line (L) | Rainwater Line | 5 | Flat | 3300 | 100 | 412.5 | 0 | 16500 | CGST 0% URD I/P | 0 | 16500 | 16500 | Approved | 0 | 0 | 165 | 26 Feb 2022
GANGA DHAM TOWERS | 498 | 93603 | 26 Feb 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 2122 | B 1001 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 150 | 26 Feb 2022
GANGA DHAM TOWERS | 498 | 93603 | 26 Feb 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 2122 | B 201 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 150 | 26 Feb 2022
GANGA DHAM TOWERS | 498 | 93603 | 26 Feb 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 2122 | B 1201 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 17.4737 | Sq.Ft | 19 | 100 | 33.2 | 0 | 332 | CGST 0% URD I/P | 0 | 332 | 332 | Approved | 0 | 0 | 150 | 26 Feb 2022
GANGA DHAM TOWERS | 498 | 93603 | 26 Feb 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 2122 | B 501 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 150 | 26 Feb 2022
GANGA DHAM TOWERS | 498 | 93603 | 26 Feb 2022 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 2122 | B 601 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 193 | Sq.Ft | 19 | 100 | 366.7 | 0 | 3667 | CGST 0% URD I/P | 0 | 3667 | 3667 | Approved | 0 | 0 | 150 | 26 Feb 2022
GANGA DHAM TOWERS | 522 | 93589 | 25 Feb 2022 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 2007 | B Bldg 1602 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 1250 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 75 | 25 Feb 2022
GANGA DHAM TOWERS | 1261 | 93582 | 24 Feb 2022 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 2055 | A 1902 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 139 | Sq.Ft | 55 | 100 | 191.13 | 0 | 7645 | C+S GST 0% I/P RD | 0 | 7645 | 7645 | Approved | 0 | 0 | 418 | 24 Feb 2022
GANGA DHAM TOWERS | 1261 | 93582 | 24 Feb 2022 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 2055 | A 1901 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 169.6 | Sq.Ft | 55 | 100 | 233.2 | 0 | 9328 | C+S GST 0% I/P RD | 0 | 9328 | 9328 | Approved | 0 | 0 | 418 | 24 Feb 2022
GANGA DHAM TOWERS | 1261 | 93582 | 24 Feb 2022 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 2055 | A 2002 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 174.9 | Sq.Ft | 55 | 100 | 240.49 | 0 | 9619.5 | C+S GST 0% I/P RD | 0 | 9619.5 | 9619.5 | Approved | 0 | 0 | 418 | 24 Feb 2022
GANGA DHAM TOWERS | 1261 | 93582 | 24 Feb 2022 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 2055 | A 1903 Ledge wall BBM/Plaster Work | Brickwork/ Plaster - Sq.Ft | 107 | Sq.Ft | 55 | 100 | 147.13 | 0 | 5885 | C+S GST 0% I/P RD | 0 | 5885 | 5885 | Approved | 0 | 0 | 418 | 24 Feb 2022
GANGA DHAM TOWERS | 1261 | 93582 | 24 Feb 2022 |  | SANTOSH HMMAT CHAVHAN | JAY GANESH ENTERPRISES | EV - 2055 | A 2001 Ledge wall BBM/Plaster Work - | Brickwork/ Plaster - Sq.Ft | 169.6 | Sq.Ft | 55 | 100 | 233.2 | 0 | 9328 | C+S GST 0% I/P RD | 0 | 9328 | 9328 | Approved | 0 | 0 | 418 | 24 Feb 2022
GANGA DHAM TOWERS | 1208 | 93574 | 24 Feb 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 2118 | Tower Crane B-Bldg Annual Maintenance charges of lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 24 Feb 2022
GANGA DHAM TOWERS | 1207 | 93573 | 24 Feb 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 2119 | Tower Crane A & C Annual maintenance for tower crane & lift | Lift AMC | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 24 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2202 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2102 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2302 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1503 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 140 | Sq.Ft | 19 | 100 | 266 | 0 | 2660 | CGST 0% URD I/P | 0 | 2660 | 2660 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2301 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2101 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1604 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1504 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1704 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2202 Chemical & IPS Waterproofing | IPS W/P | 150 | Sq.Ft | 11 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1604 Chemical & IPS Waterproofing | IPS W/P | 150 | Sq.Ft | 11 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1504 Chemical & IPS Waterproofing | IPS W/P | 150 | Sq.Ft | 11 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2302 Chemical & IPS Waterproofing | IPS W/P | 150 | Sq.Ft | 11 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2301 Chemical & IPS Waterproofing | IPS W/P | 150 | Sq.Ft | 11 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2101 Chemical & IPS Waterproofing | IPS W/P | 150 | Sq.Ft | 11 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1704 Chemical & IPS Waterproofing | IPS W/P | 150 | Sq.Ft | 11 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2102 Chemical & IPS Waterproofing | IPS W/P | 150 | Sq.Ft | 11 | 100 | 165 | 0 | 1650 | CGST 0% URD I/P | 0 | 1650 | 1650 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1503 Chemical & IPS Waterproofing | IPS W/P | 140 | Sq.Ft | 11 | 100 | 154 | 0 | 1540 | CGST 0% URD I/P | 0 | 1540 | 1540 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1504 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2301 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1704 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2202 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2302 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1604 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2101 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2102 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1503 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 2 | No. | 70 | 100 | 14 | 0 | 140 | CGST 0% URD I/P | 0 | 140 | 140 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1504 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2302 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1503 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2202 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2301 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1704 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2102 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 1604 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 401 | 93561 | 23 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2054 | A 2101 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 442 | 23 Feb 2022
GANGA DHAM TOWERS | 491 | 93557 | 22 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2052 | D Build. 1101 Blockwork 5" | Blockwork 5" - BC - | 986 | Sq.Ft | 13 | 100 | 320.45 | 0 | 12818 | C+S GST 0% I/P RD | 0 | 12818 | 12818 | Approved | 0 | 0 | 474 | 22 Feb 2022
GANGA DHAM TOWERS | 491 | 93557 | 22 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2052 | D Build. 1104 Blockwork 5" | Blockwork 5" - BC - | 813.0769 | Sq.Ft | 13 | 100 | 264.25 | 0 | 10570 | C+S GST 0% I/P RD | 0 | 10570 | 10570 | Approved | 0 | 0 | 474 | 22 Feb 2022
GANGA DHAM TOWERS | 491 | 93557 | 22 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2052 | D Build. 1102 Blockwork 5" | Blockwork 5" - BC - | 849 | Sq.Ft | 13 | 100 | 275.93 | 0 | 11037 | C+S GST 0% I/P RD | 0 | 11037 | 11037 | Approved | 0 | 0 | 474 | 22 Feb 2022
GANGA DHAM TOWERS | 491 | 93557 | 22 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2052 | D Build. 1105 Blockwork 8" | Blockwork 5" - BC - | 1000 | Sq.Ft | 13 | 100 | 325 | 0 | 13000 | C+S GST 0% I/P RD | 0 | 13000 | 13000 | Approved | 0 | 0 | 474 | 22 Feb 2022
GANGA DHAM TOWERS | 1258 | 93548 | 22 Feb 2022 |  | RAM GUNAJI MANDLIK | RAM GUNAJI MANDLIK | EV - 2012 | A Core Cutting For Gandola Work | Core Cutting Work 8" BCE | 6 | No. | 300 | 100 | 0 | 0 | 1800 | C+S GST 0% I/P RD | 0 | 1800 | 1800 | Approved | 0 | 0 | 66 | 22 Feb 2022
GANGA DHAM TOWERS | 1258 | 93548 | 22 Feb 2022 |  | RAM GUNAJI MANDLIK | RAM GUNAJI MANDLIK | EV - 2012 | B Core Cutting For Gandola Work | Core Cutting Work 8" BCE | 16 | No. | 300 | 100 | 0 | 0 | 4800 | C+S GST 0% I/P RD | 0 | 4800 | 4800 | Approved | 0 | 0 | 66 | 22 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1001 Terrace Vitrified Flooring | Vitrified Flooring -BC | 49 | Sq.Ft | 20 | 100 | 24.5 | 0 | 980 | C+S GST 18% I/P RD | 176.4 | 1156.4 | 1156.4 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 402 Terrace Vitrified Flooring | Vitrified Flooring -BC | 17 | Sq.Ft | 15 | 100 | 6.38 | 0 | 255 | C+S GST 18% I/P RD | 45.9 | 300.9 | 300.9 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Powder Toilet dado | Dado BC | 42.95 | Sq.Ft | 24 | 100 | 25.77 | 0 | 1030.8 | C+S GST 18% I/P RD | 185.54 | 1216.34 | 1216.34 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Children Toilet | Dado BC | 42.72 | Sq.Ft | 24 | 100 | 25.63 | 0 | 1025.28 | C+S GST 18% I/P RD | 184.56 | 1209.84 | 1209.84 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Master Toilet dado | Dado BC | 67.78 | Sq.Ft | 24 | 100 | 40.67 | 0 | 1626.72 | C+S GST 18% I/P RD | 292.8 | 1919.52 | 1919.52 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Parents Toilet dado | Dado BC | 81.75 | Sq.Ft | 24 | 100 | 49.05 | 0 | 1962 | C+S GST 18% I/P RD | 353.16 | 2315.16 | 2315.16 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1101 Terrace Vitrified Flooring | Vitrified Flooring -BC | 38 | Sq.Ft | 20 | 100 | 19 | 0 | 760 | C+S GST 18% I/P RD | 136.8 | 896.8 | 896.8 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1002 Terrace Vitrified Flooring | Vitrified Flooring -BC | 34 | Sq.Ft | 20 | 100 | 17 | 0 | 680 | C+S GST 18% I/P RD | 122.4 | 802.4 | 802.4 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 59.74 | Sq.Ft | 21 | 100 | 31.36 | 0 | 1254.54 | C+S GST 18% I/P RD | 225.82 | 1480.36 | 1480.36 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1302 Terrace Vitrified Flooring | Vitrified Flooring -BC | 22 | Sq.Ft | 24 | 100 | 13.2 | 0 | 528 | C+S GST 18% I/P RD | 95.04 | 623.04 | 623.04 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1701 Terrace Vitrified Flooring | Vitrified Flooring -BC | 21 | Sq.Ft | 24 | 100 | 12.6 | 0 | 504 | C+S GST 18% I/P RD | 90.72 | 594.72 | 594.72 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 59.74 | Sq.Ft | 21 | 100 | 31.36 | 0 | 1254.54 | C+S GST 18% I/P RD | 225.82 | 1480.36 | 1480.36 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.59 | Sq.Ft | 21 | 100 | 22.88 | 0 | 915.39 | C+S GST 18% I/P RD | 164.78 | 1080.17 | 1080.17 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 45.13 | Sq.Ft | 21 | 100 | 23.69 | 0 | 947.73 | C+S GST 18% I/P RD | 170.6 | 1118.33 | 1118.33 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 49.51 | Sq.Ft | 21 | 100 | 25.99 | 0 | 1039.71 | C+S GST 18% I/P RD | 187.14 | 1226.85 | 1226.85 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Master Toilet dado | L Groove - BCV | 27.65 | R.Ft | 20 | 100 | 13.83 | 0 | 553 | C+S GST 18% I/P RD | 99.54 | 652.54 | 652.54 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Children Toilet | L Groove - BCV | 32.47 | R.Ft | 20 | 100 | 16.24 | 0 | 649.4 | C+S GST 18% I/P RD | 116.9 | 766.3 | 766.3 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Parents Toilet dado | L Groove - BCV | 40.51 | R.Ft | 20 | 100 | 20.26 | 0 | 810.2 | C+S GST 18% I/P RD | 145.84 | 956.04 | 956.04 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Powder Toilet dado | L Groove - BCV | 32.47 | R.Ft | 20 | 100 | 16.24 | 0 | 649.4 | C+S GST 18% I/P RD | 116.9 | 766.3 | 766.3 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Staff Toilet dado | L Groove - BCV | 16.23 | R.Ft | 20 | 100 | 8.12 | 0 | 324.6 | C+S GST 18% I/P RD | 58.42 | 383.02 | 383.02 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Parents Toilet dado | Dado BC | 152.52 | Sq.Ft | 22 | 100 | 83.89 | 0 | 3355.44 | C+S GST 18% I/P RD | 603.98 | 3959.42 | 3959.42 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Children Toilet | Dado BC | 188.43 | Sq.Ft | 22 | 100 | 103.64 | 0 | 4145.46 | C+S GST 18% I/P RD | 746.18 | 4891.64 | 4891.64 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Master Toilet dado | Dado BC | 123.51 | Sq.Ft | 22 | 100 | 67.93 | 0 | 2717.22 | C+S GST 18% I/P RD | 489.1 | 3206.32 | 3206.32 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Staff Toilet dado | Dado BC | 129.18 | Sq.Ft | 21 | 100 | 67.82 | 0 | 2712.78 | C+S GST 18% I/P RD | 488.3 | 3201.08 | 3201.08 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93543 | 21 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2179 | A 1602 Powder Toilet dado | Dado BC | 95.25 | Sq.Ft | 22 | 100 | 52.39 | 0 | 2095.5 | C+S GST 18% I/P RD | 377.2 | 2472.7 | 2472.7 | Approved | 0 | 0 | 328 | 21 Feb 2022
GANGA DHAM TOWERS | 491 | 93542 | 21 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2053 | D Build. 1103 Blockwork 5" | Blockwork 5" - BC - | 644 | Sq.Ft | 13 | 100 | 209.3 | 0 | 8372 | C+S GST 0% I/P RD | 0 | 8372 | 8372 | Approved | 0 | 0 | 166 | 21 Feb 2022
GANGA DHAM TOWERS | 491 | 93542 | 21 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2053 | D Build. 1103 Blockwork 8" | Blockwork 8" - BC | 77 | Sq.Ft | 15 | 100 | 28.88 | 0 | 1155 | C+S GST 0% I/P RD | 0 | 1155 | 1155 | Approved | 0 | 0 | 166 | 21 Feb 2022
GANGA DHAM TOWERS | 491 | 93542 | 21 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2053 | D Build. 1104 Blockwork 8" | Blockwork 8" - BC | 206 | Sq.Ft | 15 | 100 | 77.25 | 0 | 3090 | C+S GST 0% I/P RD | 0 | 3090 | 3090 | Approved | 0 | 0 | 166 | 21 Feb 2022
GANGA DHAM TOWERS | 491 | 93542 | 21 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2053 | D Build. 1101 Blockwork 8" | Blockwork 8" - BC | 62 | Sq.Ft | 15 | 100 | 23.25 | 0 | 930 | C+S GST 0% I/P RD | 0 | 930 | 930 | Approved | 0 | 0 | 166 | 21 Feb 2022
GANGA DHAM TOWERS | 491 | 93542 | 21 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2053 | D Build. 1105 Blockwork 8" | Blockwork 8" - BC | 204 | Sq.Ft | 15 | 100 | 76.5 | 0 | 3060 | C+S GST 0% I/P RD | 0 | 3060 | 3060 | Approved | 0 | 0 | 166 | 21 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 402 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 49.51 | Sq.Ft | 13 | 100 | 16.09 | 0 | 643.63 | C+S GST 18% I/P RD | 115.86 | 759.49 | 759.49 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 402 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.14 | Sq.Ft | 13 | 100 | 7.85 | 0 | 313.82 | C+S GST 18% I/P RD | 56.48 | 370.3 | 370.3 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 402 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 59.74 | Sq.Ft | 13 | 100 | 19.42 | 0 | 776.62 | C+S GST 18% I/P RD | 139.8 | 916.42 | 916.42 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 401 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 14 | Sq.Ft | 13 | 100 | 4.55 | 0 | 182 | C+S GST 18% I/P RD | 32.76 | 214.76 | 214.76 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 502 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 13.0769 | Sq.Ft | 13 | 100 | 4.25 | 0 | 170 | C+S GST 18% I/P RD | 30.6 | 200.6 | 200.6 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 401 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.9 | Sq.Ft | 13 | 100 | 7.44 | 0 | 297.7 | C+S GST 18% I/P RD | 53.58 | 351.28 | 351.28 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 201 Children Toilet Flooring | Vitrified Flooring -BC | 9.0769 | Sq.Ft | 13 | 100 | 2.95 | 0 | 118 | C+S GST 18% I/P RD | 21.24 | 139.24 | 139.24 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 201 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 7.6923 | Sq.Ft | 13 | 100 | 2.5 | 0 | 100 | C+S GST 18% I/P RD | 18 | 118 | 118 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 201 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 8.4615 | Sq.Ft | 13 | 100 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 401 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.59 | Sq.Ft | 13 | 100 | 14.17 | 0 | 566.67 | C+S GST 18% I/P RD | 102 | 668.67 | 668.67 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 502 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 17 | Sq.Ft | 13 | 100 | 5.53 | 0 | 221 | C+S GST 18% I/P RD | 39.78 | 260.78 | 260.78 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1002 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 14.7059 | Sq.Ft | 17 | 100 | 6.25 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1101 Children Toilet Flooring | Vitrified Flooring -BC | 49.08 | Sq.Ft | 17 | 100 | 20.86 | 0 | 834.36 | C+S GST 18% I/P RD | 150.18 | 984.54 | 984.54 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 701 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 15 | Sq.Ft | 17 | 100 | 6.38 | 0 | 255 | C+S GST 18% I/P RD | 45.9 | 300.9 | 300.9 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1001 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 15 | Sq.Ft | 17 | 100 | 6.38 | 0 | 255 | C+S GST 18% I/P RD | 45.9 | 300.9 | 300.9 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1001 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.9 | Sq.Ft | 17 | 100 | 9.73 | 0 | 389.3 | C+S GST 18% I/P RD | 70.08 | 459.38 | 459.38 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1002 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 23.5294 | Sq.Ft | 17 | 100 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 701 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 14 | Sq.Ft | 17 | 100 | 5.95 | 0 | 238 | C+S GST 18% I/P RD | 42.84 | 280.84 | 280.84 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1002 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 17.6471 | Sq.Ft | 17 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1101 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.59 | Sq.Ft | 17 | 100 | 18.53 | 0 | 741.03 | C+S GST 18% I/P RD | 133.38 | 874.41 | 874.41 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1101 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.9 | Sq.Ft | 17 | 100 | 9.73 | 0 | 389.3 | C+S GST 18% I/P RD | 70.08 | 459.38 | 459.38 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 701 Children Toilet Flooring | Vitrified Flooring -BC | 14 | Sq.Ft | 17 | 100 | 5.95 | 0 | 238 | C+S GST 18% I/P RD | 42.84 | 280.84 | 280.84 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1302 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 17 | Sq.Ft | 21 | 100 | 8.93 | 0 | 357 | C+S GST 18% I/P RD | 64.26 | 421.26 | 421.26 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1402 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.14 | Sq.Ft | 21 | 100 | 12.67 | 0 | 506.94 | C+S GST 18% I/P RD | 91.24 | 598.18 | 598.18 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1701 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 10 | Sq.Ft | 21 | 100 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1302 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.14 | Sq.Ft | 21 | 100 | 12.67 | 0 | 506.94 | C+S GST 18% I/P RD | 91.24 | 598.18 | 598.18 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1402 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 8 | Sq.Ft | 21 | 100 | 4.2 | 0 | 168 | C+S GST 18% I/P RD | 30.24 | 198.24 | 198.24 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1701 Children Toilet Flooring | Vitrified Flooring -BC | 9 | Sq.Ft | 21 | 100 | 4.73 | 0 | 189 | C+S GST 18% I/P RD | 34.02 | 223.02 | 223.02 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1302 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 13 | Sq.Ft | 21 | 100 | 6.83 | 0 | 273 | C+S GST 18% I/P RD | 49.14 | 322.14 | 322.14 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1402 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 9 | Sq.Ft | 21 | 100 | 4.73 | 0 | 189 | C+S GST 18% I/P RD | 34.02 | 223.02 | 223.02 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1402 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 11.4286 | Sq.Ft | 21 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1701 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 10 | Sq.Ft | 21 | 100 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1402 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 11 | Sq.Ft | 21 | 100 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1302 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 14 | Sq.Ft | 21 | 100 | 7.35 | 0 | 294 | C+S GST 18% I/P RD | 52.92 | 346.92 | 346.92 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1701 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 8 | Sq.Ft | 21 | 100 | 4.2 | 0 | 168 | C+S GST 18% I/P RD | 30.24 | 198.24 | 198.24 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 502 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 12.3077 | Sq.Ft | 13 | 100 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 201 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 9.2308 | Sq.Ft | 13 | 100 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 601 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 15 | Sq.Ft | 13 | 100 | 4.88 | 0 | 195 | C+S GST 18% I/P RD | 35.1 | 230.1 | 230.1 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 601 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.59 | Sq.Ft | 13 | 100 | 14.17 | 0 | 566.67 | C+S GST 18% I/P RD | 102 | 668.67 | 668.67 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 401 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 52.74 | Sq.Ft | 13 | 100 | 17.14 | 0 | 685.62 | C+S GST 18% I/P RD | 123.42 | 809.04 | 809.04 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 401 Children Toilet Flooring | Vitrified Flooring -BC | 49.08 | Sq.Ft | 13 | 100 | 15.95 | 0 | 638.04 | C+S GST 18% I/P RD | 114.84 | 752.88 | 752.88 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1101 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 50.32 | Sq.Ft | 17 | 100 | 21.39 | 0 | 855.44 | C+S GST 18% I/P RD | 153.98 | 1009.42 | 1009.42 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 701 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 12 | Sq.Ft | 17 | 100 | 5.1 | 0 | 204 | C+S GST 18% I/P RD | 36.72 | 240.72 | 240.72 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1001 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 13.0588 | Sq.Ft | 17 | 100 | 5.55 | 0 | 222 | C+S GST 18% I/P RD | 39.96 | 261.96 | 261.96 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1002 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 17.6471 | Sq.Ft | 17 | 100 | 7.5 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1001 Children Toilet Flooring | Vitrified Flooring -BC | 49.08 | Sq.Ft | 17 | 100 | 20.86 | 0 | 834.36 | C+S GST 18% I/P RD | 150.18 | 984.54 | 984.54 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1101 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 52.74 | Sq.Ft | 17 | 100 | 22.41 | 0 | 896.58 | C+S GST 18% I/P RD | 161.38 | 1057.96 | 1057.96 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 701 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 6 | Sq.Ft | 17 | 100 | 2.55 | 0 | 102 | C+S GST 18% I/P RD | 18.36 | 120.36 | 120.36 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 1002 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 12.9412 | Sq.Ft | 17 | 100 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 402 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 59.74 | Sq.Ft | 13 | 100 | 19.42 | 0 | 776.62 | C+S GST 18% I/P RD | 139.8 | 916.42 | 916.42 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 502 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 16.9231 | Sq.Ft | 13 | 100 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 601 Children Toilet Flooring | Vitrified Flooring -BC | 14 | Sq.Ft | 13 | 100 | 4.55 | 0 | 182 | C+S GST 18% I/P RD | 32.76 | 214.76 | 214.76 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 502 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.14 | Sq.Ft | 13 | 100 | 7.85 | 0 | 313.82 | C+S GST 18% I/P RD | 56.48 | 370.3 | 370.3 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 601 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 15 | Sq.Ft | 13 | 100 | 4.88 | 0 | 195 | C+S GST 18% I/P RD | 35.1 | 230.1 | 230.1 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 601 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 6 | Sq.Ft | 13 | 100 | 1.95 | 0 | 78 | C+S GST 18% I/P RD | 14.04 | 92.04 | 92.04 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 401 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 50.32 | Sq.Ft | 13 | 100 | 16.35 | 0 | 654.16 | C+S GST 18% I/P RD | 117.74 | 771.9 | 771.9 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 201 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 9.2308 | Sq.Ft | 13 | 100 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 537 | 93533 | 19 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2180 | A 402 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.59 | Sq.Ft | 13 | 100 | 14.17 | 0 | 566.67 | C+S GST 18% I/P RD | 102 | 668.67 | 668.67 | Approved | 0 | 0 | 409 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 1902 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 271.2357 | Sq.Ft | 140 | 100 | 949.32 | 0 | 37973 | C+S GST 18% I/P RD | 6835.14 | 44808.14 | 44808.14 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 2001 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 241.8143 | Sq.Ft | 140 | 100 | 846.35 | 0 | 33854 | C+S GST 18% I/P RD | 6093.72 | 39947.72 | 39947.72 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 1702 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 268.6571 | Sq.Ft | 140 | 100 | 940.3 | 0 | 37612 | C+S GST 18% I/P RD | 6770.16 | 44382.16 | 44382.16 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 1701 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 219.9286 | Sq.Ft | 140 | 100 | 769.75 | 0 | 30790 | C+S GST 18% I/P RD | 5542.2 | 36332.2 | 36332.2 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 1801 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 319.9786 | Sq.Ft | 140 | 100 | 1119.93 | 0 | 44797 | C+S GST 18% I/P RD | 8063.46 | 52860.46 | 52860.46 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 1602 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 265.5929 | Sq.Ft | 140 | 100 | 929.58 | 0 | 37183 | C+S GST 18% I/P RD | 6692.94 | 43875.94 | 43875.94 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 1901 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 164.6786 | Sq.Ft | 140 | 100 | 576.38 | 0 | 23055 | C+S GST 18% I/P RD | 4149.9 | 27204.9 | 27204.9 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 1802 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 267.7143 | Sq.Ft | 140 | 100 | 937 | 0 | 37480 | C+S GST 18% I/P RD | 6746.4 | 44226.4 | 44226.4 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 2002 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 151.6429 | Sq.Ft | 140 | 100 | 530.75 | 0 | 21230 | C+S GST 18% I/P RD | 3821.4 | 25051.4 | 25051.4 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1256 | 93532 | 19 Feb 2022 |  | SADAF CONSTRUCTION | SADAF CONSTRUCTION | EV - 1968 | B 1601 Rcc Ledge Wall (L) | RCC Ledge Wall - DCW - Sq.Ft | 226.3786 | Sq.Ft | 140 | 100 | 792.33 | 0 | 31693 | C+S GST 18% I/P RD | 5704.74 | 37397.74 | 37397.74 | Approved | 0 | 0 | 3357 | 19 Feb 2022
GANGA DHAM TOWERS | 1301 | 93529 | 18 Feb 2022 |  | OM SALES CORPORATION | OM SALES CORPORATION | EV - 2092 | DA Development SS/MS Work | Fabrication work lumpsum- BRE | 1 | No. | 18900 | 100 | 0 | 0 | 18900 | C+S GST 18% I/P RD | 3402 | 22302 | 22302 | Approved | 0 | 0 | 378 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Staff Toilet dado | Dado BC | 129.18 | Sq.Ft | 21 | 100 | 67.82 | 0 | 2712.78 | C+S GST 18% I/P RD | 488.3 | 3201.08 | 3201.08 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Staff Toilet dado | Dado BC | 24 | Sq.Ft | 21 | 100 | 12.6 | 0 | 504 | C+S GST 18% I/P RD | 90.72 | 594.72 | 594.72 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Children Toilet | Dado BC | 47 | Sq.Ft | 22 | 100 | 25.85 | 0 | 1034 | C+S GST 18% I/P RD | 186.12 | 1220.12 | 1220.12 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Parents Toilet dado | Dado BC | 45 | Sq.Ft | 22 | 100 | 24.75 | 0 | 990 | C+S GST 18% I/P RD | 178.2 | 1168.2 | 1168.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Parents Toilet dado | Dado BC | 29 | Sq.Ft | 22 | 100 | 15.95 | 0 | 638 | C+S GST 18% I/P RD | 114.84 | 752.84 | 752.84 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Parents Toilet dado | Dado BC | 45 | Sq.Ft | 22 | 100 | 24.75 | 0 | 990 | C+S GST 18% I/P RD | 178.2 | 1168.2 | 1168.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Master Toilet dado | Dado BC | 12 | Sq.Ft | 22 | 100 | 6.6 | 0 | 264 | C+S GST 18% I/P RD | 47.52 | 311.52 | 311.52 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Children Toilet dado | Dado BC | 26 | Sq.Ft | 22 | 100 | 14.3 | 0 | 572 | C+S GST 18% I/P RD | 102.96 | 674.96 | 674.96 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Powder Toilet dado | Dado BC | 28 | Sq.Ft | 22 | 100 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Staff Toilet dado | Dado BC | 129.18 | Sq.Ft | 21 | 100 | 67.82 | 0 | 2712.78 | C+S GST 18% I/P RD | 488.3 | 3201.08 | 3201.08 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Master Toilet dado | Dado BC | 37 | Sq.Ft | 22 | 100 | 20.35 | 0 | 814 | C+S GST 18% I/P RD | 146.52 | 960.52 | 960.52 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Master Toilet dado | Dado BC | 14.1818 | Sq.Ft | 22 | 100 | 7.8 | 0 | 312 | C+S GST 18% I/P RD | 56.16 | 368.16 | 368.16 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Children Toilet Dado | Dado BC | 47 | Sq.Ft | 22 | 100 | 25.85 | 0 | 1034 | C+S GST 18% I/P RD | 186.12 | 1220.12 | 1220.12 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Powder Toilet dado | Dado BC | 19 | Sq.Ft | 22 | 100 | 10.45 | 0 | 418 | C+S GST 18% I/P RD | 75.24 | 493.24 | 493.24 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Powder Toilet dado | Dado BC | 8.7273 | Sq.Ft | 22 | 100 | 4.8 | 0 | 192 | C+S GST 18% I/P RD | 34.56 | 226.56 | 226.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Powder Toilet dado | Dado BC | 29 | Sq.Ft | 18 | 100 | 13.05 | 0 | 522 | C+S GST 18% I/P RD | 93.96 | 615.96 | 615.96 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Children Toilet dado | Dado BC | 40 | Sq.Ft | 18 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Parents Toilet dado | Dado BC | 44 | Sq.Ft | 18 | 100 | 19.8 | 0 | 792 | C+S GST 18% I/P RD | 142.56 | 934.56 | 934.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Powder Toilet dado | Dado BC | 29 | Sq.Ft | 18 | 100 | 13.05 | 0 | 522 | C+S GST 18% I/P RD | 93.96 | 615.96 | 615.96 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Parents Toilet dado | Dado BC | 44 | Sq.Ft | 18 | 100 | 19.8 | 0 | 792 | C+S GST 18% I/P RD | 142.56 | 934.56 | 934.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Parents Toilet dado | Dado BC | 44 | Sq.Ft | 18 | 100 | 19.8 | 0 | 792 | C+S GST 18% I/P RD | 142.56 | 934.56 | 934.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Powder Toilet dado | Dado BC | 29 | Sq.Ft | 18 | 100 | 13.05 | 0 | 522 | C+S GST 18% I/P RD | 93.96 | 615.96 | 615.96 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Children Toilet dado | Dado BC | 134.19 | Sq.Ft | 18 | 100 | 60.39 | 0 | 2415.42 | C+S GST 18% I/P RD | 434.78 | 2850.2 | 2850.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1002 Parents Toilet dado | Dado BC | 45 | Sq.Ft | 18 | 100 | 20.25 | 0 | 810 | C+S GST 18% I/P RD | 145.8 | 955.8 | 955.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Master Toilet dado | Dado BC | 37 | Sq.Ft | 18 | 100 | 16.65 | 0 | 666 | C+S GST 18% I/P RD | 119.88 | 785.88 | 785.88 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Master Toilet dado | Dado BC | 37 | Sq.Ft | 18 | 100 | 16.65 | 0 | 666 | C+S GST 18% I/P RD | 119.88 | 785.88 | 785.88 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Children Toilet dado | Dado BC | 134.19 | Sq.Ft | 18 | 100 | 60.39 | 0 | 2415.42 | C+S GST 18% I/P RD | 434.78 | 2850.2 | 2850.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Master Toilet dado | Dado BC | 37 | Sq.Ft | 18 | 100 | 16.65 | 0 | 666 | C+S GST 18% I/P RD | 119.88 | 785.88 | 785.88 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Staff Toilet dado | Dado BC | 129.18 | Sq.Ft | 13 | 100 | 41.98 | 0 | 1679.34 | C+S GST 18% I/P RD | 302.28 | 1981.62 | 1981.62 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Staff Toilet dado | Dado BC | 122 | Sq.Ft | 13 | 100 | 39.65 | 0 | 1586 | C+S GST 18% I/P RD | 285.48 | 1871.48 | 1871.48 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Staff Toilet dado | Dado BC | 36 | Sq.Ft | 13 | 100 | 11.7 | 0 | 468 | C+S GST 18% I/P RD | 84.24 | 552.24 | 552.24 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Staff Toilet dado | Dado BC | 129.18 | Sq.Ft | 13 | 100 | 41.98 | 0 | 1679.34 | C+S GST 18% I/P RD | 302.28 | 1981.62 | 1981.62 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Staff Toilet dado | Dado BC | 24 | Sq.Ft | 13 | 100 | 7.8 | 0 | 312 | C+S GST 18% I/P RD | 56.16 | 368.16 | 368.16 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Parents Toilet dado | L Groove - BCV | 12 | R.Ft | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Children Toilet dado | L Groove - BCV | 37.56 | R.Ft | 20 | 100 | 18.78 | 0 | 751.2 | C+S GST 18% I/P RD | 135.22 | 886.42 | 886.42 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Parents Toilet dado | L Groove - BCV | 12 | R.Ft | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Children Toilet | L Groove - BCV | 32.47 | R.Ft | 20 | 100 | 16.24 | 0 | 649.4 | C+S GST 18% I/P RD | 116.9 | 766.3 | 766.3 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Powder Toilet dado | L Groove - BCV | 34.93 | R.Ft | 20 | 100 | 17.47 | 0 | 698.6 | C+S GST 18% I/P RD | 125.74 | 824.34 | 824.34 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Parents Toilet dado | Dado BC | 1.7333 | Sq.Ft | 15 | 100 | 0.65 | 0 | 26 | C+S GST 18% I/P RD | 4.68 | 30.68 | 30.68 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Powder Toilet dado | Dado BC | 11 | Sq.Ft | 15 | 100 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Master Toilet dado | Dado BC | 14 | Sq.Ft | 15 | 100 | 5.25 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Master Toilet dado | Dado BC | 67 | Sq.Ft | 15 | 100 | 25.13 | 0 | 1005 | C+S GST 18% I/P RD | 180.9 | 1185.9 | 1185.9 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Powder Toilet dado | Dado BC | 38 | Sq.Ft | 15 | 100 | 14.25 | 0 | 570 | C+S GST 18% I/P RD | 102.6 | 672.6 | 672.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Parents Toilet dado | Dado BC | 12.6667 | Sq.Ft | 15 | 100 | 4.75 | 0 | 190 | C+S GST 18% I/P RD | 34.2 | 224.2 | 224.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Children Toilet dado | Dado BC | 10 | Sq.Ft | 15 | 100 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Powder Toilet dado | Dado BC | 42.95 | Sq.Ft | 15 | 100 | 16.11 | 0 | 644.25 | C+S GST 18% I/P RD | 115.96 | 760.21 | 760.21 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Children Toilet dado | Dado BC | 70 | Sq.Ft | 15 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Master Toilet dado | Dado BC | 13 | Sq.Ft | 15 | 100 | 4.88 | 0 | 195 | C+S GST 18% I/P RD | 35.1 | 230.1 | 230.1 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Powder Toilet dado | Dado BC | 8 | Sq.Ft | 15 | 100 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Parents Toilet dado | Dado BC | 15 | Sq.Ft | 15 | 100 | 5.63 | 0 | 225 | C+S GST 18% I/P RD | 40.5 | 265.5 | 265.5 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Master Toilet dado | Dado BC | 73.2 | Sq.Ft | 15 | 100 | 27.45 | 0 | 1098 | C+S GST 18% I/P RD | 197.64 | 1295.64 | 1295.64 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Parents Toilet dado | Dado BC | 65 | Sq.Ft | 15 | 100 | 24.38 | 0 | 975 | C+S GST 18% I/P RD | 175.5 | 1150.5 | 1150.5 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Parents Toilet dado | Dado BC | 13 | Sq.Ft | 15 | 100 | 4.88 | 0 | 195 | C+S GST 18% I/P RD | 35.1 | 230.1 | 230.1 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Master Toilet dado | Dado BC | 13 | Sq.Ft | 15 | 100 | 4.88 | 0 | 195 | C+S GST 18% I/P RD | 35.1 | 230.1 | 230.1 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Children Toilet dado | Dado BC | 70 | Sq.Ft | 15 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Children Toilet | Dado BC | 42 | Sq.Ft | 15 | 100 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Children Toilet | Dado BC | 8.5333 | Sq.Ft | 15 | 100 | 3.2 | 0 | 128 | C+S GST 18% I/P RD | 23.04 | 151.04 | 151.04 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Powder Toilet dado | Dado BC | 6.8667 | Sq.Ft | 15 | 100 | 2.58 | 0 | 103 | C+S GST 18% I/P RD | 18.54 | 121.54 | 121.54 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Parents Toilet dado | Dado BC | 13 | Sq.Ft | 24 | 100 | 7.8 | 0 | 312 | C+S GST 18% I/P RD | 56.16 | 368.16 | 368.16 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Powder Toilet dado | Dado BC | 8 | Sq.Ft | 24 | 100 | 4.8 | 0 | 192 | C+S GST 18% I/P RD | 34.56 | 226.56 | 226.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Children Toilet Dado | Dado BC | 8 | Sq.Ft | 24 | 100 | 4.8 | 0 | 192 | C+S GST 18% I/P RD | 34.56 | 226.56 | 226.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Powder Toilet dado | Dado BC | 8 | Sq.Ft | 24 | 100 | 4.8 | 0 | 192 | C+S GST 18% I/P RD | 34.56 | 226.56 | 226.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Children Toilet dado | Dado BC | 14 | Sq.Ft | 24 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Staff Toilet dado | Dado BC | 122 | Sq.Ft | 17 | 100 | 51.85 | 0 | 2074 | C+S GST 18% I/P RD | 373.32 | 2447.32 | 2447.32 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1002 Staff Toilet dado | Dado BC | 129.18 | Sq.Ft | 17 | 100 | 54.9 | 0 | 2196.06 | C+S GST 18% I/P RD | 395.3 | 2591.36 | 2591.36 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Staff Toilet dado | Dado BC | 122.46 | Sq.Ft | 17 | 100 | 52.05 | 0 | 2081.82 | C+S GST 18% I/P RD | 374.72 | 2456.54 | 2456.54 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Master Toilet dado | Dado BC | 7 | Sq.Ft | 24 | 100 | 4.2 | 0 | 168 | C+S GST 18% I/P RD | 30.24 | 198.24 | 198.24 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Staff Toilet dado | Dado BC | 122.46 | Sq.Ft | 17 | 100 | 52.05 | 0 | 2081.82 | C+S GST 18% I/P RD | 374.72 | 2456.54 | 2456.54 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Parents Toilet dado | Dado BC | 16 | Sq.Ft | 24 | 100 | 9.6 | 0 | 384 | C+S GST 18% I/P RD | 69.12 | 453.12 | 453.12 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Parents Toilet dado | Dado BC | 16 | Sq.Ft | 24 | 100 | 9.6 | 0 | 384 | C+S GST 18% I/P RD | 69.12 | 453.12 | 453.12 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Master Toilet dado | Dado BC | 13 | Sq.Ft | 24 | 100 | 7.8 | 0 | 312 | C+S GST 18% I/P RD | 56.16 | 368.16 | 368.16 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Master Toilet dado | Dado BC | 13 | Sq.Ft | 24 | 100 | 7.8 | 0 | 312 | C+S GST 18% I/P RD | 56.16 | 368.16 | 368.16 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Children Toilet | Dado BC | 8 | Sq.Ft | 24 | 100 | 4.8 | 0 | 192 | C+S GST 18% I/P RD | 34.56 | 226.56 | 226.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Powder Toilet dado | Dado BC | 7 | Sq.Ft | 24 | 100 | 4.2 | 0 | 168 | C+S GST 18% I/P RD | 30.24 | 198.24 | 198.24 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Master Toilet dado | L Groove - BCV | 32.21 | R.Ft | 20 | 100 | 16.11 | 0 | 644.2 | C+S GST 18% I/P RD | 115.96 | 760.16 | 760.16 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Staff Toilet dado | L Groove - BCV | 16.26 | R.Ft | 20 | 100 | 8.13 | 0 | 325.2 | C+S GST 18% I/P RD | 58.54 | 383.74 | 383.74 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Staff Toilet dado | L Groove - BCV | 16.26 | R.Ft | 20 | 100 | 8.13 | 0 | 325.2 | C+S GST 18% I/P RD | 58.54 | 383.74 | 383.74 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Master Toilet dado | L Groove - BCV | 7 | R.Ft | 20 | 100 | 3.5 | 0 | 140 | C+S GST 18% I/P RD | 25.2 | 165.2 | 165.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Parents Toilet dado | L Groove - BCV | 12 | R.Ft | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Staff Toilet dado | L Groove - BCV | 16 | R.Ft | 20 | 100 | 8 | 0 | 320 | C+S GST 18% I/P RD | 57.6 | 377.6 | 377.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Children Toilet dado | L Groove - BCV | 11 | R.Ft | 20 | 100 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Parents Toilet dado | L Groove - BCV | 42.97 | R.Ft | 20 | 100 | 21.49 | 0 | 859.4 | C+S GST 18% I/P RD | 154.7 | 1014.1 | 1014.1 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1701 Staff Toilet dado | L Groove - BCV | 16.26 | R.Ft | 20 | 100 | 8.13 | 0 | 325.2 | C+S GST 18% I/P RD | 58.54 | 383.74 | 383.74 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Master Toilet dado | L Groove - BCV | 7 | R.Ft | 20 | 100 | 3.5 | 0 | 140 | C+S GST 18% I/P RD | 25.2 | 165.2 | 165.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Powder Toilet dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Master Toilet dado | L Groove - BCV | 7 | R.Ft | 20 | 100 | 3.5 | 0 | 140 | C+S GST 18% I/P RD | 25.2 | 165.2 | 165.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Powder Toilet dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Master Toilet dado | L Groove - BCV | 32.21 | R.Ft | 20 | 100 | 16.11 | 0 | 644.2 | C+S GST 18% I/P RD | 115.96 | 760.16 | 760.16 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Parents Toilet dado | L Groove - BCV | 42.97 | R.Ft | 20 | 100 | 21.49 | 0 | 859.4 | C+S GST 18% I/P RD | 154.7 | 1014.1 | 1014.1 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Parents Toilet dado | L Groove - BCV | 11 | R.Ft | 20 | 100 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Master Toilet dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Parents Toilet dado | L Groove - BCV | 12 | R.Ft | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Staff Toilet dado | L Groove - BCV | 16.26 | R.Ft | 20 | 100 | 8.13 | 0 | 325.2 | C+S GST 18% I/P RD | 58.54 | 383.74 | 383.74 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Children Toilet Dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Master Toilet dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Parents Toilet dado | L Groove - BCV | 12 | R.Ft | 20 | 100 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Powder Toilet dado | L Groove - BCV | 10 | R.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Children Toilet dado | L Groove - BCV | 11 | R.Ft | 20 | 100 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Staff Toilet dado | L Groove - BCV | 16.26 | R.Ft | 20 | 100 | 8.13 | 0 | 325.2 | C+S GST 18% I/P RD | 58.54 | 383.74 | 383.74 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Children Toilet dado | L Groove - BCV | 37.56 | R.Ft | 20 | 100 | 18.78 | 0 | 751.2 | C+S GST 18% I/P RD | 135.22 | 886.42 | 886.42 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Powder Toilet dado | L Groove - BCV | 10 | R.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Powder Toilet dado | L Groove - BCV | 10 | R.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Parents Toilet dado | L Groove - BCV | 40.51 | R.Ft | 20 | 100 | 20.26 | 0 | 810.2 | C+S GST 18% I/P RD | 145.84 | 956.04 | 956.04 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1302 Staff Toilet dado | L Groove - BCV | 16.23 | R.Ft | 20 | 100 | 8.12 | 0 | 324.6 | C+S GST 18% I/P RD | 58.42 | 383.02 | 383.02 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1402 Staff Toilet dado | L Groove - BCV | 16.23 | R.Ft | 20 | 100 | 8.12 | 0 | 324.6 | C+S GST 18% I/P RD | 58.42 | 383.02 | 383.02 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Children Toilet dado | L Groove - BCV | 37.56 | R.Ft | 20 | 100 | 18.78 | 0 | 751.2 | C+S GST 18% I/P RD | 135.22 | 886.42 | 886.42 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Children Toilet | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Children Toilet | L Groove - BCV | 32.47 | R.Ft | 20 | 100 | 16.24 | 0 | 649.4 | C+S GST 18% I/P RD | 116.9 | 766.3 | 766.3 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Powder Toilet dado | L Groove - BCV | 32.47 | R.Ft | 20 | 100 | 16.24 | 0 | 649.4 | C+S GST 18% I/P RD | 116.9 | 766.3 | 766.3 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Children Toilet dado | L Groove - BCV | 37.56 | R.Ft | 20 | 100 | 18.78 | 0 | 751.2 | C+S GST 18% I/P RD | 135.22 | 886.42 | 886.42 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Master Toilet dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Children Toilet dado | L Groove - BCV | 37.56 | R.Ft | 20 | 100 | 18.78 | 0 | 751.2 | C+S GST 18% I/P RD | 135.22 | 886.42 | 886.42 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Powder Toilet dado | L Groove - BCV | 10 | R.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Staff Toilet dado | L Groove - BCV | 16.26 | R.Ft | 20 | 100 | 8.13 | 0 | 325.2 | C+S GST 18% I/P RD | 58.54 | 383.74 | 383.74 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Master Toilet dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Powder Toilet dado | L Groove - BCV | 10 | R.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Powder Toilet dado | L Groove - BCV | 34.93 | R.Ft | 20 | 100 | 17.47 | 0 | 698.6 | C+S GST 18% I/P RD | 125.74 | 824.34 | 824.34 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Staff Toilet dado | L Groove - BCV | 16.26 | R.Ft | 20 | 100 | 8.13 | 0 | 325.2 | C+S GST 18% I/P RD | 58.54 | 383.74 | 383.74 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Staff Toilet dado | L Groove - BCV | 16.23 | R.Ft | 20 | 100 | 8.12 | 0 | 324.6 | C+S GST 18% I/P RD | 58.42 | 383.02 | 383.02 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Master Toilet dado | L Groove - BCV | 27.65 | R.Ft | 20 | 100 | 13.83 | 0 | 553 | C+S GST 18% I/P RD | 99.54 | 652.54 | 652.54 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Powder Toilet dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Master Toilet dado | L Groove - BCV | 9 | R.Ft | 20 | 100 | 4.5 | 0 | 180 | C+S GST 18% I/P RD | 32.4 | 212.4 | 212.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Parents Toilet dado | L Groove - BCV | 10 | R.Ft | 20 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Parents Toilet dado | Dado BC | 148 | Sq.Ft | 14 | 100 | 51.8 | 0 | 2072 | C+S GST 18% I/P RD | 372.96 | 2444.96 | 2444.96 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Master Toilet dado | Dado BC | 22 | Sq.Ft | 14 | 100 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Master Toilet dado | Dado BC | 67 | Sq.Ft | 14 | 100 | 23.45 | 0 | 938 | C+S GST 18% I/P RD | 168.84 | 1106.84 | 1106.84 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Children Toilet | Dado BC | 56.4286 | Sq.Ft | 14 | 100 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Powder Toilet dado | Dado BC | 29 | Sq.Ft | 14 | 100 | 10.15 | 0 | 406 | C+S GST 18% I/P RD | 73.08 | 479.08 | 479.08 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Children Toilet dado | Dado BC | 24 | Sq.Ft | 14 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Powder Toilet dado | Dado BC | 29 | Sq.Ft | 14 | 100 | 10.15 | 0 | 406 | C+S GST 18% I/P RD | 73.08 | 479.08 | 479.08 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Parents Toilet dado | Dado BC | 152 | Sq.Ft | 14 | 100 | 53.2 | 0 | 2128 | C+S GST 18% I/P RD | 383.04 | 2511.04 | 2511.04 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Parents Toilet dado | Dado BC | 44 | Sq.Ft | 14 | 100 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Master Toilet dado | Dado BC | 127 | Sq.Ft | 14 | 100 | 44.45 | 0 | 1778 | C+S GST 18% I/P RD | 320.04 | 2098.04 | 2098.04 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Master Toilet dado | Dado BC | 37 | Sq.Ft | 14 | 100 | 12.95 | 0 | 518 | C+S GST 18% I/P RD | 93.24 | 611.24 | 611.24 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Children Toilet | Dado BC | 156 | Sq.Ft | 14 | 100 | 54.6 | 0 | 2184 | C+S GST 18% I/P RD | 393.12 | 2577.12 | 2577.12 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 402 Powder Toilet dado | Dado BC | 95.25 | Sq.Ft | 14 | 100 | 33.34 | 0 | 1333.5 | C+S GST 18% I/P RD | 240.04 | 1573.54 | 1573.54 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Children Toilet dado | Dado BC | 40 | Sq.Ft | 14 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Parents Toilet dado | Dado BC | 13 | Sq.Ft | 20 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Powder Toilet dado | Dado BC | 6 | Sq.Ft | 20 | 100 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 201 Parents Toilet dado | Dado BC | 44 | Sq.Ft | 14 | 100 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Master Toilet dado | Dado BC | 14 | Sq.Ft | 20 | 100 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Parents Toilet dado | Dado BC | 13 | Sq.Ft | 20 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Children Toilet dado | Dado BC | 70.68 | Sq.Ft | 20 | 100 | 35.34 | 0 | 1413.6 | C+S GST 18% I/P RD | 254.44 | 1668.04 | 1668.04 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Children Toilet dado | Dado BC | 134.19 | Sq.Ft | 14 | 100 | 46.97 | 0 | 1878.66 | C+S GST 18% I/P RD | 338.16 | 2216.82 | 2216.82 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Children Toilet dado | Dado BC | 70 | Sq.Ft | 20 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Powder Toilet dado | Dado BC | 7 | Sq.Ft | 20 | 100 | 3.5 | 0 | 140 | C+S GST 18% I/P RD | 25.2 | 165.2 | 165.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Powder Toilet dado | Dado BC | 7 | Sq.Ft | 20 | 100 | 3.5 | 0 | 140 | C+S GST 18% I/P RD | 25.2 | 165.2 | 165.2 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Powder Toilet dado | Dado BC | 28 | Sq.Ft | 14 | 100 | 9.8 | 0 | 392 | C+S GST 18% I/P RD | 70.56 | 462.56 | 462.56 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1002 Powder Toilet dado | Dado BC | 8 | Sq.Ft | 20 | 100 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 401 Powder Toilet dado | Dado BC | 81 | Sq.Ft | 14 | 100 | 28.35 | 0 | 1134 | C+S GST 18% I/P RD | 204.12 | 1338.12 | 1338.12 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 502 Parents Toilet dado | Dado BC | 44 | Sq.Ft | 14 | 100 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1001 Parents Toilet dado | Dado BC | 13 | Sq.Ft | 20 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Children Toilet dado | Dado BC | 70.68 | Sq.Ft | 20 | 100 | 35.34 | 0 | 1413.6 | C+S GST 18% I/P RD | 254.44 | 1668.04 | 1668.04 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 601 Master Toilet dado | Dado BC | 38 | Sq.Ft | 14 | 100 | 13.3 | 0 | 532 | C+S GST 18% I/P RD | 95.76 | 627.76 | 627.76 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1101 Master Toilet dado | Dado BC | 13 | Sq.Ft | 20 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1002 Parents Toilet dado | Dado BC | 16 | Sq.Ft | 20 | 100 | 8 | 0 | 320 | C+S GST 18% I/P RD | 57.6 | 377.6 | 377.6 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 701 Master Toilet dado | Dado BC | 13 | Sq.Ft | 20 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 537 | 93520 | 18 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 2178 | A 1002 Powder Toilet dado | Dado BC | 28 | Sq.Ft | 18 | 100 | 12.6 | 0 | 504 | C+S GST 18% I/P RD | 90.72 | 594.72 | 594.72 | Approved | 0 | 0 | 994 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 16th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 23rd Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 3rd Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 4th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 2nd Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 13th Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 7th Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 22nd Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 8th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 10th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 15th Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 17th Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 12th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 11th Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 14th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 20th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 21st Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 9th Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 19th Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 18th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 1st Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 24th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 6th Floor Texture Painting | Texture Paint (M) | 296 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1200 | 93519 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2152 | B Northside 5th Floor Texture Painting | Texture Paint (M) | 444.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1289 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 2nd Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 4th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 17th Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 24th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 3rd Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 21st Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 9th Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 10th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 8th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 22nd Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 18th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 3rd Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 4th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 11th Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 12th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 17th Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 8th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 14th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 15th Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 7th Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 13th Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 19th Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 18th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 20th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 21st Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 22nd Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 16th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 23rd Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 2nd Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 5th Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 20th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 11th Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 12th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 5th Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 13th Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 6th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 15th Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 7th Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 23rd Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 16th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 14th Floor Texture Painting | Texture Paint (L) | 296 | Sq.Ft | 7.25 | 100 | 53.65 | 0 | 2146 | C+S GST 18% I/P RD | 386.28 | 2532.28 | 2532.28 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 19th Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 1st Floor Texture Painting | Texture Paint (L) | 444.9655 | Sq.Ft | 7.25 | 100 | 80.65 | 0 | 3226 | C+S GST 18% I/P RD | 580.68 | 3806.68 | 3806.68 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 9th Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 1st Floor Texture Painting | Scaffolding/Gondola work | 445.1429 | Sq.Ft | 3.5 | 100 | 38.95 | 0 | 1558 | C+S GST 18% I/P RD | 280.44 | 1838.44 | 1838.44 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 6th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 24th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 1199 | 93518 | 18 Feb 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2210 | B Northside 10th Floor Texture Painting | Scaffolding/Gondola work | 296 | Sq.Ft | 3.5 | 100 | 25.9 | 0 | 1036 | C+S GST 18% I/P RD | 186.48 | 1222.48 | 1222.48 | Approved | 0 | 0 | 1912 | 18 Feb 2022
GANGA DHAM TOWERS | 372 | 93517 | 18 Feb 2022 |  | B & B ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2057 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10 | Sq.Ft | 150 | 100 | 0 | 0 | 1500 | C+S GST 0% I/P RD | 0 | 1500 | 1500 | Approved | 0 | 0 | 15 | 18 Feb 2022
GANGA DHAM TOWERS | 1287 | 93500 | 16 Feb 2022 |  | SANTOSH HMMAT CHAVHAN | SVS CONSTRUCTION. | EV - 1925 | B 1102 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 255.2364 | Sq.Ft | 55 | 100 | 350.95 | 0 | 14038 | C+S GST 0% I/P RD | 0 | 14038 | 14038 | Approved | 0 | 0 | 477 | 16 Feb 2022
GANGA DHAM TOWERS | 1287 | 93500 | 16 Feb 2022 |  | SANTOSH HMMAT CHAVHAN | SVS CONSTRUCTION. | EV - 1925 | B 1502 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 255.2364 | Sq.Ft | 55 | 100 | 350.95 | 0 | 14038 | C+S GST 0% I/P RD | 0 | 14038 | 14038 | Approved | 0 | 0 | 477 | 16 Feb 2022
GANGA DHAM TOWERS | 1287 | 93500 | 16 Feb 2022 |  | SANTOSH HMMAT CHAVHAN | SVS CONSTRUCTION. | EV - 1925 | B 501 Toilet Ledge wall BBM/ Plaster | Brickwork/ Plaster - Sq.Ft | 356.7273 | Sq.Ft | 55 | 100 | 490.5 | 0 | 19620 | C+S GST 0% I/P RD | 0 | 19620 | 19620 | Approved | 0 | 0 | 477 | 16 Feb 2022
GANGA DHAM TOWERS | 1296 | 93492 | 15 Feb 2022 |  | SHREYA PRAKASH OSWAL | SHREYA PRAKASH OSWAL | EV - 1921 | Miscellaneous expenses | Marketing Operating Expenses | 8.48 | Month | 25000 | 8.33 | 0 | 0 | 17659.6 | C+S GST 0% I/P RD | 0 | 17659.6 | 17659.6 | Approved | 0 | 0 | 177 | 15 Feb 2022
GANGA DHAM TOWERS | 1094 | 93491 | 15 Feb 2022 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 2185 | C Pump Charges From (Spt 21 To Feb 22) | Pumping Charges-BC | 650.4 | Cu.Mtrs | 190 | 100 | 3089.4 | 0 | 123576 | C+S GST 18% I/P RD | 22243.68 | 145819.68 | 145819.68 | Approved | 0 | 0 | 2472 | 15 Feb 2022
GANGA DHAM TOWERS | 253 | 93468 | 14 Feb 2022 |  | UNIQUE ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1964 | B Bldg 1st RCC Slab Built-up Area (L) | Hacking Work | 1199.9307 | Sq.Ft | 2.886 | 100 | 86.58 | 0 | 3463 | C+S GST 0% I/P RD | 0 | 3463 | 3463 | Approved | 0 | 0 | 35 | 14 Feb 2022
GANGA DHAM TOWERS | 395 | 93466 | 14 Feb 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2001 | A Bldg Flat No. 2304 Gypsum Plaster | Dhar Core (L) | 100 | R.Ft | 10 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 118 | 14 Feb 2022
GANGA DHAM TOWERS | 395 | 93466 | 14 Feb 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2001 | A Bldg Flat No. 2304 Gypsum Plaster | Gypsum on Wall (L) | 2698 | Sq.Ft | 4 | 100 | 269.8 | 0 | 10792 | C+S GST 18% I/P RD | 1942.56 | 12734.56 | 12734.56 | Approved | 0 | 0 | 118 | 14 Feb 2022
GANGA DHAM TOWERS | 209 | 93465 | 14 Feb 2022 |  | UNIQUE ENTERPRISES | JAY GANESH ENTERPRISES | EV - 2020 | A Bldg 1st RCC Slab (Stilt Floor) Built-up Area (L) | Hacking Work | 1885 | Sq.Ft | 5 | 100 | 235.63 | 0 | 9425 | C+S GST 0% I/P RD | 0 | 9425 | 9425 | Approved | 0 | 0 | 94 | 14 Feb 2022
GANGA DHAM TOWERS | 209 | 93464 | 14 Feb 2022 |  | UNIQUE ENTERPRISES | PRAKASH CONTRACTOR | EV - 1950 | .A Bldg RCC Plinth Beam Substructure work | RCC Beam | 140 | Sq.Ft | 37 | 100 | 129.5 | 0 | 5180 | C+S GST 0% I/P RD | 0 | 5180 | 5180 | Approved | 0 | 0 | 52 | 14 Feb 2022
GANGA DHAM TOWERS | 1247 | 93463 | 14 Feb 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1952 | B Parking 105 level Gypsum Board Breaking Work ( Sample Flat | Breaking & Shifting- Lumpsum-BRE | 1 | No. | 3000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 30 | 14 Feb 2022
GANGA DHAM TOWERS | 1232 | 93462 | 14 Feb 2022 |  | PURVA ENTERPRISES | PURVA ENTERPRISES | EV - 2005 | Tower Crane Wire Rope Removing & Refixing | Labour Lumpsum - BCo | 1 | No. | 5000 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 50 | 14 Feb 2022
GANGA DHAM TOWERS | 1184 | 93460 | 14 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1926 | A P1 Floor External Sand Face Plaster | External Plaster- BC | 650 | Sq.Ft | 20 | 100 | 325 | 0 | 13000 | C+S GST 0% I/P RD | 0 | 13000 | 13000 | Approved | 0 | 0 | 873 | 14 Feb 2022
GANGA DHAM TOWERS | 1184 | 93460 | 14 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1926 | A Podium Floor External Sand Face Plaster | External Plaster- BC | 1181 | Sq.Ft | 20 | 100 | 590.5 | 0 | 23620 | C+S GST 0% I/P RD | 0 | 23620 | 23620 | Approved | 0 | 0 | 873 | 14 Feb 2022
GANGA DHAM TOWERS | 1184 | 93460 | 14 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1926 | A P3 Floor External Sand Face Plaster | External Plaster- BC | 1497 | Sq.Ft | 20 | 100 | 748.5 | 0 | 29940 | C+S GST 0% I/P RD | 0 | 29940 | 29940 | Approved | 0 | 0 | 873 | 14 Feb 2022
GANGA DHAM TOWERS | 1184 | 93460 | 14 Feb 2022 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1926 | A P2 Floor External Sand Face Plaster | External Plaster- BC | 1037 | Sq.Ft | 20 | 100 | 518.5 | 0 | 20740 | C+S GST 0% I/P RD | 0 | 20740 | 20740 | Approved | 0 | 0 | 873 | 14 Feb 2022
GANGA DHAM TOWERS | 641 | 93459 | 14 Feb 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1993 | A 1902 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.58 | R.Ft | 60 | 100 | 47.37 | 0 | 1894.8 | C+S GST 18% I/P RD | 341.06 | 2235.86 | 2235.86 | Approved | 0 | 0 | 84 | 14 Feb 2022
GANGA DHAM TOWERS | 641 | 93459 | 14 Feb 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1993 | A 2304 Master Bed Marble Flooring | Italian Marble Champher & Polish | 28.71 | R.Ft | 60 | 100 | 43.07 | 0 | 1722.6 | C+S GST 18% I/P RD | 310.06 | 2032.66 | 2032.66 | Approved | 0 | 0 | 84 | 14 Feb 2022
GANGA DHAM TOWERS | 641 | 93459 | 14 Feb 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1993 | A 2304 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 21.49 | R.Ft | 60 | 100 | 32.24 | 0 | 1289.4 | C+S GST 18% I/P RD | 232.1 | 1521.5 | 1521.5 | Approved | 0 | 0 | 84 | 14 Feb 2022
GANGA DHAM TOWERS | 641 | 93459 | 14 Feb 2022 |  | R K INTERIOR | Kishan Enterprises | EV - 1993 | A 2304 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.13 | R.Ft | 60 | 100 | 87.2 | 0 | 3487.8 | C+S GST 18% I/P RD | 627.8 | 4115.6 | 4115.6 | Approved | 0 | 0 | 84 | 14 Feb 2022
GANGA DHAM TOWERS | 1234 | 93458 | 14 Feb 2022 |  | AVCON TECHNICS PVT LTD | Kishan Enterprises | EV - 1957 | A 2304 NOC | Italian marble Skirting - BCo | 40 | R.Ft | 55 | 100 | 0 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 22 | 14 Feb 2022
GANGA DHAM TOWERS | 551 | 93457 | 14 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1959 | A 2304 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 30.086 | R.Ft | 60 | 100 | 45.13 | 0 | 1805.16 | C+S GST 18% I/P RD | 324.92 | 2130.08 | 2130.08 | Approved | 0 | 0 | 91 | 14 Feb 2022
GANGA DHAM TOWERS | 551 | 93457 | 14 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1959 | A 2304 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81.382 | R.Ft | 60 | 100 | 122.07 | 0 | 4882.92 | C+S GST 18% I/P RD | 878.92 | 5761.84 | 5761.84 | Approved | 0 | 0 | 91 | 14 Feb 2022
GANGA DHAM TOWERS | 551 | 93457 | 14 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1959 | A 2304 Master Bed Marble Flooring | Italian marble Skirting - BCo | 40.194 | R.Ft | 60 | 100 | 60.29 | 0 | 2411.64 | C+S GST 18% I/P RD | 434.1 | 2845.74 | 2845.74 | Approved | 0 | 0 | 91 | 14 Feb 2022
GANGA DHAM TOWERS | 1251 | 93456 | 14 Feb 2022 |  | Kishan Enterprises | Kishan Enterprises | EV - 1961 | A 2002 NOC | Italian marble Skirting - BCo | 45 | R.Ft | 55 | 100 | 61.88 | 0 | 2475 | C+S GST 18% I/P RD | 445.5 | 2920.5 | 2920.5 | Approved | 0 | 0 | 25 | 14 Feb 2022
GANGA DHAM TOWERS | 1002 | 93455 | 14 Feb 2022 |  | AVCON TECHNICS PVT LTD | Kishan Enterprises | EV - 1960 | A 1902 NOC | Italian marble Skirting - BCo | 12.14 | R.Ft | 55 | 100 | 16.69 | 0 | 667.7 | C+S GST 18% I/P RD | 120.18 | 787.88 | 787.88 | Approved | 0 | 0 | 7 | 14 Feb 2022
GANGA DHAM TOWERS | 537 | 93454 | 14 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1958 | A 1902 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 31.58 | R.Ft | 60 | 100 | 47.37 | 0 | 1894.8 | C+S GST 18% I/P RD | 341.06 | 2235.86 | 2235.86 | Approved | 0 | 0 | 19 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1901 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1902 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1903 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1904 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 2001 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1902 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 457.36 | Sq.Ft | 19 | 100 | 868.98 | 0 | 8689.84 | CGST 0% URD I/P | 0 | 8689.84 | 8689.84 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1903 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 362.53 | Sq.Ft | 19 | 100 | 688.81 | 0 | 6888.07 | CGST 0% URD I/P | 0 | 6888.07 | 6888.07 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1901 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 436.05 | Sq.Ft | 19 | 100 | 828.5 | 0 | 8284.95 | CGST 0% URD I/P | 0 | 8284.95 | 8284.95 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1901 Chemical & IPS Waterproofing | IPS W/P | 436.05 | Sq.Ft | 11 | 100 | 479.66 | 0 | 4796.55 | CGST 0% URD I/P | 0 | 4796.55 | 4796.55 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 2001 Chemical & IPS Waterproofing | IPS W/P | 392.445 | Sq.Ft | 11 | 100 | 431.69 | 0 | 4316.9 | CGST 0% URD I/P | 0 | 4316.9 | 4316.9 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1902 Chemical & IPS Waterproofing | IPS W/P | 411.624 | Sq.Ft | 11 | 100 | 452.79 | 0 | 4527.86 | CGST 0% URD I/P | 0 | 4527.86 | 4527.86 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1904 Chemical & IPS Waterproofing | IPS W/P | 400.68 | Sq.Ft | 11 | 100 | 440.75 | 0 | 4407.48 | CGST 0% URD I/P | 0 | 4407.48 | 4407.48 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1002 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 702 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1502 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1701 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1602 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1001 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1201 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1702 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1402 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1101 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 802 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1703 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1903 Chemical & IPS Waterproofing | IPS W/P | 271.8975 | Sq.Ft | 11 | 100 | 299.09 | 0 | 2990.87 | CGST 0% URD I/P | 0 | 2990.87 | 2990.87 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1903 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 14 | No. | 70 | 100 | 98 | 0 | 980 | CGST 0% URD I/P | 0 | 980 | 980 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1904 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 16 | No. | 70 | 100 | 112 | 0 | 1120 | CGST 0% URD I/P | 0 | 1120 | 1120 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1901 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 16 | No. | 70 | 100 | 112 | 0 | 1120 | CGST 0% URD I/P | 0 | 1120 | 1120 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1902 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 2001 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 16 | No. | 70 | 100 | 112 | 0 | 1120 | CGST 0% URD I/P | 0 | 1120 | 1120 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1902 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1903 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 2001 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1904 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 17 | No. | 150 | 100 | 255 | 0 | 2550 | CGST 0% URD I/P | 0 | 2550 | 2550 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 401 | 93453 | 14 Feb 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 2003 | A 1901 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 807 | 14 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 903 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.31 | R.Ft | 700 | 100 | 92.93 | 0 | 3717 | C+S GST 18% I/P RD | 669.06 | 4386.06 | 4386.06 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 704 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.37 | R.Ft | 700 | 100 | 93.98 | 0 | 3759 | C+S GST 18% I/P RD | 676.62 | 4435.62 | 4435.62 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 703 Guest Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.95 | R.Ft | 700 | 100 | 86.63 | 0 | 3465 | C+S GST 18% I/P RD | 623.7 | 4088.7 | 4088.7 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 903 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.31 | R.Ft | 700 | 100 | 92.93 | 0 | 3717 | C+S GST 18% I/P RD | 669.06 | 4386.06 | 4386.06 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 704 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.98 | R.Ft | 700 | 100 | 52.15 | 0 | 2086 | C+S GST 18% I/P RD | 375.48 | 2461.48 | 2461.48 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 703 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.31 | R.Ft | 700 | 100 | 92.93 | 0 | 3717 | C+S GST 18% I/P RD | 669.06 | 4386.06 | 4386.06 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 1704 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.34 | R.Ft | 750 | 100 | 100.13 | 0 | 4005 | C+S GST 18% I/P RD | 720.9 | 4725.9 | 4725.9 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 1704 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 750 | 100 | 55.31 | 0 | 2212.5 | C+S GST 18% I/P RD | 398.26 | 2610.76 | 2610.76 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 551 | 93443 | 12 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1955 | A 1704 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.3707 | R.Ft | 750 | 100 | 100.7 | 0 | 4028.01 | C+S GST 18% I/P RD | 725.04 | 4753.05 | 4753.05 | Approved | 0 | 0 | 307 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 2101 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1901 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1902 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1502 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1301 Terrace Parapet Top Granite | Granite Sill-BCo | 20.42 | R.Ft | 50 | 100 | 25.53 | 0 | 1021 | C+S GST 18% I/P RD | 183.78 | 1204.78 | 1204.78 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 2101 Terrace Vitrified Flooring | Vitrified Skirting BC | 32.382 | R.Ft | 28 | 100 | 22.67 | 0 | 906.7 | C+S GST 18% I/P RD | 163.2 | 1069.9 | 1069.9 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 2102 Terrace Vitrified Flooring | Vitrified Skirting BC | 32.382 | R.Ft | 28 | 100 | 22.67 | 0 | 906.7 | C+S GST 18% I/P RD | 163.2 | 1069.9 | 1069.9 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 501 Terrace Parapet Top Granite | Granite Sill-BCo | 20.425 | R.Ft | 40 | 100 | 20.43 | 0 | 817 | C+S GST 18% I/P RD | 147.06 | 964.06 | 964.06 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 2101 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210 | Sq.Ft | 60 | 100 | 315 | 0 | 12600 | C+S GST 18% I/P RD | 2268 | 14868 | 14868 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 502 Kitchen Vitrified Flooring | Vitrified Skirting BC | 25 | R.Ft | 15 | 100 | 9.38 | 0 | 375 | C+S GST 18% I/P RD | 67.5 | 442.5 | 442.5 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 401 Kitchen Vitrified Flooring | Vitrified Skirting BC | 25 | R.Ft | 15 | 100 | 9.38 | 0 | 375 | C+S GST 18% I/P RD | 67.5 | 442.5 | 442.5 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 201 Terrace Vitrified Flooring | Vitrified Skirting BC | 25 | R.Ft | 15 | 100 | 9.38 | 0 | 375 | C+S GST 18% I/P RD | 67.5 | 442.5 | 442.5 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 701 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 700 | 100 | 60.2 | 0 | 2408 | C+S GST 18% I/P RD | 433.44 | 2841.44 | 2841.44 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 701 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 700 | 100 | 43.05 | 0 | 1722 | C+S GST 18% I/P RD | 309.96 | 2031.96 | 2031.96 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 701 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 700 | 100 | 95.2 | 0 | 3808 | C+S GST 18% I/P RD | 685.44 | 4493.44 | 4493.44 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1101 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 700 | 100 | 60.2 | 0 | 2408 | C+S GST 18% I/P RD | 433.44 | 2841.44 | 2841.44 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1101 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 700 | 100 | 95.2 | 0 | 3808 | C+S GST 18% I/P RD | 685.44 | 4493.44 | 4493.44 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1101 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 700 | 100 | 43.05 | 0 | 1722 | C+S GST 18% I/P RD | 309.96 | 2031.96 | 2031.96 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 701 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 700 | 100 | 51.63 | 0 | 2065 | C+S GST 18% I/P RD | 371.7 | 2436.7 | 2436.7 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 2101 Terrace Vitrified Flooring | Vitrified Flooring -BC | 139.25 | Sq.Ft | 28 | 100 | 97.48 | 0 | 3899 | C+S GST 18% I/P RD | 701.82 | 4600.82 | 4600.82 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 2102 Terrace Vitrified Flooring | Vitrified Flooring -BC | 140.472 | Sq.Ft | 28 | 100 | 98.33 | 0 | 3933.22 | C+S GST 18% I/P RD | 707.98 | 4641.2 | 4641.2 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1701 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 750 | 100 | 102 | 0 | 4080 | C+S GST 18% I/P RD | 734.4 | 4814.4 | 4814.4 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1701 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 750 | 100 | 46.13 | 0 | 1845 | C+S GST 18% I/P RD | 332.1 | 2177.1 | 2177.1 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1502 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.26 | R.Ft | 750 | 100 | 117.38 | 0 | 4695 | C+S GST 18% I/P RD | 845.1 | 5540.1 | 5540.1 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1502 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.1 | R.Ft | 750 | 100 | 114.38 | 0 | 4575 | C+S GST 18% I/P RD | 823.5 | 5398.5 | 5398.5 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1502 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.4907 | R.Ft | 750 | 100 | 46.7 | 0 | 1868.01 | C+S GST 18% I/P RD | 336.24 | 2204.25 | 2204.25 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1502 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.87 | R.Ft | 750 | 100 | 53.81 | 0 | 2152.5 | C+S GST 18% I/P RD | 387.46 | 2539.96 | 2539.96 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1701 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 750 | 100 | 64.5 | 0 | 2580 | C+S GST 18% I/P RD | 464.4 | 3044.4 | 3044.4 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 1002 Kitchen Vitrified Flooring | Vitrified Skirting BC | 25 | R.Ft | 20 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 2102 Terrace Parapet Top Granite | Granite Sill-BCo | 20.4182 | R.Ft | 55 | 100 | 28.08 | 0 | 1123 | C+S GST 18% I/P RD | 202.14 | 1325.14 | 1325.14 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 601 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 650 | 100 | 55.9 | 0 | 2236 | C+S GST 18% I/P RD | 402.48 | 2638.48 | 2638.48 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 537 | 93442 | 12 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1997 | A 601 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 650 | 100 | 39.98 | 0 | 1599 | C+S GST 18% I/P RD | 287.82 | 1886.82 | 1886.82 | Approved | 0 | 0 | 1496 | 12 Feb 2022
GANGA DHAM TOWERS | 1211 | 93438 | 11 Feb 2022 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 1963 | Ganga Collidium Shop 32 Internal paint (m + l) | Enamel Paint (M+L) | 453 | Sq.Ft | 15 | 100 | 169.88 | 0 | 6795 | C+S GST 18% I/P RD | 1223.1 | 8018.1 | 8018.1 | Approved | 0 | 0 | 532 | 11 Feb 2022
GANGA DHAM TOWERS | 1211 | 93438 | 11 Feb 2022 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 1963 | Ganga Collidium Shop 32 Internal paint (m + l) | Satin Matt Paint (M+L)-BCo | 905 | Sq.Ft | 22 | 100 | 497.75 | 0 | 19910 | C+S GST 18% I/P RD | 3583.8 | 23493.8 | 23493.8 | Approved | 0 | 0 | 532 | 11 Feb 2022
GANGA DHAM TOWERS | 1211 | 93438 | 11 Feb 2022 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 1963 | Ganga Collidium Shop 32 Internal paint (m + l) | Grid False Ceiling (M+L) | 312 | Sq.Ft | 85 | 100 | 663 | 0 | 26520 | C+S GST 18% I/P RD | 4773.6 | 31293.6 | 31293.6 | Approved | 0 | 0 | 532 | 11 Feb 2022
GANGA DHAM TOWERS | 1052 | 93437 | 11 Feb 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1887 | Legal Consultancy | Legal Consultancy | 12 | Month | 30000 | 8.33 | 0 | 0 | 29988 | CGST 0% URD I/P | 0 | 29988 | 29988 | Approved | 0 | 5700 | 2999 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 50.9211 | Sq.Ft | 152 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 50.9211 | Sq.Ft | 152 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 50.9211 | Sq.Ft | 152 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 50.9211 | Sq.Ft | 152 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 54.3158 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 47.9257 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 54.3158 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 54.3158 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 47.9257 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 272 | 93428 | 11 Feb 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2212 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 47.9257 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7740 | C+S GST 18% I/P RD | 1393.2 | 9133.2 | 9133.2 | Approved | 0 | 0 | 774 | 11 Feb 2022
GANGA DHAM TOWERS | 498 | 93427 | 11 Feb 2022 |  | SHWETA SURESH GOVALKAR | AJAY KUMAR GUPTA |  | B 1001 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 |  | 0 | 0 | 13 | 11 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Master Toilet dado | Dado BC | 148.12 | Sq.Ft | 22 | 100 | 81.47 | 0 | 3258.64 | C+S GST 18% I/P RD | 586.56 | 3845.2 | 3845.2 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Powder Toilet dado | Dado BC | 82 | Sq.Ft | 22 | 100 | 45.1 | 0 | 1804 | C+S GST 18% I/P RD | 324.72 | 2128.72 | 2128.72 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Children Toilet Dado | Dado BC | 148.12 | Sq.Ft | 22 | 100 | 81.47 | 0 | 3258.64 | C+S GST 18% I/P RD | 586.56 | 3845.2 | 3845.2 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Parents Toilet dado | Dado BC | 106.04 | Sq.Ft | 22 | 100 | 58.32 | 0 | 2332.88 | C+S GST 18% I/P RD | 419.92 | 2752.8 | 2752.8 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Master Toilet dado | L Groove - BCV | 38.61 | R.Ft | 20 | 100 | 19.31 | 0 | 772.2 | C+S GST 18% I/P RD | 139 | 911.2 | 911.2 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Parents Toilet dado | L Groove - BCV | 21.996 | R.Ft | 20 | 100 | 11 | 0 | 439.92 | C+S GST 18% I/P RD | 79.18 | 519.1 | 519.1 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Powder Toilet dado | L Groove - BCV | 32.238 | R.Ft | 20 | 100 | 16.12 | 0 | 644.76 | C+S GST 18% I/P RD | 116.06 | 760.82 | 760.82 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Children Toilet Dado | L Groove - BCV | 38.7 | R.Ft | 20 | 100 | 19.35 | 0 | 774 | C+S GST 18% I/P RD | 139.32 | 913.32 | 913.32 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Children Toilet Dado | Dado BC | 67.125 | Sq.Ft | 24 | 100 | 40.28 | 0 | 1611 | C+S GST 18% I/P RD | 289.98 | 1900.98 | 1900.98 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Master Toilet dado | Dado BC | 67.78 | Sq.Ft | 24 | 100 | 40.67 | 0 | 1626.72 | C+S GST 18% I/P RD | 292.8 | 1919.52 | 1919.52 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Parents Toilet dado | Dado BC | 75 | Sq.Ft | 24 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Powder Toilet dado | Dado BC | 38.86 | Sq.Ft | 24 | 100 | 23.32 | 0 | 932.64 | C+S GST 18% I/P RD | 167.88 | 1100.52 | 1100.52 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 42.4762 | Sq.Ft | 21 | 100 | 22.3 | 0 | 892 | C+S GST 18% I/P RD | 160.56 | 1052.56 | 1052.56 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.4286 | Sq.Ft | 21 | 100 | 19.65 | 0 | 786 | C+S GST 18% I/P RD | 141.48 | 927.48 | 927.48 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 49.2381 | Sq.Ft | 21 | 100 | 25.85 | 0 | 1034 | C+S GST 18% I/P RD | 186.12 | 1220.12 | 1220.12 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 551 | 93397 | 09 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1994 | A 1704 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 49.2381 | Sq.Ft | 21 | 100 | 25.85 | 0 | 1034 | C+S GST 18% I/P RD | 186.12 | 1220.12 | 1220.12 | Approved | 0 | 0 | 230 | 09 Feb 2022
GANGA DHAM TOWERS | 1170 | 93396 | 09 Feb 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2193 | A Fire Fighting 14 Floors | Flexible Hose Pipe 25mm Dia (1mtr length) (L) | 245 | No. | 200 | 100 | 1225 | 0 | 49000 | C+S GST 18% I/P RD | 8820 | 57820 | 57820 | Approved | 0 | 0 | 1421 | 09 Feb 2022
GANGA DHAM TOWERS | 1170 | 93396 | 09 Feb 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2193 | A Fire Fighting 14 Floors | Sprinkler 15mm 68 dg Pendent (L) | 245 | No. | 90 | 100 | 551.25 | 0 | 22050 | C+S GST 18% I/P RD | 3969 | 26019 | 26019 | Approved | 0 | 0 | 1421 | 09 Feb 2022
GANGA DHAM TOWERS | 983 | 93394 | 09 Feb 2022 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 1924 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting 6" BCE | 151 | No. | 210 | 100 | 792.75 | 0 | 31710 | C+S GST 18% I/P RD | 5707.8 | 37417.8 | 37417.8 | Approved | 0 | 0 | 317 | 09 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 602 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.26 | R.Ft | 650 | 100 | 101.73 | 0 | 4069 | C+S GST 18% I/P RD | 732.42 | 4801.42 | 4801.42 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 601 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 650 | 100 | 47.94 | 0 | 1917.5 | C+S GST 18% I/P RD | 345.16 | 2262.66 | 2262.66 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 602 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.87 | R.Ft | 650 | 100 | 46.64 | 0 | 1865.5 | C+S GST 18% I/P RD | 335.8 | 2201.3 | 2201.3 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 602 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.1 | R.Ft | 650 | 100 | 99.13 | 0 | 3965 | C+S GST 18% I/P RD | 713.7 | 4678.7 | 4678.7 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 201 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 650 | 100 | 88.4 | 0 | 3536 | C+S GST 18% I/P RD | 636.48 | 4172.48 | 4172.48 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 601 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 650 | 100 | 88.4 | 0 | 3536 | C+S GST 18% I/P RD | 636.48 | 4172.48 | 4172.48 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 201 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 650 | 100 | 47.94 | 0 | 1917.5 | C+S GST 18% I/P RD | 345.16 | 2262.66 | 2262.66 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 602 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.4908 | R.Ft | 650 | 100 | 40.48 | 0 | 1619 | C+S GST 18% I/P RD | 291.42 | 1910.42 | 1910.42 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 1001 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 700 | 100 | 95.2 | 0 | 3808 | C+S GST 18% I/P RD | 685.44 | 4493.44 | 4493.44 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 1001 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.95 | R.Ft | 700 | 100 | 51.63 | 0 | 2065 | C+S GST 18% I/P RD | 371.7 | 2436.7 | 2436.7 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 1001 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.44 | R.Ft | 700 | 100 | 60.2 | 0 | 2408 | C+S GST 18% I/P RD | 433.44 | 2841.44 | 2841.44 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 1002 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.49 | R.Ft | 700 | 100 | 43.58 | 0 | 1743 | C+S GST 18% I/P RD | 313.74 | 2056.74 | 2056.74 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 1001 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.46 | R.Ft | 700 | 100 | 43.05 | 0 | 1722 | C+S GST 18% I/P RD | 309.96 | 2031.96 | 2031.96 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 1002 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.87 | R.Ft | 700 | 100 | 50.23 | 0 | 2009 | C+S GST 18% I/P RD | 361.62 | 2370.62 | 2370.62 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 1002 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.1 | R.Ft | 700 | 100 | 106.75 | 0 | 4270 | C+S GST 18% I/P RD | 768.6 | 5038.6 | 5038.6 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 537 | 93377 | 07 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1996 | A 1002 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 6.26 | R.Ft | 700 | 100 | 109.55 | 0 | 4382 | C+S GST 18% I/P RD | 788.76 | 5170.76 | 5170.76 | Approved | 0 | 0 | 448 | 07 Feb 2022
GANGA DHAM TOWERS | 551 | 93376 | 07 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1945 | A 504 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.98 | R.Ft | 650 | 100 | 48.43 | 0 | 1937 | C+S GST 18% I/P RD | 348.66 | 2285.66 | 2285.66 | Approved | 0 | 0 | 158 | 07 Feb 2022
GANGA DHAM TOWERS | 551 | 93376 | 07 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1945 | A 603 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.3108 | R.Ft | 650 | 100 | 86.3 | 0 | 3452 | C+S GST 18% I/P RD | 621.36 | 4073.36 | 4073.36 | Approved | 0 | 0 | 158 | 07 Feb 2022
GANGA DHAM TOWERS | 551 | 93376 | 07 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1945 | A 504 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.2908 | R.Ft | 650 | 100 | 37.23 | 0 | 1489 | C+S GST 18% I/P RD | 268.02 | 1757.02 | 1757.02 | Approved | 0 | 0 | 158 | 07 Feb 2022
GANGA DHAM TOWERS | 551 | 93376 | 07 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1945 | A 604 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.98 | R.Ft | 650 | 100 | 48.43 | 0 | 1937 | C+S GST 18% I/P RD | 348.66 | 2285.66 | 2285.66 | Approved | 0 | 0 | 158 | 07 Feb 2022
GANGA DHAM TOWERS | 551 | 93376 | 07 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1945 | A 504 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.3708 | R.Ft | 650 | 100 | 87.28 | 0 | 3491 | C+S GST 18% I/P RD | 628.38 | 4119.38 | 4119.38 | Approved | 0 | 0 | 158 | 07 Feb 2022
GANGA DHAM TOWERS | 551 | 93376 | 07 Feb 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1945 | A 604 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.3708 | R.Ft | 650 | 100 | 87.28 | 0 | 3491 | C+S GST 18% I/P RD | 628.38 | 4119.38 | 4119.38 | Approved | 0 | 0 | 158 | 07 Feb 2022
GANGA DHAM TOWERS | 1275 | 93347 | 04 Feb 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1899 | B Bldg Safety Jali Work | M.S. Jali- DPo | 1258.9091 | Sq.Ft | 11 | 100 | 346.2 | 0 | 13848 | C+S GST 0% I/P RD | 0 | 13848 | 13848 | Approved | 0 | 0 | 138 | 04 Feb 2022
GANGA DHAM TOWERS | 1274 | 93346 | 04 Feb 2022 |  | PARTH ENTERPRISES | PARTH ENTERPRISES | EV - 1900 | A Safety Jali Fabrication Work | M.S. Jali- DPo | 1103 | Sq.Ft | 11 | 100 | 303.33 | 0 | 12133 | C+S GST 0% I/P RD | 0 | 12133 | 12133 | Approved | 0 | 0 | 121 | 04 Feb 2022
GANGA DHAM TOWERS | 537 | 93331 | 03 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1995 | A 2101 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 524 | Sq.Ft | 60 | 100 | 786 | 0 | 31440 | C+S GST 18% I/P RD | 5659.2 | 37099.2 | 37099.2 | Approved | 0 | 0 | 841 | 03 Feb 2022
GANGA DHAM TOWERS | 537 | 93331 | 03 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1995 | A 2101 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.9667 | Sq.Ft | 60 | 100 | 316.45 | 0 | 12658 | C+S GST 18% I/P RD | 2278.44 | 14936.44 | 14936.44 | Approved | 0 | 0 | 841 | 03 Feb 2022
GANGA DHAM TOWERS | 537 | 93331 | 03 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1995 | A 2101 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 125.3333 | Sq.Ft | 60 | 100 | 188 | 0 | 7520 | C+S GST 18% I/P RD | 1353.6 | 8873.6 | 8873.6 | Approved | 0 | 0 | 841 | 03 Feb 2022
GANGA DHAM TOWERS | 537 | 93331 | 03 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1995 | A 801 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 524.7 | Sq.Ft | 50 | 100 | 655.88 | 0 | 26235 | C+S GST 18% I/P RD | 4722.3 | 30957.3 | 30957.3 | Approved | 0 | 0 | 841 | 03 Feb 2022
GANGA DHAM TOWERS | 537 | 93331 | 03 Feb 2022 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1995 | A 801 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 125.34 | Sq.Ft | 50 | 100 | 156.68 | 0 | 6267 | C+S GST 18% I/P RD | 1128.06 | 7395.06 | 7395.06 | Approved | 0 | 0 | 841 | 03 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B Ground Floor Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 336 | Sq.Ft | 5 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P1 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 336 | Sq.Ft | 5 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P2 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 336 | Sq.Ft | 5 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P3 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 336 | Sq.Ft | 5 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P3 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (L) | 180 | Sq.Ft | 4 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P1 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (L) | 180 | Sq.Ft | 4 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P2 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 336 | Sq.Ft | 4 | 100 | 33.6 | 0 | 1344 | C+S GST 18% I/P RD | 241.92 | 1585.92 | 1585.92 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P1 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 336 | Sq.Ft | 4 | 100 | 33.6 | 0 | 1344 | C+S GST 18% I/P RD | 241.92 | 1585.92 | 1585.92 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B Ground Floor Beam & Ceiling Plaster | Gypsum Plaster (L) | 180 | Sq.Ft | 4 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P2 Parking Beam & Ceiling Plaster | Gypsum Plaster (L) | 180 | Sq.Ft | 4 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B P3 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 336 | Sq.Ft | 4 | 100 | 33.6 | 0 | 1344 | C+S GST 18% I/P RD | 241.92 | 1585.92 | 1585.92 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 696 | 93316 | 02 Feb 2022 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2222 | B Ground Floor Staircase & Lobby Plaster | Gypsum Plaster (L) | 336 | Sq.Ft | 4 | 100 | 33.6 | 0 | 1344 | C+S GST 18% I/P RD | 241.92 | 1585.92 | 1585.92 | Approved | 0 | 0 | 150 | 02 Feb 2022
GANGA DHAM TOWERS | 1162 | 93315 | 02 Feb 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 1880 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 02 Feb 2022
GANGA DHAM TOWERS | 1262 | 93314 | 02 Feb 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 2221 | B 1602 NOC | Plumbing Work - BCo | 5 | No. | 900 | 100 | 112.5 | 0 | 4500 | C+S GST 0% I/P RD | 0 | 4500 | 4500 | Approved | 0 | 0 | 45 | 02 Feb 2022
GANGA DHAM TOWERS | 634 | 93280 | 01 Feb 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1877 | A 24th Floor Lift cladding | Dado Work - BC | 30 | Sq.Ft | 70 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 2741 | 01 Feb 2022
GANGA DHAM TOWERS | 634 | 93280 | 01 Feb 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1877 | A 24th Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 2741 | 01 Feb 2022
GANGA DHAM TOWERS | 634 | 93280 | 01 Feb 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1877 | A 24th Floor Lift cladding | V Grove - BCo | 137 | R.Ft | 108 | 100 | 369.9 | 0 | 14796 | C+S GST 18% I/P RD | 2663.28 | 17459.28 | 17459.28 | Approved | 0 | 0 | 2741 | 01 Feb 2022
GANGA DHAM TOWERS | 634 | 93280 | 01 Feb 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1877 | A 24th Floor Lobbby Flooring | Vitrified Flooring -Bco | 560 | Sq.Ft | 45 | 100 | 630 | 0 | 25200 | C+S GST 18% I/P RD | 4536 | 29736 | 29736 | Approved | 0 | 0 | 2741 | 01 Feb 2022
GANGA DHAM TOWERS | 634 | 93280 | 01 Feb 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1877 | A 24th Floor Lift cladding | Italian Marble Bull Nosing | 530 | R.Ft | 76 | 100 | 1007 | 0 | 40280 | C+S GST 18% I/P RD | 7250.4 | 47530.4 | 47530.4 | Approved | 0 | 0 | 2741 | 01 Feb 2022
GANGA DHAM TOWERS | 634 | 93280 | 01 Feb 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1877 | A 24th Floor Lobbby Flooring | Vitrified Skirting -Bco | 45 | R.Ft | 45 | 100 | 50.63 | 0 | 2025 | C+S GST 18% I/P RD | 364.5 | 2389.5 | 2389.5 | Approved | 0 | 0 | 2741 | 01 Feb 2022
GANGA DHAM TOWERS | 634 | 93280 | 01 Feb 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1877 | A 24th Floor Lift cladding | Italian Marble Border-BCo | 297 | R.Ft | 94 | 100 | 697.95 | 0 | 27918 | C+S GST 18% I/P RD | 5025.24 | 32943.24 | 32943.24 | Approved | 0 | 0 | 2741 | 01 Feb 2022
GANGA DHAM TOWERS | 1002 | 93279 | 01 Feb 2022 |  | AVCON TECHNICS PVT LTD | JAY GANESH ENTERPRISES | EV - 2022 | A 2302 NOC | Blockwork 4" - BC | 83.19 | Sq.Ft | 15 | 100 | 31.2 | 0 | 1247.85 | CGST 0% URD I/P | 0 | 1247.85 | 1247.85 | Approved | 0 | 0 | 12 | 01 Feb 2022
GANGA DHAM TOWERS | 1234 | 93278 | 01 Feb 2022 |  | AVCON TECHNICS PVT LTD | JAY GANESH ENTERPRISES | EV - 1943 | A 2304 NOC | Blockwork 4" - BC | 54.98 | Sq.Ft | 24 | 100 | 0 | 0 | 1319.52 | CGST 0% URD I/P | 0 | 1319.52 | 1319.52 | Approved | 0 | 0 | 0 | 01 Feb 2022
GANGA DHAM TOWERS | 1169 | 93277 | 01 Feb 2022 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 2146 | A Fire Fighting 14 Floors | Rate Diff. GI C Class Pipe 40 mm dia. | 244 | Mtrs | 33.796 | 100 | 0 | 0 | 8246.22 | C+S GST 18% I/P RD | 1484.32 | 9730.54 | 9730.54 | Approved | 0 | 0 | 82 | 01 Feb 2022
GANGA DHAM TOWERS | 532 | 93276 | 01 Feb 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS |  | A 1304 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 44.6154 | Mtrs | 19.5 | 100 | 0 | 0 | 870 | C+S GST 18% I/P RD | 156.6 | 1026.6 | 1026.6 |  | 0 | 0 | 9 | 01 Feb 2022
GANGA DHAM TOWERS | 1240 | 93253 | 31 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | SUSHANT ENTERPRISES | EV - 2114 | Ganga Collidium Shop 32 Plumbing work | Plumbing Lumpsum - SO | 1 | No. | 10000 | 100 | 0 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 100 | 31 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 10th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 15th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 6th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 11th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 14th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 3rd Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 4th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 2nd Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 13th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 16th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 23rd Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 17th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 5th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 20th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 21st Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 7th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 18th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 9th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 12th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 1st Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 24th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 19th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 22nd Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 1200 | 93247 | 29 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 1969 | B Northside 8th Floor Texture Painting | Texture Paint (M) | 316 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1100 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 25th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 24th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 19th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 25th Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 25th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 25th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.4255 | R.Ft | 94 | 100 | 266.55 | 0 | 10662 | C+S GST 18% I/P RD | 1919.16 | 12581.16 | 12581.16 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 25th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 25th Floor Lobby Flooring & cladding work | Granite Counter Support | 69.858 | R.Ft | 70 | 100 | 122.25 | 0 | 4890.06 | C+S GST 18% I/P RD | 880.22 | 5770.28 | 5770.28 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 25th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 20th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 21st Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 23rd Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 22nd Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 741 | 93246 | 29 Jan 2022 |  | R K INTERIOR | R K INTERIOR | EV - 1878 | B 25th Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 80.793 | Sq.Ft | 200 | 100 | 403.97 | 0 | 16158.6 | C+S GST 18% I/P RD | 2908.54 | 19067.14 | 19067.14 | Approved | 0 | 0 | 2505 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 22nd Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 370 | Sq.Ft | 4 | 100 | 37 | 0 | 1480 | C+S GST 18% I/P RD | 266.4 | 1746.4 | 1746.4 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 23rd Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 370 | Sq.Ft | 4 | 100 | 37 | 0 | 1480 | C+S GST 18% I/P RD | 266.4 | 1746.4 | 1746.4 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 20th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 370 | Sq.Ft | 4 | 100 | 37 | 0 | 1480 | C+S GST 18% I/P RD | 266.4 | 1746.4 | 1746.4 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 21st Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 370 | Sq.Ft | 4 | 100 | 37 | 0 | 1480 | C+S GST 18% I/P RD | 266.4 | 1746.4 | 1746.4 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 19th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 370 | Sq.Ft | 4 | 100 | 37 | 0 | 1480 | C+S GST 18% I/P RD | 266.4 | 1746.4 | 1746.4 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 18th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 370 | Sq.Ft | 4 | 100 | 37 | 0 | 1480 | C+S GST 18% I/P RD | 266.4 | 1746.4 | 1746.4 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 24th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 370 | Sq.Ft | 4 | 100 | 37 | 0 | 1480 | C+S GST 18% I/P RD | 266.4 | 1746.4 | 1746.4 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 19th Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 183 | Sq.Ft | 4 | 100 | 18.3 | 0 | 732 | C+S GST 18% I/P RD | 131.76 | 863.76 | 863.76 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 24th Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 183 | Sq.Ft | 4 | 100 | 18.3 | 0 | 732 | C+S GST 18% I/P RD | 131.76 | 863.76 | 863.76 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 21st Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 183 | Sq.Ft | 4 | 100 | 18.3 | 0 | 732 | C+S GST 18% I/P RD | 131.76 | 863.76 | 863.76 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 23rd Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 183 | Sq.Ft | 4 | 100 | 18.3 | 0 | 732 | C+S GST 18% I/P RD | 131.76 | 863.76 | 863.76 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 18th Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 183 | Sq.Ft | 4 | 100 | 18.3 | 0 | 732 | C+S GST 18% I/P RD | 131.76 | 863.76 | 863.76 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 20th Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 183 | Sq.Ft | 4 | 100 | 18.3 | 0 | 732 | C+S GST 18% I/P RD | 131.76 | 863.76 | 863.76 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 719 | 93245 | 29 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1873 | B 22nd Floor Staircase I Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 183 | Sq.Ft | 4 | 100 | 18.3 | 0 | 732 | C+S GST 18% I/P RD | 131.76 | 863.76 | 863.76 | Approved | 0 | 0 | 116 | 29 Jan 2022
GANGA DHAM TOWERS | 272 | 93244 | 29 Jan 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1874 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 74.3034 | Sq.Ft | 161.5 | 100 | 0 | 0 | 12000 | C+S GST 0% I/P RD | 0 | 12000 | 12000 | Approved | 0 | 0 | 120 | 29 Jan 2022
GANGA DHAM TOWERS | 1204 | 93236 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1785 | A-Bldg 1st Coat primer work for External Texture Paint (L) | Primer First Coat | 13949 | Sq.Ft | 2 | 100 | 697.45 | 0 | 27898 | C+S GST 18% I/P RD | 5021.64 | 32919.64 | 32919.64 | Approved | 0 | 0 | 279 | 28 Jan 2022
GANGA DHAM TOWERS | 272 | 93235 | 28 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1787 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.8947 | Sq.Ft | 152 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 273 | 28 Jan 2022
GANGA DHAM TOWERS | 272 | 93235 | 28 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1787 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.8947 | Sq.Ft | 152 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 273 | 28 Jan 2022
GANGA DHAM TOWERS | 272 | 93235 | 28 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1787 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14.9474 | Sq.Ft | 152 | 100 | 0 | 0 | 2272 | C+S GST 18% I/P RD | 408.96 | 2680.96 | 2680.96 | Approved | 0 | 0 | 273 | 28 Jan 2022
GANGA DHAM TOWERS | 272 | 93235 | 28 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1787 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 30.9598 | Sq.Ft | 161.5 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 273 | 28 Jan 2022
GANGA DHAM TOWERS | 272 | 93235 | 28 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1787 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 30.9598 | Sq.Ft | 161.5 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 273 | 28 Jan 2022
GANGA DHAM TOWERS | 272 | 93235 | 28 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1787 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 30.9598 | Sq.Ft | 161.5 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 273 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 15th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 8th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 9th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 12th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 9th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 14th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 11th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 12th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 2nd floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 23rd floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 5th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 16th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 15th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 1st floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 2nd floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 17th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 6th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 13th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 21st floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 10th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 7th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 16th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 19th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 3rd floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 14th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 18th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 4th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 20th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 5th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 11th floor External Texture Painting | Texture Paint (L) | 351.1724 | Sq.Ft | 7.25 | 100 | 63.65 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 22nd floor External Texture Painting | Texture Paint (L) | 102.8966 | Sq.Ft | 7.25 | 100 | 18.65 | 0 | 746 | C+S GST 18% I/P RD | 134.28 | 880.28 | 880.28 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 6th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 8th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 17th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 20th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 22nd floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 3rd floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 19th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 7th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 18th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 13th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 4th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 21st floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 24th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 1st floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 844 | 93234 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1786 | A South side 10th floor External Texture Painting | Scaffolding/Gondola work | 351.1429 | Sq.Ft | 3.5 | 100 | 30.73 | 0 | 1229 | C+S GST 18% I/P RD | 221.22 | 1450.22 | 1450.22 | Approved | 0 | 0 | 837 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 15th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 22nd floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 11th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 19th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 12th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 4th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 6th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 7th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 9th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 1st floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 18th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 8th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 13th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 24th floor External Texture Painting | Texture Paint (M) | 60.9655 | Sq.Ft | 7.25 | 100 | 0 | 0 | 442 | C+S GST 18% I/P RD | 79.56 | 521.56 | 521.56 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 3rd floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 14th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 21st floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 10th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 16th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 23rd floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 2nd floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 5th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 845 | 93233 | 28 Jan 2022 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1788 | A South side 17th floor External Texture Painting | Texture Paint (M) | 351.1724 | Sq.Ft | 7.25 | 100 | 0 | 0 | 2546 | C+S GST 18% I/P RD | 458.28 | 3004.28 | 3004.28 | Approved | 0 | 0 | 0 | 28 Jan 2022
GANGA DHAM TOWERS | 272 | 93203 | 25 Jan 2022 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1875 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 165.7895 | Sq.Ft | 152 | 100 | 0 | 0 | 25200 | C+S GST 0% I/P RD | 0 | 25200 | 25200 | Approved | 0 | 0 | 252 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1301 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1201 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1202 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 47.6923 | Mtrs | 19.5 | 100 | 0 | 0 | 930 | C+S GST 18% I/P RD | 167.4 | 1097.4 | 1097.4 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1403 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 35.5897 | Mtrs | 19.5 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1303 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 35.5897 | Mtrs | 19.5 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1203 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 35.5897 | Mtrs | 19.5 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1401 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 50.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 985 | C+S GST 18% I/P RD | 177.3 | 1162.3 | 1162.3 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1404 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 44.3077 | Mtrs | 19.5 | 100 | 0 | 0 | 864 | C+S GST 18% I/P RD | 155.52 | 1019.52 | 1019.52 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 304 AC Installation & Commissioning - 1 No. | AC Installation & Commissioning (L) | 6 | No. | 750 | 100 | 0 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1203 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 28.8 | Mtrs | 105 | 100 | 0 | 0 | 3024 | C+S GST 18% I/P RD | 544.32 | 3568.32 | 3568.32 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1304 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 37.2 | Mtrs | 105 | 100 | 0 | 0 | 3906 | C+S GST 18% I/P RD | 703.08 | 4609.08 | 4609.08 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1202 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 40.5048 | Mtrs | 105 | 100 | 0 | 0 | 4253 | C+S GST 18% I/P RD | 765.54 | 5018.54 | 5018.54 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1301 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1403 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 28.8 | Mtrs | 105 | 100 | 0 | 0 | 3024 | C+S GST 18% I/P RD | 544.32 | 3568.32 | 3568.32 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1203 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18 | Mtrs | 21 | 100 | 0 | 0 | 378 | C+S GST 18% I/P RD | 68.04 | 446.04 | 446.04 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1403 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18 | Mtrs | 21 | 100 | 0 | 0 | 378 | C+S GST 18% I/P RD | 68.04 | 446.04 | 446.04 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1401 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1404 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 24.7143 | Mtrs | 21 | 100 | 0 | 0 | 519 | C+S GST 18% I/P RD | 93.42 | 612.42 | 612.42 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1201 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1202 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 27.5 | Mtrs | 21 | 100 | 0 | 0 | 577.5 | C+S GST 18% I/P RD | 103.96 | 681.46 | 681.46 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1304 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 24.7143 | Mtrs | 21 | 100 | 0 | 0 | 519 | C+S GST 18% I/P RD | 93.42 | 612.42 | 612.42 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1301 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1303 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18 | Mtrs | 21 | 100 | 0 | 0 | 378 | C+S GST 18% I/P RD | 68.04 | 446.04 | 446.04 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1404 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 37.2 | Mtrs | 105 | 100 | 0 | 0 | 3906 | C+S GST 18% I/P RD | 703.08 | 4609.08 | 4609.08 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1401 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1201 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 41.1048 | Mtrs | 105 | 100 | 0 | 0 | 4316 | C+S GST 18% I/P RD | 776.88 | 5092.88 | 5092.88 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 532 | 93196 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2018 | A 1303 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 28.8 | Mtrs | 105 | 100 | 0 | 0 | 3024 | C+S GST 18% I/P RD | 544.32 | 3568.32 | 3568.32 | Approved | 0 | 0 | 990 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1202 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 47.7025 | Mtrs | 60.5 | 100 | 0 | 0 | 2886 | C+S GST 18% I/P RD | 519.48 | 3405.48 | 3405.48 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1403 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 35.6033 | Mtrs | 60.5 | 100 | 0 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1403 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 18 | Mtrs | 49 | 100 | 0 | 0 | 882 | C+S GST 18% I/P RD | 158.76 | 1040.76 | 1040.76 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1203 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 18 | Mtrs | 49 | 100 | 0 | 0 | 882 | C+S GST 18% I/P RD | 158.76 | 1040.76 | 1040.76 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1404 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 24.6939 | Mtrs | 49 | 100 | 0 | 0 | 1210 | C+S GST 18% I/P RD | 217.8 | 1427.8 | 1427.8 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1303 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 18 | Mtrs | 49 | 100 | 0 | 0 | 882 | C+S GST 18% I/P RD | 158.76 | 1040.76 | 1040.76 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1304 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 24.6939 | Mtrs | 49 | 100 | 0 | 0 | 1210 | C+S GST 18% I/P RD | 217.8 | 1427.8 | 1427.8 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1202 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 27.5 | Mtrs | 49 | 100 | 0 | 0 | 1347.5 | C+S GST 18% I/P RD | 242.56 | 1590.06 | 1590.06 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1301 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1401 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1201 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1404 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 37.2 | Mtrs | 345 | 100 | 0 | 0 | 12834 | C+S GST 18% I/P RD | 2310.12 | 15144.12 | 15144.12 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1301 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1303 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 28.8 | Mtrs | 345 | 100 | 0 | 0 | 9936 | C+S GST 18% I/P RD | 1788.48 | 11724.48 | 11724.48 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1202 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 40.5014 | Mtrs | 345 | 100 | 0 | 0 | 13973 | C+S GST 18% I/P RD | 2515.14 | 16488.14 | 16488.14 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1303 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 35.6033 | Mtrs | 60.5 | 100 | 0 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1201 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1203 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 35.6033 | Mtrs | 60.5 | 100 | 0 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1304 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 44.595 | Mtrs | 60.5 | 100 | 0 | 0 | 2698 | C+S GST 18% I/P RD | 485.64 | 3183.64 | 3183.64 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1401 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1404 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 44.3967 | Mtrs | 60.5 | 100 | 0 | 0 | 2686 | C+S GST 18% I/P RD | 483.48 | 3169.48 | 3169.48 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1301 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 50.4959 | Mtrs | 60.5 | 100 | 0 | 0 | 3055 | C+S GST 18% I/P RD | 549.9 | 3604.9 | 3604.9 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1403 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 28.8 | Mtrs | 345 | 100 | 0 | 0 | 9936 | C+S GST 18% I/P RD | 1788.48 | 11724.48 | 11724.48 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1401 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1304 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 37.2 | Mtrs | 345 | 100 | 0 | 0 | 12834 | C+S GST 18% I/P RD | 2310.12 | 15144.12 | 15144.12 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1201 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.1014 | Mtrs | 345 | 100 | 0 | 0 | 14180 | C+S GST 18% I/P RD | 2552.4 | 16732.4 | 16732.4 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 530 | 93195 | 25 Jan 2022 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 2196 | A 1203 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 28.8 | Mtrs | 345 | 100 | 0 | 0 | 9936 | C+S GST 18% I/P RD | 1788.48 | 11724.48 | 11724.48 | Approved | 0 | 0 | 2909 | 25 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Expenses-BC | 1 | No. | 5825 | 100 | 0 | 0 | 5825 | CGST 0% URD I/P | 0 | 5825 | 5825 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.72 | 0 | 0 | 30108 | CGST 0% URD I/P | 0 | 30108 | 30108 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1052 | 93190 | 24 Jan 2022 |  | AJINKYA DEEPAK YADAV | AJINKYA DEEPAK YADAV | EV - 1766 | Legal Consultancy | Legal Consultancy | 13 | Month | 30000 | 7.69 | 0 | 0 | 29991 | CGST 0% URD I/P | 0 | 29991 | 29991 | Approved | 0 | 0 | 39583 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 13th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 2nd Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 4th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 5th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 16th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 9th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 10th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 20th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 18th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 11th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 1st Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 15th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 12th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 14th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 8th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 22nd Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 3rd Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 21st Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 19th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 17th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 24th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 6th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 7th Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 23rd Floor Texture Painting | Texture Paint (L) | 316 | Sq.Ft | 7.25 | 100 | 57.28 | 0 | 2291 | C+S GST 18% I/P RD | 412.38 | 2703.38 | 2703.38 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 6th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 16th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 23rd Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 14th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 10th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 9th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 8th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 7th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 11th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 12th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 24th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 1st Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 3rd Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 4th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 18th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 20th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 21st Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 22nd Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 15th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 13th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 19th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 17th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 2nd Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 1199 | 93189 | 24 Jan 2022 |  | GODAVARI PAINT PVT LTD | GODAVARI PAINT PVT LTD | EV - 2019 | B Northside 5th Floor Texture Painting | Scaffolding/Gondola work | 316 | Sq.Ft | 3.5 | 100 | 27.65 | 0 | 1106 | C+S GST 18% I/P RD | 199.08 | 1305.08 | 1305.08 | Approved | 0 | 0 | 1631 | 24 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20.2538 | Sq.Ft | 130 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20.2538 | Sq.Ft | 130 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20.2538 | Sq.Ft | 130 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20.2538 | Sq.Ft | 130 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20.2538 | Sq.Ft | 130 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 17.5533 | Sq.Ft | 150 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 17.5533 | Sq.Ft | 150 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 17.5533 | Sq.Ft | 150 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 17.5533 | Sq.Ft | 150 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 18.8071 | Sq.Ft | 140 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 18.8071 | Sq.Ft | 140 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 18.8071 | Sq.Ft | 140 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 18.8071 | Sq.Ft | 140 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 9th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 6th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 6th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 8th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 16.9871 | Sq.Ft | 155 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 16.9871 | Sq.Ft | 155 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 16.9871 | Sq.Ft | 155 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 7th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 8th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 7th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 372 | 93174 | 22 Jan 2022 |  | B & B ENTERPRISES | GODAVARI PAINT PVT LTD | EV - 1966 | B Bldg 9th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.9417 | Sq.Ft | 120 | 100 | 0 | 0 | 2633 | IGST 18% I/P RD | 473.94 | 3106.94 | 3106.94 | Approved | 0 | 0 | 1264 | 22 Jan 2022
GANGA DHAM TOWERS | 1234 | 93160 | 21 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1853 | A 2304 NOC | Concrete Cutting Work | 35.421 | R.Ft | 525 | 100 | 0 | 0 | 18596 | C+S GST 18% I/P RD | 3347.28 | 21943.28 | 21943.28 | Approved | 0 | 0 | 372 | 21 Jan 2022
GANGA DHAM TOWERS | 1002 | 93159 | 21 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1854 | A 2101 NOC | Concrete Cutting Work | 61.99 | R.Ft | 525 | 100 | 813.62 | 0 | 32544.75 | C+S GST 18% I/P RD | 5858.06 | 38402.81 | 38402.81 | Approved | 0 | 0 | 723 | 21 Jan 2022
GANGA DHAM TOWERS | 1002 | 93159 | 21 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1854 | A 2101 NOC | Concrete wall Crushing work | 0.5 | Cu.Mtrs | 7200 | 100 | 90 | 0 | 3600 | C+S GST 18% I/P RD | 648 | 4248 | 4248 | Approved | 0 | 0 | 723 | 21 Jan 2022
GANGA DHAM TOWERS | 1250 | 93158 | 21 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1855 | A 1103 NOC | Concrete Cutting Work | 98.6495 | R.Ft | 525 | 100 | 1294.77 | 0 | 51791 | C+S GST 18% I/P RD | 9322.38 | 61113.38 | 61113.38 | Approved | 0 | 0 | 1199 | 21 Jan 2022
GANGA DHAM TOWERS | 1250 | 93158 | 21 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1855 | A 1103 NOC | Concrete wall Crushing work | 0.28 | Cu.Mtrs | 7200 | 100 | 50.4 | 0 | 2016 | C+S GST 18% I/P RD | 362.88 | 2378.88 | 2378.88 | Approved | 0 | 0 | 1199 | 21 Jan 2022
GANGA DHAM TOWERS | 1250 | 93158 | 21 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1855 | A 1103 NOC | Concrete wall Crushing work | 0.85 | Cu.Mtrs | 7200 | 100 | 153 | 0 | 6120 | C+S GST 18% I/P RD | 1101.6 | 7221.6 | 7221.6 | Approved | 0 | 0 | 1199 | 21 Jan 2022
GANGA DHAM TOWERS | 1188 | 93151 | 20 Jan 2022 |  | CLASSIC MARBLES | R.M.Marbles | EV - 2014 | Ganga Collidium Shop 32 Tiling Work | Dado Fixing | 284.12 | Sq.Ft | 23 | 100 | 163.37 | 0 | 6534.76 | C+S GST 18% I/P RD | 1176.26 | 7711.02 | 7711.02 | Approved | 0 | 21187 | 228 | 20 Jan 2022
GANGA DHAM TOWERS | 1188 | 93151 | 20 Jan 2022 |  | CLASSIC MARBLES | R.M.Marbles | EV - 2014 | Ganga Collidium Shop 32 Tiling Work | Granite Door Frame -BRE - | 35 | R.Ft | 50 | 100 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 21187 | 228 | 20 Jan 2022
GANGA DHAM TOWERS | 1188 | 93151 | 20 Jan 2022 |  | CLASSIC MARBLES | R.M.Marbles | EV - 2014 | Ganga Collidium Shop 32 Tiling Work | Vitrified Flooring - MKT - Sq.Ft | 300.78 | Sq.Ft | 22 | 100 | 165.43 | 0 | 6617.16 | C+S GST 18% I/P RD | 1191.08 | 7808.24 | 7808.24 | Approved | 0 | 21187 | 228 | 20 Jan 2022
GANGA DHAM TOWERS | 1188 | 93151 | 20 Jan 2022 |  | CLASSIC MARBLES | R.M.Marbles | EV - 2014 | Ganga Collidium Shop 32 Tiling Work | Granite Tappa/Riser BC | 47 | R.Ft | 90 | 100 | 105.75 | 0 | 4230 | C+S GST 18% I/P RD | 761.4 | 4991.4 | 4991.4 | Approved | 0 | 21187 | 228 | 20 Jan 2022
GANGA DHAM TOWERS | 1188 | 93151 | 20 Jan 2022 |  | CLASSIC MARBLES | R.M.Marbles | EV - 2014 | Ganga Collidium Shop 32 Tiling Work | Granite Kitchen Platform (L)- SOS | 6 | R.Ft | 450 | 100 | 67.5 | 0 | 2700 | C+S GST 18% I/P RD | 486 | 3186 | 3186 | Approved | 0 | 21187 | 228 | 20 Jan 2022
GANGA DHAM TOWERS | 1188 | 93151 | 20 Jan 2022 |  | CLASSIC MARBLES | R.M.Marbles | EV - 2014 | Ganga Collidium Shop 32 Tiling Work | Vitrified Skirting - MKT - R.Ft | 43 | R.Ft | 22 | 100 | 23.65 | 0 | 946 | C+S GST 18% I/P RD | 170.28 | 1116.28 | 1116.28 | Approved | 0 | 21187 | 228 | 20 Jan 2022
GANGA DHAM TOWERS | 1219 | 93150 | 20 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2013 | A-Bldg Rebaring Work in Flat-1,2,3,4 | Rebaring work 8mm dia.- DTR | 1283 | No. | 80 | 100 | 2566 | 0 | 102640 | C+S GST 18% I/P RD | 18475.2 | 121115.2 | 121115.2 | Approved | 0 | 200000 | 7224 | 20 Jan 2022
GANGA DHAM TOWERS | 1219 | 93150 | 20 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2013 | A-Bldg Rebaring Work in Flat-1,2,3,4 | Rebaring work 8mm dia.- DTR | 846 | No. | 80 | 100 | 1692 | 0 | 67680 | C+S GST 18% I/P RD | 12182.4 | 79862.4 | 79862.4 | Approved | 0 | 200000 | 7224 | 20 Jan 2022
GANGA DHAM TOWERS | 1219 | 93150 | 20 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2013 | A-Bldg Rebaring Work in Flat-1,2,3,4 | Rebaring work 8mm dia.- DTR | 826 | No. | 80 | 100 | 1652 | 0 | 66080 | C+S GST 18% I/P RD | 11894.4 | 77974.4 | 77974.4 | Approved | 0 | 200000 | 7224 | 20 Jan 2022
GANGA DHAM TOWERS | 1219 | 93150 | 20 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2013 | A-Bldg Rebaring Work in Flat-1,2,3,4 | Rebaring work 8mm dia.- DTR | 1560 | No. | 80 | 100 | 3120 | 0 | 124800 | C+S GST 18% I/P RD | 22464 | 147264 | 147264 | Approved | 0 | 200000 | 7224 | 20 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Granite Kitchen Otta - | Granite Kitchen Otta BC | 13.581 | R.Ft | 350 | 100 | 118.83 | 0 | 4753.35 | C+S GST 18% I/P RD | 855.6 | 5608.95 | 5608.95 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Granite Kitchen Otta - | Granite Kitchen Otta BC | 13.581 | R.Ft | 350 | 100 | 118.83 | 0 | 4753.35 | C+S GST 18% I/P RD | 855.6 | 5608.95 | 5608.95 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2101 Living,Dining,Ent.Lobby | Italian Marble Flooring - BCo | 1150.67 | Sq.Ft | 60 | 100 | 1726.01 | 0 | 69040.2 | C+S GST 18% I/P RD | 12427.24 | 81467.44 | 81467.44 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2101 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 60 | 100 | 364.5 | 0 | 14580 | C+S GST 18% I/P RD | 2624.4 | 17204.4 | 17204.4 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2101 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 320.98 | Sq.Ft | 60 | 100 | 481.47 | 0 | 19258.8 | C+S GST 18% I/P RD | 3466.58 | 22725.38 | 22725.38 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 602 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 88.284 | R.Ft | 45 | 100 | 99.32 | 0 | 3972.78 | C+S GST 18% I/P RD | 715.1 | 4687.88 | 4687.88 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 602 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 50.526 | R.Ft | 45 | 100 | 56.84 | 0 | 2273.67 | C+S GST 18% I/P RD | 409.26 | 2682.93 | 2682.93 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 102 Parents Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 39.963 | R.Ft | 45 | 100 | 44.96 | 0 | 1798.34 | C+S GST 18% I/P RD | 323.7 | 2122.04 | 2122.04 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 102 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 50.526 | R.Ft | 45 | 100 | 56.84 | 0 | 2273.67 | C+S GST 18% I/P RD | 409.26 | 2682.93 | 2682.93 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 401 Kitchen Dado | Dado BC | 47.36 | Sq.Ft | 14 | 100 | 16.58 | 0 | 663.04 | C+S GST 18% I/P RD | 119.34 | 782.38 | 782.38 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2102 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 88.284 | R.Ft | 60 | 100 | 132.43 | 0 | 5297.04 | C+S GST 18% I/P RD | 953.46 | 6250.5 | 6250.5 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2101 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 55.614 | R.Ft | 60 | 100 | 83.42 | 0 | 3336.84 | C+S GST 18% I/P RD | 600.64 | 3937.48 | 3937.48 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2102 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 39.963 | R.Ft | 60 | 100 | 59.94 | 0 | 2397.78 | C+S GST 18% I/P RD | 431.6 | 2829.38 | 2829.38 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2101 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 48.461 | R.Ft | 60 | 100 | 72.69 | 0 | 2907.66 | C+S GST 18% I/P RD | 523.38 | 3431.04 | 3431.04 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2102 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 50.526 | R.Ft | 60 | 100 | 75.79 | 0 | 3031.56 | C+S GST 18% I/P RD | 545.68 | 3577.24 | 3577.24 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1902 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 50.526 | R.Ft | 60 | 100 | 75.79 | 0 | 3031.56 | C+S GST 18% I/P RD | 545.68 | 3577.24 | 3577.24 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1902 Parents Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 39.963 | R.Ft | 60 | 100 | 59.94 | 0 | 2397.78 | C+S GST 18% I/P RD | 431.6 | 2829.38 | 2829.38 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1902 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 88.284 | R.Ft | 60 | 100 | 132.43 | 0 | 5297.04 | C+S GST 18% I/P RD | 953.46 | 6250.5 | 6250.5 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 2101 Living,Dining,Ent.Lobby | Italian marble Skirting - BCo | 149.009 | R.Ft | 60 | 100 | 223.51 | 0 | 8940.54 | C+S GST 18% I/P RD | 1609.3 | 10549.84 | 10549.84 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 102 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 70 | R.Ft | 45 | 100 | 78.75 | 0 | 3150 | C+S GST 18% I/P RD | 567 | 3717 | 3717 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 602 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 39.963 | R.Ft | 45 | 100 | 44.96 | 0 | 1798.34 | C+S GST 18% I/P RD | 323.7 | 2122.04 | 2122.04 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Guest Toilet Dado - 1 No. | Dado BC | 168.732 | Sq.Ft | 22 | 100 | 92.8 | 0 | 3712.1 | C+S GST 18% I/P RD | 668.18 | 4380.28 | 4380.28 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Master Toilet Dado - 1 No. | Dado BC | 111.856 | Sq.Ft | 22 | 100 | 61.52 | 0 | 2460.83 | C+S GST 18% I/P RD | 442.94 | 2903.77 | 2903.77 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Children Toilet 1 Dado - 1 No. | Dado BC | 171.153 | Sq.Ft | 22 | 100 | 94.13 | 0 | 3765.37 | C+S GST 18% I/P RD | 677.76 | 4443.13 | 4443.13 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 StaffToilet Dado | Dado BC | 115.889 | Sq.Ft | 21 | 100 | 60.84 | 0 | 2433.67 | C+S GST 18% I/P RD | 438.06 | 2871.73 | 2871.73 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Children Toilet 2 Dado | Dado BC | 144.653 | Sq.Ft | 22 | 100 | 79.56 | 0 | 3182.37 | C+S GST 18% I/P RD | 572.82 | 3755.19 | 3755.19 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Powder Toilet Dado | Dado BC | 90.7885 | Sq.Ft | 22 | 100 | 49.93 | 0 | 1997.35 | C+S GST 18% I/P RD | 359.52 | 2356.87 | 2356.87 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 StaffToilet Dado - 1 No. | Dado BC | 122.706 | Sq.Ft | 21 | 100 | 64.42 | 0 | 2576.83 | C+S GST 18% I/P RD | 463.82 | 3040.65 | 3040.65 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Parents Toilet Dado - 1 No. | Dado BC | 132.867 | Sq.Ft | 22 | 100 | 73.08 | 0 | 2923.07 | C+S GST 18% I/P RD | 526.16 | 3449.23 | 3449.23 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Children Toilet 2 Dado - 1 No. | Dado BC | 153.162 | Sq.Ft | 22 | 100 | 84.24 | 0 | 3369.56 | C+S GST 18% I/P RD | 606.52 | 3976.08 | 3976.08 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Kitchen Dado | Dado BC | 47.36 | Sq.Ft | 22 | 100 | 26.05 | 0 | 1041.92 | C+S GST 18% I/P RD | 187.54 | 1229.46 | 1229.46 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Kitchen Dado - 1 No. | Dado BC | 47.36 | Sq.Ft | 22 | 100 | 26.05 | 0 | 1041.92 | C+S GST 18% I/P RD | 187.54 | 1229.46 | 1229.46 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Dry Balcony Dado | Dado BC | 81.378 | Sq.Ft | 22 | 100 | 44.76 | 0 | 1790.32 | C+S GST 18% I/P RD | 322.26 | 2112.58 | 2112.58 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Master Toilet Dado | Dado BC | 118.847 | Sq.Ft | 22 | 100 | 65.37 | 0 | 2614.63 | C+S GST 18% I/P RD | 470.64 | 3085.27 | 3085.27 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Parents Toilet Dado | Dado BC | 125.4855 | Sq.Ft | 22 | 100 | 69.02 | 0 | 2760.68 | C+S GST 18% I/P RD | 496.92 | 3257.6 | 3257.6 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Guest Toilet Dado | Dado BC | 159.358 | Sq.Ft | 22 | 100 | 87.65 | 0 | 3505.88 | C+S GST 18% I/P RD | 631.06 | 4136.94 | 4136.94 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Children Toilet 1 Dado | Dado BC | 171.153 | Sq.Ft | 22 | 100 | 94.13 | 0 | 3765.37 | C+S GST 18% I/P RD | 677.76 | 4443.13 | 4443.13 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Powder Toilet Dado | Dado BC | 96.129 | Sq.Ft | 22 | 100 | 52.87 | 0 | 2114.84 | C+S GST 18% I/P RD | 380.68 | 2495.52 | 2495.52 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Dry Balcony Dado - 1 No. | Dado BC | 81.378 | Sq.Ft | 22 | 100 | 44.76 | 0 | 1790.32 | C+S GST 18% I/P RD | 322.26 | 2112.58 | 2112.58 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 StaffToilet Dado | Dado BC | 115.889 | Sq.Ft | 17 | 100 | 49.25 | 0 | 1970.11 | C+S GST 18% I/P RD | 354.62 | 2324.73 | 2324.73 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 51.057 | Sq.Ft | 21 | 100 | 26.8 | 0 | 1072.2 | C+S GST 18% I/P RD | 193 | 1265.2 | 1265.2 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Children Toilet 1 Vitrified Flooring | Vitrified Flooring -BC | 52.506 | Sq.Ft | 21 | 100 | 27.57 | 0 | 1102.63 | C+S GST 18% I/P RD | 198.48 | 1301.11 | 1301.11 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 21 | 100 | 22.89 | 0 | 915.52 | C+S GST 18% I/P RD | 164.8 | 1080.32 | 1080.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.596 | Sq.Ft | 21 | 100 | 22.89 | 0 | 915.52 | C+S GST 18% I/P RD | 164.8 | 1080.32 | 1080.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Children Toilet 2 Vitrified Flooring | Vitrified Flooring -BC | 41.175 | Sq.Ft | 21 | 100 | 21.62 | 0 | 864.68 | C+S GST 18% I/P RD | 155.64 | 1020.32 | 1020.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.705 | Sq.Ft | 21 | 100 | 12.97 | 0 | 518.81 | C+S GST 18% I/P RD | 93.38 | 612.19 | 612.19 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 51.057 | Sq.Ft | 21 | 100 | 26.8 | 0 | 1072.2 | C+S GST 18% I/P RD | 193 | 1265.2 | 1265.2 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 73.431 | Sq.Ft | 21 | 100 | 38.55 | 0 | 1542.05 | C+S GST 18% I/P RD | 277.56 | 1819.61 | 1819.61 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 50.283 | Sq.Ft | 21 | 100 | 26.4 | 0 | 1055.94 | C+S GST 18% I/P RD | 190.06 | 1246 | 1246 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 73.431 | Sq.Ft | 21 | 100 | 38.55 | 0 | 1542.05 | C+S GST 18% I/P RD | 277.56 | 1819.61 | 1819.61 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 72.27 | Sq.Ft | 21 | 100 | 37.94 | 0 | 1517.67 | C+S GST 18% I/P RD | 273.18 | 1790.85 | 1790.85 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Children Toile 1 Vitrified Flooring | Vitrified Flooring -BC | 52.506 | Sq.Ft | 21 | 100 | 27.57 | 0 | 1102.63 | C+S GST 18% I/P RD | 198.48 | 1301.11 | 1301.11 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Children Toile 2 Vitrified Flooring | Vitrified Flooring -BC | 41.175 | Sq.Ft | 21 | 100 | 21.62 | 0 | 864.68 | C+S GST 18% I/P RD | 155.64 | 1020.32 | 1020.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.705 | Sq.Ft | 21 | 100 | 12.97 | 0 | 518.81 | C+S GST 18% I/P RD | 93.38 | 612.19 | 612.19 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 59 | Sq.Ft | 21 | 100 | 30.98 | 0 | 1239 | C+S GST 18% I/P RD | 223.02 | 1462.02 | 1462.02 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 50.283 | Sq.Ft | 21 | 100 | 26.4 | 0 | 1055.94 | C+S GST 18% I/P RD | 190.06 | 1246 | 1246 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Powder Toilet Dado | Dado BC | 35.604 | Sq.Ft | 24 | 100 | 21.36 | 0 | 854.5 | C+S GST 18% I/P RD | 153.82 | 1008.32 | 1008.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Children Toilet 2 Dado | Dado BC | 24.174 | Sq.Ft | 24 | 100 | 14.5 | 0 | 580.18 | C+S GST 18% I/P RD | 104.44 | 684.62 | 684.62 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 801 Kitchen Dado | Dado BC | 47.36 | Sq.Ft | 18 | 100 | 21.31 | 0 | 852.48 | C+S GST 18% I/P RD | 153.44 | 1005.92 | 1005.92 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1702 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 50.526 | R.Ft | 55 | 100 | 69.47 | 0 | 2778.93 | C+S GST 18% I/P RD | 500.2 | 3279.13 | 3279.13 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1302 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 88.284 | R.Ft | 55 | 100 | 121.39 | 0 | 4855.62 | C+S GST 18% I/P RD | 874.02 | 5729.64 | 5729.64 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1302 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 50.526 | R.Ft | 55 | 100 | 69.47 | 0 | 2778.93 | C+S GST 18% I/P RD | 500.2 | 3279.13 | 3279.13 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1302 Parents Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 39.963 | R.Ft | 55 | 100 | 54.95 | 0 | 2197.97 | C+S GST 18% I/P RD | 395.64 | 2593.61 | 2593.61 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1702 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 39.963 | R.Ft | 55 | 100 | 54.95 | 0 | 2197.97 | C+S GST 18% I/P RD | 395.64 | 2593.61 | 2593.61 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1702 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 88.284 | R.Ft | 55 | 100 | 121.39 | 0 | 4855.62 | C+S GST 18% I/P RD | 874.02 | 5729.64 | 5729.64 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 35.371 | R.Ft | 50 | 100 | 44.21 | 0 | 1768.55 | C+S GST 18% I/P RD | 318.34 | 2086.89 | 2086.89 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1002 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 88.284 | R.Ft | 50 | 100 | 110.36 | 0 | 4414.2 | C+S GST 18% I/P RD | 794.56 | 5208.76 | 5208.76 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1002 Parents Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 39.963 | R.Ft | 50 | 100 | 49.95 | 0 | 1998.15 | C+S GST 18% I/P RD | 359.66 | 2357.81 | 2357.81 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1002 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 50.526 | R.Ft | 50 | 100 | 63.16 | 0 | 2526.3 | C+S GST 18% I/P RD | 454.74 | 2981.04 | 2981.04 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1102 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 88.284 | R.Ft | 50 | 100 | 110.36 | 0 | 4414.2 | C+S GST 18% I/P RD | 794.56 | 5208.76 | 5208.76 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 161.154 | R.Ft | 50 | 100 | 201.44 | 0 | 8057.7 | C+S GST 18% I/P RD | 1450.38 | 9508.08 | 9508.08 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1102 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 50.526 | R.Ft | 50 | 100 | 63.16 | 0 | 2526.3 | C+S GST 18% I/P RD | 454.74 | 2981.04 | 2981.04 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 64.421 | R.Ft | 50 | 100 | 80.53 | 0 | 3221.05 | C+S GST 18% I/P RD | 579.78 | 3800.83 | 3800.83 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1102 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 39.963 | R.Ft | 50 | 100 | 49.95 | 0 | 1998.15 | C+S GST 18% I/P RD | 359.66 | 2357.81 | 2357.81 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Children Toilet 1 Dado | Dado BC | 36.792 | Sq.Ft | 24 | 100 | 22.08 | 0 | 883.01 | C+S GST 18% I/P RD | 158.94 | 1041.95 | 1041.95 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Parents Toilet Dado - 1 No. | Dado BC | 75.69 | Sq.Ft | 24 | 100 | 45.41 | 0 | 1816.56 | C+S GST 18% I/P RD | 326.98 | 2143.54 | 2143.54 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Children Toilet 2 Dado - 1 No. | Dado BC | 24.174 | Sq.Ft | 24 | 100 | 14.5 | 0 | 580.18 | C+S GST 18% I/P RD | 104.44 | 684.62 | 684.62 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Guest Toilet Dado - 1 No. | Dado BC | 39.56 | Sq.Ft | 24 | 100 | 23.74 | 0 | 949.44 | C+S GST 18% I/P RD | 170.9 | 1120.34 | 1120.34 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Parents Toilet Dado | Dado BC | 68.121 | Sq.Ft | 24 | 100 | 40.87 | 0 | 1634.9 | C+S GST 18% I/P RD | 294.28 | 1929.18 | 1929.18 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Children Toilet 1 Dado - 1 No. | Dado BC | 36.792 | Sq.Ft | 24 | 100 | 22.08 | 0 | 883.01 | C+S GST 18% I/P RD | 158.94 | 1041.95 | 1041.95 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Master Toilet Dado | Dado BC | 85.446 | Sq.Ft | 24 | 100 | 51.27 | 0 | 2050.7 | C+S GST 18% I/P RD | 369.12 | 2419.82 | 2419.82 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Guest Toilet Dado | Dado BC | 35.604 | Sq.Ft | 24 | 100 | 21.36 | 0 | 854.5 | C+S GST 18% I/P RD | 153.82 | 1008.32 | 1008.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1401 Master Toilet Dado - 1 No. | Dado BC | 94.94 | Sq.Ft | 24 | 100 | 56.96 | 0 | 2278.56 | C+S GST 18% I/P RD | 410.14 | 2688.7 | 2688.7 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 1301 Powder Toilet Dado | Dado BC | 35.604 | Sq.Ft | 24 | 100 | 21.36 | 0 | 854.5 | C+S GST 18% I/P RD | 153.82 | 1008.32 | 1008.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Children Toilet 1 Dado | Dado BC | 161.6445 | Sq.Ft | 18 | 100 | 72.74 | 0 | 2909.6 | C+S GST 18% I/P RD | 523.72 | 3433.32 | 3433.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 801 Granite Kitchen Otta | Granite Kitchen Otta BC | 13.581 | R.Ft | 325 | 100 | 110.35 | 0 | 4413.83 | C+S GST 18% I/P RD | 794.48 | 5208.31 | 5208.31 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 901Granite Kitchen Otta - | Granite Kitchen Otta BC | 13.581 | R.Ft | 325 | 100 | 110.35 | 0 | 4413.83 | C+S GST 18% I/P RD | 794.48 | 5208.31 | 5208.31 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 401 Granite Kitchen Otta - | Granite Kitchen Otta BC | 13.581 | R.Ft | 300 | 100 | 101.86 | 0 | 4074.3 | C+S GST 18% I/P RD | 733.38 | 4807.68 | 4807.68 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Children Toilet 2 Dado | Dado BC | 144.653 | Sq.Ft | 18 | 100 | 65.09 | 0 | 2603.75 | C+S GST 18% I/P RD | 468.68 | 3072.43 | 3072.43 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 901 Kitchen Dado | Dado BC | 47.36 | Sq.Ft | 18 | 100 | 21.31 | 0 | 852.48 | C+S GST 18% I/P RD | 153.44 | 1005.92 | 1005.92 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Parents Toilet Dado | Dado BC | 125.4855 | Sq.Ft | 18 | 100 | 56.47 | 0 | 2258.74 | C+S GST 18% I/P RD | 406.58 | 2665.32 | 2665.32 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Children Toilet 1 Dado | Dado BC | 36.792 | Sq.Ft | 20 | 100 | 18.4 | 0 | 735.84 | C+S GST 18% I/P RD | 132.46 | 868.3 | 868.3 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Parents Toilet Dado | Dado BC | 68.121 | Sq.Ft | 20 | 100 | 34.06 | 0 | 1362.42 | C+S GST 18% I/P RD | 245.24 | 1607.66 | 1607.66 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 701 Children Toilet 2 Dado | Dado BC | 24.174 | Sq.Ft | 20 | 100 | 12.09 | 0 | 483.48 | C+S GST 18% I/P RD | 87.02 | 570.5 | 570.5 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 758 | 93127 | 17 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1811 | B 601 Living Terrace Vitr.Flooring | Vitrified Flooring -BC | 193.2 | Sq.Ft | 15 | 100 | 72.45 | 0 | 2898 | C+S GST 18% I/P RD | 521.64 | 3419.64 | 3419.64 | Approved | 0 | 0 | 3233 | 17 Jan 2022
GANGA DHAM TOWERS | 793 | 93126 | 17 Jan 2022 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1891 | D 702 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3060 | 100 | 76.5 | 0 | 3060 | CGST 0% URD I/P | 0 | 3060 | 3060 | Approved | 0 | 0 | 153 | 17 Jan 2022
GANGA DHAM TOWERS | 793 | 93126 | 17 Jan 2022 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1891 | D 704 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3060 | 100 | 76.5 | 0 | 3060 | CGST 0% URD I/P | 0 | 3060 | 3060 | Approved | 0 | 0 | 153 | 17 Jan 2022
GANGA DHAM TOWERS | 793 | 93126 | 17 Jan 2022 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1891 | D 602 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3060 | 100 | 76.5 | 0 | 3060 | CGST 0% URD I/P | 0 | 3060 | 3060 | Approved | 0 | 0 | 153 | 17 Jan 2022
GANGA DHAM TOWERS | 793 | 93126 | 17 Jan 2022 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1891 | D 604 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3060 | 100 | 76.5 | 0 | 3060 | CGST 0% URD I/P | 0 | 3060 | 3060 | Approved | 0 | 0 | 153 | 17 Jan 2022
GANGA DHAM TOWERS | 793 | 93126 | 17 Jan 2022 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1891 | D 603 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3060 | 100 | 76.5 | 0 | 3060 | CGST 0% URD I/P | 0 | 3060 | 3060 | Approved | 0 | 0 | 153 | 17 Jan 2022
GANGA DHAM TOWERS | 728 | 93117 | 14 Jan 2022 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2002 | DA Development Deep Cleaning work | Deep Cleaning work | 4000 | Sq.Ft | 4 | 100 | 400 | 0 | 16000 | C+S GST 18% I/P RD | 2880 | 18880 | 18880 | Approved | 0 | 0 | 160 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 505 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 345 | Sq.Ft | 9 | 100 | 77.63 | 0 | 3105 | CGST 0% URD I/P | 0 | 3105 | 3105 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 404 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 237 | Sq.Ft | 9 | 100 | 53.33 | 0 | 2133 | CGST 0% URD I/P | 0 | 2133 | 2133 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 501 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 175 | Sq.Ft | 9 | 100 | 39.38 | 0 | 1575 | CGST 0% URD I/P | 0 | 1575 | 1575 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 403 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 119 | Sq.Ft | 9 | 100 | 26.78 | 0 | 1071 | CGST 0% URD I/P | 0 | 1071 | 1071 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 503 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 119 | Sq.Ft | 9 | 100 | 26.78 | 0 | 1071 | CGST 0% URD I/P | 0 | 1071 | 1071 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 203 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 237 | Sq.Ft | 9 | 100 | 53.33 | 0 | 2133 | CGST 0% URD I/P | 0 | 2133 | 2133 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 501 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 300 | Sq.Ft | 4 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 203 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325 | Sq.Ft | 4 | 100 | 32.5 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 505 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 300 | Sq.Ft | 4 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 502 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 200 | Sq.Ft | 4 | 100 | 20 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 698 | 93116 | 14 Jan 2022 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1809 | D 303 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 119 | Sq.Ft | 9 | 100 | 26.78 | 0 | 1071 | CGST 0% URD I/P | 0 | 1071 | 1071 | Approved | 0 | 0 | 167 | 14 Jan 2022
GANGA DHAM TOWERS | 793 | 93115 | 14 Jan 2022 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1908 | D 301 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 4500 | 100 | 112.5 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 60 | 14 Jan 2022
GANGA DHAM TOWERS | 793 | 93115 | 14 Jan 2022 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1908 | D 303 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.5 | Per Flat | 3060 | 100 | 38.25 | 0 | 1530 | CGST 0% URD I/P | 0 | 1530 | 1530 | Approved | 0 | 0 | 60 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 304 Chemical Waterproofing | Chemical Waterproofing (L) | 69.67 | Sq.Ft | 4 | 100 | 27.87 | 0 | 278.68 | CGST 0% URD I/P | 0 | 278.68 | 278.68 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 205 Chemical Waterproofing | Chemical Waterproofing (L) | 103 | Sq.Ft | 4 | 100 | 41.2 | 0 | 412 | CGST 0% URD I/P | 0 | 412 | 412 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 501 Chemical Waterproofing | Chemical Waterproofing (L) | 103 | Sq.Ft | 4 | 100 | 41.2 | 0 | 412 | CGST 0% URD I/P | 0 | 412 | 412 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 402 Chemical Waterproofing | Chemical Waterproofing (L) | 96.5 | Sq.Ft | 4 | 100 | 38.6 | 0 | 386 | CGST 0% URD I/P | 0 | 386 | 386 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 302 Chemical Waterproofing | Chemical Waterproofing (L) | 99 | Sq.Ft | 4 | 100 | 39.6 | 0 | 396 | CGST 0% URD I/P | 0 | 396 | 396 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 204 Chemical Waterproofing | Chemical Waterproofing (L) | 69 | Sq.Ft | 4 | 100 | 27.6 | 0 | 276 | CGST 0% URD I/P | 0 | 276 | 276 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D503 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D203 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D404 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D303 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D204 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D602 Chemical Grouting | Chemical Grouting.- BC | 356 | Sq.Ft | 1 | 100 | 35.6 | 0 | 356 | CGST 0% URD I/P | 0 | 356 | 356 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D403 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D304 Chemical Grouting | Chemical Grouting.- BC | 347 | Sq.Ft | 1 | 100 | 34.7 | 0 | 347 | CGST 0% URD I/P | 0 | 347 | 347 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 505 IPS Waterproofing | IPS W/P | 103 | Sq.Ft | 11 | 100 | 113.3 | 0 | 1133 | CGST 0% URD I/P | 0 | 1133 | 1133 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 504 IPS Waterproofing | IPS W/P | 69.6364 | Sq.Ft | 11 | 100 | 76.6 | 0 | 766 | CGST 0% URD I/P | 0 | 766 | 766 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D 502 IPS Waterproofing | IPS W/P | 99.4545 | Sq.Ft | 11 | 100 | 109.4 | 0 | 1094 | CGST 0% URD I/P | 0 | 1094 | 1094 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 653 | 93114 | 14 Jan 2022 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1816 | D601 Chemical Grouting | Chemical Grouting.- BC | 481 | Sq.Ft | 1 | 100 | 48.1 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 84 | 14 Jan 2022
GANGA DHAM TOWERS | 456 | 93106 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1857 | A Bldg External Plumbing Duct GI & PVC (L) | Duct Line | 10 | Flat | 2700 | 100 | 675 | 0 | 27000 | C+S GST 18% I/P RD | 4860 | 31860 | 31860 | Approved | 0 | 0 | 405 | 13 Jan 2022
GANGA DHAM TOWERS | 456 | 93106 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1857 | A Bldg External Plumbing Rainwater Line (L) | Rainwater Line | 5 | Flat | 2700 | 100 | 337.5 | 0 | 13500 | C+S GST 18% I/P RD | 2430 | 15930 | 15930 | Approved | 0 | 0 | 405 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 1803 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P URD | 252 | 1652 | 1652 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 1802 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 1801 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 1804 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1400 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 1901 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 1903 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 2001 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 1904 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 2003 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 2004 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 2002 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 455 | 93105 | 13 Jan 2022 |  | SHWETA SURESH GOVALKAR | R R TANGADE | EV - 1856 | A Bldg Flat No. 1902 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1 | No. | 1650 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 188 | 13 Jan 2022
GANGA DHAM TOWERS | 1079 | 93094 | 12 Jan 2022 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 2261 | A 32nd Slab Pumping charges for RMC | Pumping Charges-BC | 216.5579 | Cu.Mtrs | 190 | 100 | 0 | 0 | 41146 | C+S GST 18% I/P RD | 7406.28 | 48552.28 | 48552.28 | Approved | 0 | 0 | 823 | 12 Jan 2022
GANGA DHAM TOWERS | 1226 | 93078 | 11 Jan 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2059 | Lt Substation Ground Floor BBM/ Plaster (L) | Blockwork 8" - BC | 479.2667 | Sq.Ft | 15 | 100 | 179.73 | 0 | 7189 | CGST 0% URD I/P | 0 | 7189 | 7189 | Approved | 0 | 0 | 191 | 11 Jan 2022
GANGA DHAM TOWERS | 1226 | 93078 | 11 Jan 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2059 | Lt Substation Ground Floor BBM/ Plaster (L) | Blockwork 8" - BC | 79 | Sq.Ft | 15 | 100 | 29.63 | 0 | 1185 | CGST 0% URD I/P | 0 | 1185 | 1185 | Approved | 0 | 0 | 191 | 11 Jan 2022
GANGA DHAM TOWERS | 1226 | 93078 | 11 Jan 2022 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 2059 | Lt Substation Ground Floor BBM/ Plaster (L) | Sanla Plaster- BC | 534 | Sq.Ft | 20 | 100 | 267 | 0 | 10680 | CGST 0% URD I/P | 0 | 10680 | 10680 | Approved | 0 | 0 | 191 | 11 Jan 2022
GANGA DHAM TOWERS | 1242 | 93077 | 11 Jan 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2130 | Lt Substation Excavation & Backfilling work | Spreading & Levelling Work | 574.69 | Cu.Mtrs | 15 | 100 | 0 | 0 | 8620.35 | C+S GST 18% I/P RD | 1551.66 | 10172.01 | 10172.01 | Approved | 0 | 0 | 86 | 11 Jan 2022
GANGA DHAM TOWERS | 1241 | 93076 | 11 Jan 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2101 | Lt Substation Excavation & Backfilling work | Spreading & Levelling Work | 544.69 | Cu.Mtrs | 30 | 100 | 0 | 0 | 16340.7 | C+S GST 18% I/P RD | 2941.32 | 19282.02 | 19282.02 | Approved | 0 | 0 | 163 | 11 Jan 2022
GANGA DHAM TOWERS | 371 | 93075 | 11 Jan 2022 |  | CONSTROGENESIS | PRAKASH CONTRACTOR | EV - 1792 | EWS Bldg RCC 12th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 18.75 | Sq.Ft | 160 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 30 | 11 Jan 2022
GANGA DHAM TOWERS | 1119 | 93073 | 10 Jan 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1750 | C Bldg 1st RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 5430.357 | Sq.Ft | 170 | 100 | 23079.02 | 0 | 923160.69 | C+S GST 18% I/P RD | 166168.92 | 1089329.61 | 1089329.61 | Approved | 0 | 0 | 18463 | 10 Jan 2022
GANGA DHAM TOWERS | 1119 | 93073 | 10 Jan 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1750 | C Bldg 1st RCC Slab Built-up Area (L) | RCC Superstructure (B-up area) | 5430.366 | Sq.Ft | 170 | 100 | 23079.06 | 0 | 923162.22 | C+S GST 18% I/P RD | 166169.2 | 1089331.42 | 1089331.42 | Approved | 0 | 0 | 18463 | 10 Jan 2022
GANGA DHAM TOWERS | 1119 | 93068 | 08 Jan 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1751 | C Bldg Substructure Plinth Beam work | RCC Beam | 10500 | Sq.Ft | 31 | 100 | 8137.5 | 0 | 325500 | C+S GST 18% I/P RD | 58590 | 384090 | 384090 | Approved | 0 | 0 | 4410 | 08 Jan 2022
GANGA DHAM TOWERS | 1119 | 93068 | 08 Jan 2022 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1751 | C Bldg Substructure work Soling & PCC work | Soling & PCC | 10500 | Sq.Ft | 11 | 100 | 2887.5 | 0 | 115500 | C+S GST 18% I/P RD | 20790 | 136290 | 136290 | Approved | 0 | 0 | 4410 | 08 Jan 2022
GANGA DHAM TOWERS | 940 | 93065 | 08 Jan 2022 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1849 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 459.9045 | Sq.Ft | 1.25 | 100 | 14.37 | 0 | 574.88 | CGST 0% URD I/P | 0 | 574.88 | 574.88 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 73.8441 | Sq.Ft | 1.25 | 100 | 2.31 | 0 | 92.31 | CGST 0% URD I/P | 0 | 92.31 | 92.31 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.8 | Sq.Ft | 1.25 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 75.2 | Sq.Ft | 1.25 | 100 | 2.35 | 0 | 94 | CGST 0% URD I/P | 0 | 94 | 94 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 605.3256 | Sq.Ft | 1.25 | 100 | 18.92 | 0 | 756.66 | CGST 0% URD I/P | 0 | 756.66 | 756.66 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 47.2 | Sq.Ft | 1.25 | 100 | 1.48 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 8th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A-14th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 47.2 | Sq.Ft | 1.25 | 100 | 1.48 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 47.2 | Sq.Ft | 1.25 | 100 | 1.48 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 9th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.8 | Sq.Ft | 1.25 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 7th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A-11th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 6.4 | Sq.Ft | 1.25 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.8 | Sq.Ft | 1.25 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 78.5763 | Sq.Ft | 1.25 | 100 | 2.46 | 0 | 98.22 | CGST 0% URD I/P | 0 | 98.22 | 98.22 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 47.2 | Sq.Ft | 1.25 | 100 | 1.48 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 75.2 | Sq.Ft | 1.25 | 100 | 2.35 | 0 | 94 | CGST 0% URD I/P | 0 | 94 | 94 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.8 | Sq.Ft | 1.25 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A-17th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 110.4 | Sq.Ft | 1.25 | 100 | 3.45 | 0 | 138 | CGST 0% URD I/P | 0 | 138 | 138 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A-13th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A-15th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 3rd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1st floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 2nd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A-16th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A-10th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 103.6035 | Sq.Ft | 1.25 | 100 | 3.24 | 0 | 129.5 | CGST 0% URD I/P | 0 | 129.5 | 129.5 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 75.2 | Sq.Ft | 1.25 | 100 | 2.35 | 0 | 94 | CGST 0% URD I/P | 0 | 94 | 94 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 75.2 | Sq.Ft | 1.25 | 100 | 2.35 | 0 | 94 | CGST 0% URD I/P | 0 | 94 | 94 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 738.7182 | Sq.Ft | 1.25 | 100 | 23.08 | 0 | 923.4 | CGST 0% URD I/P | 0 | 923.4 | 923.4 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 47.2 | Sq.Ft | 1.25 | 100 | 1.48 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 75.2 | Sq.Ft | 1.25 | 100 | 2.35 | 0 | 94 | CGST 0% URD I/P | 0 | 94 | 94 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 4th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 5th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 47.2 | Sq.Ft | 1.25 | 100 | 1.48 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 61.6 | Sq.Ft | 1.25 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 737.4114 | Sq.Ft | 1.25 | 100 | 23.04 | 0 | 921.76 | CGST 0% URD I/P | 0 | 921.76 | 921.76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 75.2 | Sq.Ft | 1.25 | 100 | 2.35 | 0 | 94 | CGST 0% URD I/P | 0 | 94 | 94 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8.8 | Sq.Ft | 1.25 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 46.4 | Sq.Ft | 1.25 | 100 | 1.45 | 0 | 58 | CGST 0% URD I/P | 0 | 58 | 58 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 75.2 | Sq.Ft | 1.25 | 100 | 2.35 | 0 | 94 | CGST 0% URD I/P | 0 | 94 | 94 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 89.5356 | Sq.Ft | 1.25 | 100 | 2.8 | 0 | 111.92 | CGST 0% URD I/P | 0 | 111.92 | 111.92 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A-12th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 74.4 | Sq.Ft | 1.25 | 100 | 2.33 | 0 | 93 | CGST 0% URD I/P | 0 | 93 | 93 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 7.2 | Sq.Ft | 1.25 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 6th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 20 | Sq.Ft | 1.25 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 10.4 | Sq.Ft | 1.25 | 100 | 0.33 | 0 | 13 | CGST 0% URD I/P | 0 | 13 | 13 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 60.8 | Sq.Ft | 1.25 | 100 | 1.9 | 0 | 76 | CGST 0% URD I/P | 0 | 76 | 76 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 6.4 | Sq.Ft | 1.25 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 827 | 93064 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2051 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 8 | Sq.Ft | 1.25 | 100 | 0.25 | 0 | 10 | CGST 0% URD I/P | 0 | 10 | 10 | Approved | 0 | 0 | 99 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 4th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 464.55 | Sq.Ft | 1.75 | 100 | 0 | 0 | 812.96 | CGST 0% URD I/P | 0 | 812.96 | 812.96 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 82 | CGST 0% URD I/P | 0 | 82 | 82 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 61.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 107 | CGST 0% URD I/P | 0 | 107 | 107 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 12 | CGST 0% URD I/P | 0 | 12 | 12 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A-13th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 82 | CGST 0% URD I/P | 0 | 82 | 82 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 5th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 61.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 107 | CGST 0% URD I/P | 0 | 107 | 107 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 6th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 7th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A-10th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 82 | CGST 0% URD I/P | 0 | 82 | 82 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A-11th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 52 | Sq.Ft | 1.75 | 100 | 0 | 0 | 91 | CGST 0% URD I/P | 0 | 91 | 91 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 12 | CGST 0% URD I/P | 0 | 12 | 12 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 9th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 90.44 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158.27 | CGST 0% URD I/P | 0 | 158.27 | 158.27 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A-14th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 746.18 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1305.82 | CGST 0% URD I/P | 0 | 1305.82 | 1305.82 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 2nd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A-16th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A-17th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 110.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 193 | CGST 0% URD I/P | 0 | 193 | 193 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 8th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 12 | CGST 0% URD I/P | 0 | 12 | 12 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 61.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 107 | CGST 0% URD I/P | 0 | 107 | 107 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 12 | CGST 0% URD I/P | 0 | 12 | 12 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 62.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 109 | CGST 0% URD I/P | 0 | 109 | 109 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 61.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 107 | CGST 0% URD I/P | 0 | 107 | 107 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.59 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130.53 | CGST 0% URD I/P | 0 | 130.53 | 130.53 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A-12th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 744.86 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1303.51 | CGST 0% URD I/P | 0 | 1303.51 | 1303.51 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1st floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A-15th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 82 | CGST 0% URD I/P | 0 | 82 | 82 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 9.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 79.37 | Sq.Ft | 1.75 | 100 | 0 | 0 | 138.9 | CGST 0% URD I/P | 0 | 138.9 | 138.9 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 611.44 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1070.02 | CGST 0% URD I/P | 0 | 1070.02 | 1070.02 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 81 | CGST 0% URD I/P | 0 | 81 | 81 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 130 | CGST 0% URD I/P | 0 | 130 | 130 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 82 | CGST 0% URD I/P | 0 | 82 | 82 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 8 | Sq.Ft | 1.75 | 100 | 0 | 0 | 14 | CGST 0% URD I/P | 0 | 14 | 14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 104.65 | Sq.Ft | 1.75 | 100 | 0 | 0 | 183.14 | CGST 0% URD I/P | 0 | 183.14 | 183.14 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 82 | CGST 0% URD I/P | 0 | 82 | 82 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 61.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 107 | CGST 0% URD I/P | 0 | 107 | 107 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 46.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 82 | CGST 0% URD I/P | 0 | 82 | 82 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 10.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 19 | CGST 0% URD I/P | 0 | 19 | 19 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 828 | 93063 | 08 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2073 | A 3rd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 20 | Sq.Ft | 1.75 | 100 | 0 | 0 | 35 | CGST 0% URD I/P | 0 | 35 | 35 | Approved | 0 | 0 | 140 | 08 Jan 2022
GANGA DHAM TOWERS | 810 | 93062 | 08 Jan 2022 |  | GREENSOL TECH | GREENSOL TECH | EV - 1830 | STP 35 KLD (EWS Tower) - 1 No. | Sewage Treatment Plant (M) | 1 | No. | 406000 | 28.57 | 0 | 0 | 115998.26 | C+S GST 18% I/P RD | 20879.68 | 136877.94 | 136877.94 | Approved | 0 | 0 | 2320 | 08 Jan 2022
GANGA DHAM TOWERS | 808 | 93061 | 08 Jan 2022 |  | GREENSOL TECH | GREENSOL TECH | EV - 1831 | STP 200 KLD(A,B,C Tower) - 1 No. | Sewage Treatment Plant (M) | 1 | No. | 1750000 | 28.57 | 0 | 0 | 499992.5 | C+S GST 18% I/P RD | 89998.66 | 589991.16 | 589991.16 | Approved | 0 | 0 | 10000 | 08 Jan 2022
GANGA DHAM TOWERS | 1198 | 93059 | 07 Jan 2022 |  | SMITA ARTS | SMITA ARTS | EV - 1665 | MEDIA Branding | Backlet Box / Backlet Display Frame / Board | 52.2857 | Sq.Ft | 700 | 100 | 0 | 0 | 36599.99 | C+S GST 18% I/P URD | 6588 | 43187.99 | 43187.99 | Approved | 0 | 0 | 732 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1804 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1803 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | C+S GST 18% I/P RD | 135 | 885 | 885 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1802 Chemical Grouting Work | Chemical Grouting.- BC | 1189.712 | Sq.Ft | 1 | 100 | 118.97 | 0 | 1189.71 | C+S GST 18% I/P RD | 214.14 | 1403.85 | 1403.85 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1903 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | C+S GST 18% I/P RD | 202.38 | 1326.74 | 1326.74 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1804 Chemical & IPS Waterproofing | IPS W/P | 242 | Sq.Ft | 11 | 100 | 266.2 | 0 | 2662 | C+S GST 18% I/P RD | 479.16 | 3141.16 | 3141.16 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1803 Chemical & IPS Waterproofing | IPS W/P | 182 | Sq.Ft | 11 | 100 | 200.2 | 0 | 2002 | C+S GST 18% I/P RD | 360.36 | 2362.36 | 2362.36 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1802 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1189.712 | Sq.Ft | 1 | 100 | 118.97 | 0 | 1189.71 | C+S GST 18% I/P RD | 214.14 | 1403.85 | 1403.85 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1903 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | C+S GST 18% I/P RD | 202.38 | 1326.74 | 1326.74 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1804 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 242 | Sq.Ft | 19 | 100 | 459.8 | 0 | 4598 | C+S GST 18% I/P RD | 827.64 | 5425.64 | 5425.64 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1803 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 182 | Sq.Ft | 19 | 100 | 345.8 | 0 | 3458 | C+S GST 18% I/P RD | 622.44 | 4080.44 | 4080.44 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1803 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 12 | No. | 70 | 100 | 84 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1804 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 15 | No. | 70 | 100 | 105 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1803 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 12 | No. | 150 | 100 | 180 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 401 | 93041 | 07 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | R R TANGADE | EV - 1850 | A 1804 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 15 | No. | 150 | 100 | 225 | 0 | 2250 | C+S GST 18% I/P RD | 405 | 2655 | 2655 | Approved | 0 | 0 | 249 | 07 Jan 2022
GANGA DHAM TOWERS | 1239 | 93038 | 07 Jan 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2115 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | JCB Charges | 8 | Hrs | 850 | 100 | 0 | 0 | 6800 | C+S GST 18% I/P RD | 1224 | 8024 | 8024 | Approved | 0 | 0 | 162 | 07 Jan 2022
GANGA DHAM TOWERS | 1239 | 93038 | 07 Jan 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2115 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | JCB Charges | 7 | Hrs | 850 | 100 | 0 | 0 | 5950 | C+S GST 18% I/P RD | 1071 | 7021 | 7021 | Approved | 0 | 0 | 162 | 07 Jan 2022
GANGA DHAM TOWERS | 1239 | 93038 | 07 Jan 2022 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2115 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | JCB Charges | 4 | Hrs | 850 | 100 | 0 | 0 | 3400 | C+S GST 18% I/P RD | 612 | 4012 | 4012 | Approved | 0 | 0 | 162 | 07 Jan 2022
GANGA DHAM TOWERS | 1212 | 93037 | 07 Jan 2022 |  | SPARTAN ENGINEERING INDUSTRIES PVT LTD | SPARTAN ENGINEERING INDUSTRIES PVT LTD | EV - 1829 | Tower A&B Material Lift Re-Erection work | Re-Erection of SPM-200V | 6 | Mtrs | 1200 | 100 | 0 | 0 | 7200 | C+S GST 18% I/P RD | 1296 | 8496 | 8496 | Approved | 0 | 0 | 216 | 07 Jan 2022
GANGA DHAM TOWERS | 1212 | 93037 | 07 Jan 2022 |  | SPARTAN ENGINEERING INDUSTRIES PVT LTD | SPARTAN ENGINEERING INDUSTRIES PVT LTD | EV - 1829 | Tower A&B Material Lift Re-Erection work | Re-Erection of SPM-150V | 3 | Mtrs | 1200 | 100 | 0 | 0 | 3600 | C+S GST 18% I/P RD | 648 | 4248 | 4248 | Approved | 0 | 0 | 216 | 07 Jan 2022
GANGA DHAM TOWERS | 897 | 93036 | 06 Jan 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1688 | Develpoment Area Ms Work ( Near Steel Yard) | Fabrication work (L) | 4419 | Sq.Ft | 10 | 100 | 1104.75 | 0 | 44190 | CGST 0% URD I/P | 0 | 44190 | 44190 | Approved | 0 | 50000 | 518 | 06 Jan 2022
GANGA DHAM TOWERS | 897 | 93036 | 06 Jan 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1688 | Develpoment Area Ms Work ( Near Steel Yard) | Fastner (M) - SOSB | 179 | No. | 27 | 100 | 0 | 0 | 4833 | CGST 0% URD I/P | 0 | 4833 | 4833 | Approved | 0 | 50000 | 518 | 06 Jan 2022
GANGA DHAM TOWERS | 897 | 93036 | 06 Jan 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1688 | Develpoment Area Ms Work ( Near Steel Yard) | Lock Patti - SOSB | 4 | No. | 10 | 100 | 0 | 0 | 40 | CGST 0% URD I/P | 0 | 40 | 40 | Approved | 0 | 50000 | 518 | 06 Jan 2022
GANGA DHAM TOWERS | 897 | 93036 | 06 Jan 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1688 | Develpoment Area Ms Work ( Near Steel Yard) | Fabrication work (M) | 23.23 | Kgs | 65 | 100 | 0 | 0 | 1509.95 | CGST 0% URD I/P | 0 | 1509.95 | 1509.95 | Approved | 0 | 50000 | 518 | 06 Jan 2022
GANGA DHAM TOWERS | 897 | 93036 | 06 Jan 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1688 | Develpoment Area Ms Work ( Near Steel Yard) | MS Angle (M) | 39 | No. | 15 | 100 | 0 | 0 | 585 | CGST 0% URD I/P | 0 | 585 | 585 | Approved | 0 | 50000 | 518 | 06 Jan 2022
GANGA DHAM TOWERS | 897 | 93036 | 06 Jan 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1688 | Develpoment Area Ms Work ( Near Steel Yard) | Tower Bolt SOSB | 2 | No. | 100 | 100 | 0 | 0 | 200 | CGST 0% URD I/P | 0 | 200 | 200 | Approved | 0 | 50000 | 518 | 06 Jan 2022
GANGA DHAM TOWERS | 897 | 93036 | 06 Jan 2022 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1688 | Develpoment Area Ms Work ( Near Steel Yard) | Hinges Fixing - BCo | 4 | No. | 120 | 100 | 0 | 0 | 480 | CGST 0% URD I/P | 0 | 480 | 480 | Approved | 0 | 50000 | 518 | 06 Jan 2022
GANGA DHAM TOWERS | 1213 | 93035 | 06 Jan 2022 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1685 | Tower-B Ceiling Parking Painting work (L) | Putty with Touchup | 28932 | Sq.Ft | 0.25 | 100 | 180.83 | 0 | 7233 | IGST 18% I/P RD | 1301.94 | 8534.94 | 8534.94 | Approved | 0 | 15000 | 289 | 06 Jan 2022
GANGA DHAM TOWERS | 1213 | 93035 | 06 Jan 2022 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1685 | Tower-B Ceiling Parking Painting work (L) | Primer First Coat | 28930.6667 | Sq.Ft | 0.75 | 100 | 542.45 | 0 | 21698 | IGST 18% I/P RD | 3905.64 | 25603.64 | 25603.64 | Approved | 0 | 15000 | 289 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 1004 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 60 | Sq.Ft | 55 | 100 | 0 | 0 | 3300 | C+S GST 18% I/P RD | 594 | 3894 | 3894 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 1803 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 60 | Sq.Ft | 55 | 100 | 0 | 0 | 3300 | C+S GST 18% I/P RD | 594 | 3894 | 3894 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 1803 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 644 | Sq.Ft | 55 | 100 | 0 | 0 | 35420 | C+S GST 18% I/P RD | 6375.6 | 41795.6 | 41795.6 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 1804 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 2004 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 704 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 60 | Sq.Ft | 55 | 100 | 0 | 0 | 3300 | C+S GST 18% I/P RD | 594 | 3894 | 3894 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 704 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 826.6909 | Sq.Ft | 55 | 100 | 0 | 0 | 45468 | C+S GST 18% I/P RD | 8184.24 | 53652.24 | 53652.24 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 2003 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 2103 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 1004 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 826.6909 | Sq.Ft | 55 | 100 | 0 | 0 | 45468 | C+S GST 18% I/P RD | 8184.24 | 53652.24 | 53652.24 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 2103 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 2003 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 704 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 1803 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 1004 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 1804 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 629 | 93034 | 06 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1686 | A 2004 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 100000 | 0 | 06 Jan 2022
GANGA DHAM TOWERS | 971 | 93033 | 06 Jan 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1687 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 3" BCE | 181 | No. | 210 | 100 | 950.25 | 0 | 38010 | C+S GST 18% I/P RD | 6841.8 | 44851.8 | 44851.8 | Approved | 0 | 25000 | 800 | 06 Jan 2022
GANGA DHAM TOWERS | 971 | 93033 | 06 Jan 2022 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1687 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 200 | No. | 210 | 100 | 1050 | 0 | 42000 | C+S GST 18% I/P RD | 7560 | 49560 | 49560 | Approved | 0 | 25000 | 800 | 06 Jan 2022
GANGA DHAM TOWERS | 456 | 93032 | 06 Jan 2022 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1684 | A Bldg External Plumbing Rainwater Line (L) | Rainwater Line | 46 | Flat | 2700 | 100 | 3105 | 0 | 124200 | CGST 0% URD I/P | 0 | 124200 | 124200 | Approved | 0 | 50000 | 1242 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 602 Store Vitrified Flooring | Vitrified Flooring -BC | 46.1538 | Sq.Ft | 13 | 100 | 15 | 0 | 600 | C+S GST 18% I/P RD | 108 | 708 | 708 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 602 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 59 | Sq.Ft | 13 | 100 | 19.18 | 0 | 767 | C+S GST 18% I/P RD | 138.06 | 905.06 | 905.06 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 2002 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 60 | 100 | 404.13 | 0 | 16165.2 | C+S GST 18% I/P RD | 2909.74 | 19074.94 | 19074.94 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 2002 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 203.5 | Sq.Ft | 60 | 100 | 305.25 | 0 | 12210 | C+S GST 18% I/P RD | 2197.8 | 14407.8 | 14407.8 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 2002 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 645 | Sq.Ft | 60 | 100 | 967.5 | 0 | 38700 | C+S GST 18% I/P RD | 6966 | 45666 | 45666 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 602 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 45 | 100 | 231.29 | 0 | 9251.55 | C+S GST 18% I/P RD | 1665.28 | 10916.83 | 10916.83 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 602 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 45 | 100 | 742.01 | 0 | 29680.2 | C+S GST 18% I/P RD | 5342.44 | 35022.64 | 35022.64 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 602 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 45 | 100 | 303.1 | 0 | 12123.9 | C+S GST 18% I/P RD | 2182.3 | 14306.2 | 14306.2 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 602 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 147.7333 | Sq.Ft | 15 | 100 | 55.4 | 0 | 2216 | C+S GST 18% I/P RD | 398.88 | 2614.88 | 2614.88 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93031 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1682 | B 602 Ceramic Tiling | Ceramic Flooring work | 203.5385 | Sq.Ft | 13 | 100 | 66.15 | 0 | 2646 | C+S GST 18% I/P RD | 476.28 | 3122.28 | 3122.28 | Approved | 0 | 75000 | 1244 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93030 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1683 | B 102 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 147.5333 | Sq.Ft | 15 | 100 | 55.32 | 0 | 2213 | C+S GST 18% I/P RD | 398.34 | 2611.34 | 2611.34 | Approved | 0 | 75000 | 1175 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93030 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1683 | B 102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 645 | Sq.Ft | 45 | 100 | 725.63 | 0 | 29025 | C+S GST 18% I/P RD | 5224.5 | 34249.5 | 34249.5 | Approved | 0 | 75000 | 1175 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93030 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1683 | B 102 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 45 | 100 | 303.1 | 0 | 12123.9 | C+S GST 18% I/P RD | 2182.3 | 14306.2 | 14306.2 | Approved | 0 | 75000 | 1175 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93030 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1683 | B 102 Parents Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 203 | Sq.Ft | 45 | 100 | 228.38 | 0 | 9135 | C+S GST 18% I/P RD | 1644.3 | 10779.3 | 10779.3 | Approved | 0 | 75000 | 1175 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93030 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1683 | B 1702 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 645 | Sq.Ft | 55 | 100 | 886.88 | 0 | 35475 | C+S GST 18% I/P RD | 6385.5 | 41860.5 | 41860.5 | Approved | 0 | 75000 | 1175 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93030 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1683 | B 1702 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 55 | 100 | 370.45 | 0 | 14818.1 | C+S GST 18% I/P RD | 2667.26 | 17485.36 | 17485.36 | Approved | 0 | 75000 | 1175 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93030 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1683 | B 1702 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 203 | Sq.Ft | 55 | 100 | 279.13 | 0 | 11165 | C+S GST 18% I/P RD | 2009.7 | 13174.7 | 13174.7 | Approved | 0 | 75000 | 1175 | 06 Jan 2022
GANGA DHAM TOWERS | 758 | 93030 | 06 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1683 | B 1702 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 147.5417 | Sq.Ft | 24 | 100 | 88.53 | 0 | 3541 | C+S GST 18% I/P RD | 637.38 | 4178.38 | 4178.38 | Approved | 0 | 75000 | 1175 | 06 Jan 2022
GANGA DHAM TOWERS | 1037 | 93029 | 06 Jan 2022 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 1659 | Head Office Security Service | Security Guard AIE - | 62 | Day | 419.35 | 100 | 0 | 0 | 25999.7 | C+S GST 18% I/P RD | 4679.94 | 30679.64 | 30679.64 | Approved | 0 | 0 | 260 | 06 Jan 2022
GANGA DHAM TOWERS | 1229 | 93028 | 06 Jan 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1733 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 32mm dia.(M+L) | 43.2 | Mtrs | 660 | 100 | 712.8 | 0 | 28512 | C+S GST 18% I/P RD | 5132.16 | 33644.16 | 33644.16 | Approved | 0 | 0 | 6398 | 06 Jan 2022
GANGA DHAM TOWERS | 1229 | 93028 | 06 Jan 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1733 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 80mm dia.(M+L) | 24 | Mtrs | 1400 | 100 | 840 | 0 | 33600 | C+S GST 18% I/P RD | 6048 | 39648 | 39648 | Approved | 0 | 0 | 6398 | 06 Jan 2022
GANGA DHAM TOWERS | 1229 | 93028 | 06 Jan 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1733 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 25mm dia.(M+L) | 283.2 | Mtrs | 510 | 100 | 3610.8 | 0 | 144432 | C+S GST 18% I/P RD | 25997.76 | 170429.76 | 170429.76 | Approved | 0 | 0 | 6398 | 06 Jan 2022
GANGA DHAM TOWERS | 1229 | 93028 | 06 Jan 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1733 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 40mm dia.(M+L) | 134.4 | Mtrs | 760 | 100 | 2553.6 | 0 | 102144 | C+S GST 18% I/P URD | 18385.92 | 120529.92 | 120529.92 | Approved | 0 | 0 | 6398 | 06 Jan 2022
GANGA DHAM TOWERS | 1229 | 93028 | 06 Jan 2022 |  | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | OUSTFIRE SAFETY ENGINEERS PRIVATE LIMITED | EV - 1733 | B Fire Fighting 11 to 31 floor OUSTFIRE | SITC GI Pipe C Class 65mm dia.(M+L) | 9.6 | Mtrs | 1170 | 100 | 280.8 | 0 | 11232 | C+S GST 18% I/P RD | 2021.76 | 13253.76 | 13253.76 | Approved | 0 | 0 | 6398 | 06 Jan 2022
GANGA DHAM TOWERS | 384 | 93021 | 06 Jan 2022 |  | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1879 | A Stru. Wall Core Cutting | Core Cutting Work 8" BCE | 60 | No. | 300 | 100 | 450 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 180 | 06 Jan 2022
GANGA DHAM TOWERS | 1218 | 93020 | 06 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1755 | B-Bldg Rebaring work for ledge wall | Rebarring work 8mm dia- BC | 2027 | No. | 80 | 100 | 4054 | 0 | 162160 | C+S GST 18% I/P RD | 29188.8 | 191348.8 | 191348.8 | Approved | 0 | 0 | 6624 | 06 Jan 2022
GANGA DHAM TOWERS | 1218 | 93020 | 06 Jan 2022 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1755 | B-Bldg Rebaring work for ledge wall | Rebarring work 8mm dia- BC | 2113 | No. | 80 | 100 | 4226 | 0 | 169040 | C+S GST 18% I/P RD | 30427.2 | 199467.2 | 199467.2 | Approved | 0 | 0 | 6624 | 06 Jan 2022
GANGA DHAM TOWERS | 1234 | 93018 | 06 Jan 2022 |  | AVCON TECHNICS PVT LTD | Kishan Enterprises | EV - 1730 | A 2304 NOC | Italian Marble Flooring - BCo | 339 | Sq.Ft | 55 | 100 | 0 | 0 | 18645 | C+S GST 18% I/P RD | 3356.1 | 22001.1 | 22001.1 | Approved | 0 | 0 | 186 | 06 Jan 2022
GANGA DHAM TOWERS | 551 | 93017 | 06 Jan 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1729 | A 2304 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 590.89 | Sq.Ft | 60 | 100 | 886.34 | 0 | 35453.4 | C+S GST 18% I/P RD | 6381.62 | 41835.02 | 41835.02 | Approved | 0 | 0 | 651 | 06 Jan 2022
GANGA DHAM TOWERS | 551 | 93017 | 06 Jan 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1729 | A 2304 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 60 | 100 | 200.78 | 0 | 8031 | C+S GST 18% I/P RD | 1445.58 | 9476.58 | 9476.58 | Approved | 0 | 0 | 651 | 06 Jan 2022
GANGA DHAM TOWERS | 551 | 93017 | 06 Jan 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1729 | A 2304 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 150.4701 | Sq.Ft | 60 | 100 | 225.71 | 0 | 9028.21 | C+S GST 18% I/P RD | 1625.08 | 10653.29 | 10653.29 | Approved | 0 | 0 | 651 | 06 Jan 2022
GANGA DHAM TOWERS | 551 | 93017 | 06 Jan 2022 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1729 | A 2304 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 209 | Sq.Ft | 60 | 100 | 313.5 | 0 | 12540 | C+S GST 18% I/P RD | 2257.2 | 14797.2 | 14797.2 | Approved | 0 | 0 | 651 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 20th Floor Flat No 2001 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 16th Floor Flat No 1602 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 20th Floor Flat No 2001 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 526 | Sq.Ft | 1 | 100 | 0 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 19th Floor Flat No 1902 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 21st Floor Flat No 2102 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 25th Floor Flat No 2502 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 7th Floor Flat No 702 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 16th Floor Flat No 1601 Ceilings Semi-Acrylic Painting. | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 18th Floor Flat No 1801 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 526 | Sq.Ft | 1 | 100 | 0 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 22nd Floor Flat No 2202 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 4th Floor Flat No 401 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 13th Floor Flat No 1301 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 16th Floor Flat No 1602 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 19th Floor Flat No 1901 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 6th Floor Flat No 601 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 21st Floor Flat No 2101 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-17th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 1st Floor Flat No 102 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 5th Floor Flat No 502 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 12th Floor Flat No 1202 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 21st Floor Flat No 2102 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-11th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-20th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 8th Floor Flat No 802 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 17th Floor Flat No 1702 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 12th Floor Flat No 1201 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 24th Floor Flat No 2401 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 2nd Floor Flat No 202 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 4th Floor Flat No 402 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 6th Floor Flat No 601 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 6th Floor Flat No 602 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 3rd Floor Flat No 302 Walls Semi-Acrylic Painting t | 1 Coat Primer (External) (M) | 97 | Sq.Ft | 1 | 100 | 0 | 0 | 97 | CGST 0% URD I/P | 0 | 97 | 97 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 4th Floor Flat No 401 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-25th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 2nd Floor Flat No 201 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 5th Floor Flat No 501 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 10th Floor Flat No 1002 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 20th Floor Flat No 2002 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 24th Floor Flat No 2401 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 526 | Sq.Ft | 1 | 100 | 0 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 24th Floor Flat No 2402 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 12th Floor Flat No 1201 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 15th Floor Flat No 1502 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-24th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 7th Floor Flat No 702 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 11th Floor Flat No 1102 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 7th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 8th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 7th Floor Flat No 701 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 4th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 9th Floor Flat No 902 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 13th Floor Flat No 1302 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 14th Floor Flat No 1401 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 14th Floor Flat No 1401 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 17th Floor Flat No 1702 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 5th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 324 | Sq.Ft | 1 | 100 | 0 | 0 | 324 | CGST 0% URD I/P | 0 | 324 | 324 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 1st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 1st Floor Flat No 101 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 5th Floor Flat No 502 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 8th Floor Flat No 801 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-18th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 9th Floor Flat No 902 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 10th Floor Flat No 1001 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 18th Floor Flat No 1802 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 9th Floor Flat No 901 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 9th Floor Flat No 901 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 13th Floor Flat No 1301 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 17th Floor Flat No 1701 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 19th Floor Flat No 1901 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 526 | Sq.Ft | 1 | 100 | 0 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 4th Floor Flat No 402 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 97 | Sq.Ft | 1 | 100 | 0 | 0 | 97 | CGST 0% URD I/P | 0 | 97 | 97 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 1st Floor Flat No 102 Ceilings Semi-Acrylic Painting - | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 14th Floor Flat No 1402 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 18th Floor Flat No 1801 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 22nd Floor Flat No 2202 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 2nd Floor Flat No 201 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 5th Floor Flat No 501 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 10th Floor Flat No 1001 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 6th Floor Flat No 602 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 8th Floor Flat No 802 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 25th Floor Flat No 2501 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 3rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-22nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 13th Floor Flat No 1302 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 14th Floor Flat No 1402 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 15th Floor Flat No 1501 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 23rd Floor Flat No 2301 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 526 | Sq.Ft | 1 | 100 | 0 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-16th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 2nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-13th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-15th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 9th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 10th Floor Flat No 1002 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 25th Floor Flat No 2501 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 526 | Sq.Ft | 1 | 100 | 0 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 11th Floor Flat No 1101 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 23rd Floor Flat No 2302 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 25th Floor Flat No 2502 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 6th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 10th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-19th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 15th Floor Flat No 1502 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-12th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 2nd Floor Flat No 202 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 22nd Floor Flat No 2201 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 324 | Sq.Ft | 1 | 100 | 0 | 0 | 324 | CGST 0% URD I/P | 0 | 324 | 324 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 23rd Floor Flat No 2301 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 3rd Floor Flat No 302 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 1st Floor Flat No 101 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 350 | Sq.Ft | 1 | 100 | 0 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-21st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 3rd Floor Flat No 301 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 7th Floor Flat No 701 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 12th Floor Flat No 1202 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 98 | Sq.Ft | 1 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 15th Floor Flat No 1501 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8.39 | Sq.Ft | 1 | 100 | 0 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 17th Floor Flat No 1701 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 8th Floor Flat No 801 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 11th Floor Flat No 1102 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 16th Floor Flat No 1601 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 20th Floor Flat No 2002 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 24th Floor Flat No 2402 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-14th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 11th Floor Flat No 1101 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 284 | Sq.Ft | 1 | 100 | 0 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 23rd Floor Flat No 2302 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 202 | Sq.Ft | 1 | 100 | 0 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B-23rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 830 | 93016 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1882 | B 3rd Floor Flat No 302 Walls Semi-Acrylic Painting t | 1 Coat Primer (External) (M) | 324 | Sq.Ft | 1 | 100 | 0 | 0 | 324 | CGST 0% URD I/P | 0 | 324 | 324 | Approved | 0 | 0 | 151 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 19th Floor Flat No 1902 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 20th Floor Flat No 2001 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 13th Floor Flat No 1302 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 17th Floor Flat No 1702 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 18th Floor Flat No 1801 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 22nd Floor Flat No 2201 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 7th Floor Flat No 702 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104 | Sq.Ft | 1 | 100 | 2.6 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 20th Floor Flat No 2002 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 23rd Floor Flat No 2302 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 202 | Sq.Ft | 1 | 100 | 5.05 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 24th Floor Flat No 2401 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 526 | Sq.Ft | 1 | 100 | 13.15 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 24th Floor Flat No 2402 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 2nd Floor Flat No 201 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 12th Floor Flat No 1201 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-22nd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 4th Floor Flat No 401 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 23rd Floor Flat No 2301 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 526 | Sq.Ft | 1 | 100 | 13.15 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 15th Floor Flat No 1502 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 8th Floor Flat No 801 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 10th Floor Flat No 1002 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 12th Floor Flat No 1202 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 13th Floor Flat No 1301 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 18th Floor Flat No 1802 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104 | Sq.Ft | 1 | 100 | 2.6 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 14th Floor Flat No 1402 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 15th Floor Flat No 1501 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 18th Floor Flat No 1802 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 19th Floor Flat No 1901 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 25th Floor Flat No 2501 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 526 | Sq.Ft | 1 | 100 | 13.15 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 2nd Floor Flat No 202 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 4th Floor Flat No 401 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 6th Floor Flat No 602 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 19th Floor Flat No 1901 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 526 | Sq.Ft | 1 | 100 | 13.15 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 25th Floor Flat No 2501 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 10th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 2nd Floor Flat No 202 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 23rd Floor Flat No 2301 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 24th Floor Flat No 2402 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 202 | Sq.Ft | 1 | 100 | 5.05 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 8th Floor Flat No 802 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 25th Floor Flat No 2502 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 202 | Sq.Ft | 1 | 100 | 5.05 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-21st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 1st Floor Flat No 102 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 13th Floor Flat No 1302 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 18th Floor Flat No 1801 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 526 | Sq.Ft | 1 | 100 | 13.15 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 22nd Floor Flat No 2202 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 8th Floor Flat No 801 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 16th Floor Flat No 1602 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 21st Floor Flat No 2101 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 526 | Sq.Ft | 1 | 100 | 13.15 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 20th Floor Flat No 2002 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 202 | Sq.Ft | 1 | 100 | 5.05 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 1st Floor Flat No 101 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 13th Floor Flat No 1301 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 16th Floor Flat No 1601 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 10th Floor Flat No 1001 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 17th Floor Flat No 1701 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 25th Floor Flat No 2502 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-14th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 4th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 9th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-11th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 1st Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (L) - | 227.87 | Sq.Ft | 1 | 100 | 5.7 | 0 | 227.87 | CGST 0% URD I/P | 0 | 227.87 | 227.87 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-12th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-20th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 2nd Floor Flat No 201 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 7th Floor Flat No 702 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 22nd Floor Flat No 2201 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 526 | Sq.Ft | 1 | 100 | 13.15 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 9th Floor Flat No 902 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 9th Floor Flat No 902 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 19th Floor Flat No 1902 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 9th Floor Flat No 901 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 14th Floor Flat No 1402 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 15th Floor Flat No 1501 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 6th Floor Flat No 601 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 16th Floor Flat No 1602 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 21st Floor Flat No 2101 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 6th Floor Flat No 601 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 6th Floor Flat No 602 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-25th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 3rd Floor Flat No 302 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-13th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-17th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 5th Floor Flat No 501 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-16th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 12th Floor Flat No 1201 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 16th Floor Flat No 1601 Ceilings Semi-Acrylic Painting. | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 24th Floor Flat No 2401 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 5th Floor Flat No 501 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 8th Floor Flat No 802 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 11th Floor Flat No 1101 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 17th Floor Flat No 1701 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-19th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 8th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-24th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 14th Floor Flat No 1401 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 5th Floor Flat No 502 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 17th Floor Flat No 1702 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-15th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-18th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 9th Floor Flat No 901 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 21st Floor Flat No 2102 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 22nd Floor Flat No 2202 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 202 | Sq.Ft | 1 | 100 | 5.05 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 5th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 3rd Floor Flat No 301 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 3rd Floor Flat No 301 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 3rd Floor Flat No 302 Walls Semi-Acrylic Painting t | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 4th Floor Flat No 402 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 12th Floor Flat No 1202 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 23rd Floor Flat No 2302 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 11th Floor Flat No 1102 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 11th Floor Flat No 1102 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 98 | Sq.Ft | 1 | 100 | 2.45 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 15th Floor Flat No 1502 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 14th Floor Flat No 1401 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 21st Floor Flat No 2102 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 202 | Sq.Ft | 1 | 100 | 5.05 | 0 | 202 | CGST 0% URD I/P | 0 | 202 | 202 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 7th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 7th Floor Flat No 701 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 20th Floor Flat No 2001 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 526 | Sq.Ft | 1 | 100 | 13.15 | 0 | 526 | CGST 0% URD I/P | 0 | 526 | 526 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 7th Floor Flat No 701 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 11th Floor Flat No 1101 Walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 284 | Sq.Ft | 1 | 100 | 7.1 | 0 | 284 | CGST 0% URD I/P | 0 | 284 | 284 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 6th Floor Lv, Electrical shaft Semi-Acrylic Paint - 227. | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B-23rd Floor Lv, Electrical shaft Semi-Acrylic Paint - 227 | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 1st Floor Flat No 101 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8.39 | Sq.Ft | 1 | 100 | 0.21 | 0 | 8.39 | CGST 0% URD I/P | 0 | 8.39 | 8.39 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 1st Floor Flat No 102 Ceilings Semi-Acrylic Painting - | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 5th Floor Flat No 502 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 829 | 93015 | 06 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1881 | B 4th Floor Flat No 402 Ceilings Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 149 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2304 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2201 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2303 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 1904 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2302 Chemical Grouting Work | Chemical Grouting.- BC | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2301 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2303 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2301 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2304 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 1904 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 2302 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 103 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 401 | 93014 | 06 Jan 2022 |  | SHREE GURUDATTA ENTERPRISES | AJAY KUMAR GUPTA | EV - 1746 | A 103 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 177 | 06 Jan 2022
GANGA DHAM TOWERS | 237 | 93013 | 06 Jan 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1803 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.8709 | Month | 7000 | 100 | 0 | 0 | 6096 | CGST 0% URD I/P | 0 | 6096 | 6096 | Approved | 0 | 0 | 61 | 06 Jan 2022
GANGA DHAM TOWERS | 258 | 93012 | 06 Jan 2022 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1804 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.8708 | Month | 2500 | 100 | 0 | 0 | 2177 | CGST 0% URD I/P | 0 | 2177 | 2177 | Approved | 0 | 0 | 22 | 06 Jan 2022
GANGA DHAM TOWERS | 1217 | 93000 | 05 Jan 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 1681 | Ganga Collidium Rolling Shutter (L) | Rolling Shutter Removing | 1 | No. | 1800 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 493 | 05 Jan 2022
GANGA DHAM TOWERS | 1217 | 93000 | 05 Jan 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 1681 | Ganga Collidium Rolling Shutter (L) | Rolling Shutters (M+L) | 50 | Sq.Ft | 200 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 493 | 05 Jan 2022
GANGA DHAM TOWERS | 1217 | 93000 | 05 Jan 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 1681 | Ganga Collidium Rolling Shutter (L) | Gear Set | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 493 | 05 Jan 2022
GANGA DHAM TOWERS | 1217 | 93000 | 05 Jan 2022 |  | BHAGYALAXMI ENTERPRISES | BHAGYALAXMI ENTERPRISES | EV - 1681 | Ganga Collidium Rolling Shutter (L) | Rolling Shutters (M+L) | 139.5 | Sq.Ft | 240 | 100 | 837 | 0 | 33480 | C+S GST 18% I/P RD | 6026.4 | 39506.4 | 39506.4 | Approved | 0 | 0 | 493 | 05 Jan 2022
GANGA DHAM TOWERS | 149 | 92997 | 05 Jan 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1680 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 410 | No. | 4 | 100 | 0 | 0 | 1640 | CGST 0% URD I/P | 0 | 1640 | 1640 | Approved | 0 | 0 | 176 | 05 Jan 2022
GANGA DHAM TOWERS | 149 | 92997 | 05 Jan 2022 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1680 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 4000 | No. | 4 | 100 | 0 | 0 | 16000 | CGST 0% URD I/P | 0 | 16000 | 16000 | Approved | 0 | 0 | 176 | 05 Jan 2022
GANGA DHAM TOWERS | 1002 | 92996 | 05 Jan 2022 |  | AVCON TECHNICS PVT LTD | JAY GANESH ENTERPRISES | EV - 1944 | B 2402 NOC | Brickwork 4"- BC | 91.59 | Sq.Ft | 24 | 100 | 54.95 | 0 | 2198.16 | CGST 0% URD I/P | 0 | 2198.16 | 2198.16 | Approved | 0 | 0 | 22 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1302 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 0.3487 | R.Ft | 750 | 100 | 6.54 | 0 | 261.53 | C+S GST 18% I/P RD | 47.08 | 308.61 | 308.61 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1302 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.5507 | R.Ft | 750 | 100 | 104.08 | 0 | 4163.01 | C+S GST 18% I/P RD | 749.34 | 4912.35 | 4912.35 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1301 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.75 | R.Ft | 750 | 100 | 70.31 | 0 | 2812.5 | C+S GST 18% I/P RD | 506.26 | 3318.76 | 3318.76 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1302 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.75 | R.Ft | 750 | 100 | 89.06 | 0 | 3562.5 | C+S GST 18% I/P RD | 641.26 | 4203.76 | 4203.76 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1301 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 6.33 | R.Ft | 750 | 100 | 118.69 | 0 | 4747.5 | C+S GST 18% I/P RD | 854.56 | 5602.06 | 5602.06 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1301 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 750 | 100 | 102 | 0 | 4080 | C+S GST 18% I/P RD | 734.4 | 4814.4 | 4814.4 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1301 Children Toilet-2 Counter Wash Basin | Italian Marble Counter - Mkt | 5.08 | R.Ft | 750 | 100 | 95.25 | 0 | 3810 | C+S GST 18% I/P RD | 685.8 | 4495.8 | 4495.8 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1401 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 750 | 100 | 57.75 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1301 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 750 | 100 | 57.75 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1302 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 750 | 100 | 109.31 | 0 | 4372.5 | C+S GST 18% I/P RD | 787.06 | 5159.56 | 5159.56 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1401 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 6.33 | R.Ft | 750 | 100 | 118.69 | 0 | 4747.5 | C+S GST 18% I/P RD | 854.56 | 5602.06 | 5602.06 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1401 Children Toilet-2 Counter Wash Basin | Italian Marble Counter - Mkt | 5.08 | R.Ft | 750 | 100 | 95.25 | 0 | 3810 | C+S GST 18% I/P RD | 685.8 | 4495.8 | 4495.8 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1002 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 700 | 100 | 102.03 | 0 | 4081 | C+S GST 18% I/P RD | 734.58 | 4815.58 | 4815.58 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 902 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 700 | 100 | 102.03 | 0 | 4081 | C+S GST 18% I/P RD | 734.58 | 4815.58 | 4815.58 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 801 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 6.33 | R.Ft | 700 | 100 | 110.78 | 0 | 4431 | C+S GST 18% I/P RD | 797.58 | 5228.58 | 5228.58 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 902 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.9 | R.Ft | 700 | 100 | 103.25 | 0 | 4130 | C+S GST 18% I/P RD | 743.4 | 4873.4 | 4873.4 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1202 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.9 | R.Ft | 700 | 100 | 103.25 | 0 | 4130 | C+S GST 18% I/P RD | 743.4 | 4873.4 | 4873.4 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1202 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.75 | R.Ft | 700 | 100 | 83.13 | 0 | 3325 | C+S GST 18% I/P RD | 598.5 | 3923.5 | 3923.5 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 901 Children Toilet-2 Counter Wash Basin | Italian Marble Counter - Mkt | 5.08 | R.Ft | 700 | 100 | 88.9 | 0 | 3556 | C+S GST 18% I/P RD | 640.08 | 4196.08 | 4196.08 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1002 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.75 | R.Ft | 700 | 100 | 83.13 | 0 | 3325 | C+S GST 18% I/P RD | 598.5 | 3923.5 | 3923.5 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1202 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.83 | R.Ft | 700 | 100 | 102.03 | 0 | 4081 | C+S GST 18% I/P RD | 734.58 | 4815.58 | 4815.58 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 801 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 700 | 100 | 53.9 | 0 | 2156 | C+S GST 18% I/P RD | 388.08 | 2544.08 | 2544.08 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1202 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.75 | R.Ft | 700 | 100 | 83.13 | 0 | 3325 | C+S GST 18% I/P RD | 598.5 | 3923.5 | 3923.5 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1202 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 700 | 100 | 53.9 | 0 | 2156 | C+S GST 18% I/P RD | 388.08 | 2544.08 | 2544.08 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1302 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.08 | R.Ft | 750 | 100 | 57.75 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1401 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.44 | R.Ft | 750 | 100 | 102 | 0 | 4080 | C+S GST 18% I/P RD | 734.4 | 4814.4 | 4814.4 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1401 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.75 | R.Ft | 750 | 100 | 70.31 | 0 | 2812.5 | C+S GST 18% I/P RD | 506.26 | 3318.76 | 3318.76 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1301 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 6.33 | R.Ft | 750 | 100 | 118.69 | 0 | 4747.5 | C+S GST 18% I/P RD | 854.56 | 5602.06 | 5602.06 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1302 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.75 | R.Ft | 750 | 100 | 89.06 | 0 | 3562.5 | C+S GST 18% I/P RD | 641.26 | 4203.76 | 4203.76 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 758 | 92994 | 05 Jan 2022 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1895 | B 1401 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 6.33 | R.Ft | 750 | 100 | 118.69 | 0 | 4747.5 | C+S GST 18% I/P RD | 854.56 | 5602.06 | 5602.06 | Approved | 0 | 0 | 1060 | 05 Jan 2022
GANGA DHAM TOWERS | 145 | 92993 | 05 Jan 2022 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 1797 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 05 Jan 2022
GANGA DHAM TOWERS | 804 | 92992 | 05 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2000 | B 201 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 05 Jan 2022
GANGA DHAM TOWERS | 804 | 92992 | 05 Jan 2022 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 2000 | B 201 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1441.2 | Sq.Ft | 55 | 100 | 0 | 0 | 79266 | C+S GST 18% I/P RD | 14267.88 | 93533.88 | 93533.88 | Approved | 0 | 0 | 0 | 05 Jan 2022
GANGA DHAM TOWERS | 805 | 92991 | 05 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2117 | B 201 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 402 | 05 Jan 2022
GANGA DHAM TOWERS | 805 | 92991 | 05 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2117 | B 201 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1441.2 | Sq.Ft | 20 | 100 | 720.6 | 0 | 28824 | C+S GST 18% I/P RD | 5188.32 | 34012.32 | 34012.32 | Approved | 0 | 0 | 402 | 05 Jan 2022
GANGA DHAM TOWERS | 495 | 92990 | 05 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1851 | B 2401 Gypsum Plaster | Dhar Core (L) | 648.5 | R.Ft | 10 | 100 | 162.13 | 0 | 6485 | C+S GST 18% I/P RD | 1167.3 | 7652.3 | 7652.3 | Approved | 0 | 0 | 547 | 05 Jan 2022
GANGA DHAM TOWERS | 495 | 92990 | 05 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1851 | B 2501 Gypsum Plaster | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 547 | 05 Jan 2022
GANGA DHAM TOWERS | 495 | 92990 | 05 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1851 | B 2501 Gypsum Plaster | Gypsum on Wall (L) | 5658 | Sq.Ft | 4 | 100 | 565.8 | 0 | 22632 | C+S GST 18% I/P RD | 4073.76 | 26705.76 | 26705.76 | Approved | 0 | 0 | 547 | 05 Jan 2022
GANGA DHAM TOWERS | 495 | 92990 | 05 Jan 2022 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1851 | B 2401 Gypsum Plaster | Gypsum on Wall (L) | 4685 | Sq.Ft | 4 | 100 | 468.5 | 0 | 18740 | C+S GST 18% I/P RD | 3373.2 | 22113.2 | 22113.2 | Approved | 0 | 0 | 547 | 05 Jan 2022
GANGA DHAM TOWERS | 1197 | 92988 | 04 Jan 2022 |  | OPTION PRINT | OPTION PRINT | EV - 1616 | MEDIA PRINTING | Booklet Print | 500 | No. | 430 | 100 | 0 | 0 | 215000 | C+S GST 12% I/P RD | 25800 | 240800 | 240800 | Approved | 0 | 0 | 2750 | 04 Jan 2022
GANGA DHAM TOWERS | 1197 | 92988 | 04 Jan 2022 |  | OPTION PRINT | OPTION PRINT | EV - 1616 | MEDIA PRINTING | T SHIRT / BAGS / PENS / DRESS - BRANDING | 2000 | No. | 30 | 100 | 0 | 0 | 60000 | C+S GST 12% I/P RD | 7200 | 67200 | 67200 | Approved | 0 | 0 | 2750 | 04 Jan 2022
GANGA DHAM TOWERS | 187 | 92981 | 04 Jan 2022 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1890 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 460 | Sq.Ft | 1 | 100 | 11.5 | 0 | 460 | CGST 0% URD I/P | 0 | 460 | 460 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 740 | Sq.Ft | 1 | 100 | 18.5 | 0 | 740 | CGST 0% URD I/P | 0 | 740 | 740 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 100 | Sq.Ft | 1 | 100 | 2.5 | 0 | 100 | CGST 0% URD I/P | 0 | 100 | 100 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 8th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 6th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A-17th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 100 | Sq.Ft | 1 | 100 | 2.5 | 0 | 100 | CGST 0% URD I/P | 0 | 100 | 100 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1702 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 740 | Sq.Ft | 1 | 100 | 18.5 | 0 | 740 | CGST 0% URD I/P | 0 | 740 | 740 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A-14th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 78 | Sq.Ft | 1 | 100 | 1.95 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A-10th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 4th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 5th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A-15th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 9th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A-13th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A-11th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A-12th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 70 | Sq.Ft | 1 | 100 | 1.75 | 0 | 70 | CGST 0% URD I/P | 0 | 70 | 70 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A-16th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 2nd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 3rd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 7th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1701 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 611 | Sq.Ft | 1 | 100 | 15.28 | 0 | 611 | CGST 0% URD I/P | 0 | 611 | 611 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 62 | Sq.Ft | 1 | 100 | 1.55 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 11 | Sq.Ft | 1 | 100 | 0.28 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 9 | Sq.Ft | 1 | 100 | 0.23 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 75 | Sq.Ft | 1 | 100 | 1.88 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 47 | Sq.Ft | 1 | 100 | 1.18 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 1st floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 20 | Sq.Ft | 1 | 100 | 0.5 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 7 | Sq.Ft | 1 | 100 | 0.18 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 827 | 92974 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1999 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 8 | Sq.Ft | 1 | 100 | 0.2 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A-11th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 67 | Sq.Ft | 1 | 100 | 0 | 0 | 67 | CGST 0% URD I/P | 0 | 67 | 67 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 100 | Sq.Ft | 1 | 100 | 0 | 0 | 100 | CGST 0% URD I/P | 0 | 100 | 100 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 5th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1702 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 740 | Sq.Ft | 1 | 100 | 0 | 0 | 740 | CGST 0% URD I/P | 0 | 740 | 740 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1701 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 611 | Sq.Ft | 1 | 100 | 0 | 0 | 611 | CGST 0% URD I/P | 0 | 611 | 611 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 2nd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 7th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 744 | Sq.Ft | 1 | 100 | 0 | 0 | 744 | CGST 0% URD I/P | 0 | 744 | 744 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 6th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 8th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 66 | Sq.Ft | 1 | 100 | 0 | 0 | 66 | CGST 0% URD I/P | 0 | 66 | 66 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A-13th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A-10th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 3rd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A-14th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 4th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A-12th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 460 | Sq.Ft | 1 | 100 | 0 | 0 | 460 | CGST 0% URD I/P | 0 | 460 | 460 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 8 | Sq.Ft | 1 | 100 | 0 | 0 | 8 | CGST 0% URD I/P | 0 | 8 | 8 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 70 | Sq.Ft | 1 | 100 | 0 | 0 | 70 | CGST 0% URD I/P | 0 | 70 | 70 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A-15th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A-16th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A-17th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 110 | Sq.Ft | 1 | 100 | 0 | 0 | 110 | CGST 0% URD I/P | 0 | 110 | 110 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 7 | Sq.Ft | 1 | 100 | 0 | 0 | 7 | CGST 0% URD I/P | 0 | 7 | 7 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 9th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 62 | Sq.Ft | 1 | 100 | 0 | 0 | 62 | CGST 0% URD I/P | 0 | 62 | 62 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 9 | Sq.Ft | 1 | 100 | 0 | 0 | 9 | CGST 0% URD I/P | 0 | 9 | 9 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 75 | Sq.Ft | 1 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 78 | Sq.Ft | 1 | 100 | 0 | 0 | 78 | CGST 0% URD I/P | 0 | 78 | 78 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 47 | Sq.Ft | 1 | 100 | 0 | 0 | 47 | CGST 0% URD I/P | 0 | 47 | 47 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 11 | Sq.Ft | 1 | 100 | 0 | 0 | 11 | CGST 0% URD I/P | 0 | 11 | 11 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 828 | 92973 | 04 Jan 2022 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 1998 | A 1st floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 20 | Sq.Ft | 1 | 100 | 0 | 0 | 20 | CGST 0% URD I/P | 0 | 20 | 20 | Approved | 0 | 0 | 79 | 04 Jan 2022
GANGA DHAM TOWERS | 413 | 92971 | 04 Jan 2022 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1810 | Sales Oiifce Landscape Area . | Supervision Charges | 0.5 | Month | 4000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 04 Jan 2022
GANGA DHAM TOWERS | 745 | 92970 | 04 Jan 2022 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1893 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 29.0005 | Day | 451.61 | 100 | 0 | 0 | 13096.92 | C+S GST 18% I/P RD | 2357.44 | 15454.36 | 15454.36 | Approved | 0 | 0 | 131 | 04 Jan 2022
GANGA DHAM TOWERS | 480 | 92969 | 04 Jan 2022 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2021 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 31 | Day | 451.61 | 100 | 0 | 0 | 13999.91 | C+S GST 18% I/P RD | 2519.98 | 16519.89 | 16519.89 | Approved | 0 | 0 | 140 | 04 Jan 2022
GANGA DHAM TOWERS | 744 | 92966 | 04 Jan 2022 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 1738 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 6 | 04 Jan 2022
GANGA DHAM TOWERS | 1094 | 92965 | 04 Jan 2022 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1671 | C Pump Charges From (Spt 21 To Feb 22) | Pumping Charges-BC | 1200 | Cu.Mtrs | 190 | 100 | 5700 | 0 | 228000 | C+S GST 18% I/P RD | 41040 | 269040 | 269040 | Approved | 0 | 0 | 4560 | 04 Jan 2022
GANGA DHAM TOWERS | 1002 | 92946 | 03 Jan 2022 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1673 | A 2301 NOC | Concrete Cutting Work | 9.5238 | R.Ft | 525 | 100 | 125 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 75 | 03 Jan 2022
GANGA DHAM TOWERS | 1162 | 92945 | 03 Jan 2022 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 1807 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 03 Jan 2022
GANGA DHAM TOWERS | 1133 | 92944 | 03 Jan 2022 |  | BASSAPPA CHAVAN | BASSAPPA CHAVAN | EV - 1745 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Tractor Trip - Dld | 28 | No. | 800 | 100 | 0 | 0 | 22400 | CGST 0% URD I/P | 0 | 22400 | 22400 | Approved | 0 | 0 | 224 | 03 Jan 2022
GANGA DHAM TOWERS | 1228 | 92939 | 01 Jan 2022 |  | KIRAN TUKARAM DHANAWADE | DUROCRETE ENGINEERING SERVICES PVT LTD |  | R & D Purpose | R & D Purpose | 0.0796 | No. | 100000 | 100 | 0 | 0 | 7965 | C+S GST 18% I/P RD | 1433.7 | 9398.7 | 9398.7 |  | 0 | 0 | 159 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 1999.82 | C+S GST 18% I/P RD | 359.96 | 2359.78 | 2359.78 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 2000 | 8.33 | 0 | 0 | 2000.02 | C+S GST 18% I/P RD | 360 | 2360.02 | 2360.02 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 363 | 92935 | 01 Jan 2022 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 1690 | Weigh Bridge Maintenance | Stamping Charges | 1 | No. | 20500 | 100 | 0 | 0 | 20500 | C+S GST 18% I/P RD | 3690 | 24190 | 24190 | Approved | 0 | 0 | 445 | 01 Jan 2022
GANGA DHAM TOWERS | 272 | 92933 | 01 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2211 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 39.4737 | Sq.Ft | 152 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 360 | 01 Jan 2022
GANGA DHAM TOWERS | 272 | 92933 | 01 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2211 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 39.4737 | Sq.Ft | 152 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 360 | 01 Jan 2022
GANGA DHAM TOWERS | 272 | 92933 | 01 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2211 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 39.4737 | Sq.Ft | 152 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 360 | 01 Jan 2022
GANGA DHAM TOWERS | 272 | 92933 | 01 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2211 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.1517 | Sq.Ft | 161.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 360 | 01 Jan 2022
GANGA DHAM TOWERS | 272 | 92933 | 01 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2211 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.1517 | Sq.Ft | 161.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 360 | 01 Jan 2022
GANGA DHAM TOWERS | 272 | 92933 | 01 Jan 2022 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2211 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.1517 | Sq.Ft | 161.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 360 | 01 Jan 2022
GANGA DHAM TOWERS | 209 | 92909 | 30 Dec 2021 |  | UNIQUE ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1618 | A Bldg 1st RCC Slab (Stilt Floor) Built-up Area (L) | Hacking Work | 7200 | Sq.Ft | 5 | 100 | 900 | 0 | 36000 | CGST 0% URD I/P | 0 | 36000 | 36000 | Approved | 0 | 0 | 360 | 30 Dec 2021
GANGA DHAM TOWERS | 585 | 92908 | 30 Dec 2021 |  | SADGURU CONSTRO CARE | AJAY KUMAR GUPTA | EV - 1651 | A Podium 108 Level Expansion Joint | Expansion Joint (L) | 23.04 | Mtrs | 250 | 100 | 144 | 0 | 5760 | CGST 0% URD I/P | 0 | 5760 | 5760 | Approved | 0 | 0 | 58 | 30 Dec 2021
GANGA DHAM TOWERS | 584 | 92907 | 30 Dec 2021 |  | SADGURU CONSTRO CARE | AJAY KUMAR GUPTA | EV - 1652 | A Podium 108 Level Expansion Joint | Expansion Joint (M) | 28.16 | Mtrs | 1000 | 100 | 0 | 0 | 28160 | CGST 0% URD I/P | 0 | 28160 | 28160 | Approved | 0 | 0 | 282 | 30 Dec 2021
GANGA DHAM TOWERS | 697 | 92902 | 30 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2205 | D 601 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 212.2857 | Sq.Ft | 3.5 | 100 | 0 | 0 | 743 | C+S GST 18% I/P RD | 133.74 | 876.74 | 876.74 | Approved | 0 | 0 | 7 | 30 Dec 2021
GANGA DHAM TOWERS | 1074 | 92895 | 30 Dec 2021 |  | S.R.Enterprises | S.R.Enterprises | EV - 1800 | C Bldg Substructure Antitermite Treatment | Antitermite Treatment - BC] | 10306 | Sq.Ft | 4 | 100 | 0 | 0 | 41224 | C+S GST 18% I/P RD | 7420.32 | 48644.32 | 48644.32 | Approved | 0 | 0 | 412 | 30 Dec 2021
GANGA DHAM TOWERS | 1002 | 92894 | 29 Dec 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1672 | B 2402 NOC | Concrete Cutting Work | 6.6667 | R.Ft | 525 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 35 | 29 Dec 2021
GANGA DHAM TOWERS | 653 | 92886 | 29 Dec 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1817 | D 402 IPS Waterproofing | IPS W/P | 99.46 | Sq.Ft | 11 | 100 | 109.41 | 0 | 1094.06 | CGST 0% URD I/P | 0 | 1094.06 | 1094.06 | Approved | 0 | 0 | 68 | 29 Dec 2021
GANGA DHAM TOWERS | 653 | 92886 | 29 Dec 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1817 | D 304 IPS Waterproofing | IPS W/P | 69.67 | Sq.Ft | 11 | 100 | 76.64 | 0 | 766.37 | CGST 0% URD I/P | 0 | 766.37 | 766.37 | Approved | 0 | 0 | 68 | 29 Dec 2021
GANGA DHAM TOWERS | 653 | 92886 | 29 Dec 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1817 | D 302 IPS Waterproofing | IPS W/P | 99.46 | Sq.Ft | 11 | 100 | 109.41 | 0 | 1094.06 | CGST 0% URD I/P | 0 | 1094.06 | 1094.06 | Approved | 0 | 0 | 68 | 29 Dec 2021
GANGA DHAM TOWERS | 653 | 92886 | 29 Dec 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1817 | D 203 IPS Waterproofing | IPS W/P | 69.67 | Sq.Ft | 11 | 100 | 76.64 | 0 | 766.37 | CGST 0% URD I/P | 0 | 766.37 | 766.37 | Approved | 0 | 0 | 68 | 29 Dec 2021
GANGA DHAM TOWERS | 653 | 92886 | 29 Dec 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1817 | D 205 IPS Waterproofing | IPS W/P | 103.9 | Sq.Ft | 11 | 100 | 114.29 | 0 | 1142.9 | CGST 0% URD I/P | 0 | 1142.9 | 1142.9 | Approved | 0 | 0 | 68 | 29 Dec 2021
GANGA DHAM TOWERS | 653 | 92886 | 29 Dec 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1817 | D 501 IPS Waterproofing | IPS W/P | 103.9 | Sq.Ft | 11 | 100 | 114.29 | 0 | 1142.9 | CGST 0% URD I/P | 0 | 1142.9 | 1142.9 | Approved | 0 | 0 | 68 | 29 Dec 2021
GANGA DHAM TOWERS | 653 | 92886 | 29 Dec 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1817 | D 403 IPS Waterproofing | IPS W/P | 69.67 | Sq.Ft | 11 | 100 | 76.64 | 0 | 766.37 | CGST 0% URD I/P | 0 | 766.37 | 766.37 | Approved | 0 | 0 | 68 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 105 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 448.29 | Sq.Ft | 4 | 100 | 44.83 | 0 | 1793.16 | CGST 0% URD I/P | 0 | 1793.16 | 1793.16 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 301 Int. Terrace Soffit Gypsum Plaster | Gypsum on Ceiling (L) | 38.75 | Sq.Ft | 4 | 100 | 3.88 | 0 | 155 | CGST 0% URD I/P | 0 | 155 | 155 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 104 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 303 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 101 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 448.29 | Sq.Ft | 4 | 100 | 44.83 | 0 | 1793.16 | CGST 0% URD I/P | 0 | 1793.16 | 1793.16 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 305 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 448.29 | Sq.Ft | 4 | 100 | 44.83 | 0 | 1793.16 | CGST 0% URD I/P | 0 | 1793.16 | 1793.16 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 103 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 102 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | CGST 0% URD I/P | 0 | 1315.48 | 1315.48 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 698 | 92885 | 29 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1639 | D 204 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | CGST 0% URD I/P | 0 | 1301.24 | 1301.24 | Approved | 0 | 0 | 121 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | A P3 Floor External Sand Face Plaster | External Plaster- BC | 717 | Sq.Ft | 20 | 100 | 358.5 | 0 | 14340 | CGST 0% URD I/P | 0 | 14340 | 14340 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | B P1 Floor External Sand Face Plaster | External Plaster- BC | 1040 | Sq.Ft | 20 | 100 | 520 | 0 | 20800 | CGST 0% URD I/P | 0 | 20800 | 20800 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | B P1 Floor External Sand Face Plaster | External Plaster- BC | 1040 | Sq.Ft | 20 | 100 | 520 | 0 | 20800 | CGST 0% URD I/P | 0 | 20800 | 20800 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | A P2 Floor External Sand Face Plaster | External Plaster- BC | 1032 | Sq.Ft | 20 | 100 | 516 | 0 | 20640 | CGST 0% URD I/P | 0 | 20640 | 20640 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | A Ground Floor External Sand Face Plaster | External Plaster- BC | 330 | Sq.Ft | 20 | 100 | 165 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | B Podium Floor External Sand Face Plaster | External Plaster- BC | 993 | Sq.Ft | 20 | 100 | 496.5 | 0 | 19860 | CGST 0% URD I/P | 0 | 19860 | 19860 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | A Podium Floor External Sand Face Plaster | External Plaster- BC | 1958 | Sq.Ft | 20 | 100 | 979 | 0 | 39160 | CGST 0% URD I/P | 0 | 39160 | 39160 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | A P1 Floor External Sand Face Plaster | External Plaster- BC | 1024 | Sq.Ft | 20 | 100 | 512 | 0 | 20480 | CGST 0% URD I/P | 0 | 20480 | 20480 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | B Grond Floor External Sand Face Plaster | External Plaster- BC | 986 | Sq.Ft | 20 | 100 | 493 | 0 | 19720 | CGST 0% URD I/P | 0 | 19720 | 19720 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1184 | 92884 | 29 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1622 | B P3 Floor External Sand Face Plaster | External Plaster- BC | 545 | Sq.Ft | 20 | 100 | 272.5 | 0 | 10900 | CGST 0% URD I/P | 0 | 10900 | 10900 | Approved | 0 | 0 | 1933 | 29 Dec 2021
GANGA DHAM TOWERS | 1161 | 92879 | 28 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1621 | A Facade Scaffolding Fixing & Removing Work (304 Flat No) | Scaffolding & Removing | 1293 | Sq.Ft | 5 | 100 | 161.63 | 0 | 6465 | CGST 0% URD I/P | 0 | 6465 | 6465 | Approved | 0 | 0 | 65 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2001 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 60 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2203 Master Bed Marble Flooring | Italian Marble Champher & Polish | 23.445 | R.Ft | 60 | 100 | 35.17 | 0 | 1406.7 | C+S GST 18% I/P RD | 253.2 | 1659.9 | 1659.9 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2002 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 57.295 | R.Ft | 60 | 100 | 85.94 | 0 | 3437.7 | C+S GST 18% I/P RD | 618.78 | 4056.48 | 4056.48 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2103 Master Bed Marble Flooring | Italian Marble Champher & Polish | 23.445 | R.Ft | 60 | 100 | 35.17 | 0 | 1406.7 | C+S GST 18% I/P RD | 253.2 | 1659.9 | 1659.9 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2001 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 60 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1901 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 60 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2301 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 60 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2301 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 60 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1901 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 60 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1902 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 57.295 | R.Ft | 60 | 100 | 85.94 | 0 | 3437.7 | C+S GST 18% I/P RD | 618.78 | 4056.48 | 4056.48 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2002 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 24.835 | R.Ft | 60 | 100 | 37.25 | 0 | 1490.1 | C+S GST 18% I/P RD | 268.22 | 1758.32 | 1758.32 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2103 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 50.775 | R.Ft | 60 | 100 | 76.16 | 0 | 3046.5 | C+S GST 18% I/P RD | 548.38 | 3594.88 | 3594.88 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2203 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 20.835 | R.Ft | 60 | 100 | 31.25 | 0 | 1250.1 | C+S GST 18% I/P RD | 225.02 | 1475.12 | 1475.12 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2002 Master Bed Marble Flooring | Italian Marble Champher & Polish | 33.45 | R.Ft | 60 | 100 | 50.18 | 0 | 2007 | C+S GST 18% I/P RD | 361.26 | 2368.26 | 2368.26 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2203 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 50.775 | R.Ft | 60 | 100 | 76.16 | 0 | 3046.5 | C+S GST 18% I/P RD | 548.38 | 3594.88 | 3594.88 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1901 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 60 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1902 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 24.835 | R.Ft | 60 | 100 | 37.25 | 0 | 1490.1 | C+S GST 18% I/P RD | 268.22 | 1758.32 | 1758.32 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2001 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 60 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1902 Master Bed Marble Flooring | Italian Marble Champher & Polish | 33.45 | R.Ft | 60 | 100 | 50.18 | 0 | 2007 | C+S GST 18% I/P RD | 361.26 | 2368.26 | 2368.26 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2301 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 60 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 2103 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 20.835 | R.Ft | 60 | 100 | 31.25 | 0 | 1250.1 | C+S GST 18% I/P RD | 225.02 | 1475.12 | 1475.12 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1803 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 20.835 | R.Ft | 55 | 100 | 28.65 | 0 | 1145.93 | C+S GST 18% I/P RD | 206.26 | 1352.19 | 1352.19 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1804 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 21.49 | R.Ft | 55 | 100 | 29.55 | 0 | 1181.95 | C+S GST 18% I/P RD | 212.76 | 1394.71 | 1394.71 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1801 Master Bed Marble Flooring | Italian Marble Champher & Polish | 32.81 | R.Ft | 55 | 100 | 45.11 | 0 | 1804.55 | C+S GST 18% I/P RD | 324.82 | 2129.37 | 2129.37 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1804 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.13 | R.Ft | 55 | 100 | 79.93 | 0 | 3197.15 | C+S GST 18% I/P RD | 575.48 | 3772.63 | 3772.63 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1502 Master Bed Marble Flooring | Italian Marble Champher & Polish | 33.45 | R.Ft | 55 | 100 | 45.99 | 0 | 1839.75 | C+S GST 18% I/P RD | 331.16 | 2170.91 | 2170.91 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1804 Master Bed Marble Flooring | Italian Marble Champher & Polish | 28.71 | R.Ft | 55 | 100 | 39.48 | 0 | 1579.05 | C+S GST 18% I/P RD | 284.22 | 1863.27 | 1863.27 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1801 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 58.77 | R.Ft | 55 | 100 | 80.81 | 0 | 3232.35 | C+S GST 18% I/P RD | 581.82 | 3814.17 | 3814.17 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1502 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 57.295 | R.Ft | 55 | 100 | 78.78 | 0 | 3151.23 | C+S GST 18% I/P RD | 567.22 | 3718.45 | 3718.45 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1801 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 31.17 | R.Ft | 55 | 100 | 42.86 | 0 | 1714.35 | C+S GST 18% I/P RD | 308.58 | 2022.93 | 2022.93 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1803 Master Bed Marble Flooring | Italian Marble Champher & Polish | 23.445 | R.Ft | 55 | 100 | 32.24 | 0 | 1289.48 | C+S GST 18% I/P RD | 232.1 | 1521.58 | 1521.58 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 641 | 92878 | 28 Dec 2021 |  | R K INTERIOR | Kishan Enterprises | EV - 1627 | A 1803 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 50.775 | R.Ft | 55 | 100 | 69.82 | 0 | 2792.63 | C+S GST 18% I/P RD | 502.68 | 3295.31 | 3295.31 | Approved | 0 | 0 | 703 | 28 Dec 2021
GANGA DHAM TOWERS | 772 | 92877 | 28 Dec 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | JAY GANESH ENTERPRISES | EV - 1619 | B 1901 NOC | Rough Plaster- cc | 16.6667 | Sq.Ft | 12 | 100 | 5 | 0 | 200 | CGST 0% URD I/P | 0 | 200 | 200 | Approved | 0 | 0 | 61 | 28 Dec 2021
GANGA DHAM TOWERS | 772 | 92877 | 28 Dec 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | JAY GANESH ENTERPRISES | EV - 1619 | B 1901 NOC | Rough Plaster- cc | 154 | Sq.Ft | 12 | 100 | 46.2 | 0 | 1848 | CGST 0% URD I/P | 0 | 1848 | 1848 | Approved | 0 | 0 | 61 | 28 Dec 2021
GANGA DHAM TOWERS | 772 | 92877 | 28 Dec 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | JAY GANESH ENTERPRISES | EV - 1619 | B 1901 NOC | Rough Plaster- cc | 45.09 | Sq.Ft | 12 | 100 | 13.53 | 0 | 541.08 | CGST 0% URD I/P | 0 | 541.08 | 541.08 | Approved | 0 | 0 | 61 | 28 Dec 2021
GANGA DHAM TOWERS | 772 | 92877 | 28 Dec 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | JAY GANESH ENTERPRISES | EV - 1619 | B 1901 NOC | Rough Plaster- cc | 288.6 | Sq.Ft | 12 | 100 | 86.58 | 0 | 3463.2 | CGST 0% URD I/P | 0 | 3463.2 | 3463.2 | Approved | 0 | 0 | 61 | 28 Dec 2021
GANGA DHAM TOWERS | 1142 | 92875 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1629 | A 1901 NOC | Italian marble Skirting - BCo | 37 | R.Ft | 55 | 100 | 50.88 | 0 | 2035 | C+S GST 18% I/P RD | 366.3 | 2401.3 | 2401.3 | Approved | 0 | 0 | 20 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2002 Master Bed Marble Flooring | Italian marble Skirting - BCo | 53.52 | R.Ft | 60 | 100 | 80.28 | 0 | 3211.2 | C+S GST 18% I/P RD | 578.02 | 3789.22 | 3789.22 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2002 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 39.736 | R.Ft | 60 | 100 | 59.6 | 0 | 2384.16 | C+S GST 18% I/P RD | 429.14 | 2813.3 | 2813.3 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2301 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81 | R.Ft | 60 | 100 | 121.5 | 0 | 4860 | C+S GST 18% I/P RD | 874.8 | 5734.8 | 5734.8 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2301 Master Bed Marble Flooring | Italian marble Skirting - BCo | 52.496 | R.Ft | 60 | 100 | 78.74 | 0 | 3149.76 | C+S GST 18% I/P RD | 566.96 | 3716.72 | 3716.72 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2301 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 60 | 100 | 74.81 | 0 | 2992.32 | C+S GST 18% I/P RD | 538.62 | 3530.94 | 3530.94 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2002 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81 | R.Ft | 60 | 100 | 121.5 | 0 | 4860 | C+S GST 18% I/P RD | 874.8 | 5734.8 | 5734.8 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 1902 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 35 | R.Ft | 60 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 1901 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81 | R.Ft | 60 | 100 | 121.5 | 0 | 4860 | C+S GST 18% I/P RD | 874.8 | 5734.8 | 5734.8 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 1901 Master Bed Marble Flooring | Italian marble Skirting - BCo | 51.1836 | R.Ft | 60 | 100 | 76.78 | 0 | 3071.02 | C+S GST 18% I/P RD | 552.78 | 3623.8 | 3623.8 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2001 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81 | R.Ft | 60 | 100 | 121.5 | 0 | 4860 | C+S GST 18% I/P RD | 874.8 | 5734.8 | 5734.8 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2001 Master Bed Marble Flooring | Italian marble Skirting - BCo | 52.496 | R.Ft | 60 | 100 | 78.74 | 0 | 3149.76 | C+S GST 18% I/P RD | 566.96 | 3716.72 | 3716.72 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 2001 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 60 | 100 | 74.81 | 0 | 2992.32 | C+S GST 18% I/P RD | 538.62 | 3530.94 | 3530.94 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 1901 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 49.872 | R.Ft | 60 | 100 | 74.81 | 0 | 2992.32 | C+S GST 18% I/P RD | 538.62 | 3530.94 | 3530.94 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 502 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.583 | R.Ft | 650 | 100 | 41.97 | 0 | 1678.95 | C+S GST 18% I/P RD | 302.22 | 1981.17 | 1981.17 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 502 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.286 | R.Ft | 650 | 100 | 37.15 | 0 | 1485.9 | C+S GST 18% I/P RD | 267.46 | 1753.36 | 1753.36 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 401 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.655 | R.Ft | 650 | 100 | 43.14 | 0 | 1725.75 | C+S GST 18% I/P RD | 310.64 | 2036.39 | 2036.39 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 401 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 650 | 100 | 81.61 | 0 | 3264.3 | C+S GST 18% I/P RD | 587.58 | 3851.88 | 3851.88 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 401 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 3.123 | R.Ft | 650 | 100 | 50.75 | 0 | 2029.95 | C+S GST 18% I/P RD | 365.4 | 2395.35 | 2395.35 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 502 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.679 | R.Ft | 650 | 100 | 92.28 | 0 | 3691.35 | C+S GST 18% I/P RD | 664.44 | 4355.79 | 4355.79 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 537 | 92874 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1633 | A 502 Parents Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.571 | R.Ft | 650 | 100 | 90.53 | 0 | 3621.15 | C+S GST 18% I/P RD | 651.8 | 4272.95 | 4272.95 | Approved | 0 | 0 | 630 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 2203 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 33.336 | R.Ft | 60 | 100 | 50 | 0 | 2000.16 | C+S GST 18% I/P RD | 360.02 | 2360.18 | 2360.18 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 2103 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81.24 | R.Ft | 60 | 100 | 121.86 | 0 | 4874.4 | C+S GST 18% I/P RD | 877.4 | 5751.8 | 5751.8 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 2203 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81.24 | R.Ft | 60 | 100 | 121.86 | 0 | 4874.4 | C+S GST 18% I/P RD | 877.4 | 5751.8 | 5751.8 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 204 Granite Kitchen Otta | Granite Kitchen Otta BC | 19.6 | R.Ft | 300 | 100 | 147 | 0 | 5880 | C+S GST 18% I/P RD | 1058.4 | 6938.4 | 6938.4 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 1803 Master Bed Marble Flooring | Italian marble Skirting - BCo | 37.512 | R.Ft | 55 | 100 | 51.58 | 0 | 2063.16 | C+S GST 18% I/P RD | 371.36 | 2434.52 | 2434.52 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 1804 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 87.2 | R.Ft | 55 | 100 | 119.9 | 0 | 4796 | C+S GST 18% I/P RD | 863.28 | 5659.28 | 5659.28 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 1804 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 34.384 | R.Ft | 55 | 100 | 47.28 | 0 | 1891.12 | C+S GST 18% I/P RD | 340.4 | 2231.52 | 2231.52 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 1803 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 81.24 | R.Ft | 55 | 100 | 111.71 | 0 | 4468.2 | C+S GST 18% I/P RD | 804.28 | 5272.48 | 5272.48 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 1803 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 37.503 | R.Ft | 55 | 100 | 51.57 | 0 | 2062.67 | C+S GST 18% I/P RD | 371.28 | 2433.95 | 2433.95 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 1804 Master Bed Marble Flooring | Italian marble Skirting - BCo | 45.936 | R.Ft | 55 | 100 | 63.16 | 0 | 2526.48 | C+S GST 18% I/P RD | 454.76 | 2981.24 | 2981.24 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 2203 Master Bed Marble Flooring | Italian marble Skirting - BCo | 37.512 | R.Ft | 60 | 100 | 56.27 | 0 | 2250.72 | C+S GST 18% I/P RD | 405.12 | 2655.84 | 2655.84 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 2103 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 33.336 | R.Ft | 60 | 100 | 50 | 0 | 2000.16 | C+S GST 18% I/P RD | 360.02 | 2360.18 | 2360.18 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 2103 Master Bed Marble Flooring | Italian marble Skirting - BCo | 37.512 | R.Ft | 60 | 100 | 56.27 | 0 | 2250.72 | C+S GST 18% I/P RD | 405.12 | 2655.84 | 2655.84 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 503 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.869 | R.Ft | 650 | 100 | 79.12 | 0 | 3164.85 | C+S GST 18% I/P RD | 569.68 | 3734.53 | 3734.53 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 403 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.959 | R.Ft | 650 | 100 | 80.58 | 0 | 3223.35 | C+S GST 18% I/P RD | 580.2 | 3803.55 | 3803.55 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 403 Guest Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.545 | R.Ft | 650 | 100 | 73.86 | 0 | 2954.25 | C+S GST 18% I/P RD | 531.76 | 3486.01 | 3486.01 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 503 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.959 | R.Ft | 650 | 100 | 80.58 | 0 | 3223.35 | C+S GST 18% I/P RD | 580.2 | 3803.55 | 3803.55 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 503 Guest Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.545 | R.Ft | 650 | 100 | 73.86 | 0 | 2954.25 | C+S GST 18% I/P RD | 531.76 | 3486.01 | 3486.01 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 503 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 4.968 | R.Ft | 650 | 100 | 80.73 | 0 | 3229.2 | C+S GST 18% I/P RD | 581.26 | 3810.46 | 3810.46 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 551 | 92873 | 28 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1628 | A 404 Children Toilet Counter wash Basin | Italian Marble Counter - Mkt | 5.022 | R.Ft | 650 | 100 | 81.61 | 0 | 3264.3 | C+S GST 18% I/P RD | 587.58 | 3851.88 | 3851.88 | Approved | 0 | 0 | 640 | 28 Dec 2021
GANGA DHAM TOWERS | 1233 | 92872 | 28 Dec 2021 |  | KADAVATH VENKAT ENTERPRISES | JAY GANESH ENTERPRISES | EV - 1620 | B 1701 NOC | Blockwork 4" - BC | 289 | Sq.Ft | 18 | 100 | 130.05 | 0 | 5202 | C+S GST 18% I/P RD | 936.36 | 6138.36 | 6138.36 | Approved | 0 | 0 | 52 | 28 Dec 2021
GANGA DHAM TOWERS | 1001 | 92871 | 28 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1632 | A 1502 NOC | Italian marble Skirting - BCo | 50 | R.Ft | 55 | 100 | 0 | 0 | 2750 | C+S GST 18% I/P RD | 495 | 3245 | 3245 | Approved | 0 | 0 | 28 | 28 Dec 2021
GANGA DHAM TOWERS | 659 | 92869 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1674 | A 9th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 367 | Sq.Ft | 15 | 100 | 137.63 | 0 | 5505 | C+S GST 18% I/P RD | 990.9 | 6495.9 | 6495.9 | Approved | 0 | 0 | 385 | 28 Dec 2021
GANGA DHAM TOWERS | 659 | 92869 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1674 | A 5th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 367 | Sq.Ft | 15 | 100 | 137.63 | 0 | 5505 | C+S GST 18% I/P RD | 990.9 | 6495.9 | 6495.9 | Approved | 0 | 0 | 385 | 28 Dec 2021
GANGA DHAM TOWERS | 659 | 92869 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1674 | A 8th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 367 | Sq.Ft | 15 | 100 | 137.63 | 0 | 5505 | C+S GST 18% I/P RD | 990.9 | 6495.9 | 6495.9 | Approved | 0 | 0 | 385 | 28 Dec 2021
GANGA DHAM TOWERS | 659 | 92869 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1674 | A 4th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 367 | Sq.Ft | 15 | 100 | 137.63 | 0 | 5505 | C+S GST 18% I/P RD | 990.9 | 6495.9 | 6495.9 | Approved | 0 | 0 | 385 | 28 Dec 2021
GANGA DHAM TOWERS | 659 | 92869 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1674 | A 1st Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 367 | Sq.Ft | 15 | 100 | 137.63 | 0 | 5505 | C+S GST 18% I/P RD | 990.9 | 6495.9 | 6495.9 | Approved | 0 | 0 | 385 | 28 Dec 2021
GANGA DHAM TOWERS | 659 | 92869 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1674 | A 6th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 367 | Sq.Ft | 15 | 100 | 137.63 | 0 | 5505 | C+S GST 18% I/P RD | 990.9 | 6495.9 | 6495.9 | Approved | 0 | 0 | 385 | 28 Dec 2021
GANGA DHAM TOWERS | 659 | 92869 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1674 | A 7th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 367 | Sq.Ft | 15 | 100 | 137.63 | 0 | 5505 | C+S GST 18% I/P RD | 990.9 | 6495.9 | 6495.9 | Approved | 0 | 0 | 385 | 28 Dec 2021
GANGA DHAM TOWERS | 658 | 92868 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1897 | A 9th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 367 | Sq.Ft | 50 | 100 | 0 | 0 | 18350 | C+S GST 18% I/P RD | 3303 | 21653 | 21653 | Approved | 0 | 0 | 1285 | 28 Dec 2021
GANGA DHAM TOWERS | 658 | 92868 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1897 | A 4th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 367 | Sq.Ft | 50 | 100 | 0 | 0 | 18350 | C+S GST 18% I/P RD | 3303 | 21653 | 21653 | Approved | 0 | 0 | 1285 | 28 Dec 2021
GANGA DHAM TOWERS | 658 | 92868 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1897 | A 7th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 367 | Sq.Ft | 50 | 100 | 0 | 0 | 18350 | C+S GST 18% I/P RD | 3303 | 21653 | 21653 | Approved | 0 | 0 | 1285 | 28 Dec 2021
GANGA DHAM TOWERS | 658 | 92868 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1897 | A 6th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 367 | Sq.Ft | 50 | 100 | 0 | 0 | 18350 | C+S GST 18% I/P RD | 3303 | 21653 | 21653 | Approved | 0 | 0 | 1285 | 28 Dec 2021
GANGA DHAM TOWERS | 658 | 92868 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1897 | A 1st Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 367 | Sq.Ft | 50 | 100 | 0 | 0 | 18350 | C+S GST 18% I/P RD | 3303 | 21653 | 21653 | Approved | 0 | 0 | 1285 | 28 Dec 2021
GANGA DHAM TOWERS | 658 | 92868 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1897 | A 5th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 367 | Sq.Ft | 50 | 100 | 0 | 0 | 18350 | C+S GST 18% I/P RD | 3303 | 21653 | 21653 | Approved | 0 | 0 | 1285 | 28 Dec 2021
GANGA DHAM TOWERS | 658 | 92868 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1897 | A 8th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 367 | Sq.Ft | 50 | 100 | 0 | 0 | 18350 | C+S GST 18% I/P RD | 3303 | 21653 | 21653 | Approved | 0 | 0 | 1285 | 28 Dec 2021
GANGA DHAM TOWERS | 796 | 92867 | 28 Dec 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 2197 | D 2nd Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 18% I/P RD | 142.52 | 934.26 | 934.26 | Approved | 0 | 0 | 153 | 28 Dec 2021
GANGA DHAM TOWERS | 796 | 92867 | 28 Dec 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 2197 | D 5th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 18% I/P RD | 142.52 | 934.26 | 934.26 | Approved | 0 | 0 | 153 | 28 Dec 2021
GANGA DHAM TOWERS | 796 | 92867 | 28 Dec 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 2197 | D 3rd Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 18% I/P RD | 142.52 | 934.26 | 934.26 | Approved | 0 | 0 | 153 | 28 Dec 2021
GANGA DHAM TOWERS | 796 | 92867 | 28 Dec 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 2197 | D 1st Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 18% I/P RD | 142.52 | 934.26 | 934.26 | Approved | 0 | 0 | 153 | 28 Dec 2021
GANGA DHAM TOWERS | 796 | 92867 | 28 Dec 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 2197 | D 4th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (M) | 226.21 | Sq.Ft | 3.5 | 100 | 0 | 0 | 791.74 | C+S GST 18% I/P RD | 142.52 | 934.26 | 934.26 | Approved | 0 | 0 | 153 | 28 Dec 2021
GANGA DHAM TOWERS | 796 | 92867 | 28 Dec 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 2197 | D Main St.case Wall Gyp. Plaster 7th to 8th Fl. | Tikki Dhada (M) | 418.62 | Sq.Ft | 9 | 100 | 0 | 0 | 3767.58 | C+S GST 5% I/P RD | 188.38 | 3955.96 | 3955.96 | Approved | 0 | 0 | 153 | 28 Dec 2021
GANGA DHAM TOWERS | 796 | 92867 | 28 Dec 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 2197 | D Main St.case Wall Gyp. Plaster 8th to 9th Fl. | Tikki Dhada (M) | 418.62 | Sq.Ft | 9 | 100 | 0 | 0 | 3767.58 | C+S GST 5% I/P RD | 188.38 | 3955.96 | 3955.96 | Approved | 0 | 0 | 153 | 28 Dec 2021
GANGA DHAM TOWERS | 796 | 92867 | 28 Dec 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 2197 | D Main St.case Wall Gyp. Plaster 6th to 7th Fl. | Tikki Dhada (M) | 418.62 | Sq.Ft | 9 | 100 | 0 | 0 | 3767.58 | C+S GST 5% I/P RD | 188.38 | 3955.96 | 3955.96 | Approved | 0 | 0 | 153 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 501 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 502 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1151.05 | C+S GST 18% I/P RD | 207.18 | 1358.23 | 1358.23 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 202 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1151.05 | C+S GST 18% I/P RD | 207.18 | 1358.23 | 1358.23 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 404 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 401 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 105 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 278.5714 | Sq.Ft | 3.5 | 100 | 0 | 0 | 975 | C+S GST 18% I/P RD | 175.5 | 1150.5 | 1150.5 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 203 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 102 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1151.05 | C+S GST 18% I/P RD | 207.18 | 1358.23 | 1358.23 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 103 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 505 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 304 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 104 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 303 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 305 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 403 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 205 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 204 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 504 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 503 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 325.31 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1138.59 | C+S GST 18% I/P RD | 204.94 | 1343.53 | 1343.53 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 903 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792.91 | Sq.Ft | 9 | 100 | 0 | 0 | 7136.19 | C+S GST 18% I/P RD | 1284.52 | 8420.71 | 8420.71 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 905 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145.09 | Sq.Ft | 9 | 100 | 0 | 0 | 10305.81 | C+S GST 18% I/P RD | 1855.04 | 12160.85 | 12160.85 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 703 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792.91 | Sq.Ft | 9 | 100 | 0 | 0 | 7136.19 | C+S GST 18% I/P RD | 1284.52 | 8420.71 | 8420.71 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 904 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792.91 | Sq.Ft | 9 | 100 | 0 | 0 | 7136.19 | C+S GST 18% I/P RD | 1284.52 | 8420.71 | 8420.71 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 704 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792.91 | Sq.Ft | 9 | 100 | 0 | 0 | 7136.19 | C+S GST 18% I/P RD | 1284.52 | 8420.71 | 8420.71 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 705 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145.09 | Sq.Ft | 9 | 100 | 0 | 0 | 10305.81 | C+S GST 18% I/P RD | 1855.04 | 12160.85 | 12160.85 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 301 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 201 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 101 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 405 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 448.29 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1569.02 | C+S GST 18% I/P RD | 282.42 | 1851.44 | 1851.44 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 697 | 92866 | 28 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 2204 | D 302 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (M) | 328.87 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1151.05 | C+S GST 18% I/P RD | 207.18 | 1358.23 | 1358.23 | Approved | 0 | 0 | 802 | 28 Dec 2021
GANGA DHAM TOWERS | 1241 | 92861 | 27 Dec 2021 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2100 | Lt Substation Excavation & Backfilling work | Backfilling | 544.69 | Cu.Mtrs | 60 | 100 | 0 | 0 | 32681.4 | C+S GST 18% I/P RD | 5882.66 | 38564.06 | 38564.06 | Approved | 0 | 0 | 327 | 27 Dec 2021
GANGA DHAM TOWERS | 1242 | 92860 | 27 Dec 2021 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2127 | Lt Substation Excavation & Backfilling work | Excavation By Bucket (Shifting Inside) | 574.69 | Cu.Mtrs | 60 | 100 | 0 | 0 | 34481.4 | C+S GST 18% I/P RD | 6206.66 | 40688.06 | 40688.06 | Approved | 0 | 0 | 345 | 27 Dec 2021
GANGA DHAM TOWERS | 631 | 92857 | 27 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1806 | A 2102 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 244 | 27 Dec 2021
GANGA DHAM TOWERS | 631 | 92857 | 27 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1806 | A 2102 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 244 | 27 Dec 2021
GANGA DHAM TOWERS | 630 | 92856 | 27 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1954 | A 2102 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 670 | 27 Dec 2021
GANGA DHAM TOWERS | 630 | 92856 | 27 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1954 | A 2102 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 670 | 27 Dec 2021
GANGA DHAM TOWERS | 544 | 92855 | 27 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1675 | A 25th Floor Lobby Gypsum | Gypsum on Wall (L) | 700 | Sq.Ft | 4 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 56 | 27 Dec 2021
GANGA DHAM TOWERS | 544 | 92855 | 27 Dec 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1675 | A 24th Floor Lobby Gypsum | Gypsum on Wall (L) | 700 | Sq.Ft | 4 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 56 | 27 Dec 2021
GANGA DHAM TOWERS | 1002 | 92853 | 27 Dec 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1752 | B 2402 NOC | Concrete wall Crushing work | 1.54 | Cu.Mtrs | 7200 | 100 | 277.2 | 0 | 11088 | C+S GST 18% I/P RD | 1995.84 | 13083.84 | 13083.84 | Approved | 0 | 0 | 1912 | 27 Dec 2021
GANGA DHAM TOWERS | 1002 | 92853 | 27 Dec 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1752 | B 2402 NOC | Concrete Cutting Work | 161.021 | R.Ft | 525 | 100 | 2113.4 | 0 | 84536.01 | C+S GST 18% I/P RD | 15216.48 | 99752.49 | 99752.49 | Approved | 0 | 0 | 1912 | 27 Dec 2021
GANGA DHAM TOWERS | 1169 | 92852 | 27 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1739 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 65mm dia.(M) | 120.0001 | Mtrs | 952.4905 | 100 | 0 | 0 | 114299 | C+S GST 18% I/P RD | 20573.82 | 134872.82 | 134872.82 | Approved | 0 | 0 | 6648 | 27 Dec 2021
GANGA DHAM TOWERS | 1169 | 92852 | 27 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1739 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 40mm dia.(M) | 384 | Mtrs | 568 | 100 | 0 | 0 | 218112 | C+S GST 18% I/P RD | 39260.16 | 257372.16 | 257372.16 | Approved | 0 | 0 | 6648 | 27 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1003 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 12.5048 | Mtrs | 105 | 100 | 0 | 0 | 1313 | C+S GST 18% I/P RD | 236.34 | 1549.34 | 1549.34 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 703 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 16 | Mtrs | 105 | 100 | 0 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 504 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 14.4 | Mtrs | 105 | 100 | 0 | 0 | 1512 | C+S GST 18% I/P RD | 272.16 | 1784.16 | 1784.16 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1002 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 18.6 | Mtrs | 105 | 100 | 0 | 0 | 1953 | C+S GST 18% I/P RD | 351.54 | 2304.54 | 2304.54 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 904 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 24.7048 | Mtrs | 105 | 100 | 0 | 0 | 2594 | C+S GST 18% I/P RD | 466.92 | 3060.92 | 3060.92 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1603 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 6.4 | Mtrs | 105 | 100 | 0 | 0 | 672 | C+S GST 18% I/P RD | 120.96 | 792.96 | 792.96 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 20.4 | Mtrs | 105 | 100 | 0 | 0 | 2142 | C+S GST 18% I/P RD | 385.56 | 2527.56 | 2527.56 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 304 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 16.2 | Mtrs | 105 | 100 | 0 | 0 | 1701 | C+S GST 18% I/P RD | 306.18 | 2007.18 | 2007.18 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 14 | Mtrs | 105 | 100 | 0 | 0 | 1470 | C+S GST 18% I/P RD | 264.6 | 1734.6 | 1734.6 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 302 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 14 | Mtrs | 105 | 100 | 0 | 0 | 1470 | C+S GST 18% I/P RD | 264.6 | 1734.6 | 1734.6 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1604 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 35.6 | Mtrs | 105 | 100 | 0 | 0 | 3738 | C+S GST 18% I/P RD | 672.84 | 4410.84 | 4410.84 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 203 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 31 | Mtrs | 105 | 100 | 0 | 0 | 3255 | C+S GST 18% I/P RD | 585.9 | 3840.9 | 3840.9 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 704 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 17.6 | Mtrs | 105 | 100 | 0 | 0 | 1848 | C+S GST 18% I/P RD | 332.64 | 2180.64 | 2180.64 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 802 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 23 | Mtrs | 105 | 100 | 0 | 0 | 2415 | C+S GST 18% I/P RD | 434.7 | 2849.7 | 2849.7 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 1 | Mtrs | 105 | 100 | 0 | 0 | 105 | C+S GST 18% I/P RD | 18.9 | 123.9 | 123.9 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 301 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 24.8 | Mtrs | 105 | 100 | 0 | 0 | 2604 | C+S GST 18% I/P RD | 468.72 | 3072.72 | 3072.72 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 503 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 21.1048 | Mtrs | 105 | 100 | 0 | 0 | 2216 | C+S GST 18% I/P RD | 398.88 | 2614.88 | 2614.88 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 701 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 5.9048 | Mtrs | 105 | 100 | 0 | 0 | 620 | C+S GST 18% I/P RD | 111.6 | 731.6 | 731.6 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 703 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 14.8095 | Mtrs | 21 | 100 | 0 | 0 | 311 | C+S GST 18% I/P RD | 55.98 | 366.98 | 366.98 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 203 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18 | Mtrs | 21 | 100 | 0 | 0 | 378 | C+S GST 18% I/P RD | 68.04 | 446.04 | 446.04 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 304 AC Installation & Commissioning - 1 No. | Table Top Stand with Fastner (L) | 5 | No. | 187.5 | 100 | 0 | 0 | 937.5 | C+S GST 18% I/P RD | 168.76 | 1106.26 | 1106.26 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 304 AC Installation & Commissioning - 1 No. | Nitrogen Pressure & Leak Testing (L) | 6 | No. | 15 | 100 | 0 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 504 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 13 | Mtrs | 21 | 100 | 0 | 0 | 273 | C+S GST 18% I/P RD | 49.14 | 322.14 | 322.14 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 704 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18.5238 | Mtrs | 21 | 100 | 0 | 0 | 389 | C+S GST 18% I/P RD | 70.02 | 459.02 | 459.02 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1603 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 2.9048 | Mtrs | 21 | 100 | 0 | 0 | 61 | C+S GST 18% I/P RD | 10.98 | 71.98 | 71.98 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 802 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 15.619 | Mtrs | 21 | 100 | 0 | 0 | 328 | C+S GST 18% I/P RD | 59.04 | 387.04 | 387.04 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 301 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 13.9524 | Mtrs | 21 | 100 | 0 | 0 | 293 | C+S GST 18% I/P RD | 52.74 | 345.74 | 345.74 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1701 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 4.619 | Mtrs | 21 | 100 | 0 | 0 | 97 | C+S GST 18% I/P RD | 17.46 | 114.46 | 114.46 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1003 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 10.9524 | Mtrs | 21 | 100 | 0 | 0 | 230 | C+S GST 18% I/P RD | 41.4 | 271.4 | 271.4 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 503 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 15.0952 | Mtrs | 21 | 100 | 0 | 0 | 317 | C+S GST 18% I/P RD | 57.06 | 374.06 | 374.06 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1001 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 4.1905 | Mtrs | 21 | 100 | 0 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 8.619 | Mtrs | 21 | 100 | 0 | 0 | 181 | C+S GST 18% I/P RD | 32.58 | 213.58 | 213.58 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1604 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 23.8095 | Mtrs | 21 | 100 | 0 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 701 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 12.4762 | Mtrs | 21 | 100 | 0 | 0 | 262 | C+S GST 18% I/P RD | 47.16 | 309.16 | 309.16 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18.7143 | Mtrs | 21 | 100 | 0 | 0 | 393 | C+S GST 18% I/P RD | 70.74 | 463.74 | 463.74 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 304 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 17.5238 | Mtrs | 21 | 100 | 0 | 0 | 368 | C+S GST 18% I/P RD | 66.24 | 434.24 | 434.24 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 904 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 19.619 | Mtrs | 21 | 100 | 0 | 0 | 412 | C+S GST 18% I/P RD | 74.16 | 486.16 | 486.16 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 302 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 10.619 | Mtrs | 21 | 100 | 0 | 0 | 223 | C+S GST 18% I/P RD | 40.14 | 263.14 | 263.14 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1002 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 12 | Mtrs | 21 | 100 | 0 | 0 | 252 | C+S GST 18% I/P RD | 45.36 | 297.36 | 297.36 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1601 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 10.1905 | Mtrs | 21 | 100 | 0 | 0 | 214 | C+S GST 18% I/P RD | 38.52 | 252.52 | 252.52 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 304 AC Installation & Commissioning - 1 No. | L type Stand with Fastener (L) | 1 | No. | 157.5 | 100 | 0 | 0 | 157.5 | C+S GST 18% I/P RD | 28.36 | 185.86 | 185.86 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1604 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 43.5897 | Mtrs | 19.5 | 100 | 0 | 0 | 850 | C+S GST 18% I/P RD | 153 | 1003 | 1003 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 704 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 17.8974 | Mtrs | 19.5 | 100 | 0 | 0 | 349 | C+S GST 18% I/P RD | 62.82 | 411.82 | 411.82 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 904 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 28.4103 | Mtrs | 19.5 | 100 | 0 | 0 | 554 | C+S GST 18% I/P RD | 99.72 | 653.72 | 653.72 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 203 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 32.9231 | Mtrs | 19.5 | 100 | 0 | 0 | 642 | C+S GST 18% I/P RD | 115.56 | 757.56 | 757.56 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 302 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 14.3077 | Mtrs | 19.5 | 100 | 0 | 0 | 279 | C+S GST 18% I/P RD | 50.22 | 329.22 | 329.22 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1003 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 14.7692 | Mtrs | 19.5 | 100 | 0 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 19.2821 | Mtrs | 19.5 | 100 | 0 | 0 | 376 | C+S GST 18% I/P RD | 67.68 | 443.68 | 443.68 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 16 | Mtrs | 19.5 | 100 | 0 | 0 | 312 | C+S GST 18% I/P RD | 56.16 | 368.16 | 368.16 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1601 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 49.0769 | Mtrs | 19.5 | 100 | 0 | 0 | 957 | C+S GST 18% I/P RD | 172.26 | 1129.26 | 1129.26 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 32.4103 | Mtrs | 19.5 | 100 | 0 | 0 | 632 | C+S GST 18% I/P RD | 113.76 | 745.76 | 745.76 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1002 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 20.8205 | Mtrs | 19.5 | 100 | 0 | 0 | 406 | C+S GST 18% I/P RD | 73.08 | 479.08 | 479.08 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1702 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 0.8205 | Mtrs | 19.5 | 100 | 0 | 0 | 16 | C+S GST 18% I/P RD | 2.88 | 18.88 | 18.88 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 503 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 19.1795 | Mtrs | 19.5 | 100 | 0 | 0 | 374 | C+S GST 18% I/P RD | 67.32 | 441.32 | 441.32 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 802 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 23.9487 | Mtrs | 19.5 | 100 | 0 | 0 | 467 | C+S GST 18% I/P RD | 84.06 | 551.06 | 551.06 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1603 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 7.2821 | Mtrs | 19.5 | 100 | 0 | 0 | 142 | C+S GST 18% I/P RD | 25.56 | 167.56 | 167.56 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1602 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 8 | Mtrs | 19.5 | 100 | 0 | 0 | 156 | C+S GST 18% I/P RD | 28.08 | 184.08 | 184.08 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 1701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 3.2821 | Mtrs | 19.5 | 100 | 0 | 0 | 64 | C+S GST 18% I/P RD | 11.52 | 75.52 | 75.52 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 301 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 28.9231 | Mtrs | 19.5 | 100 | 0 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 703 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 18.7179 | Mtrs | 19.5 | 100 | 0 | 0 | 365 | C+S GST 18% I/P RD | 65.7 | 430.7 | 430.7 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 532 | 92821 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1609 | A 504 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 18 | Mtrs | 19.5 | 100 | 0 | 0 | 351 | C+S GST 18% I/P RD | 63.18 | 414.18 | 414.18 | Approved | 0 | 0 | 964 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 704 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 20.3913 | Mtrs | 345 | 100 | 0 | 0 | 7035 | C+S GST 18% I/P RD | 1266.3 | 8301.3 | 8301.3 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 304 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 3.398 | Mtrs | 345 | 100 | 0 | 0 | 1172.31 | C+S GST 18% I/P RD | 211.02 | 1383.33 | 1383.33 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 703 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 14.6 | Mtrs | 345 | 100 | 0 | 0 | 5037 | C+S GST 18% I/P RD | 906.66 | 5943.66 | 5943.66 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 302 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 10.5 | Mtrs | 345 | 100 | 0 | 0 | 3622.5 | C+S GST 18% I/P RD | 652.06 | 4274.56 | 4274.56 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 20.4 | Mtrs | 345 | 100 | 0 | 0 | 7038 | C+S GST 18% I/P RD | 1266.84 | 8304.84 | 8304.84 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 301 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 13.9 | Mtrs | 345 | 100 | 0 | 0 | 4795.5 | C+S GST 18% I/P RD | 863.2 | 5658.7 | 5658.7 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 802 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 23 | Mtrs | 345 | 100 | 0 | 0 | 7935 | C+S GST 18% I/P RD | 1428.3 | 9363.3 | 9363.3 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 203 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 27.6 | Mtrs | 345 | 100 | 0 | 0 | 9522 | C+S GST 18% I/P RD | 1713.96 | 11235.96 | 11235.96 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 302 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 1.7143 | Mtrs | 49 | 100 | 0 | 0 | 84 | C+S GST 18% I/P RD | 15.12 | 99.12 | 99.12 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 704 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.7959 | Mtrs | 49 | 100 | 0 | 0 | 1068 | C+S GST 18% I/P RD | 192.24 | 1260.24 | 1260.24 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1701 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 304 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 14.1837 | Mtrs | 49 | 100 | 0 | 0 | 695 | C+S GST 18% I/P RD | 125.1 | 820.1 | 820.1 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 8.6939 | Mtrs | 49 | 100 | 0 | 0 | 426 | C+S GST 18% I/P RD | 76.68 | 502.68 | 502.68 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 301 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 6.5918 | Mtrs | 49 | 100 | 0 | 0 | 323 | C+S GST 18% I/P RD | 58.14 | 381.14 | 381.14 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1604 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 23.7959 | Mtrs | 49 | 100 | 0 | 0 | 1166 | C+S GST 18% I/P RD | 209.88 | 1375.88 | 1375.88 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1003 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 14.2975 | Mtrs | 60.5 | 100 | 0 | 0 | 865 | C+S GST 18% I/P RD | 155.7 | 1020.7 | 1020.7 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 904 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 28.4132 | Mtrs | 60.5 | 100 | 0 | 0 | 1719 | C+S GST 18% I/P RD | 309.42 | 2028.42 | 2028.42 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1002 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 22.7934 | Mtrs | 60.5 | 100 | 0 | 0 | 1379 | C+S GST 18% I/P RD | 248.22 | 1627.22 | 1627.22 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 301 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 9.9033 | Mtrs | 60.5 | 100 | 0 | 0 | 599.15 | C+S GST 18% I/P RD | 107.84 | 706.99 | 706.99 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1604 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 43.6033 | Mtrs | 60.5 | 100 | 0 | 0 | 2638 | C+S GST 18% I/P RD | 474.84 | 3112.84 | 3112.84 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 203 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 32.8926 | Mtrs | 60.5 | 100 | 0 | 0 | 1990 | C+S GST 18% I/P RD | 358.2 | 2348.2 | 2348.2 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1603 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 7.8017 | Mtrs | 60.5 | 100 | 0 | 0 | 472 | C+S GST 18% I/P RD | 84.96 | 556.96 | 556.96 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 503 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 19.0083 | Mtrs | 60.5 | 100 | 0 | 0 | 1150 | C+S GST 18% I/P RD | 207 | 1357 | 1357 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 1.4876 | Mtrs | 60.5 | 100 | 0 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 302 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 6.4088 | Mtrs | 60.5 | 100 | 0 | 0 | 387.73 | C+S GST 18% I/P RD | 69.8 | 457.53 | 457.53 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 3.0083 | Mtrs | 60.5 | 100 | 0 | 0 | 182 | C+S GST 18% I/P RD | 32.76 | 214.76 | 214.76 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1601 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 49.1074 | Mtrs | 60.5 | 100 | 0 | 0 | 2971 | C+S GST 18% I/P RD | 534.78 | 3505.78 | 3505.78 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 504 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 18 | Mtrs | 60.5 | 100 | 0 | 0 | 1089 | C+S GST 18% I/P RD | 196.02 | 1285.02 | 1285.02 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 703 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 16.2975 | Mtrs | 60.5 | 100 | 0 | 0 | 986 | C+S GST 18% I/P RD | 177.48 | 1163.48 | 1163.48 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 11.3719 | Mtrs | 60.5 | 100 | 0 | 0 | 688 | C+S GST 18% I/P RD | 123.84 | 811.84 | 811.84 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1602 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 8 | Mtrs | 60.5 | 100 | 0 | 0 | 484 | C+S GST 18% I/P RD | 87.12 | 571.12 | 571.12 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1603 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 6.4 | Mtrs | 345 | 100 | 0 | 0 | 2208 | C+S GST 18% I/P RD | 397.44 | 2605.44 | 2605.44 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1003 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 14.8 | Mtrs | 345 | 100 | 0 | 0 | 5106 | C+S GST 18% I/P RD | 919.08 | 6025.08 | 6025.08 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 504 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 14.4 | Mtrs | 345 | 100 | 0 | 0 | 4968 | C+S GST 18% I/P RD | 894.24 | 5862.24 | 5862.24 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 303 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 8.6 | Mtrs | 345 | 100 | 0 | 0 | 2967 | C+S GST 18% I/P RD | 534.06 | 3501.06 | 3501.06 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 26 | Mtrs | 345 | 100 | 0 | 0 | 8970 | C+S GST 18% I/P RD | 1614.6 | 10584.6 | 10584.6 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1002 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 20 | Mtrs | 345 | 100 | 0 | 0 | 6900 | C+S GST 18% I/P RD | 1242 | 8142 | 8142 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1604 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 35.6 | Mtrs | 345 | 100 | 0 | 0 | 12282 | C+S GST 18% I/P RD | 2210.76 | 14492.76 | 14492.76 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 503 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 21.1014 | Mtrs | 345 | 100 | 0 | 0 | 7280 | C+S GST 18% I/P RD | 1310.4 | 8590.4 | 8590.4 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 14 | Mtrs | 345 | 100 | 0 | 0 | 4830 | C+S GST 18% I/P RD | 869.4 | 5699.4 | 5699.4 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 904 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 24.7014 | Mtrs | 345 | 100 | 0 | 0 | 8522 | C+S GST 18% I/P RD | 1533.96 | 10055.96 | 10055.96 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 701 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 5.7014 | Mtrs | 345 | 100 | 0 | 0 | 1967 | C+S GST 18% I/P RD | 354.06 | 2321.06 | 2321.06 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 304 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 4.6033 | Mtrs | 60.5 | 100 | 0 | 0 | 278.5 | C+S GST 18% I/P RD | 50.14 | 328.64 | 328.64 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 704 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 13.2727 | Mtrs | 60.5 | 100 | 0 | 0 | 803 | C+S GST 18% I/P RD | 144.54 | 947.54 | 947.54 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 802 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 25.9008 | Mtrs | 60.5 | 100 | 0 | 0 | 1567 | C+S GST 18% I/P RD | 282.06 | 1849.06 | 1849.06 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 16 | Mtrs | 60.5 | 100 | 0 | 0 | 968 | C+S GST 18% I/P RD | 174.24 | 1142.24 | 1142.24 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 303 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 8.5022 | Mtrs | 60.5 | 100 | 0 | 0 | 514.38 | C+S GST 18% I/P RD | 92.58 | 606.96 | 606.96 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 304 AC Installation & Commissioning - 1 No. | Nitrogen Pressure & Leak Testing (M) | 6 | No. | 35 | 100 | 0 | 0 | 210 | C+S GST 18% I/P RD | 37.8 | 247.8 | 247.8 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1003 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 12.5102 | Mtrs | 49 | 100 | 0 | 0 | 613 | C+S GST 18% I/P RD | 110.34 | 723.34 | 723.34 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1001 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 4.1837 | Mtrs | 49 | 100 | 0 | 0 | 205 | C+S GST 18% I/P RD | 36.9 | 241.9 | 241.9 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1002 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 13.7959 | Mtrs | 49 | 100 | 0 | 0 | 676 | C+S GST 18% I/P RD | 121.68 | 797.68 | 797.68 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 904 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 19.898 | Mtrs | 49 | 100 | 0 | 0 | 975 | C+S GST 18% I/P RD | 175.5 | 1150.5 | 1150.5 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 504 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 13 | Mtrs | 49 | 100 | 0 | 0 | 637 | C+S GST 18% I/P RD | 114.66 | 751.66 | 751.66 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 503 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 15.2041 | Mtrs | 49 | 100 | 0 | 0 | 745 | C+S GST 18% I/P RD | 134.1 | 879.1 | 879.1 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1603 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 2.9592 | Mtrs | 49 | 100 | 0 | 0 | 145 | C+S GST 18% I/P RD | 26.1 | 171.1 | 171.1 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 13.1837 | Mtrs | 49 | 100 | 0 | 0 | 646 | C+S GST 18% I/P RD | 116.28 | 762.28 | 762.28 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 203 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 18 | Mtrs | 49 | 100 | 0 | 0 | 882 | C+S GST 18% I/P RD | 158.76 | 1040.76 | 1040.76 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 1601 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 10.2041 | Mtrs | 49 | 100 | 0 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 703 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 15.898 | Mtrs | 49 | 100 | 0 | 0 | 779 | C+S GST 18% I/P RD | 140.22 | 919.22 | 919.22 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 802 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 15.6939 | Mtrs | 49 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 304 AC Installation & Commissioning - 1 No. | Table Top Stand with Fastner (M) | 5 | No. | 537.5 | 100 | 0 | 0 | 2687.5 | C+S GST 18% I/P RD | 483.76 | 3171.26 | 3171.26 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 530 | 92820 | 24 Dec 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1608 | A 304 AC Installation & Commissioning - 1 No. | L type Stand with Fastener (M) | 1 | No. | 467.5 | 100 | 0 | 0 | 467.5 | C+S GST 18% I/P RD | 84.16 | 551.66 | 551.66 | Approved | 0 | 0 | 2995 | 24 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 703 Kitchen dado | L Groove - BCV | 13.45 | R.Ft | 20 | 100 | 6.73 | 0 | 269 | C+S GST 18% I/P RD | 48.42 | 317.42 | 317.42 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 403 Kitchen dado | L Groove - BCV | 13.45 | R.Ft | 20 | 100 | 6.73 | 0 | 269 | C+S GST 18% I/P RD | 48.42 | 317.42 | 317.42 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 703 Kitchen dado | Dado BC | 60.16 | Sq.Ft | 18 | 100 | 27.07 | 0 | 1082.88 | C+S GST 18% I/P RD | 194.92 | 1277.8 | 1277.8 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 1003 Kitchen dado | Dado BC | 60.16 | Sq.Ft | 18 | 100 | 27.07 | 0 | 1082.88 | C+S GST 18% I/P RD | 194.92 | 1277.8 | 1277.8 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 1003 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.3015 | R.Ft | 325 | 100 | 132.45 | 0 | 5298 | C+S GST 18% I/P RD | 953.64 | 6251.64 | 6251.64 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 1003 Kitchen dado | L Groove - BCV | 13.45 | R.Ft | 20 | 100 | 6.73 | 0 | 269 | C+S GST 18% I/P RD | 48.42 | 317.42 | 317.42 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 404 Kitchen dado | L Groove - BCV | 15.42 | R.Ft | 20 | 100 | 7.71 | 0 | 308.4 | C+S GST 18% I/P RD | 55.52 | 363.92 | 363.92 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 403 Kitchen dado | Dado BC | 60.16 | Sq.Ft | 14 | 100 | 21.06 | 0 | 842.24 | C+S GST 18% I/P RD | 151.6 | 993.84 | 993.84 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 551 | 92802 | 22 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1630 | A 404 Kitchen dado | Dado BC | 65.25 | Sq.Ft | 14 | 100 | 22.84 | 0 | 913.5 | C+S GST 18% I/P RD | 164.44 | 1077.94 | 1077.94 | Approved | 0 | 0 | 103 | 22 Dec 2021
GANGA DHAM TOWERS | 537 | 92801 | 22 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 401 Granite Kitchen Otta | Granite Kitchen Otta BC | 13.68 | R.Ft | 300 | 100 | 102.6 | 0 | 4104 | C+S GST 18% I/P RD | 738.72 | 4842.72 | 4842.72 | Approved | 0 | 0 | 127 | 22 Dec 2021
GANGA DHAM TOWERS | 537 | 92801 | 22 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 202 Kitchen dado | Dado BC | 47.51 | Sq.Ft | 14 | 100 | 16.63 | 0 | 665.14 | C+S GST 18% I/P RD | 119.72 | 784.86 | 784.86 | Approved | 0 | 0 | 127 | 22 Dec 2021
GANGA DHAM TOWERS | 537 | 92801 | 22 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 602 Kitchen dado | Dado BC | 47.51 | Sq.Ft | 14 | 100 | 16.63 | 0 | 665.14 | C+S GST 18% I/P RD | 119.72 | 784.86 | 784.86 | Approved | 0 | 0 | 127 | 22 Dec 2021
GANGA DHAM TOWERS | 537 | 92801 | 22 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 1002 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.96 | R.Ft | 325 | 100 | 137.8 | 0 | 5512 | C+S GST 18% I/P RD | 992.16 | 6504.16 | 6504.16 | Approved | 0 | 0 | 127 | 22 Dec 2021
GANGA DHAM TOWERS | 537 | 92801 | 22 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 202 Kitchen dado | L Groove - BCV | 15.42 | R.Ft | 20 | 100 | 7.71 | 0 | 308.4 | C+S GST 18% I/P RD | 55.52 | 363.92 | 363.92 | Approved | 0 | 0 | 127 | 22 Dec 2021
GANGA DHAM TOWERS | 537 | 92801 | 22 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 902 Kitchen dado | L Groove - BCV | 15.42 | R.Ft | 20 | 100 | 7.71 | 0 | 308.4 | C+S GST 18% I/P RD | 55.52 | 363.92 | 363.92 | Approved | 0 | 0 | 127 | 22 Dec 2021
GANGA DHAM TOWERS | 537 | 92801 | 22 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 602 Kitchen dado | L Groove - BCV | 15.42 | R.Ft | 20 | 100 | 7.71 | 0 | 308.4 | C+S GST 18% I/P RD | 55.52 | 363.92 | 363.92 | Approved | 0 | 0 | 127 | 22 Dec 2021
GANGA DHAM TOWERS | 537 | 92801 | 22 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1631 | A 902 Kitchen dado | Dado BC | 47.51 | Sq.Ft | 18 | 100 | 21.38 | 0 | 855.18 | C+S GST 18% I/P RD | 153.94 | 1009.12 | 1009.12 | Approved | 0 | 0 | 127 | 22 Dec 2021
GANGA DHAM TOWERS | 985 | 92800 | 22 Dec 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 |  | 0 | 0 | 42 | 22 Dec 2021
GANGA DHAM TOWERS | 985 | 92799 | 22 Dec 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 |  | 0 | 0 | 42 | 22 Dec 2021
GANGA DHAM TOWERS | 985 | 92798 | 22 Dec 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 |  | 0 | 0 | 42 | 22 Dec 2021
GANGA DHAM TOWERS | 985 | 92797 | 22 Dec 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION |  | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 |  | 0 | 0 | 42 | 22 Dec 2021
GANGA DHAM TOWERS | 1214 | 92791 | 21 Dec 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1644 | Tower-A Parking Painting work of Ceiling (L) | Putty with Touchup | 4680 | Sq.Ft | 0.25 | 100 | 29.25 | 0 | 1170 | IGST 18% I/P RD | 210.6 | 1380.6 | 1380.6 | Approved | 0 | 0 | 103 | 21 Dec 2021
GANGA DHAM TOWERS | 1214 | 92791 | 21 Dec 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1644 | Tower-A Parking Painting work of Ceiling (L) | Putty with Touchup | 5980 | Sq.Ft | 0.25 | 100 | 37.38 | 0 | 1495 | IGST 18% I/P RD | 269.1 | 1764.1 | 1764.1 | Approved | 0 | 0 | 103 | 21 Dec 2021
GANGA DHAM TOWERS | 1214 | 92791 | 21 Dec 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1644 | Tower-A Parking Painting work of Ceiling (L) | Primer First Coat | 10158.6667 | Sq.Ft | 0.75 | 100 | 190.48 | 0 | 7619 | IGST 18% I/P RD | 1371.42 | 8990.42 | 8990.42 | Approved | 0 | 0 | 103 | 21 Dec 2021
GANGA DHAM TOWERS | 773 | 92790 | 21 Dec 2021 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 1634 | B P1 Parking chemical grouting | Chemical Grouting (L) | 1095 | Sq.Ft | 1 | 100 | 27.38 | 0 | 1095 | C+S GST 18% I/P RD | 197.1 | 1292.1 | 1292.1 | Approved | 0 | 0 | 22 | 21 Dec 2021
GANGA DHAM TOWERS | 773 | 92790 | 21 Dec 2021 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 1634 | B P1 Parking chemical grouting | Ghadai work- BCP | 1095 | Sq.Ft | 1 | 100 | 27.38 | 0 | 1095 | CGST 0% URD I/P | 0 | 1095 | 1095 | Approved | 0 | 0 | 22 | 21 Dec 2021
GANGA DHAM TOWERS | 742 | 92789 | 21 Dec 2021 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 1635 | A P1 Parking Ghadai & chemical grouting | Ghadai work- BCP | 8330 | Sq.Ft | 1 | 100 | 208.25 | 0 | 8330 | CGST 0% URD I/P | 0 | 8330 | 8330 | Approved | 0 | 0 | 167 | 21 Dec 2021
GANGA DHAM TOWERS | 742 | 92789 | 21 Dec 2021 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 1635 | A P1 Parking Ghadai & chemical grouting | Chemical Grouting (L) | 8330 | Sq.Ft | 1 | 100 | 208.25 | 0 | 8330 | C+S GST 18% I/P RD | 1499.4 | 9829.4 | 9829.4 | Approved | 0 | 0 | 167 | 21 Dec 2021
GANGA DHAM TOWERS | 923 | 92786 | 20 Dec 2021 |  | FIRE CLOSURE SYSTEMS | FIRE CLOSURE SYSTEMS | EV - 1821 | Fire Fightiing Maintenance | Fire Extinguisher refilling- SO | 2 | No. | 550 | 100 | 0 | 0 | 1100 | C+S GST 18% I/P RD | 198 | 1298 | 1298 | Approved | 0 | 0 | 55 | 20 Dec 2021
GANGA DHAM TOWERS | 923 | 92786 | 20 Dec 2021 |  | FIRE CLOSURE SYSTEMS | FIRE CLOSURE SYSTEMS | EV - 1821 | Fire Fightiing Maintenance | Fire Extinguisher refilling- SO | 1 | No. | 450 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 55 | 20 Dec 2021
GANGA DHAM TOWERS | 923 | 92786 | 20 Dec 2021 |  | FIRE CLOSURE SYSTEMS | FIRE CLOSURE SYSTEMS | EV - 1821 | Fire Fightiing Maintenance | Fire Extinguisher refilling- SO | 4 | No. | 250 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 55 | 20 Dec 2021
GANGA DHAM TOWERS | 923 | 92786 | 20 Dec 2021 |  | FIRE CLOSURE SYSTEMS | FIRE CLOSURE SYSTEMS | EV - 1821 | Fire Fightiing Maintenance | Fire Extinguisher refilling- SO | 3 | No. | 600 | 100 | 0 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 55 | 20 Dec 2021
GANGA DHAM TOWERS | 923 | 92786 | 20 Dec 2021 |  | FIRE CLOSURE SYSTEMS | FIRE CLOSURE SYSTEMS | EV - 1821 | Fire Fightiing Maintenance | Fire Extinguisher refilling- SO | 2 | No. | 550 | 100 | 0 | 0 | 1100 | C+S GST 18% I/P RD | 198 | 1298 | 1298 | Approved | 0 | 0 | 55 | 20 Dec 2021
GANGA DHAM TOWERS | 272 | 92783 | 20 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1735 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.2039 | Sq.Ft | 152 | 100 | 0 | 0 | 7023 | C+S GST 18% I/P RD | 1264.14 | 8287.14 | 8287.14 | Approved | 0 | 0 | 211 | 20 Dec 2021
GANGA DHAM TOWERS | 272 | 92783 | 20 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1735 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 49.2842 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7023 | C+S GST 18% I/P RD | 1264.14 | 8287.14 | 8287.14 | Approved | 0 | 0 | 211 | 20 Dec 2021
GANGA DHAM TOWERS | 272 | 92783 | 20 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1735 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 49.2842 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7023 | C+S GST 18% I/P RD | 1264.14 | 8287.14 | 8287.14 | Approved | 0 | 0 | 211 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 903 Kitchen dado | Dado BC | 60.16 | Sq.Ft | 18 | 100 | 27.07 | 0 | 1082.88 | C+S GST 18% I/P RD | 194.92 | 1277.8 | 1277.8 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 704 Kitchen dado | Dado BC | 65.25 | Sq.Ft | 18 | 100 | 29.36 | 0 | 1174.5 | C+S GST 18% I/P RD | 211.42 | 1385.92 | 1385.92 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 404 Granite Kitchen Otta | Granite Kitchen Otta BC | 19.6 | R.Ft | 300 | 100 | 147 | 0 | 5880 | C+S GST 18% I/P RD | 1058.4 | 6938.4 | 6938.4 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 603 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.28 | R.Ft | 300 | 100 | 122.1 | 0 | 4884 | C+S GST 18% I/P RD | 879.12 | 5763.12 | 5763.12 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 403 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.3 | R.Ft | 300 | 100 | 122.25 | 0 | 4890 | C+S GST 18% I/P RD | 880.2 | 5770.2 | 5770.2 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 2103 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 115.44 | Sq.Ft | 28 | 100 | 80.81 | 0 | 3232.32 | C+S GST 18% I/P RD | 581.82 | 3814.14 | 3814.14 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 2203 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 115.44 | Sq.Ft | 28 | 100 | 80.81 | 0 | 3232.32 | C+S GST 18% I/P RD | 581.82 | 3814.14 | 3814.14 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 603 Kitchen dado | L Groove - BCV | 13.45 | R.Ft | 20 | 100 | 6.73 | 0 | 269 | C+S GST 18% I/P RD | 48.42 | 317.42 | 317.42 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 903 Kitchen dado | L Groove - BCV | 13.45 | R.Ft | 20 | 100 | 6.73 | 0 | 269 | C+S GST 18% I/P RD | 48.42 | 317.42 | 317.42 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 704 Kitchen dado | L Groove - BCV | 15.42 | R.Ft | 20 | 100 | 7.71 | 0 | 308.4 | C+S GST 18% I/P RD | 55.52 | 363.92 | 363.92 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 603 Kitchen dado | Dado BC | 60.16 | Sq.Ft | 14 | 100 | 21.06 | 0 | 842.24 | C+S GST 18% I/P RD | 151.6 | 993.84 | 993.84 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 2203 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144.08 | Sq.Ft | 60 | 100 | 216.12 | 0 | 8644.8 | C+S GST 18% I/P RD | 1556.06 | 10200.86 | 10200.86 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 2103 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144.08 | Sq.Ft | 60 | 100 | 216.12 | 0 | 8644.8 | C+S GST 18% I/P RD | 1556.06 | 10200.86 | 10200.86 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 2103 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 200.32 | Sq.Ft | 60 | 100 | 300.48 | 0 | 12019.2 | C+S GST 18% I/P RD | 2163.46 | 14182.66 | 14182.66 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 2203 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 487.99 | Sq.Ft | 60 | 100 | 731.99 | 0 | 29279.4 | C+S GST 18% I/P RD | 5270.3 | 34549.7 | 34549.7 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 2203 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 200.32 | Sq.Ft | 60 | 100 | 300.48 | 0 | 12019.2 | C+S GST 18% I/P RD | 2163.46 | 14182.66 | 14182.66 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 2103 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 487.99 | Sq.Ft | 60 | 100 | 731.99 | 0 | 29279.4 | C+S GST 18% I/P RD | 5270.3 | 34549.7 | 34549.7 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 703 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.28 | R.Ft | 325 | 100 | 132.28 | 0 | 5291 | C+S GST 18% I/P RD | 952.38 | 6243.38 | 6243.38 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 704 Granite Kitchen Otta | Granite Kitchen Otta BC | 19.6 | R.Ft | 325 | 100 | 159.25 | 0 | 6370 | C+S GST 18% I/P RD | 1146.6 | 7516.6 | 7516.6 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 551 | 92782 | 20 Dec 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1670 | A 903 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.3015 | R.Ft | 325 | 100 | 132.45 | 0 | 5298 | C+S GST 18% I/P RD | 953.64 | 6251.64 | 6251.64 | Approved | 0 | 0 | 1429 | 20 Dec 2021
GANGA DHAM TOWERS | 1002 | 92781 | 20 Dec 2021 |  | AVCON TECHNICS PVT LTD | Kishan Enterprises | EV - 1626 | A 2301 NOC | Italian Marble Flooring - BCo | 376.92 | Sq.Ft | 55 | 100 | 518.27 | 0 | 20730.6 | C+S GST 18% I/P RD | 3731.5 | 24462.1 | 24462.1 | Approved | 0 | 0 | 207 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 401 Kitchen dado | L Groove - BCV | 15.42 | R.Ft | 20 | 100 | 7.71 | 0 | 308.4 | C+S GST 18% I/P RD | 55.52 | 363.92 | 363.92 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 502 Kitchen dado | L Groove - BCV | 15.4 | R.Ft | 20 | 100 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 2002 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 60 | 100 | 859.22 | 0 | 34368.6 | C+S GST 18% I/P RD | 6186.34 | 40554.94 | 40554.94 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 2301 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 205.38 | Sq.Ft | 60 | 100 | 308.07 | 0 | 12322.8 | C+S GST 18% I/P RD | 2218.1 | 14540.9 | 14540.9 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 2002 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 60 | 100 | 200.78 | 0 | 8031 | C+S GST 18% I/P RD | 1445.58 | 9476.58 | 9476.58 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 902 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.96 | R.Ft | 325 | 100 | 137.8 | 0 | 5512 | C+S GST 18% I/P RD | 992.16 | 6504.16 | 6504.16 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 602 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.96 | R.Ft | 300 | 100 | 127.2 | 0 | 5088 | C+S GST 18% I/P RD | 915.84 | 6003.84 | 6003.84 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 502 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.96 | R.Ft | 300 | 100 | 127.2 | 0 | 5088 | C+S GST 18% I/P RD | 915.84 | 6003.84 | 6003.84 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 202 Granite Kitchen Otta | Granite Kitchen Otta BC | 16.97 | R.Ft | 300 | 100 | 127.28 | 0 | 5091 | C+S GST 18% I/P RD | 916.38 | 6007.38 | 6007.38 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 401 Kitchen dado | Dado BC | 36.64 | Sq.Ft | 14 | 100 | 12.82 | 0 | 512.96 | C+S GST 18% I/P RD | 92.34 | 605.3 | 605.3 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 502 Kitchen dado | Dado BC | 47.51 | Sq.Ft | 14 | 100 | 16.63 | 0 | 665.14 | C+S GST 18% I/P RD | 119.72 | 784.86 | 784.86 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 2002 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 60 | 100 | 273.68 | 0 | 10947 | C+S GST 18% I/P RD | 1970.46 | 12917.46 | 12917.46 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 2301 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 515.43 | Sq.Ft | 60 | 100 | 773.15 | 0 | 30925.8 | C+S GST 18% I/P RD | 5566.64 | 36492.44 | 36492.44 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 2301 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 120.465 | Sq.Ft | 60 | 100 | 180.7 | 0 | 7227.9 | C+S GST 18% I/P RD | 1301.02 | 8528.92 | 8528.92 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 2002 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.65 | Sq.Ft | 60 | 100 | 315.98 | 0 | 12639 | C+S GST 18% I/P RD | 2275.02 | 14914.02 | 14914.02 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 537 | 92779 | 20 Dec 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1677 | A 2301 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 189.873 | Sq.Ft | 60 | 100 | 284.81 | 0 | 11392.38 | C+S GST 18% I/P RD | 2050.62 | 13443 | 13443 | Approved | 0 | 0 | 1504 | 20 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 65mm dia.(M) | 60 | Mtrs | 899 | 100 | 0 | 0 | 53940 | C+S GST 18% I/P RD | 9709.2 | 63649.2 | 63649.2 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | Rate Diff. GI C Class Pipe 32 mm dia. | 341.9871 | Mtrs | 29.39 | 100 | 0 | 0 | 10051 | C+S GST 18% I/P RD | 1809.18 | 11860.18 | 11860.18 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | Rate Diff. GI C Class Pipe 32 mm dia. | 300 | Mtrs | 29.39 | 100 | 0 | 0 | 8817 | C+S GST 18% I/P RD | 1587.06 | 10404.06 | 10404.06 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 40mm dia.(M) | 220 | Mtrs | 568 | 100 | 0 | 0 | 124960 | C+S GST 18% I/P RD | 22492.8 | 147452.8 | 147452.8 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 25mm dia.(M) | 1560 | Mtrs | 386 | 100 | 0 | 0 | 602160 | C+S GST 18% I/P RD | 108388.8 | 710548.8 | 710548.8 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | Rate Diff. GI C Class Pipe 25 mm dia. | 1559.9913 | Mtrs | 22.97 | 100 | 0 | 0 | 35833 | C+S GST 18% I/P RD | 6449.94 | 42282.94 | 42282.94 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | Rate Diff. GI C Class Pipe 65 mm dia. | 60 | Mtrs | 53.49 | 100 | 0 | 0 | 3209.4 | C+S GST 18% I/P RD | 577.7 | 3787.1 | 3787.1 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | SITC GI Pipe C Class 32mm dia.(M) | 342 | Mtrs | 494 | 100 | 0 | 0 | 168948 | C+S GST 18% I/P RD | 30410.64 | 199358.64 | 199358.64 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1173 | 92771 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1594 | Tower A& B Parking 3 Fire Fighting | Rate Diff. GI C Class Pipe 40 mm dia. | 220 | Mtrs | 33.8 | 100 | 0 | 0 | 7436 | C+S GST 18% I/P RD | 1338.48 | 8774.48 | 8774.48 | Approved | 0 | 0 | 20307 | 18 Dec 2021
GANGA DHAM TOWERS | 1171 | 92770 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1593 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 32mm dia.(M) | 375 | Mtrs | 494 | 100 | 0 | 0 | 185250 | C+S GST 18% I/P RD | 33345 | 218595 | 218595 | Approved | 0 | 0 | 29081 | 18 Dec 2021
GANGA DHAM TOWERS | 1171 | 92770 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1593 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 25mm dia.(M) | 1020 | Mtrs | 386 | 100 | 0 | 0 | 393720 | C+S GST 18% I/P RD | 70869.6 | 464589.6 | 464589.6 | Approved | 0 | 0 | 29081 | 18 Dec 2021
GANGA DHAM TOWERS | 1171 | 92770 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1593 | Towerr A& B Parking 1 Fire Fighting | Rate Diff. GI C Class Pipe 32 mm dia. | 389.9908 | Mtrs | 29.393 | 100 | 0 | 0 | 11463 | C+S GST 18% I/P RD | 2063.34 | 13526.34 | 13526.34 | Approved | 0 | 0 | 29081 | 18 Dec 2021
GANGA DHAM TOWERS | 1171 | 92770 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1593 | Towerr A& B Parking 1 Fire Fighting | Rate Diff. GI C Class Pipe 150 mm dia. | 389.9964 | Mtrs | 124.355 | 100 | 0 | 0 | 48498 | C+S GST 18% I/P RD | 8729.64 | 57227.64 | 57227.64 | Approved | 0 | 0 | 29081 | 18 Dec 2021
GANGA DHAM TOWERS | 1171 | 92770 | 18 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1593 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 150mm dia.(M) | 390 | Mtrs | 2090 | 100 | 0 | 0 | 815100 | C+S GST 18% I/P RD | 146718 | 961818 | 961818 | Approved | 0 | 0 | 29081 | 18 Dec 2021
GANGA DHAM TOWERS | 272 | 92769 | 18 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1737 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 56.8421 | Sq.Ft | 142.5 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 18 Dec 2021
GANGA DHAM TOWERS | 272 | 92769 | 18 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1737 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 56.8421 | Sq.Ft | 142.5 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 18 Dec 2021
GANGA DHAM TOWERS | 272 | 92769 | 18 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1737 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 60.9023 | Sq.Ft | 133 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 18 Dec 2021
GANGA DHAM TOWERS | 272 | 92769 | 18 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1737 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 60.9023 | Sq.Ft | 133 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 18 Dec 2021
GANGA DHAM TOWERS | 272 | 92769 | 18 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1737 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 60.9023 | Sq.Ft | 133 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 18 Dec 2021
GANGA DHAM TOWERS | 272 | 92769 | 18 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1737 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 60.9023 | Sq.Ft | 133 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 18 Dec 2021
GANGA DHAM TOWERS | 126 | 92754 | 17 Dec 2021 |  | SANDIP VAMANRAO RUPNAWAR | KIRAN TUKARAM DHANAWADE | EV - 1575 | Site Expenses | Site Expenses -SO | 0.2806 | Month | 15000 | 100 | 0 | 0 | 4209 | CGST 0% URD I/P | 0 | 4209 | 4209 | Approved | 0 | 0 | 42 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 65mm dia.(M) | 60 | Mtrs | 899 | 100 | 0 | 0 | 53940 | C+S GST 18% I/P RD | 9709.2 | 63649.2 | 63649.2 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | Rate Diff. GI C Class Pipe 25 mm dia. | 599.9913 | Mtrs | 22.967 | 100 | 0 | 0 | 13780 | C+S GST 18% I/P RD | 2480.4 | 16260.4 | 16260.4 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | Rate Diff. GI C Class Pipe 150 mm dia. | 210.0036 | Mtrs | 124.355 | 100 | 0 | 0 | 26115 | C+S GST 18% I/P RD | 4700.7 | 30815.7 | 30815.7 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 40mm dia.(M) | 245 | Mtrs | 568 | 100 | 0 | 0 | 139160 | C+S GST 18% I/P RD | 25048.8 | 164208.8 | 164208.8 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 150mm dia.(M) | 210 | Mtrs | 2090 | 100 | 0 | 0 | 438900 | C+S GST 18% I/P RD | 79002 | 517902 | 517902 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 25mm dia.(M) | 600 | Mtrs | 386 | 100 | 0 | 0 | 231600 | C+S GST 18% I/P RD | 41688 | 273288 | 273288 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | Rate Diff. GI C Class Pipe 65 mm dia. | 59.992 | Mtrs | 53.4905 | 100 | 0 | 0 | 3209 | C+S GST 18% I/P RD | 577.62 | 3786.62 | 3786.62 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | Rate Diff. GI C Class Pipe 40 mm dia. | 244.9994 | Mtrs | 33.796 | 100 | 0 | 0 | 8280 | C+S GST 18% I/P RD | 1490.4 | 9770.4 | 9770.4 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1171 | 92753 | 17 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1588 | Towerr A& B Parking 1 Fire Fighting | SITC GI Pipe C Class 32mm dia.(M) | 300 | Mtrs | 494 | 100 | 0 | 0 | 148200 | C+S GST 18% I/P RD | 26676 | 174876 | 174876 | Approved | 0 | 0 | 21264 | 17 Dec 2021
GANGA DHAM TOWERS | 1037 | 92748 | 16 Dec 2021 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 1561 | Head Office Security Service | Security Guard AIE - | 60 | Day | 433.33 | 100 | 0 | 0 | 25999.8 | C+S GST 18% RCM | 4679.96 | 30679.76 | 30679.76 | Approved | 0 | 0 | 260 | 16 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Marble Mirror Polish Wrk | 35.25 | R.Ft | 65 | 100 | 57.28 | 0 | 2291.25 | C+S GST 18% I/P RD | 412.42 | 2703.67 | 2703.67 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Helper- Dld | 5 | Day | 550 | 100 | 68.75 | 0 | 2750 | C+S GST 18% I/P RD | 495 | 3245 | 3245 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Department Labour - Day | 15 | Day | 1100 | 100 | 412.5 | 0 | 16500 | C+S GST 18% I/P RD | 2970 | 19470 | 19470 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Thickness of Cutting | 32.32 | R.Ft | 20 | 100 | 16.16 | 0 | 646.4 | C+S GST 18% I/P RD | 116.36 | 762.76 | 762.76 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Granite Border- Dld | 46.38 | R.Ft | 90 | 100 | 104.36 | 0 | 4174.2 | C+S GST 18% I/P RD | 751.36 | 4925.56 | 4925.56 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Italian Marble Buffing (sft) | 88.73 | Sq.Ft | 45 | 100 | 99.82 | 0 | 3992.85 | C+S GST 18% I/P RD | 718.72 | 4711.57 | 4711.57 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Door Closer fixing-BRE | 2 | No. | 300 | 100 | 15 | 0 | 600 | C+S GST 18% I/P RD | 108 | 708 | 708 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Granite Flooring - Dld | 48.7971 | Sq.Ft | 90 | 100 | 109.79 | 0 | 4391.74 | C+S GST 18% I/P RD | 790.52 | 5182.26 | 5182.26 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Zero Point Joint Making | 27.99 | R.Ft | 200 | 100 | 139.95 | 0 | 5598 | C+S GST 18% I/P RD | 1007.64 | 6605.64 | 6605.64 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Drill Hole | 6 | No. | 130 | 100 | 19.5 | 0 | 780 | C+S GST 18% I/P RD | 140.4 | 920.4 | 920.4 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Champher-DCH | 27.99 | R.Ft | 85 | 100 | 59.48 | 0 | 2379.15 | C+S GST 18% I/P RD | 428.24 | 2807.39 | 2807.39 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Edge Polish- DCH | 27.99 | R.Ft | 35 | 100 | 24.49 | 0 | 979.65 | C+S GST 18% I/P RD | 176.34 | 1155.99 | 1155.99 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1160 | 92740 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1894 | B1 1101 Tiling Work | Brush Polish on Granite- BCE | 2475.07 | Sq.Ft | 65 | 100 | 4021.99 | 0 | 160879.55 | C+S GST 18% I/P RD | 28958.32 | 189837.87 | 189837.87 | Approved | 0 | 0 | 4119 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Edge Polish- DCH | 300.24 | R.Ft | 35 | 100 | 262.71 | 0 | 10508.4 | C+S GST 18% I/P RD | 1891.52 | 12399.92 | 12399.92 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | L Groove - AIE | 19.07 | R.Ft | 150 | 100 | 71.51 | 0 | 2860.5 | C+S GST 18% I/P RD | 514.9 | 3375.4 | 3375.4 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Kadappa Flooring work | 271.44 | Sq.Ft | 65 | 100 | 441.09 | 0 | 17643.6 | C+S GST 18% I/P RD | 3175.84 | 20819.44 | 20819.44 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Dado BC | 377.63 | Sq.Ft | 100 | 100 | 944.08 | 0 | 37763 | C+S GST 18% I/P RD | 6797.34 | 44560.34 | 44560.34 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Granite Leather Polish | 61.82 | Sq.Ft | 65 | 100 | 100.46 | 0 | 4018.3 | C+S GST 18% I/P RD | 723.3 | 4741.6 | 4741.6 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Acid Wash | 377.63 | Sq.Ft | 10 | 100 | 94.41 | 0 | 3776.3 | C+S GST 18% I/P RD | 679.74 | 4456.04 | 4456.04 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Granite Buffing - | 301.29 | R.Ft | 20 | 100 | 150.65 | 0 | 6025.8 | C+S GST 18% I/P RD | 1084.64 | 7110.44 | 7110.44 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Granite Kitchen Otta -Dld | 9 | R.Ft | 800 | 100 | 180 | 0 | 7200 | C+S GST 18% I/P RD | 1296 | 8496 | 8496 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Granite Dado- ARW | 12.48 | Sq.Ft | 115 | 100 | 35.88 | 0 | 1435.2 | C+S GST 18% I/P RD | 258.34 | 1693.54 | 1693.54 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Granite Flooring - Dld | 218.97 | Sq.Ft | 90 | 100 | 492.68 | 0 | 19707.3 | C+S GST 18% I/P RD | 3547.32 | 23254.62 | 23254.62 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Bull Nosing / Moulding | 187.52 | R.Ft | 85 | 100 | 398.48 | 0 | 15939.2 | C+S GST 18% I/P RD | 2869.06 | 18808.26 | 18808.26 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Italian Marble Mirror Polish- BCo | 391.59 | Sq.Ft | 65 | 100 | 636.33 | 0 | 25453.35 | C+S GST 18% I/P RD | 4581.6 | 30034.95 | 30034.95 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Demolition work- BCE - | 626.51 | Sq.Ft | 30 | 100 | 469.88 | 0 | 18795.3 | C+S GST 18% I/P RD | 3383.16 | 22178.46 | 22178.46 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Zero Point Joint Making | 164.86 | R.Ft | 200 | 100 | 824.3 | 0 | 32972 | C+S GST 18% I/P RD | 5934.96 | 38906.96 | 38906.96 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Drill Hole | 98 | No. | 130 | 100 | 318.5 | 0 | 12740 | C+S GST 18% I/P RD | 2293.2 | 15033.2 | 15033.2 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Granite Border- Dld | 405.57 | R.Ft | 90 | 100 | 912.53 | 0 | 36501.3 | C+S GST 18% I/P RD | 6570.24 | 43071.54 | 43071.54 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1159 | 92739 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1820 | B1 1101 Tiling Work | Thickness of Cutting | 64 | R.Ft | 20 | 100 | 32 | 0 | 1280 | C+S GST 18% I/P RD | 230.4 | 1510.4 | 1510.4 | Approved | 0 | 0 | 5092 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Department Labour - Day | 2 | Day | 1100 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Edge Polish - Dld | 58.24 | R.Ft | 35 | 100 | 50.96 | 0 | 2038.4 | C+S GST 18% I/P RD | 366.92 | 2405.32 | 2405.32 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Tile Cutting work | 28 | R.Ft | 20 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Granite Dado- ARW | 35.67 | Sq.Ft | 115 | 100 | 102.55 | 0 | 4102.05 | C+S GST 18% I/P RD | 738.36 | 4840.41 | 4840.41 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Zero Point Joint Making | 0.99 | R.Ft | 200 | 100 | 4.95 | 0 | 198 | C+S GST 18% I/P RD | 35.64 | 233.64 | 233.64 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Granite Champher Polish (L) | 27.72 | R.Ft | 85 | 100 | 58.91 | 0 | 2356.2 | C+S GST 18% I/P RD | 424.12 | 2780.32 | 2780.32 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Granite Border-BCo | 70.27 | R.Ft | 90 | 100 | 158.11 | 0 | 6324.3 | C+S GST 18% I/P RD | 1138.38 | 7462.68 | 7462.68 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Helper- Dld | 2 | Day | 550 | 100 | 27.5 | 0 | 1100 | C+S GST 18% I/P RD | 198 | 1298 | 1298 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Drill Hole | 20 | No. | 130 | 100 | 65 | 0 | 2600 | C+S GST 18% I/P RD | 468 | 3068 | 3068 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Demolition work - DER | 17.32 | Sq.Ft | 30 | 100 | 12.99 | 0 | 519.6 | C+S GST 18% I/P RD | 93.52 | 613.12 | 613.12 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | V Grove - BCo | 22.78 | R.Ft | 120 | 100 | 68.34 | 0 | 2733.6 | C+S GST 18% I/P RD | 492.04 | 3225.64 | 3225.64 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 1032 | 92737 | 15 Dec 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1852 | DA Development Top Terrace Tiling work | Nahani Trap Jali Cutting | 2 | No. | 130 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 500 | 15 Dec 2021
GANGA DHAM TOWERS | 258 | 92736 | 15 Dec 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1576 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.8996 | Month | 2500 | 100 | 0 | 0 | 2249 | CGST 0% URD I/P | 0 | 2249 | 2249 | Approved | 0 | 0 | 22 | 15 Dec 2021
GANGA DHAM TOWERS | 237 | 92735 | 15 Dec 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1591 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.8999 | Month | 7000 | 100 | 0 | 0 | 6299 | CGST 0% URD I/P | 0 | 6299 | 6299 | Approved | 0 | 0 | 63 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D 10th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | C+S GST 18% I/P RD | 130.3 | 854.17 | 854.17 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Fire St.case Ceiling Gyp. Plaster 3rd to 4th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Fire St.case Ceiling Gyp. Plaster 5th to 6th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D 1st Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 180.968 | Sq.Ft | 4 | 100 | 18.1 | 0 | 723.87 | C+S GST 18% I/P RD | 130.3 | 854.17 | 854.17 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Main St.case Ceiling Gyp. Plaster 6th to 7th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Fire St.case Ceiling Gyp. Plaster 7th to 8th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Fire St.case Ceiling Gyp. Plaster 6th to 7th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Main St.case Ceiling Gyp. Plaster 3rd to 4th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Fire St.case Ceiling Gyp. Plaster 8th to 9th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Main St.case Ceiling Gyp. Plaster 7th to 8th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Main St.case Ceiling Gyp. Plaster 2nd to 3rd Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Fire St.case Ceiling Gyp. Plaster 4th to 5th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Main St.case Ceiling Gyp. Plaster 5th to 6th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 797 | 92729 | 15 Dec 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1587 | D Main St.case Ceiling Gyp. Plaster 4th to 5th Fl. | Gypsum on Ceiling (L) | 162 | Sq.Ft | 4 | 100 | 16.2 | 0 | 648 | C+S GST 18% I/P RD | 116.64 | 764.64 | 764.64 | Approved | 0 | 0 | 92 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 404 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | C+S GST 18% I/P RD | 234.22 | 1535.46 | 1535.46 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 401 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 448.29 | Sq.Ft | 4 | 100 | 44.83 | 0 | 1793.16 | C+S GST 18% I/P RD | 322.76 | 2115.92 | 2115.92 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 302 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | C+S GST 18% I/P RD | 236.78 | 1552.26 | 1552.26 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 205 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 448.29 | Sq.Ft | 4 | 100 | 44.83 | 0 | 1793.16 | C+S GST 18% I/P RD | 322.76 | 2115.92 | 2115.92 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 304 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | C+S GST 18% I/P RD | 234.22 | 1535.46 | 1535.46 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 403 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 325.31 | Sq.Ft | 4 | 100 | 32.53 | 0 | 1301.24 | C+S GST 18% I/P RD | 234.22 | 1535.46 | 1535.46 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 402 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 328.87 | Sq.Ft | 4 | 100 | 32.89 | 0 | 1315.48 | C+S GST 18% I/P RD | 236.78 | 1552.26 | 1552.26 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 301 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 448.29 | Sq.Ft | 4 | 100 | 44.83 | 0 | 1793.16 | C+S GST 18% I/P RD | 322.76 | 2115.92 | 2115.92 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 698 | 92728 | 15 Dec 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN |  | D 405 Ceiling & Wall Gypsum Plaster | Gypsum on Ceiling (L) | 313.803 | Sq.Ft | 4 | 100 | 31.38 | 0 | 1255.21 | C+S GST 18% I/P RD | 225.94 | 1481.15 | 1481.15 |  | 0 | 0 | 132 | 15 Dec 2021
GANGA DHAM TOWERS | 1225 | 92718 | 14 Dec 2021 |  | AJAY KUMAR GUPTA | SANTOSH HMMAT CHAVHAN | EV - 1570 | Substation Trench Cement Ghotai ( Vertical Tranch Area) - | Cement Ghotai - DCH | 1680 | Sq.Ft | 12 | 100 | 2016 | 0 | 20160 | CGST 0% URD I/P | 0 | 20160 | 20160 | Approved | 0 | 0 | 202 | 14 Dec 2021
GANGA DHAM TOWERS | 1226 | 92717 | 14 Dec 2021 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 1569 | Lt Substation Ground Floor BBM/ Plaster (L) | Blockwork 8" - BC | 618 | Sq.Ft | 15 | 100 | 231.75 | 0 | 9270 | CGST 0% URD I/P | 0 | 9270 | 9270 | Approved | 0 | 0 | 308 | 14 Dec 2021
GANGA DHAM TOWERS | 1226 | 92717 | 14 Dec 2021 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 1569 | Lt Substation Ground Floor BBM/ Plaster (L) | Brickwork 12" -DLd | 1001 | Sq.Ft | 18 | 100 | 450.45 | 0 | 18018 | CGST 0% URD I/P | 0 | 18018 | 18018 | Approved | 0 | 0 | 308 | 14 Dec 2021
GANGA DHAM TOWERS | 1226 | 92717 | 14 Dec 2021 |  | SANTOSH HMMAT CHAVHAN | SANTOSH HMMAT CHAVHAN | EV - 1569 | Lt Substation Ground Floor Pcc Work | PCC Work | 875 | Sq.Ft | 4 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 308 | 14 Dec 2021
GANGA DHAM TOWERS | 1180 | 92709 | 13 Dec 2021 |  | M.S. CONSTRUCTION | M.S. CONSTRUCTION | EV - 1649 | A Terrace Scaffolding Work | Scaffolding work | 2778 | Sq.Ft | 5.5 | 100 | 381.98 | 0 | 15279 | IGST 18% I/P RD | 2750.22 | 18029.22 | 18029.22 | Approved | 0 | 0 | 153 | 13 Dec 2021
GANGA DHAM TOWERS | 523 | 92693 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1650 | B Bldg External Plumbing Rainwater Line (L) | Rainwater Line | 14 | Flat | 3300 | 100 | 1155 | 0 | 46200 | CGST 0% URD I/P | 0 | 46200 | 46200 | Approved | 0 | 0 | 462 | 13 Dec 2021
GANGA DHAM TOWERS | 807 | 92690 | 13 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2172 | B 102 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 334.35 | R.Ft | 20 | 100 | 167.18 | 0 | 6687 | C+S GST 18% I/P RD | 1203.66 | 7890.66 | 7890.66 | Approved | 0 | 0 | 782 | 13 Dec 2021
GANGA DHAM TOWERS | 807 | 92690 | 13 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2172 | B-1002 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 334.35 | R.Ft | 20 | 100 | 167.18 | 0 | 6687 | C+S GST 18% I/P RD | 1203.66 | 7890.66 | 7890.66 | Approved | 0 | 0 | 782 | 13 Dec 2021
GANGA DHAM TOWERS | 807 | 92690 | 13 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2172 | B 902 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 334.35 | R.Ft | 20 | 100 | 167.18 | 0 | 6687 | C+S GST 18% I/P RD | 1203.66 | 7890.66 | 7890.66 | Approved | 0 | 0 | 782 | 13 Dec 2021
GANGA DHAM TOWERS | 807 | 92690 | 13 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2172 | B 102 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 969.48 | Sq.Ft | 20 | 100 | 484.74 | 0 | 19389.6 | C+S GST 18% I/P RD | 3490.12 | 22879.72 | 22879.72 | Approved | 0 | 0 | 782 | 13 Dec 2021
GANGA DHAM TOWERS | 807 | 92690 | 13 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2172 | B 902 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 969.48 | Sq.Ft | 20 | 100 | 484.74 | 0 | 19389.6 | C+S GST 18% I/P RD | 3490.12 | 22879.72 | 22879.72 | Approved | 0 | 0 | 782 | 13 Dec 2021
GANGA DHAM TOWERS | 807 | 92690 | 13 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2172 | B-1002 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 969.48 | Sq.Ft | 20 | 100 | 484.74 | 0 | 19389.6 | C+S GST 18% I/P RD | 3490.12 | 22879.72 | 22879.72 | Approved | 0 | 0 | 782 | 13 Dec 2021
GANGA DHAM TOWERS | 806 | 92689 | 13 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2164 | B 902 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 334.35 | R.Ft | 55 | 100 | 0 | 0 | 18389.25 | C+S GST 18% I/P RD | 3310.06 | 21699.31 | 21699.31 | Approved | 0 | 0 | 0 | 13 Dec 2021
GANGA DHAM TOWERS | 806 | 92689 | 13 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2164 | B-1002 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 334.35 | R.Ft | 55 | 100 | 0 | 0 | 18389.25 | C+S GST 18% I/P RD | 3310.06 | 21699.31 | 21699.31 | Approved | 0 | 0 | 0 | 13 Dec 2021
GANGA DHAM TOWERS | 806 | 92689 | 13 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2164 | B 102 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 969.48 | Sq.Ft | 55 | 100 | 0 | 0 | 53321.4 | C+S GST 18% I/P RD | 9597.86 | 62919.26 | 62919.26 | Approved | 0 | 0 | 0 | 13 Dec 2021
GANGA DHAM TOWERS | 806 | 92689 | 13 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2164 | B-1002 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 969.48 | Sq.Ft | 55 | 100 | 0 | 0 | 53321.4 | C+S GST 18% I/P RD | 9597.86 | 62919.26 | 62919.26 | Approved | 0 | 0 | 0 | 13 Dec 2021
GANGA DHAM TOWERS | 806 | 92689 | 13 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2164 | B 902 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 969.48 | Sq.Ft | 55 | 100 | 0 | 0 | 53321.4 | C+S GST 18% I/P RD | 9597.86 | 62919.26 | 62919.26 | Approved | 0 | 0 | 0 | 13 Dec 2021
GANGA DHAM TOWERS | 806 | 92689 | 13 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2164 | B 102 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 334.35 | R.Ft | 55 | 100 | 0 | 0 | 18389.25 | C+S GST 18% I/P RD | 3310.06 | 21699.31 | 21699.31 | Approved | 0 | 0 | 0 | 13 Dec 2021
GANGA DHAM TOWERS | 971 | 92688 | 13 Dec 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1740 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 3" BCE | 25 | No. | 210 | 100 | 131.25 | 0 | 5250 | C+S GST 18% I/P RD | 945 | 6195 | 6195 | Approved | 0 | 0 | 483 | 13 Dec 2021
GANGA DHAM TOWERS | 971 | 92688 | 13 Dec 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1740 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 120 | No. | 210 | 100 | 630 | 0 | 25200 | C+S GST 18% I/P RD | 4536 | 29736 | 29736 | Approved | 0 | 0 | 483 | 13 Dec 2021
GANGA DHAM TOWERS | 971 | 92688 | 13 Dec 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1740 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 85 | No. | 210 | 100 | 446.25 | 0 | 17850 | C+S GST 18% I/P RD | 3213 | 21063 | 21063 | Approved | 0 | 0 | 483 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1501 Chemical & IPS Waterproofing | IPS W/P | 538 | Sq.Ft | 11 | 100 | 591.8 | 0 | 5918 | CGST 0% URD I/P | 0 | 5918 | 5918 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1102 Chemical & IPS Waterproofing | IPS W/P | 424 | Sq.Ft | 11 | 100 | 466.4 | 0 | 4664 | CGST 0% URD I/P | 0 | 4664 | 4664 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1101 Chemical & IPS Waterproofing | IPS W/P | 538 | Sq.Ft | 11 | 100 | 591.8 | 0 | 5918 | CGST 0% URD I/P | 0 | 5918 | 5918 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1101 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 538.4211 | Sq.Ft | 19 | 100 | 1023 | 0 | 10230 | CGST 0% URD I/P | 0 | 10230 | 10230 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1102 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 424.5789 | Sq.Ft | 19 | 100 | 806.7 | 0 | 8067 | CGST 0% URD I/P | 0 | 8067 | 8067 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1101 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1102 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1101 Chemical Grouting | Chemical Grouting.- BC | 2330.62 | Sq.Ft | 2 | 100 | 466.12 | 0 | 4661.24 | CGST 0% URD I/P | 0 | 4661.24 | 4661.24 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1102 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1101 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1102 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1102 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 27 | No. | 70 | 100 | 189 | 0 | 1890 | CGST 0% URD I/P | 0 | 1890 | 1890 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1101 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 27 | No. | 70 | 100 | 189 | 0 | 1890 | CGST 0% URD I/P | 0 | 1890 | 1890 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1201 Chemical Grouting | Chemical Grouting.- BC | 2561.94 | Sq.Ft | 2 | 100 | 512.39 | 0 | 5123.88 | CGST 0% URD I/P | 0 | 5123.88 | 5123.88 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1702 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 102 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 2101 Chemical Grouting | Chemical Grouting.- BC | 2330.62 | Sq.Ft | 2 | 100 | 466.12 | 0 | 4661.24 | CGST 0% URD I/P | 0 | 4661.24 | 4661.24 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1502 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5.7 | No. | 150 | 100 | 85.5 | 0 | 855 | CGST 0% URD I/P | 0 | 855 | 855 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1102 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 498 | 92684 | 13 Dec 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 1669 | B 1101 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 729 | 13 Dec 2021
GANGA DHAM TOWERS | 1170 | 92664 | 10 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1595 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 65mm dia.(L) | 102.2 | Mtrs | 225 | 100 | 0 | 0 | 22995 | C+S GST 18% I/P RD | 4139.1 | 27134.1 | 27134.1 | Approved | 0 | 0 | 460 | 10 Dec 2021
GANGA DHAM TOWERS | 983 | 92655 | 09 Dec 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1910 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 191 | No. | 210 | 100 | 1002.75 | 0 | 40110 | C+S GST 18% I/P RD | 7219.8 | 47329.8 | 47329.8 | Approved | 0 | 0 | 401 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1201 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 902 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 701 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1502 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1901 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 502 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 2001 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1602 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1801 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1301 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 2001 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1901 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1801 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 701 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1502 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1301 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 502 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 902 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 631 | 92651 | 09 Dec 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1754 | A 1201 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2296 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1201 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 902 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 502 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1301 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1801 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1901 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 2001 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1602 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 701 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1502 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1301 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1801 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1901 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 502 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 2001 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1502 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 701 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 902 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 630 | 92650 | 09 Dec 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1676 | A 1201 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 09 Dec 2021
GANGA DHAM TOWERS | 395 | 92649 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1678 | A Bldg Flat No. 2503 Gypsum Plaster | Dhar Core (L) | 549.9225 | R.Ft | 10 | 100 | 137.48 | 0 | 5499.23 | C+S GST 18% I/P RD | 989.86 | 6489.09 | 6489.09 | Approved | 0 | 0 | 347 | 09 Dec 2021
GANGA DHAM TOWERS | 395 | 92649 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1678 | A Bldg Flat No. 2403 Gypsum Plaster | Dhar Core (L) | 549.9225 | R.Ft | 10 | 100 | 137.48 | 0 | 5499.23 | C+S GST 18% I/P RD | 989.86 | 6489.09 | 6489.09 | Approved | 0 | 0 | 347 | 09 Dec 2021
GANGA DHAM TOWERS | 395 | 92649 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1678 | A Bldg Flat No. 2504 Gypsum Plaster | Dhar Core (L) | 501.6825 | R.Ft | 10 | 100 | 125.42 | 0 | 5016.83 | C+S GST 18% I/P RD | 903.02 | 5919.85 | 5919.85 | Approved | 0 | 0 | 347 | 09 Dec 2021
GANGA DHAM TOWERS | 395 | 92649 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1678 | A Bldg Flat No. 2504 Gypsum Plaster | Gypsum on Wall (L) | 2474.34 | Sq.Ft | 4 | 100 | 247.43 | 0 | 9897.36 | C+S GST 18% I/P RD | 1781.52 | 11678.88 | 11678.88 | Approved | 0 | 0 | 347 | 09 Dec 2021
GANGA DHAM TOWERS | 395 | 92649 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1678 | A Bldg Flat No. 2503 Gypsum Plaster | Gypsum on Wall (L) | 2198.37 | Sq.Ft | 4 | 100 | 219.84 | 0 | 8793.48 | C+S GST 18% I/P RD | 1582.82 | 10376.3 | 10376.3 | Approved | 0 | 0 | 347 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 1803 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 1804 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 2103 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 1004 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 2003 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 2004 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 704 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 2003 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 704 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 2103 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 2004 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 1803 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 1004 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 632 | 92648 | 09 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1647 | A 1804 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1549 | 09 Dec 2021
GANGA DHAM TOWERS | 145 | 92641 | 08 Dec 2021 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 1825 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 120 | 08 Dec 2021
GANGA DHAM TOWERS | 145 | 92641 | 08 Dec 2021 |  | PEST-O-CRUSH | S.R.Enterprises | EV - 1825 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 120 | 08 Dec 2021
GANGA DHAM TOWERS | 272 | 92639 | 08 Dec 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1574 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.8947 | Sq.Ft | 152 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 155 | 08 Dec 2021
GANGA DHAM TOWERS | 272 | 92639 | 08 Dec 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1574 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 69.0789 | Sq.Ft | 152 | 100 | 0 | 0 | 10500 | CGST 0% URD I/P | 0 | 10500 | 10500 | Approved | 0 | 0 | 155 | 08 Dec 2021
GANGA DHAM TOWERS | 145 | 92638 | 08 Dec 2021 |  | PEST-O-CRUSH | PEST-O-CRUSH |  | Sales Office & Sample Flat Fogging Work | Fogging work-SO | 12 | Month | 4000 | 8.33 | 0 | 0 | 4000.03 |  | 0 | 4000.03 | 4000.03 |  | 0 | 0 | 80 | 08 Dec 2021
GANGA DHAM TOWERS | 145 | 92638 | 08 Dec 2021 |  | PEST-O-CRUSH | PEST-O-CRUSH |  | Sales Office & Sample Flat Fogging Work | Fogging work-SO | 12 | Month | 4000 | 8.33 | 0 | 0 | 4000.03 | C+S GST 18% I/P RD | 720 | 4720.03 | 4720.03 |  | 0 | 0 | 80 | 08 Dec 2021
GANGA DHAM TOWERS | 149 | 92626 | 07 Dec 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1584 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 2541 | No. | 4 | 100 | 0 | 0 | 10164 | CGST 0% URD I/P | 0 | 10164 | 10164 | Approved | 0 | 0 | 0 | 07 Dec 2021
GANGA DHAM TOWERS | 495 | 92602 | 04 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1648 | B 2301 Gypsum Plaster | Gypsum on Wall (L) | 4532 | Sq.Ft | 4 | 100 | 453.2 | 0 | 18128 | C+S GST 18% I/P RD | 3263.04 | 21391.04 | 21391.04 | Approved | 0 | 0 | 241 | 04 Dec 2021
GANGA DHAM TOWERS | 495 | 92602 | 04 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1648 | B 2301 Gypsum Plaster | Dhar Core (L) | 597.6 | R.Ft | 10 | 100 | 149.4 | 0 | 5976 | C+S GST 18% I/P RD | 1075.68 | 7051.68 | 7051.68 | Approved | 0 | 0 | 241 | 04 Dec 2021
GANGA DHAM TOWERS | 805 | 92601 | 04 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1646 | B 901 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1441.2 | Sq.Ft | 20 | 100 | 720.6 | 0 | 28824 | C+S GST 18% I/P RD | 5188.32 | 34012.32 | 34012.32 | Approved | 0 | 0 | 402 | 04 Dec 2021
GANGA DHAM TOWERS | 805 | 92601 | 04 Dec 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1646 | B 901 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 402 | 04 Dec 2021
GANGA DHAM TOWERS | 804 | 92600 | 04 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1896 | B 901 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1441.2 | Sq.Ft | 55 | 100 | 0 | 0 | 79266 | C+S GST 18% I/P RD | 14267.88 | 93533.88 | 93533.88 | Approved | 0 | 0 | 0 | 04 Dec 2021
GANGA DHAM TOWERS | 804 | 92600 | 04 Dec 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1896 | B 901 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 04 Dec 2021
GANGA DHAM TOWERS | 1133 | 92599 | 04 Dec 2021 |  | BASSAPPA CHAVAN | BASSAPPA CHAVAN | EV - 1592 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Tractor Trip - Dld | 36 | No. | 800 | 100 | 0 | 0 | 28800 | CGST 0% URD I/P | 0 | 28800 | 28800 | Approved | 0 | 0 | 288 | 04 Dec 2021
GANGA DHAM TOWERS | 178 | 92578 | 04 Dec 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1731 | Sales Oiifce Landscape Area . | Garden work. | 65.997 | Day | 420.83 | 100 | 0 | 0 | 27773.52 | C+S GST 18% I/P RD | 4999.24 | 32772.76 | 32772.76 | Approved | 0 | 0 | 278 | 04 Dec 2021
GANGA DHAM TOWERS | 186 | 92575 | 04 Dec 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1725 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 30 | Day | 600 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 854 | 04 Dec 2021
GANGA DHAM TOWERS | 186 | 92575 | 04 Dec 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1725 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 144.486 | Day | 466.66 | 100 | 0 | 0 | 67425.84 | C+S GST 18% I/P RD | 12136.66 | 79562.5 | 79562.5 | Approved | 0 | 0 | 854 | 04 Dec 2021
GANGA DHAM TOWERS | 413 | 92574 | 04 Dec 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1732 | Sales Oiifce Landscape Area . | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 100 | 04 Dec 2021
GANGA DHAM TOWERS | 187 | 92573 | 04 Dec 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1580 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 04 Dec 2021
GANGA DHAM TOWERS | 744 | 92572 | 04 Dec 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 1491 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 6 | 04 Dec 2021
GANGA DHAM TOWERS | 1162 | 92563 | 02 Dec 2021 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 1474 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 02 Dec 2021
GANGA DHAM TOWERS | 272 | 92539 | 02 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1736 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 53.2895 | Sq.Ft | 152 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 02 Dec 2021
GANGA DHAM TOWERS | 272 | 92539 | 02 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1736 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 56.8421 | Sq.Ft | 142.5 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 02 Dec 2021
GANGA DHAM TOWERS | 272 | 92539 | 02 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1736 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 56.8421 | Sq.Ft | 142.5 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 02 Dec 2021
GANGA DHAM TOWERS | 272 | 92539 | 02 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1736 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 60.9023 | Sq.Ft | 133 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 02 Dec 2021
GANGA DHAM TOWERS | 272 | 92539 | 02 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1736 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 56.8421 | Sq.Ft | 142.5 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 02 Dec 2021
GANGA DHAM TOWERS | 272 | 92539 | 02 Dec 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1736 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 56.8421 | Sq.Ft | 142.5 | 100 | 0 | 0 | 8100 | C+S GST 18% I/P RD | 1458 | 9558 | 9558 | Approved | 0 | 0 | 486 | 02 Dec 2021
GANGA DHAM TOWERS | 1094 | 92538 | 02 Dec 2021 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1791 | C Pump Charges From (Spt 21 To Feb 22) | Pumping Charges-BC | 1200 | Cu.Mtrs | 190 | 100 | 5700 | 0 | 228000 | C+S GST 18% I/P RD | 41040 | 269040 | 269040 | Approved | 0 | 0 | 4560 | 02 Dec 2021
GANGA DHAM TOWERS | 940 | 92537 | 02 Dec 2021 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1541 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 02 Dec 2021
GANGA DHAM TOWERS | 272 | 92534 | 01 Dec 2021 |  | GOURI INFRA | SAI MANDAP AND MANGAL KENDRA |  | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.8947 | Sq.Ft | 152 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 |  | 0 | 0 | 50 | 01 Dec 2021
GANGA DHAM TOWERS | 1170 | 92523 | 01 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1478 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 80mm dia.(L) | 25.5 | Mtrs | 270 | 100 | 172.13 | 0 | 6885 | C+S GST 18% I/P RD | 1239.3 | 8124.3 | 8124.3 | Approved | 0 | 0 | 2299 | 01 Dec 2021
GANGA DHAM TOWERS | 1170 | 92523 | 01 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1478 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 25mm dia-(L) | 471.5 | Mtrs | 110 | 100 | 1296.63 | 0 | 51865 | C+S GST 18% I/P RD | 9335.7 | 61200.7 | 61200.7 | Approved | 0 | 0 | 2299 | 01 Dec 2021
GANGA DHAM TOWERS | 1170 | 92523 | 01 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1478 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 40mm dia.(L) | 212.903 | Mtrs | 165 | 100 | 878.22 | 0 | 35129.01 | C+S GST 18% I/P RD | 6323.22 | 41452.23 | 41452.23 | Approved | 0 | 0 | 2299 | 01 Dec 2021
GANGA DHAM TOWERS | 1170 | 92523 | 01 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1478 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 50mm dia.(L) | 27.6 | Mtrs | 200 | 100 | 138 | 0 | 5520 | C+S GST 18% I/P RD | 993.6 | 6513.6 | 6513.6 | Approved | 0 | 0 | 2299 | 01 Dec 2021
GANGA DHAM TOWERS | 1170 | 92523 | 01 Dec 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1478 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 32mm dia.(L) | 110.9 | Mtrs | 140 | 100 | 388.15 | 0 | 15526 | C+S GST 18% I/P RD | 2794.68 | 18320.68 | 18320.68 | Approved | 0 | 0 | 2299 | 01 Dec 2021
GANGA DHAM TOWERS | 1209 | 92520 | 01 Dec 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 1636 | Sample Flat(1BHK) flooring breaking,material shift&cleaning | Breaker with Operator | 1 | Day | 900 | 100 | 22.5 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 19 | 01 Dec 2021
GANGA DHAM TOWERS | 1209 | 92520 | 01 Dec 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 1636 | Sample Flat(1BHK) flooring breaking,material shift&cleaning | Departmental Labour | 2 | No. | 500 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 19 | 01 Dec 2021
GANGA DHAM TOWERS | 389 | 92494 | 29 Nov 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1607 | Loading / Unloading Expenses | Unloading of tiles. | 31 | Metric Tonnes | 260 | 100 | 0 | 0 | 8060 | CGST 0% URD I/P | 0 | 8060 | 8060 | Approved | 0 | 0 | 0 | 29 Nov 2021
GANGA DHAM TOWERS | 389 | 92494 | 29 Nov 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1607 | Loading / Unloading Expenses | Unloading of AAC Blocks | 1518 | No. | 2 | 100 | 0 | 0 | 3036 | CGST 0% URD I/P | 0 | 3036 | 3036 | Approved | 0 | 0 | 0 | 29 Nov 2021
GANGA DHAM TOWERS | 801 | 92490 | 29 Nov 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1479 | B Sprinkler System | SITC GI Pipe C Class 50mm dia.(L) | 133.3333 | Mtrs | 150 | 100 | 500 | 0 | 20000 | C+S GST 18% I/P RD | 3600 | 23600 | 23600 | Approved | 0 | 0 | 1863 | 29 Nov 2021
GANGA DHAM TOWERS | 801 | 92490 | 29 Nov 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1479 | B Sprinkler System | SITC GI Pipe C Class 40mm dia.(L) | 458.7156 | Mtrs | 109 | 100 | 1250 | 0 | 50000 | C+S GST 18% I/P RD | 9000 | 59000 | 59000 | Approved | 0 | 0 | 1863 | 29 Nov 2021
GANGA DHAM TOWERS | 801 | 92490 | 29 Nov 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1479 | B Sprinkler System | SITC GI Pipe C Class 80mm dia.(L) | 80.6931 | Mtrs | 202 | 100 | 407.5 | 0 | 16300 | C+S GST 18% I/P RD | 2934 | 19234 | 19234 | Approved | 0 | 0 | 1863 | 29 Nov 2021
GANGA DHAM TOWERS | 801 | 92490 | 29 Nov 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1479 | B Sprinkler System | SITC GI Pipe C Class 32mm dia.(L) | 543.4783 | Mtrs | 92 | 100 | 1250 | 0 | 50000 | C+S GST 18% I/P RD | 9000 | 59000 | 59000 | Approved | 0 | 0 | 1863 | 29 Nov 2021
GANGA DHAM TOWERS | 801 | 92490 | 29 Nov 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1479 | B Sprinkler System | SITC GI Pipe C Class 25mm dia-(L) | 781.25 | Mtrs | 64 | 100 | 1250 | 0 | 50000 | C+S GST 18% I/P RD | 9000 | 59000 | 59000 | Approved | 0 | 0 | 1863 | 29 Nov 2021
GANGA DHAM TOWERS | 983 | 92489 | 29 Nov 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1949 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 200 | No. | 210 | 100 | 1050 | 0 | 42000 | C+S GST 18% I/P RD | 7560 | 49560 | 49560 | Approved | 0 | 0 | 420 | 29 Nov 2021
GANGA DHAM TOWERS | 1169 | 92488 | 29 Nov 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1476 | A Fire Fighting 14 Floors | Rossete Plate (M) | 245 | No. | 79 | 100 | 0 | 0 | 19355 | C+S GST 18% I/P RD | 3483.9 | 22838.9 | 22838.9 | Approved | 0 | 0 | 0 | 29 Nov 2021
GANGA DHAM TOWERS | 1169 | 92488 | 29 Nov 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1476 | A Fire Fighting 14 Floors | Sprinkler 15mm 68 dg Pendent (M) | 225 | No. | 229 | 100 | 0 | 0 | 51525 | C+S GST 18% I/P RD | 9274.5 | 60799.5 | 60799.5 | Approved | 0 | 0 | 0 | 29 Nov 2021
GANGA DHAM TOWERS | 1169 | 92488 | 29 Nov 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1476 | A Fire Fighting 14 Floors | Flexible Hose Pipe 25mm Dia (1mtr length) (M) | 245 | No. | 950 | 100 | 0 | 0 | 232750 | C+S GST 18% I/P RD | 41895 | 274645 | 274645 | Approved | 0 | 0 | 0 | 29 Nov 2021
GANGA DHAM TOWERS | 1195 | 92485 | 27 Nov 2021 |  | REAL GLASS AND ALUMINIUM FABRICATORS | REAL GLASS AND ALUMINIUM FABRICATORS | EV - 1928 | Ganga Collidium Sliding Window | Aluminium Window (m+l) - Mkt | 12 | Sq.Ft | 350 | 100 | 0 | 0 | 4200 | CGST 0% URD I/P | 0 | 4200 | 4200 | Approved | 0 | 0 | 47 | 27 Nov 2021
GANGA DHAM TOWERS | 1195 | 92485 | 27 Nov 2021 |  | REAL GLASS AND ALUMINIUM FABRICATORS | REAL GLASS AND ALUMINIUM FABRICATORS | EV - 1928 | Ganga Collidium Sliding Window | Labour Lumpsum - BC | 1 | No. | 500 | 100 | 0 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 47 | 27 Nov 2021
GANGA DHAM TOWERS | 1194 | 92484 | 27 Nov 2021 |  | REAL GLASS AND ALUMINIUM FABRICATORS | REAL GLASS AND ALUMINIUM FABRICATORS | EV - 1927 | Bund Garden Internal Sliding window | Aluminium Window (m+l) - Mkt | 13.5 | Sq.Ft | 350 | 100 | 0 | 0 | 4725 | CGST 0% URD I/P | 0 | 4725 | 4725 | Approved | 0 | 0 | 57 | 27 Nov 2021
GANGA DHAM TOWERS | 1194 | 92484 | 27 Nov 2021 |  | REAL GLASS AND ALUMINIUM FABRICATORS | REAL GLASS AND ALUMINIUM FABRICATORS | EV - 1927 | Bund Garden Internal Sliding window | Transport Charges | 1 | No. | 1000 | 100 | 0 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 57 | 27 Nov 2021
GANGA DHAM TOWERS | 1191 | 92483 | 27 Nov 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 1942 | Bund Garden Internal Painting Work | Satin Matt Paint (M+L)-BCo | 252.87 | Sq.Ft | 22 | 100 | 0 | 0 | 5563.14 | C+S GST 18% I/P RD | 1001.36 | 6564.5 | 6564.5 | Approved | 0 | 0 | 329 | 27 Nov 2021
GANGA DHAM TOWERS | 1191 | 92483 | 27 Nov 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 1942 | Bund Garden Internal Painting Work | Satin Matt Paint (M+L)-BCo | 369.54 | Sq.Ft | 22 | 100 | 0 | 0 | 8129.88 | C+S GST 18% I/P RD | 1463.38 | 9593.26 | 9593.26 | Approved | 0 | 0 | 329 | 27 Nov 2021
GANGA DHAM TOWERS | 1191 | 92483 | 27 Nov 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 1942 | Bund Garden Internal Painting Work | Satin Matt Paint (M+L)-BCo | 678.84 | Sq.Ft | 22 | 100 | 0 | 0 | 14934.48 | C+S GST 18% I/P RD | 2688.2 | 17622.68 | 17622.68 | Approved | 0 | 0 | 329 | 27 Nov 2021
GANGA DHAM TOWERS | 1191 | 92483 | 27 Nov 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 1942 | Bund Garden Internal Painting Work | Apex Paint (M+L) - BC | 353.65 | Sq.Ft | 12 | 100 | 0 | 0 | 4243.8 | C+S GST 18% I/P RD | 763.88 | 5007.68 | 5007.68 | Approved | 0 | 0 | 329 | 27 Nov 2021
GANGA DHAM TOWERS | 1193 | 92482 | 27 Nov 2021 |  | HARISH CHANDRA JADHAV ELECTRICALS | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1585 | Ganga Collidium Shop 32 Electrical work | Electrical Work - Dld | 1 | No. | 20000 | 100 | 0 | 0 | 20000 | C+S GST 18% I/P RD | 3600 | 23600 | 23600 | Approved | 0 | 0 | 200 | 27 Nov 2021
GANGA DHAM TOWERS | 1192 | 92481 | 27 Nov 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 1578 | Bund Gardern Police Station Excavation work with Breaker - | Excavation by Breaker | 1 | Day | 1300 | 100 | 0 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 13 | 27 Nov 2021
GANGA DHAM TOWERS | 1190 | 92480 | 27 Nov 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 2106 | Bund Garden Internal Electrical Work (M+L)- - 1 No. | Electrical work lumpsum-SO | 1 | No. | 28000 | 100 | 0 | 0 | 28000 | C+S GST 18% I/P RD | 5040 | 33040 | 33040 | Approved | 0 | 0 | 280 | 27 Nov 2021
GANGA DHAM TOWERS | 1189 | 92479 | 27 Nov 2021 |  | LALURAM B SHARMA | LALURAM B SHARMA | EV - 1744 | Ganga Collidium Shop 32 Carpentary work | Carpentary work lumpsum-BCo | 1 | No. | 5000 | 100 | 125 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 27 Nov 2021
GANGA DHAM TOWERS | 1179 | 92471 | 26 Nov 2021 |  | AMAN ENTERPRISES | AMAN ENTERPRISES | EV - 1741 | C Roller Compaction work | Roller- BC | 4 | Day | 4000 | 100 | 400 | 0 | 16000 | CGST 0% URD I/P | 0 | 16000 | 16000 | Approved | 0 | 0 | 270 | 26 Nov 2021
GANGA DHAM TOWERS | 1179 | 92471 | 26 Nov 2021 |  | AMAN ENTERPRISES | AMAN ENTERPRISES | EV - 1741 | C Roller Compaction work | Roller- BC | 2 | Day | 4000 | 100 | 200 | 0 | 8000 | CGST 0% URD I/P | 0 | 8000 | 8000 | Approved | 0 | 0 | 270 | 26 Nov 2021
GANGA DHAM TOWERS | 1179 | 92471 | 26 Nov 2021 |  | AMAN ENTERPRISES | AMAN ENTERPRISES | EV - 1741 | C Roller Compaction work | Shifting Charges-SO | 1 | No. | 1500 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 270 | 26 Nov 2021
GANGA DHAM TOWERS | 1179 | 92471 | 26 Nov 2021 |  | AMAN ENTERPRISES | AMAN ENTERPRISES | EV - 1741 | C Roller Compaction work | Shifting Charges-SO | 1 | No. | 1500 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 270 | 26 Nov 2021
GANGA DHAM TOWERS | 258 | 92470 | 26 Nov 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1498 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.6772 | Month | 2500 | 100 | 0 | 0 | 1693 | CGST 0% URD I/P | 0 | 1693 | 1693 | Approved | 0 | 0 | 17 | 26 Nov 2021
GANGA DHAM TOWERS | 237 | 92469 | 26 Nov 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1499 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.6773 | Month | 7000 | 100 | 0 | 0 | 4741 | CGST 0% URD I/P | 0 | 4741 | 4741 | Approved | 0 | 0 | 47 | 26 Nov 2021
GANGA DHAM TOWERS | 1157 | 92468 | 26 Nov 2021 |  | VECTOR SURVEYORS | VECTOR SURVEYORS | EV - 1583 | Substation - Total station survey of Bldg | Total Station Point marking- | 2 | Day | 4500 | 100 | 0 | 0 | 9000 | CGST 0% URD I/P | 0 | 9000 | 9000 | Approved | 0 | 0 | 90 | 26 Nov 2021
GANGA DHAM TOWERS | 804 | 92433 | 24 Nov 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1472 | B 101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 24 Nov 2021
GANGA DHAM TOWERS | 804 | 92433 | 24 Nov 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1472 | B 101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1395.8364 | Sq.Ft | 55 | 100 | 0 | 0 | 76771 | C+S GST 18% I/P RD | 13818.78 | 90589.78 | 90589.78 | Approved | 0 | 0 | 0 | 24 Nov 2021
GANGA DHAM TOWERS | 805 | 92432 | 24 Nov 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1470 | B 101 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1395.85 | Sq.Ft | 20 | 100 | 697.93 | 0 | 27917 | C+S GST 18% I/P RD | 5025.06 | 32942.06 | 32942.06 | Approved | 0 | 0 | 393 | 24 Nov 2021
GANGA DHAM TOWERS | 805 | 92432 | 24 Nov 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1470 | B 101 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 393 | 24 Nov 2021
GANGA DHAM TOWERS | 389 | 92431 | 23 Nov 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1420 | Loading / Unloading Expenses | Unloading of GYpsum- | 10 | Metric Tonnes | 200 | 100 | 0 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 0 | 23 Nov 2021
GANGA DHAM TOWERS | 389 | 92431 | 23 Nov 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1420 | Loading / Unloading Expenses | Unloading of tiles. | 65.5 | Metric Tonnes | 260 | 100 | 0 | 0 | 17030 | CGST 0% URD I/P | 0 | 17030 | 17030 | Approved | 0 | 0 | 0 | 23 Nov 2021
GANGA DHAM TOWERS | 1180 | 92429 | 23 Nov 2021 |  | M.S. CONSTRUCTION | M.S. CONSTRUCTION | EV - 1431 | A Terrace Scaffolding Work | Scaffolding work | 7680 | Sq.Ft | 5.5 | 100 | 1056 | 0 | 42240 | CGST 0% URD I/P | 0 | 42240 | 42240 | Approved | 0 | 0 | 422 | 23 Nov 2021
GANGA DHAM TOWERS | 1175 | 92422 | 22 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1819 | B 3rd Floor Counter Wash Basin | Granite Zero Joint-BCo | 61.668 | R.Ft | 200 | 100 | 308.34 | 0 | 12333.6 | C+S GST 18% I/P RD | 2220.04 | 14553.64 | 14553.64 | Approved | 0 | 0 | 2254 | 22 Nov 2021
GANGA DHAM TOWERS | 1175 | 92422 | 22 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1819 | B 3rd Floor Counter Wash Basin | Granite Patti- BCo | 61.668 | R.Ft | 65 | 100 | 100.21 | 0 | 4008.42 | C+S GST 18% I/P RD | 721.52 | 4729.94 | 4729.94 | Approved | 0 | 0 | 2254 | 22 Nov 2021
GANGA DHAM TOWERS | 1175 | 92422 | 22 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1819 | B 3rd Floor Counter Wash Basin | Granite Basin Counter | 49.005 | R.Ft | 1800 | 100 | 2205.23 | 0 | 88209 | C+S GST 18% I/P RD | 15877.62 | 104086.62 | 104086.62 | Approved | 0 | 0 | 2254 | 22 Nov 2021
GANGA DHAM TOWERS | 1175 | 92422 | 22 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1819 | B 3rd Floor Counter Wash Basin | Granite Bull Nose moulding | 56.151 | R.Ft | 85 | 100 | 119.32 | 0 | 4772.84 | C+S GST 18% I/P RD | 859.12 | 5631.96 | 5631.96 | Approved | 0 | 0 | 2254 | 22 Nov 2021
GANGA DHAM TOWERS | 1175 | 92422 | 22 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1819 | B 3rd Floor Counter Wash Basin | Granite Edge Polish | 96.822 | R.Ft | 35 | 100 | 84.72 | 0 | 3388.77 | C+S GST 18% I/P RD | 609.98 | 3998.75 | 3998.75 | Approved | 0 | 0 | 2254 | 22 Nov 2021
GANGA DHAM TOWERS | 497 | 92421 | 22 Nov 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1805 | B 2502 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 387 | 22 Nov 2021
GANGA DHAM TOWERS | 497 | 92421 | 22 Nov 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1805 | B 2402 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 387 | 22 Nov 2021
GANGA DHAM TOWERS | 497 | 92421 | 22 Nov 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1805 | B 2402 Gypsum Plaster | Gypsum on Wall (L) | 3581 | Sq.Ft | 4 | 100 | 358.1 | 0 | 14324 | C+S GST 18% I/P RD | 2578.32 | 16902.32 | 16902.32 | Approved | 0 | 0 | 387 | 22 Nov 2021
GANGA DHAM TOWERS | 497 | 92421 | 22 Nov 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1805 | B 2502 Gypsum Plaster | Gypsum on Wall (L) | 3581 | Sq.Ft | 4 | 100 | 358.1 | 0 | 14324 | C+S GST 18% I/P RD | 2578.32 | 16902.32 | 16902.32 | Approved | 0 | 0 | 387 | 22 Nov 2021
GANGA DHAM TOWERS | 495 | 92420 | 22 Nov 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1471 | B 2201 Gypsum Plaster | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 263 | 22 Nov 2021
GANGA DHAM TOWERS | 495 | 92420 | 22 Nov 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1471 | B 2201 Gypsum Plaster | Gypsum on Wall (L) | 4861.75 | Sq.Ft | 4 | 100 | 486.18 | 0 | 19447 | C+S GST 18% I/P RD | 3500.46 | 22947.46 | 22947.46 | Approved | 0 | 0 | 263 | 22 Nov 2021
GANGA DHAM TOWERS | 634 | 92402 | 19 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1818 | A 20th Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 6681 | 19 Nov 2021
GANGA DHAM TOWERS | 634 | 92402 | 19 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1818 | A 23rd Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 6681 | 19 Nov 2021
GANGA DHAM TOWERS | 634 | 92402 | 19 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1818 | A 23rd Floor Lift cladding | Italian Marble Bull Nosing | 573 | R.Ft | 76 | 100 | 1088.7 | 0 | 43548 | C+S GST 18% I/P RD | 7838.64 | 51386.64 | 51386.64 | Approved | 0 | 0 | 6681 | 19 Nov 2021
GANGA DHAM TOWERS | 634 | 92402 | 19 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1818 | A 22nd Floor Lift cladding | Italian Marble Bull Nosing | 573 | R.Ft | 76 | 100 | 1088.7 | 0 | 43548 | C+S GST 18% I/P RD | 7838.64 | 51386.64 | 51386.64 | Approved | 0 | 0 | 6681 | 19 Nov 2021
GANGA DHAM TOWERS | 634 | 92402 | 19 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1818 | A 21st Floor Lift cladding | Italian Marble Bull Nosing | 573 | R.Ft | 76 | 100 | 1088.7 | 0 | 43548 | C+S GST 18% I/P RD | 7838.64 | 51386.64 | 51386.64 | Approved | 0 | 0 | 6681 | 19 Nov 2021
GANGA DHAM TOWERS | 634 | 92402 | 19 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1818 | A 21st Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 6681 | 19 Nov 2021
GANGA DHAM TOWERS | 634 | 92402 | 19 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1818 | A 22nd Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 6681 | 19 Nov 2021
GANGA DHAM TOWERS | 634 | 92402 | 19 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1818 | A 19th Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 6681 | 19 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 23rd Floor Lift cladding | Italian Marble Border-BCo | 297 | R.Ft | 94 | 100 | 697.95 | 0 | 27918 | C+S GST 18% I/P RD | 5025.24 | 32943.24 | 32943.24 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 20th Floor Lift cladding | Italian Marble Border-BCo | 297 | R.Ft | 94 | 100 | 697.95 | 0 | 27918 | C+S GST 18% I/P RD | 5025.24 | 32943.24 | 32943.24 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 21st Floor Lift cladding | Italian Marble Border-BCo | 297 | R.Ft | 94 | 100 | 697.95 | 0 | 27918 | C+S GST 18% I/P RD | 5025.24 | 32943.24 | 32943.24 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 19th Floor Lift cladding | Italian Marble Border-BCo | 297 | R.Ft | 94 | 100 | 697.95 | 0 | 27918 | C+S GST 18% I/P RD | 5025.24 | 32943.24 | 32943.24 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 22nd Floor Lift cladding | Italian Marble Border-BCo | 297 | R.Ft | 94 | 100 | 697.95 | 0 | 27918 | C+S GST 18% I/P RD | 5025.24 | 32943.24 | 32943.24 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 20th Floor Lift cladding | Italian Marble Bull Nosing | 573 | R.Ft | 76 | 100 | 1088.7 | 0 | 43548 | C+S GST 18% I/P RD | 7838.64 | 51386.64 | 51386.64 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 20th Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 22nd Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 19th Floor Lift cladding | Italian Marble Bull Nosing | 537 | R.Ft | 76 | 100 | 1020.3 | 0 | 40812 | C+S GST 18% I/P RD | 7346.16 | 48158.16 | 48158.16 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 19th Floor Lift cladding | Italian Marble Bull Nosing | 36 | R.Ft | 76 | 100 | 68.4 | 0 | 2736 | C+S GST 18% I/P RD | 492.48 | 3228.48 | 3228.48 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 23rd Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 21st Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 19th Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 23rd Floor Lift cladding | V Grove - BCo | 137 | R.Ft | 108 | 100 | 369.9 | 0 | 14796 | C+S GST 18% I/P RD | 2663.28 | 17459.28 | 17459.28 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 20th Floor Lift cladding | V Grove - BCo | 137 | R.Ft | 108 | 100 | 369.9 | 0 | 14796 | C+S GST 18% I/P RD | 2663.28 | 17459.28 | 17459.28 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 22nd Floor Lift cladding | V Grove - BCo | 137 | R.Ft | 108 | 100 | 369.9 | 0 | 14796 | C+S GST 18% I/P RD | 2663.28 | 17459.28 | 17459.28 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 19th Floor Lift cladding | V Grove - BCo | 137 | R.Ft | 108 | 100 | 369.9 | 0 | 14796 | C+S GST 18% I/P RD | 2663.28 | 17459.28 | 17459.28 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 634 | 92390 | 18 Nov 2021 |  | R K INTERIOR | R K INTERIOR | EV - 1795 | A 21st Floor Lift cladding | V Grove - BCo | 137 | R.Ft | 108 | 100 | 369.9 | 0 | 14796 | C+S GST 18% I/P RD | 2663.28 | 17459.28 | 17459.28 | Approved | 0 | 0 | 8485 | 18 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 2002 Chemical Grouting Work | Chemical Grouting.- BC | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 2001 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 1801 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 18 | No. | 70 | 100 | 126 | 0 | 1260 | CGST 0% URD I/P | 0 | 1260 | 1260 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 1801 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 302 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 301 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 304 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 1801 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 5 | No. | 150 | 100 | 75 | 0 | 750 | CGST 0% URD I/P | 0 | 750 | 750 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 1801 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 275 | Sq.Ft | 19 | 100 | 522.5 | 0 | 5225 | CGST 0% URD I/P | 0 | 5225 | 5225 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 1801 Chemical & IPS Waterproofing | IPS W/P | 275 | Sq.Ft | 11 | 100 | 302.5 | 0 | 3025 | CGST 0% URD I/P | 0 | 3025 | 3025 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 303 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 2001 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 401 | 92388 | 17 Nov 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1475 | A 2002 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 230 | 17 Nov 2021
GANGA DHAM TOWERS | 455 | 92387 | 17 Nov 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1473 | A Bldg Flat No. 1703 Internal Plumbing PPR-C | Int Flat PPRC Work. | 3.5 | No. | 1400 | 100 | 122.5 | 0 | 4900 | CGST 0% URD I/P | 0 | 4900 | 4900 | Approved | 0 | 0 | 119 | 17 Nov 2021
GANGA DHAM TOWERS | 455 | 92387 | 17 Nov 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1473 | A Bldg Flat No. 1704 Internal Plumbing PPR-C | Int Flat PPRC Work. | 5 | No. | 1400 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 119 | 17 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 8th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 21st floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 10th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 22nd floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 14th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 15th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 13th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 10th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 12th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 16th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 17th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 5th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 6th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 15th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 7th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 22nd floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside1st floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 9th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 18th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 2nd floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 20th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 4th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 6th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 24th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 8th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 23rd floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 13th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 16th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 14th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 12th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 3rd floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 19th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 5th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 9th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 23rd floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 11th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 17th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 24th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 1st floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 3rd floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 19th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 21st floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 7th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 2nd floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 11th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 20th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Northside 18th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 844 | 92386 | 16 Nov 2021 | 187 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1386 | A Eastside 4th floor External Texture Painting | Scaffolding/Gondola work | 160 | Sq.Ft | 3.5 | 100 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 269 | 16 Nov 2021
GANGA DHAM TOWERS | 864 | 92382 | 16 Nov 2021 |  | B.D. DONGARE | PATIL CONSTRUCTION | EV - 1909 | B Core Cutting Work For Ac Work - | Core Cutting Work 5" BCE | 18 | No. | 300 | 100 | 0 | 0 | 5400 | C+S GST 18% I/P RD | 972 | 6372 | 6372 | Approved | 0 | 0 | 54 | 16 Nov 2021
GANGA DHAM TOWERS | 971 | 92381 | 16 Nov 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 2223 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 3" BCE | 58 | No. | 210 | 100 | 304.5 | 0 | 12180 | C+S GST 18% I/P RD | 2192.4 | 14372.4 | 14372.4 | Approved | 0 | 0 | 281 | 16 Nov 2021
GANGA DHAM TOWERS | 971 | 92381 | 16 Nov 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 2223 | B Bldg 1st to 26th Floor Core Cutting For Plumbing Work - | Core Cutting Work 5" BCE | 76 | No. | 210 | 100 | 399 | 0 | 15960 | C+S GST 18% I/P RD | 2872.8 | 18832.8 | 18832.8 | Approved | 0 | 0 | 281 | 16 Nov 2021
GANGA DHAM TOWERS | 632 | 92378 | 15 Nov 2021 | 378 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1391 | A 703 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 830 | 15 Nov 2021
GANGA DHAM TOWERS | 632 | 92378 | 15 Nov 2021 | 378 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1391 | A 104 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 830 | 15 Nov 2021
GANGA DHAM TOWERS | 632 | 92378 | 15 Nov 2021 | 378 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1391 | A 104 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 830 | 15 Nov 2021
GANGA DHAM TOWERS | 632 | 92378 | 15 Nov 2021 | 378 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1391 | A 1303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 830 | 15 Nov 2021
GANGA DHAM TOWERS | 632 | 92378 | 15 Nov 2021 | 378 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1391 | A 703 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 830 | 15 Nov 2021
GANGA DHAM TOWERS | 632 | 92378 | 15 Nov 2021 | 378 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1391 | A 1603 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 830 | 15 Nov 2021
GANGA DHAM TOWERS | 632 | 92378 | 15 Nov 2021 | 378 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1391 | A 1603 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 830 | 15 Nov 2021
GANGA DHAM TOWERS | 632 | 92378 | 15 Nov 2021 | 378 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1391 | A 1303 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 830 | 15 Nov 2021
GANGA DHAM TOWERS | 629 | 92377 | 15 Nov 2021 | 379 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1388 | A 1603 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 15 Nov 2021
GANGA DHAM TOWERS | 629 | 92377 | 15 Nov 2021 | 379 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1388 | A 1303 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 15 Nov 2021
GANGA DHAM TOWERS | 629 | 92377 | 15 Nov 2021 | 379 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1388 | A 703 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 15 Nov 2021
GANGA DHAM TOWERS | 629 | 92377 | 15 Nov 2021 | 379 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1388 | A 104 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 15 Nov 2021
GANGA DHAM TOWERS | 629 | 92377 | 15 Nov 2021 | 379 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1388 | A 1303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 15 Nov 2021
GANGA DHAM TOWERS | 629 | 92377 | 15 Nov 2021 | 379 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1388 | A 703 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 15 Nov 2021
GANGA DHAM TOWERS | 629 | 92377 | 15 Nov 2021 | 379 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1388 | A 104 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 15 Nov 2021
GANGA DHAM TOWERS | 629 | 92377 | 15 Nov 2021 | 379 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1388 | A 1603 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 15th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 6th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 22nd floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 23rd floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 5th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 7th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 21st floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 24th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 14th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 2nd floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 9th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 2nd floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 13th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 14th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 20th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 15th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 3rd floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 4th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 6th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 21st floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 12th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 12th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 8th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 11th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 8th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 11th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 3rd floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 19th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 16th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 5th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 7th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside1st floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 17th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 1st floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 20th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 22nd floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 16th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 18th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 18th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 4th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 9th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 10th floor External Texture Painting | Texture Paint (L) | 600 | Sq.Ft | 7.25 | 100 | 108.75 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 13th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 10th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 17th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 24th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 19th floor External Texture Painting | Texture Paint (L) | 582.069 | Sq.Ft | 7.25 | 100 | 105.5 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 22nd floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 14th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 15th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 16th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 13th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 14th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 24th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 2nd floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 20th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 5th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 9th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 15th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 7th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 22nd floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 11th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 17th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 7th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 23rd floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 23rd floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside1st floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 9th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 18th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 13th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 17th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 5th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 16th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 3rd floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 19th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 2nd floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 20th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 11th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 8th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 6th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 1st floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 3rd floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 19th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 6th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 24th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 10th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 12th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 21st floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 4th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 8th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 21st floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 4th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Northside 18th floor External Texture Painting | Scaffolding/Gondola work | 440.5714 | Sq.Ft | 3.5 | 100 | 38.55 | 0 | 1542 | C+S GST 18% I/P RD | 277.56 | 1819.56 | 1819.56 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 10th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 844 | 92376 | 15 Nov 2021 | 186 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1387 | A Eastside 12th floor External Texture Painting | Scaffolding/Gondola work | 422 | Sq.Ft | 3.5 | 100 | 36.93 | 0 | 1477 | C+S GST 18% I/P RD | 265.86 | 1742.86 | 1742.86 | Approved | 0 | 0 | 2739 | 15 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 5th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 22nd floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 24th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 15th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 3rd floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 4th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 17th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 19th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 10th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 17th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 9th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 18th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 19th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 23rd floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 9th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 13th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 6th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 21st floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 3rd floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 10th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 1st floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 16th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 18th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 4th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 21st floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 22nd floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 12th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 14th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 20th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 5th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 6th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 8th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside1st floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 12th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 15th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 24th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 11th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 13th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 14th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 2nd floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 16th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 11th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 20th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 7th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 2nd floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Eastside 8th floor External Texture Painting | Texture Paint (M) | 582.069 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4220 | C+S GST 18% I/P RD | 759.6 | 4979.6 | 4979.6 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 7th floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 845 | 92366 | 13 Nov 2021 | 185 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 1389 | A Northside 23rd floor External Texture Painting | Texture Paint (M) | 600 | Sq.Ft | 7.25 | 100 | 0 | 0 | 4350 | C+S GST 18% I/P RD | 783 | 5133 | 5133 | Approved | 0 | 0 | 0 | 13 Nov 2021
GANGA DHAM TOWERS | 940 | 92365 | 13 Nov 2021 |  | RESHMA JALINDAR CHANDGUDE | GREEN GARDEN DEVLOPERS AND MENTENANCE | EV - 1540 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 13 Nov 2021
GANGA DHAM TOWERS | 149 | 92363 | 12 Nov 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1404 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3330 | No. | 4 | 100 | 0 | 0 | 13320 | CGST 0% URD I/P | 0 | 13320 | 13320 | Approved | 0 | 0 | 0 | 12 Nov 2021
GANGA DHAM TOWERS | 751 | 92362 | 12 Nov 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 1581 | Testing of Gypsum | Testing of Gypsum | 0.5246 | No. | 4289 | 100 | 0 | 0 | 2250 | C+S GST 18% I/P RD | 405 | 2655 | 2655 | Approved | 0 | 0 | 45 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 7th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 14th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 16th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 9th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 2nd Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 4th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 20th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 17th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 279.21 | Sq.Ft | 4 | 100 | 27.92 | 0 | 1116.84 | C+S GST 18% I/P RD | 201.04 | 1317.88 | 1317.88 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 12th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 19th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 3rd Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 15th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 13th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 11th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 18th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 5th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 21st Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 24th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 8th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 6th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 23rd Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 1st Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 10th Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 84 | Sq.Ft | 4 | 100 | 8.4 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 12th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 18tth Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 2nd Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 20th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 7th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 1st Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 15th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 17th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 1024.33 | Sq.Ft | 4 | 100 | 102.43 | 0 | 4097.32 | C+S GST 18% I/P RD | 737.52 | 4834.84 | 4834.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 16th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 19th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 22nd Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 6th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 24th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 9th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 23rd Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 13th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 14th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 3rd Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 4th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 21st Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 618.47 | Sq.Ft | 4 | 100 | 61.85 | 0 | 2473.88 | C+S GST 18% I/P RD | 445.3 | 2919.18 | 2919.18 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 5th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 8th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 11th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 709 | 92360 | 12 Nov 2021 | 380 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1390 | A 10th Floor Staircase II Wall Gypsum Plaster | Gypsum on Wall (L) | 72 | Sq.Ft | 4 | 100 | 7.2 | 0 | 288 | C+S GST 18% I/P RD | 51.84 | 339.84 | 339.84 | Approved | 0 | 0 | 561 | 12 Nov 2021
GANGA DHAM TOWERS | 395 | 92359 | 12 Nov 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1392 | A Bldg Flat No. 2403 Gypsum Plaster | Gypsum on Wall (L) | 2198 | Sq.Ft | 4 | 100 | 219.8 | 0 | 8792 | C+S GST 18% I/P RD | 1582.56 | 10374.56 | 10374.56 | Approved | 0 | 0 | 88 | 12 Nov 2021
GANGA DHAM TOWERS | 413 | 92354 | 11 Nov 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1493 | Sales Oiifce Landscape Area . | Supervision Charges | 0.75 | Month | 4000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 300 | 11 Nov 2021
GANGA DHAM TOWERS | 178 | 92353 | 11 Nov 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1496 | Sales Oiifce Landscape Area . | Garden work. | 62.9889 | Day | 407.25 | 100 | 0 | 0 | 25652.23 | C+S GST 18% I/P RD | 4617.4 | 30269.63 | 30269.63 | Approved | 0 | 0 | 257 | 11 Nov 2021
GANGA DHAM TOWERS | 480 | 92352 | 11 Nov 2021 | 84 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1365 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 25.9997 | Day | 451.61 | 100 | 0 | 0 | 11741.72 | C+S GST 18% I/P RD | 2113.5 | 13855.22 | 13855.22 | Approved | 0 | 0 | 117 | 11 Nov 2021
GANGA DHAM TOWERS | 745 | 92351 | 11 Nov 2021 | 85 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1366 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 29.0005 | Day | 451.61 | 100 | 0 | 0 | 13096.92 | C+S GST 18% I/P RD | 2357.44 | 15454.36 | 15454.36 | Approved | 0 | 0 | 131 | 11 Nov 2021
GANGA DHAM TOWERS | 186 | 92350 | 11 Nov 2021 | 83 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1364 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 136.989 | Day | 451.613 | 100 | 0 | 0 | 61866.01 | C+S GST 18% I/P RD | 11135.88 | 73001.89 | 73001.89 | Approved | 0 | 0 | 799 | 11 Nov 2021
GANGA DHAM TOWERS | 186 | 92350 | 11 Nov 2021 | 83 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1364 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 31 | Day | 580.645 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 799 | 11 Nov 2021
GANGA DHAM TOWERS | 187 | 92349 | 11 Nov 2021 | 86 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1378 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 11 Nov 2021
GANGA DHAM TOWERS | 744 | 92348 | 11 Nov 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 1370 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 6 | 11 Nov 2021
GANGA DHAM TOWERS | 1094 | 92339 | 09 Nov 2021 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1500 | C Pump Charges From (Spt 21 To Feb 22) | Pumping Charges-BC | 1200 | Cu.Mtrs | 190 | 100 | 5700 | 0 | 228000 | C+S GST 18% I/P RD | 41040 | 269040 | 269040 | Approved | 0 | 0 | 4560 | 09 Nov 2021
GANGA DHAM TOWERS | 1162 | 92338 | 09 Nov 2021 |  | BHARAT BHIMRAO JADHAV | BHARAT BHIMRAO JADHAV | EV - 1407 | Garbage Collection& Shifting (Sales Office, Site office, Lab | Garbage Collection & Shifting | 1 | Month | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 50 | 09 Nov 2021
GANGA DHAM TOWERS | 126 | 92327 | 02 Nov 2021 |  | SANDIP VAMANRAO RUPNAWAR | KIRAN TUKARAM DHANAWADE | EV - 1399 | Site Expenses | Site Expenses -SO | 0.5361 | Month | 15000 | 100 | 0 | 0 | 8042 | CGST 0% URD I/P | 0 | 8042 | 8042 | Approved | 0 | 0 | 0 | 02 Nov 2021
GANGA DHAM TOWERS | 992 | 92326 | 02 Nov 2021 |  | SMITA ARTS | SMITA ARTS | EV - 1432 | Club House Toilet Sign Plate Fixing | SS Name Plate Making (4" x 8"). | 128 | Sq. inch | 9 | 100 | 0 | 0 | 1152 | C+S GST 18% I/P RD | 207.36 | 1359.36 | 1359.36 | Approved | 0 | 0 | 12 | 02 Nov 2021
GANGA DHAM TOWERS | 392 | 92305 | 01 Nov 2021 |  | J K INTERIOR | NKV HOME DEPOT | EV - 1311 | A Bldg Flat No. 1902 Gypsum Plaster | Gypsum on Wall (M) | 2930 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10255 | C+S GST 5% I/P RD | 512.76 | 10767.76 | 10767.76 | Approved | 0 | 0 | 455 | 01 Nov 2021
GANGA DHAM TOWERS | 392 | 92305 | 01 Nov 2021 |  | J K INTERIOR | NKV HOME DEPOT | EV - 1311 | A Bldg Flat No. 1802 Gypsum Plaster | Gypsum on Wall (M) | 3442 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12047 | C+S GST 5% I/P RD | 602.36 | 12649.36 | 12649.36 | Approved | 0 | 0 | 455 | 01 Nov 2021
GANGA DHAM TOWERS | 392 | 92305 | 01 Nov 2021 |  | J K INTERIOR | NKV HOME DEPOT | EV - 1311 | A Bldg Flat No. 1901 Gypsum Plaster | Gypsum on Wall (M) | 427.4286 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1496 | C+S GST 5% I/P RD | 74.8 | 1570.8 | 1570.8 | Approved | 0 | 0 | 455 | 01 Nov 2021
GANGA DHAM TOWERS | 392 | 92305 | 01 Nov 2021 |  | J K INTERIOR | NKV HOME DEPOT | EV - 1311 | A Bldg Flat No. 1901 Gypsum Plaster | Gypsum on Wall (M) | 2677.4286 | Sq.Ft | 3.5 | 100 | 0 | 0 | 9371 | C+S GST 5% I/P RD | 468.56 | 9839.56 | 9839.56 | Approved | 0 | 0 | 455 | 01 Nov 2021
GANGA DHAM TOWERS | 392 | 92305 | 01 Nov 2021 |  | J K INTERIOR | NKV HOME DEPOT | EV - 1311 | A Bldg Flat No. 1801 Gypsum Plaster | Gypsum on Wall (M) | 3522 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12327 | C+S GST 5% I/P RD | 616.36 | 12943.36 | 12943.36 | Approved | 0 | 0 | 455 | 01 Nov 2021
GANGA DHAM TOWERS | 272 | 92292 | 30 Oct 2021 | 184 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1395 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 67.6692 | Sq.Ft | 133 | 100 | 0 | 0 | 9000 | C+S GST 18% I/P RD | 1620 | 10620 | 10620 | Approved | 0 | 0 | 240 | 30 Oct 2021
GANGA DHAM TOWERS | 272 | 92292 | 30 Oct 2021 | 184 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1395 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.594 | Sq.Ft | 133 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 240 | 30 Oct 2021
GANGA DHAM TOWERS | 272 | 92292 | 30 Oct 2021 | 184 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1395 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 75.188 | Sq.Ft | 133 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 240 | 30 Oct 2021
GANGA DHAM TOWERS | 952 | 92291 | 30 Oct 2021 | R/21-22/44 | RAJESH MEHTA | R.M.Marbles | EV - 1293 | A 3rd Floor Staircase Sample 2 - 1 No. | Kota Champher | 50 | R.Ft | 7.5 | 100 | 9.38 | 0 | 375 | C+S GST 18% I/P RD | 67.5 | 442.5 | 442.5 | Approved | 0 | 0 | 112 | 30 Oct 2021
GANGA DHAM TOWERS | 952 | 92291 | 30 Oct 2021 | R/21-22/44 | RAJESH MEHTA | R.M.Marbles | EV - 1293 | A 3rd Floor Staircase Sample 2 - 1 No. | Kota Edge Polish- BCo | 54.16 | R.Ft | 7.5 | 100 | 10.16 | 0 | 406.2 | C+S GST 18% I/P RD | 73.12 | 479.32 | 479.32 | Approved | 0 | 0 | 112 | 30 Oct 2021
GANGA DHAM TOWERS | 952 | 92291 | 30 Oct 2021 | R/21-22/44 | RAJESH MEHTA | R.M.Marbles | EV - 1293 | A 3rd Floor Staircase Sample 2 - 1 No. | Kota Skirting (L)- BCO | 45.86 | R.Ft | 30 | 100 | 34.4 | 0 | 1375.8 | C+S GST 18% I/P RD | 247.64 | 1623.44 | 1623.44 | Approved | 0 | 0 | 112 | 30 Oct 2021
GANGA DHAM TOWERS | 952 | 92291 | 30 Oct 2021 | R/21-22/44 | RAJESH MEHTA | R.M.Marbles | EV - 1293 | A 3rd Floor Staircase Sample 2 - 1 No. | Kota Flooring (L)- BCO | 84.92 | Sq.Ft | 50 | 100 | 106.15 | 0 | 4246 | C+S GST 18% I/P RD | 764.28 | 5010.28 | 5010.28 | Approved | 0 | 0 | 112 | 30 Oct 2021
GANGA DHAM TOWERS | 952 | 92291 | 30 Oct 2021 | R/21-22/44 | RAJESH MEHTA | R.M.Marbles | EV - 1293 | A 3rd Floor Staircase Sample 2 - 1 No. | Kota Riser (L)- BCO | 50 | R.Ft | 45 | 100 | 56.25 | 0 | 2250 | C+S GST 18% I/P RD | 405 | 2655 | 2655 | Approved | 0 | 0 | 112 | 30 Oct 2021
GANGA DHAM TOWERS | 952 | 92291 | 30 Oct 2021 | R/21-22/44 | RAJESH MEHTA | R.M.Marbles | EV - 1293 | A 3rd Floor Staircase Sample 2 - 1 No. | Kota Tread (L) - DSP | 50 | R.Ft | 50 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 112 | 30 Oct 2021
GANGA DHAM TOWERS | 372 | 92290 | 30 Oct 2021 | BBE-17/21-22 | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1278 | B Bldg 32nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3562.0012 | Sq.Ft | 175.174 | 100 | 0 | 0 | 623970 | C+S GST 18% I/P RD | 112314.6 | 736284.6 | 736284.6 | Approved | 0 | 0 | 20888 | 30 Oct 2021
GANGA DHAM TOWERS | 372 | 92290 | 30 Oct 2021 | BBE-17/21-22 | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1278 | B Bldg 32nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2400.0023 | Sq.Ft | 175.174 | 100 | 0 | 0 | 420418 | C+S GST 18% I/P RD | 75675.24 | 496093.24 | 496093.24 | Approved | 0 | 0 | 20888 | 30 Oct 2021
GANGA DHAM TOWERS | 372 | 92289 | 30 Oct 2021 | BBE-16/21-22 | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1279 | B Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2436.9998 | Sq.Ft | 175.174 | 100 | 0 | 0 | 426899 | C+S GST 18% I/P RD | 76841.82 | 503740.82 | 503740.82 | Approved | 0 | 0 | 21017 | 30 Oct 2021
GANGA DHAM TOWERS | 372 | 92289 | 30 Oct 2021 | BBE-16/21-22 | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1279 | B Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3562.0012 | Sq.Ft | 175.174 | 100 | 0 | 0 | 623970 | C+S GST 18% I/P RD | 112314.6 | 736284.6 | 736284.6 | Approved | 0 | 0 | 21017 | 30 Oct 2021
GANGA DHAM TOWERS | 384 | 92286 | 30 Oct 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1734 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting Work 2" BCE | 30 | No. | 210 | 100 | 157.5 | 0 | 6300 | C+S GST 18% I/P RD | 1134 | 7434 | 7434 | Approved | 0 | 0 | 63 | 30 Oct 2021
GANGA DHAM TOWERS | 797 | 92285 | 30 Oct 2021 |  | J K INTERIOR | TASLIM NANHE KHAN |  | D 4th Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 192.2785 | Sq.Ft | 4 | 100 | 19.23 | 0 | 769.11 | CGST 0% URD I/P | 0 | 769.11 | 769.11 |  | 0 | 0 | 23 | 30 Oct 2021
GANGA DHAM TOWERS | 797 | 92285 | 30 Oct 2021 |  | J K INTERIOR | TASLIM NANHE KHAN |  | D 3rd Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 192.2785 | Sq.Ft | 4 | 100 | 19.23 | 0 | 769.11 | CGST 0% URD I/P | 0 | 769.11 | 769.11 |  | 0 | 0 | 23 | 30 Oct 2021
GANGA DHAM TOWERS | 797 | 92285 | 30 Oct 2021 |  | J K INTERIOR | TASLIM NANHE KHAN |  | D 2nd Floor Lobby Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 192.2785 | Sq.Ft | 4 | 100 | 19.23 | 0 | 769.11 | CGST 0% URD I/P | 0 | 769.11 | 769.11 |  | 0 | 0 | 23 | 30 Oct 2021
GANGA DHAM TOWERS | 698 | 92284 | 30 Oct 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1376 | D 1005 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.072 | Sq.Ft | 9 | 100 | 206.12 | 0 | 8244.65 | CGST 0% URD I/P | 0 | 8244.65 | 8244.65 | Approved | 0 | 0 | 350 | 30 Oct 2021
GANGA DHAM TOWERS | 698 | 92284 | 30 Oct 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1376 | D 1004 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.328 | Sq.Ft | 9 | 100 | 142.72 | 0 | 5708.95 | CGST 0% URD I/P | 0 | 5708.95 | 5708.95 | Approved | 0 | 0 | 350 | 30 Oct 2021
GANGA DHAM TOWERS | 698 | 92284 | 30 Oct 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1376 | D 1002 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 783.376 | Sq.Ft | 9 | 100 | 176.26 | 0 | 7050.38 | CGST 0% URD I/P | 0 | 7050.38 | 7050.38 | Approved | 0 | 0 | 350 | 30 Oct 2021
GANGA DHAM TOWERS | 698 | 92284 | 30 Oct 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1376 | D 1001 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.072 | Sq.Ft | 9 | 100 | 206.12 | 0 | 8244.65 | CGST 0% URD I/P | 0 | 8244.65 | 8244.65 | Approved | 0 | 0 | 350 | 30 Oct 2021
GANGA DHAM TOWERS | 698 | 92284 | 30 Oct 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 1376 | D 1003 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.328 | Sq.Ft | 9 | 100 | 142.72 | 0 | 5708.95 | CGST 0% URD I/P | 0 | 5708.95 | 5708.95 | Approved | 0 | 0 | 350 | 30 Oct 2021
GANGA DHAM TOWERS | 983 | 92283 | 30 Oct 2021 |  | PATIL CONSTRUCTION | RAM GUNAJI MANDLIK | EV - 1414 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 3" BCE | 122 | No. | 210 | 100 | 640.5 | 0 | 25620 | CGST 0% URD I/P | 0 | 25620 | 25620 | Approved | 0 | 0 | 256 | 30 Oct 2021
GANGA DHAM TOWERS | 983 | 92282 | 30 Oct 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1948 | A Bldg 1st to 26th Floor Core Cutting Ext Plumbing Work - | Core Cutting Work 3" BCE | 30 | No. | 210 | 100 | 157.5 | 0 | 6300 | C+S GST 18% I/P RD | 1134 | 7434 | 7434 | Approved | 0 | 0 | 483 | 30 Oct 2021
GANGA DHAM TOWERS | 983 | 92282 | 30 Oct 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1948 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 3" BCE | 140 | No. | 210 | 100 | 735 | 0 | 29400 | C+S GST 18% I/P RD | 5292 | 34692 | 34692 | Approved | 0 | 0 | 483 | 30 Oct 2021
GANGA DHAM TOWERS | 983 | 92282 | 30 Oct 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1948 | A Bldg 1st to 26th Floor Core Cut for Bathroom Outlets - 1 | Core Cutting Work 5" BCE | 60 | No. | 210 | 100 | 315 | 0 | 12600 | C+S GST 18% I/P RD | 2268 | 14868 | 14868 | Approved | 0 | 0 | 483 | 30 Oct 2021
GANGA DHAM TOWERS | 1169 | 92281 | 30 Oct 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1316 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 25mm dia.(M) | 420 | Mtrs | 386 | 100 | 0 | 0 | 162120 | C+S GST 18% I/P RD | 29181.6 | 191301.6 | 191301.6 | Approved | 0 | 0 | 0 | 30 Oct 2021
GANGA DHAM TOWERS | 1169 | 92281 | 30 Oct 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1316 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 80mm dia.(M) | 60 | Mtrs | 1079 | 100 | 0 | 0 | 64740 | C+S GST 18% I/P RD | 11653.2 | 76393.2 | 76393.2 | Approved | 0 | 0 | 0 | 30 Oct 2021
GANGA DHAM TOWERS | 1169 | 92281 | 30 Oct 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1316 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 32mm dia.(M) | 204 | Mtrs | 494 | 100 | 0 | 0 | 100776 | C+S GST 18% I/P RD | 18139.68 | 118915.68 | 118915.68 | Approved | 0 | 0 | 0 | 30 Oct 2021
GANGA DHAM TOWERS | 1169 | 92281 | 30 Oct 2021 |  | SAITECH FIRE SYSTEM PRIVATE LIMITED | SAITECH FIRE SYSTEM PRIVATE LIMITED | EV - 1316 | A Fire Fighting 14 Floors | SITC GI Pipe C Class 40mm dia.(M) | 204 | Mtrs | 568 | 100 | 0 | 0 | 115872 | C+S GST 18% I/P RD | 20856.96 | 136728.96 | 136728.96 | Approved | 0 | 0 | 0 | 30 Oct 2021
GANGA DHAM TOWERS | 1168 | 92275 | 29 Oct 2021 |  | SHRUSTI FLORALS | SHRUSTI FLORALS |  | B1- 1101 Garden Maintance Work (L) | Departmental Labour | 35 | No. | 450 | 100 | 0 | 0 | 15750 | CGST 0% URD I/P | 0 | 15750 | 15750 |  | 0 | 0 | 158 | 29 Oct 2021
GANGA DHAM TOWERS | 1167 | 92274 | 29 Oct 2021 |  | DILIP MARUTI MANDAVAKAR | DILIP MARUTI MANDAVAKAR | EV - 1590 | B1 -1101 Ms/ SS Work - 1 No. | Fabrication Work (L) - BCo | 388 | Kgs | 11 | 100 | 106.7 | 0 | 4268 | CGST 0% URD I/P | 0 | 4268 | 4268 | Approved | 0 | 0 | 43 | 29 Oct 2021
GANGA DHAM TOWERS | 1187 | 92258 | 28 Oct 2021 |  | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | DR. RAVIRAJ VASTU SPIRITUAL SERVICES (P) LTD | EV - 1270 | Ganga Dham Tower- Vastu Consultancy | Vastu Consultancy | 1 | No. | 29661 | 100 | 0 | 0 | 29661 | C+S GST 18% I/P RD | 5338.98 | 34999.98 | 34999.98 | Approved | 0 | 0 | 2966 | 28 Oct 2021
GANGA DHAM TOWERS | 1029 | 92254 | 28 Oct 2021 |  | BAJRANG ENTERPRISES | BAJRANG ENTERPRISES | EV - 1418 | HO Renovation Work | Carpentary work -Mkt | 1 | No. | 276126 | 100 | 0 | 0 | 276126 | IGST 18% I/P RD | 49702.68 | 325828.68 | 325828.68 | Approved | 0 | 0 | 2761 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 18.7959 | Mtrs | 49 | 100 | 0 | 0 | 921 | C+S GST 18% I/P RD | 165.78 | 1086.78 | 1086.78 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 504 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 6.4082 | Mtrs | 49 | 100 | 0 | 0 | 314 | C+S GST 18% I/P RD | 56.52 | 370.52 | 370.52 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 601 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 12.3061 | Mtrs | 49 | 100 | 0 | 0 | 603 | C+S GST 18% I/P RD | 108.54 | 711.54 | 711.54 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1001 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 17.3061 | Mtrs | 49 | 100 | 0 | 0 | 848 | C+S GST 18% I/P RD | 152.64 | 1000.64 | 1000.64 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 904 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 4.4082 | Mtrs | 49 | 100 | 0 | 0 | 216 | C+S GST 18% I/P RD | 38.88 | 254.88 | 254.88 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1002 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 10 | Mtrs | 49 | 100 | 0 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 602 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 27.5 | Mtrs | 49 | 100 | 0 | 0 | 1347.5 | C+S GST 18% I/P RD | 242.56 | 1590.06 | 1590.06 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1702 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 26.2041 | Mtrs | 49 | 100 | 0 | 0 | 1284 | C+S GST 18% I/P RD | 231.12 | 1515.12 | 1515.12 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 802 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 11.7959 | Mtrs | 49 | 100 | 0 | 0 | 578 | C+S GST 18% I/P RD | 104.04 | 682.04 | 682.04 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1003 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 3 | Mtrs | 49 | 100 | 0 | 0 | 147 | C+S GST 18% I/P RD | 26.46 | 173.46 | 173.46 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1601 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 11.2041 | Mtrs | 49 | 100 | 0 | 0 | 549 | C+S GST 18% I/P RD | 98.82 | 647.82 | 647.82 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1602 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 27.5 | Mtrs | 49 | 100 | 0 | 0 | 1347.5 | C+S GST 18% I/P RD | 242.56 | 1590.06 | 1590.06 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 401 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.102 | Mtrs | 49 | 100 | 0 | 0 | 1034 | C+S GST 18% I/P RD | 186.12 | 1220.12 | 1220.12 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 503 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 2.7959 | Mtrs | 49 | 100 | 0 | 0 | 137 | C+S GST 18% I/P RD | 24.66 | 161.66 | 161.66 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1603 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 14.5102 | Mtrs | 49 | 100 | 0 | 0 | 711 | C+S GST 18% I/P RD | 127.98 | 838.98 | 838.98 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 701 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 8.898 | Mtrs | 49 | 100 | 0 | 0 | 436 | C+S GST 18% I/P RD | 78.48 | 514.48 | 514.48 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 503 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 10.1983 | Mtrs | 60.5 | 100 | 0 | 0 | 617 | C+S GST 18% I/P RD | 111.06 | 728.06 | 728.06 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 25.5041 | Mtrs | 60.5 | 100 | 0 | 0 | 1543 | C+S GST 18% I/P RD | 277.74 | 1820.74 | 1820.74 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 47.2562 | Mtrs | 60.5 | 100 | 0 | 0 | 2859 | C+S GST 18% I/P RD | 514.62 | 3373.62 | 3373.62 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1702 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 51.157 | Mtrs | 60.5 | 100 | 0 | 0 | 3095 | C+S GST 18% I/P RD | 557.1 | 3652.1 | 3652.1 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 802 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 23.1074 | Mtrs | 60.5 | 100 | 0 | 0 | 1398 | C+S GST 18% I/P RD | 251.64 | 1649.64 | 1649.64 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1002 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 23.2066 | Mtrs | 60.5 | 100 | 0 | 0 | 1404 | C+S GST 18% I/P RD | 252.72 | 1656.72 | 1656.72 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1603 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 28.8926 | Mtrs | 60.5 | 100 | 0 | 0 | 1748 | C+S GST 18% I/P RD | 314.64 | 2062.64 | 2062.64 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1003 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 14.7934 | Mtrs | 60.5 | 100 | 0 | 0 | 895 | C+S GST 18% I/P RD | 161.1 | 1056.1 | 1056.1 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 401 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 49.7025 | Mtrs | 60.5 | 100 | 0 | 0 | 3007 | C+S GST 18% I/P RD | 541.26 | 3548.26 | 3548.26 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 18.7934 | Mtrs | 60.5 | 100 | 0 | 0 | 1137 | C+S GST 18% I/P RD | 204.66 | 1341.66 | 1341.66 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 704 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 17.405 | Mtrs | 60.5 | 100 | 0 | 0 | 1053 | C+S GST 18% I/P RD | 189.54 | 1242.54 | 1242.54 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 904 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 10.595 | Mtrs | 60.5 | 100 | 0 | 0 | 641 | C+S GST 18% I/P RD | 115.38 | 756.38 | 756.38 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 32 | Mtrs | 60.5 | 100 | 0 | 0 | 1936 | C+S GST 18% I/P RD | 348.48 | 2284.48 | 2284.48 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1602 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 37.405 | Mtrs | 60.5 | 100 | 0 | 0 | 2263 | C+S GST 18% I/P RD | 407.34 | 2670.34 | 2670.34 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 601 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 30.2989 | Mtrs | 60.5 | 100 | 0 | 0 | 1833.08 | C+S GST 18% I/P RD | 329.96 | 2163.04 | 2163.04 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1001 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 46.2975 | Mtrs | 60.5 | 100 | 0 | 0 | 2801 | C+S GST 18% I/P RD | 504.18 | 3305.18 | 3305.18 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 504 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 18.1983 | Mtrs | 60.5 | 100 | 0 | 0 | 1101 | C+S GST 18% I/P RD | 198.18 | 1299.18 | 1299.18 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 703 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 10.1983 | Mtrs | 60.5 | 100 | 0 | 0 | 617 | C+S GST 18% I/P RD | 111.06 | 728.06 | 728.06 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 602 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 51.7025 | Mtrs | 60.5 | 100 | 0 | 0 | 3128 | C+S GST 18% I/P RD | 563.04 | 3691.04 | 3691.04 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1602 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 38.8 | Mtrs | 345 | 100 | 0 | 0 | 13386 | C+S GST 18% I/P RD | 2409.48 | 15795.48 | 15795.48 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 401 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 40 | Mtrs | 345 | 100 | 0 | 0 | 13800 | C+S GST 18% I/P RD | 2484 | 16284 | 16284 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 704 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 12.8 | Mtrs | 345 | 100 | 0 | 0 | 4416 | C+S GST 18% I/P RD | 794.88 | 5210.88 | 5210.88 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 904 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 10.5014 | Mtrs | 345 | 100 | 0 | 0 | 3623 | C+S GST 18% I/P RD | 652.14 | 4275.14 | 4275.14 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 703 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 9 | Mtrs | 345 | 100 | 0 | 0 | 3105 | C+S GST 18% I/P RD | 558.9 | 3663.9 | 3663.9 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 28.5 | Mtrs | 345 | 100 | 0 | 0 | 9832.5 | C+S GST 18% I/P RD | 1769.86 | 11602.36 | 11602.36 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 602 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 43.4 | Mtrs | 345 | 100 | 0 | 0 | 14973 | C+S GST 18% I/P RD | 2695.14 | 17668.14 | 17668.14 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 701 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 18.3014 | Mtrs | 345 | 100 | 0 | 0 | 6314 | C+S GST 18% I/P RD | 1136.52 | 7450.52 | 7450.52 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1701 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 36.2493 | Mtrs | 345 | 100 | 0 | 0 | 12506 | C+S GST 18% I/P RD | 2251.08 | 14757.08 | 14757.08 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 28 | Mtrs | 345 | 100 | 0 | 0 | 9660 | C+S GST 18% I/P RD | 1738.8 | 11398.8 | 11398.8 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 503 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 7.3014 | Mtrs | 345 | 100 | 0 | 0 | 2519 | C+S GST 18% I/P RD | 453.42 | 2972.42 | 2972.42 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1002 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 19.5014 | Mtrs | 345 | 100 | 0 | 0 | 6728 | C+S GST 18% I/P RD | 1211.04 | 7939.04 | 7939.04 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1001 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 36.3014 | Mtrs | 345 | 100 | 0 | 0 | 12524 | C+S GST 18% I/P RD | 2254.32 | 14778.32 | 14778.32 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1003 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 9.5014 | Mtrs | 345 | 100 | 0 | 0 | 3278 | C+S GST 18% I/P RD | 590.04 | 3868.04 | 3868.04 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 504 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 12.8 | Mtrs | 345 | 100 | 0 | 0 | 4416 | C+S GST 18% I/P RD | 794.88 | 5210.88 | 5210.88 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1603 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 21.4 | Mtrs | 345 | 100 | 0 | 0 | 7383 | C+S GST 18% I/P RD | 1328.94 | 8711.94 | 8711.94 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 10.6 | Mtrs | 345 | 100 | 0 | 0 | 3657 | C+S GST 18% I/P RD | 658.26 | 4315.26 | 4315.26 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 802 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 19 | Mtrs | 345 | 100 | 0 | 0 | 6555 | C+S GST 18% I/P RD | 1179.9 | 7734.9 | 7734.9 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1702 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 35.5014 | Mtrs | 345 | 100 | 0 | 0 | 12248 | C+S GST 18% I/P RD | 2204.64 | 14452.64 | 14452.64 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 530 | 92251 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1302 | A 1601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 17.4 | Mtrs | 345 | 100 | 0 | 0 | 6003 | C+S GST 18% I/P RD | 1080.54 | 7083.54 | 7083.54 | Approved | 0 | 0 | 0 | 28 Oct 2021
GANGA DHAM TOWERS | 1037 | 92250 | 28 Oct 2021 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 1317 | Head Office Security Service | Security Guard AIE - | 62 | Day | 419.35 | 100 | 0 | 0 | 25999.7 | C+S GST 18% RCM | 4679.94 | 30679.64 | 30679.64 | Approved | 0 | 0 | 260 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1602 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 27.5 | Mtrs | 21 | 100 | 0 | 0 | 577.5 | C+S GST 18% I/P RD | 103.96 | 681.46 | 681.46 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 904 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 4.381 | Mtrs | 21 | 100 | 0 | 0 | 92 | C+S GST 18% I/P RD | 16.56 | 108.56 | 108.56 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1601 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 11.1905 | Mtrs | 21 | 100 | 0 | 0 | 235 | C+S GST 18% I/P RD | 42.3 | 277.3 | 277.3 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1701 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 16.8095 | Mtrs | 21 | 100 | 0 | 0 | 353 | C+S GST 18% I/P RD | 63.54 | 416.54 | 416.54 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 401 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.0952 | Mtrs | 21 | 100 | 0 | 0 | 443 | C+S GST 18% I/P RD | 79.74 | 522.74 | 522.74 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 703 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 2.0952 | Mtrs | 21 | 100 | 0 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 701 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 2.7143 | Mtrs | 21 | 100 | 0 | 0 | 57 | C+S GST 18% I/P RD | 10.26 | 67.26 | 67.26 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1702 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 26.1905 | Mtrs | 21 | 100 | 0 | 0 | 550 | C+S GST 18% I/P RD | 99 | 649 | 649 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 602 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 27.5 | Mtrs | 21 | 100 | 0 | 0 | 577.5 | C+S GST 18% I/P RD | 103.96 | 681.46 | 681.46 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 18.8095 | Mtrs | 21 | 100 | 0 | 0 | 395 | C+S GST 18% I/P RD | 71.1 | 466.1 | 466.1 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 503 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 2.8095 | Mtrs | 21 | 100 | 0 | 0 | 59 | C+S GST 18% I/P RD | 10.62 | 69.62 | 69.62 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 1.5238 | Mtrs | 21 | 100 | 0 | 0 | 32 | C+S GST 18% I/P RD | 5.76 | 37.76 | 37.76 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1003 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 5.381 | Mtrs | 21 | 100 | 0 | 0 | 113 | C+S GST 18% I/P RD | 20.34 | 133.34 | 133.34 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1001 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 17.2857 | Mtrs | 21 | 100 | 0 | 0 | 363 | C+S GST 18% I/P RD | 65.34 | 428.34 | 428.34 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 802 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 11.8095 | Mtrs | 21 | 100 | 0 | 0 | 248 | C+S GST 18% I/P RD | 44.64 | 292.64 | 292.64 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 704 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 6.1905 | Mtrs | 21 | 100 | 0 | 0 | 130 | C+S GST 18% I/P RD | 23.4 | 153.4 | 153.4 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 504 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 6.381 | Mtrs | 21 | 100 | 0 | 0 | 134 | C+S GST 18% I/P RD | 24.12 | 158.12 | 158.12 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 601 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 16.8571 | Mtrs | 21 | 100 | 0 | 0 | 354 | C+S GST 18% I/P RD | 63.72 | 417.72 | 417.72 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1603 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 14.5238 | Mtrs | 21 | 100 | 0 | 0 | 305 | C+S GST 18% I/P RD | 54.9 | 359.9 | 359.9 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1002 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 13.619 | Mtrs | 21 | 100 | 0 | 0 | 286 | C+S GST 18% I/P RD | 51.48 | 337.48 | 337.48 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 704 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 12.8 | Mtrs | 105 | 100 | 0 | 0 | 1344 | C+S GST 18% I/P RD | 241.92 | 1585.92 | 1585.92 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 701 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 18.3048 | Mtrs | 105 | 100 | 0 | 0 | 1922 | C+S GST 18% I/P RD | 345.96 | 2267.96 | 2267.96 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 503 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 7.3048 | Mtrs | 105 | 100 | 0 | 0 | 767 | C+S GST 18% I/P RD | 138.06 | 905.06 | 905.06 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1603 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 21.4 | Mtrs | 105 | 100 | 0 | 0 | 2247 | C+S GST 18% I/P RD | 404.46 | 2651.46 | 2651.46 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 10.6 | Mtrs | 105 | 100 | 0 | 0 | 1113 | C+S GST 18% I/P RD | 200.34 | 1313.34 | 1313.34 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1602 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 38.8 | Mtrs | 105 | 100 | 0 | 0 | 4074 | C+S GST 18% I/P RD | 733.32 | 4807.32 | 4807.32 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 28.5048 | Mtrs | 105 | 100 | 0 | 0 | 2993 | C+S GST 18% I/P RD | 538.74 | 3531.74 | 3531.74 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 401 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 40 | Mtrs | 105 | 100 | 0 | 0 | 4200 | C+S GST 18% I/P RD | 756 | 4956 | 4956 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 802 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 19 | Mtrs | 105 | 100 | 0 | 0 | 1995 | C+S GST 18% I/P RD | 359.1 | 2354.1 | 2354.1 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1701 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 36.2476 | Mtrs | 105 | 100 | 0 | 0 | 3806 | C+S GST 18% I/P RD | 685.08 | 4491.08 | 4491.08 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 28 | Mtrs | 105 | 100 | 0 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 17.4 | Mtrs | 105 | 100 | 0 | 0 | 1827 | C+S GST 18% I/P RD | 328.86 | 2155.86 | 2155.86 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1001 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 36.3048 | Mtrs | 105 | 100 | 0 | 0 | 3812 | C+S GST 18% I/P RD | 686.16 | 4498.16 | 4498.16 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 602 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 43.4 | Mtrs | 105 | 100 | 0 | 0 | 4557 | C+S GST 18% I/P RD | 820.26 | 5377.26 | 5377.26 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 504 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 12.8 | Mtrs | 105 | 100 | 0 | 0 | 1344 | C+S GST 18% I/P RD | 241.92 | 1585.92 | 1585.92 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1002 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 19.5048 | Mtrs | 105 | 100 | 0 | 0 | 2048 | C+S GST 18% I/P RD | 368.64 | 2416.64 | 2416.64 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1702 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 35.5048 | Mtrs | 105 | 100 | 0 | 0 | 3728 | C+S GST 18% I/P RD | 671.04 | 4399.04 | 4399.04 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 904 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 10.5048 | Mtrs | 105 | 100 | 0 | 0 | 1103 | C+S GST 18% I/P RD | 198.54 | 1301.54 | 1301.54 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 703 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 9 | Mtrs | 105 | 100 | 0 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1003 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 9.5048 | Mtrs | 105 | 100 | 0 | 0 | 998 | C+S GST 18% I/P RD | 179.64 | 1177.64 | 1177.64 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 704 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 17.3846 | Mtrs | 19.5 | 100 | 0 | 0 | 339 | C+S GST 18% I/P RD | 61.02 | 400.02 | 400.02 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 504 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 18.2051 | Mtrs | 19.5 | 100 | 0 | 0 | 355 | C+S GST 18% I/P RD | 63.9 | 418.9 | 418.9 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 703 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 10.2051 | Mtrs | 19.5 | 100 | 0 | 0 | 199 | C+S GST 18% I/P RD | 35.82 | 234.82 | 234.82 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 47.2308 | Mtrs | 19.5 | 100 | 0 | 0 | 921 | C+S GST 18% I/P RD | 165.78 | 1086.78 | 1086.78 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 503 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 10.2051 | Mtrs | 19.5 | 100 | 0 | 0 | 199 | C+S GST 18% I/P RD | 35.82 | 234.82 | 234.82 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1602 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 37.3846 | Mtrs | 19.5 | 100 | 0 | 0 | 729 | C+S GST 18% I/P RD | 131.22 | 860.22 | 860.22 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1603 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 28.9231 | Mtrs | 19.5 | 100 | 0 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 904 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 10.6154 | Mtrs | 19.5 | 100 | 0 | 0 | 207 | C+S GST 18% I/P RD | 37.26 | 244.26 | 244.26 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 802 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 23.0769 | Mtrs | 19.5 | 100 | 0 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1702 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 51.1282 | Mtrs | 19.5 | 100 | 0 | 0 | 997 | C+S GST 18% I/P RD | 179.46 | 1176.46 | 1176.46 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 401 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 49.6923 | Mtrs | 19.5 | 100 | 0 | 0 | 969 | C+S GST 18% I/P RD | 174.42 | 1143.42 | 1143.42 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1002 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 23.1795 | Mtrs | 19.5 | 100 | 0 | 0 | 452 | C+S GST 18% I/P RD | 81.36 | 533.36 | 533.36 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 12.4615 | Mtrs | 19.5 | 100 | 0 | 0 | 243 | C+S GST 18% I/P RD | 43.74 | 286.74 | 286.74 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 602 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 51.6923 | Mtrs | 19.5 | 100 | 0 | 0 | 1008 | C+S GST 18% I/P RD | 181.44 | 1189.44 | 1189.44 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 32 | Mtrs | 19.5 | 100 | 0 | 0 | 624 | C+S GST 18% I/P RD | 112.32 | 736.32 | 736.32 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 5.2821 | Mtrs | 19.5 | 100 | 0 | 0 | 103 | C+S GST 18% I/P RD | 18.54 | 121.54 | 121.54 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 601 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 36.9231 | Mtrs | 19.5 | 100 | 0 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1001 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 46.3077 | Mtrs | 19.5 | 100 | 0 | 0 | 903 | C+S GST 18% I/P RD | 162.54 | 1065.54 | 1065.54 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 532 | 92246 | 28 Oct 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS PRIVATE LIMITED | EV - 1303 | A 1003 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 14.8205 | Mtrs | 19.5 | 100 | 0 | 0 | 289 | C+S GST 18% I/P RD | 52.02 | 341.02 | 341.02 | Approved | 0 | 0 | 1268 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92245 | 28 Oct 2021 |  | B & B ENTERPRISES | USHA ENTERPRISES |  | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 83.92 | Sq.Ft | 150 | 100 | 0 | 0 | 12588 | IGST 18% I/P RD | 2265.84 | 14853.84 | 14853.84 |  | 0 | 0 | 768 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92245 | 28 Oct 2021 |  | B & B ENTERPRISES | USHA ENTERPRISES |  | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 73.16 | Sq.Ft | 150 | 100 | 0 | 0 | 10974 | IGST 18% I/P RD | 1975.32 | 12949.32 | 12949.32 |  | 0 | 0 | 768 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92245 | 28 Oct 2021 |  | B & B ENTERPRISES | USHA ENTERPRISES |  | B Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 141.5308 | Sq.Ft | 130 | 100 | 0 | 0 | 18399 | C+S GST 18% I/P RD | 3311.82 | 21710.82 | 21710.82 |  | 0 | 0 | 768 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92245 | 28 Oct 2021 |  | B & B ENTERPRISES | USHA ENTERPRISES |  | B Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 126.6231 | Sq.Ft | 130 | 100 | 0 | 0 | 16461 | IGST 18% I/P RD | 2962.98 | 19423.98 | 19423.98 |  | 0 | 0 | 768 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92245 | 28 Oct 2021 |  | B & B ENTERPRISES | USHA ENTERPRISES |  | B Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 131.4214 | Sq.Ft | 140 | 100 | 0 | 0 | 18399 | IGST 18% I/P RD | 3311.82 | 21710.82 | 21710.82 |  | 0 | 0 | 768 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92244 | 28 Oct 2021 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 1400 | B Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 33.3333 | Sq.Ft | 150 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 130 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92244 | 28 Oct 2021 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 1400 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10 | Sq.Ft | 150 | 100 | 0 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 130 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92244 | 28 Oct 2021 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 1400 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10 | Sq.Ft | 150 | 100 | 0 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 130 | 28 Oct 2021
GANGA DHAM TOWERS | 372 | 92244 | 28 Oct 2021 |  | B & B ENTERPRISES | PRAKASH CONTRACTOR | EV - 1400 | B Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.2581 | Sq.Ft | 155 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 130 | 28 Oct 2021
GANGA DHAM TOWERS | 194 | 92243 | 28 Oct 2021 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 2260 | Stilt Floor (102 Level) PT Slab Work | Post Tensioning Work -BC | 0.9585 | Metric Tonnes | 116000 | 37.5 | 0 | 0 | 41695 | C+S GST 18% I/P RD | 7505.1 | 49200.1 | 49200.1 | Approved | 0 | 0 | 1060 | 28 Oct 2021
GANGA DHAM TOWERS | 194 | 92243 | 28 Oct 2021 |  | UTRACON STRUCTURAL SYSTEM PVT. LTD. | UTRACON STRUCTURAL SYSTEM PVT. LTD. | EV - 2260 | P3 Parking Floor (108.00 Level) PT Slab Work | Post Tensioning Work -BC | 0.2599 | Metric Tonnes | 116000 | 37.5 | 0 | 0 | 11305 | C+S GST 18% I/P RD | 2034.9 | 13339.9 | 13339.9 | Approved | 0 | 0 | 1060 | 28 Oct 2021
GANGA DHAM TOWERS | 272 | 92230 | 27 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1403 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 33.1269 | Sq.Ft | 161.5 | 100 | 0 | 0 | 5350 | CGST 0% URD I/P | 0 | 5350 | 5350 | Approved | 0 | 0 | 104 | 27 Oct 2021
GANGA DHAM TOWERS | 272 | 92230 | 27 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1403 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 30.9598 | Sq.Ft | 161.5 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 104 | 27 Oct 2021
GANGA DHAM TOWERS | 695 | 92217 | 26 Oct 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1297 | B P2 Parking Beam & Ceiling Plaster | Gypsum PlasterTikhi Dhada (M) rate diff. | 72.7273 | Sq.Ft | 5.5 | 100 | 0 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 4 | 26 Oct 2021
GANGA DHAM TOWERS | 1142 | 92213 | 26 Oct 2021 |  | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1385 | A 1901 NOC | Italian Marble Flooring - BCo | 164.215 | Sq.Ft | 55 | 100 | 225.8 | 0 | 9031.83 | C+S GST 18% I/P RD | 1625.72 | 10657.55 | 10657.55 | Approved | 0 | 0 | 90 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 44.559 | Sq.Ft | 21 | 100 | 23.39 | 0 | 935.74 | C+S GST 18% I/P RD | 168.44 | 1104.18 | 1104.18 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 21 | 100 | 20.6 | 0 | 823.85 | C+S GST 18% I/P RD | 148.3 | 972.15 | 972.15 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Parents Toilet dado | Dado BC | 81.75 | Sq.Ft | 24 | 100 | 49.05 | 0 | 1962 | C+S GST 18% I/P RD | 353.16 | 2315.16 | 2315.16 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Master Toilet dado | Dado BC | 67.78 | Sq.Ft | 24 | 100 | 40.67 | 0 | 1626.72 | C+S GST 18% I/P RD | 292.8 | 1919.52 | 1919.52 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Children Toilet | Dado BC | 42.72 | Sq.Ft | 24 | 100 | 25.63 | 0 | 1025.28 | C+S GST 18% I/P RD | 184.56 | 1209.84 | 1209.84 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1901 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.7 | Sq.Ft | 60 | 100 | 859.05 | 0 | 34362 | C+S GST 18% I/P RD | 6185.16 | 40547.16 | 40547.16 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 2001 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 228.2 | Sq.Ft | 60 | 100 | 342.3 | 0 | 13692 | C+S GST 18% I/P RD | 2464.56 | 16156.56 | 16156.56 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 2001 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 60 | 100 | 200.78 | 0 | 8031 | C+S GST 18% I/P RD | 1445.58 | 9476.58 | 9476.58 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1901 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 60 | 100 | 200.78 | 0 | 8031 | C+S GST 18% I/P RD | 1445.58 | 9476.58 | 9476.58 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1901 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 228.2 | Sq.Ft | 60 | 100 | 342.3 | 0 | 13692 | C+S GST 18% I/P RD | 2464.56 | 16156.56 | 16156.56 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1901 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.97 | Sq.Ft | 60 | 100 | 316.46 | 0 | 12658.2 | C+S GST 18% I/P RD | 2278.48 | 14936.68 | 14936.68 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 2001 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.97 | Sq.Ft | 60 | 100 | 316.46 | 0 | 12658.2 | C+S GST 18% I/P RD | 2278.48 | 14936.68 | 14936.68 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 2001 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.7 | Sq.Ft | 60 | 100 | 859.05 | 0 | 34362 | C+S GST 18% I/P RD | 6185.16 | 40547.16 | 40547.16 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Powder Toilet dado | Dado BC | 42.95 | Sq.Ft | 24 | 100 | 25.77 | 0 | 1030.8 | C+S GST 18% I/P RD | 185.54 | 1216.34 | 1216.34 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Powder Toilet dado | Dado BC | 95.25 | Sq.Ft | 22 | 100 | 52.39 | 0 | 2095.5 | C+S GST 18% I/P RD | 377.2 | 2472.7 | 2472.7 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Parents Toilet dado | Dado BC | 152.52 | Sq.Ft | 22 | 100 | 83.89 | 0 | 3355.44 | C+S GST 18% I/P RD | 603.98 | 3959.42 | 3959.42 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Master Toilet dado | Dado BC | 123.51 | Sq.Ft | 22 | 100 | 67.93 | 0 | 2717.22 | C+S GST 18% I/P RD | 489.1 | 3206.32 | 3206.32 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Children Toilet | Dado BC | 188.43 | Sq.Ft | 22 | 100 | 103.64 | 0 | 4145.46 | C+S GST 18% I/P RD | 746.18 | 4891.64 | 4891.64 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 21 | 100 | 28.23 | 0 | 1129.09 | C+S GST 18% I/P RD | 203.24 | 1332.33 | 1332.33 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 537 | 92212 | 26 Oct 2021 | 10/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1375 | A 1502 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 53.766 | Sq.Ft | 21 | 100 | 28.23 | 0 | 1129.09 | C+S GST 18% I/P RD | 203.24 | 1332.33 | 1332.33 | Approved | 0 | 0 | 1595 | 26 Oct 2021
GANGA DHAM TOWERS | 801 | 92211 | 26 Oct 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1405 | B Sprinkler System | SITC GI Pipe C Class 40mm dia.(L) | 229.3578 | Mtrs | 109 | 100 | 625 | 0 | 25000 | CGST 0% URD I/P | 0 | 25000 | 25000 | Approved | 0 | 0 | 1166 | 26 Oct 2021
GANGA DHAM TOWERS | 801 | 92211 | 26 Oct 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1405 | B Sprinkler System | SITC GI Pipe C Class 50mm dia.(L) | 166.6667 | Mtrs | 150 | 100 | 625 | 0 | 25000.01 | CGST 0% URD I/P | 0 | 25000.01 | 25000.01 | Approved | 0 | 0 | 1166 | 26 Oct 2021
GANGA DHAM TOWERS | 801 | 92211 | 26 Oct 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1405 | B Sprinkler System | SITC GI Pipe C Class 65mm dia.(L) | 100.9146 | Mtrs | 164 | 100 | 413.75 | 0 | 16550 | CGST 0% URD I/P | 0 | 16550 | 16550 | Approved | 0 | 0 | 1166 | 26 Oct 2021
GANGA DHAM TOWERS | 801 | 92211 | 26 Oct 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1405 | B Sprinkler System | SITC GI Pipe C Class 25mm dia-(L) | 390.625 | Mtrs | 64 | 100 | 625 | 0 | 25000 | CGST 0% URD I/P | 0 | 25000 | 25000 | Approved | 0 | 0 | 1166 | 26 Oct 2021
GANGA DHAM TOWERS | 801 | 92211 | 26 Oct 2021 |  | UNIQUE FIRE AND SAFETY SERVICES (CONTRACTOR) | PRATHAM ELECTRICALS | EV - 1405 | B Sprinkler System | Flexible Hose Pipe 25mm Dia (1.2mtr length) (L) | 108.6957 | No. | 230 | 100 | 0 | 0 | 25000 | CGST 0% URD I/P | 0 | 25000 | 25000 | Approved | 0 | 0 | 1166 | 26 Oct 2021
GANGA DHAM TOWERS | 272 | 92210 | 26 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1384 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 61.9195 | Sq.Ft | 161.5 | 100 | 0 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 270 | 26 Oct 2021
GANGA DHAM TOWERS | 272 | 92210 | 26 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1384 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 43.3437 | Sq.Ft | 161.5 | 100 | 0 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 270 | 26 Oct 2021
GANGA DHAM TOWERS | 272 | 92210 | 26 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1384 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 61.9195 | Sq.Ft | 161.5 | 100 | 0 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 270 | 26 Oct 2021
GANGA DHAM TOWERS | 1184 | 92190 | 25 Oct 2021 | KVE/246 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1380 | B Podium Floor External Sand Face Plaster | External Plaster- BC | 500 | Sq.Ft | 20 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 500 | 25 Oct 2021
GANGA DHAM TOWERS | 1184 | 92190 | 25 Oct 2021 | KVE/246 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1380 | B P1 Floor External Sand Face Plaster | External Plaster- BC | 500 | Sq.Ft | 20 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 500 | 25 Oct 2021
GANGA DHAM TOWERS | 1184 | 92190 | 25 Oct 2021 | KVE/246 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1380 | B P2 Floor External Sand Face Plaster | External Plaster- BC | 500 | Sq.Ft | 20 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 500 | 25 Oct 2021
GANGA DHAM TOWERS | 1184 | 92190 | 25 Oct 2021 | KVE/246 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1380 | B P3 Floor External Sand Face Plaster | External Plaster- BC | 500 | Sq.Ft | 20 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 500 | 25 Oct 2021
GANGA DHAM TOWERS | 1184 | 92190 | 25 Oct 2021 | KVE/246 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1380 | B Grond Floor External Sand Face Plaster | External Plaster- BC | 500 | Sq.Ft | 20 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 500 | 25 Oct 2021
GANGA DHAM TOWERS | 1186 | 92188 | 25 Oct 2021 | KVE/245 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1379 | A & B Parking Floor 3 Gutter For Trimix Flooring | Gutter making | 413 | R.Ft | 56 | 100 | 578.2 | 0 | 23128 | C+S GST 18% I/P RD | 4163.04 | 27291.04 | 27291.04 | Approved | 0 | 0 | 231 | 25 Oct 2021
GANGA DHAM TOWERS | 1143 | 92187 | 25 Oct 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 1372 | Store Container Rack Fabrication work | Fabrication Work. | 12 | No. | 1515 | 100 | 0 | 0 | 18180 | CGST 0% URD I/P | 0 | 18180 | 18180 | Approved | 0 | 0 | 182 | 25 Oct 2021
GANGA DHAM TOWERS | 272 | 92186 | 25 Oct 2021 |  | GOURI INFRA | KIRAN TUKARAM DHANAWADE | EV - 1367 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 19.7368 | Sq.Ft | 152 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 70 | 25 Oct 2021
GANGA DHAM TOWERS | 272 | 92186 | 25 Oct 2021 |  | GOURI INFRA | KIRAN TUKARAM DHANAWADE | EV - 1367 | A Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 24.7678 | Sq.Ft | 161.5 | 100 | 0 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 70 | 25 Oct 2021
GANGA DHAM TOWERS | 1183 | 92165 | 23 Oct 2021 |  | CONSTROGENESIS | CONSTROGENESIS |  | D 12th Slab Rework (Flat No 2) | Removing of Reinforcement | 500 | Sq.Ft | 5 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 |  | 0 | 0 | 300 | 23 Oct 2021
GANGA DHAM TOWERS | 1183 | 92165 | 23 Oct 2021 |  | CONSTROGENESIS | CONSTROGENESIS |  | D 12th Slab Rework (Flat No 2) | Fixing of Reinforcement | 500 | Sq.Ft | 25 | 100 | 312.5 | 0 | 12500 | C+S GST 18% I/P RD | 2250 | 14750 | 14750 |  | 0 | 0 | 300 | 23 Oct 2021
GANGA DHAM TOWERS | 371 | 92153 | 22 Oct 2021 |  | CONSTROGENESIS | CONSTROGENESIS | EV - 1244 | EWS Bldg RCC 12th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 712.5 | Sq.Ft | 160 | 100 | 2850 | 0 | 114000 | C+S GST 18% I/P RD | 20520 | 134520 | 134520 | Approved | 0 | 0 | 2280 | 22 Oct 2021
GANGA DHAM TOWERS | 796 | 92152 | 22 Oct 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1313 | D Fire St.case Wall Gyp. Plaster 11th to Terrace Fl. | Tikki Dhada (M) | 400 | Sq.Ft | 9 | 100 | 0 | 0 | 3600 | C+S GST 5% I/P RD | 180 | 3780 | 3780 | Approved | 0 | 0 | 0 | 22 Oct 2021
GANGA DHAM TOWERS | 796 | 92152 | 22 Oct 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1313 | D 10th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (M) | 615 | Sq.Ft | 9 | 100 | 0 | 0 | 5535 | C+S GST 5% I/P RD | 276.76 | 5811.76 | 5811.76 | Approved | 0 | 0 | 0 | 22 Oct 2021
GANGA DHAM TOWERS | 796 | 92152 | 22 Oct 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1313 | D 11th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (M) | 615 | Sq.Ft | 9 | 100 | 0 | 0 | 5535 | C+S GST 5% I/P RD | 276.76 | 5811.76 | 5811.76 | Approved | 0 | 0 | 0 | 22 Oct 2021
GANGA DHAM TOWERS | 796 | 92152 | 22 Oct 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1313 | D Main St.case Wall Gyp. Plaster 11th to Terrace Fl. | Tikki Dhada (M) | 414.4444 | Sq.Ft | 9 | 100 | 0 | 0 | 3730 | C+S GST 5% I/P RD | 186.5 | 3916.5 | 3916.5 | Approved | 0 | 0 | 0 | 22 Oct 2021
GANGA DHAM TOWERS | 796 | 92152 | 22 Oct 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1313 | D Fire St.case Wall Gyp. Plaster 10th to 11th Fl. | Tikki Dhada (M) | 400 | Sq.Ft | 9 | 100 | 0 | 0 | 3600 | C+S GST 5% I/P RD | 180 | 3780 | 3780 | Approved | 0 | 0 | 0 | 22 Oct 2021
GANGA DHAM TOWERS | 394 | 92151 | 22 Oct 2021 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 1314 | A Bldg Flat No. 1804 Gypsum Plaster | Gypsum on Wall (M) | 2677.4286 | Sq.Ft | 3.5 | 100 | 0 | 0 | 9371 | C+S GST 5% I/P RD | 468.56 | 9839.56 | 9839.56 | Approved | 0 | 0 | 0 | 22 Oct 2021
GANGA DHAM TOWERS | 394 | 92151 | 22 Oct 2021 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 1314 | A Bldg Flat No. 1903 Gypsum Plaster | Gypsum on Wall (M) | 552.5714 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1934 | C+S GST 5% I/P RD | 96.7 | 2030.7 | 2030.7 | Approved | 0 | 0 | 0 | 22 Oct 2021
GANGA DHAM TOWERS | 394 | 92151 | 22 Oct 2021 |  | A K INTERIOR CONTRACTOR | NKV HOME DEPOT | EV - 1314 | A Bldg Flat No. 1803 Gypsum Plaster | Gypsum on Wall (M) | 2930 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10255 | C+S GST 5% I/P RD | 512.76 | 10767.76 | 10767.76 | Approved | 0 | 0 | 0 | 22 Oct 2021
GANGA DHAM TOWERS | 384 | 92145 | 20 Oct 2021 |  | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1433 | Core cutting for Fire Fighting up to 3rd Floor | Core Cutting Work 3" BCE | 10 | No. | 300 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 30 | 20 Oct 2021
GANGA DHAM TOWERS | 384 | 92144 | 20 Oct 2021 | 827 | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1288 | A Bldg Fire Fight,AC & Drain lines Core Cutting | Core Cutting Work 4" BCE | 50 | No. | 300 | 100 | 375 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 210 | 20 Oct 2021
GANGA DHAM TOWERS | 384 | 92144 | 20 Oct 2021 | 827 | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1288 | A Bldg Fire Fight,AC & Drain lines Core Cutting | Core Cutting Work 4" BCE | 20 | No. | 300 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 210 | 20 Oct 2021
GANGA DHAM TOWERS | 384 | 92143 | 20 Oct 2021 | 829 | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1282 | A Bldg Fire Fight,AC & Drain lines Core Cutting | Core Cutting Work 4" BCE | 4 | No. | 300 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 162 | 20 Oct 2021
GANGA DHAM TOWERS | 384 | 92143 | 20 Oct 2021 | 829 | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1282 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting Work 4" BCE | 50 | No. | 210 | 100 | 262.5 | 0 | 10500 | CGST 0% URD I/P | 0 | 10500 | 10500 | Approved | 0 | 0 | 162 | 20 Oct 2021
GANGA DHAM TOWERS | 384 | 92143 | 20 Oct 2021 | 829 | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1282 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting rate diff.- BC | 50 | No. | 90 | 100 | 112.5 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 162 | 20 Oct 2021
GANGA DHAM TOWERS | 384 | 92142 | 20 Oct 2021 |  | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1377 | A Bldg Fire Fight,AC & Drain lines Core Cutting | Core Cutting 6" BCE | 26 | No. | 300 | 100 | 195 | 0 | 7800 | CGST 0% URD I/P | 0 | 7800 | 7800 | Approved | 0 | 0 | 240 | 20 Oct 2021
GANGA DHAM TOWERS | 384 | 92142 | 20 Oct 2021 |  | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1377 | A Bldg Fire Fight,AC & Drain lines Core Cutting | Core Cutting Work 4" BCE | 40 | No. | 300 | 100 | 300 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 240 | 20 Oct 2021
GANGA DHAM TOWERS | 384 | 92142 | 20 Oct 2021 |  | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1377 | Tower A Non Str.Wall Core Cutting Upto 26 Floor | Core Cutting Work 5" BCE | 20 | No. | 210 | 100 | 105 | 0 | 4200 | CGST 0% URD I/P | 0 | 4200 | 4200 | Approved | 0 | 0 | 240 | 20 Oct 2021
GANGA DHAM TOWERS | 983 | 92140 | 20 Oct 2021 | 828 | PATIL CONSTRUCTION | B.D. DONGARE | EV - 1283 | A Exhaust Fan Core Cutting | Core Cutting 6" BCE | 26 | No. | 300 | 100 | 195 | 0 | 7800 | CGST 0% URD I/P | 0 | 7800 | 7800 | Approved | 0 | 0 | 78 | 20 Oct 2021
GANGA DHAM TOWERS | 864 | 92139 | 20 Oct 2021 |  | B.D. DONGARE | B.D. DONGARE | EV - 1383 | B Core Cutting Work For Ac Work - | Core Cutting Work 4" BCE | 30 | No. | 300 | 100 | 0 | 0 | 9000 | CGST 0% URD I/P | 0 | 9000 | 9000 | Approved | 0 | 0 | 90 | 20 Oct 2021
GANGA DHAM TOWERS | 184 | 92125 | 20 Oct 2021 |  | UNICORN M.E.P. CONSULTANTS PVT LTD | UNICORN M.E.P. CONSULTANTS PVT LTD | EV - 1194 | MEP Consultancy All Buildings & Amenities | MEP Consultancy Lumpsum | 1 | No. | 2000000 | 8.33 | 0 | 0 | 166652 | C+S GST 18% I/P RD | 29997.36 | 196649.36 | 196649.36 | Approved | 0 | 0 | 39999 | 20 Oct 2021
GANGA DHAM TOWERS | 184 | 92125 | 20 Oct 2021 |  | UNICORN M.E.P. CONSULTANTS PVT LTD | UNICORN M.E.P. CONSULTANTS PVT LTD | EV - 1194 | MEP Consultancy All Buildings & Amenities | MEP Consultancy Lumpsum | 0.6 | No. | 2000000 | 8.33 | 0 | 0 | 100001 | C+S GST 18% I/P RD | 18000.18 | 118001.18 | 118001.18 | Approved | 0 | 0 | 39999 | 20 Oct 2021
GANGA DHAM TOWERS | 184 | 92125 | 20 Oct 2021 |  | UNICORN M.E.P. CONSULTANTS PVT LTD | UNICORN M.E.P. CONSULTANTS PVT LTD | EV - 1194 | MEP Consultancy All Buildings & Amenities | MEP Consultancy Lumpsum | 0.8 | No. | 2000000 | 8.33 | 0 | 0 | 133334 | C+S GST 18% I/P RD | 24000.12 | 157334.12 | 157334.12 | Approved | 0 | 0 | 39999 | 20 Oct 2021
GANGA DHAM TOWERS | 401 | 92124 | 20 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1398 | A 1401 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | C+S GST 18% I/P RD | 260.46 | 1707.46 | 1707.46 | Approved | 0 | 0 | 20 | 20 Oct 2021
GANGA DHAM TOWERS | 401 | 92124 | 20 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1398 | A 1404 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 553 | Sq.Ft | 1 | 100 | 55.3 | 0 | 553 | C+S GST 18% I/P RD | 99.54 | 652.54 | 652.54 | Approved | 0 | 0 | 20 | 20 Oct 2021
GANGA DHAM TOWERS | 792 | 92116 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1382 | D 203 Dado (L) | Dado Fixing | 233.112 | Sq.Ft | 13 | 100 | 75.76 | 0 | 3030.46 | CGST 0% URD I/P | 0 | 3030.46 | 3030.46 | Approved | 0 | 0 | 130 | 20 Oct 2021
GANGA DHAM TOWERS | 792 | 92116 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1382 | D 501 Vitrified Flooring (L) | Vitrified Flooring work | 383.288 | Sq.Ft | 13 | 100 | 124.57 | 0 | 4982.74 | CGST 0% URD I/P | 0 | 4982.74 | 4982.74 | Approved | 0 | 0 | 130 | 20 Oct 2021
GANGA DHAM TOWERS | 792 | 92116 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1382 | D 505 Vitrified Flooring (L) | Vitrified Flooring work | 383.288 | Sq.Ft | 13 | 100 | 124.57 | 0 | 4982.74 | CGST 0% URD I/P | 0 | 4982.74 | 4982.74 | Approved | 0 | 0 | 130 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 1005 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 804 Kitchen Otta | Granite Kitchen Otta BC | 13.725 | R.Ft | 400 | 100 | 137.25 | 0 | 5490 | CGST 0% URD I/P | 0 | 5490 | 5490 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 902 Kitchen Otta | Granite Kitchen Otta BC | 11.511 | R.Ft | 400 | 100 | 115.11 | 0 | 4604.4 | CGST 0% URD I/P | 0 | 4604.4 | 4604.4 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 1004 Kitchen Otta | Granite Kitchen Otta BC | 13.725 | R.Ft | 400 | 100 | 137.25 | 0 | 5490 | CGST 0% URD I/P | 0 | 5490 | 5490 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 905 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 603 Kitchen Otta | Granite Kitchen Otta BC | 13.725 | R.Ft | 400 | 100 | 137.25 | 0 | 5490 | CGST 0% URD I/P | 0 | 5490 | 5490 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 803 Kitchen Otta | Granite Kitchen Otta BC | 13.725 | R.Ft | 400 | 100 | 137.25 | 0 | 5490 | CGST 0% URD I/P | 0 | 5490 | 5490 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 701 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 703 Kitchen Otta | Granite Kitchen Otta BC | 13.725 | R.Ft | 400 | 100 | 137.25 | 0 | 5490 | CGST 0% URD I/P | 0 | 5490 | 5490 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 1002 Kitchen Otta | Granite Kitchen Otta BC | 11.511 | R.Ft | 400 | 100 | 115.11 | 0 | 4604.4 | CGST 0% URD I/P | 0 | 4604.4 | 4604.4 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 805 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 901 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 1003 Kitchen Otta | Granite Kitchen Otta BC | 13.725 | R.Ft | 400 | 100 | 137.25 | 0 | 5490 | CGST 0% URD I/P | 0 | 5490 | 5490 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 903 Kitchen Otta | Granite Kitchen Otta BC | 13.725 | R.Ft | 400 | 100 | 137.25 | 0 | 5490 | CGST 0% URD I/P | 0 | 5490 | 5490 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 1001 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 602 Kitchen Otta | Granite Kitchen Otta BC | 11.511 | R.Ft | 400 | 100 | 115.11 | 0 | 4604.4 | CGST 0% URD I/P | 0 | 4604.4 | 4604.4 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 601 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 904 Kitchen Otta | Granite Kitchen Otta BC | 13.725 | R.Ft | 400 | 100 | 137.25 | 0 | 5490 | CGST 0% URD I/P | 0 | 5490 | 5490 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 705 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 801 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 605 Kitchen Otta | Granite Kitchen Otta BC | 12.402 | R.Ft | 400 | 100 | 124.02 | 0 | 4960.8 | CGST 0% URD I/P | 0 | 4960.8 | 4960.8 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 798 | 92115 | 20 Oct 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 1281 | D 702 Kitchen Otta | Granite Kitchen Otta BC | 11.511 | R.Ft | 400 | 100 | 115.11 | 0 | 4604.4 | CGST 0% URD I/P | 0 | 4604.4 | 4604.4 | Approved | 0 | 0 | 1119 | 20 Oct 2021
GANGA DHAM TOWERS | 419 | 92103 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1212 | Club House RCC Consultancy | RCC Consultancy | 6620.9524 | Sq.Ft | 5.25 | 12.5 | 0 | 0 | 4345 | C+S GST 18% I/P RD | 782.1 | 5127.1 | 5127.1 | Approved | 0 | 0 | 4959 | 19 Oct 2021
GANGA DHAM TOWERS | 419 | 92103 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1212 | EWS Building RCC Consultancy | RCC Consultancy | 44796.1905 | Sq.Ft | 5.25 | 5 | 0 | 0 | 11759 | C+S GST 18% I/P RD | 2116.62 | 13875.62 | 13875.62 | Approved | 0 | 0 | 4959 | 19 Oct 2021
GANGA DHAM TOWERS | 419 | 92103 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1212 | EWS Building RCC Consultancy | RCC Consultancy | 44796.1905 | Sq.Ft | 5.25 | 5 | 0 | 0 | 11759 | C+S GST 18% I/P RD | 2116.62 | 13875.62 | 13875.62 | Approved | 0 | 0 | 4959 | 19 Oct 2021
GANGA DHAM TOWERS | 419 | 92103 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1212 | Club House RCC Consultancy | RCC Consultancy | 6620.9524 | Sq.Ft | 5.25 | 12.5 | 0 | 0 | 4345 | C+S GST 18% I/P RD | 782.1 | 5127.1 | 5127.1 | Approved | 0 | 0 | 4959 | 19 Oct 2021
GANGA DHAM TOWERS | 419 | 92103 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1212 | Club House RCC Consultancy | RCC Consultancy | 6620.9524 | Sq.Ft | 5.25 | 20 | 0 | 0 | 6952 | C+S GST 18% I/P RD | 1251.36 | 8203.36 | 8203.36 | Approved | 0 | 0 | 4959 | 19 Oct 2021
GANGA DHAM TOWERS | 419 | 92103 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1212 | Club House RCC Consultancy | RCC Consultancy | 6620.9524 | Sq.Ft | 5.25 | 20 | 0 | 0 | 6952 | C+S GST 18% I/P RD | 1251.36 | 8203.36 | 8203.36 | Approved | 0 | 0 | 4959 | 19 Oct 2021
GANGA DHAM TOWERS | 419 | 92103 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1212 | Club House RCC Consultancy | RCC Consultancy | 6620.9524 | Sq.Ft | 5.25 | 5 | 0 | 0 | 1738 | C+S GST 18% I/P RD | 312.84 | 2050.84 | 2050.84 | Approved | 0 | 0 | 4959 | 19 Oct 2021
GANGA DHAM TOWERS | 419 | 92103 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1212 | Club House RCC Consultancy | RCC Consultancy | 6620.9524 | Sq.Ft | 5.25 | 5 | 0 | 0 | 1738 | C+S GST 18% I/P RD | 312.84 | 2050.84 | 2050.84 | Approved | 0 | 0 | 4959 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower B 21st to 28th Floor RCC Consultancy | RCC Consultancy | 58115 | Sq.Ft | 6 | 10 | 0 | 0 | 34869 | C+S GST 18% I/P RD | 6276.42 | 41145.42 | 41145.42 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | A,B,C Parking & Podium RCC Consultancy | RCC Consultancy | 29024.22 | Sq.Ft | 6 | 12.5 | 0 | 0 | 21768.17 | C+S GST 18% I/P RD | 3918.28 | 25686.45 | 25686.45 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower A 21st to 28th Floor RCC Consultancy | RCC Consultancy | 76244.4 | Sq.Ft | 6 | 12.5 | 0 | 0 | 57183.3 | C+S GST 18% I/P RD | 10293 | 67476.3 | 67476.3 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower B 21st to 28th Floor RCC Consultancy | RCC Consultancy | 52304.4 | Sq.Ft | 6 | 12.5 | 0 | 0 | 39228.3 | C+S GST 18% I/P RD | 7061.1 | 46289.4 | 46289.4 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | A,B,C Parking & Podium RCC Consultancy | RCC Consultancy | 0.49 | Sq.Ft | 6 | 10 | 0 | 0 | 0.29 | C+S GST 18% I/P RD | 0.06 | 0.35 | 0.35 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower C 21st to 28th Floor RCC Consultancy | RCC Consultancy | 87192.6667 | Sq.Ft | 6 | 25 | 0 | 0 | 130789 | C+S GST 18% I/P RD | 23542.02 | 154331.02 | 154331.02 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower C 1st to 20th Floor RCC Consultancy | RCC Consultancy | 217980.6667 | Sq.Ft | 6 | 25 | 0 | 0 | 326971 | C+S GST 18% I/P RD | 58854.78 | 385825.78 | 385825.78 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower A 1st to 20th Floor RCC Consultancy | RCC Consultancy | 211790 | Sq.Ft | 6 | 10 | 0 | 0 | 127074 | C+S GST 18% I/P RD | 22873.32 | 149947.32 | 149947.32 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower A 21st to 28th Floor RCC Consultancy | RCC Consultancy | 84715 | Sq.Ft | 6 | 10 | 0 | 0 | 50829 | C+S GST 18% I/P RD | 9149.22 | 59978.22 | 59978.22 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | A,B,C Parking & Podium RCC Consultancy | RCC Consultancy | 29024.22 | Sq.Ft | 6 | 25 | 0 | 0 | 43536.33 | C+S GST 18% I/P RD | 7836.54 | 51372.87 | 51372.87 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower A 21st to 28th Floor RCC Consultancy | RCC Consultancy | 80480.2 | Sq.Ft | 6 | 12.5 | 0 | 0 | 60360.15 | C+S GST 18% I/P RD | 10864.82 | 71224.97 | 71224.97 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower B 21st to 28th Floor RCC Consultancy | RCC Consultancy | 52304.4 | Sq.Ft | 6 | 12.5 | 0 | 0 | 39228.3 | C+S GST 18% I/P RD | 7061.1 | 46289.4 | 46289.4 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower B 21st to 28th Floor RCC Consultancy | RCC Consultancy | 52304.4 | Sq.Ft | 6 | 12.5 | 0 | 0 | 39228.3 | C+S GST 18% I/P RD | 7061.1 | 46289.4 | 46289.4 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | A,B,C Parking & Podium RCC Consultancy | RCC Consultancy | 29024.22 | Sq.Ft | 6 | 12.5 | 0 | 0 | 21768.17 | C+S GST 18% I/P RD | 3918.28 | 25686.45 | 25686.45 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower A 21st to 28th Floor RCC Consultancy | RCC Consultancy | 76244.4 | Sq.Ft | 6 | 12.5 | 0 | 0 | 57183.3 | C+S GST 18% I/P RD | 10293 | 67476.3 | 67476.3 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower B 21st to 28th Floor RCC Consultancy | RCC Consultancy | 55210.2 | Sq.Ft | 6 | 12.5 | 0 | 0 | 41407.65 | C+S GST 18% I/P RD | 7453.38 | 48861.03 | 48861.03 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 271 | 92102 | 19 Oct 2021 |  | G.A.BHILARE CONSULTANTS PVT LTD | G.A.BHILARE CONSULTANTS PVT LTD | EV - 1211 | Tower A 21st to 28th Floor RCC Consultancy | RCC Consultancy | 76244.4 | Sq.Ft | 6 | 12.5 | 0 | 0 | 57183.3 | C+S GST 18% I/P RD | 10293 | 67476.3 | 67476.3 | Approved | 0 | 0 | 114861 | 19 Oct 2021
GANGA DHAM TOWERS | 1121 | 92094 | 19 Oct 2021 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 1308 | Tower C Retaining wall & Footing Waterproofing work | Membrane Horizontal Waterproofing (L) | 1701.9 | Sq.Ft | 10 | 100 | 1701.9 | 0 | 17019 | C+S GST 18% I/P RD | 3063.42 | 20082.42 | 20082.42 | Approved | 0 | 0 | 666 | 19 Oct 2021
GANGA DHAM TOWERS | 1121 | 92094 | 19 Oct 2021 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 1308 | Tower C Retaining wall & Footing Waterproofing work | Membrane Vertical Waterproofing (L) | 4134.4167 | Sq.Ft | 12 | 100 | 4961.3 | 0 | 49613 | C+S GST 18% I/P RD | 8930.34 | 58543.34 | 58543.34 | Approved | 0 | 0 | 666 | 19 Oct 2021
GANGA DHAM TOWERS | 1122 | 92093 | 19 Oct 2021 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 1309 | Tower C Retaining wall & Footing Waterproofing work | Membrane Vertical Waterproofing (M) | 4134.4333 | Sq.Ft | 30 | 100 | 0 | 0 | 124033 | C+S GST 18% I/P RD | 22325.94 | 146358.94 | 146358.94 | Approved | 0 | 0 | 0 | 19 Oct 2021
GANGA DHAM TOWERS | 1122 | 92093 | 19 Oct 2021 |  | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 1309 | Tower C Retaining wall & Footing Waterproofing work | Membrane Horizontal Waterproofing (M) | 1701.8519 | Sq.Ft | 27 | 100 | 0 | 0 | 45950 | C+S GST 18% I/P RD | 8271 | 54221 | 54221 | Approved | 0 | 0 | 0 | 19 Oct 2021
GANGA DHAM TOWERS | 371 | 92092 | 19 Oct 2021 |  | CONSTROGENESIS | CONSTROGENESIS | EV - 1245 | EWS Bldg RCC 13th Slab Built-up Area (Terrace)(L) | RCC Superstructure (B-up area) | 623 | Sq.Ft | 150 | 100 | 2336.25 | 0 | 93450 | C+S GST 18% I/P RD | 16821 | 110271 | 110271 | Approved | 0 | 0 | 4229 | 19 Oct 2021
GANGA DHAM TOWERS | 371 | 92092 | 19 Oct 2021 |  | CONSTROGENESIS | CONSTROGENESIS | EV - 1245 | EWS Bldg RCC 12th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 737.5 | Sq.Ft | 160 | 100 | 2950 | 0 | 118000 | C+S GST 18% I/P RD | 21240 | 139240 | 139240 | Approved | 0 | 0 | 4229 | 19 Oct 2021
GANGA DHAM TOWERS | 934 | 92086 | 18 Oct 2021 | pec/21-22/043 | PEC SOLUTIONS GREEN DESIGNS PVT LTD | PEC SOLUTIONS GREEN DESIGNS PVT LTD | EV - 1168 | Tower A,B,C Green Bldg Certification Consultancy - 1319042 | Green Bldg Certification Consultancy (Rate Diff.) | 1316234.0426 | Sq.Ft | 0.47 | 10 | 0 | 0 | 61863 | C+S GST 18% I/P RD | 11135.34 | 72998.34 | 72998.34 | Approved | 0 | 0 | 43304 | 18 Oct 2021
GANGA DHAM TOWERS | 934 | 92086 | 18 Oct 2021 | pec/21-22/043 | PEC SOLUTIONS GREEN DESIGNS PVT LTD | PEC SOLUTIONS GREEN DESIGNS PVT LTD | EV - 1168 | Tower A,B,C Green Bldg Certification Consultancy - 1319042 | Green Bldg Certification Consultancy (Rate Diff.) | 1316226.9504 | Sq.Ft | 0.47 | 15 | 0 | 0 | 92794 | C+S GST 18% I/P RD | 16702.92 | 109496.92 | 109496.92 | Approved | 0 | 0 | 43304 | 18 Oct 2021
GANGA DHAM TOWERS | 934 | 92086 | 18 Oct 2021 | pec/21-22/043 | PEC SOLUTIONS GREEN DESIGNS PVT LTD | PEC SOLUTIONS GREEN DESIGNS PVT LTD | EV - 1168 | Tower A,B,C Green Bldg Certification Consultancy - 1319042 | Green Bldg Certification Consultancy (Rate Diff.) | 1316234.0426 | Sq.Ft | 0.47 | 10 | 0 | 0 | 61863 | C+S GST 18% I/P RD | 11135.34 | 72998.34 | 72998.34 | Approved | 0 | 0 | 43304 | 18 Oct 2021
GANGA DHAM TOWERS | 934 | 92086 | 18 Oct 2021 | pec/21-22/043 | PEC SOLUTIONS GREEN DESIGNS PVT LTD | PEC SOLUTIONS GREEN DESIGNS PVT LTD | EV - 1168 | Tower A,B,C Green Bldg Certification Consultancy - 1319042 | Green Bldg Certification Consultancy (Rate Diff.) | 1316234.0426 | Sq.Ft | 0.47 | 20 | 0 | 0 | 123726 | C+S GST 18% I/P RD | 22270.68 | 145996.68 | 145996.68 | Approved | 0 | 0 | 43304 | 18 Oct 2021
GANGA DHAM TOWERS | 934 | 92086 | 18 Oct 2021 | pec/21-22/043 | PEC SOLUTIONS GREEN DESIGNS PVT LTD | PEC SOLUTIONS GREEN DESIGNS PVT LTD | EV - 1168 | Tower A,B,C Green Bldg Certification Consultancy - 1319042 | Green Bldg Certification Consultancy (Rate Diff.) | 1316226.9504 | Sq.Ft | 0.47 | 15 | 0 | 0 | 92794 | C+S GST 18% I/P RD | 16702.92 | 109496.92 | 109496.92 | Approved | 0 | 0 | 43304 | 18 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 202 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 15 | 100 | 59.94 | 0 | 2397.74 | C+S GST 18% I/P RD | 431.6 | 2829.34 | 2829.34 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 402 Terrace Vitrified Flooring | Vitrified Flooring -BC | 159.849 | Sq.Ft | 15 | 100 | 59.94 | 0 | 2397.74 | C+S GST 18% I/P RD | 431.6 | 2829.34 | 2829.34 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Children Toilet dado | Dado BC | 56.544 | Sq.Ft | 24 | 100 | 33.93 | 0 | 1357.06 | C+S GST 18% I/P RD | 244.28 | 1601.34 | 1601.34 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Master Toilet dado | Dado BC | 66.456 | Sq.Ft | 24 | 100 | 39.87 | 0 | 1594.94 | C+S GST 18% I/P RD | 287.08 | 1882.02 | 1882.02 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Powder Toilet dado | Dado BC | 31.088 | Sq.Ft | 24 | 100 | 18.65 | 0 | 746.11 | C+S GST 18% I/P RD | 134.3 | 880.41 | 880.41 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Parents Toilet dado | Dado BC | 52.112 | Sq.Ft | 24 | 100 | 31.27 | 0 | 1250.69 | C+S GST 18% I/P RD | 225.12 | 1475.81 | 1475.81 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Terrace Parapet Top Granite | Granite Sill-BCo | 18.896 | R.Ft | 50 | 100 | 23.62 | 0 | 944.8 | C+S GST 18% I/P RD | 170.06 | 1114.86 | 1114.86 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Terrace Vitrified Flooring | Vitrified Skirting BC | 28.784 | R.Ft | 24 | 100 | 17.27 | 0 | 690.82 | C+S GST 18% I/P RD | 124.34 | 815.16 | 815.16 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 401 Terrace Parapet Top Granite | Granite Sill-BCo | 18.896 | R.Ft | 40 | 100 | 18.9 | 0 | 755.84 | C+S GST 18% I/P RD | 136.06 | 891.9 | 891.9 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 402 Terrace Vitrified Flooring | Vitrified Skirting BC | 34.032 | R.Ft | 15 | 100 | 12.76 | 0 | 510.48 | C+S GST 18% I/P RD | 91.88 | 602.36 | 602.36 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 202 Terrace Vitrified Flooring | Vitrified Skirting BC | 34.032 | R.Ft | 15 | 100 | 12.76 | 0 | 510.48 | C+S GST 18% I/P RD | 91.88 | 602.36 | 602.36 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1201 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 31.864 | Sq.Ft | 17 | 100 | 13.54 | 0 | 541.69 | C+S GST 18% I/P RD | 97.5 | 639.19 | 639.19 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1201 Terrace Parapet Top Granite | Granite Sill-BCo | 18.896 | R.Ft | 45 | 100 | 21.26 | 0 | 850.32 | C+S GST 18% I/P RD | 153.06 | 1003.38 | 1003.38 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1001 Terrace Parapet Top Granite | Granite Sill-BCo | 18.896 | R.Ft | 45 | 100 | 21.26 | 0 | 850.32 | C+S GST 18% I/P RD | 153.06 | 1003.38 | 1003.38 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1101 Terrace Parapet Top Granite | Granite Sill-BCo | 18.896 | R.Ft | 45 | 100 | 21.26 | 0 | 850.32 | C+S GST 18% I/P RD | 153.06 | 1003.38 | 1003.38 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 42.192 | Sq.Ft | 21 | 100 | 22.15 | 0 | 886.03 | C+S GST 18% I/P RD | 159.48 | 1045.51 | 1045.51 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 18.32 | Sq.Ft | 21 | 100 | 9.62 | 0 | 384.72 | C+S GST 18% I/P RD | 69.24 | 453.96 | 453.96 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Children Toilet Flooring | Vitrified Flooring -BC | 39.264 | Sq.Ft | 21 | 100 | 20.61 | 0 | 824.54 | C+S GST 18% I/P RD | 148.42 | 972.96 | 972.96 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 40.256 | Sq.Ft | 21 | 100 | 21.13 | 0 | 845.38 | C+S GST 18% I/P RD | 152.16 | 997.54 | 997.54 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 34.872 | Sq.Ft | 21 | 100 | 18.31 | 0 | 732.31 | C+S GST 18% I/P RD | 131.82 | 864.13 | 864.13 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 39.83 | Sq.Ft | 21 | 100 | 20.91 | 0 | 836.43 | C+S GST 18% I/P RD | 150.56 | 986.99 | 986.99 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Terrace Vitrified Flooring | Vitrified Flooring -BC | 124.864 | Sq.Ft | 24 | 100 | 74.92 | 0 | 2996.74 | C+S GST 18% I/P RD | 539.42 | 3536.16 | 3536.16 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Children Toilet dado | Dado BC | 107.352 | Sq.Ft | 22 | 100 | 59.04 | 0 | 2361.74 | C+S GST 18% I/P RD | 425.12 | 2786.86 | 2786.86 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Master Toilet dado | Dado BC | 114.714 | Sq.Ft | 22 | 100 | 63.09 | 0 | 2523.71 | C+S GST 18% I/P RD | 454.26 | 2977.97 | 2977.97 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Parents Toilet dado | Dado BC | 118.672 | Sq.Ft | 22 | 100 | 65.27 | 0 | 2610.78 | C+S GST 18% I/P RD | 469.94 | 3080.72 | 3080.72 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Staff Toilet dado | Dado BC | 97.968 | Sq.Ft | 21 | 100 | 51.43 | 0 | 2057.33 | C+S GST 18% I/P RD | 370.32 | 2427.65 | 2427.65 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 537 | 92074 | 16 Oct 2021 | 062 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 1280 | A 1701 Powder Toilet dado | Dado BC | 77.888 | Sq.Ft | 22 | 100 | 42.84 | 0 | 1713.54 | C+S GST 18% I/P RD | 308.44 | 2021.98 | 2021.98 | Approved | 0 | 0 | 700 | 16 Oct 2021
GANGA DHAM TOWERS | 652 | 92061 | 16 Oct 2021 | 52 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1394 | A P2 Podium Drop Pannel Plaster | Gypsum Patta Plaster Rate Diff (L) | 665.7 | R.Ft | 7.5 | 100 | 124.82 | 0 | 4992.75 | C+S GST 18% I/P RD | 898.7 | 5891.45 | 5891.45 | Approved | 0 | 2320 | 112 | 16 Oct 2021
GANGA DHAM TOWERS | 652 | 92061 | 16 Oct 2021 | 52 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1394 | A P3 Podium Drop Pannel Plaster | Gypsum Patta Plaster Rate Diff (L) | 833.2 | R.Ft | 7.5 | 100 | 156.23 | 0 | 6249 | C+S GST 18% I/P RD | 1124.82 | 7373.82 | 7373.82 | Approved | 0 | 2320 | 112 | 16 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Parking 1 Floor Regular Staircase | Kota Champher | 69.363 | R.Ft | 7.5 | 100 | 13.01 | 0 | 520.22 | C+S GST 18% I/P RD | 93.64 | 613.86 | 613.86 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Parking 3 Floor Regular Staircase | Kota Champher | 69.363 | R.Ft | 7.5 | 100 | 13.01 | 0 | 520.22 | C+S GST 18% I/P RD | 93.64 | 613.86 | 613.86 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Podium Floor Fire Staircase | Kota Champher | 152.593 | R.Ft | 7.5 | 100 | 28.61 | 0 | 1144.45 | C+S GST 18% I/P RD | 206 | 1350.45 | 1350.45 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Ground Floor Fire Staircase | Kota Champher | 69.363 | R.Ft | 7.5 | 100 | 13.01 | 0 | 520.22 | C+S GST 18% I/P RD | 93.64 | 613.86 | 613.86 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Ground Floor Regular Staircase | Kota Champher | 69.363 | R.Ft | 7.5 | 100 | 13.01 | 0 | 520.22 | C+S GST 18% I/P RD | 93.64 | 613.86 | 613.86 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Parking 1 Floor Fire Staircase | Kota Champher | 69.363 | R.Ft | 7.5 | 100 | 13.01 | 0 | 520.22 | C+S GST 18% I/P RD | 93.64 | 613.86 | 613.86 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Parking 2 Floor Regular Staircase | Kota Champher | 69.363 | R.Ft | 7.5 | 100 | 13.01 | 0 | 520.22 | C+S GST 18% I/P RD | 93.64 | 613.86 | 613.86 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Podium Floor Regular Staircase | Kota Champher | 152.593 | R.Ft | 7.5 | 100 | 28.61 | 0 | 1144.45 | C+S GST 18% I/P RD | 206 | 1350.45 | 1350.45 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Parking 3 Floor Fire Staircase | Kota Champher | 69.363 | R.Ft | 7.5 | 100 | 13.01 | 0 | 520.22 | C+S GST 18% I/P RD | 93.64 | 613.86 | 613.86 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 908 | 92055 | 15 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1172 | A Parking 2 Floor Fire Staircase | Kota Champher | 69.363 | R.Ft | 7.5 | 100 | 13.01 | 0 | 520.22 | C+S GST 18% I/P RD | 93.64 | 613.86 | 613.86 | Approved | 0 | 0 | 65 | 15 Oct 2021
GANGA DHAM TOWERS | 126 | 92054 | 15 Oct 2021 |  | SANDIP VAMANRAO RUPNAWAR | PUNDLIK P MAHAJAN | EV - 1304 | Site Expenses | Site Expenses -SO | 0.7521 | Month | 15000 | 100 | 0 | 0 | 11282 | CGST 0% URD I/P | 0 | 11282 | 11282 | Approved | 0 | 0 | 0 | 15 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1101 Walls Satin Matt Paint | Oil base Primer-BC | 2277.21 | Sq.Ft | 1 | 100 | 56.93 | 0 | 2277.21 | IGST 18% I/P RD | 409.9 | 2687.11 | 2687.11 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 203 Walls Satin Matt Painting | Oil base Primer-BC | 2071.8 | Sq.Ft | 1 | 100 | 51.8 | 0 | 2071.8 | IGST 18% I/P RD | 372.92 | 2444.72 | 2444.72 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1704 Walls Satin Matt Painting | Oil base Primer-BC | 2081.04 | Sq.Ft | 1 | 100 | 52.03 | 0 | 2081.04 | IGST 18% I/P RD | 374.59 | 2455.63 | 2455.63 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 502 Walls Satin Matt Painting | Oil base Primer-BC | 2204.55 | Sq.Ft | 1 | 100 | 55.11 | 0 | 2204.55 | IGST 18% I/P RD | 396.82 | 2601.37 | 2601.37 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1703 Walls Satin Matt Painting | Oil base Primer-BC | 2071.8 | Sq.Ft | 1 | 100 | 51.8 | 0 | 2071.8 | IGST 18% I/P RD | 372.92 | 2444.72 | 2444.72 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1302 Walls Satin Matt Painting | Oil base Primer-BC | 2204.55 | Sq.Ft | 1 | 100 | 55.11 | 0 | 2204.55 | IGST 18% I/P RD | 396.82 | 2601.37 | 2601.37 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 504 Walls Satin Matt Painting | Oil base Primer-BC | 2081.04 | Sq.Ft | 1 | 100 | 52.03 | 0 | 2081.04 | IGST 18% I/P RD | 374.59 | 2455.63 | 2455.63 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1603 Walls Satin Matt Painting | Oil base Primer-BC | 2071.8 | Sq.Ft | 1 | 100 | 51.8 | 0 | 2071.8 | IGST 18% I/P RD | 372.92 | 2444.72 | 2444.72 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 503 Walls Satin Matt Painting | Oil base Primer-BC | 2071.8 | Sq.Ft | 1 | 100 | 51.8 | 0 | 2071.8 | IGST 18% I/P RD | 372.92 | 2444.72 | 2444.72 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1602 Walls Satin Matt Painting | Oil base Primer-BC | 2204.55 | Sq.Ft | 1 | 100 | 55.11 | 0 | 2204.55 | IGST 18% I/P RD | 396.82 | 2601.37 | 2601.37 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1204 Walls Satin Matt Painting | Oil base Primer-BC | 2081.04 | Sq.Ft | 1 | 100 | 52.03 | 0 | 2081.04 | IGST 18% I/P RD | 374.59 | 2455.63 | 2455.63 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 202 Walls Satin Matt Painting | Oil base Primer-BC | 2204.55 | Sq.Ft | 1 | 100 | 55.11 | 0 | 2204.55 | IGST 18% I/P RD | 396.82 | 2601.37 | 2601.37 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1603 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2071.8 | Sq.Ft | 1.25 | 100 | 64.74 | 0 | 2589.75 | IGST 18% I/P RD | 466.16 | 3055.91 | 3055.91 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 202 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2204.55 | Sq.Ft | 1.25 | 100 | 68.89 | 0 | 2755.69 | IGST 18% I/P RD | 496.02 | 3251.71 | 3251.71 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1704 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2081.04 | Sq.Ft | 1.25 | 100 | 65.03 | 0 | 2601.3 | IGST 18% I/P RD | 468.23 | 3069.53 | 3069.53 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1204 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2081.04 | Sq.Ft | 1.25 | 100 | 65.03 | 0 | 2601.3 | IGST 18% I/P RD | 468.23 | 3069.53 | 3069.53 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1101 Walls Satin Matt Paint | Scrapping with 1st Coat Putty | 2277.21 | Sq.Ft | 1.25 | 100 | 71.16 | 0 | 2846.51 | IGST 18% I/P RD | 512.37 | 3358.88 | 3358.88 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 203 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2071.8 | Sq.Ft | 1.25 | 100 | 64.74 | 0 | 2589.75 | IGST 18% I/P RD | 466.16 | 3055.91 | 3055.91 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1113 | 92052 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1201 | A 1602 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2204.55 | Sq.Ft | 1.25 | 100 | 68.89 | 0 | 2755.69 | IGST 18% I/P RD | 496.02 | 3251.71 | 3251.71 | Approved | 0 | 0 | 444 | 14 Oct 2021
GANGA DHAM TOWERS | 1044 | 92050 | 14 Oct 2021 | 33 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | SUSTAINERA SOLUTIONS PRIVATE LIMITED | EV - 1169 | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | 1 | No. | 565000 | 25 | 0 | 0 | 141250 | C+S GST 18% I/P RD | 25425 | 166675 | 166675 | Approved | 0 | 0 | 50850 | 14 Oct 2021
GANGA DHAM TOWERS | 1044 | 92050 | 14 Oct 2021 | 33 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | SUSTAINERA SOLUTIONS PRIVATE LIMITED | EV - 1169 | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | 1 | No. | 565000 | 25 | 0 | 0 | 141250 | C+S GST 18% I/P RD | 25425 | 166675 | 166675 | Approved | 0 | 0 | 50850 | 14 Oct 2021
GANGA DHAM TOWERS | 1044 | 92050 | 14 Oct 2021 | 33 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | SUSTAINERA SOLUTIONS PRIVATE LIMITED | EV - 1169 | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | 1 | No. | 565000 | 20 | 0 | 0 | 113000 | C+S GST 18% I/P RD | 20340 | 133340 | 133340 | Approved | 0 | 0 | 50850 | 14 Oct 2021
GANGA DHAM TOWERS | 1044 | 92050 | 14 Oct 2021 | 33 | SUSTAINERA SOLUTIONS PRIVATE LIMITED | SUSTAINERA SOLUTIONS PRIVATE LIMITED | EV - 1169 | Environmental Clearance Consultancy | Environmental Clearance- SEAC & SEIAA | 1 | No. | 565000 | 20 | 0 | 0 | 113000 | C+S GST 18% I/P RD | 20340 | 133340 | 133340 | Approved | 0 | 0 | 50850 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 1502 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 902 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 102 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 701 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 1550.88 | 10166.88 | 10166.88 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 1101 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 1301 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 1550.88 | 10166.88 | 10166.88 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 1201 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 1550.88 | 10166.88 | 10166.88 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 1701 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 503 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 40 | 232.37 | 0 | 9294.8 | C+S GST 18% I/P RD | 1673.06 | 10967.86 | 10967.86 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 203 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 23237 | 40 | 46.47 | 0 | 1858.96 | C+S GST 18% I/P RD | 334.62 | 2193.58 | 2193.58 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 703 Electrical Work (L) | Electrical Work (Labour) -Bco | 1 | No. | 23237 | 40 | 232.37 | 0 | 9294.8 | C+S GST 18% I/P RD | 1673.06 | 10967.86 | 10967.86 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 1118 | 92039 | 14 Oct 2021 | 18 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 1157 | A 704 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 839 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Podium Floor Fire Staircase | Kota Flooring (L)- BCO | 284.172 | Sq.Ft | 50 | 100 | 355.22 | 0 | 14208.6 | C+S GST 18% I/P RD | 2557.54 | 16766.14 | 16766.14 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Podium Floor Regular Staircase | Kota Flooring (L)- BCO | 214.669 | Sq.Ft | 50 | 100 | 268.34 | 0 | 10733.45 | C+S GST 18% I/P RD | 1932.02 | 12665.47 | 12665.47 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Ground Floor Regular Staircase | Kota Flooring (L)- BCO | 113.022 | Sq.Ft | 50 | 100 | 141.28 | 0 | 5651.1 | C+S GST 18% I/P RD | 1017.2 | 6668.3 | 6668.3 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 3 Floor Regular Staircase | Kota Flooring (L)- BCO | 113.022 | Sq.Ft | 50 | 100 | 141.28 | 0 | 5651.1 | C+S GST 18% I/P RD | 1017.2 | 6668.3 | 6668.3 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 2 Floor Fire Staircase | Kota Flooring (L)- BCO | 147.868 | Sq.Ft | 50 | 100 | 184.84 | 0 | 7393.4 | C+S GST 18% I/P RD | 1330.82 | 8724.22 | 8724.22 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 3 Floor Fire Staircase | Kota Flooring (L)- BCO | 147.868 | Sq.Ft | 50 | 100 | 184.84 | 0 | 7393.4 | C+S GST 18% I/P RD | 1330.82 | 8724.22 | 8724.22 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 1 Floor Regular Staircase | Kota Flooring (L)- BCO | 113.022 | Sq.Ft | 50 | 100 | 141.28 | 0 | 5651.1 | C+S GST 18% I/P RD | 1017.2 | 6668.3 | 6668.3 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 1 Floor Fire Staircase | Kota Flooring (L)- BCO | 147.868 | Sq.Ft | 50 | 100 | 184.84 | 0 | 7393.4 | C+S GST 18% I/P RD | 1330.82 | 8724.22 | 8724.22 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 2 Floor Regular Staircase | Kota Flooring (L)- BCO | 113.022 | Sq.Ft | 50 | 100 | 141.28 | 0 | 5651.1 | C+S GST 18% I/P RD | 1017.2 | 6668.3 | 6668.3 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Ground Floor Fire Staircase | Kota Flooring (L)- BCO | 147.868 | Sq.Ft | 50 | 100 | 184.84 | 0 | 7393.4 | C+S GST 18% I/P RD | 1330.82 | 8724.22 | 8724.22 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 1 Floor Regular Staircase | Kota Riser (L)- BCO | 69.363 | R.Ft | 45 | 100 | 78.03 | 0 | 3121.34 | C+S GST 18% I/P RD | 561.84 | 3683.18 | 3683.18 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Ground Floor Regular Staircase | Kota Riser (L)- BCO | 69.363 | R.Ft | 45 | 100 | 78.03 | 0 | 3121.34 | C+S GST 18% I/P RD | 561.84 | 3683.18 | 3683.18 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 1 Floor Fire Staircase | Kota Riser (L)- BCO | 69.363 | R.Ft | 45 | 100 | 78.03 | 0 | 3121.34 | C+S GST 18% I/P RD | 561.84 | 3683.18 | 3683.18 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 2 Floor Fire Staircase | Kota Riser (L)- BCO | 69.363 | R.Ft | 45 | 100 | 78.03 | 0 | 3121.34 | C+S GST 18% I/P RD | 561.84 | 3683.18 | 3683.18 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 3 Floor Regular Staircase | Kota Riser (L)- BCO | 69.363 | R.Ft | 45 | 100 | 78.03 | 0 | 3121.34 | C+S GST 18% I/P RD | 561.84 | 3683.18 | 3683.18 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 3 Floor Fire Staircase | Kota Riser (L)- BCO | 69.363 | R.Ft | 45 | 100 | 78.03 | 0 | 3121.34 | C+S GST 18% I/P RD | 561.84 | 3683.18 | 3683.18 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 2 Floor Regular Staircase | Kota Riser (L)- BCO | 69.363 | R.Ft | 45 | 100 | 78.03 | 0 | 3121.34 | C+S GST 18% I/P RD | 561.84 | 3683.18 | 3683.18 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Ground Floor Fire Staircase | Kota Riser (L)- BCO | 69.363 | R.Ft | 45 | 100 | 78.03 | 0 | 3121.34 | C+S GST 18% I/P RD | 561.84 | 3683.18 | 3683.18 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Podium Floor Regular Staircase | Kota Riser (L)- BCO | 152.593 | R.Ft | 45 | 100 | 171.67 | 0 | 6866.69 | C+S GST 18% I/P RD | 1236 | 8102.69 | 8102.69 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Podium Floor Fire Staircase | Kota Riser (L)- BCO | 152.593 | R.Ft | 45 | 100 | 171.67 | 0 | 6866.69 | C+S GST 18% I/P RD | 1236 | 8102.69 | 8102.69 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Podium Floor Regular Staircase | Kota Skirting (L)- BCO | 107.646 | R.Ft | 30 | 100 | 80.73 | 0 | 3229.38 | C+S GST 18% I/P RD | 581.28 | 3810.66 | 3810.66 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 3 Floor Fire Staircase | Kota Skirting (L)- BCO | 60.172 | R.Ft | 30 | 100 | 45.13 | 0 | 1805.16 | C+S GST 18% I/P RD | 324.92 | 2130.08 | 2130.08 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 3 Floor Regular Staircase | Kota Skirting (L)- BCO | 53.942 | R.Ft | 30 | 100 | 40.46 | 0 | 1618.26 | C+S GST 18% I/P RD | 291.28 | 1909.54 | 1909.54 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Ground Floor Regular Staircase | Kota Skirting (L)- BCO | 53.942 | R.Ft | 30 | 100 | 40.46 | 0 | 1618.26 | C+S GST 18% I/P RD | 291.28 | 1909.54 | 1909.54 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Podium Floor Fire Staircase | Kota Skirting (L)- BCO | 123.172 | R.Ft | 30 | 100 | 92.38 | 0 | 3695.16 | C+S GST 18% I/P RD | 665.12 | 4360.28 | 4360.28 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 1 Floor Regular Staircase | Kota Skirting (L)- BCO | 53.942 | R.Ft | 30 | 100 | 40.46 | 0 | 1618.26 | C+S GST 18% I/P RD | 291.28 | 1909.54 | 1909.54 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 2 Floor Regular Staircase | Kota Skirting (L)- BCO | 53.942 | R.Ft | 30 | 100 | 40.46 | 0 | 1618.26 | C+S GST 18% I/P RD | 291.28 | 1909.54 | 1909.54 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 1 Floor Regular Staircase | Kota Tread (L) - DSP | 69.363 | R.Ft | 50 | 100 | 86.7 | 0 | 3468.15 | C+S GST 18% I/P RD | 624.26 | 4092.41 | 4092.41 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Ground Floor Fire Staircase | Kota Tread (L) - DSP | 69.363 | R.Ft | 50 | 100 | 86.7 | 0 | 3468.15 | C+S GST 18% I/P RD | 624.26 | 4092.41 | 4092.41 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 3 Floor Regular Staircase | Kota Tread (L) - DSP | 69.363 | R.Ft | 50 | 100 | 86.7 | 0 | 3468.15 | C+S GST 18% I/P RD | 624.26 | 4092.41 | 4092.41 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Podium Floor Regular Staircase | Kota Tread (L) - DSP | 152.593 | R.Ft | 50 | 100 | 190.74 | 0 | 7629.65 | C+S GST 18% I/P RD | 1373.34 | 9002.99 | 9002.99 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 2 Floor Fire Staircase | Kota Tread (L) - DSP | 69.363 | R.Ft | 50 | 100 | 86.7 | 0 | 3468.15 | C+S GST 18% I/P RD | 624.26 | 4092.41 | 4092.41 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Podium Floor Fire Staircase | Kota Tread (L) - DSP | 152.593 | R.Ft | 50 | 100 | 190.74 | 0 | 7629.65 | C+S GST 18% I/P RD | 1373.34 | 9002.99 | 9002.99 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 2 Floor Regular Staircase | Kota Tread (L) - DSP | 69.363 | R.Ft | 50 | 100 | 86.7 | 0 | 3468.15 | C+S GST 18% I/P RD | 624.26 | 4092.41 | 4092.41 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Ground Floor Regular Staircase | Kota Tread (L) - DSP | 69.363 | R.Ft | 50 | 100 | 86.7 | 0 | 3468.15 | C+S GST 18% I/P RD | 624.26 | 4092.41 | 4092.41 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 3 Floor Fire Staircase | Kota Tread (L) - DSP | 69.363 | R.Ft | 50 | 100 | 86.7 | 0 | 3468.15 | C+S GST 18% I/P RD | 624.26 | 4092.41 | 4092.41 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 1 Floor Fire Staircase | Kota Tread (L) - DSP | 69.363 | R.Ft | 50 | 100 | 86.7 | 0 | 3468.15 | C+S GST 18% I/P RD | 624.26 | 4092.41 | 4092.41 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Ground Floor Fire Staircase | Kota Skirting (L)- BCO | 60.172 | R.Ft | 30 | 100 | 45.13 | 0 | 1805.16 | C+S GST 18% I/P RD | 324.92 | 2130.08 | 2130.08 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 2 Floor Fire Staircase | Kota Skirting (L)- BCO | 60.172 | R.Ft | 30 | 100 | 45.13 | 0 | 1805.16 | C+S GST 18% I/P RD | 324.92 | 2130.08 | 2130.08 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 908 | 92030 | 14 Oct 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1171 | A Parking 1 Floor Fire Staircase | Kota Skirting (L)- BCO | 60.172 | R.Ft | 30 | 100 | 45.13 | 0 | 1805.16 | C+S GST 18% I/P RD | 324.92 | 2130.08 | 2130.08 | Approved | 0 | 0 | 1794 | 14 Oct 2021
GANGA DHAM TOWERS | 1114 | 92029 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1217 | B 1202 Walls Satin Matt Painting | Oil base Primer-BC | 3116 | Sq.Ft | 1 | 100 | 77.9 | 0 | 3116 | IGST 18% I/P RD | 560.88 | 3676.88 | 3676.88 | Approved | 0 | 0 | 62 | 14 Oct 2021
GANGA DHAM TOWERS | 1114 | 92029 | 14 Oct 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1217 | B 1302 Walls Satin Matt Painting | Oil base Primer-BC | 3116 | Sq.Ft | 1 | 100 | 77.9 | 0 | 3116 | IGST 18% I/P RD | 560.88 | 3676.88 | 3676.88 | Approved | 0 | 0 | 62 | 14 Oct 2021
GANGA DHAM TOWERS | 272 | 92025 | 13 Oct 2021 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1232 | A Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3582.0022 | Sq.Ft | 181.3 | 100 | 0 | 0 | 649417 | C+S GST 18% I/P RD | 116895.06 | 766312.06 | 766312.06 | Approved | 0 | 1200000 | 23214 | 13 Oct 2021
GANGA DHAM TOWERS | 272 | 92025 | 13 Oct 2021 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1232 | A Bldg 32nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3969.0017 | Sq.Ft | 181.3 | 100 | 0 | 0 | 719580 | C+S GST 18% I/P RD | 129524.4 | 849104.4 | 849104.4 | Approved | 0 | 1200000 | 23214 | 13 Oct 2021
GANGA DHAM TOWERS | 272 | 92025 | 13 Oct 2021 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1232 | A Bldg 32nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2500 | Sq.Ft | 181.3 | 100 | 0 | 0 | 453250 | C+S GST 18% I/P RD | 81585 | 534835 | 534835 | Approved | 0 | 1200000 | 23214 | 13 Oct 2021
GANGA DHAM TOWERS | 272 | 92025 | 13 Oct 2021 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1232 | A Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2753.0006 | Sq.Ft | 181.3 | 100 | 0 | 0 | 499119 | C+S GST 18% I/P RD | 89841.42 | 588960.42 | 588960.42 | Approved | 0 | 1200000 | 23214 | 13 Oct 2021
GANGA DHAM TOWERS | 1141 | 92016 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1298 | B 2102 NOC | Italian Marble Flooring - BCo | 356.47 | Sq.Ft | 55 | 100 | 490.15 | 0 | 19605.85 | C+S GST 18% I/P RD | 3529.06 | 23134.91 | 23134.91 | Approved | 0 | 0 | 196 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 1101 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 50 | 100 | 303.75 | 0 | 12150 | C+S GST 18% I/P RD | 2187 | 14337 | 14337 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 1101 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 320.98 | Sq.Ft | 50 | 100 | 401.23 | 0 | 16049 | C+S GST 18% I/P RD | 2888.82 | 18937.82 | 18937.82 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 2102 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 60 | 100 | 308.39 | 0 | 12335.4 | C+S GST 18% I/P RD | 2220.38 | 14555.78 | 14555.78 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 1902 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 60 | 100 | 404.13 | 0 | 16165.2 | C+S GST 18% I/P RD | 2909.74 | 19074.94 | 19074.94 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 2102 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 60 | 100 | 404.13 | 0 | 16165.2 | C+S GST 18% I/P RD | 2909.74 | 19074.94 | 19074.94 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 1902 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 60 | 100 | 989.34 | 0 | 39573.6 | C+S GST 18% I/P RD | 7123.24 | 46696.84 | 46696.84 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 1902 Parents Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 60 | 100 | 308.39 | 0 | 12335.4 | C+S GST 18% I/P RD | 2220.38 | 14555.78 | 14555.78 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 2102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 60 | 100 | 989.34 | 0 | 39573.6 | C+S GST 18% I/P RD | 7123.24 | 46696.84 | 46696.84 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 758 | 92015 | 13 Oct 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1299 | B 1101 Living,Dining,Ent.Lobby | Italian Marble Flooring - BCo | 1150.67 | Sq.Ft | 50 | 100 | 1438.34 | 0 | 57533.5 | C+S GST 18% I/P RD | 10356.04 | 67889.54 | 67889.54 | Approved | 0 | 0 | 2219 | 13 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 1501 Terrace Vitrified Flooring | Vitrified Flooring -BC | 156.08 | Sq.Ft | 24 | 100 | 93.65 | 0 | 3745.92 | C+S GST 18% I/P RD | 674.26 | 4420.18 | 4420.18 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 60 | 100 | 859.22 | 0 | 34368.6 | C+S GST 18% I/P RD | 6186.34 | 40554.94 | 40554.94 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 60 | 100 | 273.68 | 0 | 10947 | C+S GST 18% I/P RD | 1970.46 | 12917.46 | 12917.46 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.65 | Sq.Ft | 60 | 100 | 315.98 | 0 | 12639 | C+S GST 18% I/P RD | 2275.02 | 14914.02 | 14914.02 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 60 | 100 | 200.78 | 0 | 8031 | C+S GST 18% I/P RD | 1445.58 | 9476.58 | 9476.58 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Master Bed Marble Flooring | Italian marble Skirting - BCo | 50.175 | R.Ft | 60 | 100 | 75.26 | 0 | 3010.5 | C+S GST 18% I/P RD | 541.9 | 3552.4 | 3552.4 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 23.685 | R.Ft | 60 | 100 | 35.53 | 0 | 1421.1 | C+S GST 18% I/P RD | 255.8 | 1676.9 | 1676.9 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 85.9425 | R.Ft | 60 | 100 | 128.91 | 0 | 5156.55 | C+S GST 18% I/P RD | 928.18 | 6084.73 | 6084.73 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 135.873 | Sq.Ft | 28 | 100 | 95.11 | 0 | 3804.44 | C+S GST 18% I/P RD | 684.8 | 4489.24 | 4489.24 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 1501 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 55 | 100 | 184.04 | 0 | 7361.75 | C+S GST 18% I/P RD | 1325.12 | 8686.87 | 8686.87 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 537 | 91976 | 12 Oct 2021 | 91976 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1153 | A 2102 Tiling Below Wooden Flooring | Ceramic Flooring work | 163.332 | Sq.Ft | 21 | 100 | 85.75 | 0 | 3429.97 | C+S GST 18% I/P RD | 617.4 | 4047.37 | 4047.37 | Approved | 0 | 0 | 939 | 12 Oct 2021
GANGA DHAM TOWERS | 540 | 91974 | 12 Oct 2021 | 91974 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1151 | A 1702 NOC | Italian Marble Mirror Polish- BCo | 44.6225 | Sq.Ft | 45 | 100 | 50.2 | 0 | 2008.01 | C+S GST 18% I/P RD | 361.44 | 2369.45 | 2369.45 | Approved | 0 | 0 | 20 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1403 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 121.9975 | Sq.Ft | 45 | 100 | 137.25 | 0 | 5489.89 | C+S GST 18% I/P RD | 988.18 | 6478.07 | 6478.07 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1402 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 143.2025 | Sq.Ft | 45 | 100 | 161.1 | 0 | 6444.11 | C+S GST 18% I/P RD | 1159.94 | 7604.05 | 7604.05 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1704 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 52.61 | Sq.Ft | 45 | 100 | 59.19 | 0 | 2367.45 | C+S GST 18% I/P RD | 426.14 | 2793.59 | 2793.59 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1402 Master Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 52.6625 | Sq.Ft | 45 | 100 | 59.25 | 0 | 2369.81 | C+S GST 18% I/P RD | 426.56 | 2796.37 | 2796.37 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1303 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 36.02 | Sq.Ft | 45 | 100 | 40.52 | 0 | 1620.9 | C+S GST 18% I/P RD | 291.76 | 1912.66 | 1912.66 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1403 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 36.02 | Sq.Ft | 45 | 100 | 40.52 | 0 | 1620.9 | C+S GST 18% I/P RD | 291.76 | 1912.66 | 1912.66 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1403 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 50.08 | Sq.Ft | 45 | 100 | 56.34 | 0 | 2253.6 | C+S GST 18% I/P RD | 405.64 | 2659.24 | 2659.24 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1702 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 52.6625 | Sq.Ft | 45 | 100 | 59.25 | 0 | 2369.81 | C+S GST 18% I/P RD | 426.56 | 2796.37 | 2796.37 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1704 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 37.9975 | Sq.Ft | 45 | 100 | 42.75 | 0 | 1709.89 | C+S GST 18% I/P RD | 307.78 | 2017.67 | 2017.67 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1303 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 50.08 | Sq.Ft | 45 | 100 | 56.34 | 0 | 2253.6 | C+S GST 18% I/P RD | 405.64 | 2659.24 | 2659.24 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1702 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 45.6125 | Sq.Ft | 45 | 100 | 51.31 | 0 | 2052.56 | C+S GST 18% I/P RD | 369.46 | 2422.02 | 2422.02 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1603 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 36.02 | Sq.Ft | 45 | 100 | 40.52 | 0 | 1620.9 | C+S GST 18% I/P RD | 291.76 | 1912.66 | 1912.66 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1704 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 147.7225 | Sq.Ft | 45 | 100 | 166.19 | 0 | 6647.51 | C+S GST 18% I/P RD | 1196.56 | 7844.07 | 7844.07 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1402 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 33.4625 | Sq.Ft | 45 | 100 | 37.65 | 0 | 1505.81 | C+S GST 18% I/P RD | 271.04 | 1776.85 | 1776.85 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1603 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 121.9975 | Sq.Ft | 45 | 100 | 137.25 | 0 | 5489.89 | C+S GST 18% I/P RD | 988.18 | 6478.07 | 6478.07 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1603 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 50.08 | Sq.Ft | 45 | 100 | 56.34 | 0 | 2253.6 | C+S GST 18% I/P RD | 405.64 | 2659.24 | 2659.24 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1303 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 121.9975 | Sq.Ft | 45 | 100 | 137.25 | 0 | 5489.89 | C+S GST 18% I/P RD | 988.18 | 6478.07 | 6478.07 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1204 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 33.4625 | Sq.Ft | 40 | 100 | 33.46 | 0 | 1338.5 | C+S GST 18% I/P RD | 240.94 | 1579.44 | 1579.44 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A-1203 Living,Dining,Passa. Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 121.9975 | Sq.Ft | 40 | 100 | 122 | 0 | 4879.9 | C+S GST 18% I/P RD | 878.38 | 5758.28 | 5758.28 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A-1203 Guest Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 36.02 | Sq.Ft | 40 | 100 | 36.02 | 0 | 1440.8 | C+S GST 18% I/P RD | 259.34 | 1700.14 | 1700.14 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1204 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 52.61 | Sq.Ft | 40 | 100 | 52.61 | 0 | 2104.4 | C+S GST 18% I/P RD | 378.8 | 2483.2 | 2483.2 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1204 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 147.7225 | Sq.Ft | 40 | 100 | 147.72 | 0 | 5908.9 | C+S GST 18% I/P RD | 1063.6 | 6972.5 | 6972.5 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A-1203 Master Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish- BCo | 50.08 | Sq.Ft | 40 | 100 | 50.08 | 0 | 2003.2 | C+S GST 18% I/P RD | 360.58 | 2363.78 | 2363.78 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1402 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 45.6125 | Sq.Ft | 45 | 100 | 51.31 | 0 | 2052.56 | C+S GST 18% I/P RD | 369.46 | 2422.02 | 2422.02 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1702 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 143.2025 | Sq.Ft | 45 | 100 | 161.1 | 0 | 6444.11 | C+S GST 18% I/P RD | 1159.94 | 7604.05 | 7604.05 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 641 | 91973 | 12 Oct 2021 | 91973 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1294 | A 1704 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 33.4625 | Sq.Ft | 45 | 100 | 37.65 | 0 | 1505.81 | C+S GST 18% I/P RD | 271.04 | 1776.85 | 1776.85 | Approved | 0 | 0 | 812 | 12 Oct 2021
GANGA DHAM TOWERS | 678 | 91972 | 12 Oct 2021 | 91972 | AVCON TECHNICS PVT LTD | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1158 | A 803 NOC | Italian Marble Flooring- cc | 416.73 | Sq.Ft | 55 | 100 | 0 | 0 | 22920.15 | C+S GST 18% I/P URD | 4125.62 | 27045.77 | 27045.77 | Approved | 0 | 0 | 274 | 12 Oct 2021
GANGA DHAM TOWERS | 678 | 91972 | 12 Oct 2021 | 91972 | AVCON TECHNICS PVT LTD | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1158 | A 803 NOC | Italian marble Skirting - BCo | 81.72 | R.Ft | 55 | 100 | 0 | 0 | 4494.6 | C+S GST 18% I/P RD | 809.02 | 5303.62 | 5303.62 | Approved | 0 | 0 | 274 | 12 Oct 2021
GANGA DHAM TOWERS | 495 | 91971 | 12 Oct 2021 | 374 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1162 | B 2101 Gypsum Plaster (Refuge Flat) | Gypsum on Wall (L) | 4900.5 | Sq.Ft | 4 | 100 | 490.05 | 0 | 19602 | C+S GST 18% I/P RD | 3528.36 | 23130.36 | 23130.36 | Approved | 0 | 0 | 264 | 12 Oct 2021
GANGA DHAM TOWERS | 495 | 91971 | 12 Oct 2021 | 374 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1162 | B 2101 Gypsum Plaster (Refuge Flat) | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 264 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 11th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 1st Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 2nd Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 16th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 18th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 19th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 13th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 20th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 7th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 9th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 8th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 24th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 15th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 5th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 6th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 3rd Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 4th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 10th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 14th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 23rd Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 12th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 21st Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 22nd Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 25th Floor Regular Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 6th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 11th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 12th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 13th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 8th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 23rd Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 4th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 1st Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 14th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 7th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 9th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 2nd Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 3rd Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 20th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 5th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 18th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 19th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 25th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 15th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 21st Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 10th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 24th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 18th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 15th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 12th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 9th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 2nd Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 7th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 6th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 5th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 23rd Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 11th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 22nd Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 16th Floor Regular Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 3rd Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 1st Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 2nd Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 19th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 13th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 16th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 3rd floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 22nd Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 24th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 1st Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 10th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 8th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 21st Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 14th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 4th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 20th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 25th Floor Regular Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 12th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 16th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 21st Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 14th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 24th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 13th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 20th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 10th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 11th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 22nd Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 6th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 5th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 7th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 9th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 23rd Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 4th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 15th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 8th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 907 | 91970 | 12 Oct 2021 |  | RAJESH MEHTA | R.M.Marbles | EV - 1274 | B 25th Floor Regular Staircase Flooring | Kota Flooring (L)- BCO | 76.53 | Sq.Ft | 50 | 100 | 95.66 | 0 | 3826.5 | C+S GST 18% I/P RD | 688.78 | 4515.28 | 4515.28 | Approved | 0 | 0 | 2670 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 1st Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 20th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 11th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 21st Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 22nd Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 11th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 21st Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 23rd Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 8th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 1st Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 111.4725 | R.Ft | 45 | 100 | 125.41 | 0 | 5016.26 | C+S GST 18% I/P RD | 902.92 | 5919.18 | 5919.18 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 2nd Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 23rd Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 14th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 18th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 21st Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 6th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 20th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 8th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 9th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 4th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 13th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 3rd Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 24th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 23rd Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 18th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Riser (L)- BCO | 111.4725 | R.Ft | 45 | 100 | 125.41 | 0 | 5016.26 | C+S GST 18% I/P RD | 902.92 | 5919.18 | 5919.18 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 19th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 19th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 16th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 5th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 7th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 12th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 15th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 22nd Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 24th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 11th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 8th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 19th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 21st Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 6th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 7th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Flooring (L)- BCO | 99.8625 | Sq.Ft | 50 | 100 | 124.83 | 0 | 4993.13 | C+S GST 18% I/P RD | 898.76 | 5891.89 | 5891.89 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 3rd Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 4th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 14th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 18th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 20th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 1st Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 10th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 13th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 15th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 2nd Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 5th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 12th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 23rd Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 24th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 22nd Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 9th Floor Fire Staircase Flooring | Kota Flooring (L)- BCO | 158.43 | Sq.Ft | 50 | 100 | 198.04 | 0 | 7921.5 | C+S GST 18% I/P RD | 1425.88 | 9347.38 | 9347.38 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 24th Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 22nd Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 20th Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Skirting (L)- BCO | 64.47 | R.Ft | 30 | 100 | 48.35 | 0 | 1934.1 | C+S GST 18% I/P RD | 348.14 | 2282.24 | 2282.24 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 23rd Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 21st Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 19th Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Fire Staircase Flooring | Kota Skirting (L)- BCO | 64.965 | R.Ft | 30 | 100 | 48.72 | 0 | 1948.95 | C+S GST 18% I/P RD | 350.82 | 2299.77 | 2299.77 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 18th Floor Staircase Flooring | Kota Skirting (L)- BCO | 55.245 | R.Ft | 30 | 100 | 41.43 | 0 | 1657.35 | C+S GST 18% I/P RD | 298.32 | 1955.67 | 1955.67 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 18th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 20th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Tread (L) - DSP | 111.4725 | R.Ft | 50 | 100 | 139.34 | 0 | 5573.63 | C+S GST 18% I/P RD | 1003.26 | 6576.89 | 6576.89 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 8th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 9th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 11th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 13th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 15th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 16th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 19th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 3rd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 5th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 12th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 4th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 19th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 24th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 6th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 2nd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 7th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 17th Floor + Fire Check Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 111.4725 | R.Ft | 50 | 100 | 139.34 | 0 | 5573.63 | C+S GST 18% I/P RD | 1003.26 | 6576.89 | 6576.89 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 18th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 23rd Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 21st Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 22nd Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 14th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 23rd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 22nd Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 21st Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 20th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 10th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 24th Floor Fire Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 10th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 22nd Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 18th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 21st Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 2nd Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 23rd Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 18th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 9th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 13th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 12th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 14th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 19th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 24th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 3rd Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 4th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 22nd Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 15th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 5th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 6th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 7th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 20th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 19th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 20th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 16th Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 17 th Floor & Fire Check Floor Staircase Flooring | Kota Champher | 111.4725 | R.Ft | 7.5 | 100 | 20.9 | 0 | 836.04 | C+S GST 18% I/P RD | 150.48 | 986.52 | 986.52 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 1st Floor Fire Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 24th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 905 | 91969 | 12 Oct 2021 | R/21-22/46 | R.M.Marbles | R.M.Marbles | EV - 1291 | A 25th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 4537 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 39.4737 | Sq.Ft | 152 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 39.4737 | Sq.Ft | 152 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 39.4737 | Sq.Ft | 152 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 39.4737 | Sq.Ft | 152 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.1517 | Sq.Ft | 161.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 42.1053 | Sq.Ft | 142.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.1517 | Sq.Ft | 161.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.1517 | Sq.Ft | 161.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 42.1053 | Sq.Ft | 142.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 42.1053 | Sq.Ft | 142.5 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91968 | 12 Oct 2021 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 1222 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 21.0526 | Sq.Ft | 142.5 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 630 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 2003 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 76.1625 | R.Ft | 60 | 100 | 114.24 | 0 | 4569.75 | C+S GST 18% I/P RD | 822.56 | 5392.31 | 5392.31 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 2004 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 32.235 | R.Ft | 60 | 100 | 48.35 | 0 | 1934.1 | C+S GST 18% I/P RD | 348.14 | 2282.24 | 2282.24 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 2004 Master Bed Marble Flooring | Italian marble Skirting - BCo | 43.065 | R.Ft | 60 | 100 | 64.6 | 0 | 2583.9 | C+S GST 18% I/P RD | 465.1 | 3049 | 3049 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 2004 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 87.195 | R.Ft | 60 | 100 | 130.79 | 0 | 5231.7 | C+S GST 18% I/P RD | 941.7 | 6173.4 | 6173.4 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 2004 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 15.79 | R.Ft | 60 | 100 | 23.69 | 0 | 947.4 | C+S GST 18% I/P RD | 170.54 | 1117.94 | 1117.94 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 2003 Master Bed Marble Flooring | Italian marble Skirting - BCo | 35.1675 | R.Ft | 60 | 100 | 52.75 | 0 | 2110.05 | C+S GST 18% I/P RD | 379.8 | 2489.85 | 2489.85 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 2003 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 31.2525 | R.Ft | 60 | 100 | 46.88 | 0 | 1875.15 | C+S GST 18% I/P RD | 337.52 | 2212.67 | 2212.67 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 803 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 31.2525 | R.Ft | 50 | 100 | 39.07 | 0 | 1562.63 | C+S GST 18% I/P RD | 281.28 | 1843.91 | 1843.91 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 803 Master Bed Marble Flooring | Italian marble Skirting - BCo | 35.1675 | R.Ft | 50 | 100 | 43.96 | 0 | 1758.38 | C+S GST 18% I/P RD | 316.5 | 2074.88 | 2074.88 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 803 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 76.1625 | R.Ft | 50 | 100 | 95.2 | 0 | 3808.13 | C+S GST 18% I/P RD | 685.46 | 4493.59 | 4493.59 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Terrace Vitrified Flooring | Vitrified Flooring -BC | 156.08 | Sq.Ft | 15 | 100 | 58.53 | 0 | 2341.2 | C+S GST 18% I/P RD | 421.42 | 2762.62 | 2762.62 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Parents Toilet dado | Dado BC | 106.04 | Sq.Ft | 14 | 100 | 37.11 | 0 | 1484.56 | C+S GST 18% I/P RD | 267.22 | 1751.78 | 1751.78 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Powder Toilet dado | Dado BC | 85.23 | Sq.Ft | 14 | 100 | 29.83 | 0 | 1193.22 | C+S GST 18% I/P RD | 214.78 | 1408 | 1408 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Powder Toilet dado | Dado BC | 97.36 | Sq.Ft | 14 | 100 | 34.08 | 0 | 1363.04 | C+S GST 18% I/P RD | 245.34 | 1608.38 | 1608.38 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Master Toilet dado | Dado BC | 145.22 | Sq.Ft | 14 | 100 | 50.83 | 0 | 2033.08 | C+S GST 18% I/P RD | 365.96 | 2399.04 | 2399.04 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Guest Toilet dado | Dado BC | 131.02 | Sq.Ft | 14 | 100 | 45.86 | 0 | 1834.28 | C+S GST 18% I/P RD | 330.18 | 2164.46 | 2164.46 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Children Toilet dado | Dado BC | 145.22 | Sq.Ft | 14 | 100 | 50.83 | 0 | 2033.08 | C+S GST 18% I/P RD | 365.96 | 2399.04 | 2399.04 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Children Toilet Dado | Dado BC | 148.12 | Sq.Ft | 14 | 100 | 51.84 | 0 | 2073.68 | C+S GST 18% I/P RD | 373.26 | 2446.94 | 2446.94 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 403 Dry Balcony dado | Dado BC | 86.7 | Sq.Ft | 14 | 100 | 30.35 | 0 | 1213.8 | C+S GST 18% I/P RD | 218.48 | 1432.28 | 1432.28 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Master Toilet dado | Dado BC | 148.12 | Sq.Ft | 14 | 100 | 51.84 | 0 | 2073.68 | C+S GST 18% I/P RD | 373.26 | 2446.94 | 2446.94 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.231 | Sq.Ft | 13 | 100 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.503 | Sq.Ft | 13 | 100 | 15.11 | 0 | 604.54 | C+S GST 18% I/P RD | 108.82 | 713.36 | 713.36 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 603 Staff Toilet dado | L Groove - BCV | 24.67 | R.Ft | 20 | 100 | 12.34 | 0 | 493.4 | C+S GST 18% I/P RD | 88.82 | 582.22 | 582.22 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Master Toilet dado | L Groove - BCV | 43.23 | R.Ft | 20 | 100 | 21.62 | 0 | 864.6 | C+S GST 18% I/P RD | 155.62 | 1020.22 | 1020.22 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 604 Staff Toilet dado | L Groove - BCV | 24.37 | R.Ft | 20 | 100 | 12.19 | 0 | 487.4 | C+S GST 18% I/P RD | 87.74 | 575.14 | 575.14 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Parents Toilet dado | L Groove - BCV | 24.44 | R.Ft | 20 | 100 | 12.22 | 0 | 488.8 | C+S GST 18% I/P RD | 87.98 | 576.78 | 576.78 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Powder Toilet dado | L Groove - BCV | 35.82 | R.Ft | 20 | 100 | 17.91 | 0 | 716.4 | C+S GST 18% I/P RD | 128.96 | 845.36 | 845.36 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Master Toilet dado | L Groove - BCV | 42.9 | R.Ft | 20 | 100 | 21.45 | 0 | 858 | C+S GST 18% I/P RD | 154.44 | 1012.44 | 1012.44 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Children Toilet Dado | L Groove - BCV | 43 | R.Ft | 20 | 100 | 21.5 | 0 | 860 | C+S GST 18% I/P RD | 154.8 | 1014.8 | 1014.8 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 603 Staff Toilet dado | Dado BC | 135.37 | Sq.Ft | 13 | 100 | 44 | 0 | 1759.81 | C+S GST 18% I/P RD | 316.76 | 2076.57 | 2076.57 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 404 Staff Toilet dado | Dado BC | 135.37 | Sq.Ft | 13 | 100 | 44 | 0 | 1759.81 | C+S GST 18% I/P RD | 316.76 | 2076.57 | 2076.57 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 604 Staff Toilet dado | Dado BC | 121.833 | Sq.Ft | 13 | 100 | 39.6 | 0 | 1583.83 | C+S GST 18% I/P RD | 285.08 | 1868.91 | 1868.91 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 404 Staff Toilet dado | L Groove - BCV | 24.37 | R.Ft | 20 | 100 | 12.19 | 0 | 487.4 | C+S GST 18% I/P RD | 87.74 | 575.14 | 575.14 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Guest Toilet dado | L Groove - BCV | 30.01 | R.Ft | 20 | 100 | 15.01 | 0 | 600.2 | C+S GST 18% I/P RD | 108.04 | 708.24 | 708.24 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Powder Toilet dado | L Groove - BCV | 5.74 | R.Ft | 20 | 100 | 2.87 | 0 | 114.8 | C+S GST 18% I/P RD | 20.66 | 135.46 | 135.46 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 1603 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 40.648 | Sq.Ft | 21 | 100 | 21.34 | 0 | 853.61 | C+S GST 18% I/P RD | 153.64 | 1007.25 | 1007.25 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 604 Granite Kitchen Otta | Granite Kitchen Otta BC | 19.84 | R.Ft | 300 | 100 | 148.8 | 0 | 5952 | C+S GST 18% I/P RD | 1071.36 | 7023.36 | 7023.36 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Master Toilet dado | Dado BC | 67.78 | Sq.Ft | 15 | 100 | 25.42 | 0 | 1016.7 | C+S GST 18% I/P RD | 183 | 1199.7 | 1199.7 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Powder Toilet dado | Dado BC | 39.29 | Sq.Ft | 15 | 100 | 14.73 | 0 | 589.35 | C+S GST 18% I/P RD | 106.08 | 695.43 | 695.43 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Parents Toilet dado | Dado BC | 86.59 | Sq.Ft | 15 | 100 | 32.47 | 0 | 1298.85 | C+S GST 18% I/P RD | 233.8 | 1532.65 | 1532.65 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Powder Toilet dado | Dado BC | 38.86 | Sq.Ft | 15 | 100 | 14.57 | 0 | 582.9 | C+S GST 18% I/P RD | 104.92 | 687.82 | 687.82 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Children Toilet Dado | Dado BC | 68.57 | Sq.Ft | 15 | 100 | 25.71 | 0 | 1028.55 | C+S GST 18% I/P RD | 185.14 | 1213.69 | 1213.69 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Master Toilet dado | Dado BC | 66.72 | Sq.Ft | 15 | 100 | 25.02 | 0 | 1000.8 | C+S GST 18% I/P RD | 180.14 | 1180.94 | 1180.94 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Children Toilet dado | Dado BC | 66.72 | Sq.Ft | 15 | 100 | 25.02 | 0 | 1000.8 | C+S GST 18% I/P RD | 180.14 | 1180.94 | 1180.94 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Guest Toilet dado | Dado BC | 58.28 | Sq.Ft | 15 | 100 | 21.86 | 0 | 874.2 | C+S GST 18% I/P RD | 157.36 | 1031.56 | 1031.56 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.527 | Sq.Ft | 13 | 100 | 7.32 | 0 | 292.85 | C+S GST 18% I/P RD | 52.72 | 345.57 | 345.57 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 13 | 100 | 14.86 | 0 | 594.48 | C+S GST 18% I/P RD | 107 | 701.48 | 701.48 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 46.494 | Sq.Ft | 13 | 100 | 15.11 | 0 | 604.42 | C+S GST 18% I/P RD | 108.8 | 713.22 | 713.22 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 37.539 | Sq.Ft | 13 | 100 | 12.2 | 0 | 488.01 | C+S GST 18% I/P RD | 87.84 | 575.85 | 575.85 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 504 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 43.11 | Sq.Ft | 13 | 100 | 14.01 | 0 | 560.43 | C+S GST 18% I/P RD | 100.88 | 661.31 | 661.31 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 551 | 91967 | 12 Oct 2021 | 91967 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1152 | A 503 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 45.729 | Sq.Ft | 13 | 100 | 14.86 | 0 | 594.48 | C+S GST 18% I/P RD | 107 | 701.48 | 701.48 | Approved | 0 | 0 | 735 | 12 Oct 2021
GANGA DHAM TOWERS | 1163 | 91965 | 12 Oct 2021 | 91965 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1156 | A 2004 NOC | Italian marble Skirting - BCo | 34.44 | R.Ft | 55 | 100 | 47.36 | 0 | 1894.2 | C+S GST 18% I/P RD | 340.96 | 2235.16 | 2235.16 | Approved | 0 | 0 | 227 | 12 Oct 2021
GANGA DHAM TOWERS | 1163 | 91965 | 12 Oct 2021 | 91965 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1156 | A 2004 NOC | Italian marble Skirting - BCo | 37.2675 | R.Ft | 55 | 100 | 51.24 | 0 | 2049.71 | C+S GST 18% I/P RD | 368.94 | 2418.65 | 2418.65 | Approved | 0 | 0 | 227 | 12 Oct 2021
GANGA DHAM TOWERS | 1163 | 91965 | 12 Oct 2021 | 91965 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1156 | A 2004 NOC | Italian Marble Flooring - BCo | 162.47 | Sq.Ft | 55 | 100 | 223.4 | 0 | 8935.85 | C+S GST 18% I/P RD | 1608.46 | 10544.31 | 10544.31 | Approved | 0 | 0 | 227 | 12 Oct 2021
GANGA DHAM TOWERS | 1163 | 91965 | 12 Oct 2021 | 91965 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1156 | A 2004 NOC | Italian Marble Flooring - BCo | 178.62 | Sq.Ft | 55 | 100 | 245.6 | 0 | 9824.1 | C+S GST 18% I/P RD | 1768.34 | 11592.44 | 11592.44 | Approved | 0 | 0 | 227 | 12 Oct 2021
GANGA DHAM TOWERS | 634 | 91964 | 12 Oct 2021 | KVE/233 | R K INTERIOR | KADAVATH VENKAT ENTERPRISES | EV - 1406 | A 24th Floor Lobbby Flooring | Vitrified Flooring -Bco | 44.4444 | Sq.Ft | 45 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91963 | 12 Oct 2021 | KVE/230 | GOURI INFRA | KADAVATH VENKAT ENTERPRISES | EV - 1402 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.1842 | Sq.Ft | 152 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 85 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91963 | 12 Oct 2021 | KVE/230 | GOURI INFRA | KADAVATH VENKAT ENTERPRISES | EV - 1402 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.1842 | Sq.Ft | 152 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 85 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91963 | 12 Oct 2021 | KVE/230 | GOURI INFRA | KADAVATH VENKAT ENTERPRISES | EV - 1402 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10.5263 | Sq.Ft | 161.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 85 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91963 | 12 Oct 2021 | KVE/230 | GOURI INFRA | KADAVATH VENKAT ENTERPRISES | EV - 1402 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10.5263 | Sq.Ft | 161.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 85 | 12 Oct 2021
GANGA DHAM TOWERS | 272 | 91963 | 12 Oct 2021 | KVE/230 | GOURI INFRA | KADAVATH VENKAT ENTERPRISES | EV - 1402 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10.5263 | Sq.Ft | 161.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 85 | 12 Oct 2021
GANGA DHAM TOWERS | 616 | 91962 | 12 Oct 2021 | KVE/231 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1290 | B P2 Parking Floor Blockwork 4" (105 Level) | Blockwork 4" - BC | 600 | Sq.Ft | 13 | 100 | 195 | 0 | 7800 | C+S GST 18% I/P RD | 1404 | 9204 | 9204 | Approved | 0 | 0 | 78 | 12 Oct 2021
GANGA DHAM TOWERS | 773 | 91961 | 12 Oct 2021 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 1154 | B P1 Parking chemical grouting | Ghadai work- BCP | 15000 | Sq.Ft | 1 | 100 | 375 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 300 | 12 Oct 2021
GANGA DHAM TOWERS | 773 | 91961 | 12 Oct 2021 |  | SHWETA SURESH GOVALKAR | PRAKASH CONTRACTOR | EV - 1154 | B P1 Parking chemical grouting | Chemical Grouting (L) | 15000 | Sq.Ft | 1 | 100 | 375 | 0 | 15000 | CGST 0% URD I/P | 0 | 15000 | 15000 | Approved | 0 | 0 | 300 | 12 Oct 2021
GANGA DHAM TOWERS | 1011 | 91960 | 12 Oct 2021 |  | REVANTI FURNITURE | REVANTI FURNITURE | EV - 1223 | Club House Glass / Carpentary Shifting Work | Dismentalling work-UTI | 0.2 | No. | 61000 | 100 | 0 | 0 | 12200 | CGST 0% URD I/P | 0 | 12200 | 12200 | Approved | 0 | 0 | 122 | 12 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2003 Gypsum Plaster | Dhar Core (L) | 513.261 | R.Ft | 10 | 100 | 128.32 | 0 | 5132.61 | C+S GST 18% I/P RD | 923.86 | 6056.47 | 6056.47 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2204 Gypsum Plaster | Dhar Core (L) | 468.237 | R.Ft | 10 | 100 | 117.06 | 0 | 4682.37 | C+S GST 18% I/P RD | 842.82 | 5525.19 | 5525.19 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2103 Gypsum Plaster | Dhar Core (L) | 513.261 | R.Ft | 10 | 100 | 128.32 | 0 | 5132.61 | C+S GST 18% I/P RD | 923.86 | 6056.47 | 6056.47 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2004 Gypsum Plaster | Dhar Core (L) | 468.237 | R.Ft | 10 | 100 | 117.06 | 0 | 4682.37 | C+S GST 18% I/P RD | 842.82 | 5525.19 | 5525.19 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2303 Gypsum Plaster | Dhar Core (L) | 513.261 | R.Ft | 10 | 100 | 128.32 | 0 | 5132.61 | C+S GST 18% I/P RD | 923.86 | 6056.47 | 6056.47 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2104 Gypsum Plaster | Dhar Core (L) | 468.237 | R.Ft | 10 | 100 | 117.06 | 0 | 4682.37 | C+S GST 18% I/P RD | 842.82 | 5525.19 | 5525.19 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 1903 Gypsum Plaster | Dhar Core (L) | 513.261 | R.Ft | 10 | 100 | 128.32 | 0 | 5132.61 | C+S GST 18% I/P RD | 923.86 | 6056.47 | 6056.47 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2203 Gypsum Plaster | Dhar Core (L) | 513.261 | R.Ft | 10 | 100 | 128.32 | 0 | 5132.61 | C+S GST 18% I/P RD | 923.86 | 6056.47 | 6056.47 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2404 Gypsum Plaster | Dhar Core (L) | 468.237 | R.Ft | 10 | 100 | 117.06 | 0 | 4682.37 | C+S GST 18% I/P RD | 842.82 | 5525.19 | 5525.19 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 1904 Gypsum Plaster | Dhar Core (L) | 468.237 | R.Ft | 10 | 100 | 117.06 | 0 | 4682.37 | C+S GST 18% I/P RD | 842.82 | 5525.19 | 5525.19 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2103 Gypsum Plaster | Gypsum on Wall (L) | 2198.37 | Sq.Ft | 4 | 100 | 219.84 | 0 | 8793.48 | C+S GST 18% I/P RD | 1582.82 | 10376.3 | 10376.3 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2104 Gypsum Plaster | Gypsum on Wall (L) | 2474.34 | Sq.Ft | 4 | 100 | 247.43 | 0 | 9897.36 | C+S GST 18% I/P RD | 1781.52 | 11678.88 | 11678.88 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2404 Gypsum Plaster | Gypsum on Wall (L) | 2474.34 | Sq.Ft | 4 | 100 | 247.43 | 0 | 9897.36 | C+S GST 18% I/P RD | 1781.52 | 11678.88 | 11678.88 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 395 | 91954 | 11 Oct 2021 | 376 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1164 | A Bldg Flat No. 2303 Gypsum Plaster | Gypsum on Wall (L) | 2198.37 | Sq.Ft | 4 | 100 | 219.84 | 0 | 8793.48 | C+S GST 18% I/P RD | 1582.82 | 10376.3 | 10376.3 | Approved | 0 | 0 | 865 | 11 Oct 2021
GANGA DHAM TOWERS | 745 | 91940 | 09 Oct 2021 | 55 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1084 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 0.9 | Day | 466.66 | 100 | 0 | 0 | 419.99 | C+S GST 18% I/P RD | 75.6 | 495.59 | 495.59 | Approved | 0 | 0 | 126 | 09 Oct 2021
GANGA DHAM TOWERS | 745 | 91940 | 09 Oct 2021 | 55 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1084 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 26.1025 | Day | 466.66 | 100 | 0 | 0 | 12181 | C+S GST 18% I/P RD | 2192.58 | 14373.58 | 14373.58 | Approved | 0 | 0 | 126 | 09 Oct 2021
GANGA DHAM TOWERS | 237 | 91924 | 08 Oct 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1287 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.6 | Month | 7000 | 100 | 0 | 0 | 4200 | CGST 0% URD I/P | 0 | 4200 | 4200 | Approved | 0 | 0 | 42 | 08 Oct 2021
GANGA DHAM TOWERS | 258 | 91923 | 08 Oct 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1286 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.6 | Month | 2500 | 100 | 0 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 15 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 603 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 1603 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 803 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 1603 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 803 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 601 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 202 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 602 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 1703 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 1603 Bore Packing, IPS seal coat, Perma Eazee coat | Bore Packing 8"- UST | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 704 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 401 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 701 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 502 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 201 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1200 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 1703 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 5 | No. | 70 | 100 | 35 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 1603 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 19 | No. | 70 | 100 | 133 | 0 | 1330 | CGST 0% URD I/P | 0 | 1330 | 1330 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 401 | 91922 | 08 Oct 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A 803 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 12 | No. | 70 | 100 | 84 | 0 | 840 | CGST 0% URD I/P | 0 | 840 | 840 |  | 0 | 0 | 184 | 08 Oct 2021
GANGA DHAM TOWERS | 1037 | 91914 | 07 Oct 2021 | om/2021-22/272 | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 1113 | Head Office Security Service | Security Guard AIE - | 60 | Day | 433.33 | 100 | 0 | 0 | 25999.8 | C+S GST 18% RCM | 4679.96 | 30679.76 | 30679.76 | Approved | 0 | 0 | 260 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 9th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 13.7652 | Sq.Ft | 123.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.9298 | Sq.Ft | 142.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 24th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10.5263 | Sq.Ft | 161.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.9298 | Sq.Ft | 142.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 23rd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10.5263 | Sq.Ft | 161.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.9298 | Sq.Ft | 142.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.9298 | Sq.Ft | 142.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10.5263 | Sq.Ft | 161.5 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 10th Slab Refuge Built-up Area (L) | RCC Superstructure (B-up area) | 27.5 | Sq.Ft | 240 | 100 | 0 | 0 | 6600 | C+S GST 18% I/P RD | 1188 | 7788 | 7788 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 15th Slab Refuge Built-up Area (L) | RCC Superstructure (B-up area) | 27.5 | Sq.Ft | 240 | 100 | 0 | 0 | 6600 | C+S GST 18% I/P RD | 1188 | 7788 | 7788 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.1842 | Sq.Ft | 152 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.1842 | Sq.Ft | 152 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 12.782 | Sq.Ft | 133 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 12.782 | Sq.Ft | 133 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.1842 | Sq.Ft | 152 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 11.1842 | Sq.Ft | 152 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 12.782 | Sq.Ft | 133 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 272 | 91901 | 07 Oct 2021 | 91901 | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1104 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 12.782 | Sq.Ft | 133 | 100 | 0 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 404 | 07 Oct 2021
GANGA DHAM TOWERS | 616 | 91900 | 07 Oct 2021 | KVE/234 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1289 | B Ground Floor Blockwork 4" (99 Level) | Blockwork 4" - BC | 100 | Sq.Ft | 13 | 100 | 32.5 | 0 | 1300 | C+S GST 18% I/P RD | 234 | 1534 | 1534 | Approved | 0 | 0 | 162 | 07 Oct 2021
GANGA DHAM TOWERS | 616 | 91900 | 07 Oct 2021 | KVE/234 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1289 | B P2 Parking Floor Blockwork 4" (105 Level) | Blockwork 4" - BC | 300 | Sq.Ft | 13 | 100 | 97.5 | 0 | 3900 | C+S GST 18% I/P RD | 702 | 4602 | 4602 | Approved | 0 | 0 | 162 | 07 Oct 2021
GANGA DHAM TOWERS | 616 | 91900 | 07 Oct 2021 | KVE/234 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1289 | B P1 Parking Floor Blockwork 4" (102 Level) | Blockwork 4" - BC | 184 | Sq.Ft | 13 | 100 | 59.8 | 0 | 2392 | C+S GST 18% I/P RD | 430.56 | 2822.56 | 2822.56 | Approved | 0 | 0 | 162 | 07 Oct 2021
GANGA DHAM TOWERS | 616 | 91900 | 07 Oct 2021 | KVE/234 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1289 | B P3 Parking Floor Blockwork 4" (108 Level) | Blockwork 4" - BC | 665.63 | Sq.Ft | 13 | 100 | 216.33 | 0 | 8653.19 | C+S GST 18% I/P RD | 1557.58 | 10210.77 | 10210.77 | Approved | 0 | 0 | 162 | 07 Oct 2021
GANGA DHAM TOWERS | 755 | 91899 | 07 Oct 2021 | 124 | SS ENTERPRISES | SS ENTERPRISES | EV - 1369 | C Murrum Shifting | Murum Shifting work | 2681.99 | Cu.Mtrs | 150 | 100 | 10057.46 | 0 | 402298.5 | C+S GST 18% I/P RD | 72413.74 | 474712.24 | 474712.24 | Approved | 0 | 0 | 4023 | 07 Oct 2021
GANGA DHAM TOWERS | 604 | 91896 | 07 Oct 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 1300 | A 13th Floor Internal Flat Sprinkler System | SITC GI Pipe C Class 32mm dia.(L) | 15.19 | Mtrs | 92 | 100 | 34.94 | 0 | 1397.48 | C+S GST 18% I/P RD | 251.54 | 1649.02 | 1649.02 | Approved | 0 | 0 | 210 | 07 Oct 2021
GANGA DHAM TOWERS | 604 | 91896 | 07 Oct 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 1300 | A 13th Floor Internal Flat Sprinkler System | SITC GI Pipe C Class 32mm dia.(L) | 14.81 | Mtrs | 92 | 100 | 0 | 0 | 1362.52 | C+S GST 18% I/P RD | 245.26 | 1607.78 | 1607.78 | Approved | 0 | 0 | 210 | 07 Oct 2021
GANGA DHAM TOWERS | 604 | 91896 | 07 Oct 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 1300 | A 13th Floor Internal Flat Sprinkler System | SITC GI Pipe C Class 40mm dia.(L) | 44.88 | Mtrs | 110 | 100 | 123.42 | 0 | 4936.8 | C+S GST 18% I/P RD | 888.62 | 5825.42 | 5825.42 | Approved | 0 | 0 | 210 | 07 Oct 2021
GANGA DHAM TOWERS | 604 | 91896 | 07 Oct 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 1300 | A Sprinkler System | Sprinkler 15mm 68 dg Pendent (L) | 45 | No. | 57 | 100 | 64.13 | 0 | 2565 | C+S GST 18% I/P RD | 461.7 | 3026.7 | 3026.7 | Approved | 0 | 0 | 210 | 07 Oct 2021
GANGA DHAM TOWERS | 604 | 91896 | 07 Oct 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 1300 | A Sprinkler System | Sprinkler 15mm 68 dg Pendent (L) | 21.7193 | No. | 57 | 100 | 30.95 | 0 | 1238 | C+S GST 18% I/P RD | 222.84 | 1460.84 | 1460.84 | Approved | 0 | 0 | 210 | 07 Oct 2021
GANGA DHAM TOWERS | 604 | 91896 | 07 Oct 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 1300 | A Sprinkler System | SITC GI Pipe C Class 50mm dia.(L) | 30 | Mtrs | 150 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 210 | 07 Oct 2021
GANGA DHAM TOWERS | 604 | 91896 | 07 Oct 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 1300 | A 13th Floor Internal Flat Sprinkler System | SITC GI Pipe C Class 25mm dia-(L) | 68.4932 | Mtrs | 73 | 100 | 125 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 210 | 07 Oct 2021
GANGA DHAM TOWERS | 986 | 91893 | 06 Oct 2021 | MA/G/21-22/326 | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 1028 | Sales Office Dismentling Work (L) | Dismantling of AC | 6 | No. | 750 | 100 | 0 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 68 | 06 Oct 2021
GANGA DHAM TOWERS | 149 | 91872 | 05 Oct 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1116 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3276 | No. | 4 | 100 | 0 | 0 | 13104 | CGST 0% URD I/P | 0 | 13104 | 13104 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 537 | 91861 | 05 Oct 2021 | 91861 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1150 | A 1702 Terrace Vitrified Flooring | Vitrified Flooring -BC | 117.06 | Sq.Ft | 24 | 100 | 70.24 | 0 | 2809.44 | C+S GST 18% I/P RD | 505.7 | 3315.14 | 3315.14 | Approved | 0 | 0 | 28 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 2004 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 60 | 100 | 200.78 | 0 | 8031 | C+S GST 18% I/P RD | 1445.58 | 9476.58 | 9476.58 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 2003 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 487.99 | Sq.Ft | 60 | 100 | 731.99 | 0 | 29279.4 | C+S GST 18% I/P RD | 5270.3 | 34549.7 | 34549.7 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 2003 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 200.32 | Sq.Ft | 60 | 100 | 300.48 | 0 | 12019.2 | C+S GST 18% I/P RD | 2163.46 | 14182.66 | 14182.66 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 2004 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.44 | Sq.Ft | 60 | 100 | 315.66 | 0 | 12626.4 | C+S GST 18% I/P RD | 2272.76 | 14899.16 | 14899.16 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 2003 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144.08 | Sq.Ft | 60 | 100 | 216.12 | 0 | 8644.8 | C+S GST 18% I/P RD | 1556.06 | 10200.86 | 10200.86 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 2003 Tiling Below Wooden Flooring | Ceramic Flooring work | 171.58 | Sq.Ft | 21 | 100 | 90.08 | 0 | 3603.18 | C+S GST 18% I/P RD | 648.58 | 4251.76 | 4251.76 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 803 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144.08 | Sq.Ft | 50 | 100 | 180.1 | 0 | 7204 | C+S GST 18% I/P RD | 1296.72 | 8500.72 | 8500.72 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 803 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 487.99 | Sq.Ft | 50 | 100 | 609.99 | 0 | 24399.5 | C+S GST 18% I/P RD | 4391.92 | 28791.42 | 28791.42 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 803 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 200.32 | Sq.Ft | 50 | 100 | 250.4 | 0 | 10016 | C+S GST 18% I/P RD | 1802.88 | 11818.88 | 11818.88 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 2004 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 590.89 | Sq.Ft | 60 | 100 | 886.34 | 0 | 35453.4 | C+S GST 18% I/P RD | 6381.62 | 41835.02 | 41835.02 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 551 | 91860 | 05 Oct 2021 | 91860 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 1292 | A 2004 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.99 | Sq.Ft | 60 | 100 | 227.99 | 0 | 9119.4 | C+S GST 18% I/P RD | 1641.5 | 10760.9 | 10760.9 | Approved | 0 | 0 | 1604 | 05 Oct 2021
GANGA DHAM TOWERS | 400 | 91859 | 05 Oct 2021 |  | NISAR AHMAD ANSARI | ANIL MAHTO ENTERPRISES | EV - 1305 | Bldg A Flat No. 304 Ceiling Premium Emulsion Painting | Premium Emulsion Paint (L) | 1110 | Sq.Ft | 16.2 | 50 | 224.78 | 0 | 8991 | C+S GST 18% I/P RD | 1618.38 | 10609.38 | 10609.38 | Approved | 0 | 0 | 474 | 05 Oct 2021
GANGA DHAM TOWERS | 400 | 91859 | 05 Oct 2021 |  | NISAR AHMAD ANSARI | ANIL MAHTO ENTERPRISES | EV - 1305 | Bldg A Flat No. 303 Ceiling Premium Emulsion Painting | Premium Emulsion Paint (L) | 1016.2963 | Sq.Ft | 16.2 | 50 | 205.8 | 0 | 8232 | C+S GST 18% I/P RD | 1481.76 | 9713.76 | 9713.76 | Approved | 0 | 0 | 474 | 05 Oct 2021
GANGA DHAM TOWERS | 400 | 91859 | 05 Oct 2021 |  | NISAR AHMAD ANSARI | ANIL MAHTO ENTERPRISES | EV - 1305 | Bldg A Flat No. 303 Walls Satin Matt Painting | Satin Mat Paint | 399.9111 | Sq.Ft | 22.5 | 50 | 112.47 | 0 | 4499 | C+S GST 18% I/P RD | 809.82 | 5308.82 | 5308.82 | Approved | 0 | 0 | 474 | 05 Oct 2021
GANGA DHAM TOWERS | 400 | 91859 | 05 Oct 2021 |  | NISAR AHMAD ANSARI | ANIL MAHTO ENTERPRISES | EV - 1305 | Bldg A Flat No. 304 Walls Satin Matt Painting | Satin Mat Paint | 2278.1333 | Sq.Ft | 22.5 | 50 | 640.72 | 0 | 25629 | C+S GST 18% I/P RD | 4613.22 | 30242.22 | 30242.22 | Approved | 0 | 0 | 474 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10 | Sq.Ft | 142.5 | 100 | 0 | 0 | 1425 | CGST 0% URD I/P | 0 | 1425 | 1425 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | CGST 0% URD I/P | 0 | 2138 | 2138 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 12 | Sq.Ft | 142.5 | 100 | 0 | 0 | 1710 | CGST 0% URD I/P | 0 | 1710 | 1710 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10 | Sq.Ft | 142.5 | 100 | 0 | 0 | 1425 | CGST 0% URD I/P | 0 | 1425 | 1425 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 9th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14 | Sq.Ft | 123.5 | 100 | 0 | 0 | 1729 | CGST 0% URD I/P | 0 | 1729 | 1729 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14.2632 | Sq.Ft | 152 | 100 | 0 | 0 | 2168 | CGST 0% URD I/P | 0 | 2168 | 2168 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15 | Sq.Ft | 152 | 100 | 0 | 0 | 2280 | CGST 0% URD I/P | 0 | 2280 | 2280 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 12 | Sq.Ft | 133 | 100 | 0 | 0 | 1596 | CGST 0% URD I/P | 0 | 1596 | 1596 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15 | Sq.Ft | 133 | 100 | 0 | 0 | 1995 | CGST 0% URD I/P | 0 | 1995 | 1995 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 10 | Sq.Ft | 133 | 100 | 0 | 0 | 1330 | CGST 0% URD I/P | 0 | 1330 | 1330 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 272 | 91858 | 05 Oct 2021 |  | GOURI INFRA | PRAKASH CONTRACTOR | EV - 1381 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 13 | Sq.Ft | 133 | 100 | 0 | 0 | 1729 | CGST 0% URD I/P | 0 | 1729 | 1729 | Approved | 0 | 0 | 195 | 05 Oct 2021
GANGA DHAM TOWERS | 145 | 91857 | 05 Oct 2021 | 250 | PEST-O-CRUSH | S.R.Enterprises | EV - 1224 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 05 Oct 2021
GANGA DHAM TOWERS | 395 | 91856 | 05 Oct 2021 | 375 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1163 | A Bldg Flat No. 2003 Gypsum Plaster | Gypsum on Wall (L) | 2198.37 | Sq.Ft | 4 | 100 | 219.84 | 0 | 8793.48 | C+S GST 18% I/P RD | 1582.82 | 10376.3 | 10376.3 | Approved | 0 | 0 | 462 | 05 Oct 2021
GANGA DHAM TOWERS | 395 | 91856 | 05 Oct 2021 | 375 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1163 | A Bldg Flat No. 1903 Gypsum Plaster | Gypsum on Wall (L) | 2198.37 | Sq.Ft | 4 | 100 | 219.84 | 0 | 8793.48 | C+S GST 18% I/P RD | 1582.82 | 10376.3 | 10376.3 | Approved | 0 | 0 | 462 | 05 Oct 2021
GANGA DHAM TOWERS | 395 | 91856 | 05 Oct 2021 | 375 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1163 | A Bldg Flat No. 1904 Gypsum Plaster | Gypsum on Wall (L) | 2474.34 | Sq.Ft | 4 | 100 | 247.43 | 0 | 9897.36 | C+S GST 18% I/P RD | 1781.52 | 11678.88 | 11678.88 | Approved | 0 | 0 | 462 | 05 Oct 2021
GANGA DHAM TOWERS | 395 | 91856 | 05 Oct 2021 | 375 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1163 | A Bldg Flat No. 2004 Gypsum Plaster | Gypsum on Wall (L) | 2474.34 | Sq.Ft | 4 | 100 | 247.43 | 0 | 9897.36 | C+S GST 18% I/P RD | 1781.52 | 11678.88 | 11678.88 | Approved | 0 | 0 | 462 | 05 Oct 2021
GANGA DHAM TOWERS | 395 | 91856 | 05 Oct 2021 | 375 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1163 | A Bldg Flat No. 2203 Gypsum Plaster | Gypsum on Wall (L) | 2198.37 | Sq.Ft | 4 | 100 | 219.84 | 0 | 8793.48 | C+S GST 18% I/P RD | 1582.82 | 10376.3 | 10376.3 | Approved | 0 | 0 | 462 | 05 Oct 2021
GANGA DHAM TOWERS | 393 | 91855 | 05 Oct 2021 | 77 | J K INTERIOR | J K INTERIOR | EV - 1105 | A Bldg Flat No. 2302 Gypsum Plaster | Gypsum on Wall (L) | 2410.471 | Sq.Ft | 4 | 100 | 241.05 | 0 | 9641.88 | C+S GST 18% I/P RD | 1735.54 | 11377.42 | 11377.42 | Approved | 0 | 0 | 291 | 05 Oct 2021
GANGA DHAM TOWERS | 393 | 91855 | 05 Oct 2021 | 77 | J K INTERIOR | J K INTERIOR | EV - 1105 | A Bldg Flat No. 2401 Gypsum Plaster | Gypsum on Wall (L) | 2466.135 | Sq.Ft | 4 | 100 | 246.61 | 0 | 9864.54 | C+S GST 18% I/P RD | 1775.62 | 11640.16 | 11640.16 | Approved | 0 | 0 | 291 | 05 Oct 2021
GANGA DHAM TOWERS | 393 | 91855 | 05 Oct 2021 | 77 | J K INTERIOR | J K INTERIOR | EV - 1105 | A Bldg Flat No. 2402 Gypsum Plaster | Gypsum on Wall (L) | 2410.471 | Sq.Ft | 4 | 100 | 241.05 | 0 | 9641.88 | C+S GST 18% I/P RD | 1735.54 | 11377.42 | 11377.42 | Approved | 0 | 0 | 291 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 21st Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 15th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 19th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 22nd Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 20th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 24th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 18th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 23rd Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 708 | 91854 | 05 Oct 2021 | 75 | J K INTERIOR | J K INTERIOR | EV - 1110 | A 16th Floor Staircase I Wall Gypsum Plaster | Gypsum on Wall (L) | 500.94 | Sq.Ft | 4 | 100 | 50.09 | 0 | 2003.76 | C+S GST 18% I/P RD | 360.68 | 2364.44 | 2364.44 | Approved | 0 | 0 | 180 | 05 Oct 2021
GANGA DHAM TOWERS | 413 | 91853 | 05 Oct 2021 | 634 | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1240 | Sales Oiifce Landscape Area . | Supervision Charges | 0.75 | Month | 4000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 300 | 05 Oct 2021
GANGA DHAM TOWERS | 178 | 91852 | 05 Oct 2021 | 633 | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1234 | Sales Oiifce Landscape Area . | Garden work. | 47.988 | Day | 420.83 | 100 | 0 | 0 | 20194.79 | C+S GST 18% I/P RD | 3635.06 | 23829.85 | 23829.85 | Approved | 0 | 0 | 202 | 05 Oct 2021
GANGA DHAM TOWERS | 745 | 91851 | 05 Oct 2021 | 78 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1276 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 29.019 | Day | 466.66 | 100 | 0 | 0 | 13542.01 | C+S GST 18% I/P RD | 2437.56 | 15979.57 | 15979.57 | Approved | 0 | 0 | 135 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 15th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 2nd Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 13th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 16th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 17th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 11th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 14th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 10th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 12th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (M) | 31.992 | R.Ft | 25 | 100 | 0 | 0 | 799.8 | C+S GST 18% I/P RD | 143.96 | 943.76 | 943.76 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 16th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 10th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 2nd Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 11th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 13th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 15th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 14th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 17th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 658 | 91850 | 05 Oct 2021 | 76 | A K INTERIOR CONTRACTOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1103 | A 12th Floor Lobby False Ceiling | Gypsum Board False Ceiling (M) | 421.182 | Sq.Ft | 50 | 100 | 0 | 0 | 21059.1 | C+S GST 18% I/P RD | 3790.64 | 24849.74 | 24849.74 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 480 | 91849 | 05 Oct 2021 | 77 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1277 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 24.516 | Day | 466.66 | 100 | 0 | 0 | 11440.64 | C+S GST 18% I/P RD | 2059.32 | 13499.96 | 13499.96 | Approved | 0 | 0 | 114 | 05 Oct 2021
GANGA DHAM TOWERS | 187 | 91848 | 05 Oct 2021 | 79 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1225 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 05 Oct 2021
GANGA DHAM TOWERS | 186 | 91847 | 05 Oct 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1251 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 140.094 | Day | 466.66 | 100 | 0 | 0 | 65376.27 | C+S GST 18% I/P RD | 11767.72 | 77143.99 | 77143.99 | Approved | 0 | 0 | 813 | 05 Oct 2021
GANGA DHAM TOWERS | 186 | 91847 | 05 Oct 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1251 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 26.499 | Day | 600 | 100 | 0 | 0 | 15899.4 | C+S GST 18% I/P RD | 2861.9 | 18761.3 | 18761.3 | Approved | 0 | 0 | 813 | 05 Oct 2021
GANGA DHAM TOWERS | 744 | 91846 | 05 Oct 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 1301 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 6 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 22nd Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 20th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 18th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0611 | R.Ft | 180 | 100 | 459.27 | 0 | 18371 | C+S GST 18% I/P RD | 3306.78 | 21677.78 | 21677.78 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 21st Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 23rd Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 19th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 24th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 24th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 22nd Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 24th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 19th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 20th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 21st Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 23rd Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 23rd Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 19th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.2979 | R.Ft | 94 | 100 | 52.4 | 0 | 2096 | C+S GST 18% I/P RD | 377.28 | 2473.28 | 2473.28 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 21st Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 20th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 24th Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 21st Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 20th Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 23rd Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 19th Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 22nd Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 22nd Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 23rd Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B-12th Floor Lobby Flooring & cladding work - 1 Job | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B-17th Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B-14th Floor Lobby Flooring & cladding work - 1 Job | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B-15th Floor Lobby Flooring & cladding work - 1 Job | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B-13th Floor Lobby Flooring & cladding work - 1 Job | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 18th Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 20th Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 24th Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B-16th Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 19th Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B-11th Floor Lobby Flooring & cladding work - 1 Job | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 21st Floor Lobby Flooring & cladding work | Granite Counter Support | 65.977 | R.Ft | 70 | 100 | 115.46 | 0 | 4618.39 | C+S GST 18% I/P RD | 831.32 | 5449.71 | 5449.71 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 22nd Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.4255 | R.Ft | 94 | 100 | 266.55 | 0 | 10662 | C+S GST 18% I/P RD | 1919.16 | 12581.16 | 12581.16 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 24th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.4255 | R.Ft | 94 | 100 | 266.55 | 0 | 10662 | C+S GST 18% I/P RD | 1919.16 | 12581.16 | 12581.16 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 20th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.4255 | R.Ft | 94 | 100 | 266.55 | 0 | 10662 | C+S GST 18% I/P RD | 1919.16 | 12581.16 | 12581.16 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 23rd Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.4255 | R.Ft | 94 | 100 | 266.55 | 0 | 10662 | C+S GST 18% I/P RD | 1919.16 | 12581.16 | 12581.16 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 19th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.4255 | R.Ft | 94 | 100 | 266.55 | 0 | 10662 | C+S GST 18% I/P RD | 1919.16 | 12581.16 | 12581.16 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 21st Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.4255 | R.Ft | 94 | 100 | 266.55 | 0 | 10662 | C+S GST 18% I/P RD | 1919.16 | 12581.16 | 12581.16 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 23rd Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 89.77 | Sq.Ft | 200 | 100 | 448.85 | 0 | 17954 | C+S GST 18% I/P RD | 3231.72 | 21185.72 | 21185.72 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 20th Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 89.77 | Sq.Ft | 200 | 100 | 448.85 | 0 | 17954 | C+S GST 18% I/P RD | 3231.72 | 21185.72 | 21185.72 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 22nd Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 89.77 | Sq.Ft | 200 | 100 | 448.85 | 0 | 17954 | C+S GST 18% I/P RD | 3231.72 | 21185.72 | 21185.72 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 19th Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 89.77 | Sq.Ft | 200 | 100 | 448.85 | 0 | 17954 | C+S GST 18% I/P RD | 3231.72 | 21185.72 | 21185.72 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 24th Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 80.793 | Sq.Ft | 200 | 100 | 403.97 | 0 | 16158.6 | C+S GST 18% I/P RD | 2908.54 | 19067.14 | 19067.14 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 21st Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 89.77 | Sq.Ft | 200 | 100 | 448.85 | 0 | 17954 | C+S GST 18% I/P RD | 3231.72 | 21185.72 | 21185.72 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 22nd Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 741 | 91845 | 05 Oct 2021 | 91845 | R K INTERIOR | R K INTERIOR | EV - 1159 | B 25th Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 10796 | 05 Oct 2021
GANGA DHAM TOWERS | 497 | 91844 | 05 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1109 | B 2302 Gypsum Plaster | Gypsum on Wall (L) | 3581 | Sq.Ft | 4 | 100 | 358.1 | 0 | 14324 | C+S GST 18% I/P RD | 2578.32 | 16902.32 | 16902.32 | Approved | 0 | 0 | 193 | 05 Oct 2021
GANGA DHAM TOWERS | 497 | 91844 | 05 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1109 | B 2302 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 193 | 05 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | Data Point | 7 | No. | 220 | 5 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | Data Point | 4 | No. | 220 | 5 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1002 Internal Electrical Work | Data Point | 4 | No. | 220 | 5 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | Data Point | 7 | No. | 220 | 5 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | Data Point | 4 | No. | 220 | 5 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1001 Internal Electrical Work | Data Point | 7 | No. | 220 | 5 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | Data Point | 4 | No. | 220 | 5 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | Data Point | 7 | No. | 220 | 5 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 5 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 5 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 5 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 5 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 5 | 1.09 | 0 | 43.55 | C+S GST 18% I/P RD | 7.84 | 51.39 | 51.39 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 5 | 1.26 | 0 | 50.25 | C+S GST 18% I/P RD | 9.04 | 59.29 | 59.29 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 5 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 5 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 5 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 5 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 5 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1002 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 5 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1001 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 5 | 0.55 | 0 | 22 | C+S GST 18% I/P RD | 3.96 | 25.96 | 25.96 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 5 | 0.83 | 0 | 33 | C+S GST 18% I/P RD | 5.94 | 38.94 | 38.94 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 5 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 5 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 5 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 5 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 5 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 5 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 5 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1001 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 5 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 5 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1002 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 5 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 5 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 5 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 5 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 5 | 0.25 | 0 | 10 | C+S GST 18% I/P RD | 1.8 | 11.8 | 11.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 5 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 5 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 5 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 5 | 13.25 | 0 | 530 | C+S GST 18% I/P RD | 95.4 | 625.4 | 625.4 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 5 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 5 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 5 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 5 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1002 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 5 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 5 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 5 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 5 | 3.6 | 0 | 144.05 | C+S GST 18% I/P RD | 25.92 | 169.97 | 169.97 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 5 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1001 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 5 | 4.61 | 0 | 184.25 | C+S GST 18% I/P RD | 33.16 | 217.41 | 217.41 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 5 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 5 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 5 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1001 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 5 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 5 | 19.75 | 0 | 790 | C+S GST 18% I/P RD | 142.2 | 932.2 | 932.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 5 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1002 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 5 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 5 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1400 | 5 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1400 | 5 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1400 | 5 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 5 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 5 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 5 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 5 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 5 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 5 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1002 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 5 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1001 Internal Electrical Work | TV/Tel DB Fixing | 1 | No. | 500 | 5 | 0.63 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 5 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 5 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 5 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 5 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1001 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 5 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 5 | 1.25 | 0 | 50 | C+S GST 18% I/P RD | 9 | 59 | 59 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 5 | 2 | 0 | 80 | C+S GST 18% I/P RD | 14.4 | 94.4 | 94.4 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1001 Internal Electrical Work | Fan Point | 11 | No. | 200 | 5 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | Fan Point | 9 | No. | 200 | 5 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | Fan Point | 11 | No. | 200 | 5 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | Fan Point | 11 | No. | 200 | 5 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | Fan Point | 11 | No. | 200 | 5 | 2.75 | 0 | 110 | C+S GST 18% I/P RD | 19.8 | 129.8 | 129.8 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | Fan Point | 9 | No. | 200 | 5 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | Fan Point | 9 | No. | 200 | 5 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1002 Internal Electrical Work | Fan Point | 9 | No. | 200 | 5 | 2.25 | 0 | 90 | C+S GST 18% I/P RD | 16.2 | 106.2 | 106.2 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1300 | 5 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1300 | 5 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1300 | 5 | 1.63 | 0 | 65 | C+S GST 18% I/P RD | 11.7 | 76.7 | 76.7 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | TV Point | 8 | No. | 220 | 5 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | TV Point | 8 | No. | 220 | 5 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | TV Point | 6 | No. | 220 | 5 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | TV Point | 8 | No. | 220 | 5 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | TV Point | 6 | No. | 220 | 5 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | TV Point | 6 | No. | 220 | 5 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1102 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 5 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1201 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 5 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 901 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 5 | 2.48 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 902 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 5 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1101 Internal Electrical Work | AC Point BC | 5 | No. | 220 | 5 | 1.38 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91832 | 04 Oct 2021 | 22 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1107 | B Bldg Flat No. 1202 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 5 | 1.65 | 0 | 66 | C+S GST 18% I/P RD | 11.88 | 77.88 | 77.88 | Approved | 0 | 0 | 296 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2202 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2201 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1902 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 102 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 602 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2101 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1601 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 1602 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 399 | 91831 | 04 Oct 2021 | 23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1106 | B Bldg Flat No. 2102 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 973 | 04 Oct 2021
GANGA DHAM TOWERS | 932 | 91815 | 04 Oct 2021 | 240 | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 1098 | Pumping Charges Groung Floor Pumping Charges | Pumping Charges-BC | 301.3579 | Cu.Mtrs | 190 | 100 | 0 | 0 | 57258 | C+S GST 18% I/P RD | 10306.44 | 67564.44 | 67564.44 | Approved | 0 | 0 | 2046 | 04 Oct 2021
GANGA DHAM TOWERS | 932 | 91815 | 04 Oct 2021 | 240 | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 1098 | Pumping Charges P3 Floor Pumping Charges | Pumping Charges-BC | 237.1211 | Cu.Mtrs | 190 | 100 | 0 | 0 | 45053 | C+S GST 18% I/P RD | 8109.54 | 53162.54 | 53162.54 | Approved | 0 | 0 | 2046 | 04 Oct 2021
GANGA DHAM TOWERS | 1080 | 91814 | 04 Oct 2021 | 239 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1099 | B P1 Floor Trimix Pumping Charges | Pumping Charges-BC | 220.6 | Cu.Mtrs | 190 | 100 | 0 | 0 | 41914 | C+S GST 18% I/P RD | 7544.52 | 49458.52 | 49458.52 | Approved | 0 | 0 | 838 | 04 Oct 2021
GANGA DHAM TOWERS | 1079 | 91813 | 04 Oct 2021 | 238 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1100 | A GF Trimix Pumping Charges | Pumping Charges-BC | 217.81 | Cu.Mtrs | 190 | 100 | 0 | 0 | 41383.9 | C+S GST 18% I/P RD | 7449.1 | 48833 | 48833 | Approved | 0 | 0 | 1675 | 04 Oct 2021
GANGA DHAM TOWERS | 1079 | 91813 | 04 Oct 2021 | 238 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 1100 | A P1 Trimix Pumping Charges | Pumping Charges-BC | 223.11 | Cu.Mtrs | 190 | 100 | 0 | 0 | 42390.9 | C+S GST 18% I/P RD | 7630.36 | 50021.26 | 50021.26 | Approved | 0 | 0 | 1675 | 04 Oct 2021
GANGA DHAM TOWERS | 1133 | 91798 | 02 Oct 2021 |  | BASSAPPA CHAVAN | BASSAPPA CHAVAN | EV - 1408 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Tractor Trip - Dld | 40 | No. | 800 | 100 | 0 | 0 | 32000 | CGST 0% URD I/P | 0 | 32000 | 32000 | Approved | 0 | 0 | 320 | 02 Oct 2021
GANGA DHAM TOWERS | 724 | 91791 | 02 Oct 2021 | 109 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 1160 | A Parking Floor 3 Trimix work | Weld mesh fixing(L) BCo | 19200 | Sq.Ft | 1 | 100 | 480 | 0 | 19200 | C+S GST 18% I/P RD | 3456 | 22656 | 22656 | Approved | 0 | 0 | 2320 | 02 Oct 2021
GANGA DHAM TOWERS | 724 | 91791 | 02 Oct 2021 | 109 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 1160 | A Parking Floor 2 Trimix work | Weld mesh fixing(L) BCo | 4000 | Sq.Ft | 1 | 100 | 100 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 2320 | 02 Oct 2021
GANGA DHAM TOWERS | 724 | 91791 | 02 Oct 2021 | 109 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 1160 | A Parking Floor 2 Trimix work | Trimix Work - BC | 4000 | Sq.Ft | 9 | 100 | 900 | 0 | 36000 | C+S GST 18% I/P RD | 6480 | 42480 | 42480 | Approved | 0 | 0 | 2320 | 02 Oct 2021
GANGA DHAM TOWERS | 724 | 91791 | 02 Oct 2021 | 109 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 1160 | A Parking Floor 3 Trimix work | Trimix Work - BC | 19200 | Sq.Ft | 9 | 100 | 4320 | 0 | 172800 | C+S GST 18% I/P RD | 31104 | 203904 | 203904 | Approved | 0 | 0 | 2320 | 02 Oct 2021
GANGA DHAM TOWERS | 774 | 91790 | 02 Oct 2021 | 110 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 1161 | B Parking Floor 3 Trimix work | Trimix Work - BC | 3700 | Sq.Ft | 9 | 100 | 832.5 | 0 | 33300 | C+S GST 18% I/P RD | 5994 | 39294 | 39294 | Approved | 0 | 0 | 740 | 02 Oct 2021
GANGA DHAM TOWERS | 774 | 91790 | 02 Oct 2021 | 110 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 1161 | B Parking Floor 3 Trimix work | Weld mesh fixing(L) BCo | 3700 | Sq.Ft | 1 | 100 | 92.5 | 0 | 3700 | C+S GST 18% I/P RD | 666 | 4366 | 4366 | Approved | 0 | 0 | 740 | 02 Oct 2021
GANGA DHAM TOWERS | 940 | 91789 | 02 Oct 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 1056 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 02 Oct 2021
GANGA DHAM TOWERS | 1158 | 91788 | 02 Oct 2021 | 16 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1034 | C-Core Cutting Work | Rebarring work 16mm dia- BC | 240 | No. | 350 | 100 | 2100 | 0 | 84000 | C+S GST 18% I/P RD | 15120 | 99120 | 99120 | Approved | 0 | 0 | 2400 | 02 Oct 2021
GANGA DHAM TOWERS | 1158 | 91788 | 02 Oct 2021 | 16 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1034 | C-Core Cutting Work | Rebarring work 12mm dia- BC | 300 | No. | 120 | 100 | 900 | 0 | 36000 | C+S GST 18% I/P RD | 6480 | 42480 | 42480 | Approved | 0 | 0 | 2400 | 02 Oct 2021
GANGA DHAM TOWERS | 1110 | 91787 | 02 Oct 2021 | 198/21-22 | A N INTERIORS | A N INTERIORS | EV - 1057 | B1 -1101 Carpentary Work | Carpentary work lumpsum- Dld | 0.8532 | No. | 340590 | 100 | 0 | 0 | 290591.39 | C+S GST 18% I/P RD | 52306.46 | 342897.85 | 342897.85 | Approved | 0 | 0 | 2906 | 02 Oct 2021
GANGA DHAM TOWERS | 1002 | 91786 | 02 Oct 2021 | 224 | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 1031 | B 1201 NOC | Concrete Cutting Work | 1.0305 | R.Ft | 525 | 100 | 13.53 | 0 | 541 | C+S GST 18% I/P RD | 97.38 | 638.38 | 638.38 | Approved | 0 | 0 | 133 | 02 Oct 2021
GANGA DHAM TOWERS | 1002 | 91786 | 02 Oct 2021 | 224 | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 1031 | B 1201 NOC | Blockwork 4" - BC | 376.64 | Sq.Ft | 18 | 100 | 169.49 | 0 | 6779.52 | C+S GST 18% I/P RD | 1220.32 | 7999.84 | 7999.84 | Approved | 0 | 0 | 133 | 02 Oct 2021
GANGA DHAM TOWERS | 1002 | 91786 | 02 Oct 2021 | 224 | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 1031 | B 601 NOC | Blockwork 4" - BC | 332.16 | Sq.Ft | 18 | 100 | 149.47 | 0 | 5978.88 | C+S GST 18% I/P RD | 1076.2 | 7055.08 | 7055.08 | Approved | 0 | 0 | 133 | 02 Oct 2021
GANGA DHAM TOWERS | 807 | 91785 | 02 Oct 2021 | 65 | J K INTERIOR | J K INTERIOR | EV - 1051 | B 402 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 334.35 | R.Ft | 20 | 100 | 167.18 | 0 | 6687 | C+S GST 18% I/P RD | 1203.66 | 7890.66 | 7890.66 | Approved | 0 | 0 | 67 | 02 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 1701 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 1001 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 1702 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 201 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 202 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 1402 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 602 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 1302 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 1002 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 313.992 | R.Ft | 20 | 100 | 157 | 0 | 6279.84 | C+S GST 18% I/P RD | 1130.38 | 7410.22 | 7410.22 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 1501 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 401 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 631 | 91752 | 01 Oct 2021 |  | J K INTERIOR | J K INTERIOR | EV - 1368 | A 601 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 336.672 | R.Ft | 20 | 100 | 168.34 | 0 | 6733.44 | C+S GST 18% I/P RD | 1212.02 | 7945.46 | 7945.46 | Approved | 0 | 0 | 781 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 201 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 401 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 1302 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 1702 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 1001 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 601 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 602 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 1002 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 1501 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 1402 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 202 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 313.992 | R.Ft | 55 | 100 | 0 | 0 | 17269.56 | C+S GST 18% I/P RD | 3108.52 | 20378.08 | 20378.08 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 1701 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 336.672 | R.Ft | 55 | 100 | 0 | 0 | 18516.96 | C+S GST 18% I/P RD | 3333.06 | 21850.02 | 21850.02 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 630 | 91751 | 01 Oct 2021 | 68 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1047 | A 1501 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 203 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 1003 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 504 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 1704 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 303 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 1703 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 803 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 603 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 1204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 203 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 403 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 1403 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 903 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 404 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 312.102 | R.Ft | 20 | 100 | 156.05 | 0 | 6242.04 | C+S GST 18% I/P RD | 1123.56 | 7365.6 | 7365.6 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 632 | 91750 | 01 Oct 2021 | 371 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 987 | A 503 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 279.6 | R.Ft | 20 | 100 | 139.8 | 0 | 5592 | C+S GST 18% I/P RD | 1006.56 | 6598.56 | 6598.56 | Approved | 0 | 0 | 1012 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 203 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 1403 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 1204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 403 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 404 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 1003 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 903 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 803 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 303 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 1703 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 204 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 603 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 503 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 279.6 | R.Ft | 55 | 100 | 0 | 0 | 15378 | C+S GST 18% I/P RD | 2768.04 | 18146.04 | 18146.04 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 1704 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 629 | 91749 | 01 Oct 2021 | 370 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1023 | A 504 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 312.102 | R.Ft | 55 | 100 | 0 | 0 | 17165.61 | C+S GST 18% I/P RD | 3089.8 | 20255.41 | 20255.41 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 15th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 10th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 11th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 17th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 12th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 13th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 14th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 2nd Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 16th Floor Lobby False Ceiling | Gypsum False Ceiling Patta (L) | 31.992 | R.Ft | 7.5 | 100 | 6 | 0 | 239.94 | C+S GST 18% I/P RD | 43.18 | 283.12 | 283.12 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 17th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 10th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 2nd Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 11th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 13th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 14th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 15th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 12th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 659 | 91747 | 01 Oct 2021 | 73 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1108 | A 16th Floor Lobby False Ceiling | Gypsum Board False Ceiling (L) | 421.182 | Sq.Ft | 15 | 100 | 157.94 | 0 | 6317.73 | C+S GST 18% I/P RD | 1137.2 | 7454.93 | 7454.93 | Approved | 0 | 0 | 590 | 01 Oct 2021
GANGA DHAM TOWERS | 806 | 91746 | 01 Oct 2021 | 67 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1050 | B 402 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 334.35 | R.Ft | 55 | 100 | 0 | 0 | 18389.25 | C+S GST 18% I/P RD | 3310.06 | 21699.31 | 21699.31 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 804 | 91745 | 01 Oct 2021 | 369 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1027 | B 701 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 804 | 91745 | 01 Oct 2021 | 369 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1027 | B 301 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 804 | 91745 | 01 Oct 2021 | 369 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1027 | B 801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 567.21 | R.Ft | 55 | 100 | 0 | 0 | 31196.55 | C+S GST 18% I/P RD | 5615.38 | 36811.93 | 36811.93 | Approved | 0 | 0 | 0 | 01 Oct 2021
GANGA DHAM TOWERS | 805 | 91744 | 01 Oct 2021 | 368 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1054 | B 801 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 340 | 01 Oct 2021
GANGA DHAM TOWERS | 805 | 91744 | 01 Oct 2021 | 368 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1054 | B 701 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 340 | 01 Oct 2021
GANGA DHAM TOWERS | 805 | 91744 | 01 Oct 2021 | 368 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1054 | B 301 Internal Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 567.21 | R.Ft | 20 | 100 | 283.61 | 0 | 11344.2 | C+S GST 18% I/P RD | 2041.96 | 13386.16 | 13386.16 | Approved | 0 | 0 | 340 | 01 Oct 2021
GANGA DHAM TOWERS | 987 | 91741 | 30 Sep 2021 | 124 | HI TEK INDUSTRIES | HI TEK INDUSTRIES | EV - 1041 | DA Development Carpentary work | Folding Door (M+L) | 2 | No. | 15000 | 100 | 750 | 0 | 30000 | C+S GST 18% I/P RD | 5400 | 35400 | 35400 | Approved | 0 | 0 | 300 | 30 Sep 2021
GANGA DHAM TOWERS | 1119 | 91738 | 30 Sep 2021 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1748 | C SW32, SW33, P66 Footing Jacketing Work - | Shuttering Work-Dev | 66.45 | Sq.m. | 450 | 100 | 747.56 | 0 | 29902.5 | C+S GST 18% I/P RD | 5382.46 | 35284.96 | 35284.96 | Approved | 0 | 0 | 468 | 30 Sep 2021
GANGA DHAM TOWERS | 1119 | 91738 | 30 Sep 2021 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1748 | C SW32, SW33, P66 Footing Jacketing Work - | Reinforcement Work-Dev | 1234 | Kgs | 7 | 100 | 215.95 | 0 | 8638 | C+S GST 18% I/P RD | 1554.84 | 10192.84 | 10192.84 | Approved | 0 | 0 | 468 | 30 Sep 2021
GANGA DHAM TOWERS | 1119 | 91738 | 30 Sep 2021 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1748 | C SW32, SW33, P66 Footing Jacketing Work - | Concrete Work - BCP | 33.19 | Cu.Mtrs | 250 | 100 | 207.44 | 0 | 8297.5 | C+S GST 18% I/P RD | 1493.56 | 9791.06 | 9791.06 | Approved | 0 | 0 | 468 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 502 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2699 | Per Flat | 3060 | 100 | 20.65 | 0 | 826 | CGST 0% URD I/P | 0 | 826 | 826 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 402 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2699 | Per Flat | 3060 | 100 | 20.65 | 0 | 826 | CGST 0% URD I/P | 0 | 826 | 826 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 503 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2699 | Per Flat | 3060 | 100 | 20.65 | 0 | 826 | CGST 0% URD I/P | 0 | 826 | 826 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 302 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.5 | Per Flat | 3060 | 100 | 38.25 | 0 | 1530 | CGST 0% URD I/P | 0 | 1530 | 1530 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 403 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2699 | Per Flat | 3060 | 100 | 20.65 | 0 | 826 | CGST 0% URD I/P | 0 | 826 | 826 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 203 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.7699 | Per Flat | 3060 | 100 | 58.9 | 0 | 2356 | CGST 0% URD I/P | 0 | 2356 | 2356 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 204 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.3301 | Per Flat | 3060 | 100 | 25.25 | 0 | 1010 | CGST 0% URD I/P | 0 | 1010 | 1010 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 404 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2699 | Per Flat | 3060 | 100 | 20.65 | 0 | 826 | CGST 0% URD I/P | 0 | 826 | 826 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 304 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2699 | Per Flat | 3060 | 100 | 20.65 | 0 | 826 | CGST 0% URD I/P | 0 | 826 | 826 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 793 | 91736 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1039 | D 303 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.5 | Per Flat | 3060 | 100 | 38.25 | 0 | 1530 | CGST 0% URD I/P | 0 | 1530 | 1530 | Approved | 0 | 0 | 114 | 30 Sep 2021
GANGA DHAM TOWERS | 813 | 91735 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1040 | D 4th Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 5 | 30 Sep 2021
GANGA DHAM TOWERS | 813 | 91735 | 30 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1040 | D 3rd Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | CGST 0% URD I/P | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 5 | 30 Sep 2021
GANGA DHAM TOWERS | 410 | 91708 | 29 Sep 2021 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1888 | Load Testing for Material Lift (10th, 15th, 20th & 25th Fl.) | Testing & Certification Charges | 1 | No. | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 15 | 29 Sep 2021
GANGA DHAM TOWERS | 545 | 91707 | 29 Sep 2021 |  | SAMARTH SAFETY SERVICES | SAMARTH SAFETY SERVICES | EV - 1889 | Tower B Lift Jumping (4th,9th,14th,19th &24th Floor) | Lift Jumping Work | 5 | No. | 1500 | 20 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 15 | 29 Sep 2021
GANGA DHAM TOWERS | 862 | 91705 | 29 Sep 2021 |  | J K INTERIOR | NKV HOME DEPOT |  | Club House 1st Floor Brickwork/ Plaster | Gypsum on Ceiling (L) | 942 | Sq.Ft | 4 | 100 | 94.2 | 0 | 3768 | C+S GST 18% I/P RD | 678.24 | 4446.24 | 4446.24 |  | 0 | 0 | 38 | 29 Sep 2021
GANGA DHAM TOWERS | 807 | 91701 | 28 Sep 2021 | 70 | J K INTERIOR | J K INTERIOR | EV - 1049 | B 402 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 969.48 | Sq.Ft | 20 | 100 | 484.74 | 0 | 19389.6 | C+S GST 18% I/P RD | 3490.12 | 22879.72 | 22879.72 | Approved | 0 | 0 | 194 | 28 Sep 2021
GANGA DHAM TOWERS | 522 | 91687 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1013 | B Bldg 1501 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1400 | 100 | 245 | 0 | 9800 | CGST 0% URD I/P | 0 | 9800 | 9800 | Approved | 0 | 0 | 98 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 1702 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 1701 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 201 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 601 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 1001 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 1302 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 401 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 915 | Sq.Ft | 55 | 100 | 0 | 0 | 50325 | C+S GST 18% I/P RD | 9058.5 | 59383.5 | 59383.5 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 602 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 1402 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 1002 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 630 | 91684 | 28 Sep 2021 | 64 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1010 | A 1602 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 904.8 | Sq.Ft | 55 | 100 | 0 | 0 | 49764 | C+S GST 18% I/P RD | 8957.52 | 58721.52 | 58721.52 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 1001 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 1702 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 1602 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 402 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 1501 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 601 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 1002 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 1302 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 201 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 1701 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 1402 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 401 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 915 | Sq.Ft | 20 | 100 | 457.5 | 0 | 18300 | C+S GST 18% I/P RD | 3294 | 21594 | 21594 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 631 | 91683 | 28 Sep 2021 | 63 | J K INTERIOR | J K INTERIOR | EV - 988 | A 602 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 904.8 | Sq.Ft | 20 | 100 | 452.4 | 0 | 18096 | C+S GST 18% I/P RD | 3257.28 | 21353.28 | 21353.28 | Approved | 0 | 0 | 2365 | 28 Sep 2021
GANGA DHAM TOWERS | 806 | 91682 | 28 Sep 2021 | 71 | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 1052 | B 402 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 969.48 | Sq.Ft | 55 | 100 | 0 | 0 | 53321.4 | C+S GST 18% I/P RD | 9597.86 | 62919.26 | 62919.26 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 804 | 91681 | 28 Sep 2021 | 364 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1025 | B 801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1441.2 | Sq.Ft | 55 | 100 | 0 | 0 | 79266 | C+S GST 18% I/P RD | 14267.88 | 93533.88 | 93533.88 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 804 | 91681 | 28 Sep 2021 | 364 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1025 | B 301 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1441.2 | Sq.Ft | 55 | 100 | 0 | 0 | 79266 | C+S GST 18% I/P RD | 14267.88 | 93533.88 | 93533.88 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 804 | 91681 | 28 Sep 2021 | 364 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1025 | B 701 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1441.2 | Sq.Ft | 55 | 100 | 0 | 0 | 79266 | C+S GST 18% I/P RD | 14267.88 | 93533.88 | 93533.88 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 805 | 91680 | 28 Sep 2021 | 363 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1022 | B 301 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1441.2 | Sq.Ft | 20 | 100 | 720.6 | 0 | 28824 | C+S GST 18% I/P RD | 5188.32 | 34012.32 | 34012.32 | Approved | 0 | 0 | 865 | 28 Sep 2021
GANGA DHAM TOWERS | 805 | 91680 | 28 Sep 2021 | 363 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1022 | B 801 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1441.2 | Sq.Ft | 20 | 100 | 720.6 | 0 | 28824 | C+S GST 18% I/P RD | 5188.32 | 34012.32 | 34012.32 | Approved | 0 | 0 | 865 | 28 Sep 2021
GANGA DHAM TOWERS | 805 | 91680 | 28 Sep 2021 | 363 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1022 | B 701 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 1441.2 | Sq.Ft | 20 | 100 | 720.6 | 0 | 28824 | C+S GST 18% I/P RD | 5188.32 | 34012.32 | 34012.32 | Approved | 0 | 0 | 865 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 803 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 1403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 503 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 1003 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 903 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 1704 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 1204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 1703 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 504 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 886.692 | Sq.Ft | 20 | 100 | 443.35 | 0 | 17733.84 | C+S GST 18% I/P RD | 3192.1 | 20925.94 | 20925.94 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 603 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 632 | 91679 | 28 Sep 2021 | 367 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1024 | A 403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 704.016 | Sq.Ft | 20 | 100 | 352.01 | 0 | 14080.32 | C+S GST 18% I/P RD | 2534.46 | 16614.78 | 16614.78 | Approved | 0 | 0 | 2154 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 203 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 503 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 1003 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 903 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 603 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 1704 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 303 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 1204 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 404 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 1703 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 1403 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 803 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 704.016 | Sq.Ft | 55 | 100 | 0 | 0 | 38720.88 | C+S GST 18% I/P RD | 6969.76 | 45690.64 | 45690.64 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 629 | 91678 | 28 Sep 2021 | 365 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 1021 | A 504 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 886.692 | Sq.Ft | 55 | 100 | 0 | 0 | 48768.06 | C+S GST 18% I/P RD | 8778.26 | 57546.32 | 57546.32 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 602 GI Folding Door | Galv. Folding Door - Door Frame (M) | 56.83 | Sq.Ft | 90 | 100 | 0 | 0 | 5114.7 | C+S GST 18% I/P RD | 920.64 | 6035.34 | 6035.34 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 903 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 601 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 605 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 1003 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 604 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 1002 GI Folding Door | Galv. Folding Door - Door Frame (M) | 56.83 | Sq.Ft | 90 | 100 | 0 | 0 | 5114.7 | C+S GST 18% I/P RD | 920.64 | 6035.34 | 6035.34 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 701 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 704 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 705 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 1004 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 1005 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 703 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 904 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 1001 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 603 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 902 GI Folding Door | Galv. Folding Door - Door Frame (M) | 56.83 | Sq.Ft | 90 | 100 | 0 | 0 | 5114.7 | C+S GST 18% I/P RD | 920.64 | 6035.34 | 6035.34 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 805 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 803 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 905 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 804 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 702 GI Folding Door | Galv. Folding Door - Door Frame (M) | 56.83 | Sq.Ft | 90 | 100 | 0 | 0 | 5114.7 | C+S GST 18% I/P RD | 920.64 | 6035.34 | 6035.34 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 901 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 704 | 91677 | 28 Sep 2021 | 36/saI2021-22 | SAI ENGINEERING WORKS (MATERIAL) | SAI ENGINEERING WORKS (MATERIAL) | EV - 1115 | D 801 GI Folding Door | Galv. Folding Door - Door Frame (M) | 62 | Sq.Ft | 90 | 100 | 0 | 0 | 5580 | C+S GST 18% I/P RD | 1004.4 | 6584.4 | 6584.4 | Approved | 0 | 0 | 0 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1601 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 532.6842 | Sq.Ft | 19 | 100 | 1012.1 | 0 | 10121 | CGST 0% URD I/P | 0 | 10121 | 10121 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1602 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 430.4737 | Sq.Ft | 19 | 100 | 817.9 | 0 | 8179 | CGST 0% URD I/P | 0 | 8179 | 8179 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1502 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 430.4737 | Sq.Ft | 19 | 100 | 817.9 | 0 | 8179 | CGST 0% URD I/P | 0 | 8179 | 8179 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1601 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1602 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1502 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 0.3 | No. | 150 | 100 | 4.5 | 0 | 45 | CGST 0% URD I/P | 0 | 45 | 45 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 2002 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 2102 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1902 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1502 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1601 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1602 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1502 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 25 | No. | 70 | 100 | 175 | 0 | 1750 | CGST 0% URD I/P | 0 | 1750 | 1750 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1601 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 26 | No. | 70 | 100 | 182 | 0 | 1820 | CGST 0% URD I/P | 0 | 1820 | 1820 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1602 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 25 | No. | 70 | 100 | 175 | 0 | 1750 | CGST 0% URD I/P | 0 | 1750 | 1750 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1602 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1502 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1601 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1602 Chemical & IPS Waterproofing | IPS W/P | 430.4545 | Sq.Ft | 11 | 100 | 473.5 | 0 | 4735 | CGST 0% URD I/P | 0 | 4735 | 4735 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1502 Chemical & IPS Waterproofing | IPS W/P | 430.4545 | Sq.Ft | 11 | 100 | 473.5 | 0 | 4735 | CGST 0% URD I/P | 0 | 4735 | 4735 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 498 | 91676 | 28 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1014 | B 1601 Chemical & IPS Waterproofing | IPS W/P | 532.6364 | Sq.Ft | 11 | 100 | 585.9 | 0 | 5859 | CGST 0% URD I/P | 0 | 5859 | 5859 | Approved | 0 | 0 | 686 | 28 Sep 2021
GANGA DHAM TOWERS | 797 | 91675 | 28 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1015 | D Main St.case Wall Gyp. Plaster 6th to 7th Fl. | Tikki Dhada (L) | 376.758 | Sq.Ft | 9 | 100 | 84.77 | 0 | 3390.82 | CGST 0% URD I/P | 0 | 3390.82 | 3390.82 | Approved | 0 | 0 | 265 | 28 Sep 2021
GANGA DHAM TOWERS | 797 | 91675 | 28 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1015 | D Fire St.case Wall Gyp. Plaster 7th to 8th Fl. | Tikki Dhada (L) | 364.383 | Sq.Ft | 9 | 100 | 81.99 | 0 | 3279.45 | CGST 0% URD I/P | 0 | 3279.45 | 3279.45 | Approved | 0 | 0 | 265 | 28 Sep 2021
GANGA DHAM TOWERS | 797 | 91675 | 28 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1015 | D Fire St.case Wall Gyp. Plaster 6th to 7th Fl. | Tikki Dhada (L) | 344.1395 | Sq.Ft | 9 | 100 | 77.43 | 0 | 3097.26 | CGST 0% URD I/P | 0 | 3097.26 | 3097.26 | Approved | 0 | 0 | 265 | 28 Sep 2021
GANGA DHAM TOWERS | 797 | 91675 | 28 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1015 | D Fire St.case Wall Gyp. Plaster 8th to 9th Fl. | Tikki Dhada (L) | 364.383 | Sq.Ft | 9 | 100 | 81.99 | 0 | 3279.45 | CGST 0% URD I/P | 0 | 3279.45 | 3279.45 | Approved | 0 | 0 | 265 | 28 Sep 2021
GANGA DHAM TOWERS | 797 | 91675 | 28 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1015 | D Main St.case Wall Gyp. Plaster 7th to 8th Fl. | Tikki Dhada (L) | 376.758 | Sq.Ft | 9 | 100 | 84.77 | 0 | 3390.82 | CGST 0% URD I/P | 0 | 3390.82 | 3390.82 | Approved | 0 | 0 | 265 | 28 Sep 2021
GANGA DHAM TOWERS | 797 | 91675 | 28 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1015 | D Main St.case Wall Gyp. Plaster 5th to 6th Fl. | Tikki Dhada (L) | 376.758 | Sq.Ft | 9 | 100 | 84.77 | 0 | 3390.82 | CGST 0% URD I/P | 0 | 3390.82 | 3390.82 | Approved | 0 | 0 | 265 | 28 Sep 2021
GANGA DHAM TOWERS | 797 | 91675 | 28 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1015 | D Main St.case Wall Gyp. Plaster 8th to 9th Fl. | Tikki Dhada (L) | 376.758 | Sq.Ft | 9 | 100 | 84.77 | 0 | 3390.82 | CGST 0% URD I/P | 0 | 3390.82 | 3390.82 | Approved | 0 | 0 | 265 | 28 Sep 2021
GANGA DHAM TOWERS | 797 | 91675 | 28 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 1015 | D Fire St.case Wall Gyp. Plaster 5th to 6th Fl. | Tikki Dhada (L) | 364.383 | Sq.Ft | 9 | 100 | 81.99 | 0 | 3279.45 | CGST 0% URD I/P | 0 | 3279.45 | 3279.45 | Approved | 0 | 0 | 265 | 28 Sep 2021
GANGA DHAM TOWERS | 551 | 91674 | 28 Sep 2021 | 03/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1122 | A 1804 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 55 | 100 | 184.04 | 0 | 7361.75 | C+S GST 18% I/P RD | 1325.12 | 8686.87 | 8686.87 | Approved | 0 | 0 | 669 | 28 Sep 2021
GANGA DHAM TOWERS | 551 | 91674 | 28 Sep 2021 | 03/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1122 | A 1804 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.99 | Sq.Ft | 55 | 100 | 208.99 | 0 | 8359.45 | C+S GST 18% I/P RD | 1504.7 | 9864.15 | 9864.15 | Approved | 0 | 0 | 669 | 28 Sep 2021
GANGA DHAM TOWERS | 551 | 91674 | 28 Sep 2021 | 03/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1122 | A 1804 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.44 | Sq.Ft | 55 | 100 | 289.36 | 0 | 11574.2 | C+S GST 18% I/P RD | 2083.36 | 13657.56 | 13657.56 | Approved | 0 | 0 | 669 | 28 Sep 2021
GANGA DHAM TOWERS | 551 | 91674 | 28 Sep 2021 | 03/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1122 | A 1804 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 590.89 | Sq.Ft | 55 | 100 | 812.47 | 0 | 32498.95 | C+S GST 18% I/P RD | 5849.82 | 38348.77 | 38348.77 | Approved | 0 | 0 | 669 | 28 Sep 2021
GANGA DHAM TOWERS | 551 | 91674 | 28 Sep 2021 | 03/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1122 | A 1804 Tiling Below Wooden Flooring | Ceramic Flooring work | 178.68 | Sq.Ft | 18 | 100 | 80.41 | 0 | 3216.24 | C+S GST 18% I/P RD | 578.92 | 3795.16 | 3795.16 | Approved | 0 | 0 | 669 | 28 Sep 2021
GANGA DHAM TOWERS | 551 | 91674 | 28 Sep 2021 | 03/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1122 | A 1804 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 161.94 | Sq.Ft | 24 | 100 | 97.16 | 0 | 3886.56 | C+S GST 18% I/P RD | 699.58 | 4586.14 | 4586.14 | Approved | 0 | 0 | 669 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1502 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 55 | 100 | 787.61 | 0 | 31504.55 | C+S GST 18% I/P RD | 5670.82 | 37175.37 | 37175.37 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1902 Tiling Below Wooden Flooring | Ceramic Flooring work | 181.48 | Sq.Ft | 21 | 100 | 95.28 | 0 | 3811.08 | C+S GST 18% I/P RD | 686 | 4497.08 | 4497.08 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1801 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 82.278 | R.Ft | 55 | 100 | 113.13 | 0 | 4525.29 | C+S GST 18% I/P RD | 814.56 | 5339.85 | 5339.85 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1502 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 22.106 | R.Ft | 55 | 100 | 30.4 | 0 | 1215.83 | C+S GST 18% I/P RD | 218.84 | 1434.67 | 1434.67 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1502 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 34.769 | R.Ft | 55 | 100 | 47.81 | 0 | 1912.3 | C+S GST 18% I/P RD | 344.22 | 2256.52 | 2256.52 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1502 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 80.213 | R.Ft | 55 | 100 | 110.29 | 0 | 4411.72 | C+S GST 18% I/P RD | 794.1 | 5205.82 | 5205.82 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1801 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 43.638 | R.Ft | 55 | 100 | 60 | 0 | 2400.09 | C+S GST 18% I/P RD | 432.02 | 2832.11 | 2832.11 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1801 Master Bed Marble Flooring | Italian marble Skirting - BCo | 45.934 | R.Ft | 55 | 100 | 63.16 | 0 | 2526.37 | C+S GST 18% I/P RD | 454.74 | 2981.11 | 2981.11 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1502 Master Bed Marble Flooring | Italian marble Skirting - BCo | 46.83 | R.Ft | 55 | 100 | 64.39 | 0 | 2575.65 | C+S GST 18% I/P RD | 463.62 | 3039.27 | 3039.27 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1902 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 80.213 | R.Ft | 60 | 100 | 120.32 | 0 | 4812.78 | C+S GST 18% I/P RD | 866.3 | 5679.08 | 5679.08 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1902 Master Bed Marble Flooring | Italian marble Skirting - BCo | 46.83 | R.Ft | 60 | 100 | 70.25 | 0 | 2809.8 | C+S GST 18% I/P RD | 505.76 | 3315.56 | 3315.56 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1902 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 60 | 100 | 859.22 | 0 | 34368.6 | C+S GST 18% I/P RD | 6186.34 | 40554.94 | 40554.94 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1902 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.65 | Sq.Ft | 60 | 100 | 315.98 | 0 | 12639 | C+S GST 18% I/P RD | 2275.02 | 14914.02 | 14914.02 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 537 | 91673 | 28 Sep 2021 | 02/21-22 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1119 | A 1902 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 45.13 | Sq.Ft | 24 | 100 | 27.08 | 0 | 1083.12 | C+S GST 18% I/P RD | 194.96 | 1278.08 | 1278.08 | Approved | 0 | 0 | 1106 | 28 Sep 2021
GANGA DHAM TOWERS | 796 | 91672 | 27 Sep 2021 | mum/2582 | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1112 | D Fire St.case Wall Gyp. Plaster 4th to 5th Fl. | Tikki Dhada (M) | 400 | Sq.Ft | 9 | 100 | 0 | 0 | 3600 | C+S GST 5% I/P RD | 180 | 3780 | 3780 | Approved | 0 | 0 | 0 | 27 Sep 2021
GANGA DHAM TOWERS | 796 | 91672 | 27 Sep 2021 | mum/2582 | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1112 | D Fire St.case Wall Gyp. Plaster 6th to 7th Fl. | Tikki Dhada (M) | 400 | Sq.Ft | 9 | 100 | 0 | 0 | 3600 | C+S GST 5% I/P RD | 180 | 3780 | 3780 | Approved | 0 | 0 | 0 | 27 Sep 2021
GANGA DHAM TOWERS | 796 | 91672 | 27 Sep 2021 | mum/2582 | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1112 | D 9th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (M) | 616 | Sq.Ft | 9 | 100 | 0 | 0 | 5544 | C+S GST 5% I/P RD | 277.2 | 5821.2 | 5821.2 | Approved | 0 | 0 | 0 | 27 Sep 2021
GANGA DHAM TOWERS | 796 | 91672 | 27 Sep 2021 | mum/2582 | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1112 | D Fire St.case Wall Gyp. Plaster 5th to 6th Fl. | Tikki Dhada (M) | 400 | Sq.Ft | 9 | 100 | 0 | 0 | 3600 | C+S GST 5% I/P RD | 180 | 3780 | 3780 | Approved | 0 | 0 | 0 | 27 Sep 2021
GANGA DHAM TOWERS | 796 | 91672 | 27 Sep 2021 | mum/2582 | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1112 | D 7th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (M) | 616 | Sq.Ft | 9 | 100 | 0 | 0 | 5544 | C+S GST 5% I/P RD | 277.2 | 5821.2 | 5821.2 | Approved | 0 | 0 | 0 | 27 Sep 2021
GANGA DHAM TOWERS | 796 | 91672 | 27 Sep 2021 | mum/2582 | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1112 | D Fire St.case Wall Gyp. Plaster 7th to 8th Fl. | Tikki Dhada (M) | 400 | Sq.Ft | 9 | 100 | 0 | 0 | 3600 | C+S GST 5% I/P RD | 180 | 3780 | 3780 | Approved | 0 | 0 | 0 | 27 Sep 2021
GANGA DHAM TOWERS | 796 | 91672 | 27 Sep 2021 | mum/2582 | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1112 | D Fire St.case Wall Gyp. Plaster 8th to 9th Fl. | Tikki Dhada (M) | 386.7778 | Sq.Ft | 9 | 100 | 0 | 0 | 3481 | C+S GST 5% I/P RD | 174.06 | 3655.06 | 3655.06 | Approved | 0 | 0 | 0 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P2 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 561 | Sq.Ft | 5 | 100 | 70.13 | 0 | 2805 | C+S GST 18% I/P RD | 504.9 | 3309.9 | 3309.9 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P2 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 574.8 | Sq.Ft | 5 | 100 | 71.85 | 0 | 2874 | C+S GST 18% I/P RD | 517.32 | 3391.32 | 3391.32 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P3 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 561 | Sq.Ft | 5 | 100 | 70.13 | 0 | 2805 | C+S GST 18% I/P RD | 504.9 | 3309.9 | 3309.9 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P1 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 943 | Sq.Ft | 5 | 100 | 117.88 | 0 | 4715 | C+S GST 18% I/P RD | 848.7 | 5563.7 | 5563.7 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P2 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (L) | 655.5 | Sq.Ft | 4 | 100 | 65.55 | 0 | 2622 | C+S GST 18% I/P RD | 471.96 | 3093.96 | 3093.96 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P2 Parking Floor Column Plaster | Gypsum Plaster (L) | 574.75 | Sq.Ft | 4 | 100 | 57.48 | 0 | 2299 | C+S GST 18% I/P RD | 413.82 | 2712.82 | 2712.82 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P1 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 561 | Sq.Ft | 4 | 100 | 56.1 | 0 | 2244 | C+S GST 18% I/P RD | 403.92 | 2647.92 | 2647.92 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P2 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 561 | Sq.Ft | 4 | 100 | 56.1 | 0 | 2244 | C+S GST 18% I/P RD | 403.92 | 2647.92 | 2647.92 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A Ground Floor Staircase & Lobby Plaster | Gypsum Plaster (L) | 561 | Sq.Ft | 4 | 100 | 56.1 | 0 | 2244 | C+S GST 18% I/P RD | 403.92 | 2647.92 | 2647.92 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 649 | 91669 | 27 Sep 2021 | 66 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1053 | A P3 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 561 | Sq.Ft | 4 | 100 | 56.1 | 0 | 2244 | C+S GST 18% I/P RD | 403.92 | 2647.92 | 2647.92 | Approved | 0 | 0 | 271 | 27 Sep 2021
GANGA DHAM TOWERS | 1001 | 91668 | 27 Sep 2021 | 91668 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1026 | A 1502 NOC | Italian Marble Flooring - BCo | 375.62 | Sq.Ft | 55 | 100 | 0 | 0 | 20659.1 | C+S GST 18% I/P RD | 3718.64 | 24377.74 | 24377.74 | Approved | 0 | 0 | 207 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1801 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 228.2 | Sq.Ft | 55 | 100 | 313.78 | 0 | 12551 | C+S GST 18% I/P RD | 2259.18 | 14810.18 | 14810.18 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1502 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 55 | 100 | 250.87 | 0 | 10034.75 | C+S GST 18% I/P RD | 1806.26 | 11841.01 | 11841.01 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1801 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.97 | Sq.Ft | 55 | 100 | 290.08 | 0 | 11603.35 | C+S GST 18% I/P RD | 2088.6 | 13691.95 | 13691.95 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1801 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.7 | Sq.Ft | 55 | 100 | 787.46 | 0 | 31498.5 | C+S GST 18% I/P RD | 5669.74 | 37168.24 | 37168.24 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1502 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 55 | 100 | 184.04 | 0 | 7361.75 | C+S GST 18% I/P RD | 1325.12 | 8686.87 | 8686.87 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1502 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.65 | Sq.Ft | 55 | 100 | 289.64 | 0 | 11585.75 | C+S GST 18% I/P RD | 2085.44 | 13671.19 | 13671.19 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1801 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 133.85 | Sq.Ft | 55 | 100 | 184.04 | 0 | 7361.75 | C+S GST 18% I/P RD | 1325.12 | 8686.87 | 8686.87 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1902 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 150.97 | Sq.Ft | 28 | 100 | 105.68 | 0 | 4227.16 | C+S GST 18% I/P RD | 760.88 | 4988.04 | 4988.04 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1502 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 43.06 | Sq.Ft | 21 | 100 | 22.61 | 0 | 904.26 | C+S GST 18% I/P RD | 162.76 | 1067.02 | 1067.02 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1801 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 161.84 | Sq.Ft | 24 | 100 | 97.1 | 0 | 3884.16 | C+S GST 18% I/P RD | 699.14 | 4583.3 | 4583.3 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1801 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 44.05 | Sq.Ft | 21 | 100 | 23.13 | 0 | 925.05 | C+S GST 18% I/P RD | 166.5 | 1091.55 | 1091.55 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 537 | 91667 | 27 Sep 2021 | 91667 | MONIKA ENTERPRISES | Kishan Enterprises | EV - 1118 | A 1502 Terrace Vitrified Flooring | Vitrified Flooring -BC | 140 | Sq.Ft | 24 | 100 | 84 | 0 | 3360 | C+S GST 18% I/P RD | 604.8 | 3964.8 | 3964.8 | Approved | 0 | 0 | 1053 | 27 Sep 2021
GANGA DHAM TOWERS | 551 | 91666 | 27 Sep 2021 | 06/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1121 | A 1803 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 115.44 | Sq.Ft | 24 | 100 | 69.26 | 0 | 2770.56 | C+S GST 18% I/P RD | 498.7 | 3269.26 | 3269.26 | Approved | 0 | 0 | 59 | 27 Sep 2021
GANGA DHAM TOWERS | 551 | 91666 | 27 Sep 2021 | 06/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1121 | A 1803 Tiling Below Wooden Flooring | Ceramic Flooring work | 171.58 | Sq.Ft | 18 | 100 | 77.21 | 0 | 3088.44 | C+S GST 18% I/P RD | 555.92 | 3644.36 | 3644.36 | Approved | 0 | 0 | 59 | 27 Sep 2021
GANGA DHAM TOWERS | 796 | 91665 | 25 Sep 2021 | 16/punr-21-22 | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 962 | D 8th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (M) | 126.5556 | Sq.Ft | 9 | 100 | 0 | 0 | 1139 | C+S GST 5% I/P RD | 56.96 | 1195.96 | 1195.96 | Approved | 0 | 0 | 0 | 25 Sep 2021
GANGA DHAM TOWERS | 1154 | 91654 | 25 Sep 2021 |  | H.R.DHANAVE | H.R.DHANAVE | EV - 1117 | B1- 1101 Tractor Trips Breaking Material | Tractor Trips-BRE | 2 | Trips | 750 | 100 | 0 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 82 | 25 Sep 2021
GANGA DHAM TOWERS | 1154 | 91654 | 25 Sep 2021 |  | H.R.DHANAVE | H.R.DHANAVE | EV - 1117 | B1- 1101 Tractor Trips Breaking Material | Tractor Trips-BRE | 7 | Trips | 950 | 100 | 0 | 0 | 6650 | CGST 0% URD I/P | 0 | 6650 | 6650 | Approved | 0 | 0 | 82 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Melamine Polish 3" Patta | 773.76 | R.Ft | 40 | 100 | 773.76 | 0 | 30950.4 | C+S GST 18% I/P RD | 5571.08 | 36521.48 | 36521.48 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Lamination polish | 48.97 | Sq.Ft | 450 | 100 | 550.91 | 0 | 22036.5 | C+S GST 18% I/P RD | 3966.58 | 26003.08 | 26003.08 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Duco P.U. Polish -BCo | 106 | Sq.Ft | 250 | 100 | 662.5 | 0 | 26500 | C+S GST 18% I/P RD | 4770 | 31270 | 31270 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Duco 1" Patta | 475.8 | R.Ft | 30 | 100 | 356.85 | 0 | 14274 | C+S GST 18% I/P RD | 2569.32 | 16843.32 | 16843.32 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | 3" P.U. Polish Patta-AIE | 74 | R.Ft | 70 | 100 | 129.5 | 0 | 5180 | C+S GST 18% I/P RD | 932.4 | 6112.4 | 6112.4 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Lamination polish 1" patta | 21 | R.Ft | 100 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Melamine Polish 1" Patti | 722.554 | R.Ft | 20 | 100 | 361.28 | 0 | 14451.08 | C+S GST 18% I/P RD | 2601.2 | 17052.28 | 17052.28 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | P.U. Polish-AIE | 3.86 | Sq.Ft | 200 | 100 | 19.3 | 0 | 772 | C+S GST 18% I/P RD | 138.96 | 910.96 | 910.96 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Melamine Polish - BC | 59.59 | Sq.Ft | 75 | 100 | 111.73 | 0 | 4469.25 | C+S GST 18% I/P RD | 804.46 | 5273.71 | 5273.71 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Velvet Touch Paint ARW | 326 | Sq.Ft | 20 | 100 | 163 | 0 | 6520 | C+S GST 18% I/P RD | 1173.6 | 7693.6 | 7693.6 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Duco P.U. polish 2" patta | 57.28 | R.Ft | 60 | 100 | 85.92 | 0 | 3436.8 | C+S GST 18% I/P RD | 618.62 | 4055.42 | 4055.42 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Lamination polish 2" patta | 42.32 | R.Ft | 150 | 100 | 158.7 | 0 | 6348 | C+S GST 18% I/P RD | 1142.64 | 7490.64 | 7490.64 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | 2" P.U. Polish Patta-AIE | 80.96 | R.Ft | 50 | 100 | 101.2 | 0 | 4048 | C+S GST 18% I/P RD | 728.64 | 4776.64 | 4776.64 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Lamination polish 3" patta | 21.16 | R.Ft | 200 | 100 | 105.8 | 0 | 4232 | C+S GST 18% I/P RD | 761.76 | 4993.76 | 4993.76 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Velvet Touch Paint ARW | 5836 | Sq.Ft | 40 | 100 | 5836 | 0 | 233440 | C+S GST 18% I/P RD | 42019.2 | 275459.2 | 275459.2 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | 2" Melamine Polish - AIE | 306.16 | R.Ft | 30 | 100 | 229.62 | 0 | 9184.8 | C+S GST 18% I/P RD | 1653.26 | 10838.06 | 10838.06 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Duco 2" Patta | 92.33 | R.Ft | 50 | 100 | 115.41 | 0 | 4616.5 | C+S GST 18% I/P RD | 830.98 | 5447.48 | 5447.48 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 1164 | 91653 | 25 Sep 2021 | 24 | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | MANSURI ENTERPRISES (PROP. SHAMIM AKBAR NAMSURI) | EV - 1079 | B 1 - 1101 Painting Work | Duco Paint | 6.4 | Sq.Ft | 200 | 100 | 32 | 0 | 1280 | C+S GST 18% I/P RD | 230.4 | 1510.4 | 1510.4 | Approved | 0 | 0 | 3938 | 25 Sep 2021
GANGA DHAM TOWERS | 371 | 91649 | 24 Sep 2021 | 105 | CONSTROGENESIS | MARVEL ENTERPRISES | EV - 1006 | EWS Bldg RCC 7th Slab Built-up Area (L) | Hacking Work | 3400 | Sq.Ft | 2.5 | 100 | 212.5 | 0 | 8500 | C+S GST 18% I/P RD | 1530 | 10030 | 10030 | Approved | 0 | 0 | 277 | 24 Sep 2021
GANGA DHAM TOWERS | 371 | 91649 | 24 Sep 2021 | 105 | CONSTROGENESIS | MARVEL ENTERPRISES | EV - 1006 | EWS Bldg RCC 8th Slab Built-up Area (L) | Hacking Work | 851.6 | Sq.Ft | 2.5 | 100 | 53.23 | 0 | 2129 | C+S GST 18% I/P RD | 383.22 | 2512.22 | 2512.22 | Approved | 0 | 0 | 277 | 24 Sep 2021
GANGA DHAM TOWERS | 371 | 91649 | 24 Sep 2021 | 105 | CONSTROGENESIS | MARVEL ENTERPRISES | EV - 1006 | EWS Bldg RCC 5th Slab Built-up Area (L) | Hacking Work | 3419 | Sq.Ft | 2.5 | 100 | 213.69 | 0 | 8547.5 | C+S GST 18% I/P RD | 1538.56 | 10086.06 | 10086.06 | Approved | 0 | 0 | 277 | 24 Sep 2021
GANGA DHAM TOWERS | 371 | 91649 | 24 Sep 2021 | 105 | CONSTROGENESIS | MARVEL ENTERPRISES | EV - 1006 | EWS Bldg RCC 6th Slab Built-up Area (L) | Hacking Work | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | C+S GST 18% I/P RD | 1538.62 | 10086.5 | 10086.5 | Approved | 0 | 0 | 277 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 803 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 1603 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 2004 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 2103 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 1902 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 1901 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 2102 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 2003 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 1603 Chemical & IPS Waterproofing | IPS W/P | 200 | Sq.Ft | 11 | 100 | 220 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 803 Chemical & IPS Waterproofing | IPS W/P | 200 | Sq.Ft | 11 | 100 | 220 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 2003 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 1804 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 1803 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 2004 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 2102 Chemical Grouting Work | Chemical Grouting.- BC | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 2103 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 1901 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 401 | 91648 | 24 Sep 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 1017 | A 1902 Chemical Grouting Work | Chemical Grouting.- BC | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 308 | 24 Sep 2021
GANGA DHAM TOWERS | 455 | 91647 | 24 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1016 | A Bldg Flat No. 1502 Internal Plumbing PPR-C | Int Flat PPRC Work. | 4 | No. | 1400 | 100 | 140 | 0 | 5600 | CGST 0% URD I/P | 0 | 5600 | 5600 | Approved | 0 | 0 | 56 | 24 Sep 2021
GANGA DHAM TOWERS | 505 | 91646 | 24 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1020 | A 25th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 647.13 | Sq.Ft | 2 | 100 | 129.43 | 0 | 1294.26 | CGST 0% URD I/P | 0 | 1294.26 | 1294.26 | Approved | 0 | 0 | 39 | 24 Sep 2021
GANGA DHAM TOWERS | 505 | 91646 | 24 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1020 | A 23rd Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 647.13 | Sq.Ft | 2 | 100 | 129.43 | 0 | 1294.26 | CGST 0% URD I/P | 0 | 1294.26 | 1294.26 | Approved | 0 | 0 | 39 | 24 Sep 2021
GANGA DHAM TOWERS | 505 | 91646 | 24 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 1020 | A 24th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 647.13 | Sq.Ft | 2 | 100 | 129.43 | 0 | 1294.26 | CGST 0% URD I/P | 0 | 1294.26 | 1294.26 | Approved | 0 | 0 | 39 | 24 Sep 2021
GANGA DHAM TOWERS | 1158 | 91645 | 24 Sep 2021 | 17 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1055 | D tower 12th roof slab rebarring work | Rebarring work 8mm dia- BC | 21 | No. | 120 | 100 | 63 | 0 | 2520 | C+S GST 18% I/P RD | 453.6 | 2973.6 | 2973.6 | Approved | 0 | 0 | 95 | 24 Sep 2021
GANGA DHAM TOWERS | 1158 | 91645 | 24 Sep 2021 | 17 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1055 | D tower 12th roof slab rebarring work | Rebarring work 12mm dia- BC | 7 | No. | 120 | 100 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 95 | 24 Sep 2021
GANGA DHAM TOWERS | 1158 | 91645 | 24 Sep 2021 | 17 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1055 | D tower 12th roof slab rebarring work | Rebarring work 16mm dia- BC | 4 | No. | 350 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 95 | 24 Sep 2021
GANGA DHAM TOWERS | 763 | 91644 | 24 Sep 2021 | 80 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1242 | A 304 Deep Cleaning Work | Deep Cleaning work | 1896.48 | Sq.Ft | 4 | 100 | 189.65 | 0 | 7585.92 | C+S GST 18% I/P RD | 1365.46 | 8951.38 | 8951.38 | Approved | 0 | 0 | 76 | 24 Sep 2021
GANGA DHAM TOWERS | 695 | 91643 | 23 Sep 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1296 | B P2 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (M) | 2637.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 9230 | C+S GST 5% I/P RD | 461.5 | 9691.5 | 9691.5 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 863 | 91642 | 23 Sep 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1295 | Club House 1st Floor Brickwork/ Plaster | Gypsum on Ceiling (M) | 942 | Sq.Ft | 3.5 | 100 | 0 | 0 | 3297 | C+S GST 5% I/P RD | 164.86 | 3461.86 | 3461.86 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 863 | 91642 | 23 Sep 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1295 | Club house GF Brickwork/Plaster | Gypsum Plaster (M) | 2655 | Sq.Ft | 9 | 100 | 0 | 0 | 23895 | C+S GST 5% I/P RD | 1194.76 | 25089.76 | 25089.76 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 863 | 91642 | 23 Sep 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1295 | Club House 1st Floor Brickwork/ Plaster | Gypsum Plaster (M) | 967.1111 | Sq.Ft | 9 | 100 | 0 | 0 | 8704 | C+S GST 5% I/P RD | 435.2 | 9139.2 | 9139.2 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 863 | 91642 | 23 Sep 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1295 | Club House 1st Floor Brickwork/ Plaster | Gypsum Plaster (M) | 1022.3333 | Sq.Ft | 9 | 100 | 0 | 0 | 9201 | C+S GST 5% I/P RD | 460.06 | 9661.06 | 9661.06 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 863 | 91642 | 23 Sep 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1295 | Club house GF Brickwork/Plaster | Gypsum Plaster (M) | 2128.6667 | Sq.Ft | 9 | 100 | 0 | 0 | 19158 | C+S GST 5% I/P RD | 957.9 | 20115.9 | 20115.9 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 863 | 91642 | 23 Sep 2021 |  | J K INTERIOR (MATERIAL) | NKV HOME DEPOT | EV - 1295 | Club house GF Brickwork/Plaster | Gypsum on Ceiling (M) | 1610 | Sq.Ft | 3.5 | 100 | 0 | 0 | 5635 | C+S GST 5% I/P RD | 281.76 | 5916.76 | 5916.76 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 371 | 91640 | 23 Sep 2021 | 24 | CONSTROGENESIS | CONSTROGENESIS | EV - 1037 | EWS Bldg RCC 1st Slab Built-up Area (L) | Hacking Work | 3537.2 | Sq.Ft | 2.5 | 100 | 221.08 | 0 | 8843 | C+S GST 18% I/P RD | 1591.74 | 10434.74 | 10434.74 | Approved | 0 | 0 | 690 | 23 Sep 2021
GANGA DHAM TOWERS | 371 | 91640 | 23 Sep 2021 | 24 | CONSTROGENESIS | CONSTROGENESIS | EV - 1037 | EWS Bldg RCC 3rd Slab Built-up Area (L) | Hacking Work | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | C+S GST 18% I/P RD | 1538.62 | 10086.5 | 10086.5 | Approved | 0 | 0 | 690 | 23 Sep 2021
GANGA DHAM TOWERS | 371 | 91640 | 23 Sep 2021 | 24 | CONSTROGENESIS | CONSTROGENESIS | EV - 1037 | EWS Bldg RCC 4th Slab Built-up Area (L) | Hacking Work | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | C+S GST 18% I/P RD | 1538.62 | 10086.5 | 10086.5 | Approved | 0 | 0 | 690 | 23 Sep 2021
GANGA DHAM TOWERS | 371 | 91640 | 23 Sep 2021 | 24 | CONSTROGENESIS | CONSTROGENESIS | EV - 1037 | EWS Bldg RCC 2nd Slab Built-up Area (L) | Hacking Work | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | C+S GST 18% I/P RD | 1538.62 | 10086.5 | 10086.5 | Approved | 0 | 0 | 690 | 23 Sep 2021
GANGA DHAM TOWERS | 540 | 91634 | 23 Sep 2021 | 56 | MONIKA ENTERPRISES | J K INTERIOR | EV - 1045 | A 602 NOC | Gypsum Plaster (L) | 400 | Sq.Ft | 9 | 100 | 90 | 0 | 3600 | C+S GST 18% I/P URD | 648 | 4248 | 4248 | Approved | 0 | 0 | 36 | 23 Sep 2021
GANGA DHAM TOWERS | 544 | 91633 | 23 Sep 2021 | 58 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1048 | A 22nd Floor Lobby Gypsum | Gypsum on Wall (L) | 625 | Sq.Ft | 4 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 175 | 23 Sep 2021
GANGA DHAM TOWERS | 544 | 91633 | 23 Sep 2021 | 58 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1048 | A 19th Floor Lobby Gypsum | Gypsum on Wall (L) | 625 | Sq.Ft | 4 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 175 | 23 Sep 2021
GANGA DHAM TOWERS | 544 | 91633 | 23 Sep 2021 | 58 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1048 | A 23rd Floor Lobby Gypsum | Gypsum on Wall (L) | 625 | Sq.Ft | 4 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 175 | 23 Sep 2021
GANGA DHAM TOWERS | 544 | 91633 | 23 Sep 2021 | 58 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1048 | A 18th Floor Lobby Gypsum | Gypsum on Wall (L) | 625 | Sq.Ft | 4 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 175 | 23 Sep 2021
GANGA DHAM TOWERS | 544 | 91633 | 23 Sep 2021 | 58 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1048 | A 20th Floor Lobby Gypsum | Gypsum on Wall (L) | 625 | Sq.Ft | 4 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 175 | 23 Sep 2021
GANGA DHAM TOWERS | 544 | 91633 | 23 Sep 2021 | 58 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1048 | A 21st Floor Lobby Gypsum | Gypsum on Wall (L) | 625 | Sq.Ft | 4 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 175 | 23 Sep 2021
GANGA DHAM TOWERS | 544 | 91633 | 23 Sep 2021 | 58 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 1048 | A 17th Floor Lobby Gypsum | Gypsum on Wall (L) | 625 | Sq.Ft | 4 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 175 | 23 Sep 2021
GANGA DHAM TOWERS | 393 | 91632 | 23 Sep 2021 | 62 | J K INTERIOR | J K INTERIOR | EV - 1046 | A Bldg Flat No. 2202 Gypsum Plaster | Dhar Core (L) | 450 | R.Ft | 10 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 590 | 23 Sep 2021
GANGA DHAM TOWERS | 393 | 91632 | 23 Sep 2021 | 62 | J K INTERIOR | J K INTERIOR | EV - 1046 | A Bldg Flat No. 2101 Gypsum Plaster | Dhar Core (L) | 430 | R.Ft | 10 | 100 | 107.5 | 0 | 4300 | C+S GST 18% I/P RD | 774 | 5074 | 5074 | Approved | 0 | 0 | 590 | 23 Sep 2021
GANGA DHAM TOWERS | 393 | 91632 | 23 Sep 2021 | 62 | J K INTERIOR | J K INTERIOR | EV - 1046 | A Bldg Flat No. 2301 Gypsum Plaster | Dhar Core (L) | 430 | R.Ft | 10 | 100 | 107.5 | 0 | 4300 | C+S GST 18% I/P RD | 774 | 5074 | 5074 | Approved | 0 | 0 | 590 | 23 Sep 2021
GANGA DHAM TOWERS | 393 | 91632 | 23 Sep 2021 | 62 | J K INTERIOR | J K INTERIOR | EV - 1046 | A Bldg Flat No. 2201 Gypsum Plaster | Dhar Core (L) | 430 | R.Ft | 10 | 100 | 107.5 | 0 | 4300 | C+S GST 18% I/P RD | 774 | 5074 | 5074 | Approved | 0 | 0 | 590 | 23 Sep 2021
GANGA DHAM TOWERS | 393 | 91632 | 23 Sep 2021 | 62 | J K INTERIOR | J K INTERIOR | EV - 1046 | A Bldg Flat No. 2301 Gypsum Plaster | Gypsum on Wall (L) | 2600 | Sq.Ft | 4 | 100 | 260 | 0 | 10400 | C+S GST 18% I/P RD | 1872 | 12272 | 12272 | Approved | 0 | 0 | 590 | 23 Sep 2021
GANGA DHAM TOWERS | 393 | 91632 | 23 Sep 2021 | 62 | J K INTERIOR | J K INTERIOR | EV - 1046 | A Bldg Flat No. 2101 Gypsum Plaster | Gypsum on Wall (L) | 2600 | Sq.Ft | 4 | 100 | 260 | 0 | 10400 | C+S GST 18% I/P RD | 1872 | 12272 | 12272 | Approved | 0 | 0 | 590 | 23 Sep 2021
GANGA DHAM TOWERS | 393 | 91632 | 23 Sep 2021 | 62 | J K INTERIOR | J K INTERIOR | EV - 1046 | A Bldg Flat No. 2201 Gypsum Plaster | Gypsum on Wall (L) | 2600 | Sq.Ft | 4 | 100 | 260 | 0 | 10400 | C+S GST 18% I/P RD | 1872 | 12272 | 12272 | Approved | 0 | 0 | 590 | 23 Sep 2021
GANGA DHAM TOWERS | 393 | 91632 | 23 Sep 2021 | 62 | J K INTERIOR | J K INTERIOR | EV - 1046 | A Bldg Flat No. 2202 Gypsum Plaster | Gypsum on Wall (L) | 2600 | Sq.Ft | 4 | 100 | 260 | 0 | 10400 | C+S GST 18% I/P RD | 1872 | 12272 | 12272 | Approved | 0 | 0 | 590 | 23 Sep 2021
GANGA DHAM TOWERS | 697 | 91630 | 23 Sep 2021 | mum/2582 | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 1132 | D 1102 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 979 | Sq.Ft | 9 | 100 | 0 | 0 | 8811 | C+S GST 18% I/P RD | 1585.98 | 10396.98 | 10396.98 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 697 | 91630 | 23 Sep 2021 | mum/2582 | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 1132 | D 1105 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145 | Sq.Ft | 9 | 100 | 0 | 0 | 10305 | C+S GST 18% I/P RD | 1854.9 | 12159.9 | 12159.9 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 697 | 91630 | 23 Sep 2021 | mum/2582 | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 1132 | D 802 (Refuge area) Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 826 | Sq.Ft | 9 | 100 | 0 | 0 | 7434 | C+S GST 18% I/P RD | 1338.12 | 8772.12 | 8772.12 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 697 | 91630 | 23 Sep 2021 | mum/2582 | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 1132 | D 1104 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792 | Sq.Ft | 9 | 100 | 0 | 0 | 7128 | C+S GST 18% I/P RD | 1283.04 | 8411.04 | 8411.04 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 697 | 91630 | 23 Sep 2021 | mum/2582 | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 1132 | D 1101 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145 | Sq.Ft | 9 | 100 | 0 | 0 | 10305 | C+S GST 18% I/P RD | 1854.9 | 12159.9 | 12159.9 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 697 | 91630 | 23 Sep 2021 | mum/2582 | A K INTERIOR CONTRACTOR (MATERIAL) | NKV HOME DEPOT | EV - 1132 | D 1103 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792 | Sq.Ft | 9 | 100 | 0 | 0 | 7128 | C+S GST 18% I/P RD | 1283.04 | 8411.04 | 8411.04 | Approved | 0 | 0 | 0 | 23 Sep 2021
GANGA DHAM TOWERS | 634 | 91629 | 23 Sep 2021 | 91629 | R K INTERIOR | R K INTERIOR | EV - 1043 | A 23rd Floor Lobbby Flooring | Vitrified Flooring -Bco | 500 | Sq.Ft | 45 | 100 | 562.5 | 0 | 22500 | C+S GST 18% I/P RD | 4050 | 26550 | 26550 | Approved | 0 | 0 | 2475 | 23 Sep 2021
GANGA DHAM TOWERS | 634 | 91629 | 23 Sep 2021 | 91629 | R K INTERIOR | R K INTERIOR | EV - 1043 | A 21st Floor Lobbby Flooring | Vitrified Flooring -Bco | 450 | Sq.Ft | 45 | 100 | 506.25 | 0 | 20250 | C+S GST 18% I/P RD | 3645 | 23895 | 23895 | Approved | 0 | 0 | 2475 | 23 Sep 2021
GANGA DHAM TOWERS | 634 | 91629 | 23 Sep 2021 | 91629 | R K INTERIOR | R K INTERIOR | EV - 1043 | A 22nd Floor Lobbby Flooring | Vitrified Flooring -Bco | 600 | Sq.Ft | 45 | 100 | 675 | 0 | 27000 | C+S GST 18% I/P RD | 4860 | 31860 | 31860 | Approved | 0 | 0 | 2475 | 23 Sep 2021
GANGA DHAM TOWERS | 634 | 91629 | 23 Sep 2021 | 91629 | R K INTERIOR | R K INTERIOR | EV - 1043 | A 20th Floor Lobbby Flooring | Vitrified Flooring -Bco | 600 | Sq.Ft | 45 | 100 | 675 | 0 | 27000 | C+S GST 18% I/P RD | 4860 | 31860 | 31860 | Approved | 0 | 0 | 2475 | 23 Sep 2021
GANGA DHAM TOWERS | 634 | 91629 | 23 Sep 2021 | 91629 | R K INTERIOR | R K INTERIOR | EV - 1043 | A 19th Floor Lobbby Flooring | Vitrified Flooring -Bco | 600 | Sq.Ft | 45 | 100 | 675 | 0 | 27000 | C+S GST 18% I/P RD | 4860 | 31860 | 31860 | Approved | 0 | 0 | 2475 | 23 Sep 2021
GANGA DHAM TOWERS | 551 | 91628 | 23 Sep 2021 | 07/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1120 | A 1803 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 487.99 | Sq.Ft | 55 | 100 | 670.99 | 0 | 26839.45 | C+S GST 18% I/P RD | 4831.1 | 31670.55 | 31670.55 | Approved | 0 | 0 | 458 | 23 Sep 2021
GANGA DHAM TOWERS | 551 | 91628 | 23 Sep 2021 | 07/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1120 | A 1803 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 200.32 | Sq.Ft | 55 | 100 | 275.44 | 0 | 11017.6 | C+S GST 18% I/P RD | 1983.16 | 13000.76 | 13000.76 | Approved | 0 | 0 | 458 | 23 Sep 2021
GANGA DHAM TOWERS | 551 | 91628 | 23 Sep 2021 | 07/21-22 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | Kishan Enterprises | EV - 1120 | A 1803 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144.08 | Sq.Ft | 55 | 100 | 198.11 | 0 | 7924.4 | C+S GST 18% I/P RD | 1426.4 | 9350.8 | 9350.8 | Approved | 0 | 0 | 458 | 23 Sep 2021
GANGA DHAM TOWERS | 993 | 91625 | 23 Sep 2021 | 50 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1061 | B 1602 NOC | Italian marble Skirting - BCo | 28.992 | R.Ft | 55 | 100 | 39.86 | 0 | 1594.56 | C+S GST 18% I/P RD | 287.02 | 1881.58 | 1881.58 | Approved | 0 | 0 | 16 | 23 Sep 2021
GANGA DHAM TOWERS | 1119 | 91624 | 23 Sep 2021 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1747 | C Bldg Substructure PCC work - | PCC Work | 10500 | Sq.Ft | 3 | 100 | 787.5 | 0 | 31500 | C+S GST 18% I/P RD | 5670 | 37170 | 37170 | Approved | 0 | 0 | 4539 | 23 Sep 2021
GANGA DHAM TOWERS | 1119 | 91624 | 23 Sep 2021 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1747 | C Bldg Substructure Footing & Column work | Footing & Column | 8447.229 | Sq.Ft | 50 | 100 | 10559.04 | 0 | 422361.45 | C+S GST 18% I/P RD | 76025.06 | 498386.51 | 498386.51 | Approved | 0 | 0 | 4539 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1102 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 138.483 | Sq.Ft | 20 | 100 | 69.24 | 0 | 2769.66 | C+S GST 18% I/P RD | 498.54 | 3268.2 | 3268.2 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 402 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.247 | R.Ft | 650 | 100 | 85.26 | 0 | 3410.55 | C+S GST 18% I/P RD | 613.9 | 4024.45 | 4024.45 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 101 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 650 | 100 | 92.58 | 0 | 3703.05 | C+S GST 18% I/P RD | 666.54 | 4369.59 | 4369.59 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 101 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 650 | 100 | 45.05 | 0 | 1801.8 | C+S GST 18% I/P RD | 324.32 | 2126.12 | 2126.12 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 402 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.275 | R.Ft | 650 | 100 | 69.47 | 0 | 2778.75 | C+S GST 18% I/P RD | 500.18 | 3278.93 | 3278.93 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 401 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.375 | R.Ft | 650 | 100 | 54.84 | 0 | 2193.75 | C+S GST 18% I/P RD | 394.88 | 2588.63 | 2588.63 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 902 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 100.896 | R.Ft | 50 | 100 | 126.12 | 0 | 5044.8 | C+S GST 18% I/P RD | 908.06 | 5952.86 | 5952.86 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 902 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 57.744 | R.Ft | 50 | 100 | 72.18 | 0 | 2887.2 | C+S GST 18% I/P RD | 519.7 | 3406.9 | 3406.9 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 902 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 45.672 | R.Ft | 50 | 100 | 57.09 | 0 | 2283.6 | C+S GST 18% I/P RD | 411.04 | 2694.64 | 2694.64 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1601 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 55 | 100 | 334.13 | 0 | 13365 | C+S GST 18% I/P RD | 2405.7 | 15770.7 | 15770.7 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1502 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 55 | 100 | 370.45 | 0 | 14818.1 | C+S GST 18% I/P RD | 2667.26 | 17485.36 | 17485.36 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1602 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 57.744 | R.Ft | 55 | 100 | 79.4 | 0 | 3175.92 | C+S GST 18% I/P RD | 571.66 | 3747.58 | 3747.58 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1601 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 69.5175 | R.Ft | 55 | 100 | 95.59 | 0 | 3823.46 | C+S GST 18% I/P RD | 688.22 | 4511.68 | 4511.68 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1502 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 45.672 | R.Ft | 55 | 100 | 62.8 | 0 | 2511.96 | C+S GST 18% I/P RD | 452.16 | 2964.12 | 2964.12 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1602 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 100.896 | R.Ft | 55 | 100 | 138.73 | 0 | 5549.28 | C+S GST 18% I/P RD | 998.88 | 6548.16 | 6548.16 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1502 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 57.744 | R.Ft | 55 | 100 | 79.4 | 0 | 3175.92 | C+S GST 18% I/P RD | 571.66 | 3747.58 | 3747.58 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1601 Living,Dining,Ent.Lobby | Italian marble Skirting - BCo | 159.6525 | R.Ft | 55 | 100 | 219.52 | 0 | 8780.89 | C+S GST 18% I/P RD | 1580.56 | 10361.45 | 10361.45 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1601 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 51.9225 | R.Ft | 55 | 100 | 71.39 | 0 | 2855.74 | C+S GST 18% I/P RD | 514.04 | 3369.78 | 3369.78 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1502 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 100.896 | R.Ft | 55 | 100 | 138.73 | 0 | 5549.28 | C+S GST 18% I/P RD | 998.88 | 6548.16 | 6548.16 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1602 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 45.672 | R.Ft | 55 | 100 | 62.8 | 0 | 2511.96 | C+S GST 18% I/P RD | 452.16 | 2964.12 | 2964.12 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 101 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 650 | 100 | 92.58 | 0 | 3703.05 | C+S GST 18% I/P RD | 666.54 | 4369.59 | 4369.59 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1801 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 147.713 | Sq.Ft | 24 | 100 | 88.63 | 0 | 3545.11 | C+S GST 18% I/P RD | 638.12 | 4183.23 | 4183.23 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1602 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 138.483 | Sq.Ft | 24 | 100 | 83.09 | 0 | 3323.59 | C+S GST 18% I/P RD | 598.24 | 3921.83 | 3921.83 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1502 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 138.483 | Sq.Ft | 24 | 100 | 83.09 | 0 | 3323.59 | C+S GST 18% I/P RD | 598.24 | 3921.83 | 3921.83 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1601 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 156.402 | Sq.Ft | 24 | 100 | 93.84 | 0 | 3753.65 | C+S GST 18% I/P RD | 675.66 | 4429.31 | 4429.31 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1502 Ceramic Tiling | Ceramic Flooring work | 356.56 | Sq.Ft | 18 | 100 | 160.45 | 0 | 6418.08 | C+S GST 18% I/P RD | 1155.26 | 7573.34 | 7573.34 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1102 Ceramic Tiling | Ceramic Flooring work | 356.56 | Sq.Ft | 16 | 100 | 142.62 | 0 | 5704.96 | C+S GST 18% I/P RD | 1026.9 | 6731.86 | 6731.86 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1601 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 320.98 | Sq.Ft | 55 | 100 | 441.35 | 0 | 17653.9 | C+S GST 18% I/P RD | 3177.7 | 20831.6 | 20831.6 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1601 Living,Dining,Ent.Lobby | Italian Marble Flooring - BCo | 1150.67 | Sq.Ft | 55 | 100 | 1582.17 | 0 | 63286.85 | C+S GST 18% I/P RD | 11391.64 | 74678.49 | 74678.49 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1502 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 55 | 100 | 906.9 | 0 | 36275.8 | C+S GST 18% I/P RD | 6529.64 | 42805.44 | 42805.44 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1502 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 55 | 100 | 282.69 | 0 | 11307.45 | C+S GST 18% I/P RD | 2035.34 | 13342.79 | 13342.79 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1102 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 50 | 100 | 256.99 | 0 | 10279.5 | C+S GST 18% I/P RD | 1850.32 | 12129.82 | 12129.82 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1102 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 50 | 100 | 336.78 | 0 | 13471 | C+S GST 18% I/P RD | 2424.78 | 15895.78 | 15895.78 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1102 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 50 | 100 | 824.45 | 0 | 32978 | C+S GST 18% I/P RD | 5936.04 | 38914.04 | 38914.04 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 901 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 700 | 100 | 99.7 | 0 | 3987.9 | C+S GST 18% I/P RD | 717.82 | 4705.72 | 4705.72 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1002 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.275 | R.Ft | 700 | 100 | 74.81 | 0 | 2992.5 | C+S GST 18% I/P RD | 538.66 | 3531.16 | 3531.16 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 901 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 700 | 100 | 99.7 | 0 | 3987.9 | C+S GST 18% I/P RD | 717.82 | 4705.72 | 4705.72 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1002 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.319 | R.Ft | 700 | 100 | 93.08 | 0 | 3723.3 | C+S GST 18% I/P RD | 670.2 | 4393.5 | 4393.5 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 1002 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 700 | 100 | 48.51 | 0 | 1940.4 | C+S GST 18% I/P RD | 349.28 | 2289.68 | 2289.68 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 901 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 700 | 100 | 48.51 | 0 | 1940.4 | C+S GST 18% I/P RD | 349.28 | 2289.68 | 2289.68 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 902 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 700 | 100 | 48.51 | 0 | 1940.4 | C+S GST 18% I/P RD | 349.28 | 2289.68 | 2289.68 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 801 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.375 | R.Ft | 700 | 100 | 59.06 | 0 | 2362.5 | C+S GST 18% I/P RD | 425.26 | 2787.76 | 2787.76 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 901 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.375 | R.Ft | 700 | 100 | 59.06 | 0 | 2362.5 | C+S GST 18% I/P RD | 425.26 | 2787.76 | 2787.76 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 902 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.275 | R.Ft | 700 | 100 | 74.81 | 0 | 2992.5 | C+S GST 18% I/P RD | 538.66 | 3531.16 | 3531.16 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 801 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.95 | R.Ft | 700 | 100 | 86.63 | 0 | 3465 | C+S GST 18% I/P RD | 623.7 | 4088.7 | 4088.7 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 902 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.275 | R.Ft | 700 | 100 | 74.81 | 0 | 2992.5 | C+S GST 18% I/P RD | 538.66 | 3531.16 | 3531.16 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 901 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.95 | R.Ft | 700 | 100 | 86.63 | 0 | 3465 | C+S GST 18% I/P RD | 623.7 | 4088.7 | 4088.7 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 402 Common Toilet Counter Wash Basin-(No.) | Italian Marble Counter - Mkt | 4.275 | R.Ft | 650 | 100 | 69.47 | 0 | 2778.75 | C+S GST 18% I/P RD | 500.18 | 3278.93 | 3278.93 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 101 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 3.375 | R.Ft | 650 | 100 | 54.84 | 0 | 2193.75 | C+S GST 18% I/P RD | 394.88 | 2588.63 | 2588.63 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 401 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 650 | 100 | 45.05 | 0 | 1801.8 | C+S GST 18% I/P RD | 324.32 | 2126.12 | 2126.12 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 101 Children Toilet-2 Counter Wash Basin | Italian Marble Counter - Mkt | 4.572 | R.Ft | 650 | 100 | 74.3 | 0 | 2971.8 | C+S GST 18% I/P RD | 534.92 | 3506.72 | 3506.72 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 101 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.95 | R.Ft | 650 | 100 | 80.44 | 0 | 3217.5 | C+S GST 18% I/P RD | 579.16 | 3796.66 | 3796.66 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 401 Children Toilet-1 Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 650 | 100 | 92.58 | 0 | 3703.05 | C+S GST 18% I/P RD | 666.54 | 4369.59 | 4369.59 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 401 Common Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 4.95 | R.Ft | 650 | 100 | 80.44 | 0 | 3217.5 | C+S GST 18% I/P RD | 579.16 | 3796.66 | 3796.66 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 401 Guest Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.697 | R.Ft | 650 | 100 | 92.58 | 0 | 3703.05 | C+S GST 18% I/P RD | 666.54 | 4369.59 | 4369.59 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 402 Parents Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 5.319 | R.Ft | 650 | 100 | 86.43 | 0 | 3457.35 | C+S GST 18% I/P RD | 622.32 | 4079.67 | 4079.67 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 758 | 91623 | 23 Sep 2021 | 49 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1111 | B 402 Master Toilet Counter Wash Basin | Italian Marble Counter - Mkt | 2.772 | R.Ft | 650 | 100 | 45.05 | 0 | 1801.8 | C+S GST 18% I/P RD | 324.32 | 2126.12 | 2126.12 | Approved | 0 | 0 | 3750 | 23 Sep 2021
GANGA DHAM TOWERS | 1158 | 91609 | 22 Sep 2021 | 17 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1035 | D tower 12th roof slab rebarring work | Rebarring work 12mm dia- BC | 14 | No. | 120 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 519 | 22 Sep 2021
GANGA DHAM TOWERS | 1158 | 91609 | 22 Sep 2021 | 17 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1035 | D tower 12th roof slab rebarring work | Rebarring work 16mm dia- BC | 8 | No. | 350 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 519 | 22 Sep 2021
GANGA DHAM TOWERS | 1158 | 91609 | 22 Sep 2021 | 17 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1035 | D tower 12th roof slab rebarring work | Rebarring work 10mm dia- BC | 10 | No. | 120 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 519 | 22 Sep 2021
GANGA DHAM TOWERS | 1158 | 91609 | 22 Sep 2021 | 17 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1035 | D tower 12th roof slab rebarring work | Rebarring work 8mm dia- BC | 169 | No. | 120 | 100 | 507 | 0 | 20280 | C+S GST 18% I/P RD | 3650.4 | 23930.4 | 23930.4 | Approved | 0 | 0 | 519 | 22 Sep 2021
GANGA DHAM TOWERS | 1002 | 91607 | 22 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1058 | A 1902 NOC | Concrete Cutting Work | 1.7143 | R.Ft | 525 | 100 | 22.5 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 59 | 22 Sep 2021
GANGA DHAM TOWERS | 1002 | 91607 | 22 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1058 | A 1401 NOC | Concrete Cutting Work | 1.7143 | R.Ft | 525 | 100 | 22.5 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 59 | 22 Sep 2021
GANGA DHAM TOWERS | 1002 | 91607 | 22 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1058 | A 2002 NOC | Concrete Cutting Work | 1.7143 | R.Ft | 525 | 100 | 22.5 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 59 | 22 Sep 2021
GANGA DHAM TOWERS | 1002 | 91607 | 22 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1058 | A 2302 NOC | Concrete Cutting Work | 1.7143 | R.Ft | 525 | 100 | 22.5 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 59 | 22 Sep 2021
GANGA DHAM TOWERS | 1002 | 91607 | 22 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1058 | B 1602 NOC | Concrete Cutting Work | 1.7143 | R.Ft | 525 | 100 | 22.5 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 59 | 22 Sep 2021
GANGA DHAM TOWERS | 1002 | 91607 | 22 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1058 | A 2301 NOC | Concrete Cutting Work | 1.7143 | R.Ft | 525 | 100 | 22.5 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 59 | 22 Sep 2021
GANGA DHAM TOWERS | 1002 | 91607 | 22 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 1058 | A 1601 NOC | Concrete wall Crushing work | 0.0625 | Cu.Mtrs | 7200 | 100 | 11.25 | 0 | 450 | CGST 0% URD I/P | 0 | 450 | 450 | Approved | 0 | 0 | 59 | 22 Sep 2021
GANGA DHAM TOWERS | 1120 | 91599 | 21 Sep 2021 |  | UNIQUE ENTERPRISES | UNIQUE ENTERPRISES | EV - 1749 | C SW 36 & C9 Footing Cleaning work | Cleaning Work - Dld | 1 | No. | 5000 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 50 | 21 Sep 2021
GANGA DHAM TOWERS | 999 | 91597 | 21 Sep 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2015 | DA Development Top Terrace Painting Work | Apex Paint | 4188.8 | Sq.Ft | 18 | 100 | 1884.96 | 0 | 75398.4 | C+S GST 18% I/P RD | 13571.72 | 88970.12 | 88970.12 | Approved | 0 | 0 | 1036 | 21 Sep 2021
GANGA DHAM TOWERS | 999 | 91597 | 21 Sep 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2015 | DA Development Top Terrace Painting Work | Oil Paint | 718.38 | Sq.Ft | 10 | 100 | 179.6 | 0 | 7183.8 | C+S GST 18% I/P RD | 1293.08 | 8476.88 | 8476.88 | Approved | 0 | 0 | 1036 | 21 Sep 2021
GANGA DHAM TOWERS | 999 | 91597 | 21 Sep 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2015 | DA Development Top Terrace Painting Work | Enamel Paint | 1401.54 | Sq.Ft | 15 | 100 | 525.58 | 0 | 21023.1 | C+S GST 18% I/P RD | 3784.16 | 24807.26 | 24807.26 | Approved | 0 | 0 | 1036 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1101 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 37.9014 | Mtrs | 345 | 100 | 0 | 0 | 13076 | C+S GST 18% I/P RD | 2353.68 | 15429.68 | 15429.68 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 903 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 25.1014 | Mtrs | 345 | 100 | 0 | 0 | 8660 | C+S GST 18% I/P RD | 1558.8 | 10218.8 | 10218.8 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1704 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 32.6 | Mtrs | 345 | 100 | 0 | 0 | 11247 | C+S GST 18% I/P RD | 2024.46 | 13271.46 | 13271.46 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 404 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 33.1971 | Mtrs | 345 | 100 | 0 | 0 | 11453 | C+S GST 18% I/P RD | 2061.54 | 13514.54 | 13514.54 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 603 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 24.6 | Mtrs | 345 | 100 | 0 | 0 | 8487 | C+S GST 18% I/P RD | 1527.66 | 10014.66 | 10014.66 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 604 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 31.998 | Mtrs | 345 | 100 | 0 | 0 | 11039.31 | C+S GST 18% I/P RD | 1987.08 | 13026.39 | 13026.39 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1703 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 26 | Mtrs | 345 | 100 | 0 | 0 | 8970 | C+S GST 18% I/P RD | 1614.6 | 10584.6 | 10584.6 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 403 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 10.2899 | Mtrs | 345 | 100 | 0 | 0 | 3550 | C+S GST 18% I/P RD | 639 | 4189 | 4189 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 403 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 11.686 | Mtrs | 60.5 | 100 | 0 | 0 | 707 | C+S GST 18% I/P RD | 127.26 | 834.26 | 834.26 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 404 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 33.5868 | Mtrs | 60.5 | 100 | 0 | 0 | 2032 | C+S GST 18% I/P RD | 365.76 | 2397.76 | 2397.76 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 903 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 28.19 | Mtrs | 60.5 | 100 | 0 | 0 | 1705.5 | C+S GST 18% I/P RD | 307 | 2012.5 | 2012.5 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 603 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 25.686 | Mtrs | 60.5 | 100 | 0 | 0 | 1554 | C+S GST 18% I/P RD | 279.72 | 1833.72 | 1833.72 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1704 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 34.0992 | Mtrs | 60.5 | 100 | 0 | 0 | 2063 | C+S GST 18% I/P RD | 371.34 | 2434.34 | 2434.34 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1703 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 31.7025 | Mtrs | 60.5 | 100 | 0 | 0 | 1918 | C+S GST 18% I/P RD | 345.24 | 2263.24 | 2263.24 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1101 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 46.8926 | Mtrs | 60.5 | 100 | 0 | 0 | 2837 | C+S GST 18% I/P RD | 510.66 | 3347.66 | 3347.66 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 604 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 29.5868 | Mtrs | 60.5 | 100 | 0 | 0 | 1790 | C+S GST 18% I/P RD | 322.2 | 2112.2 | 2112.2 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 403 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 4.898 | Mtrs | 49 | 100 | 0 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1101 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.5 | Mtrs | 49 | 100 | 0 | 0 | 1053.5 | C+S GST 18% I/P RD | 189.64 | 1243.14 | 1243.14 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 604 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 20 | Mtrs | 49 | 100 | 0 | 0 | 980 | C+S GST 18% I/P RD | 176.4 | 1156.4 | 1156.4 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 903 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 13.5918 | Mtrs | 49 | 100 | 0 | 0 | 666 | C+S GST 18% I/P RD | 119.88 | 785.88 | 785.88 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1704 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21.2041 | Mtrs | 49 | 100 | 0 | 0 | 1039 | C+S GST 18% I/P RD | 187.02 | 1226.02 | 1226.02 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 1703 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 17 | Mtrs | 49 | 100 | 0 | 0 | 833 | C+S GST 18% I/P RD | 149.94 | 982.94 | 982.94 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 404 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 21 | Mtrs | 49 | 100 | 0 | 0 | 1029 | C+S GST 18% I/P RD | 185.22 | 1214.22 | 1214.22 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 530 | 91596 | 21 Sep 2021 | NEP/051/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 967 | A 603 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 14.102 | Mtrs | 49 | 100 | 0 | 0 | 691 | C+S GST 18% I/P RD | 124.38 | 815.38 | 815.38 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 801 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 36.5102 | Mtrs | 49 | 100 | 0 | 0 | 1789 | C+S GST 18% I/P RD | 322.02 | 2111.02 | 2111.02 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 1301 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 38.7959 | Mtrs | 49 | 100 | 0 | 0 | 1901 | C+S GST 18% I/P RD | 342.18 | 2243.18 | 2243.18 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 901 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 36.3061 | Mtrs | 49 | 100 | 0 | 0 | 1779 | C+S GST 18% I/P RD | 320.22 | 2099.22 | 2099.22 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 402 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 23 | Mtrs | 49 | 100 | 0 | 0 | 1127 | C+S GST 18% I/P RD | 202.86 | 1329.86 | 1329.86 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 401 AC Installation & Commissioning | Drain Pipe with Insulation (M) | 36.3061 | Mtrs | 49 | 100 | 0 | 0 | 1779 | C+S GST 18% I/P RD | 320.22 | 2099.22 | 2099.22 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 401 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 43.4 | Mtrs | 345 | 100 | 0 | 0 | 14973 | C+S GST 18% I/P RD | 2695.14 | 17668.14 | 17668.14 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 401 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 9 | Mtrs | 345 | 100 | 0 | 0 | 3105 | C+S GST 18% I/P RD | 558.9 | 3663.9 | 3663.9 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 801 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 9 | Mtrs | 345 | 100 | 0 | 0 | 3105 | C+S GST 18% I/P RD | 558.9 | 3663.9 | 3663.9 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 1301 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 9 | Mtrs | 345 | 100 | 0 | 0 | 3105 | C+S GST 18% I/P RD | 558.9 | 3663.9 | 3663.9 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 402 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 18 | Mtrs | 345 | 100 | 0 | 0 | 6210 | C+S GST 18% I/P RD | 1117.8 | 7327.8 | 7327.8 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 402 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 40.7934 | Mtrs | 60.5 | 100 | 0 | 0 | 2468 | C+S GST 18% I/P RD | 444.24 | 2912.24 | 2912.24 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 801 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 60.5 | 100 | 0 | 0 | 3388 | C+S GST 18% I/P RD | 609.84 | 3997.84 | 3997.84 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 901 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 60.5 | 100 | 0 | 0 | 3388 | C+S GST 18% I/P RD | 609.84 | 3997.84 | 3997.84 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 401 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 60.5 | 100 | 0 | 0 | 3388 | C+S GST 18% I/P RD | 609.84 | 3997.84 | 3997.84 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 1301 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (M) | 56 | Mtrs | 60.5 | 100 | 0 | 0 | 3388 | C+S GST 18% I/P RD | 609.84 | 3997.84 | 3997.84 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 901 AC Installation & Commissioning | Copper Pipe with Insulation-1.5 Ton (M) | 9 | Mtrs | 345 | 100 | 0 | 0 | 3105 | C+S GST 18% I/P RD | 558.9 | 3663.9 | 3663.9 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 402 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 15.2 | Mtrs | 345 | 100 | 0 | 0 | 5244 | C+S GST 18% I/P RD | 943.92 | 6187.92 | 6187.92 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 1301 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 43.7014 | Mtrs | 345 | 100 | 0 | 0 | 15077 | C+S GST 18% I/P RD | 2713.86 | 17790.86 | 17790.86 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 901 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 40.5014 | Mtrs | 345 | 100 | 0 | 0 | 13973 | C+S GST 18% I/P RD | 2515.14 | 16488.14 | 16488.14 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 531 | 91595 | 21 Sep 2021 | 049/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1063 | Tower B 801 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (M) | 41.8 | Mtrs | 345 | 100 | 0 | 0 | 14421 | C+S GST 18% I/P RD | 2595.78 | 17016.78 | 17016.78 | Approved | 0 | 0 | 0 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 401 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 9 | Mtrs | 105 | 100 | 0 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 402 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 18 | Mtrs | 105 | 100 | 0 | 0 | 1890 | C+S GST 18% I/P RD | 340.2 | 2230.2 | 2230.2 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 901 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 9 | Mtrs | 105 | 100 | 0 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 801 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 9 | Mtrs | 105 | 100 | 0 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 1301 AC Installation & Commissioning | Copper Pipe with Insulation-1.5Ton (L) | 9 | Mtrs | 105 | 100 | 0 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 401 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 19.5 | 100 | 0 | 0 | 1092 | C+S GST 18% I/P RD | 196.56 | 1288.56 | 1288.56 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 1301 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 19.5 | 100 | 0 | 0 | 1092 | C+S GST 18% I/P RD | 196.56 | 1288.56 | 1288.56 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 402 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 40.8205 | Mtrs | 19.5 | 100 | 0 | 0 | 796 | C+S GST 18% I/P RD | 143.28 | 939.28 | 939.28 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 801 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 19.5 | 100 | 0 | 0 | 1092 | C+S GST 18% I/P RD | 196.56 | 1288.56 | 1288.56 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 901 AC Installation & Commissioning | Cable 4C for Indoor to Outdoor (L) | 56 | Mtrs | 19.5 | 100 | 0 | 0 | 1092 | C+S GST 18% I/P RD | 196.56 | 1288.56 | 1288.56 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 401 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 43.4 | Mtrs | 105 | 100 | 0 | 0 | 4557 | C+S GST 18% I/P RD | 820.26 | 5377.26 | 5377.26 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 402 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 15.3048 | Mtrs | 105 | 100 | 0 | 0 | 1607 | C+S GST 18% I/P RD | 289.26 | 1896.26 | 1896.26 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 901 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 40.5048 | Mtrs | 105 | 100 | 0 | 0 | 4253 | C+S GST 18% I/P RD | 765.54 | 5018.54 | 5018.54 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 401 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 36.2857 | Mtrs | 21 | 100 | 0 | 0 | 762 | C+S GST 18% I/P RD | 137.16 | 899.16 | 899.16 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 402 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 23 | Mtrs | 21 | 100 | 0 | 0 | 483 | C+S GST 18% I/P RD | 86.94 | 569.94 | 569.94 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 1301 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 38.8095 | Mtrs | 21 | 100 | 0 | 0 | 815 | C+S GST 18% I/P RD | 146.7 | 961.7 | 961.7 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 801 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 36.5238 | Mtrs | 21 | 100 | 0 | 0 | 767 | C+S GST 18% I/P RD | 138.06 | 905.06 | 905.06 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 901 AC Installation & Commissioning | Drain Pipe with Insulation (L) | 36.2857 | Mtrs | 21 | 100 | 0 | 0 | 762 | C+S GST 18% I/P RD | 137.16 | 899.16 | 899.16 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 1301 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 43.7048 | Mtrs | 105 | 100 | 0 | 0 | 4589 | C+S GST 18% I/P RD | 826.02 | 5415.02 | 5415.02 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 529 | 91594 | 21 Sep 2021 | 048/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1064 | Tower B 801 AC Installation & Commissioning | Copper Pipe with Insulation-2 Ton (L) | 41.8 | Mtrs | 105 | 100 | 0 | 0 | 4389 | C+S GST 18% I/P RD | 790.02 | 5179.02 | 5179.02 | Approved | 0 | 0 | 338 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 604 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 22.5714 | Mtrs | 21 | 100 | 0 | 0 | 474 | C+S GST 18% I/P RD | 85.32 | 559.32 | 559.32 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1703 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 17 | Mtrs | 21 | 100 | 0 | 0 | 357 | C+S GST 18% I/P RD | 64.26 | 421.26 | 421.26 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 903 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 15.8095 | Mtrs | 21 | 100 | 0 | 0 | 332 | C+S GST 18% I/P RD | 59.76 | 391.76 | 391.76 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1704 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.1905 | Mtrs | 21 | 100 | 0 | 0 | 445 | C+S GST 18% I/P RD | 80.1 | 525.1 | 525.1 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1101 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 21.5 | Mtrs | 21 | 100 | 0 | 0 | 451.5 | C+S GST 18% I/P RD | 81.28 | 532.78 | 532.78 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 403 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 11.381 | Mtrs | 21 | 100 | 0 | 0 | 239 | C+S GST 18% I/P RD | 43.02 | 282.02 | 282.02 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 404 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 24.4762 | Mtrs | 21 | 100 | 0 | 0 | 514 | C+S GST 18% I/P RD | 92.52 | 606.52 | 606.52 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 603 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 14.619 | Mtrs | 21 | 100 | 0 | 0 | 307 | C+S GST 18% I/P RD | 55.26 | 362.26 | 362.26 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 404 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 37.0769 | Mtrs | 19.5 | 100 | 0 | 0 | 723 | C+S GST 18% I/P RD | 130.14 | 853.14 | 853.14 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1703 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 31.6923 | Mtrs | 19.5 | 100 | 0 | 0 | 618 | C+S GST 18% I/P RD | 111.24 | 729.24 | 729.24 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 403 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 23.4872 | Mtrs | 19.5 | 100 | 0 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1101 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 46.9231 | Mtrs | 19.5 | 100 | 0 | 0 | 915 | C+S GST 18% I/P RD | 164.7 | 1079.7 | 1079.7 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 903 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 31.6923 | Mtrs | 19.5 | 100 | 0 | 0 | 618 | C+S GST 18% I/P RD | 111.24 | 729.24 | 729.24 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 603 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 29.3333 | Mtrs | 19.5 | 100 | 0 | 0 | 572 | C+S GST 18% I/P RD | 102.96 | 674.96 | 674.96 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1704 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 32.6 | Mtrs | 105 | 100 | 0 | 0 | 3423 | C+S GST 18% I/P RD | 616.14 | 4039.14 | 4039.14 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 603 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 25 | Mtrs | 105 | 100 | 0 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1703 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 26 | Mtrs | 105 | 100 | 0 | 0 | 2730 | C+S GST 18% I/P RD | 491.4 | 3221.4 | 3221.4 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 903 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 21.6 | Mtrs | 105 | 100 | 0 | 0 | 2268 | C+S GST 18% I/P RD | 408.24 | 2676.24 | 2676.24 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 403 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 20.3048 | Mtrs | 105 | 100 | 0 | 0 | 2132 | C+S GST 18% I/P RD | 383.76 | 2515.76 | 2515.76 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1101 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 37.9048 | Mtrs | 105 | 100 | 0 | 0 | 3980 | C+S GST 18% I/P RD | 716.4 | 4696.4 | 4696.4 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 604 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 32.1048 | Mtrs | 105 | 100 | 0 | 0 | 3371 | C+S GST 18% I/P RD | 606.78 | 3977.78 | 3977.78 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 404 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 32 | Mtrs | 105 | 100 | 0 | 0 | 3360 | C+S GST 18% I/P RD | 604.8 | 3964.8 | 3964.8 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 604 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 39.4359 | Mtrs | 19.5 | 100 | 0 | 0 | 769 | C+S GST 18% I/P RD | 138.42 | 907.42 | 907.42 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 532 | 91593 | 21 Sep 2021 | 050/21-22 | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 1062 | A 1704 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 34.1026 | Mtrs | 19.5 | 100 | 0 | 0 | 665 | C+S GST 18% I/P RD | 119.7 | 784.7 | 784.7 | Approved | 0 | 0 | 323 | 21 Sep 2021
GANGA DHAM TOWERS | 1032 | 91579 | 18 Sep 2021 | 91579 | R K INTERIOR | R K INTERIOR | EV - 1092 | DA Development Top Terrace Tiling work | Edge Polish - Dld | 195.35 | R.Ft | 35 | 100 | 170.93 | 0 | 6837.25 | C+S GST 18% I/P RD | 1230.7 | 8067.95 | 8067.95 | Approved | 0 | 0 | 137 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91578 | 18 Sep 2021 | 91578 | R K INTERIOR | R K INTERIOR | EV - 1094 | DA Development Tiling work | Italian Marble Counter - Mkt | 20.49 | R.Ft | 1200 | 100 | 614.7 | 0 | 24588 | C+S GST 18% I/P RD | 4425.84 | 29013.84 | 29013.84 | Approved | 0 | 0 | 964 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91578 | 18 Sep 2021 | 91578 | R K INTERIOR | R K INTERIOR | EV - 1094 | DA Development Tiling work | Italian Marble Dado - BCo | 19.69 | Sq.Ft | 110 | 100 | 54.15 | 0 | 2165.9 | C+S GST 18% I/P RD | 389.86 | 2555.76 | 2555.76 | Approved | 0 | 0 | 964 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91578 | 18 Sep 2021 | 91578 | R K INTERIOR | R K INTERIOR | EV - 1094 | DA Development Tiling work | Zero Point Joint making- AIE | 99.63 | R.Ft | 150 | 100 | 373.61 | 0 | 14944.5 | C+S GST 18% I/P RD | 2690.02 | 17634.52 | 17634.52 | Approved | 0 | 0 | 964 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91578 | 18 Sep 2021 | 91578 | R K INTERIOR | R K INTERIOR | EV - 1094 | DA Development Tiling work | V Groove - AIE | 65.1 | R.Ft | 100 | 100 | 162.75 | 0 | 6510 | C+S GST 18% I/P RD | 1171.8 | 7681.8 | 7681.8 | Approved | 0 | 0 | 964 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91577 | 18 Sep 2021 | 91577 | R K INTERIOR | R K INTERIOR | EV - 1091 | DA Development Top Terrace Tiling work | Jaisalmer Skirting Mirror Polish | 76.14 | R.Ft | 65 | 100 | 123.73 | 0 | 4949.1 | C+S GST 18% I/P RD | 890.84 | 5839.94 | 5839.94 | Approved | 0 | 0 | 380 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91577 | 18 Sep 2021 | 91577 | R K INTERIOR | R K INTERIOR | EV - 1091 | DA Development Top Terrace Tiling work | Jaisalmer Skirting Mirror Polish | 216 | R.Ft | 65 | 100 | 351 | 0 | 14040 | C+S GST 18% I/P RD | 2527.2 | 16567.2 | 16567.2 | Approved | 0 | 0 | 380 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Edge Polish - Dld | 110.99 | R.Ft | 25 | 100 | 69.37 | 0 | 2774.75 | C+S GST 18% I/P RD | 499.46 | 3274.21 | 3274.21 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Vitrified Tile Border | 7.25 | R.Ft | 30 | 100 | 5.44 | 0 | 217.5 | C+S GST 18% I/P RD | 39.16 | 256.66 | 256.66 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Vitrified Flooring -Bco | 15.23 | Sq.Ft | 40 | 100 | 15.23 | 0 | 609.2 | C+S GST 18% I/P RD | 109.66 | 718.86 | 718.86 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Italian Marble Border-BCo | 12.74 | R.Ft | 100 | 100 | 31.85 | 0 | 1274 | C+S GST 18% I/P RD | 229.32 | 1503.32 | 1503.32 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Italian Marble Border-BCo | 64.13 | R.Ft | 100 | 100 | 160.33 | 0 | 6413 | C+S GST 18% I/P RD | 1154.34 | 7567.34 | 7567.34 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Granite Counter-cc | 23.17 | R.Ft | 800 | 100 | 463.4 | 0 | 18536 | C+S GST 18% I/P RD | 3336.48 | 21872.48 | 21872.48 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | V Groove - AIE | 9 | R.Ft | 100 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Zero Point Joint making- AIE | 45.7 | R.Ft | 150 | 100 | 171.38 | 0 | 6855 | C+S GST 18% I/P RD | 1233.9 | 8088.9 | 8088.9 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Vitrified Skirting work | 13.98 | R.Ft | 40 | 100 | 13.98 | 0 | 559.2 | C+S GST 18% I/P RD | 100.66 | 659.86 | 659.86 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Granite Border-BCo | 43.92 | R.Ft | 60 | 100 | 65.88 | 0 | 2635.2 | C+S GST 18% I/P RD | 474.34 | 3109.54 | 3109.54 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Italian Marble Skirting -BCV | 12.65 | R.Ft | 100 | 100 | 31.63 | 0 | 1265 | C+S GST 18% I/P RD | 227.7 | 1492.7 | 1492.7 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Acid Wash | 223.75 | Sq.Ft | 10 | 100 | 55.94 | 0 | 2237.5 | C+S GST 18% I/P RD | 402.76 | 2640.26 | 2640.26 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Dado BC | 58.81 | Sq.Ft | 50 | 100 | 73.51 | 0 | 2940.5 | C+S GST 18% I/P RD | 529.3 | 3469.8 | 3469.8 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Italian Marble Top - AIE | 7.45 | R.Ft | 100 | 100 | 18.63 | 0 | 745 | C+S GST 18% I/P RD | 134.1 | 879.1 | 879.1 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Drill Hole-AIE | 3 | No. | 50 | 100 | 3.75 | 0 | 150 | C+S GST 18% I/P RD | 27 | 177 | 177 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Granite Dado Work - DSP | 5.76 | Sq.Ft | 60 | 100 | 8.64 | 0 | 345.6 | C+S GST 18% I/P RD | 62.2 | 407.8 | 407.8 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Vitrified Tile Counter | 29.69 | Sq.Ft | 40 | 100 | 29.69 | 0 | 1187.6 | C+S GST 18% I/P RD | 213.76 | 1401.36 | 1401.36 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | C Groove- BCo | 16.5 | R.Ft | 100 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Bull Nosing / Moulding | 54.64 | R.Ft | 85 | 100 | 116.11 | 0 | 4644.4 | C+S GST 18% I/P RD | 836 | 5480.4 | 5480.4 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Vitrified Tile Border | 114.22 | R.Ft | 40 | 100 | 114.22 | 0 | 4568.8 | C+S GST 18% I/P RD | 822.38 | 5391.18 | 5391.18 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Vitrified Tile Border | 110.86 | R.Ft | 40 | 100 | 110.86 | 0 | 4434.4 | C+S GST 18% I/P RD | 798.2 | 5232.6 | 5232.6 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Dado BC | 46.47 | Sq.Ft | 50 | 100 | 58.09 | 0 | 2323.5 | C+S GST 18% I/P RD | 418.24 | 2741.74 | 2741.74 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Demolition Work - Mkt | 96.61 | Sq.Ft | 10 | 100 | 24.15 | 0 | 966.1 | C+S GST 18% I/P RD | 173.9 | 1140 | 1140 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Granite Buffing | 117.41 | Sq.Ft | 20 | 100 | 58.71 | 0 | 2348.2 | C+S GST 18% I/P RD | 422.68 | 2770.88 | 2770.88 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Italian Marble Mirror Polish - AIE | 23.32 | Sq.Ft | 40 | 100 | 23.32 | 0 | 932.8 | C+S GST 18% I/P RD | 167.9 | 1100.7 | 1100.7 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 485 | 91576 | 18 Sep 2021 | 91576 | R K INTERIOR | R K INTERIOR | EV - 1093 | DA Development Tiling work | Champher Polish- Dld | 29.82 | R.Ft | 60 | 100 | 44.73 | 0 | 1789.2 | C+S GST 18% I/P RD | 322.06 | 2111.26 | 2111.26 | Approved | 0 | 0 | 1466 | 18 Sep 2021
GANGA DHAM TOWERS | 471 | 91568 | 17 Sep 2021 |  | SHIV SHAMBHO FABRICATION | SAURABH FABRICATION |  | Tower B- Lift Duct Temporary Door MS Work (30 Floors) | Hold Fast fixing- BCo | 95 | No. | 10 | 100 | 0 | 0 | 950 | CGST 0% URD I/P | 0 | 950 | 950 |  | 0 | 0 | 60 | 17 Sep 2021
GANGA DHAM TOWERS | 471 | 91568 | 17 Sep 2021 |  | SHIV SHAMBHO FABRICATION | SAURABH FABRICATION |  | Tower B- Lift Duct Temporary Door MS Work (30 Floors) | Fabrication Work-(L) | 340.5926 | Kgs | 13.5 | 100 | 114.95 | 0 | 4598 | CGST 0% URD I/P | 0 | 4598 | 4598 |  | 0 | 0 | 60 | 17 Sep 2021
GANGA DHAM TOWERS | 471 | 91568 | 17 Sep 2021 |  | SHIV SHAMBHO FABRICATION | SAURABH FABRICATION |  | Tower B- Lift Duct Temporary Door MS Work (30 Floors) | Nails- BC | 100 | No. | 5 | 100 | 0 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 |  | 0 | 0 | 60 | 17 Sep 2021
GANGA DHAM TOWERS | 985 | 91567 | 17 Sep 2021 | ma/g/21-22/314 | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 1076 | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 | Approved | 0 | 0 | 168 | 17 Sep 2021
GANGA DHAM TOWERS | 985 | 91567 | 17 Sep 2021 | ma/g/21-22/314 | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 1076 | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 | Approved | 0 | 0 | 168 | 17 Sep 2021
GANGA DHAM TOWERS | 985 | 91567 | 17 Sep 2021 | ma/g/21-22/314 | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 1076 | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 | Approved | 0 | 0 | 168 | 17 Sep 2021
GANGA DHAM TOWERS | 985 | 91567 | 17 Sep 2021 | ma/g/21-22/314 | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 1076 | Sales Office AMC Charges (L) | VRF System AMC Charges | 18 | Hp | 2800 | 8.33 | 0 | 0 | 4200.03 | C+S GST 18% I/P RD | 756 | 4956.03 | 4956.03 | Approved | 0 | 0 | 168 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 1001 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 704 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 803 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 2 | No. | 400 | 100 | 20 | 0 | 800 | C+S GST 18% I/P RD | 144 | 944 | 944 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 703 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 802 (Refuge) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 0.5 | No. | 400 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 904 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 1002 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 805 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 2.5 | No. | 400 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 901 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 902 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 1003 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 701 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 702 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 705 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 1005 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 903 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 905 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 1004 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 4 | No. | 400 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 605 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 5 | No. | 400 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 804 (1bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 2 | No. | 400 | 100 | 20 | 0 | 800 | C+S GST 18% I/P RD | 144 | 944 | 944 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 759 | 91566 | 17 Sep 2021 | 222 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1029 | D 801 (2bhk) Doors Frame, Shutter & Fittings | RCC Door frame fixing | 2.5 | No. | 400 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 322 | 17 Sep 2021
GANGA DHAM TOWERS | 1002 | 91565 | 17 Sep 2021 | 13 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1096 | B 2002 NOC | Concrete Cutting Work | 123.981 | R.Ft | 525 | 100 | 1627.25 | 0 | 65090.01 | C+S GST 18% I/P RD | 11716.2 | 76806.21 | 76806.21 | Approved | 0 | 0 | 10863 | 17 Sep 2021
GANGA DHAM TOWERS | 1002 | 91565 | 17 Sep 2021 | 13 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1096 | B 602 NOC | Concrete Cutting Work | 8.101 | R.Ft | 525 | 100 | 106.33 | 0 | 4253 | C+S GST 18% I/P RD | 765.54 | 5018.54 | 5018.54 | Approved | 0 | 0 | 10863 | 17 Sep 2021
GANGA DHAM TOWERS | 1002 | 91565 | 17 Sep 2021 | 13 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1096 | B 501 NOC | Concrete Cutting Work | 773.0133 | R.Ft | 525 | 100 | 10145.8 | 0 | 405832 | C+S GST 18% I/P RD | 73049.76 | 478881.76 | 478881.76 | Approved | 0 | 0 | 10863 | 17 Sep 2021
GANGA DHAM TOWERS | 1002 | 91565 | 17 Sep 2021 | 13 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1096 | B 501 NOC | Concrete wall Crushing work | 8.18 | Cu.Mtrs | 7200 | 100 | 1472.4 | 0 | 58896 | C+S GST 18% I/P RD | 10601.28 | 69497.28 | 69497.28 | Approved | 0 | 0 | 10863 | 17 Sep 2021
GANGA DHAM TOWERS | 1002 | 91565 | 17 Sep 2021 | 13 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1096 | B 2002 NOC | Concrete wall Crushing work | 1.0769 | Cu.Mtrs | 7200 | 100 | 193.84 | 0 | 7754 | C+S GST 18% I/P RD | 1395.72 | 9149.72 | 9149.72 | Approved | 0 | 0 | 10863 | 17 Sep 2021
GANGA DHAM TOWERS | 1002 | 91565 | 17 Sep 2021 | 13 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1096 | B 602 NOC | Concrete wall Crushing work | 0.1831 | Cu.Mtrs | 7200 | 100 | 32.96 | 0 | 1318 | C+S GST 18% I/P RD | 237.24 | 1555.24 | 1555.24 | Approved | 0 | 0 | 10863 | 17 Sep 2021
GANGA DHAM TOWERS | 1002 | 91558 | 16 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 956 | B 1201 NOC | Concrete Cutting Work | 21.2381 | R.Ft | 525 | 100 | 278.75 | 0 | 11150 | CGST 0% URD I/P | 0 | 11150 | 11150 | Approved | 0 | 0 | 212 | 16 Sep 2021
GANGA DHAM TOWERS | 1002 | 91558 | 16 Sep 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 956 | B 601 NOC | Concrete Cutting Work | 19.0476 | R.Ft | 525 | 100 | 250 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 212 | 16 Sep 2021
GANGA DHAM TOWERS | 497 | 91557 | 16 Sep 2021 | 57 | J K INTERIOR | J K INTERIOR | EV - 1044 | B 2202 Gypsum Plaster | Gypsum on Wall (L) | 3581 | Sq.Ft | 4 | 100 | 358.1 | 0 | 14324 | C+S GST 18% I/P RD | 2578.32 | 16902.32 | 16902.32 | Approved | 0 | 0 | 193 | 16 Sep 2021
GANGA DHAM TOWERS | 497 | 91557 | 16 Sep 2021 | 57 | J K INTERIOR | J K INTERIOR | EV - 1044 | B 2202 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 193 | 16 Sep 2021
GANGA DHAM TOWERS | 371 | 91553 | 15 Sep 2021 | 23 | CONSTROGENESIS | CONSTROGENESIS | EV - 1036 | EWS Bldg RCC 3rd Slab Built-up Area (L) | Schedule & Quality | 2338 | Sq.Ft | 2.5 | 100 | 146.13 | 0 | 5845 | C+S GST 18% I/P RD | 1052.1 | 6897.1 | 6897.1 | Approved | 0 | 0 | 378 | 15 Sep 2021
GANGA DHAM TOWERS | 371 | 91553 | 15 Sep 2021 | 23 | CONSTROGENESIS | CONSTROGENESIS | EV - 1036 | EWS Bldg RCC 5th Slab Built-up Area (L) | Schedule & Quality | 1800 | Sq.Ft | 2.5 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 378 | 15 Sep 2021
GANGA DHAM TOWERS | 371 | 91553 | 15 Sep 2021 | 23 | CONSTROGENESIS | CONSTROGENESIS | EV - 1036 | EWS Bldg RCC 6th Slab Built-up Area (L) | Schedule & Quality | 3419.15 | Sq.Ft | 2.5 | 100 | 213.7 | 0 | 8547.88 | C+S GST 18% I/P RD | 1538.62 | 10086.5 | 10086.5 | Approved | 0 | 0 | 378 | 15 Sep 2021
GANGA DHAM TOWERS | 797 | 91544 | 15 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN |  | D Main St.case Wall Gyp. Plaster 2nd to 3rd Fl. | Tikki Dhada (L) | 418.62 | Sq.Ft | 9 | 100 | 94.19 | 0 | 3767.58 | CGST 0% URD I/P | 0 | 3767.58 | 3767.58 |  | 0 | 0 | 75 | 15 Sep 2021
GANGA DHAM TOWERS | 797 | 91544 | 15 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN |  | D Main St.case Wall Gyp. Plaster 1st to 2nd Fl. | Tikki Dhada (L) | 418 | Sq.Ft | 9 | 100 | 94.05 | 0 | 3762 | CGST 0% URD I/P | 0 | 3762 | 3762 |  | 0 | 0 | 75 | 15 Sep 2021
GANGA DHAM TOWERS | 395 | 91538 | 14 Sep 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1396 | A Bldg Flat No. 2204 Gypsum Plaster | Gypsum on Wall (L) | 2690 | Sq.Ft | 4 | 100 | 269 | 0 | 10760 | C+S GST 18% I/P RD | 1936.8 | 12696.8 | 12696.8 | Approved | 0 | 0 | 108 | 14 Sep 2021
GANGA DHAM TOWERS | 1149 | 91516 | 14 Sep 2021 | 359 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 957 | Internal False Ceiling | Gypsum Board False Ceiling (M+L) | 290.99 | Sq.Ft | 75 | 100 | 545.61 | 0 | 21824.25 | C+S GST 18% I/P RD | 3928.36 | 25752.61 | 25752.61 | Approved | 0 | 0 | 343 | 14 Sep 2021
GANGA DHAM TOWERS | 1149 | 91516 | 14 Sep 2021 | 359 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 957 | Internal False Ceiling | Armstrong False Ceiling (L+M) - Sq.Ft | 96 | Sq.Ft | 125 | 100 | 300 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 343 | 14 Sep 2021
GANGA DHAM TOWERS | 1149 | 91516 | 14 Sep 2021 | 359 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 957 | Internal False Ceiling | Gala Cutting | 8 | No. | 60 | 100 | 12 | 0 | 480 | C+S GST 18% I/P RD | 86.4 | 566.4 | 566.4 | Approved | 0 | 0 | 343 | 14 Sep 2021
GANGA DHAM TOWERS | 1152 | 91514 | 14 Sep 2021 | 22 | CONSTROGENESIS | CONSTROGENESIS | EV - 1038 | D Rcc Work & Material Shifting | Material Shifting | 1768.7 | Sq.Ft | 25 | 100 | 1105.44 | 0 | 44217.5 | C+S GST 18% I/P RD | 7959.16 | 52176.66 | 52176.66 | Approved | 0 | 0 | 4384 | 14 Sep 2021
GANGA DHAM TOWERS | 1152 | 91514 | 14 Sep 2021 | 22 | CONSTROGENESIS | CONSTROGENESIS | EV - 1038 | D Rcc Work & Material Shifting | RCC Work -Dld | 1 | No. | 175000 | 100 | 4375 | 0 | 175000 | C+S GST 18% I/P RD | 31500 | 206500 | 206500 | Approved | 0 | 0 | 4384 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 902 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 903 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 105 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 502 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 401 Rough Plaster | Rough Plaster | 100 | Sq.Ft | 15 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 505 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 201 Rough Plaster | Rough Plaster | 100 | Sq.Ft | 15 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 702 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 901 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 703 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 602 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 203 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 601 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 905 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 405 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 801 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 205 Rough Plaster | Rough Plaster | 100 | Sq.Ft | 15 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 504 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 402 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 704 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 102 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 204 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 1001 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 1005 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 501 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 605 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 101 Rough Plaster | Rough Plaster | 100 | Sq.Ft | 15 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 202 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 104 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 805 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 301 Rough Plaster | Rough Plaster | 100 | Sq.Ft | 15 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 303 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 803 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 1002 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 1004 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 103 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 305 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 604 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 701 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 302 Rough Plaster | Rough Plaster | 48.14 | Sq.Ft | 15 | 100 | 18.05 | 0 | 722.1 | C+S GST 18% I/P RD | 129.98 | 852.08 | 852.08 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 804 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 1003 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 503 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 603 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 403 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 404 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 705 Rough Plaster | Rough Plaster | 121.14 | Sq.Ft | 15 | 100 | 45.43 | 0 | 1817.1 | C+S GST 18% I/P RD | 327.08 | 2144.18 | 2144.18 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 492 | 91513 | 14 Sep 2021 | 223 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1030 | D Building 904 Rough Plaster | Rough Plaster | 76.85 | Sq.Ft | 15 | 100 | 28.82 | 0 | 1152.75 | C+S GST 18% I/P RD | 207.5 | 1360.25 | 1360.25 | Approved | 0 | 0 | 632 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.501 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.503 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.504 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.502 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.505 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.101 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.204 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.203 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.403 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.201 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.105 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.102 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.401 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.404 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.301 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.402 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.302 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.103 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.304 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.405 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.104 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.303 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.202 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.205 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 452 | 91512 | 14 Sep 2021 | 205 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1042 | D Bldg Flat No.305 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 26 | 14 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 203 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 23237 | 40 | 185.9 | 0 | 7435.84 | C+S GST 18% I/P RD | 1338.46 | 8774.3 | 8774.3 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 1402 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 1702 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 1002 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 1602 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 1302 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 202 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 402 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1118 | 91506 | 13 Sep 2021 | 16 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 919 | A 504 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 0 | 740 | 13 Sep 2021
GANGA DHAM TOWERS | 1131 | 91505 | 13 Sep 2021 | 358 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 955 | A 304 Sample Flat Rectification in Gypsum False Ceiling | Gypsum False Ceiling removing-BC | 445.65 | Sq.Ft | 10 | 100 | 111.41 | 0 | 4456.5 | C+S GST 18% I/P RD | 802.18 | 5258.68 | 5258.68 | Approved | 0 | 0 | 334 | 13 Sep 2021
GANGA DHAM TOWERS | 1131 | 91505 | 13 Sep 2021 | 358 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 955 | A 304 Sample Flat Rectification in Gypsum False Ceiling | Gypsum False Ceiling Fixing | 445.65 | R.Ft | 65 | 100 | 724.18 | 0 | 28967.25 | C+S GST 18% I/P RD | 5214.1 | 34181.35 | 34181.35 | Approved | 0 | 0 | 334 | 13 Sep 2021
GANGA DHAM TOWERS | 1032 | 91504 | 13 Sep 2021 |  | R K INTERIOR | R K INTERIOR |  | DA Development Top Terrace Tiling work | Vitrified Flooring work | 44.45 | Sq.Ft | 35 | 100 | 38.89 | 0 | 1555.75 | C+S GST 18% I/P RD | 280.04 | 1835.79 | 1835.79 |  | 0 | 0 | 31 | 13 Sep 2021
GANGA DHAM TOWERS | 1153 | 91498 | 11 Sep 2021 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 886 | MEDIA Flex printing | Eco Vinyal With Foam Sheet | 130 | Sq.Ft | 95 | 100 | 0 | 0 | 12350 | C+S GST 18% I/P RD | 2223 | 14573 | 14573 | Approved | 0 | 0 | 1193 | 11 Sep 2021
GANGA DHAM TOWERS | 1153 | 91498 | 11 Sep 2021 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 886 | MEDIA Flex printing | Flex Printing & Pasting | 2255 | Sq.Ft | 19 | 100 | 0 | 0 | 42845 | C+S GST 18% I/P RD | 7712.1 | 50557.1 | 50557.1 | Approved | 0 | 0 | 1193 | 11 Sep 2021
GANGA DHAM TOWERS | 1153 | 91498 | 11 Sep 2021 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 886 | MEDIA Flex printing | print | 0.8944 | No. | 5000 | 100 | 0 | 0 | 4472 | C+S GST 18% I/P RD | 804.96 | 5276.96 | 5276.96 | Approved | 0 | 0 | 1193 | 11 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 1501 Walls Satin Matt Paint | Scrapping with 1st Coat Putty | 2429.024 | Sq.Ft | 1.25 | 100 | 75.91 | 0 | 3036.28 | IGST 18% I/P RD | 546.53 | 3582.81 | 3582.81 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 1402 Walls Satin Matt Painting | Oil base Primer-BC | 2351.52 | Sq.Ft | 1 | 100 | 58.79 | 0 | 2351.52 | IGST 18% I/P RD | 423.27 | 2774.79 | 2774.79 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 602 Walls Satin Matt Painting | Oil base Primer-BC | 2351.52 | Sq.Ft | 1 | 100 | 58.79 | 0 | 2351.52 | IGST 18% I/P RD | 423.27 | 2774.79 | 2774.79 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 604 Walls Satin Matt Painting | Oil base Primer-BC | 2219.776 | Sq.Ft | 1 | 100 | 55.49 | 0 | 2219.78 | IGST 18% I/P RD | 399.56 | 2619.34 | 2619.34 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 1501 Walls Satin Matt Paint | Oil base Primer-BC | 2429.024 | Sq.Ft | 1 | 100 | 60.73 | 0 | 2429.02 | IGST 18% I/P RD | 437.22 | 2866.24 | 2866.24 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 403 Walls Satin Matt Painting | Oil base Primer-BC | 2209.92 | Sq.Ft | 1 | 100 | 55.25 | 0 | 2209.92 | IGST 18% I/P RD | 397.79 | 2607.71 | 2607.71 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 603 Walls Satin Matt Painting | Oil base Primer-BC | 2209.92 | Sq.Ft | 1 | 100 | 55.25 | 0 | 2209.92 | IGST 18% I/P RD | 397.79 | 2607.71 | 2607.71 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 903 Walls Satin Matt Painting | Oil base Primer-BC | 2209.92 | Sq.Ft | 1 | 100 | 55.25 | 0 | 2209.92 | IGST 18% I/P RD | 397.79 | 2607.71 | 2607.71 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 601 Walls Satin Matt Paint | Oil base Primer-BC | 2429.024 | Sq.Ft | 1 | 100 | 60.73 | 0 | 2429.02 | IGST 18% I/P RD | 437.22 | 2866.24 | 2866.24 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 1113 | 91473 | 09 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1216 | A 1701 Walls Satin Matt Paint | Oil base Primer-BC | 2429.024 | Sq.Ft | 1 | 100 | 60.73 | 0 | 2429.02 | IGST 18% I/P RD | 437.22 | 2866.24 | 2866.24 | Approved | 0 | 0 | 239 | 09 Sep 2021
GANGA DHAM TOWERS | 389 | 91472 | 09 Sep 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 875 | Loading / Unloading Expenses | Unloading of tiles. | 15.5 | Metric Tonnes | 130 | 100 | 0 | 0 | 2015 | CGST 0% URD I/P | 0 | 2015 | 2015 | Approved | 0 | 0 | 0 | 09 Sep 2021
GANGA DHAM TOWERS | 389 | 91472 | 09 Sep 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 875 | Loading / Unloading Expenses | Unloading of tiles. | 13.5 | Metric Tonnes | 130 | 100 | 0 | 0 | 1755 | CGST 0% URD I/P | 0 | 1755 | 1755 | Approved | 0 | 0 | 0 | 09 Sep 2021
GANGA DHAM TOWERS | 389 | 91472 | 09 Sep 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 875 | Loading / Unloading Expenses | Unloading of tiles. | 5 | Metric Tonnes | 130 | 100 | 0 | 0 | 650 | CGST 0% URD I/P | 0 | 650 | 650 | Approved | 0 | 0 | 0 | 09 Sep 2021
GANGA DHAM TOWERS | 389 | 91472 | 09 Sep 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 875 | Loading / Unloading Expenses | Unloading of tiles. | 17 | Metric Tonnes | 260 | 100 | 0 | 0 | 4420 | CGST 0% URD I/P | 0 | 4420 | 4420 | Approved | 0 | 0 | 0 | 09 Sep 2021
GANGA DHAM TOWERS | 1037 | 91471 | 09 Sep 2021 | om/2021-22/30 | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 865 | Head Office Security Service | Security Guard AIE - | 62 | Day | 419.35 | 100 | 0 | 0 | 25999.7 | C+S GST 18% RCM | 4679.94 | 30679.64 | 30679.64 | Approved | 0 | 0 | 260 | 09 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.902 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.802 Refuge Flat Electrical | 6 AMP Plug point (Dependent) | 1 | No. | 67 | 20 | 0.34 | 0 | 13.4 | C+S GST 18% I/P RD | 2.42 | 15.82 | 15.82 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.605 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.902 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.505 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.603 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.702 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.703 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.602 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.801 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.601 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.704 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.803 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.905 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.705 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.804 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.805 Electrical Work | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.903 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.604 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.904 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.701 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.901 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.904 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.505 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 452 | 91449 | 08 Sep 2021 | 204 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1007 | D Bldg Flat No.805 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 32 | 08 Sep 2021
GANGA DHAM TOWERS | 797 | 91448 | 08 Sep 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 948 | D 9th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 493.16 | Sq.Ft | 9 | 100 | 110.96 | 0 | 4438.44 | CGST 0% URD I/P | 0 | 4438.44 | 4438.44 | Approved | 0 | 0 | 44 | 08 Sep 2021
GANGA DHAM TOWERS | 698 | 91447 | 08 Sep 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 959 | D 905 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.072 | Sq.Ft | 9 | 100 | 206.12 | 0 | 8244.65 | CGST 0% URD I/P | 0 | 8244.65 | 8244.65 | Approved | 0 | 0 | 489 | 08 Sep 2021
GANGA DHAM TOWERS | 698 | 91447 | 08 Sep 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 959 | D 901 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.072 | Sq.Ft | 9 | 100 | 206.12 | 0 | 8244.65 | CGST 0% URD I/P | 0 | 8244.65 | 8244.65 | Approved | 0 | 0 | 489 | 08 Sep 2021
GANGA DHAM TOWERS | 698 | 91447 | 08 Sep 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 959 | D 904 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.328 | Sq.Ft | 9 | 100 | 142.72 | 0 | 5708.95 | CGST 0% URD I/P | 0 | 5708.95 | 5708.95 | Approved | 0 | 0 | 489 | 08 Sep 2021
GANGA DHAM TOWERS | 698 | 91447 | 08 Sep 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 959 | D 705 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 916.072 | Sq.Ft | 9 | 100 | 206.12 | 0 | 8244.65 | CGST 0% URD I/P | 0 | 8244.65 | 8244.65 | Approved | 0 | 0 | 489 | 08 Sep 2021
GANGA DHAM TOWERS | 698 | 91447 | 08 Sep 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 959 | D 903 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.328 | Sq.Ft | 9 | 100 | 142.72 | 0 | 5708.95 | CGST 0% URD I/P | 0 | 5708.95 | 5708.95 | Approved | 0 | 0 | 489 | 08 Sep 2021
GANGA DHAM TOWERS | 698 | 91447 | 08 Sep 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 959 | D 902 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 783.376 | Sq.Ft | 9 | 100 | 176.26 | 0 | 7050.38 | CGST 0% URD I/P | 0 | 7050.38 | 7050.38 | Approved | 0 | 0 | 489 | 08 Sep 2021
GANGA DHAM TOWERS | 698 | 91447 | 08 Sep 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 959 | D 704 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.328 | Sq.Ft | 9 | 100 | 142.72 | 0 | 5708.95 | CGST 0% URD I/P | 0 | 5708.95 | 5708.95 | Approved | 0 | 0 | 489 | 08 Sep 2021
GANGA DHAM TOWERS | 1114 | 91438 | 07 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1218 | B 901 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 4540.16 | Sq.Ft | 1.25 | 100 | 141.88 | 0 | 5675.2 | IGST 18% I/P RD | 1021.54 | 6696.74 | 6696.74 | Approved | 0 | 0 | 310 | 07 Sep 2021
GANGA DHAM TOWERS | 1114 | 91438 | 07 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1218 | B 1401 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 4540.16 | Sq.Ft | 1.25 | 100 | 141.88 | 0 | 5675.2 | IGST 18% I/P RD | 1021.54 | 6696.74 | 6696.74 | Approved | 0 | 0 | 310 | 07 Sep 2021
GANGA DHAM TOWERS | 1114 | 91438 | 07 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1218 | B 1002 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 3115.864 | Sq.Ft | 1.25 | 100 | 97.37 | 0 | 3894.83 | IGST 18% I/P RD | 701.07 | 4595.9 | 4595.9 | Approved | 0 | 0 | 310 | 07 Sep 2021
GANGA DHAM TOWERS | 1114 | 91438 | 07 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1218 | B 1301 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 4540.16 | Sq.Ft | 1.25 | 100 | 141.88 | 0 | 5675.2 | IGST 18% I/P RD | 1021.54 | 6696.74 | 6696.74 | Approved | 0 | 0 | 310 | 07 Sep 2021
GANGA DHAM TOWERS | 1114 | 91438 | 07 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1218 | B 902 Walls Satin Matt Painting | Oil base Primer-BC | 3115.84 | Sq.Ft | 1 | 100 | 77.9 | 0 | 3115.84 | IGST 18% I/P RD | 560.85 | 3676.69 | 3676.69 | Approved | 0 | 0 | 310 | 07 Sep 2021
GANGA DHAM TOWERS | 1114 | 91438 | 07 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1218 | B 402 Walls Satin Matt Painting | Oil base Primer-BC | 3116 | Sq.Ft | 1 | 100 | 77.9 | 0 | 3116 | IGST 18% I/P RD | 560.88 | 3676.88 | 3676.88 | Approved | 0 | 0 | 310 | 07 Sep 2021
GANGA DHAM TOWERS | 1114 | 91438 | 07 Sep 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 1218 | B 902 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 3115.864 | Sq.Ft | 1.25 | 100 | 97.37 | 0 | 3894.83 | IGST 18% I/P RD | 701.07 | 4595.9 | 4595.9 | Approved | 0 | 0 | 310 | 07 Sep 2021
GANGA DHAM TOWERS | 149 | 91436 | 07 Sep 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 873 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3333 | No. | 4 | 100 | 0 | 0 | 13332 | CGST 0% URD I/P | 0 | 13332 | 13332 | Approved | 0 | 0 | 0 | 07 Sep 2021
GANGA DHAM TOWERS | 413 | 91432 | 04 Sep 2021 | 631 | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 976 | Sales Oiifce Landscape Area . | Supervision Charges | 0.75 | Month | 4000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 300 | 04 Sep 2021
GANGA DHAM TOWERS | 178 | 91431 | 04 Sep 2021 | 630 | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 975 | Sales Oiifce Landscape Area . | Garden work. | 87.9966 | Day | 407.25 | 100 | 0 | 0 | 35836.62 | C+S GST 18% I/P RD | 6450.6 | 42287.22 | 42287.22 | Approved | 0 | 0 | 358 | 04 Sep 2021
GANGA DHAM TOWERS | 372 | 91424 | 04 Sep 2021 | 168 | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 958 | B Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 107.1429 | Sq.Ft | 140 | 100 | 0 | 0 | 15000 | IGST 18% I/P RD | 2700 | 17700 | 17700 | Approved | 0 | 0 | 507 | 04 Sep 2021
GANGA DHAM TOWERS | 372 | 91424 | 04 Sep 2021 | 168 | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 958 | B Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 104.3667 | Sq.Ft | 150 | 100 | 0 | 0 | 15655.01 | IGST 18% I/P RD | 2817.9 | 18472.91 | 18472.91 | Approved | 0 | 0 | 507 | 04 Sep 2021
GANGA DHAM TOWERS | 372 | 91424 | 04 Sep 2021 | 168 | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 958 | B Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 71.4286 | Sq.Ft | 140 | 100 | 0 | 0 | 10000 | IGST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 507 | 04 Sep 2021
GANGA DHAM TOWERS | 372 | 91424 | 04 Sep 2021 | 168 | B & B ENTERPRISES | SAI NIRMAL COLOURS & TEXTURES | EV - 958 | B Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 71.4286 | Sq.Ft | 140 | 100 | 0 | 0 | 10000 | IGST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 507 | 04 Sep 2021
GANGA DHAM TOWERS | 932 | 91423 | 04 Sep 2021 | 228 | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 863 | Podium P4 RCC Slab Pumping Charges | Pumping Charges-BC | 495 | Cu.Mtrs | 190 | 100 | 0 | 0 | 94050 | C+S GST 18% I/P RD | 16929 | 110979 | 110979 | Approved | 0 | 0 | 2871 | 04 Sep 2021
GANGA DHAM TOWERS | 932 | 91423 | 04 Sep 2021 | 228 | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 863 | Pumping Charges P3 Floor Pumping Charges | Pumping Charges-BC | 232.5105 | Cu.Mtrs | 190 | 100 | 0 | 0 | 44177 | C+S GST 18% I/P RD | 7951.86 | 52128.86 | 52128.86 | Approved | 0 | 0 | 2871 | 04 Sep 2021
GANGA DHAM TOWERS | 932 | 91423 | 04 Sep 2021 | 228 | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 863 | Podium P3 RCC Slab Pumping Charges | Pumping Charges-BC | 28 | Cu.Mtrs | 190 | 100 | 0 | 0 | 5320 | C+S GST 18% I/P RD | 957.6 | 6277.6 | 6277.6 | Approved | 0 | 0 | 2871 | 04 Sep 2021
GANGA DHAM TOWERS | 1080 | 91422 | 04 Sep 2021 | 229 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 864 | B P3 Floor Trimix Pumping Charges | Pumping Charges-BC | 220.48 | Cu.Mtrs | 190 | 100 | 0 | 0 | 41891.2 | C+S GST 18% I/P RD | 7540.42 | 49431.62 | 49431.62 | Approved | 0 | 0 | 838 | 04 Sep 2021
GANGA DHAM TOWERS | 187 | 91421 | 04 Sep 2021 | 64 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 835 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 04 Sep 2021
GANGA DHAM TOWERS | 742 | 91420 | 04 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 836 | A P2 Parking Ghadai & chemical grouting | Chemical Grouting (L) | 1056 | Sq.Ft | 1 | 100 | 26.4 | 0 | 1056 | CGST 0% URD I/P | 0 | 1056 | 1056 | Approved | 0 | 0 | 218 | 04 Sep 2021
GANGA DHAM TOWERS | 742 | 91420 | 04 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 836 | A P3 Parking Ghadai & chemical grouting | Chemical Grouting (L) | 9828 | Sq.Ft | 1 | 100 | 245.7 | 0 | 9828 | CGST 0% URD I/P | 0 | 9828 | 9828 | Approved | 0 | 0 | 218 | 04 Sep 2021
GANGA DHAM TOWERS | 742 | 91420 | 04 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 836 | A P2 Parking Ghadai & chemical grouting | Ghadai work- BCP | 1056 | Sq.Ft | 1 | 100 | 26.4 | 0 | 1056 | CGST 0% URD I/P | 0 | 1056 | 1056 | Approved | 0 | 0 | 218 | 04 Sep 2021
GANGA DHAM TOWERS | 742 | 91420 | 04 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 836 | A P3 Parking Ghadai & chemical grouting | Ghadai work- BCP | 9828 | Sq.Ft | 1 | 100 | 245.7 | 0 | 9828 | CGST 0% URD I/P | 0 | 9828 | 9828 | Approved | 0 | 0 | 218 | 04 Sep 2021
GANGA DHAM TOWERS | 745 | 91419 | 04 Sep 2021 | 72 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1060 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 29.45 | Day | 451.61 | 100 | 0 | 0 | 13299.91 | C+S GST 18% I/P RD | 2393.98 | 15693.89 | 15693.89 | Approved | 0 | 0 | 133 | 04 Sep 2021
GANGA DHAM TOWERS | 480 | 91418 | 04 Sep 2021 | 71 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1011 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 31 | Day | 451.61 | 100 | 0 | 0 | 13999.91 | C+S GST 18% I/P RD | 2519.98 | 16519.89 | 16519.89 | Approved | 0 | 0 | 140 | 04 Sep 2021
GANGA DHAM TOWERS | 1079 | 91417 | 04 Sep 2021 | 228 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 862 | A P3 Trimix Pumping Charges | Pumping Charges-BC | 224.01 | Cu.Mtrs | 190 | 100 | 0 | 0 | 42561.9 | C+S GST 18% I/P RD | 7661.14 | 50223.04 | 50223.04 | Approved | 0 | 0 | 851 | 04 Sep 2021
GANGA DHAM TOWERS | 186 | 91416 | 04 Sep 2021 | 70 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1012 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 164.4798 | Day | 451.613 | 100 | 0 | 0 | 74281.22 | C+S GST 18% I/P RD | 13370.62 | 87651.84 | 87651.84 | Approved | 0 | 0 | 923 | 04 Sep 2021
GANGA DHAM TOWERS | 186 | 91416 | 04 Sep 2021 | 70 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1012 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 31 | Day | 580.645 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 923 | 04 Sep 2021
GANGA DHAM TOWERS | 187 | 91414 | 04 Sep 2021 | 73 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1059 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 04 Sep 2021
GANGA DHAM TOWERS | 744 | 91413 | 04 Sep 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 874 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 6 | 04 Sep 2021
GANGA DHAM TOWERS | 773 | 91411 | 03 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 880 | B P2 Parking chemical grouting | Chemical Grouting (L) | 23732.14 | Sq.Ft | 1 | 100 | 593.3 | 0 | 23732.14 | CGST 0% URD I/P | 0 | 23732.14 | 23732.14 | Approved | 0 | 40000 | 475 | 03 Sep 2021
GANGA DHAM TOWERS | 773 | 91411 | 03 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 880 | B P2 Parking chemical grouting | Ghadai work- BCP | 23732.14 | Sq.Ft | 1 | 100 | 593.3 | 0 | 23732.14 | CGST 0% URD I/P | 0 | 23732.14 | 23732.14 | Approved | 0 | 40000 | 475 | 03 Sep 2021
GANGA DHAM TOWERS | 742 | 91410 | 03 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 881 | A P2 Parking Ghadai & chemical grouting | Ghadai work- BCP | 5268 | Sq.Ft | 1 | 100 | 131.7 | 0 | 5268 | CGST 0% URD I/P | 0 | 5268 | 5268 | Approved | 0 | 10000 | 105 | 03 Sep 2021
GANGA DHAM TOWERS | 742 | 91410 | 03 Sep 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 881 | A P2 Parking Ghadai & chemical grouting | Chemical Grouting (L) | 5268 | Sq.Ft | 1 | 100 | 131.7 | 0 | 5268 | CGST 0% URD I/P | 0 | 5268 | 5268 | Approved | 0 | 10000 | 105 | 03 Sep 2021
GANGA DHAM TOWERS | 1115 | 91406 | 03 Sep 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 918 | B1- 1101 Pop Breaking Rabbit Shifting | Department Labour-Dev | 5 | No. | 450 | 100 | 0 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 104 | 03 Sep 2021
GANGA DHAM TOWERS | 1115 | 91406 | 03 Sep 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 918 | B1- 1101 Pop Breaking Rabbit Shifting | Department Labour-Dev | 18 | No. | 450 | 100 | 0 | 0 | 8100 | CGST 0% URD I/P | 0 | 8100 | 8100 | Approved | 0 | 0 | 104 | 03 Sep 2021
GANGA DHAM TOWERS | 1151 | 91397 | 03 Sep 2021 | 226 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 1032 | B 1601 NOC | Brickwork 4" Rate Difference | 235.03 | Sq.Ft | 5 | 100 | 29.38 | 0 | 1175.15 | C+S GST 18% I/P RD | 211.52 | 1386.67 | 1386.67 | Approved | 0 | 0 | 12 | 03 Sep 2021
GANGA DHAM TOWERS | 1002 | 91396 | 03 Sep 2021 | 11 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 974 | A 2302 NOC | Concrete wall Crushing work | 1.1019 | Cu.Mtrs | 7200 | 100 | 198.34 | 0 | 7934 | C+S GST 18% I/P RD | 1428.12 | 9362.12 | 9362.12 | Approved | 0 | 0 | 2259 | 03 Sep 2021
GANGA DHAM TOWERS | 1002 | 91396 | 03 Sep 2021 | 11 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 974 | A 1601 NOC | Concrete wall Crushing work | 0.51 | Cu.Mtrs | 7200 | 100 | 91.8 | 0 | 3672 | C+S GST 18% I/P RD | 660.96 | 4332.96 | 4332.96 | Approved | 0 | 0 | 2259 | 03 Sep 2021
GANGA DHAM TOWERS | 1002 | 91396 | 03 Sep 2021 | 11 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 974 | A 1902 NOC | Concrete wall Crushing work | 0.1 | Cu.Mtrs | 7200 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 2259 | 03 Sep 2021
GANGA DHAM TOWERS | 1002 | 91396 | 03 Sep 2021 | 11 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 974 | A 1601 NOC | Concrete Cutting Work | 50.18 | R.Ft | 525 | 100 | 658.61 | 0 | 26344.5 | C+S GST 18% I/P RD | 4742.02 | 31086.52 | 31086.52 | Approved | 0 | 0 | 2259 | 03 Sep 2021
GANGA DHAM TOWERS | 1002 | 91396 | 03 Sep 2021 | 11 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 974 | A 2302 NOC | Concrete Cutting Work | 138.0495 | R.Ft | 525 | 100 | 1811.9 | 0 | 72476 | C+S GST 18% I/P RD | 13045.68 | 85521.68 | 85521.68 | Approved | 0 | 0 | 2259 | 03 Sep 2021
GANGA DHAM TOWERS | 1002 | 91396 | 03 Sep 2021 | 11 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 974 | A 1902 NOC | Concrete Cutting Work | 3.4743 | R.Ft | 525 | 100 | 45.6 | 0 | 1824 | C+S GST 18% I/P RD | 328.32 | 2152.32 | 2152.32 | Approved | 0 | 0 | 2259 | 03 Sep 2021
GANGA DHAM TOWERS | 1100 | 91395 | 03 Sep 2021 |  | FINE TRADERS | FINE TRADERS | EV - 2241 | DA Dev SS Railing for Gym | S.S. Railing (L)- BC | 12.5 | R.Ft | 90 | 100 | 28.13 | 0 | 1125 | C+S GST 18% I/P RD | 202.5 | 1327.5 | 1327.5 | Approved | 0 | 0 | 11 | 03 Sep 2021
GANGA DHAM TOWERS | 1101 | 91394 | 03 Sep 2021 |  | FINE TRADERS | FINE TRADERS | EV - 2242 | DA Dev SS Railing for Gym | S.S. Railing (M)- BC | 12.5 | R.Ft | 210 | 100 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 0 | 03 Sep 2021
GANGA DHAM TOWERS | 1109 | 91392 | 03 Sep 2021 | 166 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 860 | B1- 1101 Hiring,Erection&Shifting of Gandola-(No.) | Hiring of Gondola | 1 | Month | 30000 | 100 | 0 | 0 | 30000 | C+S GST 18% I/P RD | 5400 | 35400 | 35400 | Approved | 0 | 0 | 330 | 03 Sep 2021
GANGA DHAM TOWERS | 1109 | 91392 | 03 Sep 2021 | 166 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 860 | B1- 1101 Hiring,Erection&Shifting of Gandola-(No.) | Errection & Shifting of Gondola | 1 | No. | 3000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 330 | 03 Sep 2021
GANGA DHAM TOWERS | 940 | 91391 | 03 Sep 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 878 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 03 Sep 2021
GANGA DHAM TOWERS | 1155 | 91390 | 03 Sep 2021 | 167 | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 839 | A External Texture Paint Gondola charges | Hiring of Gondola | 1 | Month | 140000 | 100 | 0 | 0 | 140000 | C+S GST 18% I/P RD | 25200 | 165200 | 165200 | Approved | 0 | 0 | 1400 | 03 Sep 2021
GANGA DHAM TOWERS | 1070 | 91389 | 03 Sep 2021 | FITI/GGIPL/030 | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 856 | Lab Performance Test for strip window system | Lab Test for Strip Window System. | 1 | No. | 900000 | 10 | 0 | 0 | 90000 | C+S GST 18% I/P RD | 16200 | 106200 | 106200 | Approved | 0 | 0 | 1800 | 03 Sep 2021
GANGA DHAM TOWERS | 145 | 91363 | 01 Sep 2021 | 203 | PEST-O-CRUSH | S.R.Enterprises | EV - 968 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 01 Sep 2021
GANGA DHAM TOWERS | 237 | 91362 | 01 Sep 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 969 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.742 | Month | 7000 | 100 | 0 | 0 | 5194 | CGST 0% URD I/P | 0 | 5194 | 5194 | Approved | 0 | 0 | 52 | 01 Sep 2021
GANGA DHAM TOWERS | 258 | 91361 | 01 Sep 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 1074 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.742 | Month | 2500 | 100 | 0 | 0 | 1855 | CGST 0% URD I/P | 0 | 1855 | 1855 | Approved | 0 | 0 | 19 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 671.562 | Sq.Ft | 1.25 | 100 | 20.99 | 0 | 839.45 | CGST 0% URD I/P | 0 | 839.45 | 839.45 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 671.562 | Sq.Ft | 1.25 | 100 | 20.99 | 0 | 839.45 | CGST 0% URD I/P | 0 | 839.45 | 839.45 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 539.2 | Sq.Ft | 1.25 | 100 | 16.85 | 0 | 674 | CGST 0% URD I/P | 0 | 674 | 674 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 6th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-12th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-11th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 3rd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-12th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-16th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 4th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 2nd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 550.296 | Sq.Ft | 1.25 | 100 | 17.2 | 0 | 687.87 | CGST 0% URD I/P | 0 | 687.87 | 687.87 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-10th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 550.296 | Sq.Ft | 1.25 | 100 | 17.2 | 0 | 687.87 | CGST 0% URD I/P | 0 | 687.87 | 687.87 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 580.8 | Sq.Ft | 1.25 | 100 | 18.15 | 0 | 726 | CGST 0% URD I/P | 0 | 726 | 726 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-15th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-14th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 216.8 | Sq.Ft | 1.25 | 100 | 6.78 | 0 | 271 | CGST 0% URD I/P | 0 | 271 | 271 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 670.374 | Sq.Ft | 1.25 | 100 | 20.95 | 0 | 837.97 | CGST 0% URD I/P | 0 | 837.97 | 837.97 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 580.8 | Sq.Ft | 1.25 | 100 | 18.15 | 0 | 726 | CGST 0% URD I/P | 0 | 726 | 726 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 670.374 | Sq.Ft | 1.25 | 100 | 20.95 | 0 | 837.97 | CGST 0% URD I/P | 0 | 837.97 | 837.97 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 670.374 | Sq.Ft | 1.25 | 100 | 20.95 | 0 | 837.97 | CGST 0% URD I/P | 0 | 837.97 | 837.97 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 670.374 | Sq.Ft | 1.25 | 100 | 20.95 | 0 | 837.97 | CGST 0% URD I/P | 0 | 837.97 | 837.97 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 580.8 | Sq.Ft | 1.25 | 100 | 18.15 | 0 | 726 | CGST 0% URD I/P | 0 | 726 | 726 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 671.562 | Sq.Ft | 1.25 | 100 | 20.99 | 0 | 839.45 | CGST 0% URD I/P | 0 | 839.45 | 839.45 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 216.8 | Sq.Ft | 1.25 | 100 | 6.78 | 0 | 271 | CGST 0% URD I/P | 0 | 271 | 271 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 539.2 | Sq.Ft | 1.25 | 100 | 16.85 | 0 | 674 | CGST 0% URD I/P | 0 | 674 | 674 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 539.2 | Sq.Ft | 1.25 | 100 | 16.85 | 0 | 674 | CGST 0% URD I/P | 0 | 674 | 674 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 671.562 | Sq.Ft | 1.25 | 100 | 20.99 | 0 | 839.45 | CGST 0% URD I/P | 0 | 839.45 | 839.45 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 670.374 | Sq.Ft | 1.25 | 100 | 20.95 | 0 | 837.97 | CGST 0% URD I/P | 0 | 837.97 | 837.97 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 3rd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-11th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 5th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 539.2 | Sq.Ft | 1.25 | 100 | 16.85 | 0 | 674 | CGST 0% URD I/P | 0 | 674 | 674 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 550.296 | Sq.Ft | 1.25 | 100 | 17.2 | 0 | 687.87 | CGST 0% URD I/P | 0 | 687.87 | 687.87 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 670.374 | Sq.Ft | 1.25 | 100 | 20.95 | 0 | 837.97 | CGST 0% URD I/P | 0 | 837.97 | 837.97 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 580.8 | Sq.Ft | 1.25 | 100 | 18.15 | 0 | 726 | CGST 0% URD I/P | 0 | 726 | 726 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 671.562 | Sq.Ft | 1.25 | 100 | 20.99 | 0 | 839.45 | CGST 0% URD I/P | 0 | 839.45 | 839.45 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 9th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 4th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 8th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1st floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 2nd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 5th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 7th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 539.2 | Sq.Ft | 1.25 | 100 | 16.85 | 0 | 674 | CGST 0% URD I/P | 0 | 674 | 674 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 9th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-13th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 550.296 | Sq.Ft | 1.25 | 100 | 17.2 | 0 | 687.87 | CGST 0% URD I/P | 0 | 687.87 | 687.87 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 580.8 | Sq.Ft | 1.25 | 100 | 18.15 | 0 | 726 | CGST 0% URD I/P | 0 | 726 | 726 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 216.8 | Sq.Ft | 1.25 | 100 | 6.78 | 0 | 271 | CGST 0% URD I/P | 0 | 271 | 271 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 580.8 | Sq.Ft | 1.25 | 100 | 18.15 | 0 | 726 | CGST 0% URD I/P | 0 | 726 | 726 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 216.8 | Sq.Ft | 1.25 | 100 | 6.78 | 0 | 271 | CGST 0% URD I/P | 0 | 271 | 271 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1st Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 7th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-10th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 8th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 418.095 | Sq.Ft | 1.25 | 100 | 13.07 | 0 | 522.62 | CGST 0% URD I/P | 0 | 522.62 | 522.62 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 6th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 539.2 | Sq.Ft | 1.25 | 100 | 16.85 | 0 | 674 | CGST 0% URD I/P | 0 | 674 | 674 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 550.296 | Sq.Ft | 1.25 | 100 | 17.2 | 0 | 687.87 | CGST 0% URD I/P | 0 | 687.87 | 687.87 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 550.296 | Sq.Ft | 1.25 | 100 | 17.2 | 0 | 687.87 | CGST 0% URD I/P | 0 | 687.87 | 687.87 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 216.8 | Sq.Ft | 1.25 | 100 | 6.78 | 0 | 271 | CGST 0% URD I/P | 0 | 271 | 271 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 670.374 | Sq.Ft | 1.25 | 100 | 20.95 | 0 | 837.97 | CGST 0% URD I/P | 0 | 837.97 | 837.97 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 670.374 | Sq.Ft | 1.25 | 100 | 20.95 | 0 | 837.97 | CGST 0% URD I/P | 0 | 837.97 | 837.97 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 216.8 | Sq.Ft | 1.25 | 100 | 6.78 | 0 | 271 | CGST 0% URD I/P | 0 | 271 | 271 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 399.2 | Sq.Ft | 1.25 | 100 | 12.48 | 0 | 499 | CGST 0% URD I/P | 0 | 499 | 499 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 671.562 | Sq.Ft | 1.25 | 100 | 20.99 | 0 | 839.45 | CGST 0% URD I/P | 0 | 839.45 | 839.45 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 539.2 | Sq.Ft | 1.25 | 100 | 16.85 | 0 | 674 | CGST 0% URD I/P | 0 | 674 | 674 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 550.296 | Sq.Ft | 1.25 | 100 | 17.2 | 0 | 687.87 | CGST 0% URD I/P | 0 | 687.87 | 687.87 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 671.562 | Sq.Ft | 1.25 | 100 | 20.99 | 0 | 839.45 | CGST 0% URD I/P | 0 | 839.45 | 839.45 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 539.2 | Sq.Ft | 1.25 | 100 | 16.85 | 0 | 674 | CGST 0% URD I/P | 0 | 674 | 674 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 471.2 | Sq.Ft | 1.25 | 100 | 14.73 | 0 | 589 | CGST 0% URD I/P | 0 | 589 | 589 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 71.433 | Sq.Ft | 1.25 | 100 | 2.23 | 0 | 89.29 | CGST 0% URD I/P | 0 | 89.29 | 89.29 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 671.562 | Sq.Ft | 1.25 | 100 | 20.99 | 0 | 839.45 | CGST 0% URD I/P | 0 | 839.45 | 839.45 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-16th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-14th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (L) | 280 | Sq.Ft | 1.25 | 100 | 8.75 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-13th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A-15th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 81.396 | Sq.Ft | 1.25 | 100 | 2.54 | 0 | 101.75 | CGST 0% URD I/P | 0 | 101.75 | 101.75 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 580.8 | Sq.Ft | 1.25 | 100 | 18.15 | 0 | 726 | CGST 0% URD I/P | 0 | 726 | 726 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 94.185 | Sq.Ft | 1.25 | 100 | 2.94 | 0 | 117.73 | CGST 0% URD I/P | 0 | 117.73 | 117.73 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 827 | 91360 | 01 Sep 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 861 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 67.131 | Sq.Ft | 1.25 | 100 | 2.1 | 0 | 83.91 | CGST 0% URD I/P | 0 | 83.91 | 83.91 | Approved | 0 | 0 | 543 | 01 Sep 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 104 | Sq.Ft | 1.75 | 100 | 0 | 0 | 182 | CGST 0% URD I/P | 0 | 182 | 182 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 25.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 44 | CGST 0% URD I/P | 0 | 44 | 44 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 25.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 44 | CGST 0% URD I/P | 0 | 44 | 44 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 6th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 4th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 8th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-13th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 24 | Sq.Ft | 1.75 | 100 | 0 | 0 | 42 | CGST 0% URD I/P | 0 | 42 | 42 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1st floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-15th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 9th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 249 | CGST 0% URD I/P | 0 | 249 | 249 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 25.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 44 | CGST 0% URD I/P | 0 | 44 | 44 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 16 | Sq.Ft | 1.75 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 226.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 397 | CGST 0% URD I/P | 0 | 397 | 397 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-15th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 104 | Sq.Ft | 1.75 | 100 | 0 | 0 | 182 | CGST 0% URD I/P | 0 | 182 | 182 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 104 | Sq.Ft | 1.75 | 100 | 0 | 0 | 182 | CGST 0% URD I/P | 0 | 182 | 182 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-12th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 5th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-12th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 104 | Sq.Ft | 1.75 | 100 | 0 | 0 | 182 | CGST 0% URD I/P | 0 | 182 | 182 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 249 | CGST 0% URD I/P | 0 | 249 | 249 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 7th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 3rd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-14th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 5th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 249 | CGST 0% URD I/P | 0 | 249 | 249 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 25.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 44 | CGST 0% URD I/P | 0 | 44 | 44 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 2nd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 7th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-10th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 24 | Sq.Ft | 1.75 | 100 | 0 | 0 | 42 | CGST 0% URD I/P | 0 | 42 | 42 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 24 | Sq.Ft | 1.75 | 100 | 0 | 0 | 42 | CGST 0% URD I/P | 0 | 42 | 42 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 24 | Sq.Ft | 1.75 | 100 | 0 | 0 | 42 | CGST 0% URD I/P | 0 | 42 | 42 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 25.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 44 | CGST 0% URD I/P | 0 | 44 | 44 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-13th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-11th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 24 | Sq.Ft | 1.75 | 100 | 0 | 0 | 42 | CGST 0% URD I/P | 0 | 42 | 42 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-16th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-14th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 85.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 149 | CGST 0% URD I/P | 0 | 149 | 149 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 24 | Sq.Ft | 1.75 | 100 | 0 | 0 | 42 | CGST 0% URD I/P | 0 | 42 | 42 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 6.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 12 | CGST 0% URD I/P | 0 | 12 | 12 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 25.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 44 | CGST 0% URD I/P | 0 | 44 | 44 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 105.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 184 | CGST 0% URD I/P | 0 | 184 | 184 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-10th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-11th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 2nd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A-16th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 249 | CGST 0% URD I/P | 0 | 249 | 249 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 66.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 116 | CGST 0% URD I/P | 0 | 116 | 116 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 77.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 135 | CGST 0% URD I/P | 0 | 135 | 135 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 25.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 44 | CGST 0% URD I/P | 0 | 44 | 44 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1st Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 142.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 34.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 60 | CGST 0% URD I/P | 0 | 60 | 60 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 17.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 30 | CGST 0% URD I/P | 0 | 30 | 30 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 3rd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 4th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1st Coat Semi-Acrylic Paint (M) | 280 | Sq.Ft | 1.75 | 100 | 0 | 0 | 490 | CGST 0% URD I/P | 0 | 490 | 490 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 8th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 9th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 6th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 104 | Sq.Ft | 1.75 | 100 | 0 | 0 | 182 | CGST 0% URD I/P | 0 | 182 | 182 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 44 | Sq.Ft | 1.75 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 226.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 397 | CGST 0% URD I/P | 0 | 397 | 397 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 22.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 39 | CGST 0% URD I/P | 0 | 39 | 39 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 226.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 397 | CGST 0% URD I/P | 0 | 397 | 397 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 828 | 91348 | 31 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 879 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 29.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 51 | CGST 0% URD I/P | 0 | 51 | 51 | Approved | 0 | 0 | 0 | 31 Aug 2021
GANGA DHAM TOWERS | 1036 | 91341 | 30 Aug 2021 |  | NAVAY RENEWABLES | NAVAY RENEWABLES | EV - 917 | Club House Solar Panel installation . | Earthing Patti (M) | 1 | No. | 4000 | 100 | 0 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 0 | 30 Aug 2021
GANGA DHAM TOWERS | 1036 | 91341 | 30 Aug 2021 |  | NAVAY RENEWABLES | NAVAY RENEWABLES | EV - 917 | Club House Solar Panel installation . | Transport Charges | 1 | No. | 2000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 0 | 30 Aug 2021
GANGA DHAM TOWERS | 1036 | 91341 | 30 Aug 2021 |  | NAVAY RENEWABLES | NAVAY RENEWABLES | EV - 917 | Club House Solar Panel installation . | GI Structure (M) | 1100 | Kgs | 64 | 100 | 0 | 0 | 70400 | C+S GST 18% I/P RD | 12672 | 83072 | 83072 | Approved | 0 | 0 | 0 | 30 Aug 2021
GANGA DHAM TOWERS | 1036 | 91341 | 30 Aug 2021 |  | NAVAY RENEWABLES | NAVAY RENEWABLES | EV - 917 | Club House Solar Panel installation . | DC Cable (M) | 1 | No. | 8000 | 100 | 0 | 0 | 8000 | C+S GST 18% I/P RD | 1440 | 9440 | 9440 | Approved | 0 | 0 | 0 | 30 Aug 2021
GANGA DHAM TOWERS | 1035 | 91340 | 30 Aug 2021 | 41 | NAVAY RENEWABLES | NAVAY RENEWABLES | EV - 1095 | Club House Solar Panel installation . | DC Cable (L) | 1 | No. | 2000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 1556 | 30 Aug 2021
GANGA DHAM TOWERS | 1035 | 91340 | 30 Aug 2021 | 41 | NAVAY RENEWABLES | NAVAY RENEWABLES | EV - 1095 | Club House Solar Panel installation . | GI Structure (L) | 1100 | Kgs | 16 | 100 | 0 | 0 | 17600 | C+S GST 18% I/P RD | 3168 | 20768 | 20768 | Approved | 0 | 0 | 1556 | 30 Aug 2021
GANGA DHAM TOWERS | 1035 | 91340 | 30 Aug 2021 | 41 | NAVAY RENEWABLES | NAVAY RENEWABLES | EV - 1095 | Club House Solar Panel installation . | Earthing Patti (L) | 1 | No. | 1000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 1556 | 30 Aug 2021
GANGA DHAM TOWERS | 1035 | 91340 | 30 Aug 2021 | 41 | NAVAY RENEWABLES | NAVAY RENEWABLES | EV - 1095 | Club House Solar Panel installation . | Installation Charges | 1 | No. | 135000 | 100 | 0 | 0 | 135000 | C+S GST 18% I/P RD | 24300 | 159300 | 159300 | Approved | 0 | 0 | 1556 | 30 Aug 2021
GANGA DHAM TOWERS | 389 | 91339 | 28 Aug 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 797 | Loading / Unloading Expenses | Unloading of tiles. | 25 | Metric Tonnes | 160 | 100 | 0 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 0 | 28 Aug 2021
GANGA DHAM TOWERS | 993 | 91336 | 28 Aug 2021 | 227 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 1033 | B 701 NOC | Blockwork 4" - BC | 16.2667 | Sq.Ft | 15 | 100 | 0 | 0 | 244 | C+S GST 18% I/P RD | 43.92 | 287.92 | 287.92 | Approved | 0 | 0 | 2 | 28 Aug 2021
GANGA DHAM TOWERS | 1002 | 91335 | 28 Aug 2021 | KVE/225 | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 1401 | B 602 NOC | Blockwork 4" - BC | 46.59 | Sq.Ft | 24 | 100 | 27.95 | 0 | 1118.16 | C+S GST 18% I/P RD | 201.26 | 1319.42 | 1319.42 | Approved | 0 | 0 | 17 | 28 Aug 2021
GANGA DHAM TOWERS | 1002 | 91335 | 28 Aug 2021 | KVE/225 | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 1401 | B 1602 NOC | Blockwork 4" - BC | 26.61 | Sq.Ft | 22 | 100 | 14.64 | 0 | 585.42 | C+S GST 18% I/P RD | 105.38 | 690.8 | 690.8 | Approved | 0 | 0 | 17 | 28 Aug 2021
GANGA DHAM TOWERS | 495 | 91334 | 28 Aug 2021 | 357 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 920 | B 2001 Gypsum Plaster | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 590 | 28 Aug 2021
GANGA DHAM TOWERS | 495 | 91334 | 28 Aug 2021 | 357 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 920 | B 1901 Gypsum Plaster | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 590 | 28 Aug 2021
GANGA DHAM TOWERS | 495 | 91334 | 28 Aug 2021 | 357 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 920 | B 1901 Gypsum Plaster | Gypsum on Wall (L) | 5658 | Sq.Ft | 4 | 100 | 565.8 | 0 | 22632 | C+S GST 18% I/P RD | 4073.76 | 26705.76 | 26705.76 | Approved | 0 | 0 | 590 | 28 Aug 2021
GANGA DHAM TOWERS | 495 | 91334 | 28 Aug 2021 | 357 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 920 | B 2001 Gypsum Plaster | Gypsum on Wall (L) | 5658 | Sq.Ft | 4 | 100 | 565.8 | 0 | 22632 | C+S GST 18% I/P RD | 4073.76 | 26705.76 | 26705.76 | Approved | 0 | 0 | 590 | 28 Aug 2021
GANGA DHAM TOWERS | 1055 | 91328 | 26 Aug 2021 | gst334/21-22 | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 922 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 53 | 26 Aug 2021
GANGA DHAM TOWERS | 1055 | 91328 | 26 Aug 2021 | gst334/21-22 | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 922 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 53 | 26 Aug 2021
GANGA DHAM TOWERS | 1055 | 91328 | 26 Aug 2021 | gst334/21-22 | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 922 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 53 | 26 Aug 2021
GANGA DHAM TOWERS | 126 | 91327 | 26 Aug 2021 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP VAMANRAO RUPNAWAR |  | Site Expenses | Site Expenses -SO | 0.4667 | Month | 15000 | 100 | 0 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 |  | 0 | 0 | 0 | 26 Aug 2021
GANGA DHAM TOWERS | 1056 | 91308 | 25 Aug 2021 | gst335/21-22 | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 921 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 53 | 25 Aug 2021
GANGA DHAM TOWERS | 1056 | 91308 | 25 Aug 2021 | gst335/21-22 | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 921 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 53 | 25 Aug 2021
GANGA DHAM TOWERS | 1056 | 91308 | 25 Aug 2021 | gst335/21-22 | MEGAPOWER SOLUTION PVT LTD | MEGAPOWER SOLUTION PVT LTD | EV - 921 | DG Annual Maintenance Charges | AMC Charges | 12 | Month | 875 | 8.33 | 0 | 0 | 875.01 | C+S GST 18% I/P RD | 157.5 | 1032.51 | 1032.51 | Approved | 0 | 0 | 53 | 25 Aug 2021
GANGA DHAM TOWERS | 389 | 91304 | 24 Aug 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 793 | Loading / Unloading Expenses | Unloading of tiles. | 22 | Metric Tonnes | 130 | 100 | 0 | 0 | 2860 | CGST 0% URD I/P | 0 | 2860 | 2860 | Approved | 0 | 0 | 0 | 24 Aug 2021
GANGA DHAM TOWERS | 1123 | 91288 | 23 Aug 2021 |  | SURESH GOWALKAR | SURESH GOWALKAR | EV - 1019 | Club House Staff Room and Seravant Room Chemical W/P | Chemical Waterproofing work (m+l) | 114 | R.Ft | 12 | 100 | 136.8 | 0 | 1368 | CGST 0% URD I/P | 0 | 1368 | 1368 | Approved | 0 | 0 | 14 | 23 Aug 2021
GANGA DHAM TOWERS | 1130 | 91287 | 23 Aug 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 876 | Old Labour Camp Slab breaking work | Slab Breaking | 1 | No. | 30000 | 100 | 0 | 0 | 30000 | CGST 0% URD I/P | 0 | 30000 | 30000 | Approved | 0 | 0 | 404 | 23 Aug 2021
GANGA DHAM TOWERS | 1130 | 91287 | 23 Aug 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 876 | Old Labour Camp Slab breaking work | Slab Breaking | 8 | No. | 1300 | 100 | 0 | 0 | 10400 | CGST 0% URD I/P | 0 | 10400 | 10400 | Approved | 0 | 0 | 404 | 23 Aug 2021
GANGA DHAM TOWERS | 1108 | 91286 | 23 Aug 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1018 | A & B Parking Floor 2 Pour Strip Joint Treatment (L) | Chemical Grouting. | 660 | R.Ft | 5 | 100 | 330 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 66 | 23 Aug 2021
GANGA DHAM TOWERS | 1108 | 91286 | 23 Aug 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1018 | A & B Parking Floor 3 Pour Strip Joint Treatment (L) | Chemical Grouting. | 660 | R.Ft | 5 | 100 | 330 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 66 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | A 2301 NOC | Concrete Cutting Work | 101.581 | R.Ft | 525 | 100 | 1333.25 | 0 | 53330.01 | C+S GST 18% I/P RD | 9599.4 | 62929.41 | 62929.41 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | B 1602 NOC | Concrete Cutting Work | 10.581 | R.Ft | 525 | 100 | 138.88 | 0 | 5555.01 | C+S GST 18% I/P RD | 999.9 | 6554.91 | 6554.91 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | B 602 NOC | Concrete Cutting Work | 100.36 | R.Ft | 525 | 100 | 1317.23 | 0 | 52689 | C+S GST 18% I/P RD | 9484.02 | 62173.02 | 62173.02 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | B 601 NOC | Concrete Cutting Work | 406 | R.Ft | 525 | 100 | 5328.75 | 0 | 213150 | C+S GST 18% I/P RD | 38367 | 251517 | 251517 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | B 1201 NOC | Concrete Cutting Work | 550.5905 | R.Ft | 525 | 100 | 7226.5 | 0 | 289060 | C+S GST 18% I/P RD | 52030.8 | 341090.8 | 341090.8 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | A 2301 NOC | Concrete wall Crushing work | 1.0081 | Cu.Mtrs | 7200 | 100 | 181.46 | 0 | 7258 | C+S GST 18% I/P RD | 1306.44 | 8564.44 | 8564.44 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | B 601 NOC | Concrete wall Crushing work | 4 | Cu.Mtrs | 7200 | 100 | 720 | 0 | 28800 | C+S GST 18% I/P RD | 5184 | 33984 | 33984 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | B 1602 NOC | Concrete wall Crushing work | 0.06 | Cu.Mtrs | 7200 | 100 | 10.8 | 0 | 432 | C+S GST 18% I/P RD | 77.76 | 509.76 | 509.76 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | B 602 NOC | Concrete wall Crushing work | 0.8269 | Cu.Mtrs | 7200 | 100 | 148.84 | 0 | 5954 | C+S GST 18% I/P RD | 1071.72 | 7025.72 | 7025.72 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 1002 | 91285 | 23 Aug 2021 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 970 | B 1201 NOC | Concrete wall Crushing work | 5.34 | Cu.Mtrs | 7200 | 100 | 961.2 | 0 | 38448 | C+S GST 18% I/P RD | 6920.64 | 45368.64 | 45368.64 | Approved | 0 | 0 | 13894 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1004 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1005 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1003 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1001 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91284 | 23 Aug 2021 | 202 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1009 | D Bldg Flat No.1002 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 98 | 23 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1001 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1005 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1003 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1004 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1002 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1005 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1002 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1004 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1003 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1001 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1001 Electrical Work - 0 No. | Exhaust Fan fixing | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1003 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1001 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1005 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1002 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 452 | 91273 | 20 Aug 2021 | 206 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1008 | D Bldg Flat No.1004 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 19 | 20 Aug 2021
GANGA DHAM TOWERS | 237 | 91258 | 19 Aug 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 733 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.8386 | Month | 7000 | 100 | 0 | 0 | 5870 | CGST 0% URD I/P | 0 | 5870 | 5870 | Approved | 0 | 0 | 59 | 19 Aug 2021
GANGA DHAM TOWERS | 258 | 91257 | 19 Aug 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 732 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.8384 | Month | 2500 | 100 | 0 | 0 | 2096 | CGST 0% URD I/P | 0 | 2096 | 2096 | Approved | 0 | 0 | 21 | 19 Aug 2021
GANGA DHAM TOWERS | 389 | 91256 | 19 Aug 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 795 | Loading / Unloading Expenses | Unloading of GYpsum- | 12 | Metric Tonnes | 200 | 100 | 0 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 0 | 19 Aug 2021
GANGA DHAM TOWERS | 389 | 91255 | 19 Aug 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 794 | Loading / Unloading Expenses | Unloading of GYpsum- | 10 | Metric Tonnes | 200 | 100 | 0 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 0 | 19 Aug 2021
GANGA DHAM TOWERS | 389 | 91254 | 19 Aug 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 796 | Loading / Unloading Expenses | Unloading of GYpsum- | 10 | Metric Tonnes | 200 | 100 | 0 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 0 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 1703 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 23237 | 40 | 46.47 | 0 | 1858.96 | C+S GST 18% I/P RD | 334.62 | 2193.58 | 2193.58 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 803 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 23237 | 40 | 46.47 | 0 | 1858.96 | C+S GST 18% I/P RD | 334.62 | 2193.58 | 2193.58 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 403 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 23237 | 40 | 46.47 | 0 | 1858.96 | C+S GST 18% I/P RD | 334.62 | 2193.58 | 2193.58 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 903 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 23237 | 40 | 46.47 | 0 | 1858.96 | C+S GST 18% I/P RD | 334.62 | 2193.58 | 2193.58 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 1003 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 23237 | 40 | 46.47 | 0 | 1858.96 | C+S GST 18% I/P RD | 334.62 | 2193.58 | 2193.58 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 601 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 1001 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 201 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26925 | 40 | 53.85 | 0 | 2154 | C+S GST 18% I/P RD | 387.72 | 2541.72 | 2541.72 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 1004 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 1204 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 404 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 604 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 204 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 502 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 602 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 26015 | 40 | 52.03 | 0 | 2081.2 | C+S GST 18% I/P RD | 374.62 | 2455.82 | 2455.82 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 1403 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 23237 | 40 | 46.47 | 0 | 1858.96 | C+S GST 18% I/P RD | 334.62 | 2193.58 | 2193.58 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 1118 | 91247 | 19 Aug 2021 | 15 | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 825 | A 1603 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.2 | No. | 23237 | 40 | 46.47 | 0 | 1858.96 | C+S GST 18% I/P RD | 334.62 | 2193.58 | 2193.58 | Approved | 0 | 0 | 340 | 19 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 1003 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 703 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 100 | Sq.Ft | 19 | 100 | 190 | 0 | 1900 | CGST 0% URD I/P | 0 | 1900 | 1900 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 1201 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 100 | Sq.Ft | 19 | 100 | 190 | 0 | 1900 | CGST 0% URD I/P | 0 | 1900 | 1900 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 402 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 82 | Sq.Ft | 19 | 100 | 155.8 | 0 | 1558 | CGST 0% URD I/P | 0 | 1558 | 1558 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 601 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 87 | Sq.Ft | 19 | 100 | 165.3 | 0 | 1653 | CGST 0% URD I/P | 0 | 1653 | 1653 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 704 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 50 | Sq.Ft | 19 | 100 | 95 | 0 | 950 | CGST 0% URD I/P | 0 | 950 | 950 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 903 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 150 | Sq.Ft | 19 | 100 | 285 | 0 | 2850 | CGST 0% URD I/P | 0 | 2850 | 2850 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 401 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 82 | Sq.Ft | 19 | 100 | 155.8 | 0 | 1558 | CGST 0% URD I/P | 0 | 1558 | 1558 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 1204 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 701 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 87 | Sq.Ft | 19 | 100 | 165.3 | 0 | 1653 | CGST 0% URD I/P | 0 | 1653 | 1653 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 604 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 89 | Sq.Ft | 19 | 100 | 169.1 | 0 | 1691 | CGST 0% URD I/P | 0 | 1691 | 1691 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 603 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 230 | Sq.Ft | 19 | 100 | 437 | 0 | 4370 | CGST 0% URD I/P | 0 | 4370 | 4370 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 401 | 91246 | 18 Aug 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 821 | A 602 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 91 | Sq.Ft | 19 | 100 | 172.9 | 0 | 1729 | CGST 0% URD I/P | 0 | 1729 | 1729 | Approved | 0 | 0 | 294 | 18 Aug 2021
GANGA DHAM TOWERS | 363 | 91245 | 18 Aug 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.01 | C+S GST 18% I/P RD | 270 | 1770.01 | 1770.01 |  | 0 | 0 | 105 | 18 Aug 2021
GANGA DHAM TOWERS | 363 | 91245 | 18 Aug 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.01 | C+S GST 18% I/P RD | 270 | 1770.01 | 1770.01 |  | 0 | 0 | 105 | 18 Aug 2021
GANGA DHAM TOWERS | 363 | 91245 | 18 Aug 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.01 | C+S GST 18% I/P RD | 270 | 1770.01 | 1770.01 |  | 0 | 0 | 105 | 18 Aug 2021
GANGA DHAM TOWERS | 363 | 91245 | 18 Aug 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.01 | C+S GST 18% I/P RD | 270 | 1770.01 | 1770.01 |  | 0 | 0 | 105 | 18 Aug 2021
GANGA DHAM TOWERS | 363 | 91245 | 18 Aug 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.01 | C+S GST 18% I/P RD | 270 | 1770.01 | 1770.01 |  | 0 | 0 | 105 | 18 Aug 2021
GANGA DHAM TOWERS | 363 | 91245 | 18 Aug 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.01 | C+S GST 18% I/P RD | 270 | 1770.01 | 1770.01 |  | 0 | 0 | 105 | 18 Aug 2021
GANGA DHAM TOWERS | 363 | 91245 | 18 Aug 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.01 | C+S GST 18% I/P RD | 270 | 1770.01 | 1770.01 |  | 0 | 0 | 105 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2302 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2004 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2404 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2503 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2304 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2601 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2002 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2402 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2001 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2303 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2504 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2203 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2003 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2501 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 1803 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2204 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2104 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2401 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2502 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 1903 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 1804 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2603 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2102 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2403 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2101 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 1802 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 1902 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2103 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2201 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 1904 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2202 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2301 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2604 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 2602 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 1801 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 1005 | 91239 | 18 Aug 2021 | 221 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 820 | A 1901 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 180 | 18 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Champher-DCH | 1428 | R.Ft | 85 | 100 | 3034.5 | 0 | 121380 | C+S GST 18% I/P RD | 21848.4 | 143228.4 | 143228.4 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Vitrified Flooring - MKT - Sq.Ft | 2834.24 | Sq.Ft | 35 | 100 | 2479.96 | 0 | 99198.4 | C+S GST 18% I/P RD | 17855.72 | 117054.12 | 117054.12 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Door Closer Gala Cutting- BCo | 8 | No. | 300 | 100 | 60 | 0 | 2400 | C+S GST 18% I/P RD | 432 | 2832 | 2832 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Vitrified Skirting - MKT - R.Ft | 235.46 | R.Ft | 35 | 100 | 206.03 | 0 | 8241.1 | C+S GST 18% I/P RD | 1483.4 | 9724.5 | 9724.5 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Zero Point Joint making- BCo | 181.18 | R.Ft | 200 | 100 | 905.9 | 0 | 36236 | C+S GST 18% I/P RD | 6522.48 | 42758.48 | 42758.48 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Skirting | 261.16 | R.Ft | 90 | 100 | 587.61 | 0 | 23504.4 | C+S GST 18% I/P RD | 4230.8 | 27735.2 | 27735.2 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Champher Polish- Dld | 6.75 | R.Ft | 200 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Window Jamb - Mkt | 76.94 | R.Ft | 90 | 100 | 173.12 | 0 | 6924.6 | C+S GST 18% I/P RD | 1246.42 | 8171.02 | 8171.02 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Floor Groove Grouting | 1861.19 | Sq.Ft | 15 | 100 | 697.95 | 0 | 27917.85 | C+S GST 18% I/P RD | 5025.22 | 32943.07 | 32943.07 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Edge Polish - Mkt | 2686.7 | R.Ft | 35 | 100 | 2350.86 | 0 | 94034.5 | C+S GST 18% I/P RD | 16926.22 | 110960.72 | 110960.72 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Dado - Mkt | 941.74 | Sq.Ft | 75 | 100 | 1765.76 | 0 | 70630.5 | C+S GST 18% I/P RD | 12713.5 | 83344 | 83344 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Dado - Mkt | 257.97 | Sq.Ft | 75 | 100 | 483.69 | 0 | 19347.75 | C+S GST 18% I/P RD | 3482.6 | 22830.35 | 22830.35 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Cross Skirting | 55.31 | R.Ft | 150 | 100 | 207.41 | 0 | 8296.5 | C+S GST 18% I/P RD | 1493.38 | 9789.88 | 9789.88 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Drill Hole | 64 | No. | 130 | 100 | 208 | 0 | 8320 | C+S GST 18% I/P RD | 1497.6 | 9817.6 | 9817.6 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Dado Work - Dld | 660.24 | Sq.Ft | 115 | 100 | 1898.19 | 0 | 75927.6 | C+S GST 18% I/P RD | 13666.96 | 89594.56 | 89594.56 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Flooring | 3239.95 | Sq.Ft | 90 | 100 | 7289.89 | 0 | 291595.5 | C+S GST 18% I/P RD | 52487.2 | 344082.7 | 344082.7 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Bull Nosing / Moulding | 335.6 | R.Ft | 85 | 100 | 713.15 | 0 | 28526 | C+S GST 18% I/P RD | 5134.68 | 33660.68 | 33660.68 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | V Groove- Dld | 812.71 | R.Ft | 120 | 100 | 2438.13 | 0 | 97525.2 | C+S GST 18% I/P RD | 17554.54 | 115079.74 | 115079.74 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | L Groove- Dld | 150.56 | R.Ft | 150 | 100 | 564.6 | 0 | 22584 | C+S GST 18% I/P RD | 4065.12 | 26649.12 | 26649.12 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Tappa/Riser BC | 749.07 | R.Ft | 90 | 100 | 1685.41 | 0 | 67416.3 | C+S GST 18% I/P RD | 12134.94 | 79551.24 | 79551.24 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Vitrified Tile Border | 104 | R.Ft | 75 | 100 | 195 | 0 | 7800 | C+S GST 18% I/P RD | 1404 | 9204 | 9204 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Border- Dld | 2707.46 | R.Ft | 90 | 100 | 6091.79 | 0 | 243671.4 | C+S GST 18% I/P RD | 43860.86 | 287532.26 | 287532.26 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Basin Counter | 14.57 | R.Ft | 1800 | 100 | 655.65 | 0 | 26226 | C+S GST 18% I/P RD | 4720.68 | 30946.68 | 30946.68 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Round Border | 222.78 | R.Ft | 180 | 100 | 1002.51 | 0 | 40100.4 | C+S GST 18% I/P RD | 7218.08 | 47318.48 | 47318.48 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Granite Kitchen Counter | 10.91 | R.Ft | 800 | 100 | 218.2 | 0 | 8728 | C+S GST 18% I/P RD | 1571.04 | 10299.04 | 10299.04 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 996 | 91225 | 16 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 710 | Club House Flooring/ Tiling ( L) | Nahani Trap Jali Cutting | 10 | No. | 130 | 100 | 32.5 | 0 | 1300 | C+S GST 18% I/P RD | 234 | 1534 | 1534 | Approved | 0 | 500000 | 28784 | 16 Aug 2021
GANGA DHAM TOWERS | 698 | 91217 | 16 Aug 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 832 | D 804 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 634.328 | Sq.Ft | 9 | 100 | 142.72 | 0 | 5708.95 | CGST 0% URD I/P | 0 | 5708.95 | 5708.95 | Approved | 0 | 0 | 57 | 16 Aug 2021
GANGA DHAM TOWERS | 797 | 91216 | 16 Aug 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 823 | D 7th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 493.16 | Sq.Ft | 9 | 100 | 110.96 | 0 | 4438.44 | CGST 0% URD I/P | 0 | 4438.44 | 4438.44 | Approved | 0 | 0 | 140 | 16 Aug 2021
GANGA DHAM TOWERS | 797 | 91216 | 16 Aug 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 823 | D 6th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 493.16 | Sq.Ft | 9 | 100 | 110.96 | 0 | 4438.44 | CGST 0% URD I/P | 0 | 4438.44 | 4438.44 | Approved | 0 | 0 | 140 | 16 Aug 2021
GANGA DHAM TOWERS | 797 | 91216 | 16 Aug 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 823 | D 5th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 80 | Sq.Ft | 9 | 100 | 18 | 0 | 720 | CGST 0% URD I/P | 0 | 720 | 720 | Approved | 0 | 0 | 140 | 16 Aug 2021
GANGA DHAM TOWERS | 797 | 91216 | 16 Aug 2021 |  | J K INTERIOR | TASLIM NANHE KHAN | EV - 823 | D 8th Floor Lobby Wall Gypsum Plaster | Tikki Dhada (L) | 493.16 | Sq.Ft | 9 | 100 | 110.96 | 0 | 4438.44 | CGST 0% URD I/P | 0 | 4438.44 | 4438.44 | Approved | 0 | 0 | 140 | 16 Aug 2021
GANGA DHAM TOWERS | 493 | 91215 | 16 Aug 2021 | 218 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 742 | D Bldg North Side External Plaster | External Plaster- BC | 300 | Sq.Ft | 28 | 100 | 210 | 0 | 8400 | C+S GST 18% I/P RD | 1512 | 9912 | 9912 | Approved | 0 | 0 | 454 | 16 Aug 2021
GANGA DHAM TOWERS | 493 | 91215 | 16 Aug 2021 | 218 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 742 | D Bldg South Side External Plaster | External Plaster- BC | 1057.1429 | Sq.Ft | 35 | 100 | 925 | 0 | 37000 | C+S GST 18% I/P RD | 6660 | 43660 | 43660 | Approved | 0 | 0 | 454 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.605 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.701 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.905 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.901 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.805 Electrical Work | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.601 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.604 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.702 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.802 Refuge Flat Electrical | Primary Light Pt. (Controlled by Sw. Board) | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.602 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.705 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.703 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.904 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.603 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.601 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.801 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.701 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.802 Refuge Flat Electrical | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.803 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.704 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.904 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.902 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.703 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.603 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.604 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.602 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.702 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.804 Electrical Work | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.901 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.701 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.805 Electrical Work | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.804 Electrical Work | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.603 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.704 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.803 Electrical Work | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.904 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.601 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.705 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.604 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.801 Electrical Work | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.602 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.702 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.904 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.801 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.903 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.605 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.905 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.705 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.701 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.702 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.703 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.603 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.901 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.705 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.601 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.904 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.701 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.704 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.903 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.901 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.602 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.801 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.905 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.703 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.604 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.902 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.804 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.605 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 5 | No. | 220 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.702 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.803 Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.603 Electrical Work - 0 No. | Power Point (2.5 & 1.5 Sqmm) | 4 | No. | 220 | 20 | 4.4 | 0 | 176 | C+S GST 18% I/P RD | 31.68 | 207.68 | 207.68 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.902 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.905 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.903 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.605 Electrical Work - 0 No. | Gyser Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.703 Electrical Work - 0 No. | Gyser Point BC | 1 | No. | 220 | 20 | 1.1 | 0 | 44 | C+S GST 18% I/P RD | 7.92 | 51.92 | 51.92 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.702 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.901 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.705 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.605 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.902 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.601 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.803 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.701 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.705 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.903 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.704 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.804 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.605 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.703 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.801 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.902 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.601 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.904 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.901 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.701 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.905 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.702 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.805 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.603 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.602 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.604 Electrical Work - 0 No. | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.803 Electrical Work | 6 AMP Plug point (Independent) | 10 | No. | 200 | 20 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.903 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.602 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.905 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.703 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.603 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.801 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.904 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.805 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.704 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.604 Electrical Work - 0 No. | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.804 Electrical Work | Invertor Point- cc | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.704 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.805 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.803 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.903 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.804 Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.605 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.902 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.905 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.901 Electrical Work - 0 No. | Primary Light Pt. (Controlled by Sw. Board) | 9 | No. | 200 | 20 | 9 | 0 | 360 | C+S GST 18% I/P RD | 64.8 | 424.8 | 424.8 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.602 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.804 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.902 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.601 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.704 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.803 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.805 Electrical Work | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.604 Electrical Work - 0 No. | Bell Point BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.705 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.801 Electrical Work | 16 Way SPN DB | 1 | No. | 1100 | 20 | 5.5 | 0 | 220 | C+S GST 18% I/P RD | 39.6 | 259.6 | 259.6 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 452 | 91214 | 16 Aug 2021 | 203 | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS | EV - 1082 | D Bldg Flat No.903 Electrical Work - 0 No. | 16 Way SPN DB | 1 | No. | 1000 | 20 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 247 | 16 Aug 2021
GANGA DHAM TOWERS | 1112 | 91203 | 14 Aug 2021 | 356 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 954 | B1- 1101 False Ceiling&Wall Punning Work | Wall Gypsum Plaster (M+L) | 414 | Sq.Ft | 24 | 100 | 248.4 | 0 | 9936 | C+S GST 18% I/P RD | 1788.48 | 11724.48 | 11724.48 | Approved | 0 | 0 | 539 | 14 Aug 2021
GANGA DHAM TOWERS | 1112 | 91203 | 14 Aug 2021 | 356 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 954 | B1- 1101 False Ceiling&Wall Punning Work | Gypsum False Ceiling (M+L) - BC | 586.32 | Sq.Ft | 75 | 100 | 1099.35 | 0 | 43974 | C+S GST 18% I/P RD | 7915.32 | 51889.32 | 51889.32 | Approved | 0 | 0 | 539 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.702 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.801 Electrical Work | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.602 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.902 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 25 | 4.13 | 0 | 165 | C+S GST 18% I/P RD | 29.7 | 194.7 | 194.7 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.603 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.705 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.601 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.804 Electrical Work | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.604 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.605 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.601 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.803 Electrical Work | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.802 Refuge Flat Electrical | Wall Light Point | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.703 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.804 Electrical Work | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.902 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.705 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.704 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.701 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.603 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.801 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.904 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.704 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.701 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.601 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.604 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.705 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.902 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.804 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.605 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.803 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.904 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.805 Electrical Work | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.702 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.705 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.904 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.805 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.605 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.701 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.801 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.602 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.704 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.703 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.604 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.904 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.702 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.803 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.703 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.805 Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 15 | 0.75 | 0 | 30 | C+S GST 18% I/P RD | 5.4 | 35.4 | 35.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.602 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.902 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.603 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.605 Electrical Work - 0 No. | Video Door Phone (L)- BC | 1 | No. | 200 | 20 | 1 | 0 | 40 | C+S GST 18% I/P RD | 7.2 | 47.2 | 47.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.702 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.703 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.601 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.904 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.902 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.805 Electrical Work | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.603 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.701 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.601 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.805 Electrical Work | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.904 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.703 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.801 Electrical Work | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.605 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.602 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.705 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.804 Electrical Work | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.902 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.603 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.701 Electrical Work - 0 No. | Fan Point | 4 | No. | 200 | 20 | 4 | 0 | 160 | C+S GST 18% I/P RD | 28.8 | 188.8 | 188.8 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.702 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.704 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.604 Electrical Work - 0 No. | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.803 Electrical Work | Fan Point | 3 | No. | 200 | 20 | 3 | 0 | 120 | C+S GST 18% I/P RD | 21.6 | 141.6 | 141.6 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.602 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.604 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.605 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.801 Electrical Work | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.904 Electrical Work - 0 No. | Wall Light Point | 6 | No. | 200 | 20 | 6 | 0 | 240 | C+S GST 18% I/P RD | 43.2 | 283.2 | 283.2 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.805 Electrical Work | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.702 Electrical Work - 0 No. | Wall Light Point | 7 | No. | 200 | 20 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.704 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.703 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.602 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.702 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.705 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.801 Electrical Work | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.604 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.601 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.701 Electrical Work - 0 No. | Secondary Light Points (Looping) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.802 Refuge Flat Electrical | Secondary Light Points (Looping) | 5 | No. | 67 | 20 | 1.68 | 0 | 67 | C+S GST 18% I/P RD | 12.06 | 79.06 | 79.06 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.603 Electrical Work - 0 No. | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.804 Electrical Work | Secondary Light Points (Looping) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.601 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.803 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.603 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.902 Electrical Work - 0 No. | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.804 Electrical Work | AC Point BC | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.602 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.603 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.805 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.801 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.605 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.701 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.901 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.703 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.905 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.804 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.902 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.705 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.601 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.803 Electrical Work | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.904 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.702 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.801 Electrical Work | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.803 Electrical Work | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.703 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.805 Electrical Work | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.701 Electrical Work - 0 No. | Telephone Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.704 Electrical Work - 0 No. | Telephone Point | 3 | No. | 220 | 20 | 3.3 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.803 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.704 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.602 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.604 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.903 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.605 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.804 Electrical Work | 6 AMP Plug point (Dependent) | 6 | No. | 67 | 20 | 2.01 | 0 | 80.4 | C+S GST 18% I/P RD | 14.48 | 94.88 | 94.88 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.705 Electrical Work - 0 No. | 6 AMP Plug point (Dependent) | 8 | No. | 67 | 20 | 2.68 | 0 | 107.2 | C+S GST 18% I/P RD | 19.3 | 126.5 | 126.5 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.604 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 452 | 91198 | 14 Aug 2021 |  | SAHOO ELECTRICAL | HARISH CHANDRA JADHAV ELECTRICALS |  | D Bldg Flat No.704 Electrical Work - 0 No. | TV Point | 2 | No. | 220 | 20 | 2.2 | 0 | 88 | C+S GST 18% I/P RD | 15.84 | 103.84 | 103.84 |  | 0 | 0 | 174 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 1602 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.5 | No. | 1400 | 100 | 52.5 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 304 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 402 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 602 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 604 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 404 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 401 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 603 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 601 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 403 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.7 | No. | 1000 | 100 | 42.5 | 0 | 1700 | CGST 0% URD I/P | 0 | 1700 | 1700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 1002 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.25 | No. | 1200 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 1003 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.25 | No. | 1200 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 701 Internal Plumbing PPR-C | Int Flat PPRC Work. | 1.25 | No. | 1200 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 1001 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.25 | No. | 1200 | 100 | 67.5 | 0 | 2700 | CGST 0% URD I/P | 0 | 2700 | 2700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 455 | 91197 | 14 Aug 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 822 | A Bldg Flat No. 903 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.25 | No. | 1200 | 100 | 67.5 | 0 | 2700 | CGST 0% URD I/P | 0 | 2700 | 2700 | Approved | 0 | 0 | 273 | 14 Aug 2021
GANGA DHAM TOWERS | 1114 | 91195 | 14 Aug 2021 | GDT-02 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 833 | B 901 Walls Satin Matt Painting | Oil base Primer-BC | 4540.16 | Sq.Ft | 1 | 100 | 113.5 | 0 | 4540.16 | IGST 18% I/P RD | 817.23 | 5357.39 | 5357.39 | Approved | 0 | 0 | 272 | 14 Aug 2021
GANGA DHAM TOWERS | 1114 | 91195 | 14 Aug 2021 | GDT-02 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 833 | B 1401 Walls Satin Matt Painting | Oil base Primer-BC | 4256.4 | Sq.Ft | 1 | 100 | 106.41 | 0 | 4256.4 | IGST 18% I/P RD | 766.15 | 5022.55 | 5022.55 | Approved | 0 | 0 | 272 | 14 Aug 2021
GANGA DHAM TOWERS | 1114 | 91195 | 14 Aug 2021 | GDT-02 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 833 | B 1301 Walls Satin Matt Painting | Oil base Primer-BC | 4256.4 | Sq.Ft | 1 | 100 | 106.41 | 0 | 4256.4 | IGST 18% I/P RD | 766.15 | 5022.55 | 5022.55 | Approved | 0 | 0 | 272 | 14 Aug 2021
GANGA DHAM TOWERS | 1114 | 91195 | 14 Aug 2021 | GDT-02 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 833 | B 301 Walls Satin Matt Painting | Oil base Primer-BC | 4540.16 | Sq.Ft | 1 | 100 | 113.5 | 0 | 4540.16 | IGST 18% I/P RD | 817.23 | 5357.39 | 5357.39 | Approved | 0 | 0 | 272 | 14 Aug 2021
GANGA DHAM TOWERS | 1114 | 91195 | 14 Aug 2021 | GDT-02 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 833 | B 202 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 3115.864 | Sq.Ft | 1.25 | 100 | 97.37 | 0 | 3894.83 | IGST 18% I/P RD | 701.07 | 4595.9 | 4595.9 | Approved | 0 | 0 | 272 | 14 Aug 2021
GANGA DHAM TOWERS | 1114 | 91195 | 14 Aug 2021 | GDT-02 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 833 | B 301 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 4540.16 | Sq.Ft | 1.25 | 100 | 141.88 | 0 | 5675.2 | IGST 18% I/P RD | 1021.54 | 6696.74 | 6696.74 | Approved | 0 | 0 | 272 | 14 Aug 2021
GANGA DHAM TOWERS | 1002 | 91194 | 14 Aug 2021 | 8 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 952 | A 1401 NOC | Concrete wall Crushing work | 1.0081 | Cu.Mtrs | 7200 | 100 | 181.46 | 0 | 7258 | C+S GST 18% I/P RD | 1306.44 | 8564.44 | 8564.44 | Approved | 0 | 0 | 2549 | 14 Aug 2021
GANGA DHAM TOWERS | 1002 | 91194 | 14 Aug 2021 | 8 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 952 | A 2002 NOC | Concrete wall Crushing work | 1.15 | Cu.Mtrs | 7200 | 100 | 207 | 0 | 8280 | C+S GST 18% I/P RD | 1490.4 | 9770.4 | 9770.4 | Approved | 0 | 0 | 2549 | 14 Aug 2021
GANGA DHAM TOWERS | 1002 | 91194 | 14 Aug 2021 | 8 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 952 | A 2002 NOC | Concrete Cutting Work | 120.6305 | R.Ft | 525 | 100 | 1583.28 | 0 | 63331 | C+S GST 18% I/P RD | 11399.58 | 74730.58 | 74730.58 | Approved | 0 | 0 | 2549 | 14 Aug 2021
GANGA DHAM TOWERS | 1002 | 91194 | 14 Aug 2021 | 8 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 952 | A 1401 NOC | Concrete Cutting Work | 92.52 | R.Ft | 525 | 100 | 1214.33 | 0 | 48573 | C+S GST 18% I/P RD | 8743.14 | 57316.14 | 57316.14 | Approved | 0 | 0 | 2549 | 14 Aug 2021
GANGA DHAM TOWERS | 1116 | 91193 | 14 Aug 2021 | fy-21-22/sept003 | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 949 | B 1 - 1101 Waterproofing work | Chemical W/P - Bco | 2000 | Sq.Ft | 60 | 100 | 12000 | 0 | 120000 | C+S GST 18% I/P RD | 21600 | 141600 | 141600 | Approved | 0 | 0 | 1200 | 14 Aug 2021
GANGA DHAM TOWERS | 856 | 91192 | 13 Aug 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 699 | Club House Internal+Landscape BBM/Plaster (L) - 1 No. | Rough Plaster | 5917.32 | Sq.Ft | 15 | 100 | 2219 | 0 | 88759.8 | C+S GST 18% I/P RD | 0 | 88759.8 | 88759.8 | Approved | 0 | 200000 | 2140 | 13 Aug 2021
GANGA DHAM TOWERS | 856 | 91192 | 13 Aug 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 699 | Club House Internal+Landscape BBM/Plaster (L) - 1 No. | Brickwork 6" DCH | 1745.99 | Sq.Ft | 18 | 100 | 785.7 | 0 | 31427.82 | C+S GST 18% I/P RD | 0 | 31427.82 | 31427.82 | Approved | 0 | 200000 | 2140 | 13 Aug 2021
GANGA DHAM TOWERS | 856 | 91192 | 13 Aug 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 699 | Club House Internal+Landscape BBM/Plaster (L) - 1 No. | BBM for Steps-SRMC | 376.02 | R.Ft | 50 | 100 | 470.03 | 0 | 18801 | C+S GST 18% I/P RD | 2522.56 | 21323.56 | 21323.56 | Approved | 0 | 200000 | 2140 | 13 Aug 2021
GANGA DHAM TOWERS | 856 | 91192 | 13 Aug 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 699 | Club House Internal+Landscape BBM/Plaster (L) - 1 No. | Brickwork 4" DCH | 319.55 | Sq.Ft | 20 | 100 | 159.78 | 0 | 6391 | C+S GST 18% I/P RD | 0 | 6391 | 6391 | Approved | 0 | 200000 | 2140 | 13 Aug 2021
GANGA DHAM TOWERS | 856 | 91192 | 13 Aug 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 699 | Club House Internal+Landscape BBM/Plaster (L) - 1 No. | Coping Work - BC - R.Ft | 345.42 | R.Ft | 12 | 100 | 103.63 | 0 | 4145.04 | C+S GST 18% I/P RD | 0 | 4145.04 | 4145.04 | Approved | 0 | 200000 | 2140 | 13 Aug 2021
GANGA DHAM TOWERS | 856 | 91192 | 13 Aug 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 699 | Club House Internal+Landscape BBM/Plaster (L) - 1 No. | Sand Face Plaster DCH | 2303.2 | Sq.Ft | 28 | 100 | 1612.24 | 0 | 64489.6 | C+S GST 18% I/P RD | 0 | 64489.6 | 64489.6 | Approved | 0 | 200000 | 2140 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 404 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1004 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1204 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 204 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 601 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 0 | 8616 | 8616 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1101 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 0 | 8616 | 8616 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1701 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 0 | 8616 | 8616 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 201 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 0 | 8616 | 8616 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1001 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 0 | 8616 | 8616 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1501 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26925 | 40 | 215.4 | 0 | 8616 | C+S GST 18% I/P RD | 0 | 8616 | 8616 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 602 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 0 | 8324.8 | 8324.8 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 502 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 0 | 8324.8 | 8324.8 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 903 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 23237 | 40 | 185.9 | 0 | 7435.84 | C+S GST 18% I/P RD | 0 | 7435.84 | 7435.84 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 403 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 23237 | 40 | 185.9 | 0 | 7435.84 | C+S GST 18% I/P RD | 0 | 7435.84 | 7435.84 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1703 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 23237 | 40 | 185.9 | 0 | 7435.84 | C+S GST 18% I/P RD | 1338.46 | 8774.3 | 8774.3 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 803 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 23237 | 40 | 185.9 | 0 | 7435.84 | C+S GST 18% I/P RD | 0 | 7435.84 | 7435.84 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1003 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 23237 | 40 | 185.9 | 0 | 7435.84 | C+S GST 18% I/P RD | 0 | 7435.84 | 7435.84 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1403 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 23237 | 40 | 185.9 | 0 | 7435.84 | C+S GST 18% I/P RD | 994.46 | 8430.3 | 8430.3 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 1603 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 23237 | 40 | 185.9 | 0 | 7435.84 | C+S GST 18% I/P RD | 1338.46 | 8774.3 | 8774.3 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 1118 | 91191 | 13 Aug 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 700 | A 604 Electrical Work (L) | Electrical Work (Labour) -Bco | 0.8 | No. | 26015 | 40 | 208.12 | 0 | 8324.8 | C+S GST 18% I/P RD | 1498.46 | 9823.26 | 9823.26 | Approved | 0 | 100000 | 1620 | 13 Aug 2021
GANGA DHAM TOWERS | 630 | 91190 | 13 Aug 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 684 | A 1101 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1170.776 | Sq.Ft | 50 | 100 | 0 | 0 | 58538.8 | C+S GST 18% I/P RD | 10536.98 | 69075.78 | 69075.78 | Approved | 0 | 50000 | 0 | 13 Aug 2021
GANGA DHAM TOWERS | 630 | 91190 | 13 Aug 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 684 | A 301 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1400 | Sq.Ft | 50 | 100 | 0 | 0 | 70000 | C+S GST 18% I/P RD | 3600 | 73600 | 73600 | Approved | 0 | 50000 | 0 | 13 Aug 2021
GANGA DHAM TOWERS | 774 | 91181 | 13 Aug 2021 | 107 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 728 | B Parking Floor 3 Trimix work | Trimix Work - BC | 15000 | Sq.Ft | 9 | 100 | 3375 | 0 | 135000 | C+S GST 18% I/P RD | 24300 | 159300 | 159300 | Approved | 0 | 0 | 1732 | 13 Aug 2021
GANGA DHAM TOWERS | 774 | 91181 | 13 Aug 2021 | 107 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 728 | B Parking Floor 2 Trimix work | Trimix Work - BC | 2321 | Sq.Ft | 9 | 100 | 522.23 | 0 | 20889 | C+S GST 18% I/P RD | 3760.02 | 24649.02 | 24649.02 | Approved | 0 | 0 | 1732 | 13 Aug 2021
GANGA DHAM TOWERS | 774 | 91181 | 13 Aug 2021 | 107 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 728 | B Parking Floor 3 Trimix work | Weld mesh fixing(L) BCo | 15000 | Sq.Ft | 1 | 100 | 375 | 0 | 15000 | C+S GST 18% I/P RD | 2700 | 17700 | 17700 | Approved | 0 | 0 | 1732 | 13 Aug 2021
GANGA DHAM TOWERS | 774 | 91181 | 13 Aug 2021 | 107 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 728 | B Parking Floor 2 Trimix work | Weld mesh fixing(L) BCo | 2321 | Sq.Ft | 1 | 100 | 58.03 | 0 | 2321 | C+S GST 18% I/P RD | 417.78 | 2738.78 | 2738.78 | Approved | 0 | 0 | 1732 | 13 Aug 2021
GANGA DHAM TOWERS | 724 | 91180 | 13 Aug 2021 | 108 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 754 | A Parking Floor 2 Trimix work | Weld mesh fixing(L) BCo | 11099 | Sq.Ft | 1 | 100 | 277.48 | 0 | 11099 | C+S GST 18% I/P RD | 1997.82 | 13096.82 | 13096.82 | Approved | 0 | 0 | 1110 | 13 Aug 2021
GANGA DHAM TOWERS | 724 | 91180 | 13 Aug 2021 | 108 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 754 | A Parking Floor 2 Trimix work | Trimix Work - BC | 11099 | Sq.Ft | 9 | 100 | 2497.28 | 0 | 99891 | C+S GST 18% I/P RD | 17980.38 | 117871.38 | 117871.38 | Approved | 0 | 0 | 1110 | 13 Aug 2021
GANGA DHAM TOWERS | 604 | 91176 | 12 Aug 2021 | 19 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 744 | A Sprinkler System | Rossete Plate (L) | 180 | No. | 20 | 100 | 0 | 0 | 3600 | C+S GST 18% I/P RD | 648 | 4248 | 4248 | Approved | 0 | 0 | 53 | 12 Aug 2021
GANGA DHAM TOWERS | 604 | 91176 | 12 Aug 2021 | 19 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 744 | A Sprinkler System | Rossete Plate (L) | 5 | No. | 20 | 100 | 0 | 0 | 100 | C+S GST 18% I/P RD | 18 | 118 | 118 | Approved | 0 | 0 | 53 | 12 Aug 2021
GANGA DHAM TOWERS | 604 | 91176 | 12 Aug 2021 | 19 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 744 | A Sprinkler System | Flexible Hose Pipe 25mm Dia (1mtr length) (L) | 8 | No. | 205 | 100 | 41 | 0 | 1640 | C+S GST 18% I/P RD | 295.2 | 1935.2 | 1935.2 | Approved | 0 | 0 | 53 | 12 Aug 2021
GANGA DHAM TOWERS | 623 | 91175 | 12 Aug 2021 | 092 | DIVINE ENTERPRISES | DIVINE ENTERPRISES | EV - 702 | A 10th Floor Lobby Planter GI Frame | G.I. Frame (M) | 2 | No. | 2300 | 100 | 0 | 0 | 4600 | C+S GST 18% I/P RD | 828 | 5428 | 5428 | Approved | 0 | 0 | 0 | 12 Aug 2021
GANGA DHAM TOWERS | 623 | 91175 | 12 Aug 2021 | 092 | DIVINE ENTERPRISES | DIVINE ENTERPRISES | EV - 702 | A 9th Floor Lobby Planter GI Frame | G.I. Frame (M) | 6 | No. | 2300 | 100 | 0 | 0 | 13800 | C+S GST 18% I/P RD | 2484 | 16284 | 16284 | Approved | 0 | 0 | 0 | 12 Aug 2021
GANGA DHAM TOWERS | 623 | 91175 | 12 Aug 2021 | 092 | DIVINE ENTERPRISES | DIVINE ENTERPRISES | EV - 702 | A 2nd Floor Lobby Planter GI Frame | G.I. Frame (M) | 6 | No. | 2300 | 100 | 0 | 0 | 13800 | C+S GST 18% I/P RD | 2484 | 16284 | 16284 | Approved | 0 | 0 | 0 | 12 Aug 2021
GANGA DHAM TOWERS | 497 | 91174 | 12 Aug 2021 | 42 | J K INTERIOR | J K INTERIOR | EV - 703 | B 1802 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 193 | 12 Aug 2021
GANGA DHAM TOWERS | 497 | 91174 | 12 Aug 2021 | 42 | J K INTERIOR | J K INTERIOR | EV - 703 | B 1802 Gypsum Plaster | Gypsum on Wall (L) | 3580 | Sq.Ft | 4 | 100 | 358 | 0 | 14320 | C+S GST 18% I/P RD | 2577.6 | 16897.6 | 16897.6 | Approved | 0 | 0 | 193 | 12 Aug 2021
GANGA DHAM TOWERS | 634 | 91172 | 12 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 701 | A 1st Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 3660 | 12 Aug 2021
GANGA DHAM TOWERS | 634 | 91172 | 12 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 701 | A 1st Floor Lobbby Flooring | Vitrified Skirting -Bco | 45 | R.Ft | 45 | 100 | 50.63 | 0 | 2025 | C+S GST 18% I/P RD | 364.5 | 2389.5 | 2389.5 | Approved | 0 | 0 | 3660 | 12 Aug 2021
GANGA DHAM TOWERS | 634 | 91172 | 12 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 701 | A 1st Floor Lobbby Flooring | Vitrified Flooring -Bco | 600 | Sq.Ft | 45 | 100 | 675 | 0 | 27000 | C+S GST 18% I/P RD | 4860 | 31860 | 31860 | Approved | 0 | 0 | 3660 | 12 Aug 2021
GANGA DHAM TOWERS | 634 | 91172 | 12 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 701 | A 1st Floor Lift cladding | Italian Marble Bull Nosing | 573.8947 | R.Ft | 76 | 100 | 1090.4 | 0 | 43616 | C+S GST 18% I/P RD | 7850.88 | 51466.88 | 51466.88 | Approved | 0 | 0 | 3660 | 12 Aug 2021
GANGA DHAM TOWERS | 634 | 91172 | 12 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 701 | A 1st Floor Lift cladding | Dado Work - BC | 30 | Sq.Ft | 70 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 3660 | 12 Aug 2021
GANGA DHAM TOWERS | 634 | 91172 | 12 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 701 | A 1st Floor Lift cladding | V Grove - BCo | 137.8056 | R.Ft | 108 | 100 | 372.08 | 0 | 14883 | C+S GST 18% I/P RD | 2678.94 | 17561.94 | 17561.94 | Approved | 0 | 0 | 3660 | 12 Aug 2021
GANGA DHAM TOWERS | 634 | 91172 | 12 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 701 | A 1st Floor Lift cladding | Italian Marble Border-BCo | 297.8723 | R.Ft | 94 | 100 | 700 | 0 | 28000 | C+S GST 18% I/P RD | 5040 | 33040 | 33040 | Approved | 0 | 0 | 3660 | 12 Aug 2021
GANGA DHAM TOWERS | 634 | 91172 | 12 Aug 2021 |  | R K INTERIOR | R K INTERIOR | EV - 701 | A 1st Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 3660 | 12 Aug 2021
GANGA DHAM TOWERS | 389 | 91171 | 12 Aug 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 663 | Loading / Unloading Expenses | Unloading of tiles. | 24 | Metric Tonnes | 130 | 100 | 0 | 0 | 3120 | CGST 0% URD I/P | 0 | 3120 | 3120 | Approved | 0 | 0 | 0 | 12 Aug 2021
GANGA DHAM TOWERS | 604 | 91165 | 12 Aug 2021 | 20 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 756 | A Sprinkler System | Chilly Support for Sprinkler Pipe-(L) | 960 | No. | 9 | 100 | 216 | 0 | 8640 | C+S GST 18% I/P RD | 1555.2 | 10195.2 | 10195.2 | Approved | 0 | 0 | 698 | 12 Aug 2021
GANGA DHAM TOWERS | 604 | 91165 | 12 Aug 2021 | 20 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 756 | A 2nd Floor Internal Flat Sprinkler System | SITC GI Pipe C Class 32mm dia.(L) | 15.1848 | Mtrs | 92 | 100 | 34.93 | 0 | 1397 | C+S GST 18% I/P RD | 251.46 | 1648.46 | 1648.46 | Approved | 0 | 0 | 698 | 12 Aug 2021
GANGA DHAM TOWERS | 604 | 91165 | 12 Aug 2021 | 20 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 756 | A Sprinkler System | Flexible Hose Pipe 25mm Dia (1mtr length) (L) | 198 | No. | 205 | 100 | 1014.75 | 0 | 40590 | C+S GST 18% I/P RD | 7306.2 | 47896.2 | 47896.2 | Approved | 0 | 0 | 698 | 12 Aug 2021
GANGA DHAM TOWERS | 604 | 91165 | 12 Aug 2021 | 20 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 756 | A Sprinkler System | Sprinkler 15mm 68 dg Pendent (L) | 180 | No. | 57 | 100 | 256.5 | 0 | 10260 | C+S GST 18% I/P RD | 1846.8 | 12106.8 | 12106.8 | Approved | 0 | 0 | 698 | 12 Aug 2021
GANGA DHAM TOWERS | 604 | 91165 | 12 Aug 2021 | 20 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 756 | A Sprinkler System | SITC Ball Valve 50mm (L) | 16 | No. | 560 | 100 | 224 | 0 | 8960 | C+S GST 18% I/P RD | 1612.8 | 10572.8 | 10572.8 | Approved | 0 | 0 | 698 | 12 Aug 2021
GANGA DHAM TOWERS | 758 | 91158 | 11 Aug 2021 | 46 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 747 | B 1602 Ceramic Tiling | Ceramic Flooring work | 356.56 | Sq.Ft | 18 | 100 | 160.45 | 0 | 6418.08 | C+S GST 18% I/P RD | 1155.26 | 7573.34 | 7573.34 | Approved | 0 | 0 | 688 | 11 Aug 2021
GANGA DHAM TOWERS | 758 | 91158 | 11 Aug 2021 | 46 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 747 | B 1602 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 55 | 100 | 282.69 | 0 | 11307.45 | C+S GST 18% I/P RD | 2035.34 | 13342.79 | 13342.79 | Approved | 0 | 0 | 688 | 11 Aug 2021
GANGA DHAM TOWERS | 758 | 91158 | 11 Aug 2021 | 46 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 747 | B 1602 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 55 | 100 | 906.9 | 0 | 36275.8 | C+S GST 18% I/P RD | 6529.64 | 42805.44 | 42805.44 | Approved | 0 | 0 | 688 | 11 Aug 2021
GANGA DHAM TOWERS | 758 | 91158 | 11 Aug 2021 | 46 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 747 | B 1602 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 55 | 100 | 370.45 | 0 | 14818.1 | C+S GST 18% I/P RD | 2667.26 | 17485.36 | 17485.36 | Approved | 0 | 0 | 688 | 11 Aug 2021
GANGA DHAM TOWERS | 1070 | 91154 | 10 Aug 2021 |  | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 638 | Lab Performance Test For Strip Window System | Testing & Certification Charges | 1 | No. | 90000 | 50 | 0 | 0 | 45000 | C+S GST 18% I/P RD | 8100 | 53100 | 53100 | Approved | 0 | 0 | 3600 | 10 Aug 2021
GANGA DHAM TOWERS | 1070 | 91154 | 10 Aug 2021 |  | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 638 | Lab Performance Test For Strip Window System | Testing & Certification Charges | 1 | No. | 45000 | 50 | 0 | 0 | 22500 | C+S GST 18% I/P RD | 4050 | 26550 | 26550 | Approved | 0 | 0 | 3600 | 10 Aug 2021
GANGA DHAM TOWERS | 1070 | 91154 | 10 Aug 2021 |  | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 638 | Lab Performance Test For Strip Window System | Testing & Certification Charges | 1 | No. | 45000 | 50 | 0 | 0 | 22500 | C+S GST 18% I/P RD | 4050 | 26550 | 26550 | Approved | 0 | 0 | 3600 | 10 Aug 2021
GANGA DHAM TOWERS | 1070 | 91154 | 10 Aug 2021 |  | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 638 | Lab Performance Test For Strip Window System | Testing & Certification Charges | 1 | No. | 90000 | 50 | 0 | 0 | 45000 | C+S GST 18% I/P RD | 8100 | 53100 | 53100 | Approved | 0 | 0 | 3600 | 10 Aug 2021
GANGA DHAM TOWERS | 1070 | 91154 | 10 Aug 2021 |  | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 638 | Lab Performance Test For Strip Window System | Testing & Certification Charges | 1 | No. | 45000 | 50 | 0 | 0 | 22500 | C+S GST 18% I/P RD | 4050 | 26550 | 26550 | Approved | 0 | 0 | 3600 | 10 Aug 2021
GANGA DHAM TOWERS | 1070 | 91154 | 10 Aug 2021 |  | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 638 | Lab Performance Test For Strip Window System | Testing & Certification Charges | 1 | No. | 45000 | 50 | 0 | 0 | 22500 | C+S GST 18% I/P RD | 4050 | 26550 | 26550 | Approved | 0 | 0 | 3600 | 10 Aug 2021
GANGA DHAM TOWERS | 1105 | 91141 | 07 Aug 2021 | 350 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 666 | A 902 Terrace False Ceiling | PVC False Ceiling (M) | 156.08 | Sq.Ft | 50 | 100 | 0 | 0 | 7804 | C+S GST 18% I/P RD | 1404.72 | 9208.72 | 9208.72 | Approved | 0 | 0 | 0 | 07 Aug 2021
GANGA DHAM TOWERS | 1105 | 91141 | 07 Aug 2021 | 350 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 666 | A 204 Terrace False Ceiling | PVC False Ceiling (M) | 177.61 | Sq.Ft | 50 | 100 | 0 | 0 | 8880.5 | C+S GST 18% I/P RD | 1598.5 | 10479 | 10479 | Approved | 0 | 0 | 0 | 07 Aug 2021
GANGA DHAM TOWERS | 1104 | 91140 | 07 Aug 2021 | 351 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 668 | A 902 Terrace False Ceiling | PVC False Ceiling (L) | 156.08 | Sq.Ft | 20 | 100 | 78.04 | 0 | 3121.6 | C+S GST 18% I/P RD | 561.88 | 3683.48 | 3683.48 | Approved | 0 | 0 | 67 | 07 Aug 2021
GANGA DHAM TOWERS | 1104 | 91140 | 07 Aug 2021 | 351 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 668 | A 204 Terrace False Ceiling | PVC False Ceiling (L) | 177.61 | Sq.Ft | 20 | 100 | 88.81 | 0 | 3552.2 | C+S GST 18% I/P RD | 639.4 | 4191.6 | 4191.6 | Approved | 0 | 0 | 67 | 07 Aug 2021
GANGA DHAM TOWERS | 634 | 91137 | 07 Aug 2021 | 2021-22-030 | R K INTERIOR | R K INTERIOR | EV - 743 | A 3rd Floor Lift cladding | Italian Marble Mirror Polish- BCo | 28 | Sq.Ft | 58 | 100 | 40.6 | 0 | 1624 | C+S GST 18% I/P RD | 292.32 | 1916.32 | 1916.32 | Approved | 0 | 0 | 389 | 07 Aug 2021
GANGA DHAM TOWERS | 634 | 91137 | 07 Aug 2021 | 2021-22-030 | R K INTERIOR | R K INTERIOR | EV - 743 | A 3rd Floor Lift cladding | Italian Marble Border-BCo | 12 | R.Ft | 94 | 100 | 28.2 | 0 | 1128 | C+S GST 18% I/P RD | 203.04 | 1331.04 | 1331.04 | Approved | 0 | 0 | 389 | 07 Aug 2021
GANGA DHAM TOWERS | 634 | 91137 | 07 Aug 2021 | 2021-22-030 | R K INTERIOR | R K INTERIOR | EV - 743 | A 3rd Floor Lift cladding | Italian Marble Edge Polish- BCo | 51 | R.Ft | 31 | 100 | 39.53 | 0 | 1581 | C+S GST 18% I/P RD | 284.58 | 1865.58 | 1865.58 | Approved | 0 | 0 | 389 | 07 Aug 2021
GANGA DHAM TOWERS | 634 | 91137 | 07 Aug 2021 | 2021-22-030 | R K INTERIOR | R K INTERIOR | EV - 743 | A 3rd Floor Lift cladding | Italian Marble Bull Nosing | 20 | R.Ft | 76 | 100 | 38 | 0 | 1520 | C+S GST 18% I/P RD | 273.6 | 1793.6 | 1793.6 | Approved | 0 | 0 | 389 | 07 Aug 2021
GANGA DHAM TOWERS | 634 | 91137 | 07 Aug 2021 | 2021-22-030 | R K INTERIOR | R K INTERIOR | EV - 743 | A 3rd Floor Lift cladding | Italian Marble Cladding - BCo | 132 | Sq.Ft | 103 | 100 | 339.9 | 0 | 13596 | C+S GST 18% I/P RD | 2447.28 | 16043.28 | 16043.28 | Approved | 0 | 0 | 389 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Italian Marble Counter - Mkt | 13.32 | R.Ft | 1476 | 100 | 491.51 | 0 | 19660.32 | C+S GST 18% I/P RD | 3538.86 | 23199.18 | 23199.18 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Vitrified Skirting work | 62.6132 | R.Ft | 28.7 | 100 | 44.92 | 0 | 1797 | C+S GST 18% I/P RD | 323.46 | 2120.46 | 2120.46 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Granite Edge Polish (L) | 24.6 | R.Ft | 28.7 | 100 | 17.65 | 0 | 706.02 | C+S GST 18% I/P RD | 127.08 | 833.1 | 833.1 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Italian marble Skirting - BCo | 47.9559 | R.Ft | 86.1 | 100 | 103.23 | 0 | 4129 | C+S GST 18% I/P RD | 743.22 | 4872.22 | 4872.22 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | L Grove - BCo | 130.87 | R.Ft | 123 | 100 | 402.43 | 0 | 16097.01 | C+S GST 18% I/P RD | 2897.46 | 18994.47 | 18994.47 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Italian Marble Edge Polish | 285.23 | R.Ft | 28.7 | 100 | 204.65 | 0 | 8186.1 | C+S GST 18% I/P RD | 1473.5 | 9659.6 | 9659.6 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Dado Fixing | 146 | Sq.Ft | 61.5 | 100 | 224.48 | 0 | 8979 | C+S GST 18% I/P RD | 1616.22 | 10595.22 | 10595.22 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Italian Marble Mirror Polish- BCo | 952.61 | Sq.Ft | 53.3 | 100 | 1269.35 | 0 | 50774.11 | C+S GST 18% I/P RD | 9139.34 | 59913.45 | 59913.45 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Granite Platform- SOf | 19.84 | R.Ft | 656 | 100 | 325.38 | 0 | 13015.04 | C+S GST 18% I/P RD | 2342.7 | 15357.74 | 15357.74 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 396 | 91136 | 07 Aug 2021 | 2021-22-031 | R K INTERIOR | R K INTERIOR | EV - 778 | A 3rd Fl. Mock up Tiling Work Flat No. 304 | Italian Marble Champher Polish (L) | 47.9484 | R.Ft | 69.7 | 100 | 83.55 | 0 | 3342 | C+S GST 18% I/P RD | 601.56 | 3943.56 | 3943.56 | Approved | 0 | 0 | 2534 | 07 Aug 2021
GANGA DHAM TOWERS | 1135 | 91135 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 752 | Old Sales office Fabrication Work | Department Labour - Day | 10 | Day | 750 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 147 | 07 Aug 2021
GANGA DHAM TOWERS | 1135 | 91135 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 752 | Old Sales office Fabrication Work | MS Frame Making & Fixing | 220 | Sq.Ft | 10 | 100 | 55 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 147 | 07 Aug 2021
GANGA DHAM TOWERS | 1135 | 91135 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 752 | Old Sales office Fabrication Work | Department Labour - Day | 10 | Day | 500 | 100 | 125 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 147 | 07 Aug 2021
GANGA DHAM TOWERS | 1136 | 91134 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 751 | A P2 Parking MS Work | MS Frame Making & Fixing | 985.96 | Sq.Ft | 10 | 100 | 0 | 0 | 9859.6 | CGST 0% URD I/P | 0 | 9859.6 | 9859.6 | Approved | 0 | 0 | 99 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91133 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 757 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | Fabrication work (M) | 4.58 | Kgs | 65 | 100 | 0 | 0 | 297.7 | CGST 0% URD I/P | 0 | 297.7 | 297.7 | Approved | 0 | 0 | 8 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91133 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 757 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | Fastner (M) - SOSB | 20 | No. | 25 | 100 | 0 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 8 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91132 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 753 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | MS Angle (L) | 10 | No. | 20 | 100 | 5 | 0 | 200 | CGST 0% URD I/P | 0 | 200 | 200 | Approved | 0 | 0 | 213 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91132 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 753 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | Fabrication work (L) | 105 | Kgs | 17.5 | 100 | 45.94 | 0 | 1837.5 | CGST 0% URD I/P | 0 | 1837.5 | 1837.5 | Approved | 0 | 0 | 213 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91132 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 753 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | Meta colour Sheet Fixing BC | 1049.25 | Sq.Ft | 6 | 100 | 157.39 | 0 | 6295.5 | CGST 0% URD I/P | 0 | 6295.5 | 6295.5 | Approved | 0 | 0 | 213 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91132 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 753 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | Fabrication work (L) | 170.75 | Kgs | 21 | 100 | 89.64 | 0 | 3585.75 | CGST 0% URD I/P | 0 | 3585.75 | 3585.75 | Approved | 0 | 0 | 213 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91132 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 753 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | Fabrication work (L) | 196.88 | Kgs | 21 | 100 | 103.36 | 0 | 4134.48 | CGST 0% URD I/P | 0 | 4134.48 | 4134.48 | Approved | 0 | 0 | 213 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91132 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 753 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | Fabrication work (L) | 57.88 | Kgs | 21 | 100 | 30.39 | 0 | 1215.48 | CGST 0% URD I/P | 0 | 1215.48 | 1215.48 | Approved | 0 | 0 | 213 | 07 Aug 2021
GANGA DHAM TOWERS | 1137 | 91132 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 753 | Club House Metacolour Sheet Fixing at 1st floor - 1 No. | GI Sheet Fixing. | 20 | R.Ft | 200 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 213 | 07 Aug 2021
GANGA DHAM TOWERS | 1132 | 91131 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 727 | Old Labour Camp Fabrication Work | Sheet Removing - AIE | 21563 | Sq.Ft | 2 | 100 | 1078.15 | 0 | 43126 | CGST 0% URD I/P | 0 | 43126 | 43126 | Approved | 0 | 0 | 1438 | 07 Aug 2021
GANGA DHAM TOWERS | 1132 | 91131 | 07 Aug 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 727 | Old Labour Camp Fabrication Work | Fabrication work Removing | 16781 | Kgs | 6 | 100 | 2517.15 | 0 | 100686 | CGST 0% URD I/P | 0 | 100686 | 100686 | Approved | 0 | 0 | 1438 | 07 Aug 2021
GANGA DHAM TOWERS | 549 | 91130 | 07 Aug 2021 | 2021-22-034 | R K INTERIOR | R K INTERIOR | EV - 777 | B 302 Mock Up Tiling Work | Dado Fixing | 52.7967 | Sq.Ft | 61.5 | 100 | 81.17 | 0 | 3247 | C+S GST 18% I/P RD | 584.46 | 3831.46 | 3831.46 | Approved | 0 | 0 | 558 | 07 Aug 2021
GANGA DHAM TOWERS | 549 | 91130 | 07 Aug 2021 | 2021-22-034 | R K INTERIOR | R K INTERIOR | EV - 777 | B 301 Mock Up Tiling Work | Dado Fixing | 147.6748 | Sq.Ft | 61.5 | 100 | 227.05 | 0 | 9082 | C+S GST 18% I/P RD | 1634.76 | 10716.76 | 10716.76 | Approved | 0 | 0 | 558 | 07 Aug 2021
GANGA DHAM TOWERS | 549 | 91130 | 07 Aug 2021 | 2021-22-034 | R K INTERIOR | R K INTERIOR | EV - 777 | B 302 Mock Up Tiling Work | Vitrified Flooring work | 109.6864 | Sq.Ft | 28.7 | 100 | 78.7 | 0 | 3148 | C+S GST 18% I/P RD | 566.64 | 3714.64 | 3714.64 | Approved | 0 | 0 | 558 | 07 Aug 2021
GANGA DHAM TOWERS | 549 | 91130 | 07 Aug 2021 | 2021-22-034 | R K INTERIOR | R K INTERIOR | EV - 777 | B 301 Mock Up Tiling Work | Vitrified Flooring work | 122.9965 | Sq.Ft | 28.7 | 100 | 88.25 | 0 | 3530 | C+S GST 18% I/P RD | 635.4 | 4165.4 | 4165.4 | Approved | 0 | 0 | 558 | 07 Aug 2021
GANGA DHAM TOWERS | 549 | 91130 | 07 Aug 2021 | 2021-22-034 | R K INTERIOR | R K INTERIOR | EV - 777 | B 301 Mock Up Tiling Work | Granite Platform- SOf | 13.581 | R.Ft | 656 | 100 | 222.73 | 0 | 8909.14 | C+S GST 18% I/P RD | 1603.64 | 10512.78 | 10512.78 | Approved | 0 | 0 | 558 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 23rd Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 1st Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 22nd Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 24th Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 2nd Floor Lobby Flooring & cladding work - 1 Job | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 20th Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 3rd Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 19th Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 741 | 91129 | 07 Aug 2021 | 2021-22-033 | R K INTERIOR | R K INTERIOR | EV - 775 | B 21st Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 208.08 | Sq.Ft | 45 | 100 | 234.09 | 0 | 9363.6 | C+S GST 18% I/P RD | 1685.44 | 11049.04 | 11049.04 | Approved | 0 | 0 | 1685 | 07 Aug 2021
GANGA DHAM TOWERS | 493 | 91125 | 06 Aug 2021 | 219 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 741 | D Bldg North Side External Plaster | External Plaster- BC | 400 | Sq.Ft | 28 | 100 | 280 | 0 | 11200 | C+S GST 18% I/P RD | 2016 | 13216 | 13216 | Approved | 0 | 0 | 112 | 06 Aug 2021
GANGA DHAM TOWERS | 1105 | 91124 | 06 Aug 2021 | 352 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 665 | A 604 Terrace False Ceiling | PVC False Ceiling (M) | 177.61 | Sq.Ft | 50 | 100 | 0 | 0 | 8880.5 | C+S GST 18% I/P RD | 1598.5 | 10479 | 10479 | Approved | 0 | 0 | 0 | 06 Aug 2021
GANGA DHAM TOWERS | 1105 | 91124 | 06 Aug 2021 | 352 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 665 | A 401 Terrace False Ceiling | PVC False Ceiling (M) | 177.61 | Sq.Ft | 50 | 100 | 0 | 0 | 8880.5 | C+S GST 18% I/P RD | 1598.5 | 10479 | 10479 | Approved | 0 | 0 | 0 | 06 Aug 2021
GANGA DHAM TOWERS | 1105 | 91124 | 06 Aug 2021 | 352 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 665 | A 802 Terrace False Ceiling | PVC False Ceiling (M) | 177.61 | Sq.Ft | 50 | 100 | 0 | 0 | 8880.5 | C+S GST 18% I/P RD | 1598.5 | 10479 | 10479 | Approved | 0 | 0 | 0 | 06 Aug 2021
GANGA DHAM TOWERS | 1105 | 91124 | 06 Aug 2021 | 352 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 665 | A 602 Terrace False Ceiling | PVC False Ceiling (M) | 177.61 | Sq.Ft | 50 | 100 | 0 | 0 | 8880.5 | C+S GST 18% I/P RD | 1598.5 | 10479 | 10479 | Approved | 0 | 0 | 0 | 06 Aug 2021
GANGA DHAM TOWERS | 1105 | 91124 | 06 Aug 2021 | 352 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 665 | A 702 Terrace False Ceiling | PVC False Ceiling (M) | 156.08 | Sq.Ft | 50 | 100 | 0 | 0 | 7804 | C+S GST 18% I/P RD | 1404.72 | 9208.72 | 9208.72 | Approved | 0 | 0 | 0 | 06 Aug 2021
GANGA DHAM TOWERS | 1105 | 91124 | 06 Aug 2021 | 352 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 665 | A 402 Terrace False Ceiling | PVC False Ceiling (M) | 177.61 | Sq.Ft | 50 | 100 | 0 | 0 | 8880.5 | C+S GST 18% I/P RD | 1598.5 | 10479 | 10479 | Approved | 0 | 0 | 0 | 06 Aug 2021
GANGA DHAM TOWERS | 1105 | 91124 | 06 Aug 2021 | 352 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 665 | A 601 Terrace False Ceiling | PVC False Ceiling (M) | 177.61 | Sq.Ft | 50 | 100 | 0 | 0 | 8880.5 | C+S GST 18% I/P RD | 1598.5 | 10479 | 10479 | Approved | 0 | 0 | 0 | 06 Aug 2021
GANGA DHAM TOWERS | 1104 | 91123 | 06 Aug 2021 | 353 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 667 | A 802 Terrace False Ceiling | PVC False Ceiling (L) | 177.61 | Sq.Ft | 20 | 100 | 88.81 | 0 | 3552.2 | C+S GST 18% I/P RD | 639.4 | 4191.6 | 4191.6 | Approved | 0 | 0 | 244 | 06 Aug 2021
GANGA DHAM TOWERS | 1104 | 91123 | 06 Aug 2021 | 353 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 667 | A 604 Terrace False Ceiling | PVC False Ceiling (L) | 177.61 | Sq.Ft | 20 | 100 | 88.81 | 0 | 3552.2 | C+S GST 18% I/P RD | 639.4 | 4191.6 | 4191.6 | Approved | 0 | 0 | 244 | 06 Aug 2021
GANGA DHAM TOWERS | 1104 | 91123 | 06 Aug 2021 | 353 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 667 | A 401 Terrace False Ceiling | PVC False Ceiling (L) | 177.61 | Sq.Ft | 20 | 100 | 88.81 | 0 | 3552.2 | C+S GST 18% I/P RD | 639.4 | 4191.6 | 4191.6 | Approved | 0 | 0 | 244 | 06 Aug 2021
GANGA DHAM TOWERS | 1104 | 91123 | 06 Aug 2021 | 353 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 667 | A 702 Terrace False Ceiling | PVC False Ceiling (L) | 156.08 | Sq.Ft | 20 | 100 | 78.04 | 0 | 3121.6 | C+S GST 18% I/P RD | 561.88 | 3683.48 | 3683.48 | Approved | 0 | 0 | 244 | 06 Aug 2021
GANGA DHAM TOWERS | 1104 | 91123 | 06 Aug 2021 | 353 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 667 | A 601 Terrace False Ceiling | PVC False Ceiling (L) | 177.61 | Sq.Ft | 20 | 100 | 88.81 | 0 | 3552.2 | C+S GST 18% I/P RD | 639.4 | 4191.6 | 4191.6 | Approved | 0 | 0 | 244 | 06 Aug 2021
GANGA DHAM TOWERS | 1104 | 91123 | 06 Aug 2021 | 353 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 667 | A 602 Terrace False Ceiling | PVC False Ceiling (L) | 177.61 | Sq.Ft | 20 | 100 | 88.81 | 0 | 3552.2 | C+S GST 18% I/P RD | 639.4 | 4191.6 | 4191.6 | Approved | 0 | 0 | 244 | 06 Aug 2021
GANGA DHAM TOWERS | 1104 | 91123 | 06 Aug 2021 | 353 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 667 | A 402 Terrace False Ceiling | PVC False Ceiling (L) | 177.61 | Sq.Ft | 20 | 100 | 88.81 | 0 | 3552.2 | C+S GST 18% I/P RD | 639.4 | 4191.6 | 4191.6 | Approved | 0 | 0 | 244 | 06 Aug 2021
GANGA DHAM TOWERS | 1114 | 91122 | 06 Aug 2021 | GDT-03 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 834 | B 401 Walls Satin Matt Painting | Scrapping with 2nd Coat Putty | 4540.16 | Sq.Ft | 1.25 | 100 | 141.88 | 0 | 5675.2 | IGST 18% I/P RD | 1021.54 | 6696.74 | 6696.74 | Approved | 0 | 0 | 323 | 06 Aug 2021
GANGA DHAM TOWERS | 1114 | 91122 | 06 Aug 2021 | GDT-03 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 834 | B 202 Walls Satin Matt Painting | Oil base Primer-BC | 3115.864 | Sq.Ft | 1 | 100 | 77.9 | 0 | 3115.86 | IGST 18% I/P RD | 560.85 | 3676.71 | 3676.71 | Approved | 0 | 0 | 323 | 06 Aug 2021
GANGA DHAM TOWERS | 1114 | 91122 | 06 Aug 2021 | GDT-03 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 834 | B 401 Walls Satin Matt Painting | Oil base Primer-BC | 4540.16 | Sq.Ft | 1 | 100 | 113.5 | 0 | 4540.16 | IGST 18% I/P RD | 817.23 | 5357.39 | 5357.39 | Approved | 0 | 0 | 323 | 06 Aug 2021
GANGA DHAM TOWERS | 1114 | 91122 | 06 Aug 2021 | GDT-03 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 834 | B 1002 Walls Satin Matt Painting | Oil base Primer-BC | 3115.864 | Sq.Ft | 1 | 100 | 77.9 | 0 | 3115.86 | IGST 18% I/P RD | 560.85 | 3676.71 | 3676.71 | Approved | 0 | 0 | 323 | 06 Aug 2021
GANGA DHAM TOWERS | 1114 | 91122 | 06 Aug 2021 | GDT-03 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 834 | B 801 Walls Satin Matt Painting | Oil base Primer-BC | 4540.16 | Sq.Ft | 1 | 100 | 113.5 | 0 | 4540.16 | IGST 18% I/P RD | 817.23 | 5357.39 | 5357.39 | Approved | 0 | 0 | 323 | 06 Aug 2021
GANGA DHAM TOWERS | 1114 | 91122 | 06 Aug 2021 | GDT-03 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 834 | B 401 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 4540.16 | Sq.Ft | 1.25 | 100 | 141.88 | 0 | 5675.2 | IGST 18% I/P RD | 1021.54 | 6696.74 | 6696.74 | Approved | 0 | 0 | 323 | 06 Aug 2021
GANGA DHAM TOWERS | 1114 | 91122 | 06 Aug 2021 | GDT-03 | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 834 | B 801 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 4540.16 | Sq.Ft | 1.25 | 100 | 141.88 | 0 | 5675.2 | IGST 18% I/P RD | 1021.54 | 6696.74 | 6696.74 | Approved | 0 | 0 | 323 | 06 Aug 2021
GANGA DHAM TOWERS | 1037 | 91116 | 05 Aug 2021 | OM/2021-22/187 | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 631 | Head Office Security Service | Security Guard AIE - | 62 | Day | 419.35 | 100 | 0 | 0 | 25999.7 | C+S GST 18% I/P RD | 4679.94 | 30679.64 | 30679.64 | Approved | 0 | 0 | 260 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 3rd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 290 | Sq.Ft | 1 | 100 | 7.25 | 0 | 290 | CGST 0% URD I/P | 0 | 290 | 290 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 227 | Sq.Ft | 1 | 100 | 5.68 | 0 | 227 | CGST 0% URD I/P | 0 | 227 | 227 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-11th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-12th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 8th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-10th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104 | Sq.Ft | 1 | 100 | 2.6 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 6th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 4th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 6th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 290 | Sq.Ft | 1 | 100 | 7.25 | 0 | 290 | CGST 0% URD I/P | 0 | 290 | 290 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-14th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 227 | Sq.Ft | 1 | 100 | 5.68 | 0 | 227 | CGST 0% URD I/P | 0 | 227 | 227 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1st Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 7th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 227 | Sq.Ft | 1 | 100 | 5.68 | 0 | 227 | CGST 0% URD I/P | 0 | 227 | 227 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-12th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 2nd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 3rd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 17 | Sq.Ft | 1 | 100 | 0.43 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-16th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 50 | Sq.Ft | 1 | 100 | 1.25 | 0 | 50 | CGST 0% URD I/P | 0 | 50 | 50 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 143 | Sq.Ft | 1 | 100 | 3.58 | 0 | 143 | CGST 0% URD I/P | 0 | 143 | 143 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-11th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1st floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 5th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-13th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 9th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 8th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-15th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 143 | Sq.Ft | 1 | 100 | 3.58 | 0 | 143 | CGST 0% URD I/P | 0 | 143 | 143 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104 | Sq.Ft | 1 | 100 | 2.6 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-14th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-13th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-15th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104 | Sq.Ft | 1 | 100 | 2.6 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 104 | Sq.Ft | 1 | 100 | 2.6 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 9th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 143 | Sq.Ft | 1 | 100 | 3.58 | 0 | 143 | CGST 0% URD I/P | 0 | 143 | 143 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 2nd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 7th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-16th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (L) - | 280 | Sq.Ft | 1 | 100 | 7 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A-10th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 4th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 5th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (L) - | 90 | Sq.Ft | 1 | 100 | 2.25 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 29 | Sq.Ft | 1 | 100 | 0.73 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 224 | Sq.Ft | 1 | 100 | 5.6 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 105 | Sq.Ft | 1 | 100 | 2.63 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 22 | Sq.Ft | 1 | 100 | 0.55 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 142 | Sq.Ft | 1 | 100 | 3.55 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 77 | Sq.Ft | 1 | 100 | 1.93 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 827 | 91107 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 654 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 34 | Sq.Ft | 1 | 100 | 0.85 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 165 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 2nd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 104 | Sq.Ft | 1 | 100 | 0 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 6th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-13th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1st Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 104 | Sq.Ft | 1 | 100 | 0 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-16th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 6th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 8th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 227 | Sq.Ft | 1 | 100 | 0 | 0 | 227 | CGST 0% URD I/P | 0 | 227 | 227 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-11th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 5th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 227 | Sq.Ft | 1 | 100 | 0 | 0 | 227 | CGST 0% URD I/P | 0 | 227 | 227 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 8th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-10th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 9th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 227 | Sq.Ft | 1 | 100 | 0 | 0 | 227 | CGST 0% URD I/P | 0 | 227 | 227 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-12th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-13th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 50 | Sq.Ft | 1 | 100 | 0 | 0 | 50 | CGST 0% URD I/P | 0 | 50 | 50 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 143 | Sq.Ft | 1 | 100 | 0 | 0 | 143 | CGST 0% URD I/P | 0 | 143 | 143 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-15th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 2nd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 4th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 143 | Sq.Ft | 1 | 100 | 0 | 0 | 143 | CGST 0% URD I/P | 0 | 143 | 143 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 143 | Sq.Ft | 1 | 100 | 0 | 0 | 143 | CGST 0% URD I/P | 0 | 143 | 143 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-14th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-11th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 3rd floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 17 | Sq.Ft | 1 | 100 | 0 | 0 | 17 | CGST 0% URD I/P | 0 | 17 | 17 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 7th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 143 | Sq.Ft | 1 | 100 | 0 | 0 | 143 | CGST 0% URD I/P | 0 | 143 | 143 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 9th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-15th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-12th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-14th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 7th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 104 | Sq.Ft | 1 | 100 | 0 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-10th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 105 | Sq.Ft | 1 | 100 | 0 | 0 | 105 | CGST 0% URD I/P | 0 | 105 | 105 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1st floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft) | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 104 | Sq.Ft | 1 | 100 | 0 | 0 | 104 | CGST 0% URD I/P | 0 | 104 | 104 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 3rd Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 5th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 4th Floor Lv Shaft, Electrical Shaft, Service Shaft Duct w | 1 Coat Primer (External) (M) | 280 | Sq.Ft | 1 | 100 | 0 | 0 | 280 | CGST 0% URD I/P | 0 | 280 | 280 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 34 | Sq.Ft | 1 | 100 | 0 | 0 | 34 | CGST 0% URD I/P | 0 | 34 | 34 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 142 | Sq.Ft | 1 | 100 | 0 | 0 | 142 | CGST 0% URD I/P | 0 | 142 | 142 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 224 | Sq.Ft | 1 | 100 | 0 | 0 | 224 | CGST 0% URD I/P | 0 | 224 | 224 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 77 | Sq.Ft | 1 | 100 | 0 | 0 | 77 | CGST 0% URD I/P | 0 | 77 | 77 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 29 | Sq.Ft | 1 | 100 | 0 | 0 | 29 | CGST 0% URD I/P | 0 | 29 | 29 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A-16th floor Fire Shaft Duct walls Semi-Acrylic Paint-(Sq.Ft | 1 Coat Primer (External) (M) | 90 | Sq.Ft | 1 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 828 | 91106 | 05 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 653 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 05 Aug 2021
GANGA DHAM TOWERS | 932 | 91105 | 05 Aug 2021 | 214 | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 649 | Podium P2 RCC Slab Pumping Charges | Pumping Charges-BC | 321 | Cu.Mtrs | 190 | 100 | 0 | 0 | 60990 | C+S GST 18% I/P RD | 10978.2 | 71968.2 | 71968.2 | Approved | 0 | 0 | 2934 | 05 Aug 2021
GANGA DHAM TOWERS | 932 | 91105 | 05 Aug 2021 | 214 | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 649 | Podium P3 RCC Slab Pumping Charges | Pumping Charges-BC | 451 | Cu.Mtrs | 190 | 100 | 0 | 0 | 85690 | C+S GST 18% I/P RD | 15424.2 | 101114.2 | 101114.2 | Approved | 0 | 0 | 2934 | 05 Aug 2021
GANGA DHAM TOWERS | 1107 | 91101 | 04 Aug 2021 | 348 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR | EV - 671 | B 401 Terrace False Ceiling | PVC False Ceiling (M) | 192.46 | Sq.Ft | 50 | 100 | 0 | 0 | 9623 | C+S GST 18% I/P RD | 1732.14 | 11355.14 | 11355.14 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 805 | 91099 | 04 Aug 2021 | 347 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 670 | B 401 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 2245.23 | Sq.Ft | 15 | 100 | 841.96 | 0 | 33678.45 | C+S GST 18% I/P RD | 6062.12 | 39740.57 | 39740.57 | Approved | 0 | 0 | 337 | 04 Aug 2021
GANGA DHAM TOWERS | 392 | 91094 | 04 Aug 2021 | 16/pune/21-22 | J K INTERIOR | SEVEN STAR GYPSUM | EV - 961 | A Bldg Flat No. 1702 Gypsum Plaster | Gypsum on Wall (M) | 3443.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12051 | C+S GST 18% I/P RD | 2169.18 | 14220.18 | 14220.18 | Approved | 0 | 0 | 243 | 04 Aug 2021
GANGA DHAM TOWERS | 392 | 91094 | 04 Aug 2021 | 16/pune/21-22 | J K INTERIOR | SEVEN STAR GYPSUM | EV - 961 | A Bldg Flat No. 1701 Gypsum Plaster | Gypsum on Wall (M) | 3500 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12250 | C+S GST 18% I/P RD | 2205 | 14455 | 14455 | Approved | 0 | 0 | 243 | 04 Aug 2021
GANGA DHAM TOWERS | 697 | 91093 | 04 Aug 2021 | 16/pune/21-22 | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 960 | D 1005 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145 | Sq.Ft | 9 | 100 | 0 | 0 | 10305 | C+S GST 18% I/P RD | 1854.9 | 12159.9 | 12159.9 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 697 | 91093 | 04 Aug 2021 | 16/pune/21-22 | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 960 | D 1004 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792 | Sq.Ft | 9 | 100 | 0 | 0 | 7128 | C+S GST 18% I/P RD | 1283.04 | 8411.04 | 8411.04 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 697 | 91093 | 04 Aug 2021 | 16/pune/21-22 | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 960 | D 804 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792 | Sq.Ft | 9 | 100 | 0 | 0 | 7128 | C+S GST 18% I/P RD | 1283.04 | 8411.04 | 8411.04 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 697 | 91093 | 04 Aug 2021 | 16/pune/21-22 | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 960 | D 1003 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792 | Sq.Ft | 9 | 100 | 0 | 0 | 7128 | C+S GST 18% I/P RD | 1283.04 | 8411.04 | 8411.04 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 697 | 91093 | 04 Aug 2021 | 16/pune/21-22 | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 960 | D 805 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145 | Sq.Ft | 9 | 100 | 0 | 0 | 10305 | C+S GST 18% I/P RD | 1854.9 | 12159.9 | 12159.9 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 697 | 91093 | 04 Aug 2021 | 16/pune/21-22 | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 960 | D 1002 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 979 | Sq.Ft | 9 | 100 | 0 | 0 | 8811 | C+S GST 18% I/P RD | 1585.98 | 10396.98 | 10396.98 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 697 | 91093 | 04 Aug 2021 | 16/pune/21-22 | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 960 | D 1001 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145 | Sq.Ft | 9 | 100 | 0 | 0 | 10305 | C+S GST 18% I/P RD | 1854.9 | 12159.9 | 12159.9 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 697 | 91093 | 04 Aug 2021 | 16/pune/21-22 | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 960 | D 803 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 792 | Sq.Ft | 9 | 100 | 0 | 0 | 7128 | C+S GST 18% I/P RD | 1283.04 | 8411.04 | 8411.04 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 804 | 91092 | 04 Aug 2021 | 346 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 672 | B 401 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 748.41 | Sq.Ft | 50 | 100 | 0 | 0 | 37420.5 | C+S GST 18% I/P RD | 6735.7 | 44156.2 | 44156.2 | Approved | 0 | 0 | 0 | 04 Aug 2021
GANGA DHAM TOWERS | 1106 | 91090 | 04 Aug 2021 | 349 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 669 | B 401 Terrace False Ceiling | PVC False Ceiling (L) | 192.46 | Sq.Ft | 20 | 100 | 96.23 | 0 | 3849.2 | C+S GST 18% I/P RD | 692.86 | 4542.06 | 4542.06 | Approved | 0 | 0 | 48 | 04 Aug 2021
GANGA DHAM TOWERS | 1106 | 91090 | 04 Aug 2021 | 349 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 669 | B 401 Terrace False Ceiling | Scaffolding work | 192.46 | Sq.Ft | 5 | 100 | 24.06 | 0 | 962.3 | C+S GST 18% I/P RD | 173.22 | 1135.52 | 1135.52 | Approved | 0 | 0 | 48 | 04 Aug 2021
GANGA DHAM TOWERS | 149 | 91089 | 04 Aug 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 655 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3944 | No. | 4 | 100 | 0 | 0 | 15776 | CGST 0% URD I/P | 0 | 15776 | 15776 | Approved | 0 | 0 | 158 | 04 Aug 2021
GANGA DHAM TOWERS | 634 | 91088 | 04 Aug 2021 | 2021-22-029 | R K INTERIOR | R K INTERIOR | EV - 772 | A 18th Floor Lift cladding | Italian Marble Bull Nosing | 573.8947 | R.Ft | 76 | 100 | 1090.4 | 0 | 43616 | C+S GST 18% I/P RD | 7850.88 | 51466.88 | 51466.88 | Approved | 0 | 0 | 2026 | 04 Aug 2021
GANGA DHAM TOWERS | 634 | 91088 | 04 Aug 2021 | 2021-22-029 | R K INTERIOR | R K INTERIOR | EV - 772 | A 18th Floor Lift cladding | Dado Work - BC | 30 | Sq.Ft | 70 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 2026 | 04 Aug 2021
GANGA DHAM TOWERS | 634 | 91088 | 04 Aug 2021 | 2021-22-029 | R K INTERIOR | R K INTERIOR | EV - 772 | A 18th Floor Lift cladding | V Grove - BCo | 137.8056 | R.Ft | 108 | 100 | 372.08 | 0 | 14883 | C+S GST 18% I/P RD | 2678.94 | 17561.94 | 17561.94 | Approved | 0 | 0 | 2026 | 04 Aug 2021
GANGA DHAM TOWERS | 634 | 91088 | 04 Aug 2021 | 2021-22-029 | R K INTERIOR | R K INTERIOR | EV - 772 | A 18th Floor Lift cladding | Italian Marble Zero Joint-BCo | 226 | R.Ft | 180 | 100 | 1017 | 0 | 40680 | C+S GST 18% I/P RD | 7322.4 | 48002.4 | 48002.4 | Approved | 0 | 0 | 2026 | 04 Aug 2021
GANGA DHAM TOWERS | 258 | 91081 | 03 Aug 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 657 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 1 | Month | 2500 | 100 | 0 | 0 | 2500 | CGST 0% URD I/P | 0 | 2500 | 2500 | Approved | 0 | 0 | 25 | 03 Aug 2021
GANGA DHAM TOWERS | 237 | 91080 | 03 Aug 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 656 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 1 | Month | 7000 | 100 | 0 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 70 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 274.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 480 | CGST 0% URD I/P | 0 | 480 | 480 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 224 | Sq.Ft | 1.75 | 100 | 0 | 0 | 392 | CGST 0% URD I/P | 0 | 392 | 392 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 444 | Sq.Ft | 1.75 | 100 | 0 | 0 | 777 | CGST 0% URD I/P | 0 | 777 | 777 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 445.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 779 | CGST 0% URD I/P | 0 | 779 | 779 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 56 | Sq.Ft | 1.75 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 444 | Sq.Ft | 1.75 | 100 | 0 | 0 | 777 | CGST 0% URD I/P | 0 | 777 | 777 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 504 | Sq.Ft | 1.75 | 100 | 0 | 0 | 882 | CGST 0% URD I/P | 0 | 882 | 882 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 38.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 67 | CGST 0% URD I/P | 0 | 67 | 67 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 504 | Sq.Ft | 1.75 | 100 | 0 | 0 | 882 | CGST 0% URD I/P | 0 | 882 | 882 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 56 | Sq.Ft | 1.75 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 516 | CGST 0% URD I/P | 0 | 516 | 516 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 312 | Sq.Ft | 1.75 | 100 | 0 | 0 | 546 | CGST 0% URD I/P | 0 | 546 | 546 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 297.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 520 | CGST 0% URD I/P | 0 | 520 | 520 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 274.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 314.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 551 | CGST 0% URD I/P | 0 | 551 | 551 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 56 | Sq.Ft | 1.75 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 314.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 551 | CGST 0% URD I/P | 0 | 551 | 551 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 312 | Sq.Ft | 1.75 | 100 | 0 | 0 | 546 | CGST 0% URD I/P | 0 | 546 | 546 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 274.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 480 | CGST 0% URD I/P | 0 | 480 | 480 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 314.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 551 | CGST 0% URD I/P | 0 | 551 | 551 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 515 | CGST 0% URD I/P | 0 | 515 | 515 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 314.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 551 | CGST 0% URD I/P | 0 | 551 | 551 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 314.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 551 | CGST 0% URD I/P | 0 | 551 | 551 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 314.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 551 | CGST 0% URD I/P | 0 | 551 | 551 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 594.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1040 | CGST 0% URD I/P | 0 | 1040 | 1040 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 314.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 551 | CGST 0% URD I/P | 0 | 551 | 551 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 445.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 779 | CGST 0% URD I/P | 0 | 779 | 779 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 56 | Sq.Ft | 1.75 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 38.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 67 | CGST 0% URD I/P | 0 | 67 | 67 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 38.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 67 | CGST 0% URD I/P | 0 | 67 | 67 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 38.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 67 | CGST 0% URD I/P | 0 | 67 | 67 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 504 | Sq.Ft | 1.75 | 100 | 0 | 0 | 882 | CGST 0% URD I/P | 0 | 882 | 882 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 74.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 131 | CGST 0% URD I/P | 0 | 131 | 131 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 28 | Sq.Ft | 1.75 | 100 | 0 | 0 | 49 | CGST 0% URD I/P | 0 | 49 | 49 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 594.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1040 | CGST 0% URD I/P | 0 | 1040 | 1040 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 274.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 515 | CGST 0% URD I/P | 0 | 515 | 515 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 504 | Sq.Ft | 1.75 | 100 | 0 | 0 | 882 | CGST 0% URD I/P | 0 | 882 | 882 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 504 | Sq.Ft | 1.75 | 100 | 0 | 0 | 882 | CGST 0% URD I/P | 0 | 882 | 882 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 274.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 504 | Sq.Ft | 1.75 | 100 | 0 | 0 | 882 | CGST 0% URD I/P | 0 | 882 | 882 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 38.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 67 | CGST 0% URD I/P | 0 | 67 | 67 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 274.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 442.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 774 | CGST 0% URD I/P | 0 | 774 | 774 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 516 | CGST 0% URD I/P | 0 | 516 | 516 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 516 | CGST 0% URD I/P | 0 | 516 | 516 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 515 | CGST 0% URD I/P | 0 | 515 | 515 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 137.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 240 | CGST 0% URD I/P | 0 | 240 | 240 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 70.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 123 | CGST 0% URD I/P | 0 | 123 | 123 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 594.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1040 | CGST 0% URD I/P | 0 | 1040 | 1040 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 594.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1040 | CGST 0% URD I/P | 0 | 1040 | 1040 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 515 | CGST 0% URD I/P | 0 | 515 | 515 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 56 | Sq.Ft | 1.75 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 594.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1040 | CGST 0% URD I/P | 0 | 1040 | 1040 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 594.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1040 | CGST 0% URD I/P | 0 | 1040 | 1040 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 274.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 481 | CGST 0% URD I/P | 0 | 481 | 481 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 222.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 389 | CGST 0% URD I/P | 0 | 389 | 389 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 56 | Sq.Ft | 1.75 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 445.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 779 | CGST 0% URD I/P | 0 | 779 | 779 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 16 | Sq.Ft | 1.75 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 444 | Sq.Ft | 1.75 | 100 | 0 | 0 | 777 | CGST 0% URD I/P | 0 | 777 | 777 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 444 | Sq.Ft | 1.75 | 100 | 0 | 0 | 777 | CGST 0% URD I/P | 0 | 777 | 777 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 444 | Sq.Ft | 1.75 | 100 | 0 | 0 | 777 | CGST 0% URD I/P | 0 | 777 | 777 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 496 | Sq.Ft | 1.75 | 100 | 0 | 0 | 868 | CGST 0% URD I/P | 0 | 868 | 868 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 515 | CGST 0% URD I/P | 0 | 515 | 515 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 274.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 480 | CGST 0% URD I/P | 0 | 480 | 480 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 445.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 779 | CGST 0% URD I/P | 0 | 779 | 779 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 56 | Sq.Ft | 1.75 | 100 | 0 | 0 | 98 | CGST 0% URD I/P | 0 | 98 | 98 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 594.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1040 | CGST 0% URD I/P | 0 | 1040 | 1040 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 38.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 67 | CGST 0% URD I/P | 0 | 67 | 67 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 137.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 240 | CGST 0% URD I/P | 0 | 240 | 240 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 445.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 779 | CGST 0% URD I/P | 0 | 779 | 779 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 50.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 88 | CGST 0% URD I/P | 0 | 88 | 88 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 32 | Sq.Ft | 1.75 | 100 | 0 | 0 | 56 | CGST 0% URD I/P | 0 | 56 | 56 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 444 | Sq.Ft | 1.75 | 100 | 0 | 0 | 777 | CGST 0% URD I/P | 0 | 777 | 777 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 594.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 1040 | CGST 0% URD I/P | 0 | 1040 | 1040 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 64 | Sq.Ft | 1.75 | 100 | 0 | 0 | 112 | CGST 0% URD I/P | 0 | 112 | 112 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 37.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 65 | CGST 0% URD I/P | 0 | 65 | 65 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 25.1429 | Sq.Ft | 1.75 | 100 | 0 | 0 | 44 | CGST 0% URD I/P | 0 | 44 | 44 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 828 | 91079 | 03 Aug 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 652 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 294.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 516 | CGST 0% URD I/P | 0 | 516 | 516 | Approved | 0 | 0 | 450 | 03 Aug 2021
GANGA DHAM TOWERS | 480 | 91077 | 03 Aug 2021 | 63 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 854 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 28.9985 | Day | 451.61 | 100 | 0 | 0 | 13096 | C+S GST 18% I/P RD | 2357.28 | 15453.28 | 15453.28 | Approved | 0 | 0 | 131 | 03 Aug 2021
GANGA DHAM TOWERS | 745 | 91076 | 03 Aug 2021 | 65 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 855 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 29.4989 | Day | 451.61 | 100 | 0 | 0 | 13322 | C+S GST 18% I/P RD | 2397.96 | 15719.96 | 15719.96 | Approved | 0 | 0 | 133 | 03 Aug 2021
GANGA DHAM TOWERS | 186 | 91075 | 03 Aug 2021 | 62 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 853 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 29.9994 | Day | 580.645 | 100 | 0 | 0 | 17419 | C+S GST 18% I/P RD | 3135.42 | 20554.42 | 20554.42 | Approved | 0 | 0 | 969 | 03 Aug 2021
GANGA DHAM TOWERS | 186 | 91075 | 03 Aug 2021 | 62 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 853 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 145.9967 | Day | 451.613 | 100 | 0 | 0 | 65934 | C+S GST 18% I/P RD | 11868.12 | 77802.12 | 77802.12 | Approved | 0 | 0 | 969 | 03 Aug 2021
GANGA DHAM TOWERS | 186 | 91075 | 03 Aug 2021 | 62 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 853 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 30 | Day | 451.613 | 100 | 0 | 0 | 13548.39 | C+S GST 18% I/P RD | 2438.72 | 15987.11 | 15987.11 | Approved | 0 | 0 | 969 | 03 Aug 2021
GANGA DHAM TOWERS | 413 | 91074 | 03 Aug 2021 | 626 | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 696 | Sales Oiifce Landscape Area . | Supervision Charges | 0.75 | Month | 4000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 30 | 03 Aug 2021
GANGA DHAM TOWERS | 178 | 91073 | 03 Aug 2021 | 625 | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 688 | Sales Oiifce Landscape Area . | Garden work. | 79.05 | Day | 407.25 | 100 | 0 | 0 | 32193.11 | C+S GST 18% I/P RD | 5794.76 | 37987.87 | 37987.87 | Approved | 0 | 0 | 322 | 03 Aug 2021
GANGA DHAM TOWERS | 179 | 91072 | 03 Aug 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) |  | Road Divider Garden Maintenance | Garden work. | 23.25 | Day | 407.25 | 100 | 0 | 0 | 9468.56 | C+S GST 18% I/P RD | 1704.34 | 11172.9 | 11172.9 |  | 0 | 0 | 95 | 03 Aug 2021
GANGA DHAM TOWERS | 572 | 91071 | 03 Aug 2021 | 219 | PRITAM GANJEWAR INFRASTRUCTURE PRIVATE LIMITED | LOTUS ENTERPRISES | EV - 973 | D Buil.Supply Of Pump For Concreting | Pumping Charges-BC | 16 | Cu.Mtrs | 127.119 | 100 | 0 | 0 | 2033.9 | C+S GST 18% I/P RD | 366.1 | 2400 | 2400 | Approved | 0 | 0 | 41 | 03 Aug 2021
GANGA DHAM TOWERS | 1081 | 91070 | 03 Aug 2021 | 218 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 650 | D 12th Slab Pumping Charges for RMC | Pumping Charges-BC | 36 | Cu.Mtrs | 190 | 100 | 0 | 0 | 6840 | C+S GST 18% I/P RD | 1231.2 | 8071.2 | 8071.2 | Approved | 0 | 0 | 137 | 03 Aug 2021
GANGA DHAM TOWERS | 666 | 91069 | 03 Aug 2021 | 217 | ACC LTD (SUPPLIER) | LOTUS ENTERPRISES | EV - 972 | Club House 1st slab Pump Charges | Pumping Charges-BC | 58 | Cu.Mtrs | 169.492 | 100 | 0 | 0 | 9830.54 | C+S GST 18% I/P RD | 1769.5 | 11600.04 | 11600.04 | Approved | 0 | 0 | 197 | 03 Aug 2021
GANGA DHAM TOWERS | 667 | 91068 | 03 Aug 2021 | 216 | ACC LTD (SUPPLIER) | LOTUS ENTERPRISES | EV - 971 | C PCC Pump Charges | Pumping Charges-BC | 24 | Cu.Mtrs | 169.492 | 100 | 0 | 0 | 4067.81 | C+S GST 18% I/P RD | 732.2 | 4800.01 | 4800.01 | Approved | 0 | 0 | 81 | 03 Aug 2021
GANGA DHAM TOWERS | 1080 | 91067 | 03 Aug 2021 | 215 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 651 | B GF Floor Trimix Pumping Charges | Pumping Charges-BC | 215.01 | Cu.Mtrs | 190 | 100 | 0 | 0 | 40851.9 | C+S GST 18% I/P RD | 7353.34 | 48205.24 | 48205.24 | Approved | 0 | 0 | 1117 | 03 Aug 2021
GANGA DHAM TOWERS | 1080 | 91067 | 03 Aug 2021 | 215 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 651 | B P2 Floor Trimix Pumping Charges | Pumping Charges-BC | 79 | Cu.Mtrs | 190 | 100 | 0 | 0 | 15010 | C+S GST 18% I/P RD | 2701.8 | 17711.8 | 17711.8 | Approved | 0 | 0 | 1117 | 03 Aug 2021
GANGA DHAM TOWERS | 744 | 91066 | 03 Aug 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 679 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 6 | 03 Aug 2021
GANGA DHAM TOWERS | 698 | 91065 | 03 Aug 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 694 | D 801 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 1030.581 | Sq.Ft | 9 | 100 | 231.88 | 0 | 9275.23 | C+S GST 18% I/P RD | 1669.54 | 10944.77 | 10944.77 | Approved | 0 | 0 | 250 | 03 Aug 2021
GANGA DHAM TOWERS | 698 | 91065 | 03 Aug 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 694 | D 803 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 713.619 | Sq.Ft | 9 | 100 | 160.56 | 0 | 6422.57 | C+S GST 18% I/P RD | 1156.06 | 7578.63 | 7578.63 | Approved | 0 | 0 | 250 | 03 Aug 2021
GANGA DHAM TOWERS | 698 | 91065 | 03 Aug 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 694 | D 805 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 1030.581 | Sq.Ft | 9 | 100 | 231.88 | 0 | 9275.23 | C+S GST 18% I/P RD | 1669.54 | 10944.77 | 10944.77 | Approved | 0 | 0 | 250 | 03 Aug 2021
GANGA DHAM TOWERS | 491 | 91064 | 03 Aug 2021 | 210 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 723 | D Build. 1003 Blockwork 5" | Blockwork 5" - BC - | 547.5615 | Sq.Ft | 13 | 100 | 177.96 | 0 | 7118.3 | C+S GST 18% I/P RD | 1281.3 | 8399.6 | 8399.6 | Approved | 0 | 0 | 446 | 03 Aug 2021
GANGA DHAM TOWERS | 491 | 91064 | 03 Aug 2021 | 210 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 723 | D Build. 1001 Blockwork 5" | Blockwork 5" - BC - | 838.491 | Sq.Ft | 13 | 100 | 272.51 | 0 | 10900.38 | C+S GST 18% I/P RD | 1962.06 | 12862.44 | 12862.44 | Approved | 0 | 0 | 446 | 03 Aug 2021
GANGA DHAM TOWERS | 491 | 91064 | 03 Aug 2021 | 210 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 723 | D Build. 1002 Blockwork 5" | Blockwork 5" - BC - | 722.381 | Sq.Ft | 13 | 100 | 234.77 | 0 | 9390.95 | C+S GST 18% I/P RD | 1690.38 | 11081.33 | 11081.33 | Approved | 0 | 0 | 446 | 03 Aug 2021
GANGA DHAM TOWERS | 491 | 91064 | 03 Aug 2021 | 210 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 723 | D Build. 1004 Blockwork 5" | Blockwork 5" - BC - | 691.118 | Sq.Ft | 13 | 100 | 224.61 | 0 | 8984.53 | C+S GST 18% I/P RD | 1617.22 | 10601.75 | 10601.75 | Approved | 0 | 0 | 446 | 03 Aug 2021
GANGA DHAM TOWERS | 491 | 91064 | 03 Aug 2021 | 210 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 723 | D Build. 1001 Blockwork 8" | Blockwork 8" - BC | 62 | Sq.Ft | 15 | 100 | 23.25 | 0 | 930 | C+S GST 18% I/P RD | 167.4 | 1097.4 | 1097.4 | Approved | 0 | 0 | 446 | 03 Aug 2021
GANGA DHAM TOWERS | 491 | 91064 | 03 Aug 2021 | 210 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 723 | D Build. 1005 Blockwork 8" | Blockwork 8" - BC | 204.09 | Sq.Ft | 15 | 100 | 76.53 | 0 | 3061.35 | C+S GST 18% I/P RD | 551.04 | 3612.39 | 3612.39 | Approved | 0 | 0 | 446 | 03 Aug 2021
GANGA DHAM TOWERS | 491 | 91064 | 03 Aug 2021 | 210 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 723 | D Build. 1003 Blockwork 8" | Blockwork 8" - BC | 77.5 | Sq.Ft | 15 | 100 | 29.06 | 0 | 1162.5 | C+S GST 18% I/P RD | 209.26 | 1371.76 | 1371.76 | Approved | 0 | 0 | 446 | 03 Aug 2021
GANGA DHAM TOWERS | 491 | 91064 | 03 Aug 2021 | 210 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 723 | D Build. 1004 Blockwork 8" | Blockwork 8" - BC | 206.67 | Sq.Ft | 15 | 100 | 77.5 | 0 | 3100.05 | C+S GST 18% I/P RD | 558 | 3658.05 | 3658.05 | Approved | 0 | 0 | 446 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 1005 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | C+S GST 18% I/P RD | 934 | 6122.92 | 6122.92 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 905 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | C+S GST 18% I/P RD | 934 | 6122.92 | 6122.92 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 1002 Rough Plaster | Rough Plaster | 326.7 | Sq.Ft | 12 | 100 | 98.01 | 0 | 3920.4 | C+S GST 18% I/P RD | 705.68 | 4626.08 | 4626.08 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 901 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | C+S GST 18% I/P RD | 934 | 6122.92 | 6122.92 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 904 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | C+S GST 18% I/P RD | 752.84 | 4935.32 | 4935.32 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 1004 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | C+S GST 18% I/P RD | 752.84 | 4935.32 | 4935.32 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 902 Rough Plaster | Rough Plaster | 326.7 | Sq.Ft | 12 | 100 | 98.01 | 0 | 3920.4 | C+S GST 18% I/P RD | 705.68 | 4626.08 | 4626.08 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 903 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | C+S GST 18% I/P RD | 752.84 | 4935.32 | 4935.32 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 1003 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | C+S GST 18% I/P RD | 752.84 | 4935.32 | 4935.32 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 492 | 91063 | 03 Aug 2021 | 209 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 722 | D Building 1001 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | C+S GST 18% I/P RD | 934 | 6122.92 | 6122.92 | Approved | 0 | 0 | 453 | 03 Aug 2021
GANGA DHAM TOWERS | 1067 | 91044 | 02 Aug 2021 | 51 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 769 | B P2 Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 130 | Sq.Ft | 9 | 100 | 29.25 | 0 | 1170 | C+S GST 18% I/P RD | 210.6 | 1380.6 | 1380.6 | Approved | 0 | 0 | 12 | 02 Aug 2021
GANGA DHAM TOWERS | 1065 | 91043 | 02 Aug 2021 | 50 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 770 | A P2 Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 97 | Sq.Ft | 9 | 100 | 21.83 | 0 | 873 | C+S GST 18% I/P RD | 157.14 | 1030.14 | 1030.14 | Approved | 0 | 0 | 9 | 02 Aug 2021
GANGA DHAM TOWERS | 694 | 91042 | 02 Aug 2021 | 53 | J K INTERIOR | J K INTERIOR | EV - 768 | B P2 Podium Drop Pannel Plaster - 1 No. | Gypsum Patta Plaster Rate Diff (L) | 971 | R.Ft | 7.5 | 100 | 182.06 | 0 | 7282.5 | C+S GST 18% I/P RD | 1310.86 | 8593.36 | 8593.36 | Approved | 0 | 0 | 146 | 02 Aug 2021
GANGA DHAM TOWERS | 694 | 91042 | 02 Aug 2021 | 53 | J K INTERIOR | J K INTERIOR | EV - 768 | B P3 Podium Drop Pannel Plaste | Gypsum Patta Plaster Rate Diff (L) | 978.7 | R.Ft | 7.5 | 100 | 183.51 | 0 | 7340.25 | C+S GST 18% I/P RD | 1321.24 | 8661.49 | 8661.49 | Approved | 0 | 0 | 146 | 02 Aug 2021
GANGA DHAM TOWERS | 696 | 91040 | 02 Aug 2021 | 54 | J K INTERIOR | J K INTERIOR | EV - 717 | B P2 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 450 | Sq.Ft | 5 | 100 | 56.25 | 0 | 2250 | C+S GST 18% I/P RD | 405 | 2655 | 2655 | Approved | 0 | 0 | 96 | 02 Aug 2021
GANGA DHAM TOWERS | 696 | 91040 | 02 Aug 2021 | 54 | J K INTERIOR | J K INTERIOR | EV - 717 | B P3 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 1465.73 | Sq.Ft | 5 | 100 | 183.22 | 0 | 7328.65 | C+S GST 18% I/P RD | 1319.16 | 8647.81 | 8647.81 | Approved | 0 | 0 | 96 | 02 Aug 2021
GANGA DHAM TOWERS | 649 | 91039 | 02 Aug 2021 | 49 | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 771 | A P3 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 80 | Sq.Ft | 5 | 100 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 4 | 02 Aug 2021
GANGA DHAM TOWERS | 1133 | 91038 | 02 Aug 2021 |  | BASSAPPA CHAVAN | BASSAPPA CHAVAN | EV - 698 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Tractor Trip - Dld | 15 | No. | 800 | 100 | 0 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 120 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 901 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 172.665 | R.Ft | 50 | 100 | 215.83 | 0 | 8633.25 | C+S GST 18% I/P RD | 1553.98 | 10187.23 | 10187.23 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 401 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 69.0225 | R.Ft | 45 | 100 | 77.65 | 0 | 3106.01 | C+S GST 18% I/P RD | 559.08 | 3665.09 | 3665.09 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 101 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 55.384 | R.Ft | 45 | 100 | 62.31 | 0 | 2492.28 | C+S GST 18% I/P RD | 448.62 | 2940.9 | 2940.9 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 402 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 54.135 | R.Ft | 45 | 100 | 60.9 | 0 | 2436.08 | C+S GST 18% I/P RD | 438.5 | 2874.58 | 2874.58 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 401 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 37.8975 | R.Ft | 45 | 100 | 42.63 | 0 | 1705.39 | C+S GST 18% I/P RD | 306.98 | 2012.37 | 2012.37 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 401 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 51.9225 | R.Ft | 45 | 100 | 58.41 | 0 | 2336.51 | C+S GST 18% I/P RD | 420.58 | 2757.09 | 2757.09 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 401 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 172.665 | R.Ft | 45 | 100 | 194.25 | 0 | 7769.93 | C+S GST 18% I/P RD | 1398.58 | 9168.51 | 9168.51 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 402 Parents Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 42.8175 | R.Ft | 45 | 100 | 48.17 | 0 | 1926.79 | C+S GST 18% I/P RD | 346.82 | 2273.61 | 2273.61 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1301 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 55.384 | R.Ft | 55 | 100 | 76.15 | 0 | 3046.12 | C+S GST 18% I/P RD | 548.3 | 3594.42 | 3594.42 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 101 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 73.624 | R.Ft | 45 | 100 | 82.83 | 0 | 3313.08 | C+S GST 18% I/P RD | 596.36 | 3909.44 | 3909.44 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 402 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 94.59 | R.Ft | 45 | 100 | 106.41 | 0 | 4256.55 | C+S GST 18% I/P RD | 766.18 | 5022.73 | 5022.73 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 101 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 40.424 | R.Ft | 45 | 100 | 45.48 | 0 | 1819.08 | C+S GST 18% I/P RD | 327.44 | 2146.52 | 2146.52 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 101 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 184.176 | R.Ft | 45 | 100 | 207.2 | 0 | 8287.92 | C+S GST 18% I/P RD | 1491.82 | 9779.74 | 9779.74 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1301 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 40.424 | R.Ft | 55 | 100 | 55.58 | 0 | 2223.32 | C+S GST 18% I/P RD | 400.2 | 2623.52 | 2623.52 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1401 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 40.424 | R.Ft | 55 | 100 | 55.58 | 0 | 2223.32 | C+S GST 18% I/P RD | 400.2 | 2623.52 | 2623.52 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1301 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 184.176 | R.Ft | 55 | 100 | 253.24 | 0 | 10129.68 | C+S GST 18% I/P RD | 1823.34 | 11953.02 | 11953.02 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1301 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 73.624 | R.Ft | 55 | 100 | 101.23 | 0 | 4049.32 | C+S GST 18% I/P RD | 728.88 | 4778.2 | 4778.2 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1401 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 73.624 | R.Ft | 55 | 100 | 101.23 | 0 | 4049.32 | C+S GST 18% I/P RD | 728.88 | 4778.2 | 4778.2 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1801 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 73.624 | R.Ft | 55 | 100 | 101.23 | 0 | 4049.32 | C+S GST 18% I/P RD | 728.88 | 4778.2 | 4778.2 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1401 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 184.176 | R.Ft | 55 | 100 | 253.24 | 0 | 10129.68 | C+S GST 18% I/P RD | 1823.34 | 11953.02 | 11953.02 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1401 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 55.384 | R.Ft | 55 | 100 | 76.15 | 0 | 3046.12 | C+S GST 18% I/P RD | 548.3 | 3594.42 | 3594.42 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1801 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 55.384 | R.Ft | 55 | 100 | 76.15 | 0 | 3046.12 | C+S GST 18% I/P RD | 548.3 | 3594.42 | 3594.42 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1801 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 40.424 | R.Ft | 55 | 100 | 55.58 | 0 | 2223.32 | C+S GST 18% I/P RD | 400.2 | 2623.52 | 2623.52 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 801 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 37.8975 | R.Ft | 50 | 100 | 47.37 | 0 | 1894.88 | C+S GST 18% I/P RD | 341.08 | 2235.96 | 2235.96 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 801 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 69.0225 | R.Ft | 50 | 100 | 86.28 | 0 | 3451.13 | C+S GST 18% I/P RD | 621.2 | 4072.33 | 4072.33 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 901 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 37.8975 | R.Ft | 50 | 100 | 47.37 | 0 | 1894.88 | C+S GST 18% I/P RD | 341.08 | 2235.96 | 2235.96 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 801 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 172.665 | R.Ft | 50 | 100 | 215.83 | 0 | 8633.25 | C+S GST 18% I/P RD | 1553.98 | 10187.23 | 10187.23 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 801 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 51.9225 | R.Ft | 50 | 100 | 64.9 | 0 | 2596.13 | C+S GST 18% I/P RD | 467.3 | 3063.43 | 3063.43 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 901 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 51.9225 | R.Ft | 50 | 100 | 64.9 | 0 | 2596.13 | C+S GST 18% I/P RD | 467.3 | 3063.43 | 3063.43 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 901 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 69.0225 | R.Ft | 50 | 100 | 86.28 | 0 | 3451.13 | C+S GST 18% I/P RD | 621.2 | 4072.33 | 4072.33 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 758 | 91037 | 02 Aug 2021 | 47 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 748 | B 1801 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 184.176 | R.Ft | 55 | 100 | 253.24 | 0 | 10129.68 | C+S GST 18% I/P RD | 1823.34 | 11953.02 | 11953.02 | Approved | 0 | 0 | 1309 | 02 Aug 2021
GANGA DHAM TOWERS | 604 | 91036 | 02 Aug 2021 | 15 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 695 | A Internal Hydrant System | SITC GI Pipe C Class 150mm dia.(L) | 100 | Mtrs | 416 | 100 | 1040 | 0 | 41600 | C+S GST 18% I/P RD | 7488 | 49088 | 49088 | Approved | 0 | 0 | 1316 | 02 Aug 2021
GANGA DHAM TOWERS | 604 | 91036 | 02 Aug 2021 | 15 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 695 | A Sprinkler System | Sprinkler 15mm 68 dg Pendent (L) | 315 | No. | 57 | 100 | 448.88 | 0 | 17955 | C+S GST 18% I/P RD | 3231.9 | 21186.9 | 21186.9 | Approved | 0 | 0 | 1316 | 02 Aug 2021
GANGA DHAM TOWERS | 604 | 91036 | 02 Aug 2021 | 15 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 695 | A Sprinkler System | SITC GI Pipe C Class 80mm dia.(L) | 50 | Mtrs | 202 | 100 | 252.5 | 0 | 10100 | C+S GST 18% I/P RD | 1818 | 11918 | 11918 | Approved | 0 | 0 | 1316 | 02 Aug 2021
GANGA DHAM TOWERS | 604 | 91036 | 02 Aug 2021 | 15 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 695 | A Sprinkler System | SITC Ball Valve 50mm (L) | 28 | No. | 560 | 100 | 392 | 0 | 15680 | C+S GST 18% I/P RD | 2822.4 | 18502.4 | 18502.4 | Approved | 0 | 0 | 1316 | 02 Aug 2021
GANGA DHAM TOWERS | 604 | 91036 | 02 Aug 2021 | 15 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 695 | A Sprinkler System | SITC GI Pipe C Class 50mm dia.(L) | 195 | Mtrs | 150 | 100 | 731.25 | 0 | 29250 | C+S GST 18% I/P RD | 5265 | 34515 | 34515 | Approved | 0 | 0 | 1316 | 02 Aug 2021
GANGA DHAM TOWERS | 604 | 91036 | 02 Aug 2021 | 15 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 695 | A 2nd Floor Internal Flat Sprinkler System | SITC GI Pipe C Class 40mm dia.(L) | 33.6 | Mtrs | 110 | 100 | 92.4 | 0 | 3696 | C+S GST 18% I/P RD | 665.28 | 4361.28 | 4361.28 | Approved | 0 | 0 | 1316 | 02 Aug 2021
GANGA DHAM TOWERS | 604 | 91036 | 02 Aug 2021 | 15 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 695 | A 2nd Floor Internal Flat Sprinkler System | SITC GI Pipe C Class 25mm dia-(L) | 96 | Mtrs | 73 | 100 | 175.2 | 0 | 7008 | C+S GST 18% I/P RD | 1261.44 | 8269.44 | 8269.44 | Approved | 0 | 0 | 1316 | 02 Aug 2021
GANGA DHAM TOWERS | 604 | 91036 | 02 Aug 2021 | 15 | AGS TECHNOLOGIES INDIA PRIVATE LIMITED | BEYOND VISION ENGINEERS & CONSULTANTS | EV - 695 | A Sprinkler System | Rossete Plate (L) | 315 | No. | 20 | 100 | 0 | 0 | 6300 | C+S GST 18% I/P RD | 1134 | 7434 | 7434 | Approved | 0 | 0 | 1316 | 02 Aug 2021
GANGA DHAM TOWERS | 145 | 91035 | 02 Aug 2021 | 169 | PEST-O-CRUSH | S.R.Enterprises | EV - 749 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 02 Aug 2021
GANGA DHAM TOWERS | 940 | 91034 | 02 Aug 2021 | 4 | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 746 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 02 Aug 2021
GANGA DHAM TOWERS | 522 | 91031 | 31 Jul 2021 | 46 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 634 | B Bldg 202 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1.5 | No. | 900 | 100 | 33.75 | 0 | 1350 | CGST 0% URD I/P | 0 | 1350 | 1350 | Approved | 0 | 0 | 112 | 31 Jul 2021
GANGA DHAM TOWERS | 522 | 91031 | 31 Jul 2021 | 46 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 634 | B Bldg 1401 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1400 | 100 | 245 | 0 | 9800 | CGST 0% URD I/P | 0 | 9800 | 9800 | Approved | 0 | 0 | 112 | 31 Jul 2021
GANGA DHAM TOWERS | 522 | 91029 | 30 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 642 | B Bldg 401 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1.75 | No. | 1050 | 100 | 45.94 | 0 | 1837.48 | CGST 0% URD I/P | 0 | 1837.48 | 1837.48 | Approved | 0 | 0 | 18 | 30 Jul 2021
GANGA DHAM TOWERS | 991 | 91023 | 30 Jul 2021 | 217 | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 718 | B 1601 NOC | Lintel Casting | 25.42 | R.Ft | 50 | 100 | 0 | 0 | 1271 | C+S GST 18% I/P RD | 228.78 | 1499.78 | 1499.78 | Approved | 0 | 0 | 13 | 30 Jul 2021
GANGA DHAM TOWERS | 993 | 91022 | 30 Jul 2021 | 45 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 646 | B 402 NOC | Italian Marble Flooring - BCo | 58.99 | Sq.Ft | 55 | 100 | 81.11 | 0 | 3244.45 | C+S GST 18% I/P RD | 584 | 3828.45 | 3828.45 | Approved | 0 | 0 | 32 | 30 Jul 2021
GANGA DHAM TOWERS | 981 | 91021 | 30 Jul 2021 | 214 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 767 | B 1101 | Lintel Casting | 4.92 | R.Ft | 50 | 100 | 0 | 0 | 246 | C+S GST 18% I/P RD | 44.28 | 290.28 | 290.28 | Approved | 0 | 0 | 2 | 30 Jul 2021
GANGA DHAM TOWERS | 767 | 91020 | 30 Jul 2021 | 216 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 766 | B Bldg 4th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.8 | No. | 2500 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 401 Ceramic Tiling | Ceramic Flooring work | 280 | Sq.Ft | 13 | 100 | 91 | 0 | 3640 | C+S GST 18% I/P RD | 655.2 | 4295.2 | 4295.2 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Ceramic Tiling | Ceramic Flooring work | 356.56 | Sq.Ft | 13 | 100 | 115.88 | 0 | 4635.28 | C+S GST 18% I/P RD | 834.36 | 5469.64 | 5469.64 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Ceramic Tiling | Ceramic Flooring work | 356.56 | Sq.Ft | 13 | 100 | 115.88 | 0 | 4635.28 | C+S GST 18% I/P RD | 834.36 | 5469.64 | 5469.64 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Living Terrace Vitr.Flooring | Vitrified Flooring -BC | 192.46 | Sq.Ft | 15 | 100 | 72.17 | 0 | 2886.9 | C+S GST 18% I/P RD | 519.64 | 3406.54 | 3406.54 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 173.78 | Sq.Ft | 15 | 100 | 65.17 | 0 | 2606.7 | C+S GST 18% I/P RD | 469.2 | 3075.9 | 3075.9 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1301 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 173.78 | Sq.Ft | 24 | 100 | 104.27 | 0 | 4170.72 | C+S GST 18% I/P RD | 750.72 | 4921.44 | 4921.44 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1301 Living Terrace Vitr.Flooring | Vitrified Flooring -BC | 192.46 | Sq.Ft | 24 | 100 | 115.48 | 0 | 4619.04 | C+S GST 18% I/P RD | 831.42 | 5450.46 | 5450.46 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1302 Living Terrace Vitrfied Flooring | Vitrified Flooring -BC | 165.23 | Sq.Ft | 24 | 100 | 99.14 | 0 | 3965.52 | C+S GST 18% I/P RD | 713.8 | 4679.32 | 4679.32 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1401 Living Terrace Vitr.Flooring | Vitrified Flooring -BC | 192.46 | Sq.Ft | 24 | 100 | 115.48 | 0 | 4619.04 | C+S GST 18% I/P RD | 831.42 | 5450.46 | 5450.46 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 StaffToilet Dado | Dado BC | 102.3375 | Sq.Ft | 13 | 100 | 33.26 | 0 | 1330.39 | C+S GST 18% I/P RD | 239.48 | 1569.87 | 1569.87 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 StaffToilet Dado | Dado BC | 102.255 | Sq.Ft | 13 | 100 | 33.23 | 0 | 1329.32 | C+S GST 18% I/P RD | 239.28 | 1568.6 | 1568.6 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1801 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 305 | Sq.Ft | 55 | 100 | 419.38 | 0 | 16775 | C+S GST 18% I/P RD | 3019.5 | 19794.5 | 19794.5 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1801 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 55 | 100 | 334.13 | 0 | 13365 | C+S GST 18% I/P RD | 2405.7 | 15770.7 | 15770.7 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1801 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1154 | Sq.Ft | 55 | 100 | 1586.75 | 0 | 63470 | C+S GST 18% I/P RD | 11424.6 | 74894.6 | 74894.6 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1801 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 196.93 | Sq.Ft | 55 | 100 | 270.78 | 0 | 10831.15 | C+S GST 18% I/P RD | 1949.6 | 12780.75 | 12780.75 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1301 Ceramic Tiling | Ceramic Flooring work | 370.07 | Sq.Ft | 18 | 100 | 166.53 | 0 | 6661.26 | C+S GST 18% I/P RD | 1199.02 | 7860.28 | 7860.28 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1401 Ceramic Tiling | Ceramic Flooring work | 370.07 | Sq.Ft | 18 | 100 | 166.53 | 0 | 6661.26 | C+S GST 18% I/P RD | 1199.02 | 7860.28 | 7860.28 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Children Toilet 1 Dado | Dado BC | 40.88 | Sq.Ft | 15 | 100 | 15.33 | 0 | 613.2 | C+S GST 18% I/P RD | 110.38 | 723.58 | 723.58 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Children Toilet 1 Dado | Dado BC | 49.58 | Sq.Ft | 15 | 100 | 18.59 | 0 | 743.7 | C+S GST 18% I/P RD | 133.86 | 877.56 | 877.56 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Children Toilet 2 Dado | Dado BC | 26.86 | Sq.Ft | 15 | 100 | 10.07 | 0 | 402.9 | C+S GST 18% I/P RD | 72.52 | 475.42 | 475.42 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Powder Toilet Dado | Dado BC | 39.56 | Sq.Ft | 15 | 100 | 14.84 | 0 | 593.4 | C+S GST 18% I/P RD | 106.82 | 700.22 | 700.22 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Master Toilet Dado | Dado BC | 56.7 | Sq.Ft | 15 | 100 | 21.26 | 0 | 850.5 | C+S GST 18% I/P RD | 153.1 | 1003.6 | 1003.6 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Guest Toilet Dado | Dado BC | 39.56 | Sq.Ft | 15 | 100 | 14.84 | 0 | 593.4 | C+S GST 18% I/P RD | 106.82 | 700.22 | 700.22 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Guest Toilet Dado | Dado BC | 65.93 | Sq.Ft | 15 | 100 | 24.72 | 0 | 988.95 | C+S GST 18% I/P RD | 178.02 | 1166.97 | 1166.97 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Powder Toilet Dado | Dado BC | 38.77 | Sq.Ft | 15 | 100 | 14.54 | 0 | 581.55 | C+S GST 18% I/P RD | 104.68 | 686.23 | 686.23 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Parents Toilet Dado | Dado BC | 54.06 | Sq.Ft | 15 | 100 | 20.27 | 0 | 810.9 | C+S GST 18% I/P RD | 145.96 | 956.86 | 956.86 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Parents Toilet Dado | Dado BC | 75.69 | Sq.Ft | 15 | 100 | 28.38 | 0 | 1135.35 | C+S GST 18% I/P RD | 204.36 | 1339.71 | 1339.71 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Master Toilet Dado | Dado BC | 94.94 | Sq.Ft | 15 | 100 | 35.6 | 0 | 1424.1 | C+S GST 18% I/P RD | 256.34 | 1680.44 | 1680.44 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Children Toilet 1 Dado | Dado BC | 162.77 | Sq.Ft | 14 | 100 | 56.97 | 0 | 2278.78 | C+S GST 18% I/P RD | 410.18 | 2688.96 | 2688.96 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Children Toilet 2 Dado | Dado BC | 170.18 | Sq.Ft | 14 | 100 | 59.56 | 0 | 2382.52 | C+S GST 18% I/P RD | 428.86 | 2811.38 | 2811.38 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Guest Toilet Dado | Dado BC | 187.48 | Sq.Ft | 14 | 100 | 65.62 | 0 | 2624.72 | C+S GST 18% I/P RD | 472.44 | 3097.16 | 3097.16 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Powder Toilet Dado | Dado BC | 106.81 | Sq.Ft | 14 | 100 | 37.38 | 0 | 1495.34 | C+S GST 18% I/P RD | 269.16 | 1764.5 | 1764.5 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Dry Balcony Dado | Dado BC | 81.38 | Sq.Ft | 14 | 100 | 28.48 | 0 | 1139.32 | C+S GST 18% I/P RD | 205.08 | 1344.4 | 1344.4 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Master Toilet Dado | Dado BC | 139.82 | Sq.Ft | 14 | 100 | 48.94 | 0 | 1957.48 | C+S GST 18% I/P RD | 352.34 | 2309.82 | 2309.82 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Children Toilet 1 Dado | Dado BC | 190.17 | Sq.Ft | 14 | 100 | 66.56 | 0 | 2662.38 | C+S GST 18% I/P RD | 479.22 | 3141.6 | 3141.6 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Master Toilet Dado | Dado BC | 173.61 | Sq.Ft | 14 | 100 | 60.76 | 0 | 2430.54 | C+S GST 18% I/P RD | 437.5 | 2868.04 | 2868.04 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Parents Toilet Dado | Dado BC | 181 | Sq.Ft | 14 | 100 | 63.35 | 0 | 2534 | C+S GST 18% I/P RD | 456.12 | 2990.12 | 2990.12 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Guest Toilet Dado | Dado BC | 134.85 | Sq.Ft | 14 | 100 | 47.2 | 0 | 1887.9 | C+S GST 18% I/P RD | 339.82 | 2227.72 | 2227.72 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Dry Balcony Dado | Dado BC | 90.42 | Sq.Ft | 14 | 100 | 31.65 | 0 | 1265.88 | C+S GST 18% I/P RD | 227.86 | 1493.74 | 1493.74 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 101 Parents Toilet Dado | Dado BC | 147.63 | Sq.Ft | 14 | 100 | 51.67 | 0 | 2066.82 | C+S GST 18% I/P RD | 372.02 | 2438.84 | 2438.84 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Powder Toilet Dado | Dado BC | 94.94 | Sq.Ft | 14 | 100 | 33.23 | 0 | 1329.16 | C+S GST 18% I/P RD | 239.24 | 1568.4 | 1568.4 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 1401 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 173.78 | Sq.Ft | 24 | 100 | 104.27 | 0 | 4170.72 | C+S GST 18% I/P RD | 750.72 | 4921.44 | 4921.44 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 701 Living Terrace Vitr.Flooring | Vitrified Flooring -BC | 192.46 | Sq.Ft | 20 | 100 | 96.23 | 0 | 3849.2 | C+S GST 18% I/P RD | 692.86 | 4542.06 | 4542.06 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Parents Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 45 | 100 | 231.29 | 0 | 9251.55 | C+S GST 18% I/P RD | 1665.28 | 10916.83 | 10916.83 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 45 | 100 | 742.01 | 0 | 29680.2 | C+S GST 18% I/P RD | 5342.44 | 35022.64 | 35022.64 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 758 | 91019 | 30 Jul 2021 | 44 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 647 | B 402 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 45 | 100 | 303.1 | 0 | 12123.9 | C+S GST 18% I/P RD | 2182.3 | 14306.2 | 14306.2 | Approved | 0 | 0 | 2501 | 30 Jul 2021
GANGA DHAM TOWERS | 772 | 91018 | 30 Jul 2021 | 215 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 765 | B 301 NOC - | Lintel Casting | 3.28 | R.Ft | 50 | 100 | 4.1 | 0 | 164 | C+S GST 18% I/P RD | 29.52 | 193.52 | 193.52 | Approved | 0 | 0 | 6 | 30 Jul 2021
GANGA DHAM TOWERS | 772 | 91018 | 30 Jul 2021 | 215 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 765 | B 1901 NOC | Labour Lumpsum - BC | 1 | No. | 200 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 6 | 30 Jul 2021
GANGA DHAM TOWERS | 772 | 91018 | 30 Jul 2021 | 215 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 765 | B 1901 NOC | Labour Lumpsum - BC | 1 | No. | 200 | 100 | 5 | 0 | 200 | C+S GST 18% I/P RD | 36 | 236 | 236 | Approved | 0 | 0 | 6 | 30 Jul 2021
GANGA DHAM TOWERS | 455 | 91017 | 30 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 643 | A Bldg Flat No. 1702 Internal Plumbing PPR-C | Int Flat PPRC Work. | 5 | No. | 1400 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 189 | 30 Jul 2021
GANGA DHAM TOWERS | 455 | 91017 | 30 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 643 | A Bldg Flat No. 1701 Internal Plumbing PPR-C | Int Flat PPRC Work. | 5 | No. | 1400 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 189 | 30 Jul 2021
GANGA DHAM TOWERS | 455 | 91017 | 30 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 643 | A Bldg Flat No. 1602 Internal Plumbing PPR-C | Int Flat PPRC Work. | 3.5 | No. | 1400 | 100 | 122.5 | 0 | 4900 | CGST 0% URD I/P | 0 | 4900 | 4900 | Approved | 0 | 0 | 189 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1501 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1701 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1702 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1703 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1502 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1702 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1703 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 300 | Sq.Ft | 19 | 100 | 570 | 0 | 5700 | CGST 0% URD I/P | 0 | 5700 | 5700 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1703 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 14 | No. | 70 | 100 | 98 | 0 | 980 | CGST 0% URD I/P | 0 | 980 | 980 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1701 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 14 | No. | 70 | 100 | 98 | 0 | 980 | CGST 0% URD I/P | 0 | 980 | 980 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1701 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1703 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1501 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1701 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 400 | Sq.Ft | 19 | 100 | 760 | 0 | 7600 | CGST 0% URD I/P | 0 | 7600 | 7600 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1502 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1801 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1601 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1701 Chemical & IPS Waterproofing | IPS W/P | 400 | Sq.Ft | 11 | 100 | 440 | 0 | 4400 | CGST 0% URD I/P | 0 | 4400 | 4400 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1502 Chemical & IPS Waterproofing | IPS W/P | 200 | Sq.Ft | 11 | 100 | 220 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1501 Chemical & IPS Waterproofing | IPS W/P | 200 | Sq.Ft | 11 | 100 | 220 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1702 Chemical & IPS Waterproofing | IPS W/P | 200 | Sq.Ft | 11 | 100 | 220 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1703 Chemical & IPS Waterproofing | IPS W/P | 300 | Sq.Ft | 11 | 100 | 330 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1601 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 401 | 91016 | 30 Jul 2021 | 162 | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 645 | A 1801 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 533 | 30 Jul 2021
GANGA DHAM TOWERS | 505 | 91015 | 30 Jul 2021 | 42 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 633 | A 19th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 647.13 | Sq.Ft | 2 | 100 | 129.43 | 0 | 1294.26 | CGST 0% URD I/P | 0 | 1294.26 | 1294.26 | Approved | 0 | 0 | 52 | 30 Jul 2021
GANGA DHAM TOWERS | 505 | 91015 | 30 Jul 2021 | 42 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 633 | A 21st Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 647.13 | Sq.Ft | 2 | 100 | 129.43 | 0 | 1294.26 | CGST 0% URD I/P | 0 | 1294.26 | 1294.26 | Approved | 0 | 0 | 52 | 30 Jul 2021
GANGA DHAM TOWERS | 505 | 91015 | 30 Jul 2021 | 42 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 633 | A 22nd Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 647.13 | Sq.Ft | 2 | 100 | 129.43 | 0 | 1294.26 | CGST 0% URD I/P | 0 | 1294.26 | 1294.26 | Approved | 0 | 0 | 52 | 30 Jul 2021
GANGA DHAM TOWERS | 505 | 91015 | 30 Jul 2021 | 42 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 633 | A 20th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 647.13 | Sq.Ft | 2 | 100 | 129.43 | 0 | 1294.26 | CGST 0% URD I/P | 0 | 1294.26 | 1294.26 | Approved | 0 | 0 | 52 | 30 Jul 2021
GANGA DHAM TOWERS | 1140 | 91014 | 29 Jul 2021 |  | ADDONE | ADDONE | EV - 596 | MEDIA FLEX PASTING | Backlet Box / Backlet Display Frame / Board | 220 | Sq.Ft | 180 | 100 | 0 | 0 | 39600 | C+S GST 18% I/P RD | 7128 | 46728 | 46728 | Approved | 0 | 0 | 792 | 29 Jul 2021
GANGA DHAM TOWERS | 634 | 91010 | 29 Jul 2021 | 2021-22-028 | R K INTERIOR | R K INTERIOR | EV - 750 | A 18th Floor Lobbby Flooring | Vitrified Skirting -Bco | 45 | R.Ft | 45 | 100 | 50.63 | 0 | 2025 | C+S GST 18% I/P RD | 364.5 | 2389.5 | 2389.5 | Approved | 0 | 0 | 1634 | 29 Jul 2021
GANGA DHAM TOWERS | 634 | 91010 | 29 Jul 2021 | 2021-22-028 | R K INTERIOR | R K INTERIOR | EV - 750 | A 18th Floor Lift cladding | Italian Marble Cladding - BCo | 240 | Sq.Ft | 103 | 100 | 618 | 0 | 24720 | C+S GST 18% I/P RD | 4449.6 | 29169.6 | 29169.6 | Approved | 0 | 0 | 1634 | 29 Jul 2021
GANGA DHAM TOWERS | 634 | 91010 | 29 Jul 2021 | 2021-22-028 | R K INTERIOR | R K INTERIOR | EV - 750 | A 18th Floor Lift cladding | Italian Marble Border-BCo | 297.8723 | R.Ft | 94 | 100 | 700 | 0 | 28000 | C+S GST 18% I/P RD | 5040 | 33040 | 33040 | Approved | 0 | 0 | 1634 | 29 Jul 2021
GANGA DHAM TOWERS | 634 | 91010 | 29 Jul 2021 | 2021-22-028 | R K INTERIOR | R K INTERIOR | EV - 750 | A 18th Floor Lobbby Flooring | Vitrified Flooring -Bco | 599.22 | Sq.Ft | 45 | 100 | 674.12 | 0 | 26964.9 | C+S GST 18% I/P RD | 4853.68 | 31818.58 | 31818.58 | Approved | 0 | 0 | 1634 | 29 Jul 2021
GANGA DHAM TOWERS | 209 | 91008 | 29 Jul 2021 | 213 | UNIQUE ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 719 | .A Bldg RCC Plinth Beam Substructure work | RCC Beam | 1352.8378 | Sq.Ft | 37 | 100 | 1251.37 | 0 | 50055 | C+S GST 18% I/P RD | 9009.9 | 59064.9 | 59064.9 | Approved | 0 | 0 | 501 | 29 Jul 2021
GANGA DHAM TOWERS | 996 | 91005 | 29 Jul 2021 | 2021-22-032 | R K INTERIOR | R K INTERIOR | EV - 776 | Club House Flooring/ Tiling ( L) | Acid Wash - Mkt | 5174.42 | Sq.Ft | 10 | 100 | 1293.61 | 0 | 51744.2 | C+S GST 18% I/P RD | 9313.96 | 61058.16 | 61058.16 | Approved | 0 | 0 | 1719 | 29 Jul 2021
GANGA DHAM TOWERS | 996 | 91005 | 29 Jul 2021 | 2021-22-032 | R K INTERIOR | R K INTERIOR | EV - 776 | Club House Flooring/ Tiling ( L) | Granite Buffing | 1710.64 | Sq.Ft | 20 | 100 | 855.32 | 0 | 34212.8 | C+S GST 18% I/P RD | 6158.3 | 40371.1 | 40371.1 | Approved | 0 | 0 | 1719 | 29 Jul 2021
GANGA DHAM TOWERS | 773 | 91004 | 29 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 640 | B P3 Parking chemical grouting | Chemical Grouting (L) | 18032 | Sq.Ft | 1 | 100 | 450.8 | 0 | 18032 | CGST 0% URD I/P | 0 | 18032 | 18032 | Approved | 0 | 0 | 361 | 29 Jul 2021
GANGA DHAM TOWERS | 773 | 91004 | 29 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 640 | B P3 Parking chemical grouting | Ghadai work- BCP | 18032 | Sq.Ft | 1 | 100 | 450.8 | 0 | 18032 | CGST 0% URD I/P | 0 | 18032 | 18032 | Approved | 0 | 0 | 361 | 29 Jul 2021
GANGA DHAM TOWERS | 742 | 91003 | 29 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 635 | A P2 Parking Ghadai & chemical grouting | Ghadai work- BCP | 2321 | Sq.Ft | 1 | 100 | 58.03 | 0 | 2321 | CGST 0% URD I/P | 0 | 2321 | 2321 | Approved | 0 | 0 | 46 | 29 Jul 2021
GANGA DHAM TOWERS | 742 | 91003 | 29 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 635 | A P2 Parking Ghadai & chemical grouting | Chemical Grouting (L) | 2321 | Sq.Ft | 1 | 100 | 58.03 | 0 | 2321 | CGST 0% URD I/P | 0 | 2321 | 2321 | Approved | 0 | 0 | 46 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 1902 Gypsum Plaster | Dhar Core (L) | 450 | R.Ft | 10 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 2002 Gypsum Plaster | Dhar Core (L) | 450 | R.Ft | 10 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 2102 Gypsum Plaster | Dhar Core (L) | 450 | R.Ft | 10 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 1901 Gypsum Plaster | Dhar Core (L) | 430 | R.Ft | 10 | 100 | 107.5 | 0 | 4300 | C+S GST 18% I/P RD | 774 | 5074 | 5074 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 2001 Gypsum Plaster | Dhar Core (L) | 430 | R.Ft | 10 | 100 | 107.5 | 0 | 4300 | C+S GST 18% I/P RD | 774 | 5074 | 5074 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 2002 Gypsum Plaster | Gypsum on Wall (L) | 2527 | Sq.Ft | 4 | 100 | 252.7 | 0 | 10108 | C+S GST 18% I/P RD | 1819.44 | 11927.44 | 11927.44 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 2102 Gypsum Plaster | Gypsum on Wall (L) | 2527 | Sq.Ft | 4 | 100 | 252.7 | 0 | 10108 | C+S GST 18% I/P RD | 1819.44 | 11927.44 | 11927.44 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 2001 Gypsum Plaster | Gypsum on Wall (L) | 2586 | Sq.Ft | 4 | 100 | 258.6 | 0 | 10344 | C+S GST 18% I/P RD | 1861.92 | 12205.92 | 12205.92 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 1901 Gypsum Plaster | Gypsum on Wall (L) | 2586 | Sq.Ft | 4 | 100 | 258.6 | 0 | 10344 | C+S GST 18% I/P RD | 1861.92 | 12205.92 | 12205.92 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 393 | 91002 | 29 Jul 2021 | 55 | J K INTERIOR | J K INTERIOR | EV - 715 | A Bldg Flat No. 1902 Gypsum Plaster | Gypsum on Wall (L) | 2527 | Sq.Ft | 4 | 100 | 252.7 | 0 | 10108 | C+S GST 18% I/P RD | 1819.44 | 11927.44 | 11927.44 | Approved | 0 | 0 | 731 | 29 Jul 2021
GANGA DHAM TOWERS | 1071 | 90986 | 26 Jul 2021 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 591 | Club House Electrical Work | Electrical Work (Labour) | 1 | No. | 213173 | 100 | 5329.33 | 0 | 213173 | C+S GST 18% I/P RD | 38371.14 | 251544.14 | 251544.14 | Approved | 0 | 100000 | 4263 | 26 Jul 2021
GANGA DHAM TOWERS | 1094 | 90985 | 26 Jul 2021 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 587 | Idle Pump Charges ( A ,B Up to 26th Floor) | Pumping Charges-BC | 587 | Cu.Mtrs | 190 | 100 | 0 | 0 | 111530 | C+S GST 18% I/P RD | 20075.4 | 131605.4 | 131605.4 | Approved | 0 | 100000 | 2231 | 26 Jul 2021
GANGA DHAM TOWERS | 864 | 90981 | 26 Jul 2021 |  | B.D. DONGARE | B.D. DONGARE | EV - 588 | B Core Cutting Work For Ac Work - | Core Cutting Work 4" BCE | 66 | No. | 300 | 100 | 0 | 0 | 19800 | C+S GST 18% I/P RD | 3564 | 23364 | 23364 | Approved | 0 | 25000 | 288 | 26 Jul 2021
GANGA DHAM TOWERS | 864 | 90981 | 26 Jul 2021 |  | B.D. DONGARE | B.D. DONGARE | EV - 588 | B Core Cutting Work For Ac Work - | Core Cutting Work 5" BCE | 30 | No. | 300 | 100 | 0 | 0 | 9000 | C+S GST 18% I/P RD | 1620 | 10620 | 10620 | Approved | 0 | 25000 | 288 | 26 Jul 2021
GANGA DHAM TOWERS | 698 | 90980 | 26 Jul 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 593 | D 603 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 673.9735 | Sq.Ft | 9 | 100 | 151.64 | 0 | 6065.76 | CGST 0% URD I/P | 0 | 6065.76 | 6065.76 | Approved | 0 | 10000 | 223 | 26 Jul 2021
GANGA DHAM TOWERS | 698 | 90980 | 26 Jul 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 593 | D 602 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 832.337 | Sq.Ft | 9 | 100 | 187.28 | 0 | 7491.03 | CGST 0% URD I/P | 0 | 7491.03 | 7491.03 | Approved | 0 | 10000 | 223 | 26 Jul 2021
GANGA DHAM TOWERS | 698 | 90980 | 26 Jul 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 593 | D 601 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 973.3265 | Sq.Ft | 9 | 100 | 219 | 0 | 8759.94 | CGST 0% URD I/P | 0 | 8759.94 | 8759.94 | Approved | 0 | 10000 | 223 | 26 Jul 2021
GANGA DHAM TOWERS | 522 | 90978 | 26 Jul 2021 | 45 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 639 | B Bldg 1301 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1400 | 100 | 245 | 0 | 9800 | CGST 0% URD I/P | 0 | 9800 | 9800 | Approved | 0 | 0 | 152 | 26 Jul 2021
GANGA DHAM TOWERS | 522 | 90978 | 26 Jul 2021 | 45 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 639 | B Bldg 402 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 900 | 100 | 135 | 0 | 5400 | CGST 0% URD I/P | 0 | 5400 | 5400 | Approved | 0 | 0 | 152 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 1601 Chemical Grouting | Chemical Grouting.- BC | 2330.62 | Sq.Ft | 2 | 100 | 466.12 | 0 | 4661.24 | CGST 0% URD I/P | 0 | 4661.24 | 4661.24 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 502 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 1602 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 501 Chemical Grouting | Chemical Grouting.- BC | 2561.94 | Sq.Ft | 2 | 100 | 512.39 | 0 | 5123.88 | CGST 0% URD I/P | 0 | 5123.88 | 5123.88 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 402 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 165 | Sq.Ft | 19 | 100 | 313.5 | 0 | 3135 | CGST 0% URD I/P | 0 | 3135 | 3135 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 902 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 402 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 0.25 | Flat | 1300 | 100 | 32.5 | 0 | 325 | CGST 0% URD I/P | 0 | 325 | 325 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 901 Bore Packing, IPS seal coat, Perma Eazee coat | IPS Seal Pack | 1 | Flat | 1300 | 100 | 130 | 0 | 1300 | CGST 0% URD I/P | 0 | 1300 | 1300 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 301 Chemical & IPS Waterproofing | IPS W/P | 581.79 | Sq.Ft | 11 | 100 | 639.97 | 0 | 6399.69 | CGST 0% URD I/P | 0 | 6399.69 | 6399.69 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 302 Chemical & IPS Waterproofing | IPS W/P | 468.45 | Sq.Ft | 11 | 100 | 515.3 | 0 | 5152.95 | CGST 0% URD I/P | 0 | 5152.95 | 5152.95 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 402 Chemical & IPS Waterproofing | IPS W/P | 468.45 | Sq.Ft | 11 | 100 | 515.3 | 0 | 5152.95 | CGST 0% URD I/P | 0 | 5152.95 | 5152.95 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 498 | 90977 | 26 Jul 2021 | 41 | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 637 | B 1401 Chemical & IPS Waterproofing | IPS W/P | 581.79 | Sq.Ft | 11 | 100 | 639.97 | 0 | 6399.69 | CGST 0% URD I/P | 0 | 6399.69 | 6399.69 | Approved | 0 | 0 | 460 | 26 Jul 2021
GANGA DHAM TOWERS | 506 | 90976 | 26 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 641 | B 19th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 19 | 26 Jul 2021
GANGA DHAM TOWERS | 506 | 90976 | 26 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 641 | B 18th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 19 | 26 Jul 2021
GANGA DHAM TOWERS | 506 | 90976 | 26 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 641 | B 20th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 19 | 26 Jul 2021
GANGA DHAM TOWERS | 549 | 90954 | 23 Jul 2021 | 2021-22-025 | R K INTERIOR | R K INTERIOR | EV - 773 | B 301 Mock Up Tiling Work | Dado Fixing | 80 | Sq.Ft | 61.5 | 100 | 123 | 0 | 4920 | C+S GST 18% I/P RD | 885.6 | 5805.6 | 5805.6 | Approved | 0 | 0 | 98 | 23 Jul 2021
GANGA DHAM TOWERS | 772 | 90953 | 23 Jul 2021 | 2021-22-024 | RAHUL ENTERPRISES (Prop Laburi) | R K INTERIOR | EV - 774 | B 301 NOC - | Dado -cc | 76.1 | Sq.Ft | 22 | 100 | 41.86 | 0 | 1674.2 | C+S GST 18% I/P RD | 301.36 | 1975.56 | 1975.56 | Approved | 0 | 0 | 33 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 9th Floor Lobby Flooring & cladding work | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 6th Floor Lobby Flooring & cladding work | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-12th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 7th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-10th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Border-BCo | 19.68 | R.Ft | 94 | 100 | 46.25 | 0 | 1849.92 | C+S GST 18% I/P RD | 332.98 | 2182.9 | 2182.9 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-10th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Border-BCo | 2.624 | R.Ft | 94 | 100 | 6.17 | 0 | 246.66 | C+S GST 18% I/P RD | 44.4 | 291.06 | 291.06 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 18th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-14th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 9th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-11th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 3rd Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 5th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-17th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 2nd Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-16th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-13th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 6th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 4th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-15th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 8th Floor Lobby Flooring & cladding work | Italian Marble Border-BCo | 22.304 | R.Ft | 94 | 100 | 52.41 | 0 | 2096.58 | C+S GST 18% I/P RD | 377.38 | 2473.96 | 2473.96 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 18th Floor Lobby Flooring & cladding work | Vitrified Flooring -Bco | 196.52 | Sq.Ft | 45 | 100 | 221.09 | 0 | 8843.4 | C+S GST 18% I/P RD | 1591.82 | 10435.22 | 10435.22 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 2nd Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 3rd Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 4th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-10th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 5th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-12th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-17th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 18th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 9th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 2nd Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-16th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 6th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 7th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 5th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-13th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 8th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-10th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-15th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 3rd Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-12th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-11th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 4th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-14th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-17th Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 18th Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-16th Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 1st Floor Lobby Flooring & cladding work | Italian Marble Cladding - BCo | 196.1748 | Sq.Ft | 103 | 100 | 505.15 | 0 | 20206 | C+S GST 18% I/P RD | 3637.08 | 23843.08 | 23843.08 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 3rd Floor Lobby Flooring & cladding work | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 1st Floor Lobby Flooring & cladding work | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 7th Floor Lobby Flooring & cladding work | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-10th Floor Lobby Flooring & cladding work - 1 Job | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 2nd Floor Lobby Flooring & cladding work - 1 Job | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 4th Floor Lobby Flooring & cladding work | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 5th Floor Lobby Flooring & cladding work | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 8th Floor Lobby Flooring & cladding work | Granite Counter Support | 77.62 | R.Ft | 70 | 100 | 135.84 | 0 | 5433.4 | C+S GST 18% I/P RD | 978.02 | 6411.42 | 6411.42 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 1st Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 89.55 | Sq.Ft | 200 | 100 | 447.75 | 0 | 17910 | C+S GST 18% I/P RD | 3223.8 | 21133.8 | 21133.8 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 18th Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 89.55 | Sq.Ft | 200 | 100 | 447.75 | 0 | 17910 | C+S GST 18% I/P RD | 3223.8 | 21133.8 | 21133.8 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-16th Floor Lobby Flooring & cladding work | Italian Marble Dry Cladding work (L) | 89.55 | Sq.Ft | 200 | 100 | 447.75 | 0 | 17910 | C+S GST 18% I/P RD | 3223.8 | 21133.8 | 21133.8 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-13th Floor Lobby Flooring & cladding work - 1 Job | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 7th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 4th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-17th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-14th Floor Lobby Flooring & cladding work - 1 Job | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 5th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-11th Floor Lobby Flooring & cladding work - 1 Job | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 18th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 8th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 1st Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-16th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 3rd Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-10th Floor Lobby Flooring & cladding work - 1 Job | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-15th Floor Lobby Flooring & cladding work - 1 Job | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-12th Floor Lobby Flooring & cladding work - 1 Job | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 6th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 9th Floor Lobby Flooring & cladding work | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 2nd Floor Lobby Flooring & cladding work - 1 Job | V Grove - BCo | 62.55 | R.Ft | 108 | 100 | 168.89 | 0 | 6755.4 | C+S GST 18% I/P RD | 1215.98 | 7971.38 | 7971.38 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 7th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 8th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-15th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-14th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 9th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 6th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-11th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-13th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-16th Floor Lobby Flooring & cladding work | Italian Marble Zero Joint-BCo | 102.0675 | R.Ft | 180 | 100 | 459.3 | 0 | 18372.15 | C+S GST 18% I/P RD | 3306.98 | 21679.13 | 21679.13 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 1st Floor Lobby Flooring & cladding work | Italian Marble Cladding | 113.43 | R.Ft | 94 | 100 | 266.56 | 0 | 10662.42 | C+S GST 18% I/P RD | 1919.24 | 12581.66 | 12581.66 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-13th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 2nd Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 3rd Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 1st Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 7th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 8th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-16th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 6th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-15th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 4th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-17th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 9th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-12th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 5th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-14th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B 18th Floor Lobby Flooring & cladding work | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-10th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 741 | 90949 | 23 Jul 2021 | 2021-22-026 | R K INTERIOR | R K INTERIOR | EV - 764 | B-11th Floor Lobby Flooring & cladding work - 1 Job | Italian Marble Bull Nosing | 73.3425 | R.Ft | 76 | 100 | 139.35 | 0 | 5574.03 | C+S GST 18% I/P RD | 1003.32 | 6577.35 | 6577.35 | Approved | 0 | 0 | 18419 | 23 Jul 2021
GANGA DHAM TOWERS | 991 | 90942 | 22 Jul 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 600 | B 1001 NOC | Concrete Cutting Work | 13.3333 | R.Ft | 525 | 100 | 175 | 0 | 7000 | CGST 0% URD I/P | 0 | 7000 | 7000 | Approved | 0 | 0 | 70 | 22 Jul 2021
GANGA DHAM TOWERS | 773 | 90934 | 21 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 636 | B P3 Parking chemical grouting | Ghadai work- BCP | 2490 | Sq.Ft | 1 | 100 | 62.25 | 0 | 2490 | CGST 0% URD I/P | 0 | 2490 | 2490 | Approved | 0 | 0 | 50 | 21 Jul 2021
GANGA DHAM TOWERS | 773 | 90934 | 21 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 636 | B P3 Parking chemical grouting | Chemical Grouting (L) | 2490 | Sq.Ft | 1 | 100 | 62.25 | 0 | 2490 | CGST 0% URD I/P | 0 | 2490 | 2490 | Approved | 0 | 0 | 50 | 21 Jul 2021
GANGA DHAM TOWERS | 1067 | 90933 | 21 Jul 2021 | 339 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 677 | B Ground Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 400 | Sq.Ft | 9 | 100 | 90 | 0 | 3600 | C+S GST 18% I/P RD | 648 | 4248 | 4248 | Approved | 0 | 0 | 36 | 21 Jul 2021
GANGA DHAM TOWERS | 1065 | 90932 | 21 Jul 2021 | 338 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 676 | A Ground Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 400 | Sq.Ft | 9 | 100 | 90 | 0 | 3600 | C+S GST 18% I/P RD | 648 | 4248 | 4248 | Approved | 0 | 0 | 36 | 21 Jul 2021
GANGA DHAM TOWERS | 1045 | 90931 | 21 Jul 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 599 | Developement Drainage Line Breaker | Breaker - UTI | 4 | Day | 900 | 100 | 0 | 0 | 3600 | CGST 0% URD I/P | 0 | 3600 | 3600 | Approved | 0 | 0 | 36 | 21 Jul 2021
GANGA DHAM TOWERS | 742 | 90929 | 21 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 644 | A P3 Parking Ghadai & chemical grouting | Ghadai work- BCP | 6623 | Sq.Ft | 1 | 100 | 165.58 | 0 | 6623 | CGST 0% URD I/P | 0 | 6623 | 6623 | Approved | 0 | 0 | 132 | 21 Jul 2021
GANGA DHAM TOWERS | 742 | 90929 | 21 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 644 | A P3 Parking Ghadai & chemical grouting | Chemical Grouting (L) | 6623 | Sq.Ft | 1 | 100 | 165.58 | 0 | 6623 | CGST 0% URD I/P | 0 | 6623 | 6623 | Approved | 0 | 0 | 132 | 21 Jul 2021
GANGA DHAM TOWERS | 1133 | 90928 | 21 Jul 2021 |  | BASSAPPA CHAVAN | BASSAPPA CHAVAN | EV - 697 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | Tractor Trip - Dld | 45 | No. | 800 | 100 | 0 | 0 | 36000 | CGST 0% URD I/P | 0 | 36000 | 36000 | Approved | 0 | 0 | 360 | 21 Jul 2021
GANGA DHAM TOWERS | 649 | 90927 | 21 Jul 2021 | 337 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 673 | A P1 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 500 | Sq.Ft | 5 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 203 | 21 Jul 2021
GANGA DHAM TOWERS | 649 | 90927 | 21 Jul 2021 | 337 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 673 | A Ground Floor Column Plaster | Tikki Dhada rate diff. (L) | 500 | Sq.Ft | 5 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 203 | 21 Jul 2021
GANGA DHAM TOWERS | 649 | 90927 | 21 Jul 2021 | 337 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 673 | A Ground Floor Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 1533 | Sq.Ft | 5 | 100 | 191.63 | 0 | 7665 | C+S GST 18% I/P RD | 1379.7 | 9044.7 | 9044.7 | Approved | 0 | 0 | 203 | 21 Jul 2021
GANGA DHAM TOWERS | 649 | 90927 | 21 Jul 2021 | 337 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 673 | A Ground Floor Beam & Ceiling Plaster | Tikki Dhada rate diff. (L) | 167 | Sq.Ft | 5 | 100 | 20.88 | 0 | 835 | C+S GST 18% I/P RD | 150.3 | 985.3 | 985.3 | Approved | 0 | 0 | 203 | 21 Jul 2021
GANGA DHAM TOWERS | 649 | 90927 | 21 Jul 2021 | 337 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 673 | A P1 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (L) | 1700 | Sq.Ft | 4 | 100 | 170 | 0 | 6800 | C+S GST 18% I/P RD | 1224 | 8024 | 8024 | Approved | 0 | 0 | 203 | 21 Jul 2021
GANGA DHAM TOWERS | 389 | 90922 | 19 Jul 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 544 | Loading / Unloading Expenses | Unloading of AAC Blocks | 10 | Metric Tonnes | 120 | 100 | 0 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 0 | 19 Jul 2021
GANGA DHAM TOWERS | 1111 | 90918 | 17 Jul 2021 | KKENG/21-22/040 | K.K.ENGINEERING | K.K.ENGINEERING | EV - 755 | DA Dev Top Terr. Store Alum Window | Al Window (m+l)-BCo- | 90 | Sq.Ft | 180 | 100 | 405 | 0 | 16200 | C+S GST 18% I/P RD | 2916 | 19116 | 19116 | Approved | 0 | 0 | 0 | 17 Jul 2021
GANGA DHAM TOWERS | 1111 | 90918 | 17 Jul 2021 | KKENG/21-22/040 | K.K.ENGINEERING | K.K.ENGINEERING | EV - 755 | DA Dev Top Terr. Store Alum Window | Aluminium work lumpsum-AIE | 1 | No. | 5000 | 100 | 125 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 0 | 17 Jul 2021
GANGA DHAM TOWERS | 1117 | 90917 | 17 Jul 2021 | 185/21-22 | A N INTERIORS | A N INTERIORS | EV - 575 | DA Development Carpentary work | Department Labour - Day | 11 | Day | 700 | 100 | 0 | 0 | 7700 | C+S GST 18% I/P RD | 1386 | 9086 | 9086 | Approved | 0 | 0 | 207 | 17 Jul 2021
GANGA DHAM TOWERS | 1117 | 90917 | 17 Jul 2021 | 185/21-22 | A N INTERIORS | A N INTERIORS | EV - 575 | DA Development Carpentary work | Department Labour - Day | 13 | Day | 1000 | 100 | 0 | 0 | 13000 | C+S GST 18% I/P RD | 2340 | 15340 | 15340 | Approved | 0 | 0 | 207 | 17 Jul 2021
GANGA DHAM TOWERS | 1110 | 90916 | 17 Jul 2021 | 184/21-22 | A N INTERIORS | A N INTERIORS | EV - 1102 | B1- 1101 Carpentry Work (L) | Carpentary work -Mkt | 0.5 | No. | 100000 | 100 | 0 | 0 | 50000 | C+S GST 18% I/P RD | 9000 | 59000 | 59000 | Approved | 0 | 0 | 500 | 17 Jul 2021
GANGA DHAM TOWERS | 368 | 90909 | 15 Jul 2021 |  | VATSA ENGINEERING | SAURABH FABRICATION | EV - 568 | Tower-A Terrace Safety Railing 4th Floor to 26th Floor | Fabrication Work (L) - BCo | 1263.9091 | Kgs | 11 | 100 | 347.58 | 0 | 13903 | CGST 0% URD I/P | 0 | 13903 | 13903 | Approved | 0 | 0 | 220 | 15 Jul 2021
GANGA DHAM TOWERS | 368 | 90909 | 15 Jul 2021 |  | VATSA ENGINEERING | SAURABH FABRICATION | EV - 568 | Tower-A Terrace Safety Railing 4th Floor to 26th Floor | Nails | 8 | Kgs | 90 | 100 | 0 | 0 | 720 | CGST 0% URD I/P | 0 | 720 | 720 | Approved | 0 | 0 | 220 | 15 Jul 2021
GANGA DHAM TOWERS | 368 | 90909 | 15 Jul 2021 |  | VATSA ENGINEERING | SAURABH FABRICATION | EV - 568 | Tower-A Terrace Safety Railing 4th Floor to 26th Floor | Hold Fast Patti- DSP | 736 | No. | 10 | 100 | 184 | 0 | 7360 | CGST 0% URD I/P | 0 | 7360 | 7360 | Approved | 0 | 0 | 220 | 15 Jul 2021
GANGA DHAM TOWERS | 1104 | 90895 | 13 Jul 2021 | 334 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 675 | A 404 Terrace False Ceiling | PVC False Ceiling (L) | 177.61 | Sq.Ft | 20 | 100 | 88.81 | 0 | 3552.2 | C+S GST 18% I/P RD | 639.4 | 4191.6 | 4191.6 | Approved | 0 | 0 | 67 | 13 Jul 2021
GANGA DHAM TOWERS | 1104 | 90895 | 13 Jul 2021 | 334 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 675 | A 304 Terrace False Ceiling | PVC False Ceiling (L) | 156.08 | Sq.Ft | 20 | 100 | 78.04 | 0 | 3121.6 | C+S GST 18% I/P RD | 561.88 | 3683.48 | 3683.48 | Approved | 0 | 0 | 67 | 13 Jul 2021
GANGA DHAM TOWERS | 1105 | 90894 | 13 Jul 2021 | 335 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 674 | A 404 Terrace False Ceiling | PVC False Ceiling (M) | 177.61 | Sq.Ft | 50 | 100 | 0 | 0 | 8880.5 | C+S GST 18% I/P RD | 1598.5 | 10479 | 10479 | Approved | 0 | 0 | 0 | 13 Jul 2021
GANGA DHAM TOWERS | 1105 | 90894 | 13 Jul 2021 | 335 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 674 | A 304 Terrace False Ceiling | PVC False Ceiling (M) | 156.08 | Sq.Ft | 50 | 100 | 0 | 0 | 7804 | C+S GST 18% I/P RD | 1404.72 | 9208.72 | 9208.72 | Approved | 0 | 0 | 0 | 13 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | Video Door Phone (L)- BC | 0.7 | No. | 200 | 25 | 0.88 | 0 | 35 | C+S GST 18% I/P RD | 6.3 | 41.3 | 41.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 501 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 701 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 402 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1701 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1101 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1502 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 399 | 90869 | 12 Jul 2021 | PLVE/21-22/17 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 745 | B Bldg Flat No. 1102 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 873 | 12 Jul 2021
GANGA DHAM TOWERS | 1115 | 90868 | 12 Jul 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 693 | B1- 1101 Pop Breaking Rabbit Shifting | Department Labour-Dev | 25 | No. | 450 | 100 | 0 | 0 | 11250 | CGST 0% URD I/P | 0 | 11250 | 11250 | Approved | 0 | 0 | 405 | 12 Jul 2021
GANGA DHAM TOWERS | 1115 | 90868 | 12 Jul 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 693 | B1- 1101 Pop Breaking Rabbit Shifting | Department Labour-Dev | 57 | No. | 450 | 100 | 0 | 0 | 25650 | CGST 0% URD I/P | 0 | 25650 | 25650 | Approved | 0 | 0 | 405 | 12 Jul 2021
GANGA DHAM TOWERS | 1115 | 90868 | 12 Jul 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 693 | B1- 1101 Pop Breaking Rabbit Shifting | Breaker | 4 | Day | 900 | 100 | 0 | 0 | 3600 | CGST 0% URD I/P | 0 | 3600 | 3600 | Approved | 0 | 0 | 405 | 12 Jul 2021
GANGA DHAM TOWERS | 991 | 90867 | 12 Jul 2021 | 7 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 953 | B 1001 NOC | Concrete Cutting Work | 541.8705 | R.Ft | 525 | 100 | 7112.05 | 0 | 284482 | C+S GST 18% I/P RD | 51206.76 | 335688.76 | 335688.76 | Approved | 0 | 0 | 6384 | 12 Jul 2021
GANGA DHAM TOWERS | 991 | 90867 | 12 Jul 2021 | 7 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 953 | B 1001 NOC | Concrete wall Crushing work | 4.82 | Cu.Mtrs | 7200 | 100 | 867.6 | 0 | 34704 | C+S GST 18% I/P RD | 6246.72 | 40950.72 | 40950.72 | Approved | 0 | 0 | 6384 | 12 Jul 2021
GANGA DHAM TOWERS | 1070 | 90859 | 10 Jul 2021 |  | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 518 | Lab Performance Test for strip window system | Lab Test for Strip Window System. | 1 | No. | 900000 | 50 | 0 | 0 | 450000 | C+S GST 18% I/P RD | 81000 | 531000 | 531000 | Approved | 0 | 0 | 9000 | 10 Jul 2021
GANGA DHAM TOWERS | 300 | 90844 | 09 Jul 2021 |  | AMOL WATER SUPPLIERS | AMOL WATER SUPPLIERS | EV - 1097 | Road Divider Water Supply | Water Tanker - Mkt | 15 | Trips | 700 | 100 | 0 | 0 | 10500 | C+S GST 0% I/P RD | 0 | 10500 | 10500 | Approved | 0 | 0 | 0 | 09 Jul 2021
GANGA DHAM TOWERS | 300 | 90844 | 09 Jul 2021 |  | AMOL WATER SUPPLIERS | AMOL WATER SUPPLIERS | EV - 1097 | Road Divider Water Supply | Water Tanker - Mkt | 13 | Trips | 700 | 100 | 0 | 0 | 9100 | C+S GST 0% I/P RD | 0 | 9100 | 9100 | Approved | 0 | 0 | 0 | 09 Jul 2021
GANGA DHAM TOWERS | 272 | 90843 | 09 Jul 2021 | 161 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 628 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.594 | Sq.Ft | 133 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 428 | 09 Jul 2021
GANGA DHAM TOWERS | 272 | 90843 | 09 Jul 2021 | 161 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 628 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.594 | Sq.Ft | 133 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 428 | 09 Jul 2021
GANGA DHAM TOWERS | 272 | 90843 | 09 Jul 2021 | 161 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 628 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.1203 | Sq.Ft | 133 | 100 | 0 | 0 | 6400 | C+S GST 18% I/P RD | 1152 | 7552 | 7552 | Approved | 0 | 0 | 428 | 09 Jul 2021
GANGA DHAM TOWERS | 272 | 90843 | 09 Jul 2021 | 161 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 628 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 48.1579 | Sq.Ft | 133 | 100 | 0 | 0 | 6405 | C+S GST 18% I/P RD | 1152.9 | 7557.9 | 7557.9 | Approved | 0 | 0 | 428 | 09 Jul 2021
GANGA DHAM TOWERS | 272 | 90843 | 09 Jul 2021 | 161 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 628 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.594 | Sq.Ft | 133 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 428 | 09 Jul 2021
GANGA DHAM TOWERS | 272 | 90843 | 09 Jul 2021 | 161 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 628 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.594 | Sq.Ft | 133 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 428 | 09 Jul 2021
GANGA DHAM TOWERS | 272 | 90843 | 09 Jul 2021 | 161 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 628 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.594 | Sq.Ft | 133 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 428 | 09 Jul 2021
GANGA DHAM TOWERS | 272 | 90843 | 09 Jul 2021 | 161 | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 628 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 37.594 | Sq.Ft | 133 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 428 | 09 Jul 2021
GANGA DHAM TOWERS | 126 | 90842 | 09 Jul 2021 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP VAMANRAO RUPNAWAR | EV - 567 | Site Expenses | Site Expenses -SO | 0.5333 | Month | 15000 | 100 | 0 | 0 | 8000 | CGST 0% URD I/P | 0 | 8000 | 8000 | Approved | 0 | 0 | 0 | 09 Jul 2021
GANGA DHAM TOWERS | 258 | 90841 | 09 Jul 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 581 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.8 | Month | 2500 | 100 | 0 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 20 | 09 Jul 2021
GANGA DHAM TOWERS | 237 | 90840 | 09 Jul 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 580 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.8 | Month | 7000 | 100 | 0 | 0 | 5600 | CGST 0% URD I/P | 0 | 5600 | 5600 | Approved | 0 | 0 | 56 | 09 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 404 Walls Satin Matt Painting | Oil base Primer-BC | 2219.776 | Sq.Ft | 1 | 100 | 55.49 | 0 | 2219.78 | IGST 18% I/P RD | 399.56 | 2619.34 | 2619.34 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1702 Walls Satin Matt Painting | Oil base Primer-BC | 2351.52 | Sq.Ft | 1 | 100 | 58.79 | 0 | 2351.52 | IGST 18% I/P RD | 423.27 | 2774.79 | 2774.79 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1403 Walls Satin Matt Painting | Oil base Primer-BC | 2209.92 | Sq.Ft | 1 | 100 | 55.25 | 0 | 2209.92 | IGST 18% I/P RD | 397.79 | 2607.71 | 2607.71 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1001 Walls Satin Matt Paint | Oil base Primer-BC | 2429.024 | Sq.Ft | 1 | 100 | 60.73 | 0 | 2429.02 | IGST 18% I/P RD | 437.22 | 2866.24 | 2866.24 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1002 Walls Satin Matt Painting | Oil base Primer-BC | 2351.52 | Sq.Ft | 1 | 100 | 58.79 | 0 | 2351.52 | IGST 18% I/P RD | 423.27 | 2774.79 | 2774.79 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 201 Walls Satin Matt Paint | Oil base Primer-BC | 2429.024 | Sq.Ft | 1 | 100 | 60.73 | 0 | 2429.02 | IGST 18% I/P RD | 437.22 | 2866.24 | 2866.24 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1003 Walls Satin Matt Painting | Oil base Primer-BC | 2209.92 | Sq.Ft | 1 | 100 | 55.25 | 0 | 2209.92 | IGST 18% I/P RD | 397.79 | 2607.71 | 2607.71 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 404 Walls Satin Matt Painting | Scrapping with 2nd Coat Putty | 2219.776 | Sq.Ft | 1.25 | 100 | 69.37 | 0 | 2774.72 | IGST 18% I/P RD | 499.45 | 3274.17 | 3274.17 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 401 Walls Satin Matt Paint | Scrapping with 2nd Coat Putty | 2429.024 | Sq.Ft | 1.25 | 100 | 75.91 | 0 | 3036.28 | IGST 18% I/P RD | 546.53 | 3582.81 | 3582.81 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 604 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2219.776 | Sq.Ft | 1.25 | 100 | 69.37 | 0 | 2774.72 | IGST 18% I/P RD | 499.45 | 3274.17 | 3274.17 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1003 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2209.92 | Sq.Ft | 1.25 | 100 | 69.06 | 0 | 2762.4 | IGST 18% I/P RD | 497.23 | 3259.63 | 3259.63 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 601 Walls Satin Matt Paint | Scrapping with 1st Coat Putty | 2429.024 | Sq.Ft | 1.25 | 100 | 75.91 | 0 | 3036.28 | IGST 18% I/P RD | 546.53 | 3582.81 | 3582.81 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 201 Walls Satin Matt Paint | Scrapping with 1st Coat Putty | 2429.024 | Sq.Ft | 1.25 | 100 | 75.91 | 0 | 3036.28 | IGST 18% I/P RD | 546.53 | 3582.81 | 3582.81 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 401 Walls Satin Matt Paint | Scrapping with 1st Coat Putty | 2429.024 | Sq.Ft | 1.25 | 100 | 75.91 | 0 | 3036.28 | IGST 18% I/P RD | 546.53 | 3582.81 | 3582.81 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1002 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2351.52 | Sq.Ft | 1.25 | 100 | 73.49 | 0 | 2939.4 | IGST 18% I/P RD | 529.09 | 3468.49 | 3468.49 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1402 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2351.52 | Sq.Ft | 1.25 | 100 | 73.49 | 0 | 2939.4 | IGST 18% I/P RD | 529.09 | 3468.49 | 3468.49 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 602 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2351.52 | Sq.Ft | 1.25 | 100 | 73.49 | 0 | 2939.4 | IGST 18% I/P RD | 529.09 | 3468.49 | 3468.49 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1403 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2209.92 | Sq.Ft | 1.25 | 100 | 69.06 | 0 | 2762.4 | IGST 18% I/P RD | 497.23 | 3259.63 | 3259.63 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 603 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2209.92 | Sq.Ft | 1.25 | 100 | 69.06 | 0 | 2762.4 | IGST 18% I/P RD | 497.23 | 3259.63 | 3259.63 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 404 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2219.776 | Sq.Ft | 1.25 | 100 | 69.37 | 0 | 2774.72 | IGST 18% I/P RD | 499.45 | 3274.17 | 3274.17 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 403 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2209.92 | Sq.Ft | 1.25 | 100 | 69.06 | 0 | 2762.4 | IGST 18% I/P RD | 497.23 | 3259.63 | 3259.63 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1701 Walls Satin Matt Paint | Scrapping with 1st Coat Putty | 2429.024 | Sq.Ft | 1.25 | 100 | 75.91 | 0 | 3036.28 | IGST 18% I/P RD | 546.53 | 3582.81 | 3582.81 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1001 Walls Satin Matt Paint | Scrapping with 1st Coat Putty | 2429.024 | Sq.Ft | 1.25 | 100 | 75.91 | 0 | 3036.28 | IGST 18% I/P RD | 546.53 | 3582.81 | 3582.81 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1702 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2351.52 | Sq.Ft | 1.25 | 100 | 73.49 | 0 | 2939.4 | IGST 18% I/P RD | 529.09 | 3468.49 | 3468.49 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 903 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2209.92 | Sq.Ft | 1.25 | 100 | 69.06 | 0 | 2762.4 | IGST 18% I/P RD | 497.23 | 3259.63 | 3259.63 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 1113 | 90814 | 07 Jul 2021 |  | HINDUSTAN MAINTENANCE COMPANY | HINDUSTAN MAINTENANCE COMPANY | EV - 532 | A 1302 Walls Satin Matt Painting | Scrapping with 1st Coat Putty | 2351.52 | Sq.Ft | 1.25 | 100 | 73.49 | 0 | 2939.4 | IGST 18% I/P RD | 529.09 | 3468.49 | 3468.49 | Approved | 0 | 0 | 713 | 07 Jul 2021
GANGA DHAM TOWERS | 742 | 90806 | 06 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 559 | A P3 Parking Ghadai & chemical grouting | Ghadai work- BCP | 1970 | Sq.Ft | 1 | 100 | 49.25 | 0 | 1970 | CGST 0% URD I/P | 0 | 1970 | 1970 | Approved | 0 | 0 | 39 | 06 Jul 2021
GANGA DHAM TOWERS | 742 | 90806 | 06 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 559 | A P3 Parking Ghadai & chemical grouting | Chemical Grouting (L) | 1970 | Sq.Ft | 1 | 100 | 49.25 | 0 | 1970 | CGST 0% URD I/P | 0 | 1970 | 1970 | Approved | 0 | 0 | 39 | 06 Jul 2021
GANGA DHAM TOWERS | 1037 | 90803 | 06 Jul 2021 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 449 | Head Office Security Service | Security Guard AIE - | 60 | Day | 433.33 | 100 | 0 | 0 | 25999.8 | C+S GST 18% I/P RD | 4679.96 | 30679.76 | 30679.76 | Approved | 0 | 0 | 260 | 06 Jul 2021
GANGA DHAM TOWERS | 145 | 90801 | 06 Jul 2021 | 168 | PEST-O-CRUSH | S.R.Enterprises | EV - 951 | Fogging Work | Fogging work-SO | 1 | Month | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 06 Jul 2021
GANGA DHAM TOWERS | 940 | 90800 | 06 Jul 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 500 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 06 Jul 2021
GANGA DHAM TOWERS | 149 | 90799 | 06 Jul 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 479 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 1936 | No. | 4 | 100 | 0 | 0 | 7744 | CGST 0% URD I/P | 0 | 7744 | 7744 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 868 | 90798 | 06 Jul 2021 | GFE/NEW/013 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 490 | B FAS & PA System | 2 Way Commnction fire fighters Handset (M) | 1 | No. | 4850.02 | 100 | 0 | 0 | 4850 | C+S GST 18% I/P RD | 873 | 5723 | 5723 | Approved | 0 | 0 | 9397 | 06 Jul 2021
GANGA DHAM TOWERS | 868 | 90798 | 06 Jul 2021 | GFE/NEW/013 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 490 | B FAS & PA System | Manual Pull Station (M) | 22 | No. | 3600 | 100 | 0 | 0 | 79200 | C+S GST 18% I/P RD | 14256 | 93456 | 93456 | Approved | 0 | 0 | 9397 | 06 Jul 2021
GANGA DHAM TOWERS | 868 | 90798 | 06 Jul 2021 | GFE/NEW/013 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 490 | B FAS & PA System | Addressable Monitor Module (M) | 22 | No. | 2043 | 100 | 0 | 0 | 44946 | C+S GST 18% I/P RD | 8090.28 | 53036.28 | 53036.28 | Approved | 0 | 0 | 9397 | 06 Jul 2021
GANGA DHAM TOWERS | 868 | 90798 | 06 Jul 2021 | GFE/NEW/013 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 490 | B FAS & PA System | Addressable Fire Alarm Panel (M) | 2 | No. | 281930 | 100 | 0 | 0 | 563860 | C+S GST 18% I/P RD | 101494.8 | 665354.8 | 665354.8 | Approved | 0 | 0 | 9397 | 06 Jul 2021
GANGA DHAM TOWERS | 868 | 90798 | 06 Jul 2021 | GFE/NEW/013 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 490 | B FAS & PA System | Ceiling Mountable ABS Plastic Grill (M) | 46 | No. | 850 | 100 | 0 | 0 | 39100 | C+S GST 18% I/P RD | 7038 | 46138 | 46138 | Approved | 0 | 0 | 9397 | 06 Jul 2021
GANGA DHAM TOWERS | 868 | 90798 | 06 Jul 2021 | GFE/NEW/013 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 490 | B FAS & PA System | Addressable Mini Monitor Module (M) | 22 | No. | 1176 | 100 | 0 | 0 | 25872 | C+S GST 18% I/P RD | 4656.96 | 30528.96 | 30528.96 | Approved | 0 | 0 | 9397 | 06 Jul 2021
GANGA DHAM TOWERS | 868 | 90798 | 06 Jul 2021 | GFE/NEW/013 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 490 | B FAS & PA System | SITC Fireman's Phone Jack (M) | 22 | No. | 1450 | 100 | 0 | 0 | 31900 | C+S GST 18% I/P RD | 5742 | 37642 | 37642 | Approved | 0 | 0 | 9397 | 06 Jul 2021
GANGA DHAM TOWERS | 868 | 90798 | 06 Jul 2021 | GFE/NEW/013 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 490 | B FAS & PA System | 2C 1.5 sqmm (FRLS) Cable (M) | 5000 | Mtrs | 30 | 100 | 0 | 0 | 150000 | C+S GST 18% I/P RD | 27000 | 177000 | 177000 | Approved | 0 | 0 | 9397 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | Addressable Mini Monitor Module (M) | 22 | No. | 1176 | 100 | 0 | 0 | 25872 | C+S GST 18% I/P RD | 4656.96 | 30528.96 | 30528.96 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | Ceiling Mountable ABS Plastic Grill (M) | 46 | No. | 850 | 100 | 0 | 0 | 39100 | C+S GST 18% I/P RD | 7038 | 46138 | 46138 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | Addressable Fire Alarm Panel (M) | 3 | No. | 281930 | 100 | 0 | 0 | 845790 | C+S GST 18% I/P RD | 152242.2 | 998032.2 | 998032.2 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | Addressable Monitor Module (M) | 29 | No. | 2043 | 100 | 0 | 0 | 59247 | C+S GST 18% I/P RD | 10664.46 | 69911.46 | 69911.46 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | Manual Pull Station (M) | 22 | No. | 3600 | 100 | 0 | 0 | 79200 | C+S GST 18% I/P RD | 14256 | 93456 | 93456 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | Digital Amplifier (M) | 1 | No. | 29500 | 100 | 0 | 0 | 29500 | C+S GST 18% I/P RD | 5310 | 34810 | 34810 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | SITC Fireman's Phone Jack (M) | 22 | No. | 1450 | 100 | 0 | 0 | 31900 | C+S GST 18% I/P RD | 5742 | 37642 | 37642 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | 2 Way Commnction fire fighters Handset (M) | 2 | No. | 4850.02 | 100 | 0 | 0 | 9700 | C+S GST 18% I/P RD | 1746 | 11446 | 11446 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 866 | 90797 | 06 Jul 2021 | gfe/new/014 | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 487 | A FAS & PA System | Digital Voice Evacuation System Expander (M) | 1 | No. | 35500 | 100 | 0 | 0 | 35500 | C+S GST 18% I/P RD | 6390 | 41890 | 41890 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 774 | 90796 | 06 Jul 2021 | 104 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 545 | B Parking Floor 2 Trimix work | Weld mesh fixing(L) BCo | 15000 | Sq.Ft | 1 | 100 | 375 | 0 | 15000 | C+S GST 18% I/P RD | 2700 | 17700 | 17700 | Approved | 0 | 0 | 3000 | 06 Jul 2021
GANGA DHAM TOWERS | 774 | 90796 | 06 Jul 2021 | 104 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 545 | B Parking Floor 2 Trimix work | Trimix Work - BC | 15000 | Sq.Ft | 9 | 100 | 3375 | 0 | 135000 | C+S GST 18% I/P RD | 24300 | 159300 | 159300 | Approved | 0 | 0 | 3000 | 06 Jul 2021
GANGA DHAM TOWERS | 724 | 90795 | 06 Jul 2021 | 105 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 546 | A Parking Floor 2 Trimix work | Trimix Work - BC | 4000 | Sq.Ft | 9 | 100 | 900 | 0 | 36000 | C+S GST 18% I/P RD | 6480 | 42480 | 42480 | Approved | 0 | 0 | 800 | 06 Jul 2021
GANGA DHAM TOWERS | 724 | 90795 | 06 Jul 2021 | 105 | MUKESH CONSTRUCTIONS | VISION INFRA | EV - 546 | A Parking Floor 2 Trimix work | Weld mesh fixing(L) BCo | 4000 | Sq.Ft | 1 | 100 | 100 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 800 | 06 Jul 2021
GANGA DHAM TOWERS | 742 | 90794 | 06 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 560 | A P2 Parking Ghadai & chemical grouting | Chemical Grouting (L) | 9671 | Sq.Ft | 1 | 100 | 241.78 | 0 | 9671 | CGST 0% URD I/P | 0 | 9671 | 9671 | Approved | 0 | 0 | 193 | 06 Jul 2021
GANGA DHAM TOWERS | 742 | 90794 | 06 Jul 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 560 | A P2 Parking Ghadai & chemical grouting | Ghadai work- BCP | 9671 | Sq.Ft | 1 | 100 | 241.78 | 0 | 9671 | CGST 0% URD I/P | 0 | 9671 | 9671 | Approved | 0 | 0 | 193 | 06 Jul 2021
GANGA DHAM TOWERS | 1065 | 90793 | 06 Jul 2021 | 331 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 477 | A P1 Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 28 | Sq.Ft | 9 | 100 | 6.3 | 0 | 252 | C+S GST 18% I/P RD | 45.36 | 297.36 | 297.36 | Approved | 0 | 0 | 86 | 06 Jul 2021
GANGA DHAM TOWERS | 1065 | 90793 | 06 Jul 2021 | 331 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 477 | A Ground Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 925 | Sq.Ft | 9 | 100 | 208.13 | 0 | 8325 | C+S GST 18% I/P RD | 1498.5 | 9823.5 | 9823.5 | Approved | 0 | 0 | 86 | 06 Jul 2021
GANGA DHAM TOWERS | 1067 | 90792 | 06 Jul 2021 | 332 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 476 | B P1 Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 352 | Sq.Ft | 9 | 100 | 79.2 | 0 | 3168 | C+S GST 18% I/P RD | 570.24 | 3738.24 | 3738.24 | Approved | 0 | 0 | 167 | 06 Jul 2021
GANGA DHAM TOWERS | 1067 | 90792 | 06 Jul 2021 | 332 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 476 | B Ground Floor Gypsum Plaster On Blockwork | Tikki Dhada (L) | 1503 | Sq.Ft | 9 | 100 | 338.18 | 0 | 13527 | C+S GST 18% I/P RD | 2434.86 | 15961.86 | 15961.86 | Approved | 0 | 0 | 167 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 134 | Sq.Ft | 1 | 100 | 0 | 0 | 134 | CGST 0% URD I/P | 0 | 134 | 134 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 137 | Sq.Ft | 1 | 100 | 0 | 0 | 137 | CGST 0% URD I/P | 0 | 137 | 137 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 134 | Sq.Ft | 1 | 100 | 0 | 0 | 134 | CGST 0% URD I/P | 0 | 134 | 134 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 137 | Sq.Ft | 1 | 100 | 0 | 0 | 137 | CGST 0% URD I/P | 0 | 137 | 137 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 137 | Sq.Ft | 1 | 100 | 0 | 0 | 137 | CGST 0% URD I/P | 0 | 137 | 137 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 166 | Sq.Ft | 1 | 100 | 0 | 0 | 166 | CGST 0% URD I/P | 0 | 166 | 166 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 134 | Sq.Ft | 1 | 100 | 0 | 0 | 134 | CGST 0% URD I/P | 0 | 134 | 134 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 221 | Sq.Ft | 1 | 100 | 0 | 0 | 221 | CGST 0% URD I/P | 0 | 221 | 221 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 31 | Sq.Ft | 1 | 100 | 0 | 0 | 31 | CGST 0% URD I/P | 0 | 31 | 31 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 166 | Sq.Ft | 1 | 100 | 0 | 0 | 166 | CGST 0% URD I/P | 0 | 166 | 166 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 137 | Sq.Ft | 1 | 100 | 0 | 0 | 137 | CGST 0% URD I/P | 0 | 137 | 137 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 36 | Sq.Ft | 1 | 100 | 0 | 0 | 36 | CGST 0% URD I/P | 0 | 36 | 36 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 134 | Sq.Ft | 1 | 100 | 0 | 0 | 134 | CGST 0% URD I/P | 0 | 134 | 134 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 297 | Sq.Ft | 1 | 100 | 0 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 372 | Sq.Ft | 1 | 100 | 0 | 0 | 372 | CGST 0% URD I/P | 0 | 372 | 372 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 25 | Sq.Ft | 1 | 100 | 0 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 169 | Sq.Ft | 1 | 100 | 0 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 64 | Sq.Ft | 1 | 100 | 0 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 32 | Sq.Ft | 1 | 100 | 0 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 22 | Sq.Ft | 1 | 100 | 0 | 0 | 22 | CGST 0% URD I/P | 0 | 22 | 22 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 16 | Sq.Ft | 1 | 100 | 0 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 28 | Sq.Ft | 1 | 100 | 0 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 828 | 90791 | 06 Jul 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 565 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 222 | Sq.Ft | 1 | 100 | 0 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 804 | 90790 | 06 Jul 2021 | 330 | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 475 | B 401 Internal Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 1746.29 | Sq.Ft | 50 | 100 | 0 | 0 | 87314.5 | C+S GST 18% I/P RD | 15716.62 | 103031.12 | 103031.12 | Approved | 0 | 0 | 0 | 06 Jul 2021
GANGA DHAM TOWERS | 1081 | 90776 | 05 Jul 2021 | 206 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 521 | D 12th Slab Pumping Charges for RMC | Pumping Charges-BC | 60 | Cu.Mtrs | 190 | 100 | 0 | 0 | 11400 | C+S GST 18% I/P RD | 2052 | 13452 | 13452 | Approved | 0 | 0 | 228 | 05 Jul 2021
GANGA DHAM TOWERS | 1080 | 90775 | 05 Jul 2021 | 205 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 524 | B 32nd Slab Pumping Charges for RMC | Pumping Charges-BC | 329.02 | Cu.Mtrs | 190 | 100 | 0 | 0 | 62513.8 | C+S GST 18% I/P RD | 11252.48 | 73766.28 | 73766.28 | Approved | 0 | 0 | 1250 | 05 Jul 2021
GANGA DHAM TOWERS | 1079 | 90774 | 05 Jul 2021 | 204 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 523 | A P2 Trimix Pumping Charges | Pumping Charges-BC | 224.01 | Cu.Mtrs | 190 | 100 | 0 | 0 | 42561.9 | C+S GST 18% I/P RD | 7661.14 | 50223.04 | 50223.04 | Approved | 0 | 0 | 851 | 05 Jul 2021
GANGA DHAM TOWERS | 178 | 90762 | 02 Jul 2021 | 619 | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 543 | Sales Oiifce Landscape Area . | Garden work. | 75.0018 | Day | 420.83 | 100 | 0 | 0 | 31563 | C+S GST 18% I/P RD | 5681.34 | 37244.34 | 37244.34 | Approved | 0 | 0 | 316 | 02 Jul 2021
GANGA DHAM TOWERS | 186 | 90760 | 02 Jul 2021 | 53 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 852 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 174.0025 | Day | 466.66 | 100 | 0 | 0 | 81200 | C+S GST 18% I/P RD | 14616 | 95816 | 95816 | Approved | 0 | 0 | 992 | 02 Jul 2021
GANGA DHAM TOWERS | 186 | 90760 | 02 Jul 2021 | 53 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 852 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 30 | Day | 600 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 992 | 02 Jul 2021
GANGA DHAM TOWERS | 698 | 90754 | 02 Jul 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 464 | D 703 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 673.9735 | Sq.Ft | 9 | 100 | 151.64 | 0 | 6065.76 | CGST 0% URD I/P | 0 | 6065.76 | 6065.76 | Approved | 0 | 0 | 223 | 02 Jul 2021
GANGA DHAM TOWERS | 698 | 90754 | 02 Jul 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 464 | D 702 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 832.337 | Sq.Ft | 9 | 100 | 187.28 | 0 | 7491.03 | CGST 0% URD I/P | 0 | 7491.03 | 7491.03 | Approved | 0 | 0 | 223 | 02 Jul 2021
GANGA DHAM TOWERS | 698 | 90754 | 02 Jul 2021 |  | A K INTERIOR CONTRACTOR | TASLIM NANHE KHAN | EV - 464 | D 701 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 973.3265 | Sq.Ft | 9 | 100 | 219 | 0 | 8759.94 | CGST 0% URD I/P | 0 | 8759.94 | 8759.94 | Approved | 0 | 0 | 223 | 02 Jul 2021
GANGA DHAM TOWERS | 187 | 90753 | 02 Jul 2021 | 56 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 562 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 02 Jul 2021
GANGA DHAM TOWERS | 413 | 90752 | 02 Jul 2021 | 620 | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 542 | Sales Oiifce Landscape Area . | Supervision Charges | 0.75 | Month | 4000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 300 | 02 Jul 2021
GANGA DHAM TOWERS | 179 | 90751 | 02 Jul 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) |  | Road Divider Garden Maintenance | Garden work. | 0.83 | Day | 420.83 | 100 | 0 | 0 | 349.29 | C+S GST 18% I/P RD | 62.88 | 412.17 | 412.17 |  | 0 | 0 | 3 | 02 Jul 2021
GANGA DHAM TOWERS | 480 | 90749 | 02 Jul 2021 | 54 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 561 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 30 | Day | 466.66 | 100 | 0 | 0 | 13999.8 | C+S GST 18% I/P RD | 2519.96 | 16519.76 | 16519.76 | Approved | 0 | 0 | 140 | 02 Jul 2021
GANGA DHAM TOWERS | 744 | 90748 | 02 Jul 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 466 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 0 | 02 Jul 2021
GANGA DHAM TOWERS | 772 | 90746 | 01 Jul 2021 | 212 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 720 | B 1901 NOC | Blockwork 4" - BC | 77 | Sq.Ft | 15 | 100 | 28.88 | 0 | 1155 | C+S GST 18% I/P RD | 207.9 | 1362.9 | 1362.9 | Approved | 0 | 0 | 51 | 01 Jul 2021
GANGA DHAM TOWERS | 772 | 90746 | 01 Jul 2021 | 212 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 720 | B 1901 NOC | Blockwork 4" - BC | 6.72 | Sq.Ft | 15 | 100 | 2.52 | 0 | 100.8 | C+S GST 18% I/P RD | 18.14 | 118.94 | 118.94 | Approved | 0 | 0 | 51 | 01 Jul 2021
GANGA DHAM TOWERS | 772 | 90746 | 01 Jul 2021 | 212 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 720 | B 1901 NOC | Blockwork 4" - BC | 6.72 | Sq.Ft | 15 | 100 | 2.52 | 0 | 100.8 | C+S GST 18% I/P RD | 18.14 | 118.94 | 118.94 | Approved | 0 | 0 | 51 | 01 Jul 2021
GANGA DHAM TOWERS | 772 | 90746 | 01 Jul 2021 | 212 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 720 | B 1901 NOC | Blockwork 4" - BC | 22.54 | Sq.Ft | 15 | 100 | 8.45 | 0 | 338.1 | C+S GST 18% I/P RD | 60.86 | 398.96 | 398.96 | Approved | 0 | 0 | 51 | 01 Jul 2021
GANGA DHAM TOWERS | 772 | 90746 | 01 Jul 2021 | 212 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 720 | B 1901 NOC | Blockwork 4" - BC | 63.9 | Sq.Ft | 15 | 100 | 23.96 | 0 | 958.5 | C+S GST 18% I/P RD | 172.54 | 1131.04 | 1131.04 | Approved | 0 | 0 | 51 | 01 Jul 2021
GANGA DHAM TOWERS | 772 | 90746 | 01 Jul 2021 | 212 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 720 | B 1901 NOC | Blockwork 4" - BC | 144.3 | Sq.Ft | 15 | 100 | 54.11 | 0 | 2164.5 | C+S GST 18% I/P RD | 389.62 | 2554.12 | 2554.12 | Approved | 0 | 0 | 51 | 01 Jul 2021
GANGA DHAM TOWERS | 772 | 90746 | 01 Jul 2021 | 212 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 720 | B 1901 NOC | Blockwork 4" - BC | 8.07 | Sq.Ft | 15 | 100 | 3.03 | 0 | 121.05 | C+S GST 18% I/P RD | 21.78 | 142.83 | 142.83 | Approved | 0 | 0 | 51 | 01 Jul 2021
GANGA DHAM TOWERS | 772 | 90746 | 01 Jul 2021 | 212 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 720 | B 1901 NOC | Blockwork 4" - BC | 10.09 | Sq.Ft | 15 | 100 | 3.78 | 0 | 151.35 | C+S GST 18% I/P RD | 27.24 | 178.59 | 178.59 | Approved | 0 | 0 | 51 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2201 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1402 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1501 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2001 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1201 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1901 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1401 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2101 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1302 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2401 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1801 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2102 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1301 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1702 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1202 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2002 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2402 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1701 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2501 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1502 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1601 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2302 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1101 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1802 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1902 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2202 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1602 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2301 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 2502 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 1004 | 90745 | 01 Jul 2021 | 211 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 721 | B 1102 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 150 | 01 Jul 2021
GANGA DHAM TOWERS | 778 | 90727 | 30 Jun 2021 | 208 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 724 | D Build. 10th Floor RCC Patli (L) | Patli (Band)- BC | 674.82 | R.Ft | 12 | 100 | 202.45 | 0 | 8097.84 | C+S GST 18% I/P RD | 1457.62 | 9555.46 | 9555.46 | Approved | 0 | 0 | 81 | 30 Jun 2021
GANGA DHAM TOWERS | 998 | 90696 | 25 Jun 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 731 | DA Dev. Top Terr,Servent room BBM,Plaster (L) | Department Labour- BC | 3 | No. | 600 | 100 | 0 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 48 | 25 Jun 2021
GANGA DHAM TOWERS | 998 | 90696 | 25 Jun 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 731 | DA Dev. Top Terr,Servent room BBM,Plaster (L) | Department Labour- BC | 3 | No. | 1000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 48 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 221 | Sq.Ft | 1 | 100 | 5.53 | 0 | 221 | CGST 0% URD I/P | 0 | 221 | 221 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1002 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 137 | Sq.Ft | 1 | 100 | 3.43 | 0 | 137 | CGST 0% URD I/P | 0 | 137 | 137 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 166 | Sq.Ft | 1 | 100 | 4.15 | 0 | 166 | CGST 0% URD I/P | 0 | 166 | 166 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 903 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1001 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 904 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 902 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1002 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 204 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1001 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 166 | Sq.Ft | 1 | 100 | 4.15 | 0 | 166 | CGST 0% URD I/P | 0 | 166 | 166 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 134 | Sq.Ft | 1 | 100 | 3.35 | 0 | 134 | CGST 0% URD I/P | 0 | 134 | 134 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 134 | Sq.Ft | 1 | 100 | 3.35 | 0 | 134 | CGST 0% URD I/P | 0 | 134 | 134 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1602 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 137 | Sq.Ft | 1 | 100 | 3.43 | 0 | 137 | CGST 0% URD I/P | 0 | 137 | 137 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 702 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 603 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1104 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1303 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 134 | Sq.Ft | 1 | 100 | 3.35 | 0 | 134 | CGST 0% URD I/P | 0 | 134 | 134 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1402 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1602 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 603 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 137 | Sq.Ft | 1 | 100 | 3.43 | 0 | 137 | CGST 0% URD I/P | 0 | 137 | 137 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1502 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 137 | Sq.Ft | 1 | 100 | 3.43 | 0 | 137 | CGST 0% URD I/P | 0 | 137 | 137 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 134 | Sq.Ft | 1 | 100 | 3.35 | 0 | 134 | CGST 0% URD I/P | 0 | 134 | 134 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 604 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 804 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1102 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 504 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1003 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1302 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1103 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 503 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 703 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1502 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1404 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1403 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 802 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 50 | Sq.Ft | 1 | 100 | 1.25 | 0 | 50 | CGST 0% URD I/P | 0 | 50 | 50 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 803 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 704 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1601 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1302 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 297 | Sq.Ft | 1 | 100 | 7.43 | 0 | 297 | CGST 0% URD I/P | 0 | 297 | 297 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1402 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 25 | Sq.Ft | 1 | 100 | 0.63 | 0 | 25 | CGST 0% URD I/P | 0 | 25 | 25 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 28 | Sq.Ft | 1 | 100 | 0.7 | 0 | 28 | CGST 0% URD I/P | 0 | 28 | 28 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1004 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 203 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 16 | Sq.Ft | 1 | 100 | 0.4 | 0 | 16 | CGST 0% URD I/P | 0 | 16 | 16 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 169 | Sq.Ft | 1 | 100 | 4.23 | 0 | 169 | CGST 0% URD I/P | 0 | 169 | 169 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1304 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 32 | Sq.Ft | 1 | 100 | 0.8 | 0 | 32 | CGST 0% URD I/P | 0 | 32 | 32 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1101 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 222 | Sq.Ft | 1 | 100 | 5.55 | 0 | 222 | CGST 0% URD I/P | 0 | 222 | 222 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1202 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 50 | Sq.Ft | 1 | 100 | 1.25 | 0 | 50 | CGST 0% URD I/P | 0 | 50 | 50 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 827 | 90695 | 25 Jun 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 566 | A 1601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 64 | Sq.Ft | 1 | 100 | 1.6 | 0 | 64 | CGST 0% URD I/P | 0 | 64 | 64 | Approved | 0 | 0 | 138 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 203 Gypsum Plaster | Gypsum on Wall (L) | 400 | Sq.Ft | 4 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 604 Gypsum Plaster | Gypsum on Wall (L) | 220 | Sq.Ft | 4 | 100 | 22 | 0 | 880 | C+S GST 18% I/P RD | 158.4 | 1038.4 | 1038.4 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 503 Gypsum Plaster | Gypsum on Wall (L) | 400 | Sq.Ft | 4 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 504 Gypsum Plaster | Gypsum on Wall (L) | 220 | Sq.Ft | 4 | 100 | 22 | 0 | 880 | C+S GST 18% I/P RD | 158.4 | 1038.4 | 1038.4 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 603 Gypsum Plaster | Gypsum on Wall (L) | 400 | Sq.Ft | 4 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 304 Gypsum Plaster | Gypsum on Wall (L) | 220 | Sq.Ft | 4 | 100 | 22 | 0 | 880 | C+S GST 18% I/P RD | 158.4 | 1038.4 | 1038.4 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 403 Gypsum Plaster | Gypsum on Wall (L) | 400 | Sq.Ft | 4 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 303 Gypsum Plaster | Gypsum on Wall (L) | 400 | Sq.Ft | 4 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 395 | 90694 | 25 Jun 2021 | 333 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 478 | A Bldg Flat No. 404 Gypsum Plaster | Gypsum on Wall (L) | 220 | Sq.Ft | 4 | 100 | 22 | 0 | 880 | C+S GST 18% I/P RD | 158.4 | 1038.4 | 1038.4 | Approved | 0 | 0 | 115 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 604 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 1402 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 55 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 403 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 404 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 603 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 602 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 1003 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 50 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 1204 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 50 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 903 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 50 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 704 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 50 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 641 | 90693 | 25 Jun 2021 | 90693 | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 627 | A 703 Toilet & Dry Balcony Devider Patti | Italian Marble Champher & Polish | 30 | R.Ft | 50 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 159 | 25 Jun 2021
GANGA DHAM TOWERS | 1012 | 90692 | 25 Jun 2021 |  | LALURAM B SHARMA | LALURAM B SHARMA | EV - 462 | A Temporary Door Maintanance Work | Door Repairing Work | 8 | No. | 200 | 100 | 0 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 16 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 502 5th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 904 9th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1501 15th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1502 15th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 302 3rd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1404 14th Floor AC Wooden beam . | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 301 3rd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 704 7th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1301 13th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 601 6th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 702 7th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1401 14th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1402 14th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1002 10th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1101 11th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 804 8th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 901 9th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1201 12th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1504 15th Floor AC Wooden beam . | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 201 2nd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 202 2nd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 104 1st Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 504 5th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 101 1st Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 604 6th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1204 12th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1102 11th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 701 7th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1004 10th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A Master Bedroom Wooden Box | Making Wooden Beam for AC fixing (L) | 6 | No. | 1000 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 204 2nd Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1302 13th Floor AC Wooden beam . | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1602 16th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1604 16th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1601 16th Floor AC Wooden beam . | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 304 3rd Floor AC Wooden beam- | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1001 10th Floor AC Wooden beam. | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1104 11th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 501 5th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 902 9th Floor AC Wooden beam . | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 1202 12th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 801 8th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 102 1st Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 401 4th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 602 6th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 779 | 90691 | 25 Jun 2021 |  | RAMDEVRA INTERIORS | LALURAM B SHARMA | EV - 463 | A 802 8th Floor AC Wooden beam | Making Wooden Beam for AC fixing (L) | 1 | No. | 1000 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 510 | 25 Jun 2021
GANGA DHAM TOWERS | 678 | 90680 | 24 Jun 2021 |  | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 429 | A 804 NOC | Blockwork 4" - BC | 16.3333 | Sq.Ft | 15 | 100 | 6.12 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 10 | 24 Jun 2021
GANGA DHAM TOWERS | 678 | 90680 | 24 Jun 2021 |  | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 429 | A 803 NOC | Blockwork 4" - BC | 50 | Sq.Ft | 15 | 100 | 0 | 0 | 750 | C+S GST 18% I/P RD | 135 | 885 | 885 | Approved | 0 | 0 | 10 | 24 Jun 2021
GANGA DHAM TOWERS | 389 | 90673 | 24 Jun 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 403 | Loading / Unloading Expenses | Unloading of AAC Blocks | 4548 | No. | 2 | 100 | 0 | 0 | 9096 | CGST 0% URD I/P | 0 | 9096 | 9096 | Approved | 0 | 0 | 0 | 24 Jun 2021
GANGA DHAM TOWERS | 389 | 90673 | 24 Jun 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 403 | Loading / Unloading Expenses | Unloading of tiles. | 3 | Metric Tonnes | 260 | 100 | 0 | 0 | 780 | CGST 0% URD I/P | 0 | 780 | 780 | Approved | 0 | 0 | 0 | 24 Jun 2021
GANGA DHAM TOWERS | 389 | 90673 | 24 Jun 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 403 | Loading / Unloading Expenses | Unloading of tiles. | 22.5 | Metric Tonnes | 100 | 100 | 0 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 0 | 24 Jun 2021
GANGA DHAM TOWERS | 772 | 90649 | 23 Jun 2021 | KVE/185 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 470 | B 301 NOC - | Blockwork 4" - BC | 43.33 | Sq.Ft | 15 | 100 | 16.25 | 0 | 649.95 | C+S GST 18% I/P RD | 117 | 766.95 | 766.95 | Approved | 0 | 0 | 29 | 23 Jun 2021
GANGA DHAM TOWERS | 772 | 90649 | 23 Jun 2021 | KVE/185 | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 470 | B 301 NOC - | Rough Plaster- cc | 152.2 | Sq.Ft | 15 | 100 | 57.08 | 0 | 2283 | C+S GST 18% I/P RD | 410.94 | 2693.94 | 2693.94 | Approved | 0 | 0 | 29 | 23 Jun 2021
GANGA DHAM TOWERS | 272 | 90648 | 23 Jun 2021 | KVE/182 | GOURI INFRA | KADAVATH VENKAT ENTERPRISES | EV - 468 | A Bldg 25th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 18.5759 | Sq.Ft | 161.5 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 30 | 23 Jun 2021
GANGA DHAM TOWERS | 1083 | 90647 | 23 Jun 2021 | 013 | GURUDATTA KRUPA ENTERPRISES | GURUDATTA KRUPA ENTERPRISES | EV - 502 | Development Area Safety board Framing work | Flex Framing. | 30 | No. | 100 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 37 | 23 Jun 2021
GANGA DHAM TOWERS | 1083 | 90647 | 23 Jun 2021 | 013 | GURUDATTA KRUPA ENTERPRISES | GURUDATTA KRUPA ENTERPRISES | EV - 502 | Development Area Safety board Framing work | Flex Framing | 72 | Sq.Ft | 10 | 100 | 0 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 37 | 23 Jun 2021
GANGA DHAM TOWERS | 1086 | 90646 | 23 Jun 2021 | KVE/183 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 467 | Tower A & B Podium Floor Cleaning work | Cleaning Work - Dld | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 23 Jun 2021
GANGA DHAM TOWERS | 1076 | 90645 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 507 | Steel Yard Baricading work - 1 No. | Repairing Work Mkt | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 209 | 23 Jun 2021
GANGA DHAM TOWERS | 1076 | 90645 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 507 | Steel Yard Baricading work - 1 No. | Fabrication work (L) | 116.99 | Kgs | 17.5 | 100 | 51.18 | 0 | 2047.33 | CGST 0% URD I/P | 0 | 2047.33 | 2047.33 | Approved | 0 | 0 | 209 | 23 Jun 2021
GANGA DHAM TOWERS | 1076 | 90645 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 507 | Steel Yard Baricading work - 1 No. | Fabrication work (L) | 50.4 | Kgs | 17.5 | 100 | 22.05 | 0 | 882 | CGST 0% URD I/P | 0 | 882 | 882 | Approved | 0 | 0 | 209 | 23 Jun 2021
GANGA DHAM TOWERS | 1076 | 90645 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 507 | Steel Yard Baricading work - 1 No. | Meta colour Sheet Fixing BC | 1499.75 | Sq.Ft | 6 | 100 | 224.96 | 0 | 8998.5 | CGST 0% URD I/P | 0 | 8998.5 | 8998.5 | Approved | 0 | 0 | 209 | 23 Jun 2021
GANGA DHAM TOWERS | 1076 | 90645 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 507 | Steel Yard Baricading work - 1 No. | Fabrication work (L) | 298.12 | Kgs | 21 | 100 | 156.51 | 0 | 6260.52 | CGST 0% URD I/P | 0 | 6260.52 | 6260.52 | Approved | 0 | 0 | 209 | 23 Jun 2021
GANGA DHAM TOWERS | 1076 | 90645 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 507 | Steel Yard Baricading work - 1 No. | Fabrication work (L) | 32.49 | Kgs | 21 | 100 | 17.06 | 0 | 682.29 | CGST 0% URD I/P | 0 | 682.29 | 682.29 | Approved | 0 | 0 | 209 | 23 Jun 2021
GANGA DHAM TOWERS | 862 | 90644 | 23 Jun 2021 | 39 | J K INTERIOR | J K INTERIOR | EV - 552 | Club house GF Brickwork/Plaster | Gypsum Plaster (L) | 2128.7325 | Sq.Ft | 9 | 100 | 478.96 | 0 | 19158.59 | C+S GST 18% I/P RD | 3448.54 | 22607.13 | 22607.13 | Approved | 0 | 0 | 284 | 23 Jun 2021
GANGA DHAM TOWERS | 862 | 90644 | 23 Jun 2021 | 39 | J K INTERIOR | J K INTERIOR | EV - 552 | Club House 1st Floor Brickwork/ Plaster | Gypsum Plaster (L) | 1022.425 | Sq.Ft | 9 | 100 | 230.05 | 0 | 9201.83 | C+S GST 18% I/P RD | 1656.32 | 10858.15 | 10858.15 | Approved | 0 | 0 | 284 | 23 Jun 2021
GANGA DHAM TOWERS | 1078 | 90643 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 505 | Club House Metacolour Sheet Fixing work (Staff+ Servant) - | Fabrication work (L) | 100.5 | Kgs | 21 | 100 | 52.76 | 0 | 2110.5 | CGST 0% URD I/P | 0 | 2110.5 | 2110.5 | Approved | 0 | 0 | 96 | 23 Jun 2021
GANGA DHAM TOWERS | 1078 | 90643 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 505 | Club House Metacolour Sheet Fixing work (Staff+ Servant) - | Fabrication work (L) | 163.4 | Kgs | 21 | 100 | 85.79 | 0 | 3431.4 | CGST 0% URD I/P | 0 | 3431.4 | 3431.4 | Approved | 0 | 0 | 96 | 23 Jun 2021
GANGA DHAM TOWERS | 1078 | 90643 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 505 | Club House Metacolour Sheet Fixing work (Staff+ Servant) - | Meta colour Sheet Fixing BC | 670 | Sq.Ft | 6 | 100 | 100.5 | 0 | 4020 | CGST 0% URD I/P | 0 | 4020 | 4020 | Approved | 0 | 0 | 96 | 23 Jun 2021
GANGA DHAM TOWERS | 1082 | 90642 | 23 Jun 2021 | 014 | GURUDATTA KRUPA ENTERPRISES | GURUDATTA KRUPA ENTERPRISES | EV - 503 | Sales Off&Sample Flats Ms Barricating Removing Work - 1 N | Metacolur Sheet Removing - DER | 1962 | Sq.Ft | 2.5 | 100 | 0 | 0 | 4905 | C+S GST 18% I/P RD | 882.9 | 5787.9 | 5787.9 | Approved | 0 | 0 | 97 | 23 Jun 2021
GANGA DHAM TOWERS | 1082 | 90642 | 23 Jun 2021 | 014 | GURUDATTA KRUPA ENTERPRISES | GURUDATTA KRUPA ENTERPRISES | EV - 503 | Sales Off&Sample Flats Ms Barricating Removing Work - 1 N | MS Column Removing | 183 | Kgs | 7 | 100 | 0 | 0 | 1281 | C+S GST 18% I/P RD | 230.58 | 1511.58 | 1511.58 | Approved | 0 | 0 | 97 | 23 Jun 2021
GANGA DHAM TOWERS | 1082 | 90642 | 23 Jun 2021 | 014 | GURUDATTA KRUPA ENTERPRISES | GURUDATTA KRUPA ENTERPRISES | EV - 503 | Sales Off&Sample Flats Ms Barricating Removing Work - 1 N | Angle Removing (L)-DER | 508 | Kgs | 7 | 100 | 0 | 0 | 3556 | C+S GST 18% I/P RD | 640.08 | 4196.08 | 4196.08 | Approved | 0 | 0 | 97 | 23 Jun 2021
GANGA DHAM TOWERS | 1087 | 90641 | 23 Jun 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 558 | Sales Off&Sample Flats Removing Of CP Sanitary Ware | Plumbing work lumpsum- | 1 | No. | 3500 | 100 | 0 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 35 | 23 Jun 2021
GANGA DHAM TOWERS | 1084 | 90640 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 504 | Temple Gate M.S Frame Fixing - 1 No. | MS Frame Making & Fixing | 720 | Sq.Ft | 8 | 100 | 144 | 0 | 5760 | CGST 0% URD I/P | 0 | 5760 | 5760 | Approved | 0 | 0 | 69 | 23 Jun 2021
GANGA DHAM TOWERS | 1084 | 90640 | 23 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 504 | Temple Gate M.S Frame Fixing - 1 No. | MS Frame Fixing | 190 | Sq.Ft | 6 | 100 | 28.5 | 0 | 1140 | CGST 0% URD I/P | 0 | 1140 | 1140 | Approved | 0 | 0 | 69 | 23 Jun 2021
GANGA DHAM TOWERS | 441 | 90639 | 23 Jun 2021 |  | SHIV SHAMBHO FABRICATION | SAURABH FABRICATION | EV - 508 | Tower-B Terrace Safety Railing 1st Floor to 26th Floor | Nails | 2.7 | Kgs | 90 | 100 | 0 | 0 | 243 | CGST 0% URD I/P | 0 | 243 | 243 | Approved | 0 | 0 | 206 | 23 Jun 2021
GANGA DHAM TOWERS | 441 | 90639 | 23 Jun 2021 |  | SHIV SHAMBHO FABRICATION | SAURABH FABRICATION | EV - 508 | Tower-B Terrace Safety Railing 1st Floor to 26th Floor | Hold Fast fixing- BCo | 672 | No. | 10 | 100 | 168 | 0 | 6720 | CGST 0% URD I/P | 0 | 6720 | 6720 | Approved | 0 | 0 | 206 | 23 Jun 2021
GANGA DHAM TOWERS | 441 | 90639 | 23 Jun 2021 |  | SHIV SHAMBHO FABRICATION | SAURABH FABRICATION | EV - 508 | Tower-B Terrace Safety Railing 1st Floor to 26th Floor | Fabrication Work (L) - BCo | 1240 | Kgs | 11 | 100 | 341 | 0 | 13640 | CGST 0% URD I/P | 0 | 13640 | 13640 | Approved | 0 | 0 | 206 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1701 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1501 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 101 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 301 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 801 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 401 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1401 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 901 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1801 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1301 Master Toilet BBM/Plaster | Rough Plaster | 38.75 | Sq.Ft | 15 | 100 | 14.53 | 0 | 581.25 | C+S GST 18% I/P RD | 104.62 | 685.87 | 685.87 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1401 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1501 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 401 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1801 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 301 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 101 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 901 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 801 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1701 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1006 | 90638 | 23 Jun 2021 | KVE/184 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 469 | B 1301 Master Toilet BBM/Plaster | Brickwork 4"- BC | 36.81 | Sq.Ft | 18 | 100 | 16.56 | 0 | 662.58 | C+S GST 18% I/P RD | 119.26 | 781.84 | 781.84 | Approved | 0 | 0 | 124 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 501 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 902 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 601 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 1001 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 801 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 102 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 401 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B802 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 602 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 301 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 302 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 701 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 702 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 101 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 402 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 502 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 1002 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 901 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 201 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1004 | 90637 | 23 Jun 2021 | KVE/186 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 579 | B 202 Ac Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 100 | 23 Jun 2021
GANGA DHAM TOWERS | 1060 | 90629 | 22 Jun 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD |  | Tower A Non Destructive Test - 1 No. | NDT by Rebound Hammer | 20 | No. | 105 | 100 | 0 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 |  | 0 | 0 | 293 | 22 Jun 2021
GANGA DHAM TOWERS | 1060 | 90629 | 22 Jun 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD |  | Tower B Non Destructive Test - 1 No. | NDT by Rebound Hammer | 20 | No. | 105 | 100 | 0 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 |  | 0 | 0 | 293 | 22 Jun 2021
GANGA DHAM TOWERS | 1060 | 90629 | 22 Jun 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD |  | Tower B Non Destructive Test - 1 No. | Travelling charges- SO | 0.65 | No. | 1600 | 100 | 0 | 0 | 1040 | C+S GST 18% I/P RD | 187.2 | 1227.2 | 1227.2 |  | 0 | 0 | 293 | 22 Jun 2021
GANGA DHAM TOWERS | 1060 | 90629 | 22 Jun 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD |  | Tower A Non Destructive Test - 1 No. | Travelling charges- SO | 0.625 | No. | 1600 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 |  | 0 | 0 | 293 | 22 Jun 2021
GANGA DHAM TOWERS | 1060 | 90629 | 22 Jun 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD |  | Tower B Non Destructive Test - 1 No. | NDT by Ultrasonic Plus Velocity | 20 | No. | 210 | 100 | 0 | 0 | 4200 | C+S GST 18% I/P RD | 756 | 4956 | 4956 |  | 0 | 0 | 293 | 22 Jun 2021
GANGA DHAM TOWERS | 1060 | 90629 | 22 Jun 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD |  | Tower A Non Destructive Test - 1 No. | NDT by Ultrasonic Plus Velocity | 20 | No. | 210 | 100 | 0 | 0 | 4200 | C+S GST 18% I/P RD | 756 | 4956 | 4956 |  | 0 | 0 | 293 | 22 Jun 2021
GANGA DHAM TOWERS | 540 | 90628 | 22 Jun 2021 |  | MONIKA ENTERPRISES | KADAVATH VENKAT ENTERPRISES |  | A 804 NOC | Blockwork 4" - BC | 14 | Sq.Ft | 14 | 100 | 4.9 | 0 | 196 | C+S GST 18% I/P RD | 35.28 | 231.28 | 231.28 |  | 0 | 0 | 26 | 22 Jun 2021
GANGA DHAM TOWERS | 540 | 90628 | 22 Jun 2021 |  | MONIKA ENTERPRISES | KADAVATH VENKAT ENTERPRISES |  | A 1504 NOC | Blockwork 4" - BC | 35 | Sq.Ft | 14 | 100 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 |  | 0 | 0 | 26 | 22 Jun 2021
GANGA DHAM TOWERS | 540 | 90628 | 22 Jun 2021 |  | MONIKA ENTERPRISES | KADAVATH VENKAT ENTERPRISES |  | A 1001 NOC | Blockwork 4" - BC | 46.59 | Sq.Ft | 14 | 100 | 16.31 | 0 | 652.26 | C+S GST 18% I/P RD | 117.4 | 769.66 | 769.66 |  | 0 | 0 | 26 | 22 Jun 2021
GANGA DHAM TOWERS | 540 | 90628 | 22 Jun 2021 |  | MONIKA ENTERPRISES | KADAVATH VENKAT ENTERPRISES |  | A 303 NOC | Blockwork 4" - BC | 93 | Sq.Ft | 14 | 100 | 32.55 | 0 | 1302 | C+S GST 18% I/P RD | 234.36 | 1536.36 | 1536.36 |  | 0 | 0 | 26 | 22 Jun 2021
GANGA DHAM TOWERS | 1031 | 90619 | 21 Jun 2021 | 175/21-22 | A N INTERIORS | A N INTERIORS | EV - 1101 | DA Development Carpentary work | Carpentary work- lumpsum- DER | 0.54 | No. | 60000 | 100 | 0 | 0 | 32400 | C+S GST 18% I/P RD | 5832 | 38232 | 38232 | Approved | 0 | 0 | 324 | 21 Jun 2021
GANGA DHAM TOWERS | 540 | 90618 | 21 Jun 2021 | 90618 | MONIKA ENTERPRISES | R K INTERIOR | EV - 550 | A 303 NOC | Italian Marble Flooring - BCo | 91 | Sq.Ft | 86.1 | 100 | 195.88 | 0 | 7835.1 | C+S GST 18% I/P RD | 1410.32 | 9245.42 | 9245.42 | Approved | 0 | 0 | 157 | 21 Jun 2021
GANGA DHAM TOWERS | 149 | 90617 | 21 Jun 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 406 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3921 | No. | 4 | 100 | 0 | 0 | 15684 | CGST 0% URD I/P | 0 | 15684 | 15684 | Approved | 0 | 0 | 0 | 21 Jun 2021
GANGA DHAM TOWERS | 540 | 90616 | 21 Jun 2021 | 90616 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 626 | A 1702 NOC | Italian Marble Flooring- cc | 178.49 | Sq.Ft | 55 | 100 | 245.42 | 0 | 9816.95 | C+S GST 18% I/P RD | 1767.06 | 11584.01 | 11584.01 | Approved | 0 | 0 | 371 | 21 Jun 2021
GANGA DHAM TOWERS | 540 | 90616 | 21 Jun 2021 | 90616 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 626 | A 804 NOC | Italian Marble Flooring - BCo | 171 | Sq.Ft | 55 | 100 | 235.13 | 0 | 9405 | C+S GST 18% I/P RD | 1692.9 | 11097.9 | 11097.9 | Approved | 0 | 0 | 371 | 21 Jun 2021
GANGA DHAM TOWERS | 540 | 90616 | 21 Jun 2021 | 90616 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 626 | A 1701 NOC | Italian Marble Flooring - BCo | 160.89 | Sq.Ft | 55 | 100 | 221.22 | 0 | 8848.95 | C+S GST 18% I/P RD | 1592.82 | 10441.77 | 10441.77 | Approved | 0 | 0 | 371 | 21 Jun 2021
GANGA DHAM TOWERS | 540 | 90616 | 21 Jun 2021 | 90616 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 626 | A 1403 NOC | Italian Marble Flooring - BCo | 164 | Sq.Ft | 55 | 100 | 225.5 | 0 | 9020 | C+S GST 18% I/P RD | 1623.6 | 10643.6 | 10643.6 | Approved | 0 | 0 | 371 | 21 Jun 2021
GANGA DHAM TOWERS | 540 | 90615 | 21 Jun 2021 | 059 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 726 | A 502 NOC | Italian Marble Flooring - BCo | 181.5 | Sq.Ft | 55 | 100 | 249.56 | 0 | 9982.5 | C+S GST 18% I/P RD | 1796.86 | 11779.36 | 11779.36 | Approved | 0 | 0 | 236 | 21 Jun 2021
GANGA DHAM TOWERS | 540 | 90615 | 21 Jun 2021 | 059 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 726 | A 502 NOC | Tile Removing work - BRE | 181.5 | Sq.Ft | 10 | 100 | 45.38 | 0 | 1815 | C+S GST 18% I/P RD | 326.7 | 2141.7 | 2141.7 | Approved | 0 | 0 | 236 | 21 Jun 2021
GANGA DHAM TOWERS | 551 | 90614 | 21 Jun 2021 | 90614 | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 623 | A 504 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 126 | Sq.Ft | 45 | 100 | 141.75 | 0 | 5670 | C+S GST 18% I/P RD | 1020.6 | 6690.6 | 6690.6 | Approved | 0 | 0 | 57 | 21 Jun 2021
GANGA DHAM TOWERS | 537 | 90613 | 21 Jun 2021 | 90613 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 625 | A 1701 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 228.2 | Sq.Ft | 55 | 100 | 313.78 | 0 | 12551 | C+S GST 18% I/P RD | 2259.18 | 14810.18 | 14810.18 | Approved | 0 | 0 | 126 | 21 Jun 2021
GANGA DHAM TOWERS | 537 | 90612 | 21 Jun 2021 | 058 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 725 | A 1701 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.7 | Sq.Ft | 55 | 100 | 787.46 | 0 | 31498.5 | C+S GST 18% I/P RD | 5669.74 | 37168.24 | 37168.24 | Approved | 0 | 0 | 1001 | 21 Jun 2021
GANGA DHAM TOWERS | 537 | 90612 | 21 Jun 2021 | 058 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 725 | A 1701 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.97 | Sq.Ft | 55 | 100 | 290.08 | 0 | 11603.35 | C+S GST 18% I/P RD | 2088.6 | 13691.95 | 13691.95 | Approved | 0 | 0 | 1001 | 21 Jun 2021
GANGA DHAM TOWERS | 537 | 90612 | 21 Jun 2021 | 058 | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 725 | A 1701 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 126 | Sq.Ft | 55 | 100 | 173.25 | 0 | 6930 | C+S GST 18% I/P RD | 1247.4 | 8177.4 | 8177.4 | Approved | 0 | 0 | 1001 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 1504 AC Drain Plumbing Groove | Groove Filling | 0.336 | No. | 500 | 100 | 4.2 | 0 | 168 | C+S GST 18% I/P RD | 30.24 | 198.24 | 198.24 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 903 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 1303 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 1703 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 1103 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 203 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 1403 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 403 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 1203 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 503 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 703 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 103 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 1003 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 303 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 603 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 1005 | 90611 | 21 Jun 2021 | KVE/181 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 578 | A 1603 AC Drain Plumbing Groove | Groove Filling | 0.668 | No. | 500 | 100 | 8.35 | 0 | 334 | C+S GST 18% I/P RD | 60.12 | 394.12 | 394.12 | Approved | 0 | 0 | 53 | 21 Jun 2021
GANGA DHAM TOWERS | 837 | 90606 | 19 Jun 2021 |  | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1582 | DA Development Electrical work | Secondary Light Points (Looping) | 5 | No. | 450 | 100 | 56.25 | 0 | 2250 | CGST 0% URD I/P | 0 | 2250 | 2250 | Approved | 0 | 0 | 541 | 19 Jun 2021
GANGA DHAM TOWERS | 837 | 90606 | 19 Jun 2021 |  | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1582 | DA Development Electrical work | 16 AMP Full Point BC | 2 | No. | 4150 | 100 | 207.5 | 0 | 8300 | CGST 0% URD I/P | 0 | 8300 | 8300 | Approved | 0 | 0 | 541 | 19 Jun 2021
GANGA DHAM TOWERS | 837 | 90606 | 19 Jun 2021 |  | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1582 | DA Development Electrical work | 6 AMP Plug point (Independent) | 12 | No. | 1375 | 100 | 412.5 | 0 | 16500 | CGST 0% URD I/P | 0 | 16500 | 16500 | Approved | 0 | 0 | 541 | 19 Jun 2021
GANGA DHAM TOWERS | 837 | 90606 | 19 Jun 2021 |  | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1582 | DA Development Electrical work | MCB Fixing with DB | 20 | No. | 600 | 100 | 300 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 541 | 19 Jun 2021
GANGA DHAM TOWERS | 837 | 90606 | 19 Jun 2021 |  | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1582 | DA Development Electrical work | Primary Light Points (Controlled by MCB) | 10 | No. | 850 | 100 | 212.5 | 0 | 8500 | CGST 0% URD I/P | 0 | 8500 | 8500 | Approved | 0 | 0 | 541 | 19 Jun 2021
GANGA DHAM TOWERS | 837 | 90606 | 19 Jun 2021 |  | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1582 | DA Development Electrical work | Light Fitting Fixing | 30 | No. | 100 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 541 | 19 Jun 2021
GANGA DHAM TOWERS | 837 | 90606 | 19 Jun 2021 |  | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1582 | DA Development Electrical work | 4 Pole 63 Amp MCB & RCCB | 1 | No. | 3500 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 541 | 19 Jun 2021
GANGA DHAM TOWERS | 957 | 90601 | 18 Jun 2021 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS |  | Electricity Infrastructure-Trnsformer,HT,LT Work | RMU Touch proof joint 300 sqmm - No. | 2 | No. | 2500 | 100 | 125 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 |  | 0 | 0 | 50 | 18 Jun 2021
GANGA DHAM TOWERS | 698 | 90600 | 18 Jun 2021 | 328 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 486 | D 202 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 50 | Sq.Ft | 9 | 100 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 38 | 18 Jun 2021
GANGA DHAM TOWERS | 698 | 90600 | 18 Jun 2021 | 328 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 486 | D 201 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 57 | Sq.Ft | 9 | 100 | 12.83 | 0 | 513 | C+S GST 18% I/P RD | 92.34 | 605.34 | 605.34 | Approved | 0 | 0 | 38 | 18 Jun 2021
GANGA DHAM TOWERS | 698 | 90600 | 18 Jun 2021 | 328 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 486 | D 101 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 170 | Sq.Ft | 9 | 100 | 38.25 | 0 | 1530 | C+S GST 18% I/P RD | 275.4 | 1805.4 | 1805.4 | Approved | 0 | 0 | 38 | 18 Jun 2021
GANGA DHAM TOWERS | 698 | 90600 | 18 Jun 2021 | 328 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 486 | D 102 Ceiling & Wall Gypsum Plaster | Tikki Dhada (L) | 140 | Sq.Ft | 9 | 100 | 31.5 | 0 | 1260 | C+S GST 18% I/P RD | 226.8 | 1486.8 | 1486.8 | Approved | 0 | 0 | 38 | 18 Jun 2021
GANGA DHAM TOWERS | 957 | 90594 | 17 Jun 2021 | 90594 | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 483 | Electricity Infrastructure-Trnsformer,HT,LT Work | Straight Thr. Joint 300sqmm 3C-UTI | 2 | No. | 3000 | 100 | 150 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 17 Jun 2021
GANGA DHAM TOWERS | 1094 | 90586 | 16 Jun 2021 |  | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 658 | Idle Pump Charges ( A ,B Up to 26th Floor) | Pumping Charges-BC | 1059 | Cu.Mtrs | 190 | 100 | 0 | 0 | 201210 | C+S GST 18% I/P RD | 36217.8 | 237427.8 | 237427.8 | Approved | 0 | 0 | 4024 | 16 Jun 2021
GANGA DHAM TOWERS | 1080 | 90585 | 16 Jun 2021 | 202 | LOTUS ENTERPRISES | LOTUS ENTERPRISES | EV - 522 | B P2 Floor Trimix Pumping Charges | Pumping Charges-BC | 141 | Cu.Mtrs | 190 | 100 | 0 | 0 | 26790 | C+S GST 18% I/P RD | 4822.2 | 31612.2 | 31612.2 | Approved | 0 | 0 | 536 | 16 Jun 2021
GANGA DHAM TOWERS | 1072 | 90583 | 16 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 415 | Club House M.S Frame Fixing | MS Frame Making & Fixing | 4020 | Sq.Ft | 8 | 100 | 804 | 0 | 32160 | CGST 0% URD I/P | 0 | 32160 | 32160 | Approved | 0 | 0 | 322 | 16 Jun 2021
GANGA DHAM TOWERS | 758 | 90582 | 16 Jun 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | KADAVATH VENKAT ENTERPRISES | EV - 407 | B 1002 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 40 | Sq.Ft | 50 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 16 Jun 2021
GANGA DHAM TOWERS | 272 | 90581 | 16 Jun 2021 |  | GOURI INFRA | KADAVATH VENKAT ENTERPRISES | EV - 409 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 12.3839 | Sq.Ft | 161.5 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 16 Jun 2021
GANGA DHAM TOWERS | 372 | 90580 | 16 Jun 2021 |  | B & B ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 417 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 33.3333 | Sq.Ft | 150 | 100 | 0 | 0 | 5000 | IGST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 50 | 16 Jun 2021
GANGA DHAM TOWERS | 927 | 90579 | 16 Jun 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 418 | A 11th Floor Back Coat Plaster | Back Coat Plaster | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 16 Jun 2021
GANGA DHAM TOWERS | 905 | 90578 | 16 Jun 2021 |  | R.M.Marbles | KADAVATH VENKAT ENTERPRISES | EV - 420 | A 3rd Floor Staircase Flooring | Kota Flooring (L)- BCO | 40 | Sq.Ft | 50 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 16 Jun 2021
GANGA DHAM TOWERS | 537 | 90577 | 16 Jun 2021 |  | MONIKA ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 408 | A 1302 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 36.3636 | Sq.Ft | 55 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 16 Jun 2021
GANGA DHAM TOWERS | 551 | 90576 | 16 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | KADAVATH VENKAT ENTERPRISES | EV - 411 | A 1003 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 40 | Sq.Ft | 50 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 16 Jun 2021
GANGA DHAM TOWERS | 1073 | 90575 | 16 Jun 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 416 | D Removal of Shade | Metacolur Sheet Removing - DER | 1218 | Sq.Ft | 2.5 | 100 | 0 | 0 | 3045 | CGST 0% URD I/P | 0 | 3045 | 3045 | Approved | 0 | 0 | 30 | 16 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 201 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1003 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 801 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1602 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1303 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 603 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 303 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 701 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1302 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1702 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 903 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 401 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 704 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 804 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1304 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1704 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 504 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1601 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 202 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 403 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1201 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1404 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 802 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1202 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 902 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 904 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 901 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1102 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1104 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1502 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 301 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 404 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 502 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 703 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 602 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1504 AC Drain Plumbing Groove | Groove Filling | 0.664 | No. | 500 | 100 | 8.3 | 0 | 332 | C+S GST 18% I/P RD | 59.76 | 391.76 | 391.76 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 104 AC Drain Plumbing Groove | Groove Filling | 0.664 | No. | 500 | 100 | 8.3 | 0 | 332 | C+S GST 18% I/P RD | 59.76 | 391.76 | 391.76 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 203 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 601 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 304 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 402 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 702 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1703 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1004 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1402 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1401 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1001 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1002 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1501 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 101 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 503 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 204 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 302 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1603 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1203 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1204 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1701 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1604 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1103 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1403 AC Drain Plumbing Groove | Groove Filling | 0.332 | No. | 500 | 100 | 4.15 | 0 | 166 | C+S GST 18% I/P RD | 29.88 | 195.88 | 195.88 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 501 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1301 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 102 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 1005 | 90530 | 14 Jun 2021 | KVE/176 | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 577 | A 1101 AC Drain Plumbing Groove | Groove Filling | 1 | No. | 500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 270 | 14 Jun 2021
GANGA DHAM TOWERS | 778 | 90529 | 14 Jun 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 419 | D Build. 9th Floor RCC Patli (L) | Patli (Band)- BC | 674.82 | R.Ft | 12 | 100 | 202.45 | 0 | 8097.84 | C+S GST 18% I/P RD | 1457.62 | 9555.46 | 9555.46 | Approved | 0 | 0 | 81 | 14 Jun 2021
GANGA DHAM TOWERS | 1070 | 90493 | 10 Jun 2021 |  | FACADE INDIA TESTING INC | FACADE INDIA TESTING INC | EV - 356 | Lab Performance Test for strip window system | Lab Test for Strip Window System. | 1 | No. | 900000 | 40 | 0 | 0 | 360000 | C+S GST 18% I/P RD | 64800 | 424800 | 424800 | Approved | 0 | 0 | 7200 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 104 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 93.008 | R.Ft | 45 | 100 | 104.63 | 0 | 4185.36 | C+S GST 18% I/P RD | 753.36 | 4938.72 | 4938.72 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 104 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 34.384 | R.Ft | 45 | 100 | 38.68 | 0 | 1547.28 | C+S GST 18% I/P RD | 278.52 | 1825.8 | 1825.8 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 204 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 650 | 100 | 45.34 | 0 | 1813.5 | C+S GST 18% I/P RD | 326.44 | 2139.94 | 2139.94 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 603 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.76 | R.Ft | 650 | 100 | 44.85 | 0 | 1794 | C+S GST 18% I/P RD | 322.92 | 2116.92 | 2116.92 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 404 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 650 | 100 | 45.34 | 0 | 1813.5 | C+S GST 18% I/P RD | 326.44 | 2139.94 | 2139.94 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 604 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 650 | 100 | 45.34 | 0 | 1813.5 | C+S GST 18% I/P RD | 326.44 | 2139.94 | 2139.94 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 604 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 650 | 100 | 23.97 | 0 | 958.75 | C+S GST 18% I/P RD | 172.58 | 1131.33 | 1131.33 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 603 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.705 | R.Ft | 650 | 100 | 43.96 | 0 | 1758.25 | C+S GST 18% I/P RD | 316.48 | 2074.73 | 2074.73 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 404 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 650 | 100 | 23.97 | 0 | 958.75 | C+S GST 18% I/P RD | 172.58 | 1131.33 | 1131.33 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 204 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 650 | 100 | 23.97 | 0 | 958.75 | C+S GST 18% I/P RD | 172.58 | 1131.33 | 1131.33 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 1704 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 25 | Sq.Ft | 21 | 100 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 403 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.76 | R.Ft | 650 | 100 | 44.85 | 0 | 1794 | C+S GST 18% I/P RD | 322.92 | 2116.92 | 2116.92 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 403 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.705 | R.Ft | 650 | 100 | 43.96 | 0 | 1758.25 | C+S GST 18% I/P RD | 316.48 | 2074.73 | 2074.73 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 704 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 700 | 100 | 48.83 | 0 | 1953 | C+S GST 18% I/P RD | 351.54 | 2304.54 | 2304.54 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 703 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.76 | R.Ft | 700 | 100 | 48.3 | 0 | 1932 | C+S GST 18% I/P RD | 347.76 | 2279.76 | 2279.76 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 704 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 700 | 100 | 25.81 | 0 | 1032.5 | C+S GST 18% I/P RD | 185.86 | 1218.36 | 1218.36 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 703 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.705 | R.Ft | 700 | 100 | 47.34 | 0 | 1893.5 | C+S GST 18% I/P RD | 340.84 | 2234.34 | 2234.34 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 1204 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 700 | 100 | 48.83 | 0 | 1953 | C+S GST 18% I/P RD | 351.54 | 2304.54 | 2304.54 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 551 | 90492 | 10 Jun 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 355 | A 1204 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 700 | 100 | 25.81 | 0 | 1032.5 | C+S GST 18% I/P RD | 185.86 | 1218.36 | 1218.36 | Approved | 0 | 864 | 315 | 10 Jun 2021
GANGA DHAM TOWERS | 933 | 90491 | 10 Jun 2021 |  | REVANTI FURNITURE | REVANTI FURNITURE | EV - 1221 | Club House Furniture Work | Carpentary work (L)-BC | 1 | No. | 38721 | 100 | 0 | 0 | 38721 | CGST 0% URD I/P | 0 | 38721 | 38721 | Approved | 0 | 0 | 387 | 10 Jun 2021
GANGA DHAM TOWERS | 209 | 90490 | 10 Jun 2021 |  | UNIQUE ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 410 | A Bldg 1st RCC Slab (Stilt Floor) Built-up Area (L) | Hacking Work | 1000 | Sq.Ft | 5 | 100 | 125 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 50 | 10 Jun 2021
GANGA DHAM TOWERS | 715 | 90474 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR |  | A P2 Parking Floor Staircase II Ceiling Gypsum Plaster | Gypsum on Ceiling (L) | 259.84 | Sq.Ft | 4 | 100 | 25.98 | 0 | 1039.36 | C+S GST 18% I/P RD | 187.08 | 1226.44 | 1226.44 |  | 0 | 0 | 10 | 08 Jun 2021
GANGA DHAM TOWERS | 652 | 90473 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 405 | A P3 Podium Beam & Ceiling Plaster | Gypsum Plaster (L) | 366 | Sq.Ft | 4 | 100 | 36.6 | 0 | 1464 | C+S GST 18% I/P RD | 263.52 | 1727.52 | 1727.52 | Approved | 0 | 0 | 15 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P2 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 700 | Sq.Ft | 4 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P3 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 700 | Sq.Ft | 4 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A Ground Floor Staircase & Lobby Plaster | Gypsum Plaster (L) | 700 | Sq.Ft | 4 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P1 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 700 | Sq.Ft | 4 | 100 | 70 | 0 | 2800 | C+S GST 18% I/P RD | 504 | 3304 | 3304 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P2 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 700 | Sq.Ft | 5 | 100 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A Ground Floor Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 700 | Sq.Ft | 5 | 100 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A Ground Floor Beam & Ceiling Plaster | Tikki Dhada rate diff. (L) | 366 | Sq.Ft | 5 | 100 | 45.75 | 0 | 1830 | C+S GST 18% I/P RD | 329.4 | 2159.4 | 2159.4 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P1 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 700 | Sq.Ft | 5 | 100 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P3 Parking Beam & Ceiling Plaster | Tikki Dhada rate diff. (L) | 366 | Sq.Ft | 5 | 100 | 45.75 | 0 | 1830 | C+S GST 18% I/P RD | 329.4 | 2159.4 | 2159.4 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P1 Parking Beam & Ceiling Plaster | Gypsum Plaster (L) | 366 | Sq.Ft | 4 | 100 | 36.6 | 0 | 1464 | C+S GST 18% I/P RD | 263.52 | 1727.52 | 1727.52 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P3 Parking Beam & Ceiling Plaster | Gypsum on Ceiling (L) | 366 | Sq.Ft | 4 | 100 | 36.6 | 0 | 1464 | C+S GST 18% I/P RD | 263.52 | 1727.52 | 1727.52 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P2 Parking Beam & Ceiling Plaster | Tikki Dhada rate diff. (L) | 366 | Sq.Ft | 5 | 100 | 45.75 | 0 | 1830 | C+S GST 18% I/P RD | 329.4 | 2159.4 | 2159.4 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P3 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 700 | Sq.Ft | 5 | 100 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 649 | 90472 | 08 Jun 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 404 | A P1 Parking Beam & Ceiling Plaster | Tikki Dhada rate diff. (L) | 366 | Sq.Ft | 5 | 100 | 45.75 | 0 | 1830 | C+S GST 18% I/P RD | 329.4 | 2159.4 | 2159.4 | Approved | 0 | 0 | 354 | 08 Jun 2021
GANGA DHAM TOWERS | 145 | 90471 | 08 Jun 2021 | 83 | PEST-O-CRUSH | S.R.Enterprises | EV - 484 | Fogging Work | Fogging work-SO | 0.5 | Month | 6000 | 100 | 0 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 30 | 08 Jun 2021
GANGA DHAM TOWERS | 933 | 90470 | 08 Jun 2021 |  | REVANTI FURNITURE | REVANTI FURNITURE | EV - 396 | Club House Furniture Work | Carpentary work (L)-BC | 0.2 | No. | 500000 | 100 | 0 | 0 | 100000 | CGST 0% URD I/P | 0 | 100000 | 100000 | Approved | 0 | 0 | 1000 | 08 Jun 2021
GANGA DHAM TOWERS | 384 | 90457 | 05 Jun 2021 |  | PATIL CONSTRUCTION | B.D. DONGARE | EV - 397 | A Bldg Fire Fight,AC & Drain lines Core Cutting | Core Cutting Work 4" BCE | 55 | No. | 300 | 100 | 412.5 | 0 | 16500 | C+S GST 18% I/P RD | 2970 | 19470 | 19470 | Approved | 0 | 0 | 165 | 05 Jun 2021
GANGA DHAM TOWERS | 1037 | 90441 | 03 Jun 2021 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 314 | Head Office Security Service | Security Guard AIE - | 62 | Day | 419.35 | 100 | 0 | 0 | 25999.7 | C+S GST 18% I/P RD | 4679.94 | 30679.64 | 30679.64 | Approved | 0 | 0 | 260 | 03 Jun 2021
GANGA DHAM TOWERS | 187 | 90424 | 02 Jun 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 433 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 02 Jun 2021
GANGA DHAM TOWERS | 940 | 90423 | 02 Jun 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 394 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 02 Jun 2021
GANGA DHAM TOWERS | 413 | 90422 | 02 Jun 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 422 | Sales Oiifce Landscape Area . | Supervision Charges | 1 | Month | 4000 | 100 | 0 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 40 | 02 Jun 2021
GANGA DHAM TOWERS | 178 | 90421 | 02 Jun 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 421 | Sales Oiifce Landscape Area . | Garden work. | 87.9873 | Day | 407.25 | 100 | 0 | 0 | 35832.83 | C+S GST 18% I/P RD | 6449.9 | 42282.73 | 42282.73 | Approved | 0 | 0 | 358 | 02 Jun 2021
GANGA DHAM TOWERS | 745 | 90420 | 02 Jun 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 423 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 29.4965 | Day | 451.61 | 100 | 0 | 0 | 13320.91 | C+S GST 18% I/P RD | 2397.76 | 15718.67 | 15718.67 | Approved | 0 | 0 | 133 | 02 Jun 2021
GANGA DHAM TOWERS | 480 | 90419 | 02 Jun 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 395 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 16.4982 | Day | 451.61 | 100 | 0 | 0 | 7450.75 | C+S GST 18% I/P RD | 1341.14 | 8791.89 | 8791.89 | Approved | 0 | 0 | 75 | 02 Jun 2021
GANGA DHAM TOWERS | 186 | 90418 | 02 Jun 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 424 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 153.4128 | Day | 451.613 | 100 | 0 | 0 | 69283.21 | C+S GST 18% I/P RD | 12470.98 | 81754.19 | 81754.19 | Approved | 0 | 0 | 873 | 02 Jun 2021
GANGA DHAM TOWERS | 186 | 90418 | 02 Jun 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 424 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 31 | Day | 580.645 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 873 | 02 Jun 2021
GANGA DHAM TOWERS | 1058 | 90372 | 29 May 2021 |  | HELIOS (Material) | HELIOS (Material) | EV - 359 | Club House Glass/ SS Railing Work | Glass Railing (M) | 14.25 | R.Ft | 1350 | 100 | 0 | 0 | 19237.5 | C+S GST 18% I/P RD | 3462.76 | 22700.26 | 22700.26 | Approved | 0 | 0 | 0 | 29 May 2021
GANGA DHAM TOWERS | 1058 | 90372 | 29 May 2021 |  | HELIOS (Material) | HELIOS (Material) | EV - 359 | Club House Glass/ SS Railing Work | SS Railing (M) | 71.16 | R.Ft | 325 | 100 | 0 | 0 | 23127 | C+S GST 18% I/P RD | 4162.86 | 27289.86 | 27289.86 | Approved | 0 | 0 | 0 | 29 May 2021
GANGA DHAM TOWERS | 787 | 90371 | 29 May 2021 | 131 | SHARVANKUMAR MANGILAL KUMAWAT | A K ENTERPRISES | EV - 474 | A Bldg 304 (Sample flat children bedroom) Wooden Flooring | Wooden Flooring(L)- BC | 142.944 | Sq.Ft | 10 | 100 | 35.74 | 0 | 1429.44 | CGST 0% URD I/P | 0 | 1429.44 | 1429.44 | Approved | 0 | 0 | 14 | 29 May 2021
GANGA DHAM TOWERS | 629 | 90370 | 29 May 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 337 | A 304 Dry Bal,Staff,Toilet False Ceiling Work | Moisture Proof Ceiling (M) | 247.848 | Sq.Ft | 70 | 100 | 0 | 0 | 17349.36 | C+S GST 18% I/P RD | 3122.88 | 20472.24 | 20472.24 | Approved | 0 | 0 | 0 | 29 May 2021
GANGA DHAM TOWERS | 629 | 90370 | 29 May 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 337 | A 604 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 714.7 | Sq.Ft | 50 | 100 | 0 | 0 | 35735 | C+S GST 18% I/P RD | 6432.3 | 42167.3 | 42167.3 | Approved | 0 | 0 | 0 | 29 May 2021
GANGA DHAM TOWERS | 632 | 90369 | 29 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 338 | A 304 Dry Bal,Staff,Toilet False Ceiling Work | Moisture Proof Ceiling (L) | 247.848 | Sq.Ft | 15 | 100 | 92.94 | 0 | 3717.72 | C+S GST 18% I/P RD | 669.18 | 4386.9 | 4386.9 | Approved | 0 | 0 | 144 | 29 May 2021
GANGA DHAM TOWERS | 632 | 90369 | 29 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 338 | A 604 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 714.7 | Sq.Ft | 15 | 100 | 268.01 | 0 | 10720.5 | C+S GST 18% I/P RD | 1929.7 | 12650.2 | 12650.2 | Approved | 0 | 0 | 144 | 29 May 2021
GANGA DHAM TOWERS | 126 | 90353 | 28 May 2021 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP VAMANRAO RUPNAWAR | EV - 333 | Site Expenses | Site Expenses -SO | 0.1617 | Month | 15000 | 100 | 0 | 0 | 2425 | CGST 0% URD I/P | 0 | 2425 | 2425 | Approved | 0 | 0 | 0 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 903 Blockwork 5" | Blockwork 5" - BC - | 644.19 | Sq.Ft | 13 | 100 | 209.36 | 0 | 8374.47 | C+S GST 18% I/P RD | 1507.4 | 9881.87 | 9881.87 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 905 Blockwork 8" | Blockwork 5" - BC - | 1169.49 | Sq.Ft | 13 | 100 | 380.08 | 0 | 15203.37 | C+S GST 18% I/P RD | 2736.6 | 17939.97 | 17939.97 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 802 Blockwork 5" | Blockwork 5" - BC - | 695.51 | Sq.Ft | 13 | 100 | 226.04 | 0 | 9041.63 | C+S GST 18% I/P RD | 1627.5 | 10669.13 | 10669.13 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 902 Blockwork 5" | Blockwork 5" - BC - | 849.86 | Sq.Ft | 13 | 100 | 276.2 | 0 | 11048.18 | C+S GST 18% I/P RD | 1988.68 | 13036.86 | 13036.86 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 904 Blockwork 5" | Blockwork 5" - BC - | 813.08 | Sq.Ft | 13 | 100 | 264.25 | 0 | 10570.04 | C+S GST 18% I/P RD | 1902.6 | 12472.64 | 12472.64 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 903 Blockwork 8" | Blockwork 8" - BC | 77.5 | Sq.Ft | 15 | 100 | 29.06 | 0 | 1162.5 | C+S GST 18% I/P RD | 209.26 | 1371.76 | 1371.76 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 901 Blockwork 8" | Blockwork 8" - BC | 62 | Sq.Ft | 15 | 100 | 23.25 | 0 | 930 | C+S GST 18% I/P RD | 167.4 | 1097.4 | 1097.4 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 905 Blockwork 8" | Blockwork 8" - BC | 204.09 | Sq.Ft | 15 | 100 | 76.53 | 0 | 3061.35 | C+S GST 18% I/P RD | 551.04 | 3612.39 | 3612.39 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 491 | 90352 | 28 May 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 332 | D Build. 904 Blockwork 8" | Blockwork 8" - BC | 206.67 | Sq.Ft | 15 | 100 | 77.5 | 0 | 3100.05 | C+S GST 18% I/P RD | 558 | 3658.05 | 3658.05 | Approved | 0 | 0 | 625 | 28 May 2021
GANGA DHAM TOWERS | 1057 | 90332 | 27 May 2021 |  | HELIOS | HELIOS | EV - 358 | Club House Glass/ SS Railing Work | SS Railing (L) | 71.16 | R.Ft | 125 | 100 | 222.38 | 0 | 8895 | C+S GST 18% I/P RD | 1601.1 | 10496.1 | 10496.1 | Approved | 0 | 0 | 167 | 27 May 2021
GANGA DHAM TOWERS | 1057 | 90332 | 27 May 2021 |  | HELIOS | HELIOS | EV - 358 | Club House Glass/ SS Railing Work | Glass Railing (L) | 14.25 | R.Ft | 550 | 100 | 195.94 | 0 | 7837.5 | C+S GST 18% I/P RD | 1410.76 | 9248.26 | 9248.26 | Approved | 0 | 0 | 167 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Granite Top- Dld. | 19.23 | R.Ft | 90 | 100 | 43.27 | 0 | 1730.7 | C+S GST 18% I/P RD | 311.52 | 2042.22 | 2042.22 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Italian Marble Dado - BCo | 14.21 | Sq.Ft | 115 | 100 | 40.85 | 0 | 1634.15 | C+S GST 18% I/P RD | 294.14 | 1928.29 | 1928.29 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Italian Marble Border-BCo | 54.64 | R.Ft | 105 | 100 | 143.43 | 0 | 5737.2 | C+S GST 18% I/P RD | 1032.7 | 6769.9 | 6769.9 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Zero Point Joint making- BCo | 55.79 | R.Ft | 200 | 100 | 278.95 | 0 | 11158 | C+S GST 18% I/P RD | 2008.44 | 13166.44 | 13166.44 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Italian Marble Edge Polish- BCo | 25.15 | R.Ft | 35 | 100 | 22.01 | 0 | 880.25 | C+S GST 18% I/P RD | 158.44 | 1038.69 | 1038.69 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Italian Marble Bull Nosing | 55.79 | R.Ft | 85 | 100 | 118.55 | 0 | 4742.15 | C+S GST 18% I/P RD | 853.58 | 5595.73 | 5595.73 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Italian Marbal Mirror Polish- DCH | 14.21 | Sq.Ft | 70 | 100 | 24.87 | 0 | 994.7 | C+S GST 18% I/P RD | 179.04 | 1173.74 | 1173.74 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Granite Border-BCo | 12.16 | R.Ft | 90 | 100 | 27.36 | 0 | 1094.4 | C+S GST 18% I/P RD | 197 | 1291.4 | 1291.4 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1059 | 90331 | 27 May 2021 |  | R K INTERIOR | R K INTERIOR | EV - 323 | Club House Reception Table | Italian Marble Mirror Polish- BC | 54.64 | R.Ft | 65 | 100 | 88.79 | 0 | 3551.6 | C+S GST 18% I/P RD | 639.28 | 4190.88 | 4190.88 | Approved | 0 | 0 | 630 | 27 May 2021
GANGA DHAM TOWERS | 1061 | 90330 | 27 May 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 339 | Ganga Collidium Shop no 32 Maintanace Work | Travelling charges- SO | 1 | No. | 210 | 100 | 0 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 34 | 27 May 2021
GANGA DHAM TOWERS | 1061 | 90330 | 27 May 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 339 | Ganga Collidium Shop no 32 Maintanace Work | Departmental Labour | 7 | No. | 450 | 100 | 0 | 0 | 3150 | CGST 0% URD I/P | 0 | 3150 | 3150 | Approved | 0 | 0 | 34 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2602 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 9 | No. | 450 | 35 | 35.44 | 0 | 1417.5 | C+S GST 18% I/P RD | 255.16 | 1672.66 | 1672.66 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2601 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1 | No. | 450 | 35 | 3.94 | 0 | 157.5 | C+S GST 18% I/P RD | 28.36 | 185.86 | 185.86 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2604 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | TV Point | 1 | No. | 350 | 35 | 3.06 | 0 | 122.5 | C+S GST 18% I/P RD | 22.06 | 144.56 | 144.56 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | Telephone Point | 1 | No. | 350 | 35 | 3.06 | 0 | 122.5 | C+S GST 18% I/P RD | 22.06 | 144.56 | 144.56 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2601 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 35 | 37.19 | 0 | 1487.5 | C+S GST 18% I/P RD | 267.76 | 1755.26 | 1755.26 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2604 Internal Electrical Work | 6 AMP Plug point (Independent) | 20 | No. | 250 | 35 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | 6 AMP Plug point (Independent) | 30 | No. | 250 | 35 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2602 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 225 | 35 | 1.97 | 0 | 78.75 | C+S GST 18% I/P RD | 14.18 | 92.93 | 92.93 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | AC Point BC | 1 | No. | 450 | 35 | 3.94 | 0 | 157.5 | C+S GST 18% I/P RD | 28.36 | 185.86 | 185.86 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2604 Internal Electrical Work | Fan Point | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2602 Internal Electrical Work | Fan Point | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | Fan Point | 2 | No. | 250 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2604 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 21 | No. | 250 | 35 | 45.94 | 0 | 1837.5 | C+S GST 18% I/P RD | 330.76 | 2168.26 | 2168.26 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 23 | No. | 250 | 35 | 50.31 | 0 | 2012.5 | C+S GST 18% I/P RD | 362.26 | 2374.76 | 2374.76 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2602 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2601 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 35 | 32.81 | 0 | 1312.5 | C+S GST 18% I/P RD | 236.26 | 1548.76 | 1548.76 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2601 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2602 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2603 Internal Electrical Work | Data Point | 2 | No. | 350 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 359 | 90329 | 27 May 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 431 | A Bldg Flat No.-2604 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 463 | 27 May 2021
GANGA DHAM TOWERS | 178 | 90309 | 25 May 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 285 | Sales Oiifce Landscape Area . | Garden work. | 53.5003 | Day | 407.25 | 100 | 0 | 0 | 21788 | C+S GST 18% I/P RD | 3921.84 | 25709.84 | 25709.84 | Approved | 0 | 0 | 218 | 25 May 2021
GANGA DHAM TOWERS | 179 | 90308 | 25 May 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 286 | Road Divider Garden Maintenance | Garden work. | 28.9994 | Day | 407.25 | 100 | 0 | 0 | 11810 | C+S GST 18% I/P RD | 2125.8 | 13935.8 | 13935.8 | Approved | 0 | 0 | 118 | 25 May 2021
GANGA DHAM TOWERS | 413 | 90307 | 25 May 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 287 | Sales Oiifce Landscape Area . | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 10 | 25 May 2021
GANGA DHAM TOWERS | 984 | 90304 | 24 May 2021 |  | SMITA ARTS | SMITA ARTS | EV - 289 | MEDIA Branding | LOGO / LETTER / DESIGN - MS / STEEL / ACRYLIC MATERIAL | 0.2548 | No. | 105000 | 100 | 0 | 0 | 26750 | C+S GST 18% I/P RD | 4815 | 31565 | 31565 | Approved | 0 | 0 | 1565 | 24 May 2021
GANGA DHAM TOWERS | 984 | 90304 | 24 May 2021 |  | SMITA ARTS | SMITA ARTS | EV - 289 | MEDIA Branding | ALUMINIUM COMPOSITE ACP SHEET PANEL | 76.66 | Sq.Ft | 150 | 100 | 0 | 0 | 11499 | C+S GST 18% I/P RD | 2069.82 | 13568.82 | 13568.82 | Approved | 0 | 0 | 1565 | 24 May 2021
GANGA DHAM TOWERS | 984 | 90304 | 24 May 2021 |  | SMITA ARTS | SMITA ARTS | EV - 289 | MEDIA Branding | LED STRIP LIGHT PANEL | 1 | No. | 40000 | 100 | 0 | 0 | 40000 | C+S GST 18% I/P RD | 7200 | 47200 | 47200 | Approved | 0 | 0 | 1565 | 24 May 2021
GANGA DHAM TOWERS | 984 | 90303 | 24 May 2021 |  | SMITA ARTS | SMITA ARTS | EV - 290 | MEDIA Branding | LOGO / LETTER / DESIGN - MS / STEEL / ACRYLIC MATERIAL | 0.7452 | No. | 105000 | 100 | 0 | 0 | 78250 | C+S GST 18% I/P RD | 14085 | 92335 | 92335 | Approved | 0 | 0 | 1565 | 24 May 2021
GANGA DHAM TOWERS | 984 | 90302 | 24 May 2021 |  | SMITA ARTS | SMITA ARTS | EV - 291 | MEDIA Branding | ALUMINIUM COMPOSITE ACP SHEET PANEL | 521.6667 | Sq.Ft | 150 | 100 | 0 | 0 | 78250.01 | C+S GST 18% I/P RD | 14085 | 92335.01 | 92335.01 | Approved | 0 | 0 | 1565 | 24 May 2021
GANGA DHAM TOWERS | 984 | 90301 | 24 May 2021 |  | SMITA ARTS | SMITA ARTS | EV - 288 | MEDIA Branding | ALUMINIUM COMPOSITE ACP SHEET PANEL | 521.6667 | Sq.Ft | 150 | 100 | 0 | 0 | 78250.01 | C+S GST 18% I/P RD | 14085 | 92335.01 | 92335.01 | Approved | 0 | 0 | 1565 | 24 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 11th Floor Lobby Planter GI Frame | G.I. Frame (L) | 3 | No. | 700 | 100 | 52.5 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 12th Floor Lobby Planter GI Frame | G.I. Frame (L) | 5 | No. | 700 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 10th Floor Lobby Planter GI Frame | G.I. Frame (L) | 3 | No. | 700 | 100 | 52.5 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 9th Floor Lobby Planter GI Frame | G.I. Frame (L) | 5 | No. | 700 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 2nd Floor Lobby Planter GI Frame | G.I. Frame (L) | 5 | No. | 700 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 5th Floor Lobby Planter GI Frame | G.I. Frame (L) | 5 | No. | 700 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 6th Floor Lobby Planter GI Frame | G.I. Frame (L) | 3 | No. | 700 | 100 | 52.5 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 7thFloor Lobby Planter GI Frame | G.I. Frame (L) | 5 | No. | 700 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 8th Floor Lobby Planter GI Frame | G.I. Frame (L) | 5 | No. | 700 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 642 | 90279 | 20 May 2021 |  | MAGAR ENTERPRISES | MAGAR ENTERPRISES | EV - 425 | A 4th Floor Lobby Planter GI Frame | G.I. Frame (L) | 5 | No. | 700 | 100 | 87.5 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 308 | 20 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 7th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 2nd Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 12th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 13th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 4th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 6th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 16th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 14th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 8th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 10th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 11th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 1st Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 5th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 15th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 9th Floor Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 10th Floor Fire Staircase Flooring | Kota Riser (L)- BCO | 74.3175 | R.Ft | 45 | 100 | 83.61 | 0 | 3344.29 | C+S GST 18% I/P RD | 601.98 | 3946.27 | 3946.27 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 1st Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 9th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 14th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 5th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 3rd Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 4th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 8th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 15th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 1st Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 9th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 2nd Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 14th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 6th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 13th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 11th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 16th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 10th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 12th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 7th Floor Staircase Flooring | Kota Tread (L) - DSP | 74.3175 | R.Ft | 50 | 100 | 92.9 | 0 | 3715.88 | C+S GST 18% I/P RD | 668.86 | 4384.74 | 4384.74 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 12th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 16th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 14th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 8th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 10th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 13th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 15th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 6th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 4th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 9th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 5th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 7th Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 1st Floor Staircase Flooring | Kota Skirting (L)- BCO | 36.83 | R.Ft | 30 | 100 | 27.62 | 0 | 1104.9 | C+S GST 18% I/P RD | 198.88 | 1303.78 | 1303.78 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 1st Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 10th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 11th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 6th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 8th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 15th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 13th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 2nd Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 4th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 14th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 7th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 16th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 5th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 9th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 12th Floor Staircase Flooring | Kota Champher | 74.3175 | R.Ft | 7.5 | 100 | 13.93 | 0 | 557.38 | C+S GST 18% I/P RD | 100.32 | 657.7 | 657.7 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 10th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 13th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 5th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 6th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 7th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 16th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 11th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 2nd Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 4th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 15th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 12th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 905 | 90271 | 19 May 2021 |  | R.M.Marbles | R.M.Marbles | EV - 1275 | A 8th Floor Staircase Flooring | Kota Flooring (L)- BCO | 121.095 | Sq.Ft | 50 | 100 | 151.37 | 0 | 6054.75 | C+S GST 18% I/P RD | 1089.86 | 7144.61 | 7144.61 | Approved | 0 | 0 | 2265 | 19 May 2021
GANGA DHAM TOWERS | 389 | 90256 | 17 May 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 240 | Loading / Unloading Expenses | Unloading of GYpsum- | 33 | Metric Tonnes | 200 | 100 | 0 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 389 | 90256 | 17 May 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 240 | Loading / Unloading Expenses | Unloading of AAC Blocks | 3334 | No. | 2 | 100 | 0 | 0 | 6668 | CGST 0% URD I/P | 0 | 6668 | 6668 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 389 | 90256 | 17 May 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 240 | Loading / Unloading Expenses | Unloading of AAC Blocks | 1244 | No. | 2 | 100 | 0 | 0 | 2488 | CGST 0% URD I/P | 0 | 2488 | 2488 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 389 | 90256 | 17 May 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 240 | Loading / Unloading Expenses | Unloading of AAC Blocks | 2327 | No. | 2 | 100 | 0 | 0 | 4654 | CGST 0% URD I/P | 0 | 4654 | 4654 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 389 | 90256 | 17 May 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 240 | Loading / Unloading Expenses | Unloading of AAC Blocks | 484 | No. | 2 | 100 | 0 | 0 | 968 | CGST 0% URD I/P | 0 | 968 | 968 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 389 | 90256 | 17 May 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 240 | Loading / Unloading Expenses | Unloading of tiles. | 19.5 | Metric Tonnes | 160 | 100 | 0 | 0 | 3120 | CGST 0% URD I/P | 0 | 3120 | 3120 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 389 | 90256 | 17 May 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 240 | Loading / Unloading Expenses | Unloading of tiles. | 3 | Metric Tonnes | 160 | 100 | 0 | 0 | 480 | CGST 0% URD I/P | 0 | 480 | 480 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 1022 | 90255 | 17 May 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 329 | DA Development Top Terrace Ms Work | Aluminium Sheet Fixing | 608 | Sq.Ft | 25 | 100 | 380 | 0 | 15200 | CGST 0% URD I/P | 0 | 15200 | 15200 | Approved | 0 | 0 | 340 | 17 May 2021
GANGA DHAM TOWERS | 1022 | 90255 | 17 May 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 329 | DA Development Top Terrace Ms Work | Fabrication work (L) | 340.719 | Kgs | 26.6 | 100 | 226.58 | 0 | 9063.13 | CGST 0% URD I/P | 0 | 9063.13 | 9063.13 | Approved | 0 | 0 | 340 | 17 May 2021
GANGA DHAM TOWERS | 1022 | 90255 | 17 May 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 329 | DA Development Top Terrace Ms Work | Fabrication work (L) | 235.196 | Kgs | 19.95 | 100 | 117.3 | 0 | 4692.16 | CGST 0% URD I/P | 0 | 4692.16 | 4692.16 | Approved | 0 | 0 | 340 | 17 May 2021
GANGA DHAM TOWERS | 1022 | 90255 | 17 May 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 329 | DA Development Top Terrace Ms Work | GI Sheet Removing & Fixing | 1 | No. | 5000 | 100 | 125 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 340 | 17 May 2021
GANGA DHAM TOWERS | 1023 | 90254 | 17 May 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 330 | DA Development Top Terrace Ms Work | Fabrication work (M) | 340.719 | Kgs | 76 | 100 | 0 | 0 | 25894.64 | CGST 0% URD I/P | 0 | 25894.64 | 25894.64 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 1023 | 90254 | 17 May 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 330 | DA Development Top Terrace Ms Work | Fabrication work (M) | 235.196 | Kgs | 57 | 100 | 0 | 0 | 13406.17 | CGST 0% URD I/P | 0 | 13406.17 | 13406.17 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 1023 | 90254 | 17 May 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 330 | DA Development Top Terrace Ms Work | Self Tamping Screw (M) | 200 | No. | 2.5 | 100 | 0 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 1023 | 90254 | 17 May 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 330 | DA Development Top Terrace Ms Work | MS Angle (M) | 12 | No. | 20 | 100 | 0 | 0 | 240 | CGST 0% URD I/P | 0 | 240 | 240 | Approved | 0 | 0 | 0 | 17 May 2021
GANGA DHAM TOWERS | 497 | 90253 | 17 May 2021 | 38 | J K INTERIOR | J K INTERIOR | EV - 553 | B 2102 Gypsum Plaster | Gypsum on Wall (L) | 3581 | Sq.Ft | 4 | 100 | 358.1 | 0 | 14324 | C+S GST 18% I/P RD | 2578.32 | 16902.32 | 16902.32 | Approved | 0 | 0 | 193 | 17 May 2021
GANGA DHAM TOWERS | 497 | 90253 | 17 May 2021 | 38 | J K INTERIOR | J K INTERIOR | EV - 553 | B 2102 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 193 | 17 May 2021
GANGA DHAM TOWERS | 1041 | 90240 | 13 May 2021 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 278 | MEDIA FLEX PASTING | Eco Vinyal With Foam Sheet | 12 | Sq.Ft | 90 | 100 | 0 | 0 | 1080 | C+S GST 18% I/P RD | 194.4 | 1274.4 | 1274.4 | Approved | 0 | 0 | 3332 | 13 May 2021
GANGA DHAM TOWERS | 1041 | 90240 | 13 May 2021 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 278 | MEDIA FLEX PASTING | Eco Vinyal with Lamination | 40 | Sq.Ft | 65 | 100 | 0 | 0 | 2600 | C+S GST 18% I/P RD | 468 | 3068 | 3068 | Approved | 0 | 0 | 3332 | 13 May 2021
GANGA DHAM TOWERS | 1041 | 90240 | 13 May 2021 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 278 | MEDIA FLEX PASTING | Star Flex | 450 | Sq.Ft | 40 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 3332 | 13 May 2021
GANGA DHAM TOWERS | 1041 | 90240 | 13 May 2021 |  | DREAMTREE EXPERIENCE | DREAMTREE EXPERIENCE | EV - 278 | MEDIA FLEX PASTING | Black Back Flex | 7628 | Sq.Ft | 19 | 100 | 0 | 0 | 144932 | C+S GST 18% I/P RD | 26087.76 | 171019.76 | 171019.76 | Approved | 0 | 0 | 3332 | 13 May 2021
GANGA DHAM TOWERS | 1047 | 90234 | 13 May 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES |  | Club House Flower Bed Texture | Texture Paint (L) | 461.37 | Sq.Ft | 11.75 | 100 | 135.53 | 0 | 5421.1 | C+S GST 18% I/P RD | 975.8 | 6396.9 | 6396.9 |  | 0 | 0 | 54 | 13 May 2021
GANGA DHAM TOWERS | 1049 | 90233 | 13 May 2021 | 120 | SS ENTERPRISES | SS ENTERPRISES | EV - 563 | JCB/Poclain/Dumper/Crane/Tractor Charges For Dev Work | JCB Charges | 8 | Hrs | 850 | 100 | 0 | 0 | 6800 | CGST 0% URD I/P | 0 | 6800 | 6800 | Approved | 0 | 0 | 68 | 13 May 2021
GANGA DHAM TOWERS | 696 | 90232 | 13 May 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 277 | B P1 Parking Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 561 | Sq.Ft | 5 | 100 | 70.13 | 0 | 2805 | C+S GST 18% I/P RD | 504.9 | 3309.9 | 3309.9 | Approved | 0 | 0 | 157 | 13 May 2021
GANGA DHAM TOWERS | 696 | 90232 | 13 May 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 277 | B P2 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 413.75 | Sq.Ft | 4 | 100 | 41.38 | 0 | 1655 | C+S GST 18% I/P RD | 297.9 | 1952.9 | 1952.9 | Approved | 0 | 0 | 157 | 13 May 2021
GANGA DHAM TOWERS | 696 | 90232 | 13 May 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 277 | B P1 Parking Floor Column Plaster | Gypsum Plaster (L) | 1058.29 | Sq.Ft | 4 | 100 | 105.83 | 0 | 4233.16 | C+S GST 18% I/P RD | 761.96 | 4995.12 | 4995.12 | Approved | 0 | 0 | 157 | 13 May 2021
GANGA DHAM TOWERS | 696 | 90232 | 13 May 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 277 | B Ground Floor Staircase & Lobby Plaster | Gypsum Plaster (L) | 413.75 | Sq.Ft | 4 | 100 | 41.38 | 0 | 1655 | C+S GST 18% I/P RD | 297.9 | 1952.9 | 1952.9 | Approved | 0 | 0 | 157 | 13 May 2021
GANGA DHAM TOWERS | 696 | 90232 | 13 May 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 277 | B Ground Floor Column Plaster | Gypsum Plaster (L) | 925.705 | Sq.Ft | 4 | 100 | 92.57 | 0 | 3702.82 | C+S GST 18% I/P RD | 666.5 | 4369.32 | 4369.32 | Approved | 0 | 0 | 157 | 13 May 2021
GANGA DHAM TOWERS | 696 | 90232 | 13 May 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 277 | B P1 Parking Staircase & Lobby Plaster | Gypsum Plaster (L) | 413.75 | Sq.Ft | 4 | 100 | 41.38 | 0 | 1655 | C+S GST 18% I/P RD | 297.9 | 1952.9 | 1952.9 | Approved | 0 | 0 | 157 | 13 May 2021
GANGA DHAM TOWERS | 126 | 90231 | 13 May 2021 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 280 | Site Expenses | Site Expenses -SO | 0.2333 | Month | 15000 | 100 | 0 | 0 | 3500 | CGST 0% URD I/P | 0 | 3500 | 3500 | Approved | 0 | 0 | 0 | 13 May 2021
GANGA DHAM TOWERS | 1045 | 90228 | 12 May 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 267 | Developement Drainage Line Breaker | Breaker - UTI | 9 | Day | 900 | 100 | 0 | 0 | 8100 | CGST 0% URD I/P | 0 | 8100 | 8100 | Approved | 0 | 0 | 81 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Edge Polish- DCH | 479.02 | R.Ft | 12 | 100 | 143.71 | 0 | 5748.24 | C+S GST 18% I/P RD | 1034.68 | 6782.92 | 6782.92 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Groove-BC | 4 | R.Ft | 25 | 100 | 2.5 | 0 | 100 | C+S GST 18% I/P RD | 18 | 118 | 118 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Patti | 167.21 | R.Ft | 55 | 100 | 229.91 | 0 | 9196.55 | C+S GST 18% I/P RD | 1655.38 | 10851.93 | 10851.93 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Patti | 182.38 | R.Ft | 55 | 100 | 250.77 | 0 | 10030.9 | C+S GST 18% I/P RD | 1805.56 | 11836.46 | 11836.46 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Grouting Work -Dld | 2092.103 | Sq.Ft | 5 | 100 | 261.51 | 0 | 10460.52 | C+S GST 18% I/P RD | 1882.9 | 12343.42 | 12343.42 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Top- Dld. | 101.8182 | R.Ft | 55 | 100 | 140 | 0 | 5600 | C+S GST 18% I/P RD | 1008 | 6608 | 6608 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Champher & Polish-ULT | 1144.46 | R.Ft | 24 | 100 | 686.68 | 0 | 27467.04 | C+S GST 18% I/P RD | 4944.06 | 32411.1 | 32411.1 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Cladding - BCo | 12 | Sq.Ft | 55 | 100 | 16.5 | 0 | 660 | C+S GST 18% I/P RD | 118.8 | 778.8 | 778.8 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Patti | 306.39 | R.Ft | 55 | 100 | 421.29 | 0 | 16851.45 | C+S GST 18% I/P RD | 3033.26 | 19884.71 | 19884.71 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Patti | 101.82 | R.Ft | 55 | 100 | 140 | 0 | 5600.1 | C+S GST 18% I/P RD | 1008.02 | 6608.12 | 6608.12 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Groove-BC | 3264.29 | R.Ft | 12.5 | 100 | 1020.09 | 0 | 40803.63 | C+S GST 18% I/P RD | 7344.66 | 48148.29 | 48148.29 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 1053 | 90227 | 12 May 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 272 | Clubhouse Landscape Tiling work (L) | Granite Flooring | 2092.1 | Sq.Ft | 55 | 100 | 2876.64 | 0 | 115065.5 | C+S GST 18% I/P RD | 20711.8 | 135777.3 | 135777.3 | Approved | 0 | 0 | 2476 | 12 May 2021
GANGA DHAM TOWERS | 678 | 90223 | 11 May 2021 |  | AVCON TECHNICS PVT LTD | PRAKASH CONTRACTOR | EV - 214 | A 804 NOC | Breaking Of Tile - Mkt | 1507.48 | Sq.Ft | 13.267 | 100 | 499.99 | 0 | 19999.74 | CGST 0% URD I/P | 0 | 19999.74 | 19999.74 | Approved | 0 | 0 | 200 | 11 May 2021
GANGA DHAM TOWERS | 813 | 90222 | 11 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 213 | D 2nd Floor Lobby Chemical Grouting | Chemical Grouting (L) | 230.78 | Sq.Ft | 1 | 100 | 23.08 | 0 | 230.78 | C+S GST 0% I/P RD | 0 | 230.78 | 230.78 | Approved | 0 | 0 | 2 | 11 May 2021
GANGA DHAM TOWERS | 126 | 90215 | 11 May 2021 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 266 | Site Expenses | Site Expenses -SO | 0.0333 | Month | 15000 | 100 | 0 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 0 | 11 May 2021
GANGA DHAM TOWERS | 126 | 90215 | 11 May 2021 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 266 | Site Expenses | Site Expenses -SO | 0.2693 | Month | 15000 | 100 | 0 | 0 | 4040 | CGST 0% URD I/P | 0 | 4040 | 4040 | Approved | 0 | 0 | 0 | 11 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 503 Terrace False Ceiling | Sherawood False Ceiling (M) | 45.7538 | Sq.Ft | 130 | 100 | 0 | 0 | 5948 | C+S GST 18% I/P RD | 1070.64 | 7018.64 | 7018.64 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 901 Terrace False Ceiling | Sherawood False Ceiling (M) | 54.0769 | Sq.Ft | 130 | 100 | 0 | 0 | 7030 | C+S GST 18% I/P RD | 1265.4 | 8295.4 | 8295.4 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 602 Terrace False Ceiling | Sherawood False Ceiling (M) | 61.8769 | Sq.Ft | 130 | 100 | 0 | 0 | 8044 | C+S GST 18% I/P RD | 1447.92 | 9491.92 | 9491.92 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 803 Terrace False Ceiling | Sherawood False Ceiling (M) | 45.7538 | Sq.Ft | 130 | 100 | 0 | 0 | 5948 | C+S GST 18% I/P RD | 1070.64 | 7018.64 | 7018.64 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 1002 Terrace False Ceiling | Sherawood False Ceiling (M) | 61.8769 | Sq.Ft | 130 | 100 | 0 | 0 | 8044 | C+S GST 18% I/P RD | 1447.92 | 9491.92 | 9491.92 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 702 Terrace False Ceiling | Sherawood False Ceiling (M) | 54.0769 | Sq.Ft | 130 | 100 | 0 | 0 | 7030 | C+S GST 18% I/P RD | 1265.4 | 8295.4 | 8295.4 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 1203 Terrace False Ceiling | Sherawood False Ceiling (M) | 18.0385 | Sq.Ft | 130 | 100 | 0 | 0 | 2345.01 | C+S GST 18% I/P RD | 422.1 | 2767.11 | 2767.11 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 501 Terrace False Ceiling | Sherawood False Ceiling (M) | 54.0692 | Sq.Ft | 130 | 100 | 0 | 0 | 7029 | C+S GST 18% I/P RD | 1265.22 | 8294.22 | 8294.22 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 502 Terrace False Ceiling | Sherawood False Ceiling (M) | 69.7692 | Sq.Ft | 130 | 100 | 0 | 0 | 9070 | C+S GST 18% I/P RD | 1632.6 | 10702.6 | 10702.6 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 804 Terrace False Ceiling | Sherawood False Ceiling (M) | 61.8769 | Sq.Ft | 130 | 100 | 0 | 0 | 8044 | C+S GST 18% I/P RD | 1447.92 | 9491.92 | 9491.92 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 604 Terrace False Ceiling | Sherawood False Ceiling (M) | 61.8769 | Sq.Ft | 130 | 100 | 0 | 0 | 8044 | C+S GST 18% I/P RD | 1447.92 | 9491.92 | 9491.92 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 902 Terrace False Ceiling | Sherawood False Ceiling (M) | 54.0769 | Sq.Ft | 130 | 100 | 0 | 0 | 7030 | C+S GST 18% I/P RD | 1265.4 | 8295.4 | 8295.4 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 603 Terrace False Ceiling | Sherawood False Ceiling (M) | 45.7538 | Sq.Ft | 130 | 100 | 0 | 0 | 5948 | C+S GST 18% I/P RD | 1070.64 | 7018.64 | 7018.64 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 801 Terrace False Ceiling | Sherawood False Ceiling (M) | 61.8769 | Sq.Ft | 130 | 100 | 0 | 0 | 8044 | C+S GST 18% I/P RD | 1447.92 | 9491.92 | 9491.92 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 601 Terrace False Ceiling | Sherawood False Ceiling (M) | 61.8769 | Sq.Ft | 130 | 100 | 0 | 0 | 8044 | C+S GST 18% I/P RD | 1447.92 | 9491.92 | 9491.92 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 636 | 90211 | 10 May 2021 |  | S R INFRA PROJECTS (Material) | S R INFRA PROJECTS (Material) | EV - 208 | A 1103 Terrace False Ceiling | Sherawood False Ceiling (M) | 25 | Sq.Ft | 130 | 100 | 0 | 0 | 3250 | C+S GST 18% I/P RD | 585 | 3835 | 3835 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 126 | 90210 | 10 May 2021 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 209 | Site Expenses | Site Expenses -SO | 0.0513 | Month | 15000 | 100 | 0 | 0 | 770 | CGST 0% URD I/P | 0 | 770 | 770 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 982 | 90208 | 10 May 2021 |  | S J INDUSTRIES | S J INDUSTRIES | EV - 206 | A Facade Scaffolding Fitting & Removing Work | H Frame & Cross Bracing | 100 | set | 3880 | 100 | 0 | 0 | 388000 | C+S GST 18% I/P RD | 69840 | 457840 | 457840 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 237 | 90207 | 10 May 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 205 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.9286 | Month | 7000 | 100 | 0 | 0 | 6500 | CGST 0% URD I/P | 0 | 6500 | 6500 | Approved | 0 | 0 | 65 | 10 May 2021
GANGA DHAM TOWERS | 258 | 90205 | 10 May 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 207 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.9284 | Month | 2500 | 100 | 0 | 0 | 2321 | CGST 0% URD I/P | 0 | 2321 | 2321 | Approved | 0 | 0 | 23 | 10 May 2021
GANGA DHAM TOWERS | 653 | 90204 | 10 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 212 | D502 Chemical Grouting | Chemical Grouting.- BC | 356.8 | Sq.Ft | 1 | 100 | 35.68 | 0 | 356.8 | CGST 0% URD I/P | 0 | 356.8 | 356.8 | Approved | 0 | 0 | 26 | 10 May 2021
GANGA DHAM TOWERS | 653 | 90204 | 10 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 212 | D505 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 26 | 10 May 2021
GANGA DHAM TOWERS | 653 | 90204 | 10 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 212 | D402 Chemical Grouting | Chemical Grouting.- BC | 356.8 | Sq.Ft | 1 | 100 | 35.68 | 0 | 356.8 | CGST 0% URD I/P | 0 | 356.8 | 356.8 | Approved | 0 | 0 | 26 | 10 May 2021
GANGA DHAM TOWERS | 653 | 90204 | 10 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 212 | D501 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 26 | 10 May 2021
GANGA DHAM TOWERS | 653 | 90204 | 10 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 212 | D401 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 26 | 10 May 2021
GANGA DHAM TOWERS | 653 | 90204 | 10 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 212 | D405 Chemical Grouting | Chemical Grouting.- BC | 481.9 | Sq.Ft | 1 | 100 | 48.19 | 0 | 481.9 | CGST 0% URD I/P | 0 | 481.9 | 481.9 | Approved | 0 | 0 | 26 | 10 May 2021
GANGA DHAM TOWERS | 793 | 90203 | 10 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 211 | D 201 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 4500 | 100 | 112.5 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 76 | 10 May 2021
GANGA DHAM TOWERS | 793 | 90203 | 10 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 211 | D 202 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 1 | Per Flat | 3060 | 100 | 76.5 | 0 | 3060 | CGST 0% URD I/P | 0 | 3060 | 3060 | Approved | 0 | 0 | 76 | 10 May 2021
GANGA DHAM TOWERS | 629 | 90202 | 10 May 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 215 | A 304 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (M) | 500 | R.Ft | 25 | 100 | 0 | 0 | 12500 | C+S GST 18% I/P RD | 2250 | 14750 | 14750 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 632 | 90201 | 10 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 190 | A 304 Gypsum Board False Ceiling | Gypsum False Ceiling Patta (L) | 500 | R.Ft | 7.5 | 100 | 93.75 | 0 | 3750 | C+S GST 18% I/P RD | 675 | 4425 | 4425 | Approved | 0 | 0 | 38 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A-1101 Living,Dining,Passa. Marble Flooring - 1 No. | Italian Marble Mirror Polish.- BCo | 88.155 | R.Ft | 40 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 1002 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 85.9425 | R.Ft | 40 | 100 | 85.94 | 0 | 3437.7 | C+S GST 18% I/P RD | 618.78 | 4056.48 | 4056.48 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 1001 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 49.215 | R.Ft | 40 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A-1101 Parents Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish.- BCo | 46.755 | R.Ft | 40 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 1002 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 37.2525 | R.Ft | 40 | 100 | 37.25 | 0 | 1490.1 | C+S GST 18% I/P RD | 268.22 | 1758.32 | 1758.32 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 601 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 49.215 | R.Ft | 35 | 100 | 43.06 | 0 | 1722.53 | C+S GST 18% I/P RD | 310.06 | 2032.59 | 2032.59 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 201 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 49.215 | R.Ft | 35 | 100 | 43.06 | 0 | 1722.53 | C+S GST 18% I/P RD | 310.06 | 2032.59 | 2032.59 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 201 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 46.755 | R.Ft | 35 | 100 | 40.91 | 0 | 1636.43 | C+S GST 18% I/P RD | 294.56 | 1930.99 | 1930.99 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 201 Living,Dining,Passa. Flooring | Italian Marble Mirror Polish.- BCo | 88.155 | R.Ft | 35 | 100 | 77.14 | 0 | 3085.43 | C+S GST 18% I/P RD | 555.38 | 3640.81 | 3640.81 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 401 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 49.215 | R.Ft | 35 | 100 | 43.06 | 0 | 1722.53 | C+S GST 18% I/P RD | 310.06 | 2032.59 | 2032.59 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 1001 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 88.155 | R.Ft | 40 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A-1101 Master Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish.- BCo | 49.215 | R.Ft | 40 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 701 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 46.755 | R.Ft | 40 | 100 | 46.76 | 0 | 1870.2 | C+S GST 18% I/P RD | 336.64 | 2206.84 | 2206.84 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 1002 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 50.175 | R.Ft | 40 | 100 | 50.18 | 0 | 2007 | C+S GST 18% I/P RD | 361.26 | 2368.26 | 2368.26 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 701 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 88.155 | R.Ft | 40 | 100 | 88.16 | 0 | 3526.2 | C+S GST 18% I/P RD | 634.72 | 4160.92 | 4160.92 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 701 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 49.215 | R.Ft | 40 | 100 | 49.22 | 0 | 1968.6 | C+S GST 18% I/P RD | 354.34 | 2322.94 | 2322.94 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 601 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 46.755 | R.Ft | 35 | 100 | 40.91 | 0 | 1636.43 | C+S GST 18% I/P RD | 294.56 | 1930.99 | 1930.99 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 401 Living,Dining,Passa. Flooring | Italian Marble Mirror Polish.- BCo | 88.155 | R.Ft | 35 | 100 | 77.14 | 0 | 3085.43 | C+S GST 18% I/P RD | 555.38 | 3640.81 | 3640.81 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 401 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 46.755 | R.Ft | 35 | 100 | 40.91 | 0 | 1636.43 | C+S GST 18% I/P RD | 294.56 | 1930.99 | 1930.99 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 502 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 85.9425 | R.Ft | 35 | 100 | 75.2 | 0 | 3007.99 | C+S GST 18% I/P RD | 541.44 | 3549.43 | 3549.43 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 601 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 88.155 | R.Ft | 35 | 100 | 77.14 | 0 | 3085.43 | C+S GST 18% I/P RD | 555.38 | 3640.81 | 3640.81 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 502 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 37.2525 | R.Ft | 35 | 100 | 32.6 | 0 | 1303.84 | C+S GST 18% I/P RD | 234.7 | 1538.54 | 1538.54 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90191 | 10 May 2021 | 060 | R K INTERIOR | MONIKA ENTERPRISES | EV - 294 | A 502 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 50.175 | R.Ft | 35 | 100 | 43.9 | 0 | 1756.13 | C+S GST 18% I/P RD | 316.1 | 2072.23 | 2072.23 | Approved | 0 | 0 | 1051 | 10 May 2021
GANGA DHAM TOWERS | 744 | 90189 | 10 May 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 269 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1403 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 45 | 100 | 39.56 | 0 | 1582.54 | C+S GST 18% I/P RD | 284.86 | 1867.4 | 1867.4 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1603 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 45 | 100 | 39.56 | 0 | 1582.54 | C+S GST 18% I/P RD | 284.86 | 1867.4 | 1867.4 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1303 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 45 | 100 | 85.68 | 0 | 3427.31 | C+S GST 18% I/P RD | 616.92 | 4044.23 | 4044.23 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1402 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 85.9425 | R.Ft | 45 | 100 | 96.69 | 0 | 3867.41 | C+S GST 18% I/P RD | 696.14 | 4563.55 | 4563.55 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1403 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 45 | 100 | 35.16 | 0 | 1406.36 | C+S GST 18% I/P RD | 253.14 | 1659.5 | 1659.5 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1702 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 85.9425 | R.Ft | 45 | 100 | 96.69 | 0 | 3867.41 | C+S GST 18% I/P RD | 696.14 | 4563.55 | 4563.55 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1402 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 37.2525 | R.Ft | 45 | 100 | 41.91 | 0 | 1676.36 | C+S GST 18% I/P RD | 301.74 | 1978.1 | 1978.1 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1403 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 45 | 100 | 85.68 | 0 | 3427.31 | C+S GST 18% I/P RD | 616.92 | 4044.23 | 4044.23 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1603 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 45 | 100 | 35.16 | 0 | 1406.36 | C+S GST 18% I/P RD | 253.14 | 1659.5 | 1659.5 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1303 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 45 | 100 | 39.56 | 0 | 1582.54 | C+S GST 18% I/P RD | 284.86 | 1867.4 | 1867.4 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1303 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 45 | 100 | 35.16 | 0 | 1406.36 | C+S GST 18% I/P RD | 253.14 | 1659.5 | 1659.5 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1402 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 40 | R.Ft | 45 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1702 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 37.2525 | R.Ft | 45 | 100 | 41.91 | 0 | 1676.36 | C+S GST 18% I/P RD | 301.74 | 1978.1 | 1978.1 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1603 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 45 | 100 | 85.68 | 0 | 3427.31 | C+S GST 18% I/P RD | 616.92 | 4044.23 | 4044.23 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1704 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 43.065 | R.Ft | 45 | 100 | 48.45 | 0 | 1937.93 | C+S GST 18% I/P RD | 348.82 | 2286.75 | 2286.75 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1403 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1702 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 50.175 | R.Ft | 45 | 100 | 56.45 | 0 | 2257.88 | C+S GST 18% I/P RD | 406.42 | 2664.3 | 2664.3 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1003 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 50 | 100 | 43.96 | 0 | 1758.38 | C+S GST 18% I/P RD | 316.5 | 2074.88 | 2074.88 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1003 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 50 | 100 | 39.07 | 0 | 1562.63 | C+S GST 18% I/P RD | 281.28 | 1843.91 | 1843.91 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1204 Master Bed Marble Flooring | Italian Marble Champher & Polish | 43.065 | R.Ft | 50 | 100 | 53.83 | 0 | 2153.25 | C+S GST 18% I/P RD | 387.58 | 2540.83 | 2540.83 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 703 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 50 | 100 | 39.07 | 0 | 1562.63 | C+S GST 18% I/P RD | 281.28 | 1843.91 | 1843.91 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1003 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 50 | 100 | 95.2 | 0 | 3808.13 | C+S GST 18% I/P RD | 685.46 | 4493.59 | 4493.59 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 903 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 50 | 100 | 43.96 | 0 | 1758.38 | C+S GST 18% I/P RD | 316.5 | 2074.88 | 2074.88 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1204 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 32.235 | R.Ft | 50 | 100 | 40.29 | 0 | 1611.75 | C+S GST 18% I/P RD | 290.12 | 1901.87 | 1901.87 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 903 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 50 | 100 | 95.2 | 0 | 3808.13 | C+S GST 18% I/P RD | 685.46 | 4493.59 | 4493.59 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 903 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 50 | 100 | 39.07 | 0 | 1562.63 | C+S GST 18% I/P RD | 281.28 | 1843.91 | 1843.91 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 704 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 32.235 | R.Ft | 50 | 100 | 40.29 | 0 | 1611.75 | C+S GST 18% I/P RD | 290.12 | 1901.87 | 1901.87 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 703 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 50 | 100 | 43.96 | 0 | 1758.38 | C+S GST 18% I/P RD | 316.5 | 2074.88 | 2074.88 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 704 Master Bed Marble Flooring | Italian Marble Champher & Polish | 43.065 | R.Ft | 50 | 100 | 53.83 | 0 | 2153.25 | C+S GST 18% I/P RD | 387.58 | 2540.83 | 2540.83 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1402 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 85.9425 | R.Ft | 55 | 100 | 118.17 | 0 | 4726.84 | C+S GST 18% I/P RD | 850.84 | 5577.68 | 5577.68 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1704 Master Bed Marble Flooring | Italian Marble Champher & Polish | 43.065 | R.Ft | 55 | 100 | 59.21 | 0 | 2368.58 | C+S GST 18% I/P RD | 426.34 | 2794.92 | 2794.92 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1702 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 37.2525 | R.Ft | 55 | 100 | 51.22 | 0 | 2048.89 | C+S GST 18% I/P RD | 368.8 | 2417.69 | 2417.69 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1303 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 55 | 100 | 48.36 | 0 | 1934.21 | C+S GST 18% I/P RD | 348.16 | 2282.37 | 2282.37 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1303 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 55 | 100 | 42.97 | 0 | 1718.89 | C+S GST 18% I/P RD | 309.4 | 2028.29 | 2028.29 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1402 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 37.2525 | R.Ft | 55 | 100 | 51.22 | 0 | 2048.89 | C+S GST 18% I/P RD | 368.8 | 2417.69 | 2417.69 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1403 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 55 | 100 | 48.36 | 0 | 1934.21 | C+S GST 18% I/P RD | 348.16 | 2282.37 | 2282.37 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1402 Master Bed Marble Flooring - 1 No. | Italian Marble Champher & Polish | 50.175 | R.Ft | 55 | 100 | 68.99 | 0 | 2759.63 | C+S GST 18% I/P RD | 496.74 | 3256.37 | 3256.37 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1403 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 55 | 100 | 104.72 | 0 | 4188.94 | C+S GST 18% I/P RD | 754 | 4942.94 | 4942.94 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1303 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 55 | 100 | 104.72 | 0 | 4188.94 | C+S GST 18% I/P RD | 754 | 4942.94 | 4942.94 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1603 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 55 | 100 | 48.36 | 0 | 1934.21 | C+S GST 18% I/P RD | 348.16 | 2282.37 | 2282.37 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1603 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 55 | 100 | 42.97 | 0 | 1718.89 | C+S GST 18% I/P RD | 309.4 | 2028.29 | 2028.29 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 602 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 37.2525 | R.Ft | 45 | 100 | 41.91 | 0 | 1676.36 | C+S GST 18% I/P RD | 301.74 | 1978.1 | 1978.1 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 504 Master Bed Marble Flooring | Italian Marble Champher & Polish | 43.065 | R.Ft | 45 | 100 | 48.45 | 0 | 1937.93 | C+S GST 18% I/P RD | 348.82 | 2286.75 | 2286.75 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 204 Master Bed Marble Flooring | Italian Marble Champher & Polish | 43.065 | R.Ft | 45 | 100 | 48.45 | 0 | 1937.93 | C+S GST 18% I/P RD | 348.82 | 2286.75 | 2286.75 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 32.235 | R.Ft | 45 | 100 | 36.26 | 0 | 1450.58 | C+S GST 18% I/P RD | 261.1 | 1711.68 | 1711.68 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 45 | 100 | 39.56 | 0 | 1582.54 | C+S GST 18% I/P RD | 284.86 | 1867.4 | 1867.4 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 604 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 87.195 | R.Ft | 45 | 100 | 98.09 | 0 | 3923.78 | C+S GST 18% I/P RD | 706.28 | 4630.06 | 4630.06 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 104 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 32.235 | R.Ft | 45 | 100 | 36.26 | 0 | 1450.58 | C+S GST 18% I/P RD | 261.1 | 1711.68 | 1711.68 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 503 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 45 | 100 | 39.56 | 0 | 1582.54 | C+S GST 18% I/P RD | 284.86 | 1867.4 | 1867.4 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 603 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 45 | 100 | 39.56 | 0 | 1582.54 | C+S GST 18% I/P RD | 284.86 | 1867.4 | 1867.4 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 604 Master Bed Marble Flooring | Italian Marble Champher & Polish | 43.065 | R.Ft | 45 | 100 | 48.45 | 0 | 1937.93 | C+S GST 18% I/P RD | 348.82 | 2286.75 | 2286.75 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 504 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 87.195 | R.Ft | 45 | 100 | 98.09 | 0 | 3923.78 | C+S GST 18% I/P RD | 706.28 | 4630.06 | 4630.06 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 203 Master Bed Marble Flooring | Italian Marble Champher & Polish | 35.1675 | R.Ft | 45 | 100 | 39.56 | 0 | 1582.54 | C+S GST 18% I/P RD | 284.86 | 1867.4 | 1867.4 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 204 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 87.195 | R.Ft | 45 | 100 | 98.09 | 0 | 3923.78 | C+S GST 18% I/P RD | 706.28 | 4630.06 | 4630.06 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 45 | 100 | 35.16 | 0 | 1406.36 | C+S GST 18% I/P RD | 253.14 | 1659.5 | 1659.5 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 45 | 100 | 85.68 | 0 | 3427.31 | C+S GST 18% I/P RD | 616.92 | 4044.23 | 4044.23 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 503 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 45 | 100 | 85.68 | 0 | 3427.31 | C+S GST 18% I/P RD | 616.92 | 4044.23 | 4044.23 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 104 Master Bed Marble Flooring | Italian Marble Champher & Polish | 43.065 | R.Ft | 45 | 100 | 48.45 | 0 | 1937.93 | C+S GST 18% I/P RD | 348.82 | 2286.75 | 2286.75 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 602 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 85.9425 | R.Ft | 45 | 100 | 96.69 | 0 | 3867.41 | C+S GST 18% I/P RD | 696.14 | 4563.55 | 4563.55 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 104 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 87.195 | R.Ft | 45 | 100 | 98.09 | 0 | 3923.78 | C+S GST 18% I/P RD | 706.28 | 4630.06 | 4630.06 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 204 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 32.235 | R.Ft | 45 | 100 | 36.26 | 0 | 1450.58 | C+S GST 18% I/P RD | 261.1 | 1711.68 | 1711.68 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 503 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 45 | 100 | 35.16 | 0 | 1406.36 | C+S GST 18% I/P RD | 253.14 | 1659.5 | 1659.5 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 203 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 45 | 100 | 85.68 | 0 | 3427.31 | C+S GST 18% I/P RD | 616.92 | 4044.23 | 4044.23 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 504 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 32.235 | R.Ft | 45 | 100 | 36.26 | 0 | 1450.58 | C+S GST 18% I/P RD | 261.1 | 1711.68 | 1711.68 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 603 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 45 | 100 | 85.68 | 0 | 3427.31 | C+S GST 18% I/P RD | 616.92 | 4044.23 | 4044.23 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 604 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 32.235 | R.Ft | 45 | 100 | 36.26 | 0 | 1450.58 | C+S GST 18% I/P RD | 261.1 | 1711.68 | 1711.68 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Master Bed Marble Flooring | Italian Marble Champher & Polish | 43.065 | R.Ft | 45 | 100 | 48.45 | 0 | 1937.93 | C+S GST 18% I/P RD | 348.82 | 2286.75 | 2286.75 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 602 Master Bed Marble Flooring | Italian Marble Champher & Polish | 50.175 | R.Ft | 45 | 100 | 56.45 | 0 | 2257.88 | C+S GST 18% I/P RD | 406.42 | 2664.3 | 2664.3 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 203 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 45 | 100 | 35.16 | 0 | 1406.36 | C+S GST 18% I/P RD | 253.14 | 1659.5 | 1659.5 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 87.195 | R.Ft | 45 | 100 | 98.09 | 0 | 3923.78 | C+S GST 18% I/P RD | 706.28 | 4630.06 | 4630.06 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1603 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 55 | 100 | 104.72 | 0 | 4188.94 | C+S GST 18% I/P RD | 754 | 4942.94 | 4942.94 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1704 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 87.195 | R.Ft | 55 | 100 | 119.89 | 0 | 4795.73 | C+S GST 18% I/P RD | 863.24 | 5658.97 | 5658.97 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1403 Guest Bed Marble Flooring | Italian Marble Champher & Polish | 31.2525 | R.Ft | 55 | 100 | 42.97 | 0 | 1718.89 | C+S GST 18% I/P RD | 309.4 | 2028.29 | 2028.29 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1702 Master Bed Marble Flooring | Italian Marble Champher & Polish | 50.175 | R.Ft | 55 | 100 | 68.99 | 0 | 2759.63 | C+S GST 18% I/P RD | 496.74 | 3256.37 | 3256.37 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1704 Parents Bed Marble Flooring | Italian Marble Champher & Polish | 32.235 | R.Ft | 55 | 100 | 44.32 | 0 | 1772.93 | C+S GST 18% I/P RD | 319.12 | 2092.05 | 2092.05 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1702 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 85.9425 | R.Ft | 55 | 100 | 118.17 | 0 | 4726.84 | C+S GST 18% I/P RD | 850.84 | 5577.68 | 5577.68 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1204 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 87.195 | R.Ft | 50 | 100 | 108.99 | 0 | 4359.75 | C+S GST 18% I/P RD | 784.76 | 5144.51 | 5144.51 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 703 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 76.1625 | R.Ft | 50 | 100 | 95.2 | 0 | 3808.13 | C+S GST 18% I/P RD | 685.46 | 4493.59 | 4493.59 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 704 Living,Dining,Passa. Marble Flooring | Italian Marble Champher & Polish | 87.195 | R.Ft | 50 | 100 | 108.99 | 0 | 4359.75 | C+S GST 18% I/P RD | 784.76 | 5144.51 | 5144.51 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 602 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 85.9425 | R.Ft | 35 | 100 | 75.2 | 0 | 3007.99 | C+S GST 18% I/P RD | 541.44 | 3549.43 | 3549.43 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 104 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 32.235 | R.Ft | 35 | 100 | 28.21 | 0 | 1128.23 | C+S GST 18% I/P RD | 203.08 | 1331.31 | 1331.31 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 203 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 35 | 100 | 66.64 | 0 | 2665.69 | C+S GST 18% I/P RD | 479.82 | 3145.51 | 3145.51 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 503 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 35 | 100 | 27.35 | 0 | 1093.84 | C+S GST 18% I/P RD | 196.9 | 1290.74 | 1290.74 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 604 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 32.235 | R.Ft | 35 | 100 | 28.21 | 0 | 1128.23 | C+S GST 18% I/P RD | 203.08 | 1331.31 | 1331.31 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 104 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 87.195 | R.Ft | 35 | 100 | 76.3 | 0 | 3051.83 | C+S GST 18% I/P RD | 549.32 | 3601.15 | 3601.15 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 203 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 35 | 100 | 27.35 | 0 | 1093.84 | C+S GST 18% I/P RD | 196.9 | 1290.74 | 1290.74 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 204 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 87.195 | R.Ft | 35 | 100 | 76.3 | 0 | 3051.83 | C+S GST 18% I/P RD | 549.32 | 3601.15 | 3601.15 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 503 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 35 | 100 | 66.64 | 0 | 2665.69 | C+S GST 18% I/P RD | 479.82 | 3145.51 | 3145.51 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 504 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 32.235 | R.Ft | 35 | 100 | 28.21 | 0 | 1128.23 | C+S GST 18% I/P RD | 203.08 | 1331.31 | 1331.31 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 503 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 35 | 100 | 30.77 | 0 | 1230.86 | C+S GST 18% I/P RD | 221.56 | 1452.42 | 1452.42 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 604 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 40 | R.Ft | 35 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 35 | 100 | 66.64 | 0 | 2665.69 | C+S GST 18% I/P RD | 479.82 | 3145.51 | 3145.51 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 35 | 100 | 30.77 | 0 | 1230.86 | C+S GST 18% I/P RD | 221.56 | 1452.42 | 1452.42 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 35 | 100 | 27.35 | 0 | 1093.84 | C+S GST 18% I/P RD | 196.9 | 1290.74 | 1290.74 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 504 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 87.195 | R.Ft | 35 | 100 | 76.3 | 0 | 3051.83 | C+S GST 18% I/P RD | 549.32 | 3601.15 | 3601.15 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 604 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 87.195 | R.Ft | 35 | 100 | 76.3 | 0 | 3051.83 | C+S GST 18% I/P RD | 549.32 | 3601.15 | 3601.15 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 30 | R.Ft | 35 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 32.235 | R.Ft | 35 | 100 | 28.21 | 0 | 1128.23 | C+S GST 18% I/P RD | 203.08 | 1331.31 | 1331.31 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 204 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 40 | R.Ft | 35 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 40 | R.Ft | 35 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 504 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 43.065 | R.Ft | 35 | 100 | 37.68 | 0 | 1507.28 | C+S GST 18% I/P RD | 271.32 | 1778.6 | 1778.6 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 603 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 35 | 100 | 27.35 | 0 | 1093.84 | C+S GST 18% I/P RD | 196.9 | 1290.74 | 1290.74 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 602 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 50.175 | R.Ft | 35 | 100 | 43.9 | 0 | 1756.13 | C+S GST 18% I/P RD | 316.1 | 2072.23 | 2072.23 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 204 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 43.065 | R.Ft | 35 | 100 | 37.68 | 0 | 1507.28 | C+S GST 18% I/P RD | 271.32 | 1778.6 | 1778.6 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 603 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 35 | 100 | 66.64 | 0 | 2665.69 | C+S GST 18% I/P RD | 479.82 | 3145.51 | 3145.51 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 104 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 43.065 | R.Ft | 35 | 100 | 37.68 | 0 | 1507.28 | C+S GST 18% I/P RD | 271.32 | 1778.6 | 1778.6 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 204 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 32.235 | R.Ft | 35 | 100 | 28.21 | 0 | 1128.23 | C+S GST 18% I/P RD | 203.08 | 1331.31 | 1331.31 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 87.195 | R.Ft | 35 | 100 | 76.3 | 0 | 3051.83 | C+S GST 18% I/P RD | 549.32 | 3601.15 | 3601.15 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 203 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 35 | 100 | 30.77 | 0 | 1230.86 | C+S GST 18% I/P RD | 221.56 | 1452.42 | 1452.42 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 43.065 | R.Ft | 35 | 100 | 37.68 | 0 | 1507.28 | C+S GST 18% I/P RD | 271.32 | 1778.6 | 1778.6 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 602 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 37.2525 | R.Ft | 35 | 100 | 32.6 | 0 | 1303.84 | C+S GST 18% I/P RD | 234.7 | 1538.54 | 1538.54 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 603 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 35 | 100 | 30.77 | 0 | 1230.86 | C+S GST 18% I/P RD | 221.56 | 1452.42 | 1452.42 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 604 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 43.065 | R.Ft | 35 | 100 | 37.68 | 0 | 1507.28 | C+S GST 18% I/P RD | 271.32 | 1778.6 | 1778.6 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 603 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 30 | R.Ft | 35 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1704 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 87.195 | R.Ft | 45 | 100 | 98.09 | 0 | 3923.78 | C+S GST 18% I/P RD | 706.28 | 4630.06 | 4630.06 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1704 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 32.235 | R.Ft | 45 | 100 | 36.26 | 0 | 1450.58 | C+S GST 18% I/P RD | 261.1 | 1711.68 | 1711.68 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1402 Master Bed Marble Flooring - 1 No. | Italian Marble Mirror Polish.- BCo | 50.175 | R.Ft | 45 | 100 | 56.45 | 0 | 2257.88 | C+S GST 18% I/P RD | 406.42 | 2664.3 | 2664.3 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 903 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 40 | 100 | 35.17 | 0 | 1406.7 | C+S GST 18% I/P RD | 253.2 | 1659.9 | 1659.9 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1003 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 40 | 100 | 76.16 | 0 | 3046.5 | C+S GST 18% I/P RD | 548.38 | 3594.88 | 3594.88 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1204 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 43.065 | R.Ft | 40 | 100 | 43.07 | 0 | 1722.6 | C+S GST 18% I/P RD | 310.06 | 2032.66 | 2032.66 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1204 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 32.235 | R.Ft | 40 | 100 | 32.24 | 0 | 1289.4 | C+S GST 18% I/P RD | 232.1 | 1521.5 | 1521.5 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1003 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 40 | 100 | 31.25 | 0 | 1250.1 | C+S GST 18% I/P RD | 225.02 | 1475.12 | 1475.12 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 903 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 30 | R.Ft | 40 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 903 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 40 | 100 | 76.16 | 0 | 3046.5 | C+S GST 18% I/P RD | 548.38 | 3594.88 | 3594.88 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1204 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 87.195 | R.Ft | 40 | 100 | 87.2 | 0 | 3487.8 | C+S GST 18% I/P RD | 627.8 | 4115.6 | 4115.6 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1204 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 40 | R.Ft | 40 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 703 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 30 | R.Ft | 40 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 902 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 37.2525 | R.Ft | 40 | 100 | 37.25 | 0 | 1490.1 | C+S GST 18% I/P RD | 268.22 | 1758.32 | 1758.32 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 704 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 43.065 | R.Ft | 40 | 100 | 43.07 | 0 | 1722.6 | C+S GST 18% I/P RD | 310.06 | 2032.66 | 2032.66 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 704 Toilet & Dry Balcony Devider Patti | Italian Marble Mirror Polish.- BCo | 40 | R.Ft | 40 | 100 | 40 | 0 | 1600 | C+S GST 18% I/P RD | 288 | 1888 | 1888 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 703 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 40 | 100 | 35.17 | 0 | 1406.7 | C+S GST 18% I/P RD | 253.2 | 1659.9 | 1659.9 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 703 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 40 | 100 | 31.25 | 0 | 1250.1 | C+S GST 18% I/P RD | 225.02 | 1475.12 | 1475.12 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 903 Guest Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 31.2525 | R.Ft | 40 | 100 | 31.25 | 0 | 1250.1 | C+S GST 18% I/P RD | 225.02 | 1475.12 | 1475.12 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 704 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 87.195 | R.Ft | 40 | 100 | 87.2 | 0 | 3487.8 | C+S GST 18% I/P RD | 627.8 | 4115.6 | 4115.6 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 704 Parents Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 32.235 | R.Ft | 40 | 100 | 32.24 | 0 | 1289.4 | C+S GST 18% I/P RD | 232.1 | 1521.5 | 1521.5 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 703 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 76.1625 | R.Ft | 40 | 100 | 76.16 | 0 | 3046.5 | C+S GST 18% I/P RD | 548.38 | 3594.88 | 3594.88 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 902 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 50.175 | R.Ft | 40 | 100 | 50.18 | 0 | 2007 | C+S GST 18% I/P RD | 361.26 | 2368.26 | 2368.26 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 902 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish.- BCo | 85.9425 | R.Ft | 40 | 100 | 85.94 | 0 | 3437.7 | C+S GST 18% I/P RD | 618.78 | 4056.48 | 4056.48 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 1003 Master Bed Marble Flooring | Italian Marble Mirror Polish.- BCo | 35.1675 | R.Ft | 40 | 100 | 35.17 | 0 | 1406.7 | C+S GST 18% I/P RD | 253.2 | 1659.9 | 1659.9 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 121.9975 | Sq.Ft | 35 | 100 | 106.75 | 0 | 4269.91 | C+S GST 18% I/P RD | 768.58 | 5038.49 | 5038.49 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Parents Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 37.9975 | Sq.Ft | 35 | 100 | 33.25 | 0 | 1329.91 | C+S GST 18% I/P RD | 239.38 | 1569.29 | 1569.29 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 50.08 | Sq.Ft | 35 | 100 | 43.82 | 0 | 1752.8 | C+S GST 18% I/P RD | 315.5 | 2068.3 | 2068.3 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Living,Dining,Passa. Marble Flooring | Italian Marble Mirror Polish- BCo | 147.7225 | Sq.Ft | 35 | 100 | 129.26 | 0 | 5170.29 | C+S GST 18% I/P RD | 930.66 | 6100.95 | 6100.95 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 404 Master Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 52.61 | Sq.Ft | 35 | 100 | 46.03 | 0 | 1841.35 | C+S GST 18% I/P RD | 331.44 | 2172.79 | 2172.79 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 641 | 90188 | 10 May 2021 |  | R K INTERIOR | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 273 | A 403 Guest Bed Marble Flooring | Italian Marble Mirror Polish- BCo | 36.02 | Sq.Ft | 35 | 100 | 31.52 | 0 | 1260.7 | C+S GST 18% I/P RD | 226.92 | 1487.62 | 1487.62 | Approved | 0 | 0 | 3221 | 10 May 2021
GANGA DHAM TOWERS | 395 | 90187 | 10 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 279 | A Bldg Flat No. 1803 Gypsum Plaster | Dhar Core (L) | 513.261 | R.Ft | 10 | 100 | 128.32 | 0 | 5132.61 | C+S GST 18% I/P RD | 923.86 | 6056.47 | 6056.47 | Approved | 0 | 0 | 416 | 10 May 2021
GANGA DHAM TOWERS | 395 | 90187 | 10 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 279 | A Bldg Flat No. 1804 Gypsum Plaster | Dhar Core (L) | 468.237 | R.Ft | 10 | 100 | 117.06 | 0 | 4682.37 | C+S GST 18% I/P RD | 842.82 | 5525.19 | 5525.19 | Approved | 0 | 0 | 416 | 10 May 2021
GANGA DHAM TOWERS | 395 | 90187 | 10 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 279 | A Bldg Flat No. 1604 Gypsum Plaster | Dhar Core (L) | 468.237 | R.Ft | 10 | 100 | 117.06 | 0 | 4682.37 | C+S GST 18% I/P RD | 842.82 | 5525.19 | 5525.19 | Approved | 0 | 0 | 416 | 10 May 2021
GANGA DHAM TOWERS | 395 | 90187 | 10 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 279 | A Bldg Flat No. 1804 Gypsum Plaster | Gypsum on Wall (L) | 2290 | Sq.Ft | 4 | 100 | 229 | 0 | 9160 | C+S GST 18% I/P RD | 1648.8 | 10808.8 | 10808.8 | Approved | 0 | 0 | 416 | 10 May 2021
GANGA DHAM TOWERS | 395 | 90187 | 10 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 279 | A Bldg Flat No. 1604 Gypsum Plaster | Gypsum on Wall (L) | 2290 | Sq.Ft | 4 | 100 | 229 | 0 | 9160 | C+S GST 18% I/P RD | 1648.8 | 10808.8 | 10808.8 | Approved | 0 | 0 | 416 | 10 May 2021
GANGA DHAM TOWERS | 395 | 90187 | 10 May 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 279 | A Bldg Flat No. 1803 Gypsum Plaster | Gypsum on Wall (L) | 2193 | Sq.Ft | 4 | 100 | 219.3 | 0 | 8772 | C+S GST 18% I/P RD | 1578.96 | 10350.96 | 10350.96 | Approved | 0 | 0 | 416 | 10 May 2021
GANGA DHAM TOWERS | 393 | 90186 | 10 May 2021 | 43 | J K INTERIOR | J K INTERIOR | EV - 554 | A Bldg Flat No. 1801 Gypsum Plaster | Gypsum on Wall (L) | 2300 | Sq.Ft | 4 | 100 | 230 | 0 | 9200 | C+S GST 18% I/P RD | 1656 | 10856 | 10856 | Approved | 0 | 0 | 286 | 10 May 2021
GANGA DHAM TOWERS | 393 | 90186 | 10 May 2021 | 43 | J K INTERIOR | J K INTERIOR | EV - 554 | A Bldg Flat No. 1802 Gypsum Plaster | Gypsum on Wall (L) | 2643 | Sq.Ft | 4 | 100 | 264.3 | 0 | 10572 | C+S GST 18% I/P RD | 1902.96 | 12474.96 | 12474.96 | Approved | 0 | 0 | 286 | 10 May 2021
GANGA DHAM TOWERS | 393 | 90186 | 10 May 2021 | 43 | J K INTERIOR | J K INTERIOR | EV - 554 | A Bldg Flat No. 1802 Gypsum Plaster | Dhar Core (L) | 450 | R.Ft | 10 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 286 | 10 May 2021
GANGA DHAM TOWERS | 393 | 90186 | 10 May 2021 | 43 | J K INTERIOR | J K INTERIOR | EV - 554 | A Bldg Flat No. 1801 Gypsum Plaster | Dhar Core (L) | 430 | R.Ft | 10 | 100 | 107.5 | 0 | 4300 | C+S GST 18% I/P RD | 774 | 5074 | 5074 | Approved | 0 | 0 | 286 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 902 Terrace Vitrified Flooring | Vitrified Flooring -BC | 110 | Sq.Ft | 20 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 901 Terrace Vitrified Flooring | Vitrified Flooring -BC | 110 | Sq.Ft | 20 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 1501 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.7 | Sq.Ft | 55 | 100 | 787.46 | 0 | 31498.5 | C+S GST 18% I/P RD | 5669.74 | 37168.24 | 37168.24 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 1501 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 210.97 | Sq.Ft | 55 | 100 | 290.08 | 0 | 11603.35 | C+S GST 18% I/P RD | 2088.6 | 13691.95 | 13691.95 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 1501 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 205.38 | Sq.Ft | 55 | 100 | 282.4 | 0 | 11295.9 | C+S GST 18% I/P RD | 2033.26 | 13329.16 | 13329.16 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 602 Terrace Vitrified Flooring | Vitrified Flooring -BC | 110 | Sq.Ft | 15 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 902 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 91.672 | R.Ft | 50 | 100 | 114.59 | 0 | 4583.6 | C+S GST 18% I/P RD | 825.04 | 5408.64 | 5408.64 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 902 Master Bed Marble Flooring | Italian marble Skirting - BCo | 53.52 | R.Ft | 50 | 100 | 66.9 | 0 | 2676 | C+S GST 18% I/P RD | 481.68 | 3157.68 | 3157.68 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 902 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 39.736 | R.Ft | 50 | 100 | 49.67 | 0 | 1986.8 | C+S GST 18% I/P RD | 357.62 | 2344.42 | 2344.42 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 902 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.65 | Sq.Ft | 50 | 100 | 263.31 | 0 | 10532.5 | C+S GST 18% I/P RD | 1895.86 | 12428.36 | 12428.36 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 902 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 50 | 100 | 716.01 | 0 | 28640.5 | C+S GST 18% I/P RD | 5155.3 | 33795.8 | 33795.8 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 902 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 50 | 100 | 228.06 | 0 | 9122.5 | C+S GST 18% I/P RD | 1642.06 | 10764.56 | 10764.56 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 1501 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 25 | Sq.Ft | 21 | 100 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 1402 Terrace Vitrified Flooring | Vitrified Flooring -BC | 110 | Sq.Ft | 24 | 100 | 66 | 0 | 2640 | C+S GST 18% I/P RD | 475.2 | 3115.2 | 3115.2 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 537 | 90183 | 10 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 275 | A 1501 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 129.472 | Sq.Ft | 24 | 100 | 77.68 | 0 | 3107.33 | C+S GST 18% I/P RD | 559.32 | 3666.65 | 3666.65 | Approved | 0 | 0 | 1243 | 10 May 2021
GANGA DHAM TOWERS | 258 | 90182 | 10 May 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 328 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.8336 | Month | 2500 | 100 | 0 | 0 | 2084 | CGST 0% URD I/P | 0 | 2084 | 2084 | Approved | 0 | 0 | 21 | 10 May 2021
GANGA DHAM TOWERS | 237 | 90181 | 10 May 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 354 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.8333 | Month | 7000 | 100 | 0 | 0 | 5833 | CGST 0% URD I/P | 0 | 5833 | 5833 | Approved | 0 | 0 | 58 | 10 May 2021
GANGA DHAM TOWERS | 350 | 90179 | 10 May 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 1073 | Site Expenses | Site Expenses -SO | 0.7867 | Month | 3000 | 100 | 0 | 0 | 2360 | CGST 0% URD I/P | 0 | 2360 | 2360 | Approved | 0 | 0 | 0 | 10 May 2021
GANGA DHAM TOWERS | 456 | 90162 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 174 | A Bldg External Plumbing Duct GI & PVC (L) | Duct Line | 2 | Flat | 2700 | 100 | 135 | 0 | 5400 | CGST 0% URD I/P | 0 | 5400 | 5400 | Approved | 0 | 0 | 54 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 405 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.23 | Per Flat | 4500 | 100 | 25.88 | 0 | 1035 | CGST 0% URD I/P | 0 | 1035 | 1035 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 205 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.23 | Per Flat | 4500 | 100 | 25.88 | 0 | 1035 | CGST 0% URD I/P | 0 | 1035 | 1035 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 501 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.23 | Per Flat | 4500 | 100 | 25.88 | 0 | 1035 | CGST 0% URD I/P | 0 | 1035 | 1035 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 401 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.23 | Per Flat | 4500 | 100 | 25.88 | 0 | 1035 | CGST 0% URD I/P | 0 | 1035 | 1035 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 305 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.23 | Per Flat | 4500 | 100 | 25.88 | 0 | 1035 | CGST 0% URD I/P | 0 | 1035 | 1035 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 505 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.23 | Per Flat | 4500 | 100 | 25.88 | 0 | 1035 | CGST 0% URD I/P | 0 | 1035 | 1035 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 101 (2bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.23 | Per Flat | 4500 | 100 | 25.88 | 0 | 1035 | CGST 0% URD I/P | 0 | 1035 | 1035 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 404 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 503 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 103 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 403 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 502 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 204 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 304 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 504 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 402 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 793 | 90159 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SUSHANT ENTERPRISES | EV - 178 | D 203 (1bhk) Int. PPRC,PVC | Int Plumbing PPRC Work | 0.2301 | Per Flat | 3060 | 100 | 17.6 | 0 | 704 | CGST 0% URD I/P | 0 | 704 | 704 | Approved | 0 | 0 | 143 | 08 May 2021
GANGA DHAM TOWERS | 654 | 90158 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 179 | D 201 Chemical Waterproofing | Chemical Waterproofing (M) | 93.51 | Sq.Ft | 15 | 100 | 0 | 0 | 1402.65 | CGST 0% URD I/P | 0 | 1402.65 | 1402.65 | Approved | 0 | 0 | 0 | 08 May 2021
GANGA DHAM TOWERS | 654 | 90158 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 179 | D 301 Chemical Waterproofing | Chemical Waterproofing (M) | 93.51 | Sq.Ft | 15 | 100 | 0 | 0 | 1402.65 | CGST 0% URD I/P | 0 | 1402.65 | 1402.65 | Approved | 0 | 0 | 0 | 08 May 2021
GANGA DHAM TOWERS | 654 | 90158 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 179 | D 305 Chemical Waterproofing | Chemical Waterproofing (M) | 93.51 | Sq.Ft | 15 | 100 | 0 | 0 | 1402.65 | CGST 0% URD I/P | 0 | 1402.65 | 1402.65 | Approved | 0 | 0 | 0 | 08 May 2021
GANGA DHAM TOWERS | 654 | 90158 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 179 | D 405 Chemical Waterproofing | Chemical Waterproofing (M) | 62.703 | Sq.Ft | 15 | 100 | 0 | 0 | 940.55 | CGST 0% URD I/P | 0 | 940.55 | 940.55 | Approved | 0 | 0 | 0 | 08 May 2021
GANGA DHAM TOWERS | 654 | 90158 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 179 | D 303 Chemical Waterproofing | Chemical Waterproofing (M) | 62.703 | Sq.Ft | 15 | 100 | 0 | 0 | 940.55 | CGST 0% URD I/P | 0 | 940.55 | 940.55 | Approved | 0 | 0 | 0 | 08 May 2021
GANGA DHAM TOWERS | 654 | 90158 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 179 | D 401 Chemical Waterproofing | Chemical Waterproofing (M) | 93.51 | Sq.Ft | 15 | 100 | 0 | 0 | 1402.65 | CGST 0% URD I/P | 0 | 1402.65 | 1402.65 | Approved | 0 | 0 | 0 | 08 May 2021
GANGA DHAM TOWERS | 654 | 90158 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 179 | D 202 Chemical Waterproofing | Chemical Waterproofing (M) | 89.514 | Sq.Ft | 15 | 100 | 0 | 0 | 1342.71 | CGST 0% URD I/P | 0 | 1342.71 | 1342.71 | Approved | 0 | 0 | 0 | 08 May 2021
GANGA DHAM TOWERS | 654 | 90158 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 179 | D 203 Chemical Waterproofing | Chemical Waterproofing (M) | 69.67 | Sq.Ft | 15 | 100 | 0 | 0 | 1045.05 | CGST 0% URD I/P | 0 | 1045.05 | 1045.05 | Approved | 0 | 0 | 0 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 201 Bore Packing | 5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 405 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 504 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 401 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 403 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 405 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 405 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 305 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 205 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 404 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 501 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 501 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 503 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 502 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 301 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 405 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 405 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 304 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 302 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 504 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 505 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 401 Bore Packing | 2.5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 204 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 203 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 303 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 505 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 402 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 403 Bore Packing | 2.5" Bore Packing | 1 | No. | 150 | 100 | 15 | 0 | 150 | CGST 0% URD I/P | 0 | 150 | 150 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 305 IPS Waterproofing | IPS W/P | 93.51 | Sq.Ft | 11 | 100 | 102.86 | 0 | 1028.61 | CGST 0% URD I/P | 0 | 1028.61 | 1028.61 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 204 IPS Waterproofing | IPS W/P | 62.703 | Sq.Ft | 11 | 100 | 68.97 | 0 | 689.73 | CGST 0% URD I/P | 0 | 689.73 | 689.73 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 303 IPS Waterproofing | IPS W/P | 62.703 | Sq.Ft | 11 | 100 | 68.97 | 0 | 689.73 | CGST 0% URD I/P | 0 | 689.73 | 689.73 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 404 IPS Waterproofing | IPS W/P | 62.703 | Sq.Ft | 11 | 100 | 68.97 | 0 | 689.73 | CGST 0% URD I/P | 0 | 689.73 | 689.73 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 301 IPS Waterproofing | IPS W/P | 93.51 | Sq.Ft | 11 | 100 | 102.86 | 0 | 1028.61 | CGST 0% URD I/P | 0 | 1028.61 | 1028.61 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 405 IPS Waterproofing | IPS W/P | 93.51 | Sq.Ft | 11 | 100 | 102.86 | 0 | 1028.61 | CGST 0% URD I/P | 0 | 1028.61 | 1028.61 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 401 IPS Waterproofing | IPS W/P | 93.51 | Sq.Ft | 11 | 100 | 102.86 | 0 | 1028.61 | CGST 0% URD I/P | 0 | 1028.61 | 1028.61 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 301 Chemical Waterproofing | Chemical Waterproofing (L) | 93.51 | Sq.Ft | 4 | 100 | 37.4 | 0 | 374.04 | CGST 0% URD I/P | 0 | 374.04 | 374.04 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 203 Chemical Waterproofing | Chemical Waterproofing (L) | 62.703 | Sq.Ft | 4 | 100 | 25.08 | 0 | 250.81 | CGST 0% URD I/P | 0 | 250.81 | 250.81 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 405 Chemical Waterproofing | Chemical Waterproofing (L) | 62.703 | Sq.Ft | 4 | 100 | 25.08 | 0 | 250.81 | CGST 0% URD I/P | 0 | 250.81 | 250.81 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 403 Chemical Waterproofing | Chemical Waterproofing (L) | 62.703 | Sq.Ft | 4 | 100 | 25.08 | 0 | 250.81 | CGST 0% URD I/P | 0 | 250.81 | 250.81 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 305 Chemical Waterproofing | Chemical Waterproofing (L) | 93.51 | Sq.Ft | 4 | 100 | 37.4 | 0 | 374.04 | CGST 0% URD I/P | 0 | 374.04 | 374.04 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 303 Chemical Waterproofing | Chemical Waterproofing (L) | 62.703 | Sq.Ft | 4 | 100 | 25.08 | 0 | 250.81 | CGST 0% URD I/P | 0 | 250.81 | 250.81 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 401 Chemical Waterproofing | Chemical Waterproofing (L) | 93.51 | Sq.Ft | 4 | 100 | 37.4 | 0 | 374.04 | CGST 0% URD I/P | 0 | 374.04 | 374.04 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D103 Chemical Grouting | Chemical Grouting.- BC | 347.76 | Sq.Ft | 1 | 100 | 34.78 | 0 | 347.76 | CGST 0% URD I/P | 0 | 347.76 | 347.76 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 302 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 202 Bore Packing | Perma Eazee Coat W/P (M+L) | 1 | No. | 70 | 100 | 7 | 0 | 70 | CGST 0% URD I/P | 0 | 70 | 70 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 205 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 403 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 203 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 304 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 401 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 201 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 305 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 402 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 502 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 402 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 404 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 303 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 304 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 501 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 503 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 301 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 204 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 302 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 305 Bore Packing | 5" Bore Packing | 4 | No. | 150 | 100 | 60 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 203 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 205 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 505 Bore Packing | 5" Bore Packing | 2 | No. | 150 | 100 | 30 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 301 Bore Packing | Perma Eazee Coat W/P (M+L) | 6 | No. | 70 | 100 | 42 | 0 | 420 | CGST 0% URD I/P | 0 | 420 | 420 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 204 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 404 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 653 | 90157 | 08 May 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 180 | D 303 Bore Packing | Perma Eazee Coat W/P (M+L) | 3 | No. | 70 | 100 | 21 | 0 | 210 | CGST 0% URD I/P | 0 | 210 | 210 | Approved | 0 | 0 | 232 | 08 May 2021
GANGA DHAM TOWERS | 932 | 90155 | 08 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 185 | Podium P1 RCC Slab Pumping Charges | Pumping Charges-BC | 420.85 | Cu.Mtrs | 190 | 100 | 0 | 0 | 79961.5 | C+S GST 18% I/P RD | 14393.08 | 94354.58 | 94354.58 | Approved | 0 | 0 | 2082 | 08 May 2021
GANGA DHAM TOWERS | 932 | 90155 | 08 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 185 | Podium P2 RCC Slab Pumping Charges | Pumping Charges-BC | 127 | Cu.Mtrs | 190 | 100 | 0 | 0 | 24130 | C+S GST 18% I/P RD | 4343.4 | 28473.4 | 28473.4 | Approved | 0 | 0 | 2082 | 08 May 2021
GANGA DHAM TOWERS | 931 | 90154 | 08 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 182 | C Building RCC Plinth Beam Pumping Charges | Pumping Charges-BC | 39.95 | Cu.Mtrs | 190 | 100 | 0 | 0 | 7590.5 | C+S GST 18% I/P RD | 1366.3 | 8956.8 | 8956.8 | Approved | 0 | 0 | 338 | 08 May 2021
GANGA DHAM TOWERS | 931 | 90154 | 08 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 182 | C RCC Shear Wall Pumping Charges Up to 105 level - - 386. | Pumping Charges-BC | 37 | Cu.Mtrs | 190 | 100 | 0 | 0 | 7030 | C+S GST 18% I/P RD | 1265.4 | 8295.4 | 8295.4 | Approved | 0 | 0 | 338 | 08 May 2021
GANGA DHAM TOWERS | 931 | 90154 | 08 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 182 | C Building Grade Slab Pumping Charges | Pumping Charges-BC | 12 | Cu.Mtrs | 190 | 100 | 0 | 0 | 2280 | C+S GST 18% I/P RD | 410.4 | 2690.4 | 2690.4 | Approved | 0 | 0 | 338 | 08 May 2021
GANGA DHAM TOWERS | 401 | 90153 | 08 May 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 210 | A 1502 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 30 | 08 May 2021
GANGA DHAM TOWERS | 401 | 90153 | 08 May 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 210 | A 1502 Chemical Grouting Work | Chemical Grouting.- BC | 1487.14 | Sq.Ft | 1 | 100 | 148.71 | 0 | 1487.14 | CGST 0% URD I/P | 0 | 1487.14 | 1487.14 | Approved | 0 | 0 | 30 | 08 May 2021
GANGA DHAM TOWERS | 522 | 90152 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 175 | B Bldg 701 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1250 | 100 | 218.75 | 0 | 8750 | CGST 0% URD I/P | 0 | 8750 | 8750 | Approved | 0 | 0 | 88 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1801 Chemical Grouting | Chemical Grouting.- BC | 2561.94 | Sq.Ft | 2 | 100 | 512.39 | 0 | 5123.88 | CGST 0% URD I/P | 0 | 5123.88 | 5123.88 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1401 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 31 | No. | 70 | 100 | 217 | 0 | 2170 | CGST 0% URD I/P | 0 | 2170 | 2170 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1501 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 31 | No. | 70 | 100 | 217 | 0 | 2170 | CGST 0% URD I/P | 0 | 2170 | 2170 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1301 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 31 | No. | 70 | 100 | 217 | 0 | 2170 | CGST 0% URD I/P | 0 | 2170 | 2170 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1501 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1401 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1301 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1301 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1401 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1501 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1301 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1501 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 701 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1401 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1501 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 581.79 | Sq.Ft | 19 | 100 | 1105.4 | 0 | 11054.01 | CGST 0% URD I/P | 0 | 11054.01 | 11054.01 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1401 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 581.79 | Sq.Ft | 19 | 100 | 1105.4 | 0 | 11054.01 | CGST 0% URD I/P | 0 | 11054.01 | 11054.01 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1301 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 581.79 | Sq.Ft | 19 | 100 | 1105.4 | 0 | 11054.01 | CGST 0% URD I/P | 0 | 11054.01 | 11054.01 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 498 | 90151 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 176 | B 1301 Chemical & IPS Waterproofing | IPS W/P | 581.79 | Sq.Ft | 11 | 100 | 639.97 | 0 | 6399.69 | CGST 0% URD I/P | 0 | 6399.69 | 6399.69 | Approved | 0 | 0 | 663 | 08 May 2021
GANGA DHAM TOWERS | 455 | 90150 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 177 | A Bldg Flat No. 503 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 205 | 08 May 2021
GANGA DHAM TOWERS | 455 | 90150 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 177 | A Bldg Flat No. 504 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2 | No. | 1000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 205 | 08 May 2021
GANGA DHAM TOWERS | 455 | 90150 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 177 | A Bldg Flat No. 603 Internal Plumbing PPR-C | Int Flat PPRC Work. | 3.3 | No. | 1000 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 205 | 08 May 2021
GANGA DHAM TOWERS | 455 | 90150 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 177 | A Bldg Flat No. 602 Internal Plumbing PPR-C | Int Flat PPRC Work. | 3.3 | No. | 1000 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 205 | 08 May 2021
GANGA DHAM TOWERS | 455 | 90150 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 177 | A Bldg Flat No. 1403 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.3571 | No. | 1400 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 205 | 08 May 2021
GANGA DHAM TOWERS | 455 | 90150 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 177 | A Bldg Flat No. 1002 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.75 | No. | 1200 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 205 | 08 May 2021
GANGA DHAM TOWERS | 455 | 90150 | 08 May 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 177 | A Bldg Flat No. 1001 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.75 | No. | 1200 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 205 | 08 May 2021
GANGA DHAM TOWERS | 186 | 90129 | 07 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 202 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 117 | Day | 500 | 100 | 0 | 0 | 58500 | C+S GST 18% I/P RD | 10530 | 69030 | 69030 | Approved | 0 | 0 | 1573 | 07 May 2021
GANGA DHAM TOWERS | 186 | 90129 | 07 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 202 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 31 | Day | 580.645 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 1573 | 07 May 2021
GANGA DHAM TOWERS | 186 | 90129 | 07 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 202 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 138.9995 | Day | 451.613 | 100 | 0 | 0 | 62774 | C+S GST 18% I/P RD | 11299.32 | 74073.32 | 74073.32 | Approved | 0 | 0 | 1573 | 07 May 2021
GANGA DHAM TOWERS | 186 | 90129 | 07 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 202 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 28 | Day | 642.85 | 100 | 0 | 0 | 17999.8 | C+S GST 18% I/P RD | 3239.96 | 21239.76 | 21239.76 | Approved | 0 | 0 | 1573 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Parents Toilet dado | Dado BC | 106.764 | Sq.Ft | 22 | 100 | 58.72 | 0 | 2348.81 | C+S GST 18% I/P RD | 422.78 | 2771.59 | 2771.59 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Powder Toilet dado | Dado BC | 66.675 | Sq.Ft | 22 | 100 | 36.67 | 0 | 1466.85 | C+S GST 18% I/P RD | 264.04 | 1730.89 | 1730.89 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Master Toilet dado | Dado BC | 86.457 | Sq.Ft | 22 | 100 | 47.55 | 0 | 1902.05 | C+S GST 18% I/P RD | 342.36 | 2244.41 | 2244.41 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Children Toilet Dado | Dado BC | 131.901 | Sq.Ft | 22 | 100 | 72.55 | 0 | 2901.82 | C+S GST 18% I/P RD | 522.32 | 3424.14 | 3424.14 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 602 Powder Toilet dado | Dado BC | 34.36 | Sq.Ft | 15 | 100 | 12.89 | 0 | 515.4 | C+S GST 18% I/P RD | 92.78 | 608.18 | 608.18 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 602 Master Toilet dado | Dado BC | 54.224 | Sq.Ft | 15 | 100 | 20.33 | 0 | 813.36 | C+S GST 18% I/P RD | 146.4 | 959.76 | 959.76 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 602 Parents Toilet dado | Dado BC | 65.4 | Sq.Ft | 15 | 100 | 24.53 | 0 | 981 | C+S GST 18% I/P RD | 176.58 | 1157.58 | 1157.58 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 602 Children Toilet | Dado BC | 34.176 | Sq.Ft | 15 | 100 | 12.82 | 0 | 512.64 | C+S GST 18% I/P RD | 92.28 | 604.92 | 604.92 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Powder Toilet dado | Dado BC | 34.36 | Sq.Ft | 24 | 100 | 20.62 | 0 | 824.64 | C+S GST 18% I/P RD | 148.44 | 973.08 | 973.08 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Parents Toilet dado | Dado BC | 65.4 | Sq.Ft | 24 | 100 | 39.24 | 0 | 1569.6 | C+S GST 18% I/P RD | 282.52 | 1852.12 | 1852.12 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Master Toilet dado | Dado BC | 54.224 | Sq.Ft | 24 | 100 | 32.53 | 0 | 1301.38 | C+S GST 18% I/P RD | 234.24 | 1535.62 | 1535.62 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Children Toilet Dado | Dado BC | 34.176 | Sq.Ft | 24 | 100 | 20.51 | 0 | 820.22 | C+S GST 18% I/P RD | 147.64 | 967.86 | 967.86 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Children Toilet Dado | L Groove - BCV | 22.729 | R.Ft | 20 | 100 | 11.36 | 0 | 454.58 | C+S GST 18% I/P RD | 81.82 | 536.4 | 536.4 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Parents Toilet dado | L Groove - BCV | 28.357 | R.Ft | 20 | 100 | 14.18 | 0 | 567.14 | C+S GST 18% I/P RD | 102.08 | 669.22 | 669.22 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Powder Toilet dado | L Groove - BCV | 22.729 | R.Ft | 20 | 100 | 11.36 | 0 | 454.58 | C+S GST 18% I/P RD | 81.82 | 536.4 | 536.4 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 1402 Master Toilet dado | L Groove - BCV | 19.355 | R.Ft | 20 | 100 | 9.68 | 0 | 387.1 | C+S GST 18% I/P RD | 69.68 | 456.78 | 456.78 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 602 Children Toilet | Dado BC | 131.901 | Sq.Ft | 14 | 100 | 46.17 | 0 | 1846.61 | C+S GST 18% I/P RD | 332.38 | 2178.99 | 2178.99 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 602 Powder Toilet dado | Dado BC | 66.675 | Sq.Ft | 14 | 100 | 23.34 | 0 | 933.45 | C+S GST 18% I/P RD | 168.02 | 1101.47 | 1101.47 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 602 Parents Toilet dado | Dado BC | 106.764 | Sq.Ft | 14 | 100 | 37.37 | 0 | 1494.7 | C+S GST 18% I/P RD | 269.04 | 1763.74 | 1763.74 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 537 | 90128 | 07 May 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 203 | A 602 Master Toilet dado | Dado BC | 86.457 | Sq.Ft | 14 | 100 | 30.26 | 0 | 1210.4 | C+S GST 18% I/P RD | 217.88 | 1428.28 | 1428.28 | Approved | 0 | 0 | 233 | 07 May 2021
GANGA DHAM TOWERS | 931 | 90101 | 05 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 183 | C RCC Shear Wall Pumping Charges Up to 105 level - - 386. | Pumping Charges-BC | 110 | Cu.Mtrs | 190 | 100 | 0 | 0 | 20900 | C+S GST 18% I/P RD | 3762 | 24662 | 24662 | Approved | 0 | 0 | 418 | 05 May 2021
GANGA DHAM TOWERS | 930 | 90100 | 05 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 186 | EWS Bldg LMR, OHWT, Parapet Pumping Charges | Pumping Charges-BC | 52.31 | Cu.Mtrs | 190 | 100 | 0 | 0 | 9938.9 | C+S GST 18% I/P RD | 1789 | 11727.9 | 11727.9 | Approved | 0 | 0 | 199 | 05 May 2021
GANGA DHAM TOWERS | 929 | 90099 | 05 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 184 | B Bldg Terrace Parapet Work Pumping Charges - 52 Cu.Mtrs | Pumping Charges-BC | 52 | Cu.Mtrs | 190 | 100 | 0 | 0 | 9880 | C+S GST 18% I/P RD | 1778.4 | 11658.4 | 11658.4 | Approved | 0 | 0 | 574 | 05 May 2021
GANGA DHAM TOWERS | 929 | 90099 | 05 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 184 | B Bldg 32nd Slab Pumping Charges | Pumping Charges-BC | 99 | Cu.Mtrs | 190 | 100 | 0 | 0 | 18810 | C+S GST 18% I/P RD | 3385.8 | 22195.8 | 22195.8 | Approved | 0 | 0 | 574 | 05 May 2021
GANGA DHAM TOWERS | 928 | 90098 | 05 May 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 181 | A Bldg, Terrace Parapet Work Pumping Charges - 52 Cu.Mtrs | Pumping Charges-BC | 52 | Cu.Mtrs | 190 | 100 | 0 | 0 | 9880 | C+S GST 18% I/P RD | 1778.4 | 11658.4 | 11658.4 | Approved | 0 | 0 | 198 | 05 May 2021
GANGA DHAM TOWERS | 1037 | 90097 | 05 May 2021 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 173 | Head Office Security Service | Security Guard AIE - | 60 | Day | 433.33 | 100 | 0 | 0 | 25999.8 | C+S GST 18% RCM | 4679.96 | 30679.76 | 30679.76 | Approved | 0 | 0 | 260 | 05 May 2021
GANGA DHAM TOWERS | 940 | 90068 | 03 May 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 164 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 03 May 2021
GANGA DHAM TOWERS | 745 | 90067 | 03 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 161 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 26.5011 | Day | 466.66 | 100 | 0 | 0 | 12367 | C+S GST 18% I/P RD | 2226.06 | 14593.06 | 14593.06 | Approved | 0 | 0 | 124 | 03 May 2021
GANGA DHAM TOWERS | 480 | 90066 | 03 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 160 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 26.5011 | Day | 466.66 | 100 | 0 | 0 | 12367 | C+S GST 18% I/P RD | 2226.06 | 14593.06 | 14593.06 | Approved | 0 | 0 | 124 | 03 May 2021
GANGA DHAM TOWERS | 186 | 90065 | 03 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 158 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 128.9997 | Day | 466.66 | 100 | 0 | 0 | 60199 | C+S GST 18% I/P RD | 10835.82 | 71034.82 | 71034.82 | Approved | 0 | 0 | 602 | 03 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Premium Emulsion(m+l) - Mkt | 4914.32 | Sq.Ft | 18 | 100 | 2211.44 | 0 | 88457.76 | C+S GST 18% I/P RD | 15922.4 | 104380.16 | 104380.16 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Wall Paper Base | 1231.86 | Sq.Ft | 12 | 100 | 369.56 | 0 | 14782.32 | C+S GST 18% I/P RD | 2660.82 | 17443.14 | 17443.14 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Panel Light | 48 | No. | 250 | 100 | 300 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Speaker Cover | 6 | No. | 250 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Melamine Polish Patta- BC (m+l) | 3471.11 | R.Ft | 25 | 100 | 2169.44 | 0 | 86777.75 | C+S GST 18% I/P RD | 15620 | 102397.75 | 102397.75 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Duco Paint (M+L) | 4 | No. | 800 | 100 | 80 | 0 | 3200 | C+S GST 18% I/P RD | 576 | 3776 | 3776 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Panel Light | 35 | No. | 150 | 100 | 131.25 | 0 | 5250 | C+S GST 18% I/P RD | 945 | 6195 | 6195 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Melamine Polish- BC (m+l) | 2107.71 | Sq.Ft | 75 | 100 | 3951.96 | 0 | 158078.25 | C+S GST 18% I/P RD | 28454.08 | 186532.33 | 186532.33 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1025 | 90064 | 01 May 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 268 | Club House Internal Painting Work | Duco Paint (M+L) | 8 | No. | 1200 | 100 | 240 | 0 | 9600 | C+S GST 18% I/P RD | 1728 | 11328 | 11328 | Approved | 0 | 0 | 3796 | 01 May 2021
GANGA DHAM TOWERS | 1011 | 90063 | 01 May 2021 |  | REVANTI FURNITURE | REVANTI FURNITURE | EV - 357 | Club House Glass / Carpentary Shifting Work | Dismentalling work-UTI | 0.8 | No. | 61000 | 100 | 0 | 0 | 48800 | CGST 0% URD I/P | 0 | 48800 | 48800 | Approved | 0 | 0 | 488 | 01 May 2021
GANGA DHAM TOWERS | 413 | 90061 | 01 May 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 334 | Sales Oiifce Landscape Area . | Supervision Charges | 0.5 | Month | 4000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 20 | 01 May 2021
GANGA DHAM TOWERS | 187 | 90060 | 01 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 163 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 01 May 2021
GANGA DHAM TOWERS | 186 | 90059 | 01 May 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 159 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 30 | Day | 600 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 180 | 01 May 2021
GANGA DHAM TOWERS | 179 | 90058 | 01 May 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 336 | Road Divider Garden Maintenance | Garden work. | 27.9994 | Day | 420.83 | 100 | 0 | 0 | 11783 | C+S GST 18% I/P RD | 2120.94 | 13903.94 | 13903.94 | Approved | 0 | 0 | 118 | 01 May 2021
GANGA DHAM TOWERS | 178 | 90057 | 01 May 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 335 | Sales Oiifce Landscape Area . | Garden work. | 51.9996 | Day | 420.83 | 100 | 0 | 0 | 21883 | C+S GST 18% I/P RD | 3938.94 | 25821.94 | 25821.94 | Approved | 0 | 0 | 219 | 01 May 2021
GANGA DHAM TOWERS | 237 | 90051 | 30 Apr 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 172 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.8386 | Month | 7000 | 100 | 0 | 0 | 5870 | CGST 0% URD I/P | 0 | 5870 | 5870 | Approved | 0 | 0 | 59 | 30 Apr 2021
GANGA DHAM TOWERS | 258 | 90050 | 30 Apr 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 171 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.8384 | Month | 2500 | 100 | 0 | 0 | 2096 | CGST 0% URD I/P | 0 | 2096 | 2096 | Approved | 0 | 0 | 21 | 30 Apr 2021
GANGA DHAM TOWERS | 796 | 90042 | 29 Apr 2021 |  | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 604 | D Main St.case Wall Gyp. Plaster 2nd to 3rd Fl. | Tikki Dhada (M) | 418 | Sq.Ft | 9 | 100 | 0 | 0 | 3762 | C+S GST 5% I/P RD | 188.1 | 3950.1 | 3950.1 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 796 | 90042 | 29 Apr 2021 |  | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 604 | D Fire St.case Wall Gyp. Plaster 1st to 2nd Fl. | Tikki Dhada (M) | 404 | Sq.Ft | 9 | 100 | 0 | 0 | 3636 | C+S GST 5% I/P RD | 181.8 | 3817.8 | 3817.8 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 796 | 90042 | 29 Apr 2021 |  | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 604 | D Main St.case Wall Gyp. Plaster 5th to 6th Fl. | Tikki Dhada (M) | 418 | Sq.Ft | 9 | 100 | 0 | 0 | 3762 | C+S GST 5% I/P RD | 188.1 | 3950.1 | 3950.1 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 796 | 90042 | 29 Apr 2021 |  | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 604 | D Fire St.case Wall Gyp. Plaster 3rd to 4th Fl. | Tikki Dhada (M) | 320.7778 | Sq.Ft | 9 | 100 | 0 | 0 | 2887 | C+S GST 5% I/P RD | 144.36 | 3031.36 | 3031.36 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 796 | 90042 | 29 Apr 2021 |  | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 604 | D Main St.case Wall Gyp. Plaster 1st to 2nd Fl. | Tikki Dhada (M) | 418 | Sq.Ft | 9 | 100 | 0 | 0 | 3762 | C+S GST 5% I/P RD | 188.1 | 3950.1 | 3950.1 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 796 | 90042 | 29 Apr 2021 |  | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 604 | D Main St.case Wall Gyp. Plaster 3rd to 4th Fl. | Tikki Dhada (M) | 418 | Sq.Ft | 9 | 100 | 0 | 0 | 3762 | C+S GST 5% I/P RD | 188.1 | 3950.1 | 3950.1 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 796 | 90042 | 29 Apr 2021 |  | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 604 | D Main St.case Wall Gyp. Plaster 4th to 5th Fl. | Tikki Dhada (M) | 418 | Sq.Ft | 9 | 100 | 0 | 0 | 3762 | C+S GST 5% I/P RD | 188.1 | 3950.1 | 3950.1 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 796 | 90042 | 29 Apr 2021 |  | J K INTERIOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 604 | D Fire St.case Wall Gyp. Plaster 2nd to 3rd Fl. | Tikki Dhada (M) | 404 | Sq.Ft | 9 | 100 | 0 | 0 | 3636 | C+S GST 5% I/P RD | 181.8 | 3817.8 | 3817.8 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 988 | 90040 | 29 Apr 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 327 | DA Development Top Terrace Painting Work | Texture+Acrylic Paint | 660 | Sq.Ft | 45 | 100 | 742.5 | 0 | 29700 | C+S GST 18% I/P RD | 5346 | 35046 | 35046 | Approved | 0 | 0 | 297 | 29 Apr 2021
GANGA DHAM TOWERS | 697 | 90039 | 29 Apr 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 605 | D 901 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145 | Sq.Ft | 9 | 100 | 0 | 0 | 10305 | C+S GST 5% I/P RD | 515.26 | 10820.26 | 10820.26 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 697 | 90039 | 29 Apr 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 605 | D 801 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145 | Sq.Ft | 9 | 100 | 0 | 0 | 10305 | C+S GST 5% I/P RD | 515.26 | 10820.26 | 10820.26 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 697 | 90039 | 29 Apr 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 605 | D 701 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 1145 | Sq.Ft | 9 | 100 | 0 | 0 | 10305 | C+S GST 5% I/P RD | 515.26 | 10820.26 | 10820.26 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 697 | 90039 | 29 Apr 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 605 | D 902 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 971.4444 | Sq.Ft | 9 | 100 | 0 | 0 | 8743 | C+S GST 5% I/P RD | 437.16 | 9180.16 | 9180.16 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 697 | 90039 | 29 Apr 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | SEVEN STAR GYPSUM | EV - 605 | D 702 Ceiling & Wall Gypsum Plaster | Tikki Dhada (M) | 979 | Sq.Ft | 9 | 100 | 0 | 0 | 8811 | C+S GST 5% I/P RD | 440.56 | 9251.56 | 9251.56 | Approved | 0 | 0 | 0 | 29 Apr 2021
GANGA DHAM TOWERS | 678 | 90038 | 29 Apr 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 413 | A 804 NOC | Concrete Cutting Work | 14.66 | R.Ft | 525 | 100 | 192.41 | 0 | 7696.5 | C+S GST 18% I/P RD | 1385.38 | 9081.88 | 9081.88 | Approved | 0 | 0 | 178 | 29 Apr 2021
GANGA DHAM TOWERS | 678 | 90038 | 29 Apr 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 413 | A 804 NOC | Concrete wall Crushing work | 0.165 | Cu.Mtrs | 7200 | 100 | 29.7 | 0 | 1188 | C+S GST 18% I/P RD | 213.84 | 1401.84 | 1401.84 | Approved | 0 | 0 | 178 | 29 Apr 2021
GANGA DHAM TOWERS | 497 | 90037 | 29 Apr 2021 | 44 | J K INTERIOR | J K INTERIOR | EV - 556 | B 2002 Gypsum Plaster | Gypsum on Wall (L) | 3581 | Sq.Ft | 4 | 100 | 358.1 | 0 | 14324 | C+S GST 18% I/P RD | 2578.32 | 16902.32 | 16902.32 | Approved | 0 | 0 | 193 | 29 Apr 2021
GANGA DHAM TOWERS | 497 | 90037 | 29 Apr 2021 | 44 | J K INTERIOR | J K INTERIOR | EV - 556 | B 2002 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 193 | 29 Apr 2021
GANGA DHAM TOWERS | 461 | 90036 | 29 Apr 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 276 | DA DevelopmentTop Terrace Misc items | Rabit Shifting Work | 10 | No. | 450 | 100 | 0 | 0 | 4500 | CGST 0% URD I/P | 0 | 4500 | 4500 | Approved | 0 | 0 | 45 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 35 | 147 | 0 | 5880 | C+S GST 18% I/P RD | 1058.4 | 6938.4 | 6938.4 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 35 | 92.75 | 0 | 3710 | C+S GST 18% I/P RD | 667.8 | 4377.8 | 4377.8 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | Fan Point | 9 | No. | 200 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 35 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 35 | 8.79 | 0 | 351.75 | C+S GST 18% I/P RD | 63.32 | 415.07 | 415.07 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 35 | 7.62 | 0 | 304.85 | C+S GST 18% I/P RD | 54.88 | 359.73 | 359.73 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | Data Point | 4 | No. | 220 | 35 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 35 | 138.25 | 0 | 5530 | C+S GST 18% I/P RD | 995.4 | 6525.4 | 6525.4 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 35 | 89.25 | 0 | 3570 | C+S GST 18% I/P RD | 642.6 | 4212.6 | 4212.6 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 35 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 35 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1300 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1400 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 35 | 25.21 | 0 | 1008.35 | C+S GST 18% I/P RD | 181.5 | 1189.85 | 1189.85 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 35 | 32.24 | 0 | 1289.75 | C+S GST 18% I/P RD | 232.16 | 1521.91 | 1521.91 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2602 Internal Electrical Work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 399 | 90035 | 29 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 271 | B Bldg Flat No. 2601 Internal Electrical Work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 587 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | Secondary Light Points (Looping) | 44 | No. | 100 | 35 | 38.5 | 0 | 1540 | C+S GST 18% I/P RD | 277.2 | 1817.2 | 1817.2 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | Secondary Light Points (Looping) | 38 | No. | 100 | 35 | 33.25 | 0 | 1330 | C+S GST 18% I/P RD | 239.4 | 1569.4 | 1569.4 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | Secondary Light Points (Looping) | 42 | No. | 100 | 35 | 36.75 | 0 | 1470 | C+S GST 18% I/P RD | 264.6 | 1734.6 | 1734.6 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | Secondary Light Points (Looping) | 39 | No. | 100 | 35 | 34.13 | 0 | 1365 | C+S GST 18% I/P RD | 245.7 | 1610.7 | 1610.7 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | Fan Point | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | Fan Point | 7 | No. | 250 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 39 | No. | 250 | 35 | 85.31 | 0 | 3412.5 | C+S GST 18% I/P RD | 614.26 | 4026.76 | 4026.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 40 | No. | 250 | 35 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2603 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2601 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2604 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90034 | 29 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 270 | A Bldg Flat No.-2602 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1153 | 29 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Data Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Data Point | 2.25 | No. | 350 | 25 | 4.92 | 0 | 196.88 | C+S GST 18% I/P RD | 35.44 | 232.32 | 232.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Data Point | 0.5 | No. | 350 | 25 | 1.09 | 0 | 43.75 | C+S GST 18% I/P RD | 7.88 | 51.63 | 51.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Data Point | 1.5 | No. | 350 | 25 | 3.28 | 0 | 131.25 | C+S GST 18% I/P RD | 23.62 | 154.87 | 154.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Data Point | 1 | No. | 350 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Data Point | 3 | No. | 350 | 25 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Data Point | 3 | No. | 350 | 25 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Data Point | 1 | No. | 350 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Data Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Data Point | 2.25 | No. | 350 | 25 | 4.92 | 0 | 196.88 | C+S GST 18% I/P RD | 35.44 | 232.32 | 232.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Data Point | 0.5 | No. | 350 | 25 | 1.09 | 0 | 43.75 | C+S GST 18% I/P RD | 7.88 | 51.63 | 51.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Data Point | 1.5 | No. | 350 | 25 | 3.28 | 0 | 131.25 | C+S GST 18% I/P RD | 23.62 | 154.87 | 154.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Data Point | 1 | No. | 350 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Data Point | 3 | No. | 350 | 25 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Data Point | 1.25 | No. | 350 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Data Point | 3.75 | No. | 350 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Data Point | 2.25 | No. | 350 | 30 | 5.91 | 0 | 236.25 | C+S GST 18% I/P RD | 42.52 | 278.77 | 278.77 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Data Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Data Point | 2.25 | No. | 350 | 25 | 4.92 | 0 | 196.88 | C+S GST 18% I/P RD | 35.44 | 232.32 | 232.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Data Point | 3.75 | No. | 350 | 30 | 9.84 | 0 | 393.75 | C+S GST 18% I/P RD | 70.88 | 464.63 | 464.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Data Point | 1 | No. | 350 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Data Point | 3 | No. | 350 | 25 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Data Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Data Point | 2.25 | No. | 350 | 25 | 4.92 | 0 | 196.88 | C+S GST 18% I/P RD | 35.44 | 232.32 | 232.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Data Point | 1.25 | No. | 350 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Data Point | 3.75 | No. | 350 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Data Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Data Point | 2.25 | No. | 350 | 25 | 4.92 | 0 | 196.88 | C+S GST 18% I/P RD | 35.44 | 232.32 | 232.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Data Point | 2.25 | No. | 350 | 25 | 4.92 | 0 | 196.88 | C+S GST 18% I/P RD | 35.44 | 232.32 | 232.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Data Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 6 AMP Plug point (Independent) | 5 | No. | 250 | 25 | 7.81 | 0 | 312.5 | C+S GST 18% I/P RD | 56.26 | 368.76 | 368.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 6 AMP Plug point (Independent) | 15 | No. | 250 | 25 | 23.44 | 0 | 937.5 | C+S GST 18% I/P RD | 168.76 | 1106.26 | 1106.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 4.25 | No. | 250 | 25 | 6.64 | 0 | 265.63 | C+S GST 18% I/P RD | 47.82 | 313.45 | 313.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 12.75 | No. | 250 | 25 | 19.92 | 0 | 796.88 | C+S GST 18% I/P RD | 143.44 | 940.32 | 940.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | 6 AMP Plug point (Independent) | 7.5 | No. | 250 | 25 | 11.72 | 0 | 468.75 | C+S GST 18% I/P RD | 84.38 | 553.13 | 553.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | 6 AMP Plug point (Independent) | 7.5 | No. | 250 | 25 | 11.72 | 0 | 468.75 | C+S GST 18% I/P RD | 84.38 | 553.13 | 553.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Independent) | 4.25 | No. | 250 | 25 | 6.64 | 0 | 265.63 | C+S GST 18% I/P RD | 47.82 | 313.45 | 313.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Independent) | 12.75 | No. | 250 | 25 | 19.92 | 0 | 796.88 | C+S GST 18% I/P RD | 143.44 | 940.32 | 940.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Exhaust Fan Point | 1.5 | No. | 225 | 25 | 2.11 | 0 | 84.38 | C+S GST 18% I/P RD | 15.18 | 99.56 | 99.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Exhaust Fan Point | 4.5 | No. | 225 | 25 | 6.33 | 0 | 253.13 | C+S GST 18% I/P RD | 45.56 | 298.69 | 298.69 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Exhaust Fan Point | 1.5 | No. | 225 | 25 | 2.11 | 0 | 84.38 | C+S GST 18% I/P RD | 15.18 | 99.56 | 99.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Exhaust Fan Point | 4.5 | No. | 225 | 25 | 6.33 | 0 | 253.13 | C+S GST 18% I/P RD | 45.56 | 298.69 | 298.69 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Exhaust Fan Point | 5.25 | No. | 225 | 25 | 7.38 | 0 | 295.31 | C+S GST 18% I/P RD | 53.16 | 348.47 | 348.47 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | 8 Way TPN DB | 0.25 | No. | 1500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | 8 Way TPN DB | 0.75 | No. | 1500 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 8 Way TPN DB | 0.75 | No. | 1500 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 8 Way TPN DB | 0.25 | No. | 1500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 8 Way TPN DB | 0.75 | No. | 1500 | 30 | 8.44 | 0 | 337.5 | C+S GST 18% I/P RD | 60.76 | 398.26 | 398.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | 8 Way TPN DB | 0.25 | No. | 1500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | 8 Way TPN DB | 0.75 | No. | 1500 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | 8 Way TPN DB | 0.75 | No. | 1500 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Exhaust Fan Point | 1.75 | No. | 225 | 25 | 2.46 | 0 | 98.44 | C+S GST 18% I/P RD | 17.72 | 116.16 | 116.16 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Exhaust Fan Point | 5.25 | No. | 225 | 30 | 8.86 | 0 | 354.38 | C+S GST 18% I/P RD | 63.78 | 418.16 | 418.16 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Exhaust Fan Point | 2 | No. | 225 | 25 | 2.81 | 0 | 112.5 | C+S GST 18% I/P RD | 20.26 | 132.76 | 132.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 25 | 8.44 | 0 | 337.5 | C+S GST 18% I/P RD | 60.76 | 398.26 | 398.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Exhaust Fan Point | 1.75 | No. | 225 | 25 | 2.46 | 0 | 98.44 | C+S GST 18% I/P RD | 17.72 | 116.16 | 116.16 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Exhaust Fan Point | 5.25 | No. | 225 | 25 | 7.38 | 0 | 295.31 | C+S GST 18% I/P RD | 53.16 | 348.47 | 348.47 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Exhaust Fan Point | 2 | No. | 225 | 25 | 2.81 | 0 | 112.5 | C+S GST 18% I/P RD | 20.26 | 132.76 | 132.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 25 | 8.44 | 0 | 337.5 | C+S GST 18% I/P RD | 60.76 | 398.26 | 398.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Exhaust Fan Point | 0.25 | No. | 225 | 25 | 0.35 | 0 | 14.06 | C+S GST 18% I/P RD | 2.54 | 16.6 | 16.6 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Exhaust Fan Point | 0.75 | No. | 225 | 25 | 1.05 | 0 | 42.19 | C+S GST 18% I/P RD | 7.6 | 49.79 | 49.79 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | 8 Way TPN DB | 0.25 | No. | 1500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | 8 Way TPN DB | 0.75 | No. | 1500 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | 8 Way TPN DB | 0.25 | No. | 1500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | 8 Way TPN DB | 0.25 | No. | 1500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | 8 Way TPN DB | 0.75 | No. | 1500 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Independent) | 4.5 | No. | 250 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Independent) | 13.5 | No. | 250 | 25 | 21.09 | 0 | 843.75 | C+S GST 18% I/P RD | 151.88 | 995.63 | 995.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | 6 AMP Plug point (Independent) | 22.5 | No. | 250 | 25 | 35.16 | 0 | 1406.25 | C+S GST 18% I/P RD | 253.12 | 1659.37 | 1659.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | 6 AMP Plug point (Independent) | 22.5 | No. | 250 | 25 | 35.16 | 0 | 1406.25 | C+S GST 18% I/P RD | 253.12 | 1659.37 | 1659.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 7.5 | No. | 450 | 30 | 25.31 | 0 | 1012.5 | C+S GST 18% I/P RD | 182.26 | 1194.76 | 1194.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.25 | No. | 450 | 25 | 6.33 | 0 | 253.13 | C+S GST 18% I/P RD | 45.56 | 298.69 | 298.69 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 6.75 | No. | 450 | 25 | 18.98 | 0 | 759.38 | C+S GST 18% I/P RD | 136.68 | 896.06 | 896.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 7.5 | No. | 450 | 25 | 21.09 | 0 | 843.75 | C+S GST 18% I/P RD | 151.88 | 995.63 | 995.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.5 | No. | 450 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 7.5 | No. | 450 | 25 | 21.09 | 0 | 843.75 | C+S GST 18% I/P RD | 151.88 | 995.63 | 995.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.5 | No. | 450 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.25 | No. | 450 | 30 | 0.84 | 0 | 33.75 | C+S GST 18% I/P RD | 6.08 | 39.83 | 39.83 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.75 | No. | 450 | 30 | 2.53 | 0 | 101.25 | C+S GST 18% I/P RD | 18.22 | 119.47 | 119.47 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.5 | No. | 450 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 7.5 | No. | 450 | 25 | 21.09 | 0 | 843.75 | C+S GST 18% I/P RD | 151.88 | 995.63 | 995.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 8.75 | No. | 250 | 25 | 13.67 | 0 | 546.88 | C+S GST 18% I/P RD | 98.44 | 645.32 | 645.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 26.25 | No. | 250 | 25 | 41.02 | 0 | 1640.63 | C+S GST 18% I/P RD | 295.32 | 1935.95 | 1935.95 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 8.75 | No. | 250 | 25 | 13.67 | 0 | 546.88 | C+S GST 18% I/P RD | 98.44 | 645.32 | 645.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 26.25 | No. | 250 | 25 | 41.02 | 0 | 1640.63 | C+S GST 18% I/P RD | 295.32 | 1935.95 | 1935.95 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 17.25 | No. | 250 | 25 | 26.95 | 0 | 1078.13 | C+S GST 18% I/P RD | 194.06 | 1272.19 | 1272.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 5.75 | No. | 250 | 25 | 8.98 | 0 | 359.38 | C+S GST 18% I/P RD | 64.68 | 424.06 | 424.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 8.75 | No. | 250 | 30 | 16.41 | 0 | 656.25 | C+S GST 18% I/P RD | 118.12 | 774.37 | 774.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 26.25 | No. | 250 | 30 | 49.22 | 0 | 1968.75 | C+S GST 18% I/P RD | 354.38 | 2323.13 | 2323.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 11.25 | No. | 250 | 25 | 17.58 | 0 | 703.13 | C+S GST 18% I/P RD | 126.56 | 829.69 | 829.69 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 4.496 | No. | 250 | 25 | 7.03 | 0 | 281 | C+S GST 18% I/P RD | 50.58 | 331.58 | 331.58 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 13.5 | No. | 250 | 25 | 21.09 | 0 | 843.75 | C+S GST 18% I/P RD | 151.88 | 995.63 | 995.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.75 | No. | 250 | 30 | 29.53 | 0 | 1181.25 | C+S GST 18% I/P RD | 212.62 | 1393.87 | 1393.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15.75 | No. | 250 | 25 | 24.61 | 0 | 984.38 | C+S GST 18% I/P RD | 177.18 | 1161.56 | 1161.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 5.75 | No. | 250 | 25 | 8.98 | 0 | 359.38 | C+S GST 18% I/P RD | 64.68 | 424.06 | 424.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 17.25 | No. | 250 | 25 | 26.95 | 0 | 1078.13 | C+S GST 18% I/P RD | 194.06 | 1272.19 | 1272.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 8.75 | No. | 250 | 25 | 13.67 | 0 | 546.88 | C+S GST 18% I/P RD | 98.44 | 645.32 | 645.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 26.25 | No. | 250 | 25 | 41.02 | 0 | 1640.63 | C+S GST 18% I/P RD | 295.32 | 1935.95 | 1935.95 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 3.75 | No. | 250 | 25 | 5.86 | 0 | 234.38 | C+S GST 18% I/P RD | 42.18 | 276.56 | 276.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 11.25 | No. | 250 | 25 | 17.58 | 0 | 703.13 | C+S GST 18% I/P RD | 126.56 | 829.69 | 829.69 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10 | No. | 250 | 25 | 15.63 | 0 | 625 | C+S GST 18% I/P RD | 112.5 | 737.5 | 737.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 30 | No. | 250 | 25 | 46.88 | 0 | 1875 | C+S GST 18% I/P RD | 337.5 | 2212.5 | 2212.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 9.744 | No. | 250 | 25 | 15.23 | 0 | 609 | C+S GST 18% I/P RD | 109.62 | 718.62 | 718.62 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 29.25 | No. | 250 | 25 | 45.7 | 0 | 1828.13 | C+S GST 18% I/P RD | 329.06 | 2157.19 | 2157.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 30 | No. | 250 | 25 | 46.88 | 0 | 1875 | C+S GST 18% I/P RD | 337.5 | 2212.5 | 2212.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 10 | No. | 250 | 25 | 15.63 | 0 | 625 | C+S GST 18% I/P RD | 112.5 | 737.5 | 737.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.5 | No. | 450 | 25 | 1.41 | 0 | 56.25 | C+S GST 18% I/P RD | 10.12 | 66.37 | 66.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.5 | No. | 450 | 25 | 1.41 | 0 | 56.25 | C+S GST 18% I/P RD | 10.12 | 66.37 | 66.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.5 | No. | 450 | 25 | 1.41 | 0 | 56.25 | C+S GST 18% I/P RD | 10.12 | 66.37 | 66.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.5 | No. | 450 | 30 | 5.06 | 0 | 202.5 | C+S GST 18% I/P RD | 36.46 | 238.96 | 238.96 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.5 | No. | 450 | 25 | 1.41 | 0 | 56.25 | C+S GST 18% I/P RD | 10.12 | 66.37 | 66.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.5 | No. | 450 | 25 | 1.41 | 0 | 56.25 | C+S GST 18% I/P RD | 10.12 | 66.37 | 66.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 0.5 | No. | 450 | 25 | 1.41 | 0 | 56.25 | C+S GST 18% I/P RD | 10.12 | 66.37 | 66.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 6 AMP Plug point (Dependent) | 2.75 | No. | 100 | 25 | 1.72 | 0 | 68.75 | C+S GST 18% I/P RD | 12.38 | 81.13 | 81.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 6 AMP Plug point (Dependent) | 8.25 | No. | 100 | 25 | 5.16 | 0 | 206.25 | C+S GST 18% I/P RD | 37.12 | 243.37 | 243.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3.25 | No. | 100 | 25 | 2.03 | 0 | 81.25 | C+S GST 18% I/P RD | 14.62 | 95.87 | 95.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | AC Point BC | 1.25 | No. | 450 | 25 | 3.52 | 0 | 140.63 | C+S GST 18% I/P RD | 25.32 | 165.95 | 165.95 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | AC Point BC | 3.75 | No. | 450 | 25 | 10.55 | 0 | 421.88 | C+S GST 18% I/P RD | 75.94 | 497.82 | 497.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Video Door Phone (L)- BC | 0.25 | No. | 500 | 25 | 0.78 | 0 | 31.25 | C+S GST 18% I/P RD | 5.62 | 36.87 | 36.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Video Door Phone (L)- BC | 0.75 | No. | 500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 13.25 | No. | 250 | 25 | 20.7 | 0 | 828.13 | C+S GST 18% I/P RD | 149.06 | 977.19 | 977.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 39.75 | No. | 250 | 25 | 62.11 | 0 | 2484.38 | C+S GST 18% I/P RD | 447.18 | 2931.56 | 2931.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.75 | No. | 250 | 25 | 16.8 | 0 | 671.88 | C+S GST 18% I/P RD | 120.94 | 792.82 | 792.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 6 AMP Plug point (Independent) | 12.75 | No. | 250 | 25 | 19.92 | 0 | 796.88 | C+S GST 18% I/P RD | 143.44 | 940.32 | 940.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 6 AMP Plug point (Independent) | 38.25 | No. | 250 | 25 | 59.77 | 0 | 2390.63 | C+S GST 18% I/P RD | 430.32 | 2820.95 | 2820.95 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Video Door Phone (L)- BC | 0.75 | No. | 500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Video Door Phone (L)- BC | 0.25 | No. | 500 | 25 | 0.78 | 0 | 31.25 | C+S GST 18% I/P RD | 5.62 | 36.87 | 36.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Video Door Phone (L)- BC | 0.75 | No. | 500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Video Door Phone (L)- BC | 0.25 | No. | 500 | 25 | 0.78 | 0 | 31.25 | C+S GST 18% I/P RD | 5.62 | 36.87 | 36.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Video Door Phone (L)- BC | 0.75 | No. | 500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Video Door Phone (L)- BC | 0.25 | No. | 500 | 25 | 0.78 | 0 | 31.25 | C+S GST 18% I/P RD | 5.62 | 36.87 | 36.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Video Door Phone (L)- BC | 0.25 | No. | 500 | 25 | 0.78 | 0 | 31.25 | C+S GST 18% I/P RD | 5.62 | 36.87 | 36.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Video Door Phone (L)- BC | 0.75 | No. | 500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Video Door Phone (L)- BC | 0.25 | No. | 500 | 25 | 0.78 | 0 | 31.25 | C+S GST 18% I/P RD | 5.62 | 36.87 | 36.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Video Door Phone (L)- BC | 0.75 | No. | 500 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Video Door Phone (L)- BC | 0.75 | No. | 500 | 30 | 2.81 | 0 | 112.5 | C+S GST 18% I/P RD | 20.26 | 132.76 | 132.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Fan Point | 0.25 | No. | 250 | 25 | 0.39 | 0 | 15.63 | C+S GST 18% I/P RD | 2.82 | 18.45 | 18.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Fan Point | 0.75 | No. | 250 | 25 | 1.17 | 0 | 46.88 | C+S GST 18% I/P RD | 8.44 | 55.32 | 55.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Fan Point | 0.5 | No. | 250 | 25 | 0.78 | 0 | 31.25 | C+S GST 18% I/P RD | 5.62 | 36.87 | 36.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Fan Point | 1.5 | No. | 250 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Fan Point | 2 | No. | 250 | 25 | 3.13 | 0 | 125 | C+S GST 18% I/P RD | 22.5 | 147.5 | 147.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Fan Point | 6 | No. | 250 | 25 | 9.38 | 0 | 375 | C+S GST 18% I/P RD | 67.5 | 442.5 | 442.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Fan Point | 6 | No. | 250 | 30 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Fan Point | 0.75 | No. | 250 | 25 | 1.17 | 0 | 46.88 | C+S GST 18% I/P RD | 8.44 | 55.32 | 55.32 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Fan Point | 0.25 | No. | 250 | 25 | 0.39 | 0 | 15.63 | C+S GST 18% I/P RD | 2.82 | 18.45 | 18.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Fan Point | 1.5 | No. | 250 | 25 | 2.34 | 0 | 93.75 | C+S GST 18% I/P RD | 16.88 | 110.63 | 110.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Fan Point | 2.25 | No. | 250 | 25 | 3.52 | 0 | 140.63 | C+S GST 18% I/P RD | 25.32 | 165.95 | 165.95 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Fan Point | 6.75 | No. | 250 | 25 | 10.55 | 0 | 421.88 | C+S GST 18% I/P RD | 75.94 | 497.82 | 497.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Fan Point | 2.25 | No. | 250 | 25 | 3.52 | 0 | 140.63 | C+S GST 18% I/P RD | 25.32 | 165.95 | 165.95 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Fan Point | 1.75 | No. | 250 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Fan Point | 5.25 | No. | 250 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Fan Point | 2 | No. | 250 | 25 | 3.13 | 0 | 125 | C+S GST 18% I/P RD | 22.5 | 147.5 | 147.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Fan Point | 6 | No. | 250 | 25 | 9.38 | 0 | 375 | C+S GST 18% I/P RD | 67.5 | 442.5 | 442.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Fan Point | 1.75 | No. | 250 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Fan Point | 5.25 | No. | 250 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Fan Point | 0.75 | No. | 250 | 30 | 1.41 | 0 | 56.25 | C+S GST 18% I/P RD | 10.12 | 66.37 | 66.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Fan Point | 6.75 | No. | 250 | 25 | 10.55 | 0 | 421.88 | C+S GST 18% I/P RD | 75.94 | 497.82 | 497.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Fan Point | 0.5 | No. | 250 | 25 | 0.78 | 0 | 31.25 | C+S GST 18% I/P RD | 5.62 | 36.87 | 36.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | TV Point | 1.5 | No. | 350 | 25 | 3.28 | 0 | 131.25 | C+S GST 18% I/P RD | 23.62 | 154.87 | 154.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | TV Point | 3.75 | No. | 350 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | TV Point | 1.25 | No. | 350 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | TV Point | 1.5 | No. | 350 | 25 | 3.28 | 0 | 131.25 | C+S GST 18% I/P RD | 23.62 | 154.87 | 154.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | TV Point | 4.5 | No. | 350 | 25 | 9.84 | 0 | 393.75 | C+S GST 18% I/P RD | 70.88 | 464.63 | 464.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | TV Point | 1.25 | No. | 350 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | TV Point | 3.75 | No. | 350 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | TV Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | TV Point | 0.25 | No. | 350 | 25 | 0.55 | 0 | 21.88 | C+S GST 18% I/P RD | 3.94 | 25.82 | 25.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | TV Point | 4.5 | No. | 350 | 25 | 9.84 | 0 | 393.75 | C+S GST 18% I/P RD | 70.88 | 464.63 | 464.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | TV Point | 1.5 | No. | 350 | 25 | 3.28 | 0 | 131.25 | C+S GST 18% I/P RD | 23.62 | 154.87 | 154.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | TV Point | 4.5 | No. | 350 | 25 | 9.84 | 0 | 393.75 | C+S GST 18% I/P RD | 70.88 | 464.63 | 464.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | TV Point | 4.5 | No. | 350 | 30 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | TV Point | 1.5 | No. | 350 | 25 | 3.28 | 0 | 131.25 | C+S GST 18% I/P RD | 23.62 | 154.87 | 154.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | 6 AMP Plug point (Dependent) | 1.75 | No. | 100 | 25 | 1.09 | 0 | 43.75 | C+S GST 18% I/P RD | 7.88 | 51.63 | 51.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | 6 AMP Plug point (Dependent) | 5.25 | No. | 100 | 25 | 3.28 | 0 | 131.25 | C+S GST 18% I/P RD | 23.62 | 154.87 | 154.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3.25 | No. | 100 | 25 | 2.03 | 0 | 81.25 | C+S GST 18% I/P RD | 14.62 | 95.87 | 95.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.75 | No. | 100 | 25 | 6.09 | 0 | 243.75 | C+S GST 18% I/P RD | 43.88 | 287.63 | 287.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.75 | No. | 100 | 25 | 6.09 | 0 | 243.75 | C+S GST 18% I/P RD | 43.88 | 287.63 | 287.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 3.5 | No. | 100 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 100 | 25 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | 6 AMP Plug point (Dependent) | 1.75 | No. | 100 | 25 | 1.09 | 0 | 43.75 | C+S GST 18% I/P RD | 7.88 | 51.63 | 51.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | 6 AMP Plug point (Dependent) | 5.25 | No. | 100 | 25 | 3.28 | 0 | 131.25 | C+S GST 18% I/P RD | 23.62 | 154.87 | 154.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 6 AMP Plug point (Dependent) | 8.25 | No. | 100 | 30 | 6.19 | 0 | 247.5 | C+S GST 18% I/P RD | 44.56 | 292.06 | 292.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.5 | No. | 450 | 25 | 7.03 | 0 | 281.25 | C+S GST 18% I/P RD | 50.62 | 331.87 | 331.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 7.5 | No. | 450 | 25 | 21.09 | 0 | 843.75 | C+S GST 18% I/P RD | 151.88 | 995.63 | 995.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 6.75 | No. | 450 | 25 | 18.98 | 0 | 759.38 | C+S GST 18% I/P RD | 136.68 | 896.06 | 896.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.25 | No. | 450 | 25 | 6.33 | 0 | 253.13 | C+S GST 18% I/P RD | 45.56 | 298.69 | 298.69 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Telephone Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Telephone Point | 3.75 | No. | 350 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Telephone Point | 1.25 | No. | 350 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Telephone Point | 3.75 | No. | 350 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Telephone Point | 1.25 | No. | 350 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Telephone Point | 3.75 | No. | 350 | 30 | 9.84 | 0 | 393.75 | C+S GST 18% I/P RD | 70.88 | 464.63 | 464.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Telephone Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Telephone Point | 0.25 | No. | 350 | 25 | 0.55 | 0 | 21.88 | C+S GST 18% I/P RD | 3.94 | 25.82 | 25.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Telephone Point | 1.25 | No. | 350 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Telephone Point | 3.75 | No. | 350 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Telephone Point | 1.25 | No. | 350 | 25 | 2.73 | 0 | 109.38 | C+S GST 18% I/P RD | 19.68 | 129.06 | 129.06 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Telephone Point | 3.75 | No. | 350 | 25 | 8.2 | 0 | 328.13 | C+S GST 18% I/P RD | 59.06 | 387.19 | 387.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Telephone Point | 1 | No. | 350 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Telephone Point | 3 | No. | 350 | 25 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | AC Point BC | 0.75 | No. | 450 | 25 | 2.11 | 0 | 84.38 | C+S GST 18% I/P RD | 15.18 | 99.56 | 99.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | AC Point BC | 0.25 | No. | 450 | 25 | 0.7 | 0 | 28.13 | C+S GST 18% I/P RD | 5.06 | 33.19 | 33.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | AC Point BC | 0.25 | No. | 450 | 25 | 0.7 | 0 | 28.13 | C+S GST 18% I/P RD | 5.06 | 33.19 | 33.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | AC Point BC | 0.75 | No. | 450 | 25 | 2.11 | 0 | 84.38 | C+S GST 18% I/P RD | 15.18 | 99.56 | 99.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | AC Point BC | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | AC Point BC | 4.5 | No. | 450 | 25 | 12.66 | 0 | 506.25 | C+S GST 18% I/P RD | 91.12 | 597.37 | 597.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | AC Point BC | 4.5 | No. | 450 | 30 | 15.19 | 0 | 607.5 | C+S GST 18% I/P RD | 109.36 | 716.86 | 716.86 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | AC Point BC | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | AC Point BC | 4.5 | No. | 450 | 25 | 12.66 | 0 | 506.25 | C+S GST 18% I/P RD | 91.12 | 597.37 | 597.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | AC Point BC | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | AC Point BC | 4.5 | No. | 450 | 25 | 12.66 | 0 | 506.25 | C+S GST 18% I/P RD | 91.12 | 597.37 | 597.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | AC Point BC | 1.5 | No. | 450 | 25 | 4.22 | 0 | 168.75 | C+S GST 18% I/P RD | 30.38 | 199.13 | 199.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | AC Point BC | 4.5 | No. | 450 | 25 | 12.66 | 0 | 506.25 | C+S GST 18% I/P RD | 91.12 | 597.37 | 597.37 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | AC Point BC | 1.25 | No. | 450 | 25 | 3.52 | 0 | 140.63 | C+S GST 18% I/P RD | 25.32 | 165.95 | 165.95 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | AC Point BC | 3.75 | No. | 450 | 25 | 10.55 | 0 | 421.88 | C+S GST 18% I/P RD | 75.94 | 497.82 | 497.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Secondary Light Points (Looping) | 9.75 | No. | 100 | 25 | 6.09 | 0 | 243.75 | C+S GST 18% I/P RD | 43.88 | 287.63 | 287.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | Secondary Light Points (Looping) | 29.25 | No. | 100 | 25 | 18.28 | 0 | 731.25 | C+S GST 18% I/P RD | 131.62 | 862.87 | 862.87 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Secondary Light Points (Looping) | 33 | No. | 100 | 25 | 20.63 | 0 | 825 | C+S GST 18% I/P RD | 148.5 | 973.5 | 973.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Secondary Light Points (Looping) | 9.5 | No. | 100 | 25 | 5.94 | 0 | 237.5 | C+S GST 18% I/P RD | 42.76 | 280.26 | 280.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | Secondary Light Points (Looping) | 28.5 | No. | 100 | 25 | 17.81 | 0 | 712.5 | C+S GST 18% I/P RD | 128.26 | 840.76 | 840.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 401 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 100 | 25 | 6.88 | 0 | 275 | C+S GST 18% I/P RD | 49.5 | 324.5 | 324.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Secondary Light Points (Looping) | 31.5 | No. | 100 | 30 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Secondary Light Points (Looping) | 9.5 | No. | 100 | 25 | 5.94 | 0 | 237.5 | C+S GST 18% I/P RD | 42.76 | 280.26 | 280.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | Secondary Light Points (Looping) | 28.5 | No. | 100 | 25 | 17.81 | 0 | 712.5 | C+S GST 18% I/P RD | 128.26 | 840.76 | 840.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Secondary Light Points (Looping) | 11 | No. | 100 | 25 | 6.88 | 0 | 275 | C+S GST 18% I/P RD | 49.5 | 324.5 | 324.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | Secondary Light Points (Looping) | 33 | No. | 100 | 25 | 20.63 | 0 | 825 | C+S GST 18% I/P RD | 148.5 | 973.5 | 973.5 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Secondary Light Points (Looping) | 10.5 | No. | 100 | 25 | 6.56 | 0 | 262.5 | C+S GST 18% I/P RD | 47.26 | 309.76 | 309.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | Secondary Light Points (Looping) | 31.5 | No. | 100 | 25 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 304 Internal Electrical Work | 6 AMP Plug point (Independent) | 38.25 | No. | 250 | 30 | 71.72 | 0 | 2868.75 | C+S GST 18% I/P RD | 516.38 | 3385.13 | 3385.13 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 303 Internal Electrical Work | 6 AMP Plug point (Independent) | 32.25 | No. | 250 | 25 | 50.39 | 0 | 2015.63 | C+S GST 18% I/P RD | 362.82 | 2378.45 | 2378.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Independent) | 39.75 | No. | 250 | 25 | 62.11 | 0 | 2484.38 | C+S GST 18% I/P RD | 447.18 | 2931.56 | 2931.56 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Independent) | 13.25 | No. | 250 | 25 | 20.7 | 0 | 828.13 | C+S GST 18% I/P RD | 149.06 | 977.19 | 977.19 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Independent) | 39 | No. | 250 | 25 | 60.94 | 0 | 2437.5 | C+S GST 18% I/P RD | 438.76 | 2876.26 | 2876.26 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Independent) | 13 | No. | 250 | 25 | 20.31 | 0 | 812.5 | C+S GST 18% I/P RD | 146.26 | 958.76 | 958.76 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | 6 AMP Plug point (Independent) | 10.75 | No. | 250 | 25 | 16.8 | 0 | 671.88 | C+S GST 18% I/P RD | 120.94 | 792.82 | 792.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | 6 AMP Plug point (Independent) | 32.25 | No. | 250 | 25 | 50.39 | 0 | 2015.63 | C+S GST 18% I/P RD | 362.82 | 2378.45 | 2378.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 301 Internal Electrical Work | TV Point | 4.5 | No. | 350 | 25 | 9.84 | 0 | 393.75 | C+S GST 18% I/P RD | 70.88 | 464.63 | 464.63 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | TV Point | 0.25 | No. | 350 | 25 | 0.55 | 0 | 21.88 | C+S GST 18% I/P RD | 3.94 | 25.82 | 25.82 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90027 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 331 | A Bldg Flat No. 603 Internal Electrical Work | TV Point | 0.75 | No. | 350 | 25 | 1.64 | 0 | 65.63 | C+S GST 18% I/P RD | 11.82 | 77.45 | 77.45 | Approved | 0 | 0 | 1965 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Secondary Light Points (Looping) | 42 | No. | 100 | 35 | 36.75 | 0 | 1470 | C+S GST 18% I/P RD | 264.6 | 1734.6 | 1734.6 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Secondary Light Points (Looping) | 38 | No. | 100 | 35 | 33.25 | 0 | 1330 | C+S GST 18% I/P RD | 239.4 | 1569.4 | 1569.4 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | AC Point BC | 1 | No. | 450 | 35 | 3.94 | 0 | 157.5 | C+S GST 18% I/P RD | 28.36 | 185.86 | 185.86 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Telephone Point | 1 | No. | 350 | 35 | 3.06 | 0 | 122.5 | C+S GST 18% I/P RD | 22.06 | 144.56 | 144.56 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | TV Point | 1 | No. | 350 | 35 | 3.06 | 0 | 122.5 | C+S GST 18% I/P RD | 22.06 | 144.56 | 144.56 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Fan Point | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Fan Point | 2 | No. | 250 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Fan Point | 7 | No. | 250 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 225 | 35 | 1.97 | 0 | 78.75 | C+S GST 18% I/P RD | 14.18 | 92.93 | 92.93 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 23 | No. | 250 | 35 | 50.31 | 0 | 2012.5 | C+S GST 18% I/P RD | 362.26 | 2374.76 | 2374.76 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1 | No. | 450 | 35 | 3.94 | 0 | 157.5 | C+S GST 18% I/P RD | 28.36 | 185.86 | 185.86 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 9 | No. | 450 | 35 | 35.44 | 0 | 1417.5 | C+S GST 18% I/P RD | 255.16 | 1672.66 | 1672.66 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | 6 AMP Plug point (Independent) | 20 | No. | 250 | 35 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | 6 AMP Plug point (Independent) | 30 | No. | 250 | 35 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Data Point | 2 | No. | 350 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2504 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 359 | 90026 | 28 Apr 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 204 | A Bldg Flat No.-2503 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 710 | 28 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | Driver 10amp | 32 | No. | 680 | 100 | 544 | 0 | 21760 | C+S GST 18% I/P RD | 3916.8 | 25676.8 | 25676.8 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | Driver 5amp | 23 | No. | 510 | 100 | 293.25 | 0 | 11730 | C+S GST 18% I/P RD | 2111.4 | 13841.4 | 13841.4 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | LED Strip Fixing | 1344.8 | R.Ft | 42 | 100 | 1412.04 | 0 | 56481.6 | C+S GST 18% I/P RD | 10166.68 | 66648.28 | 66648.28 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | Profile Patti 12mm (M) | 24 | Mtrs | 135 | 100 | 81 | 0 | 3240 | C+S GST 18% I/P RD | 583.2 | 3823.2 | 3823.2 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | Wiring BC | 305 | R.Ft | 12 | 100 | 91.5 | 0 | 3660 | C+S GST 18% I/P RD | 658.8 | 4318.8 | 4318.8 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | Profile Removing (L) | 200 | R.Ft | 60 | 100 | 300 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | LED Strip (Normal) (M) | 260 | Mtrs | 120 | 100 | 780 | 0 | 31200 | C+S GST 18% I/P RD | 5616 | 36816 | 36816 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | LED Point- BCE | 45 | No. | 210 | 100 | 236.25 | 0 | 9450 | C+S GST 18% I/P RD | 1701 | 11151 | 11151 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | Profile Patti 17mm (M) | 200 | Mtrs | 80 | 100 | 400 | 0 | 16000 | C+S GST 18% I/P RD | 2880 | 18880 | 18880 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 1040 | 90024 | 27 Apr 2021 |  | VAISHALI ELECTRICAL | VAISHALI ELECTRICAL | EV - 132 | Club House Electrical Work | LED Strip (Dot less) (M) | 150 | Mtrs | 165 | 100 | 618.75 | 0 | 24750 | C+S GST 18% I/P RD | 4455 | 29205 | 29205 | Approved | 0 | 0 | 1903 | 27 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 404 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 12.102 | Mtrs | 245 | 100 | 0 | 0 | 2965 | C+S GST 18% I/P RD | 533.7 | 3498.7 | 3498.7 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 701 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 22.4 | Mtrs | 245 | 100 | 0 | 0 | 5488 | C+S GST 18% I/P RD | 987.84 | 6475.84 | 6475.84 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 502 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 9.502 | Mtrs | 245 | 100 | 0 | 0 | 2328 | C+S GST 18% I/P RD | 419.04 | 2747.04 | 2747.04 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 603 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 6.4 | Mtrs | 245 | 100 | 0 | 0 | 1568 | C+S GST 18% I/P RD | 282.24 | 1850.24 | 1850.24 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 902 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 7 | Mtrs | 245 | 100 | 0 | 0 | 1715 | C+S GST 18% I/P RD | 308.7 | 2023.7 | 2023.7 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 18 | Mtrs | 245 | 100 | 0 | 0 | 4410 | C+S GST 18% I/P RD | 793.8 | 5203.8 | 5203.8 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 1002 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 2.6 | Mtrs | 245 | 100 | 0 | 0 | 637 | C+S GST 18% I/P RD | 114.66 | 751.66 | 751.66 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 1003 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 4.6 | Mtrs | 245 | 100 | 0 | 0 | 1127 | C+S GST 18% I/P RD | 202.86 | 1329.86 | 1329.86 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 11.8 | Mtrs | 245 | 100 | 0 | 0 | 2891 | C+S GST 18% I/P RD | 520.38 | 3411.38 | 3411.38 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 304 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 41.902 | Mtrs | 245 | 100 | 0 | 0 | 10266 | C+S GST 18% I/P RD | 1847.88 | 12113.88 | 12113.88 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 703 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 7.302 | Mtrs | 245 | 100 | 0 | 0 | 1789 | C+S GST 18% I/P RD | 322.02 | 2111.02 | 2111.02 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 303 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 22.4 | Mtrs | 245 | 100 | 0 | 0 | 5488 | C+S GST 18% I/P RD | 987.84 | 6475.84 | 6475.84 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 704 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 12.102 | Mtrs | 245 | 100 | 0 | 0 | 2965 | C+S GST 18% I/P RD | 533.7 | 3498.7 | 3498.7 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 802 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 3.4 | Mtrs | 245 | 100 | 0 | 0 | 833 | C+S GST 18% I/P RD | 149.94 | 982.94 | 982.94 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 403 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 20.702 | Mtrs | 245 | 100 | 0 | 0 | 5072 | C+S GST 18% I/P RD | 912.96 | 5984.96 | 5984.96 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 301 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 32.6 | Mtrs | 245 | 100 | 0 | 0 | 7987 | C+S GST 18% I/P RD | 1437.66 | 9424.66 | 9424.66 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 302 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 38 | Mtrs | 245 | 100 | 0 | 0 | 9310 | C+S GST 18% I/P RD | 1675.8 | 10985.8 | 10985.8 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 604 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 13.302 | Mtrs | 245 | 100 | 0 | 0 | 3259 | C+S GST 18% I/P RD | 586.62 | 3845.62 | 3845.62 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 25.011 | Mtrs | 45.5 | 100 | 0 | 0 | 1138 | C+S GST 18% I/P RD | 204.84 | 1342.84 | 1342.84 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 302 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 48.7912 | Mtrs | 45.5 | 100 | 0 | 0 | 2220 | C+S GST 18% I/P RD | 399.6 | 2619.6 | 2619.6 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 303 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 28.1978 | Mtrs | 45.5 | 100 | 0 | 0 | 1283 | C+S GST 18% I/P RD | 230.94 | 1513.94 | 1513.94 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 403 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 25.011 | Mtrs | 45.5 | 100 | 0 | 0 | 1138 | C+S GST 18% I/P RD | 204.84 | 1342.84 | 1342.84 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 404 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 18.3077 | Mtrs | 45.5 | 100 | 0 | 0 | 833 | C+S GST 18% I/P RD | 149.94 | 982.94 | 982.94 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 301 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 43.2967 | Mtrs | 45.5 | 100 | 0 | 0 | 1970 | C+S GST 18% I/P RD | 354.6 | 2324.6 | 2324.6 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 604 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 22.3077 | Mtrs | 45.5 | 100 | 0 | 0 | 1015 | C+S GST 18% I/P RD | 182.7 | 1197.7 | 1197.7 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 1003 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 7.6044 | Mtrs | 45.5 | 100 | 0 | 0 | 346 | C+S GST 18% I/P RD | 62.28 | 408.28 | 408.28 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 1002 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 4 | Mtrs | 45.5 | 100 | 0 | 0 | 182 | C+S GST 18% I/P RD | 32.76 | 214.76 | 214.76 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 704 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 21.2088 | Mtrs | 45.5 | 100 | 0 | 0 | 965 | C+S GST 18% I/P RD | 173.7 | 1138.7 | 1138.7 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 903 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 4.4082 | Mtrs | 49 | 100 | 0 | 0 | 216 | C+S GST 18% I/P RD | 38.88 | 254.88 | 254.88 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 1002 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 3.6939 | Mtrs | 49 | 100 | 0 | 0 | 181 | C+S GST 18% I/P RD | 32.58 | 213.58 | 213.58 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 601 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 9.102 | Mtrs | 49 | 100 | 0 | 0 | 446 | C+S GST 18% I/P RD | 80.28 | 526.28 | 526.28 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 701 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 12.5102 | Mtrs | 49 | 100 | 0 | 0 | 613 | C+S GST 18% I/P RD | 110.34 | 723.34 | 723.34 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 304 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 14.3061 | Mtrs | 49 | 100 | 0 | 0 | 701 | C+S GST 18% I/P RD | 126.18 | 827.18 | 827.18 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 502 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 8.7959 | Mtrs | 49 | 100 | 0 | 0 | 431 | C+S GST 18% I/P RD | 77.58 | 508.58 | 508.58 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 702 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 3 | Mtrs | 49 | 100 | 0 | 0 | 147 | C+S GST 18% I/P RD | 26.46 | 173.46 | 173.46 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 14.3061 | Mtrs | 49 | 100 | 0 | 0 | 701 | C+S GST 18% I/P RD | 126.18 | 827.18 | 827.18 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 404 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 7 | Mtrs | 49 | 100 | 0 | 0 | 343 | C+S GST 18% I/P RD | 61.74 | 404.74 | 404.74 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 603 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 1.5102 | Mtrs | 49 | 100 | 0 | 0 | 74 | C+S GST 18% I/P RD | 13.32 | 87.32 | 87.32 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 1003 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 2.4082 | Mtrs | 49 | 100 | 0 | 0 | 118 | C+S GST 18% I/P RD | 21.24 | 139.24 | 139.24 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 303 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 14.2041 | Mtrs | 49 | 100 | 0 | 0 | 696 | C+S GST 18% I/P RD | 125.28 | 821.28 | 821.28 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 703 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 2.102 | Mtrs | 49 | 100 | 0 | 0 | 103 | C+S GST 18% I/P RD | 18.54 | 121.54 | 121.54 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 301 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 14.898 | Mtrs | 49 | 100 | 0 | 0 | 730 | C+S GST 18% I/P RD | 131.4 | 861.4 | 861.4 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 403 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 13.102 | Mtrs | 49 | 100 | 0 | 0 | 642 | C+S GST 18% I/P RD | 115.56 | 757.56 | 757.56 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 604 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 5.2041 | Mtrs | 49 | 100 | 0 | 0 | 255 | C+S GST 18% I/P RD | 45.9 | 300.9 | 300.9 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 302 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 17.6939 | Mtrs | 49 | 100 | 0 | 0 | 867 | C+S GST 18% I/P RD | 156.06 | 1023.06 | 1023.06 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 704 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (M) | 6.5918 | Mtrs | 49 | 100 | 0 | 0 | 323 | C+S GST 18% I/P RD | 58.14 | 381.14 | 381.14 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 601 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 22.9011 | Mtrs | 45.5 | 100 | 0 | 0 | 1042 | C+S GST 18% I/P RD | 187.56 | 1229.56 | 1229.56 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 702 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 5.4945 | Mtrs | 45.5 | 100 | 0 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 903 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 8.5055 | Mtrs | 45.5 | 100 | 0 | 0 | 387 | C+S GST 18% I/P RD | 69.66 | 456.66 | 456.66 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 603 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 11.011 | Mtrs | 45.5 | 100 | 0 | 0 | 501 | C+S GST 18% I/P RD | 90.18 | 591.18 | 591.18 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 26.1978 | Mtrs | 45.5 | 100 | 0 | 0 | 1192 | C+S GST 18% I/P RD | 214.56 | 1406.56 | 1406.56 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 502 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 19.4945 | Mtrs | 45.5 | 100 | 0 | 0 | 887 | C+S GST 18% I/P RD | 159.66 | 1046.66 | 1046.66 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 703 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 10.1978 | Mtrs | 45.5 | 100 | 0 | 0 | 464 | C+S GST 18% I/P RD | 83.52 | 547.52 | 547.52 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 304 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 47.2967 | Mtrs | 45.5 | 100 | 0 | 0 | 2152 | C+S GST 18% I/P RD | 387.36 | 2539.36 | 2539.36 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 802 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (M) | 4 | Mtrs | 45.5 | 100 | 0 | 0 | 182 | C+S GST 18% I/P RD | 32.76 | 214.76 | 214.76 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 530 | 90021 | 26 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 94 | A 702 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (M) | 3.702 | Mtrs | 245 | 100 | 0 | 0 | 907 | C+S GST 18% I/P RD | 163.26 | 1070.26 | 1070.26 | Approved | 0 | 0 | 0 | 26 Apr 2021
GANGA DHAM TOWERS | 258 | 90010 | 26 Apr 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 136 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.9032 | Month | 2500 | 100 | 0 | 0 | 2258 | CGST 0% URD I/P | 0 | 2258 | 2258 | Approved | 0 | 0 | 23 | 26 Apr 2021
GANGA DHAM TOWERS | 939 | 90009 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 162 | DA Development Deep Cleaning work | Department Labour - Day | 27 | Day | 451.61 | 100 | 0 | 0 | 12193.47 | C+S GST 18% I/P RD | 2194.82 | 14388.29 | 14388.29 | Approved | 0 | 0 | 185 | 24 Apr 2021
GANGA DHAM TOWERS | 939 | 90009 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 162 | DA Development Deep Cleaning work | Department Labour - Day | 14 | Day | 451.61 | 100 | 0 | 0 | 6322.54 | C+S GST 18% I/P RD | 1138.06 | 7460.6 | 7460.6 | Approved | 0 | 0 | 185 | 24 Apr 2021
GANGA DHAM TOWERS | 991 | 90007 | 24 Apr 2021 |  | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 91 | B 1601 NOC | Blockwork 4" - BC | 235.03 | Sq.Ft | 14 | 100 | 0 | 0 | 3290.42 | C+S GST 18% I/P RD | 592.28 | 3882.7 | 3882.7 | Approved | 0 | 0 | 33 | 24 Apr 2021
GANGA DHAM TOWERS | 904 | 90006 | 24 Apr 2021 |  | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 92 | B 701 NOC | Rough Plaster- cc | 22.54 | Sq.Ft | 15 | 100 | 8.45 | 0 | 338.1 | C+S GST 18% I/P RD | 60.86 | 398.96 | 398.96 | Approved | 0 | 0 | 7 | 24 Apr 2021
GANGA DHAM TOWERS | 904 | 90006 | 24 Apr 2021 |  | AVCON TECHNICS PVT LTD | KADAVATH VENKAT ENTERPRISES | EV - 92 | B 701 NOC | Blockwork 4" - BC | 22.54 | Sq.Ft | 15 | 100 | 8.45 | 0 | 338.1 | C+S GST 18% I/P RD | 60.86 | 398.96 | 398.96 | Approved | 0 | 0 | 7 | 24 Apr 2021
GANGA DHAM TOWERS | 480 | 90001 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 89 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 28 | Day | 500 | 100 | 0 | 0 | 14000 | C+S GST 18% I/P RD | 2520 | 16520 | 16520 | Approved | 0 | 0 | 280 | 24 Apr 2021
GANGA DHAM TOWERS | 480 | 90001 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 89 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 31 | Day | 451.61 | 100 | 0 | 0 | 13999.91 | C+S GST 18% I/P RD | 2519.98 | 16519.89 | 16519.89 | Approved | 0 | 0 | 280 | 24 Apr 2021
GANGA DHAM TOWERS | 981 | 89999 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 88 | B 1101 | Blockwork 4" - BC | 35 | Sq.Ft | 16 | 100 | 0 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 17 | 24 Apr 2021
GANGA DHAM TOWERS | 981 | 89999 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 88 | B 1101 | Rough Plaster- cc | 72.6667 | Sq.Ft | 15 | 100 | 0 | 0 | 1090 | C+S GST 18% I/P RD | 196.2 | 1286.2 | 1286.2 | Approved | 0 | 0 | 17 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 801 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | C+S GST 18% I/P RD | 934 | 6122.92 | 6122.92 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 704 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | C+S GST 18% I/P RD | 752.84 | 4935.32 | 4935.32 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 702 Rough Plaster | Rough Plaster | 326.7 | Sq.Ft | 12 | 100 | 98.01 | 0 | 3920.4 | C+S GST 18% I/P RD | 705.68 | 4626.08 | 4626.08 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 805 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | C+S GST 18% I/P RD | 934 | 6122.92 | 6122.92 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 703 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | C+S GST 18% I/P RD | 752.84 | 4935.32 | 4935.32 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 701 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | C+S GST 18% I/P RD | 934 | 6122.92 | 6122.92 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 705 Rough Plaster | Rough Plaster | 432.41 | Sq.Ft | 12 | 100 | 129.72 | 0 | 5188.92 | C+S GST 18% I/P RD | 934 | 6122.92 | 6122.92 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 803 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | C+S GST 18% I/P RD | 752.84 | 4935.32 | 4935.32 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 492 | 89997 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 87 | D Building 804 Rough Plaster | Rough Plaster | 348.54 | Sq.Ft | 12 | 100 | 104.56 | 0 | 4182.48 | C+S GST 18% I/P RD | 752.84 | 4935.32 | 4935.32 | Approved | 0 | 0 | 414 | 24 Apr 2021
GANGA DHAM TOWERS | 491 | 89996 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 86 | D Build. 801 Blockwork 8" | Blockwork 8" - BC | 62 | Sq.Ft | 15 | 100 | 23.25 | 0 | 930 | C+S GST 18% I/P RD | 167.4 | 1097.4 | 1097.4 | Approved | 0 | 0 | 71 | 24 Apr 2021
GANGA DHAM TOWERS | 491 | 89996 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 86 | D Build. 804 Blockwork 8" | Blockwork 8" - BC | 206.67 | Sq.Ft | 15 | 100 | 77.5 | 0 | 3100.05 | C+S GST 18% I/P RD | 558 | 3658.05 | 3658.05 | Approved | 0 | 0 | 71 | 24 Apr 2021
GANGA DHAM TOWERS | 491 | 89996 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 86 | D Build. 805 Blockwork 8" | Blockwork 8" - BC | 204.09 | Sq.Ft | 15 | 100 | 76.53 | 0 | 3061.35 | C+S GST 18% I/P RD | 551.04 | 3612.39 | 3612.39 | Approved | 0 | 0 | 71 | 24 Apr 2021
GANGA DHAM TOWERS | 491 | 89995 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 85 | D Build. 801 Blockwork 5" | Blockwork 5" - BC - | 986.46 | Sq.Ft | 13 | 100 | 320.6 | 0 | 12823.98 | C+S GST 18% I/P RD | 2308.32 | 15132.3 | 15132.3 | Approved | 0 | 0 | 470 | 24 Apr 2021
GANGA DHAM TOWERS | 491 | 89995 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 85 | D Build. 803 Blockwork 5" | Blockwork 5" - BC - | 644.19 | Sq.Ft | 13 | 100 | 209.36 | 0 | 8374.47 | C+S GST 18% I/P RD | 1507.4 | 9881.87 | 9881.87 | Approved | 0 | 0 | 470 | 24 Apr 2021
GANGA DHAM TOWERS | 491 | 89995 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 85 | D Build. 805 Blockwork 8" | Blockwork 5" - BC - | 1169.49 | Sq.Ft | 13 | 100 | 380.08 | 0 | 15203.37 | C+S GST 18% I/P RD | 2736.6 | 17939.97 | 17939.97 | Approved | 0 | 0 | 470 | 24 Apr 2021
GANGA DHAM TOWERS | 491 | 89995 | 24 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 85 | D Build. 804 Blockwork 5" | Blockwork 5" - BC - | 813.08 | Sq.Ft | 13 | 100 | 264.25 | 0 | 10570.04 | C+S GST 18% I/P RD | 1902.6 | 12472.64 | 12472.64 | Approved | 0 | 0 | 470 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 502 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 4.381 | Mtrs | 21 | 100 | 0 | 0 | 92 | C+S GST 18% I/P RD | 16.56 | 108.56 | 108.56 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 301 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 7.5238 | Mtrs | 21 | 100 | 0 | 0 | 158 | C+S GST 18% I/P RD | 28.44 | 186.44 | 186.44 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 704 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 3.2857 | Mtrs | 21 | 100 | 0 | 0 | 69 | C+S GST 18% I/P RD | 12.42 | 81.42 | 81.42 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 1003 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 1.1905 | Mtrs | 21 | 100 | 0 | 0 | 25 | C+S GST 18% I/P RD | 4.5 | 29.5 | 29.5 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 403 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 6.619 | Mtrs | 21 | 100 | 0 | 0 | 139 | C+S GST 18% I/P RD | 25.02 | 164.02 | 164.02 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 604 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 2.619 | Mtrs | 21 | 100 | 0 | 0 | 55 | C+S GST 18% I/P RD | 9.9 | 64.9 | 64.9 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 302 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 8.8095 | Mtrs | 21 | 100 | 0 | 0 | 185 | C+S GST 18% I/P RD | 33.3 | 218.3 | 218.3 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 304 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 7.1905 | Mtrs | 21 | 100 | 0 | 0 | 151 | C+S GST 18% I/P RD | 27.18 | 178.18 | 178.18 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 703 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 1.0952 | Mtrs | 21 | 100 | 0 | 0 | 23 | C+S GST 18% I/P RD | 4.14 | 27.14 | 27.14 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 404 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 3.5238 | Mtrs | 21 | 100 | 0 | 0 | 74 | C+S GST 18% I/P RD | 13.32 | 87.32 | 87.32 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 603 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 1 | Mtrs | 21 | 100 | 0 | 0 | 21 | C+S GST 18% I/P RD | 3.78 | 24.78 | 24.78 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 402 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 7.1905 | Mtrs | 21 | 100 | 0 | 0 | 151 | C+S GST 18% I/P RD | 27.18 | 178.18 | 178.18 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 701 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 6.2857 | Mtrs | 21 | 100 | 0 | 0 | 132 | C+S GST 18% I/P RD | 23.76 | 155.76 | 155.76 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 303 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 7.0952 | Mtrs | 21 | 100 | 0 | 0 | 149 | C+S GST 18% I/P RD | 26.82 | 175.82 | 175.82 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 1002 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 1.8095 | Mtrs | 21 | 100 | 0 | 0 | 38 | C+S GST 18% I/P RD | 6.84 | 44.84 | 44.84 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 702 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 1.5238 | Mtrs | 21 | 100 | 0 | 0 | 32 | C+S GST 18% I/P RD | 5.76 | 37.76 | 37.76 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 303 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 11.2 | Mtrs | 105 | 100 | 0 | 0 | 1176 | C+S GST 18% I/P RD | 211.68 | 1387.68 | 1387.68 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 302 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 19 | Mtrs | 105 | 100 | 0 | 0 | 1995 | C+S GST 18% I/P RD | 359.1 | 2354.1 | 2354.1 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 802 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 1.7048 | Mtrs | 105 | 100 | 0 | 0 | 179 | C+S GST 18% I/P RD | 32.22 | 211.22 | 211.22 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 1003 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 2.3048 | Mtrs | 105 | 100 | 0 | 0 | 242 | C+S GST 18% I/P RD | 43.56 | 285.56 | 285.56 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 304 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 21 | Mtrs | 105 | 100 | 0 | 0 | 2205 | C+S GST 18% I/P RD | 396.9 | 2601.9 | 2601.9 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 402 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 5.9048 | Mtrs | 105 | 100 | 0 | 0 | 620 | C+S GST 18% I/P RD | 111.6 | 731.6 | 731.6 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 704 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 6.1048 | Mtrs | 105 | 100 | 0 | 0 | 641 | C+S GST 18% I/P RD | 115.38 | 756.38 | 756.38 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 601 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 9 | Mtrs | 105 | 100 | 0 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 301 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 16.3048 | Mtrs | 105 | 100 | 0 | 0 | 1712 | C+S GST 18% I/P RD | 308.16 | 2020.16 | 2020.16 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 702 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 1.8 | Mtrs | 105 | 100 | 0 | 0 | 189 | C+S GST 18% I/P RD | 34.02 | 223.02 | 223.02 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 604 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 6.6 | Mtrs | 105 | 100 | 0 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 1002 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 1.3048 | Mtrs | 105 | 100 | 0 | 0 | 137 | C+S GST 18% I/P RD | 24.66 | 161.66 | 161.66 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 502 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 4.8 | Mtrs | 105 | 100 | 0 | 0 | 504 | C+S GST 18% I/P RD | 90.72 | 594.72 | 594.72 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 603 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 3.2 | Mtrs | 105 | 100 | 0 | 0 | 336 | C+S GST 18% I/P RD | 60.48 | 396.48 | 396.48 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 701 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 11.2 | Mtrs | 105 | 100 | 0 | 0 | 1176 | C+S GST 18% I/P RD | 211.68 | 1387.68 | 1387.68 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 403 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 10.4 | Mtrs | 105 | 100 | 0 | 0 | 1092 | C+S GST 18% I/P RD | 196.56 | 1288.56 | 1288.56 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 703 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 3.7048 | Mtrs | 105 | 100 | 0 | 0 | 389 | C+S GST 18% I/P RD | 70.02 | 459.02 | 459.02 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 404 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 6 | Mtrs | 105 | 100 | 0 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 903 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 2.1905 | Mtrs | 21 | 100 | 0 | 0 | 46 | C+S GST 18% I/P RD | 8.28 | 54.28 | 54.28 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 601 AC Installation & Commissioning - 1 No. | Drain Pipe with Insulation (L) | 4.619 | Mtrs | 21 | 100 | 0 | 0 | 97 | C+S GST 18% I/P RD | 17.46 | 114.46 | 114.46 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 304 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 28.7179 | Mtrs | 19.5 | 100 | 0 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 603 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 5.4872 | Mtrs | 19.5 | 100 | 0 | 0 | 107 | C+S GST 18% I/P RD | 19.26 | 126.26 | 126.26 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 604 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 11.0769 | Mtrs | 19.5 | 100 | 0 | 0 | 216 | C+S GST 18% I/P RD | 38.88 | 254.88 | 254.88 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 402 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 12.5128 | Mtrs | 19.5 | 100 | 0 | 0 | 244 | C+S GST 18% I/P RD | 43.92 | 287.92 | 287.92 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 1003 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 3.7949 | Mtrs | 19.5 | 100 | 0 | 0 | 74 | C+S GST 18% I/P RD | 13.32 | 87.32 | 87.32 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 404 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 9.0769 | Mtrs | 19.5 | 100 | 0 | 0 | 177 | C+S GST 18% I/P RD | 31.86 | 208.86 | 208.86 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 601 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 11.3846 | Mtrs | 19.5 | 100 | 0 | 0 | 222 | C+S GST 18% I/P RD | 39.96 | 261.96 | 261.96 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 802 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 2 | Mtrs | 19.5 | 100 | 0 | 0 | 39 | C+S GST 18% I/P RD | 7.02 | 46.02 | 46.02 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 1002 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 2 | Mtrs | 19.5 | 100 | 0 | 0 | 39 | C+S GST 18% I/P RD | 7.02 | 46.02 | 46.02 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 301 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 21.5897 | Mtrs | 19.5 | 100 | 0 | 0 | 421 | C+S GST 18% I/P RD | 75.78 | 496.78 | 496.78 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 703 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 5.0769 | Mtrs | 19.5 | 100 | 0 | 0 | 99 | C+S GST 18% I/P RD | 17.82 | 116.82 | 116.82 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 302 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 24.4103 | Mtrs | 19.5 | 100 | 0 | 0 | 476 | C+S GST 18% I/P RD | 85.68 | 561.68 | 561.68 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 701 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 13.0769 | Mtrs | 19.5 | 100 | 0 | 0 | 255 | C+S GST 18% I/P RD | 45.9 | 300.9 | 300.9 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 403 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 12.7179 | Mtrs | 19.5 | 100 | 0 | 0 | 248 | C+S GST 18% I/P RD | 44.64 | 292.64 | 292.64 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 303 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 14.1026 | Mtrs | 19.5 | 100 | 0 | 0 | 275 | C+S GST 18% I/P RD | 49.5 | 324.5 | 324.5 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 704 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 10.6154 | Mtrs | 19.5 | 100 | 0 | 0 | 207 | C+S GST 18% I/P RD | 37.26 | 244.26 | 244.26 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 903 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 4.3077 | Mtrs | 19.5 | 100 | 0 | 0 | 84 | C+S GST 18% I/P RD | 15.12 | 99.12 | 99.12 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 502 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 9.7949 | Mtrs | 19.5 | 100 | 0 | 0 | 191 | C+S GST 18% I/P RD | 34.38 | 225.38 | 225.38 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 702 AC Installation & Commissioning - 1 No. | Cable 4C for Indoor to Outdoor (L) | 2.7179 | Mtrs | 19.5 | 100 | 0 | 0 | 53 | C+S GST 18% I/P RD | 9.54 | 62.54 | 62.54 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 532 | 89992 | 24 Apr 2021 |  | NEPTUNE ENGINEERS | NEPTUNE ENGINEERS | EV - 90 | A 903 AC Installation & Commissioning - 1 No. | Copper Piping with Insulation for 1to1.5 Ton (L) | 3.5048 | Mtrs | 105 | 100 | 0 | 0 | 368 | C+S GST 18% I/P RD | 66.24 | 434.24 | 434.24 | Approved | 0 | 0 | 209 | 24 Apr 2021
GANGA DHAM TOWERS | 186 | 89991 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 80 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 182.4992 | Day | 451.613 | 100 | 0 | 0 | 82419 | C+S GST 18% I/P RD | 14835.42 | 97254.42 | 97254.42 | Approved | 0 | 0 | 1004 | 24 Apr 2021
GANGA DHAM TOWERS | 186 | 89991 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 80 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 31 | Day | 580.645 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 1004 | 24 Apr 2021
GANGA DHAM TOWERS | 745 | 89990 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 81 | B 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 30.4998 | Day | 451.61 | 100 | 0 | 0 | 13774 | C+S GST 18% I/P RD | 2479.32 | 16253.32 | 16253.32 | Approved | 0 | 0 | 138 | 24 Apr 2021
GANGA DHAM TOWERS | 480 | 89989 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 82 | A 3rd (Sample) Floor Housekeeping Work | Housekeeping work (L) | 27.4994 | Day | 451.61 | 100 | 0 | 0 | 12419 | C+S GST 18% I/P RD | 2235.42 | 14654.42 | 14654.42 | Approved | 0 | 0 | 124 | 24 Apr 2021
GANGA DHAM TOWERS | 187 | 89988 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 84 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 24 Apr 2021
GANGA DHAM TOWERS | 187 | 89988 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 84 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 24 Apr 2021
GANGA DHAM TOWERS | 747 | 89987 | 24 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 83 | Sales Office-Waterbody Maintenance | Maintainance Material | 0.95 | Month | 1000 | 100 | 0 | 0 | 950 | C+S GST 18% I/P RD | 171 | 1121 | 1121 | Approved | 0 | 0 | 0 | 24 Apr 2021
GANGA DHAM TOWERS | 497 | 89975 | 23 Apr 2021 | 41 | J K INTERIOR | J K INTERIOR | EV - 551 | B 1902 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 193 | 23 Apr 2021
GANGA DHAM TOWERS | 497 | 89975 | 23 Apr 2021 | 41 | J K INTERIOR | J K INTERIOR | EV - 551 | B 1902 Gypsum Plaster | Gypsum on Wall (L) | 3581.25 | Sq.Ft | 4 | 100 | 358.13 | 0 | 14325 | C+S GST 18% I/P RD | 2578.5 | 16903.5 | 16903.5 | Approved | 0 | 0 | 193 | 23 Apr 2021
GANGA DHAM TOWERS | 368 | 89965 | 22 Apr 2021 |  | VATSA ENGINEERING | GURUDATTA KRUPA ENTERPRISES | EV - 67 | Tower-A Terrace Safety Railing 4th Floor to 26th Floor | Fabrication Work (L) - BCo | 771 | Kgs | 11 | 100 | 212.03 | 0 | 8481 | C+S GST 18% I/P RD | 1526.58 | 10007.58 | 10007.58 | Approved | 0 | 0 | 138 | 22 Apr 2021
GANGA DHAM TOWERS | 368 | 89965 | 22 Apr 2021 |  | VATSA ENGINEERING | GURUDATTA KRUPA ENTERPRISES | EV - 67 | Tower-A Terrace Safety Railing 4th Floor to 26th Floor | Nails | 6 | Kgs | 90 | 100 | 0 | 0 | 540 | C+S GST 18% I/P RD | 97.2 | 637.2 | 637.2 | Approved | 0 | 0 | 138 | 22 Apr 2021
GANGA DHAM TOWERS | 368 | 89965 | 22 Apr 2021 |  | VATSA ENGINEERING | GURUDATTA KRUPA ENTERPRISES | EV - 67 | Tower-A Terrace Safety Railing 4th Floor to 26th Floor | Hold Fast Patti- DSP | 480 | No. | 10 | 100 | 120 | 0 | 4800 | C+S GST 18% I/P RD | 864 | 5664 | 5664 | Approved | 0 | 0 | 138 | 22 Apr 2021
GANGA DHAM TOWERS | 987 | 89953 | 22 Apr 2021 |  | HI TEK INDUSTRIES | HI TEK INDUSTRIES | EV - 133 | DA Development Carpentary work | Folding Door (M+L) | 2 | No. | 12300 | 100 | 615 | 0 | 24600 | C+S GST 18% I/P RD | 4428 | 29028 | 29028 | Approved | 0 | 0 | 476 | 22 Apr 2021
GANGA DHAM TOWERS | 987 | 89953 | 22 Apr 2021 |  | HI TEK INDUSTRIES | HI TEK INDUSTRIES | EV - 133 | DA Development Carpentary work | Galv. Folding door (m+l)-BC | 67.5 | Sq.Ft | 340 | 100 | 573.75 | 0 | 22950 | C+S GST 18% I/P RD | 4131 | 27081 | 27081 | Approved | 0 | 0 | 476 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1400 | 25 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 55.3 | No. | 200 | 25 | 69.13 | 0 | 2765 | C+S GST 18% I/P RD | 497.7 | 3262.7 | 3262.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | 6 AMP Plug point (Independent) | 37.1 | No. | 200 | 25 | 46.38 | 0 | 1855 | C+S GST 18% I/P RD | 333.9 | 2188.9 | 2188.9 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | 6 AMP Plug point (Independent) | 58.8 | No. | 200 | 25 | 73.5 | 0 | 2940 | C+S GST 18% I/P RD | 529.2 | 3469.2 | 3469.2 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | TV/Tel DB Fixing | 0.7 | No. | 500 | 25 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 9.1 | No. | 67 | 25 | 3.81 | 0 | 152.43 | C+S GST 18% I/P RD | 27.44 | 179.87 | 179.87 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 10.5 | No. | 67 | 25 | 4.4 | 0 | 175.88 | C+S GST 18% I/P RD | 31.66 | 207.54 | 207.54 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | Exhaust Fan Point | 3.5 | No. | 200 | 25 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | Exhaust Fan Point | 5.6 | No. | 200 | 25 | 7 | 0 | 280 | C+S GST 18% I/P RD | 50.4 | 330.4 | 330.4 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | 8 Way TPN DB | 0.7 | No. | 1300 | 25 | 5.69 | 0 | 227.5 | C+S GST 18% I/P RD | 40.96 | 268.46 | 268.46 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35.7 | No. | 200 | 25 | 44.63 | 0 | 1785 | C+S GST 18% I/P RD | 321.3 | 2106.3 | 2106.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1.4 | No. | 220 | 25 | 1.93 | 0 | 77 | C+S GST 18% I/P RD | 13.86 | 90.86 | 90.86 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2.1 | No. | 220 | 25 | 2.89 | 0 | 115.5 | C+S GST 18% I/P RD | 20.8 | 136.3 | 136.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | Secondary Light Points (Looping) | 30.1 | No. | 67 | 25 | 12.6 | 0 | 504.18 | C+S GST 18% I/P RD | 90.76 | 594.94 | 594.94 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | Secondary Light Points (Looping) | 38.5 | No. | 67 | 25 | 16.12 | 0 | 644.88 | C+S GST 18% I/P RD | 116.08 | 760.96 | 760.96 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | Fan Point | 7.7 | No. | 200 | 25 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | Fan Point | 6.3 | No. | 200 | 25 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1401 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | AC Point BC | 6.3 | No. | 220 | 25 | 8.66 | 0 | 346.5 | C+S GST 18% I/P RD | 62.38 | 408.88 | 408.88 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | AC Point BC | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1002 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | Data Point | 2.8 | No. | 220 | 25 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | Data Point | 4.9 | No. | 220 | 25 | 6.74 | 0 | 269.5 | C+S GST 18% I/P RD | 48.52 | 318.02 | 318.02 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1801 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 202 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 401 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 901 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 801 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1301 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1202 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 101 Internal Electrical Work | Telephone Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 302 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 1302 Internal Electrical Work | Telephone Point | 3.5 | No. | 220 | 25 | 4.81 | 0 | 192.5 | C+S GST 18% I/P RD | 34.66 | 227.16 | 227.16 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 902 Internal Electrical Work | TV Point | 4.2 | No. | 220 | 25 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 399 | 89952 | 22 Apr 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 134 | B Bldg Flat No. 301 Internal Electrical Work | TV Point | 5.6 | No. | 220 | 25 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 2117 | 22 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 301 Dado (L) | Dado Fixing | 60 | Sq.Ft | 13 | 100 | 19.5 | 0 | 780 | C+S GST 0% I/P RD | 0 | 780 | 780 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 202 Dado (L) | Dado Fixing | 42 | Sq.Ft | 13 | 100 | 13.65 | 0 | 546 | C+S GST 0% I/P RD | 0 | 546 | 546 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 202 Dado (L) | Dado Fixing | 190 | Sq.Ft | 13 | 100 | 61.75 | 0 | 2470 | C+S GST 0% I/P RD | 0 | 2470 | 2470 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 105 Dado (L) | Dado Fixing | 57 | Sq.Ft | 13 | 100 | 18.53 | 0 | 741 | C+S GST 0% I/P RD | 0 | 741 | 741 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 102 Dado (L) | Dado Fixing | 42 | Sq.Ft | 13 | 100 | 13.65 | 0 | 546 | C+S GST 0% I/P RD | 0 | 546 | 546 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 401 Dado (L) | Dado Fixing | 60 | Sq.Ft | 13 | 100 | 19.5 | 0 | 780 | C+S GST 0% I/P RD | 0 | 780 | 780 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 201 Dado (L) | Dado Fixing | 60 | Sq.Ft | 13 | 100 | 19.5 | 0 | 780 | C+S GST 0% I/P RD | 0 | 780 | 780 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 201 Dado (L) | Dado Fixing | 270 | Sq.Ft | 13 | 100 | 87.75 | 0 | 3510 | C+S GST 0% I/P RD | 0 | 3510 | 3510 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 502 Dado (L) | Dado Fixing | 42 | Sq.Ft | 13 | 100 | 13.65 | 0 | 546 | C+S GST 0% I/P RD | 0 | 546 | 546 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 101 Dado (L) | Dado Fixing | 59 | Sq.Ft | 13 | 100 | 19.18 | 0 | 767 | C+S GST 0% I/P RD | 0 | 767 | 767 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 205 Dado (L) | Dado Fixing | 57 | Sq.Ft | 13 | 100 | 18.53 | 0 | 741 | C+S GST 0% I/P RD | 0 | 741 | 741 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 405 Dado (L) | Dado Fixing | 57 | Sq.Ft | 13 | 100 | 18.53 | 0 | 741 | C+S GST 0% I/P RD | 0 | 741 | 741 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 501 Dado (L) | Dado Fixing | 60 | Sq.Ft | 13 | 100 | 19.5 | 0 | 780 | C+S GST 0% I/P RD | 0 | 780 | 780 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 505 Dado (L) | Dado Fixing | 57 | Sq.Ft | 13 | 100 | 18.53 | 0 | 741 | C+S GST 0% I/P RD | 0 | 741 | 741 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 305 Dado (L) | Dado Fixing | 57 | Sq.Ft | 13 | 100 | 18.53 | 0 | 741 | C+S GST 0% I/P RD | 0 | 741 | 741 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 402 Dado (L) | Dado Fixing | 42 | Sq.Ft | 13 | 100 | 13.65 | 0 | 546 | C+S GST 0% I/P RD | 0 | 546 | 546 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 792 | 89945 | 21 Apr 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 58 | D 302 Dado (L) | Dado Fixing | 42 | Sq.Ft | 13 | 100 | 13.65 | 0 | 546 | C+S GST 0% I/P RD | 0 | 546 | 546 | Approved | 0 | 0 | 163 | 21 Apr 2021
GANGA DHAM TOWERS | 929 | 89942 | 21 Apr 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 56 | B Bldg 30th Slab Pumping Charges | Pumping Charges-BC | 221 | Cu.Mtrs | 190 | 100 | 0 | 0 | 41990 | C+S GST 18% I/P RD | 7558.2 | 49548.2 | 49548.2 | Approved | 0 | 0 | 2345 | 21 Apr 2021
GANGA DHAM TOWERS | 929 | 89942 | 21 Apr 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 56 | B Bldg 31st Slab Pumping Charges | Pumping Charges-BC | 132 | Cu.Mtrs | 190 | 100 | 0 | 0 | 25080 | C+S GST 18% I/P RD | 4514.4 | 29594.4 | 29594.4 | Approved | 0 | 0 | 2345 | 21 Apr 2021
GANGA DHAM TOWERS | 929 | 89942 | 21 Apr 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 56 | B Bldg 32nd Slab Pumping Charges | Pumping Charges-BC | 120 | Cu.Mtrs | 190 | 100 | 0 | 0 | 22800 | C+S GST 18% I/P RD | 4104 | 26904 | 26904 | Approved | 0 | 0 | 2345 | 21 Apr 2021
GANGA DHAM TOWERS | 929 | 89942 | 21 Apr 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 56 | B Bldg 32nd Slab Pumping Charges | Pumping Charges-BC | 144 | Cu.Mtrs | 190 | 100 | 0 | 0 | 27360 | C+S GST 18% I/P RD | 4924.8 | 32284.8 | 32284.8 | Approved | 0 | 0 | 2345 | 21 Apr 2021
GANGA DHAM TOWERS | 928 | 89941 | 21 Apr 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 55 | A Bldg 31st Slab Pumping Charges | Pumping Charges-BC | 121 | Cu.Mtrs | 190 | 100 | 0 | 0 | 22990 | C+S GST 18% I/P RD | 4138.2 | 27128.2 | 27128.2 | Approved | 0 | 0 | 2215 | 21 Apr 2021
GANGA DHAM TOWERS | 928 | 89941 | 21 Apr 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 55 | A Bldg 31st Slab Pumping Charges - 462.42 Cu.Mtrs | Pumping Charges-BC | 210 | Cu.Mtrs | 190 | 100 | 0 | 0 | 39900 | C+S GST 18% I/P RD | 7182 | 47082 | 47082 | Approved | 0 | 0 | 2215 | 21 Apr 2021
GANGA DHAM TOWERS | 928 | 89941 | 21 Apr 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 55 | A Bldg 31st Slab Pumping Charges - 462.42 Cu.Mtrs | Pumping Charges-BC | 252 | Cu.Mtrs | 190 | 100 | 0 | 0 | 47880 | C+S GST 18% I/P RD | 8618.4 | 56498.4 | 56498.4 | Approved | 0 | 0 | 2215 | 21 Apr 2021
GANGA DHAM TOWERS | 632 | 89909 | 20 Apr 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 191 | A 304 Gypsum Board False Ceiling | Gypsum Board False Ceiling (L) | 200 | Sq.Ft | 15 | 100 | 75 | 0 | 3000 | C+S GST 18% I/P RD | 540 | 3540 | 3540 | Approved | 0 | 0 | 30 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 704 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20 | R.Ft | 50 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 903 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 30 | R.Ft | 50 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 1204 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20 | R.Ft | 50 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 703 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 30 | R.Ft | 50 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 703 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.705 | R.Ft | 700 | 100 | 47.34 | 0 | 1893.5 | C+S GST 18% I/P RD | 340.84 | 2234.34 | 2234.34 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 1003 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.76 | R.Ft | 700 | 100 | 48.3 | 0 | 1932 | C+S GST 18% I/P RD | 347.76 | 2279.76 | 2279.76 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 1003 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.705 | R.Ft | 700 | 100 | 47.34 | 0 | 1893.5 | C+S GST 18% I/P RD | 340.84 | 2234.34 | 2234.34 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 1204 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 700 | 100 | 25.81 | 0 | 1032.5 | C+S GST 18% I/P RD | 185.86 | 1218.36 | 1218.36 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 1204 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 700 | 100 | 48.83 | 0 | 1953 | C+S GST 18% I/P RD | 351.54 | 2304.54 | 2304.54 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 703 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.76 | R.Ft | 700 | 100 | 48.3 | 0 | 1932 | C+S GST 18% I/P RD | 347.76 | 2279.76 | 2279.76 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 704 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 700 | 100 | 25.81 | 0 | 1032.5 | C+S GST 18% I/P RD | 185.86 | 1218.36 | 1218.36 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 704 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 700 | 100 | 48.83 | 0 | 1953 | C+S GST 18% I/P RD | 351.54 | 2304.54 | 2304.54 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 204 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 650 | 100 | 23.97 | 0 | 958.75 | C+S GST 18% I/P RD | 172.58 | 1131.33 | 1131.33 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 604 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 650 | 100 | 23.97 | 0 | 958.75 | C+S GST 18% I/P RD | 172.58 | 1131.33 | 1131.33 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 403 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.705 | R.Ft | 650 | 100 | 43.96 | 0 | 1758.25 | C+S GST 18% I/P RD | 316.48 | 2074.73 | 2074.73 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 404 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 1.475 | R.Ft | 650 | 100 | 23.97 | 0 | 958.75 | C+S GST 18% I/P RD | 172.58 | 1131.33 | 1131.33 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 603 Powder Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.705 | R.Ft | 650 | 100 | 43.96 | 0 | 1758.25 | C+S GST 18% I/P RD | 316.48 | 2074.73 | 2074.73 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 604 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 650 | 100 | 45.34 | 0 | 1813.5 | C+S GST 18% I/P RD | 326.44 | 2139.94 | 2139.94 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 204 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20 | R.Ft | 45 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 204 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.79 | R.Ft | 650 | 100 | 45.34 | 0 | 1813.5 | C+S GST 18% I/P RD | 326.44 | 2139.94 | 2139.94 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 603 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.76 | R.Ft | 650 | 100 | 44.85 | 0 | 1794 | C+S GST 18% I/P RD | 322.92 | 2116.92 | 2116.92 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 403 Master Toilet Counter wash Basin | Italian Marble Counter - Mkt | 2.76 | R.Ft | 650 | 100 | 44.85 | 0 | 1794 | C+S GST 18% I/P RD | 322.92 | 2116.92 | 2116.92 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 604 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20 | R.Ft | 45 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 403 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 15 | R.Ft | 45 | 100 | 16.88 | 0 | 675 | C+S GST 18% I/P RD | 121.5 | 796.5 | 796.5 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 603 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 551 | 89907 | 20 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 129 | A 404 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 15 | R.Ft | 45 | 100 | 16.88 | 0 | 675 | C+S GST 18% I/P RD | 121.5 | 796.5 | 796.5 | Approved | 0 | 0 | 367 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 602 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.792 | Sq.Ft | 13 | 100 | 15.53 | 0 | 621.3 | C+S GST 18% I/P RD | 111.84 | 733.14 | 733.14 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 602 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.608 | Sq.Ft | 13 | 100 | 12.87 | 0 | 514.9 | C+S GST 18% I/P RD | 92.68 | 607.58 | 607.58 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 602 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 36.104 | Sq.Ft | 13 | 100 | 11.73 | 0 | 469.35 | C+S GST 18% I/P RD | 84.48 | 553.83 | 553.83 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 602 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 34.872 | Sq.Ft | 13 | 100 | 11.33 | 0 | 453.34 | C+S GST 18% I/P RD | 81.6 | 534.94 | 534.94 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 602 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 34.448 | Sq.Ft | 13 | 100 | 11.2 | 0 | 447.82 | C+S GST 18% I/P RD | 80.6 | 528.42 | 528.42 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 602 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.792 | Sq.Ft | 13 | 100 | 15.53 | 0 | 621.3 | C+S GST 18% I/P RD | 111.84 | 733.14 | 733.14 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 1402 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 34.448 | Sq.Ft | 21 | 100 | 18.09 | 0 | 723.41 | C+S GST 18% I/P RD | 130.22 | 853.63 | 853.63 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 1402 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 34.872 | Sq.Ft | 21 | 100 | 18.31 | 0 | 732.31 | C+S GST 18% I/P RD | 131.82 | 864.13 | 864.13 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 1402 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 39.608 | Sq.Ft | 21 | 100 | 20.79 | 0 | 831.77 | C+S GST 18% I/P RD | 149.72 | 981.49 | 981.49 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 1402 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.792 | Sq.Ft | 21 | 100 | 25.09 | 0 | 1003.63 | C+S GST 18% I/P RD | 180.66 | 1184.29 | 1184.29 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 537 | 89906 | 20 Apr 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 128 | A 1402 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 47.792 | Sq.Ft | 21 | 100 | 25.09 | 0 | 1003.63 | C+S GST 18% I/P RD | 180.66 | 1184.29 | 1184.29 | Approved | 0 | 0 | 74 | 20 Apr 2021
GANGA DHAM TOWERS | 395 | 89905 | 20 Apr 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 188 | A 304 Dry Balcony ,Kitchen, Common Toilet Tikki Dhada | Tikki Dhada Rate Diff (L) | 200 | Sq.Ft | 5 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 10 | 20 Apr 2021
GANGA DHAM TOWERS | 629 | 89903 | 20 Apr 2021 |  | A K INTERIOR CONTRACTOR (MATERIAL) | A K INTERIOR CONTRACTOR (MATERIAL) | EV - 189 | A 304 Gypsum Board False Ceiling | Gypsum Board False Ceiling (M) | 200 | Sq.Ft | 50 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 0 | 20 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Fabrication work (M) | 8.09 | Kgs | 57 | 100 | 0 | 0 | 461.13 | CGST 0% URD I/P | 0 | 461.13 | 461.13 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Fabrication work (M) | 21.49 | Kgs | 57 | 100 | 0 | 0 | 1224.93 | CGST 0% URD I/P | 0 | 1224.93 | 1224.93 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Fabrication work (M) | 42.49 | Kgs | 57 | 100 | 0 | 0 | 2421.93 | CGST 0% URD I/P | 0 | 2421.93 | 2421.93 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Hinges (M) | 6 | No. | 15 | 100 | 0 | 0 | 90 | CGST 0% URD I/P | 0 | 90 | 90 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Fabrication work (M) | 489.144 | Kgs | 72 | 100 | 0 | 0 | 35218.37 | CGST 0% URD I/P | 0 | 35218.37 | 35218.37 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Fabrication work (M) | 76.427 | Kgs | 76 | 100 | 0 | 0 | 5808.45 | CGST 0% URD I/P | 0 | 5808.45 | 5808.45 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Self Tamping Screw (M) | 30 | No. | 2.5 | 100 | 0 | 0 | 75 | CGST 0% URD I/P | 0 | 75 | 75 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Fastner (M) - SOSB | 10 | No. | 27 | 100 | 0 | 0 | 270 | CGST 0% URD I/P | 0 | 270 | 270 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1023 | 89898 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 165 | DA Development Top Terrace Ms Work | Lock Patti (M) | 4 | No. | 10 | 100 | 0 | 0 | 40 | CGST 0% URD I/P | 0 | 40 | 40 | Approved | 0 | 0 | 0 | 19 Apr 2021
GANGA DHAM TOWERS | 1022 | 89897 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 166 | DA Development Top Terrace Ms Work | Fabrication work (L) | 21.49 | Kgs | 19.95 | 100 | 10.72 | 0 | 428.73 | CGST 0% URD I/P | 0 | 428.73 | 428.73 | Approved | 0 | 0 | 178 | 19 Apr 2021
GANGA DHAM TOWERS | 1022 | 89897 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 166 | DA Development Top Terrace Ms Work | Fabrication work (L) | 8.09 | Kgs | 19.95 | 100 | 4.03 | 0 | 161.4 | CGST 0% URD I/P | 0 | 161.4 | 161.4 | Approved | 0 | 0 | 178 | 19 Apr 2021
GANGA DHAM TOWERS | 1022 | 89897 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 166 | DA Development Top Terrace Ms Work | Fabrication work (L) | 42.49 | Kgs | 19.95 | 100 | 21.19 | 0 | 847.68 | CGST 0% URD I/P | 0 | 847.68 | 847.68 | Approved | 0 | 0 | 178 | 19 Apr 2021
GANGA DHAM TOWERS | 1022 | 89897 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 166 | DA Development Top Terrace Ms Work | Fabrication work (L) | 489.144 | Kgs | 25.2 | 100 | 308.16 | 0 | 12326.43 | CGST 0% URD I/P | 0 | 12326.43 | 12326.43 | Approved | 0 | 0 | 178 | 19 Apr 2021
GANGA DHAM TOWERS | 1022 | 89897 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 166 | DA Development Top Terrace Ms Work | Fabrication work (L) | 76.427 | Kgs | 26.6 | 100 | 50.82 | 0 | 2032.96 | CGST 0% URD I/P | 0 | 2032.96 | 2032.96 | Approved | 0 | 0 | 178 | 19 Apr 2021
GANGA DHAM TOWERS | 1022 | 89897 | 19 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 166 | DA Development Top Terrace Ms Work | Fabrication work Lumpsum - Dld | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 178 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Window Jamb - Mkt | 147.65 | R.Ft | 90 | 100 | 332.21 | 0 | 13288.5 | C+S GST 18% I/P RD | 2391.94 | 15680.44 | 15680.44 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Skirting | 988.38 | R.Ft | 90 | 100 | 2223.86 | 0 | 88954.2 | C+S GST 18% I/P RD | 16011.76 | 104965.96 | 104965.96 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Champher Polish (L) | 757.22 | R.Ft | 85 | 100 | 1609.09 | 0 | 64363.7 | C+S GST 18% I/P RD | 11585.46 | 75949.16 | 75949.16 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Tile Cutting work | 103.08 | R.Ft | 20 | 100 | 51.54 | 0 | 2061.6 | C+S GST 18% I/P RD | 371.08 | 2432.68 | 2432.68 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Italian Marble Border-BCo | 49.08 | R.Ft | 105 | 100 | 128.84 | 0 | 5153.4 | C+S GST 18% I/P RD | 927.62 | 6081.02 | 6081.02 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Acid Wash | 3196.26 | Sq.Ft | 5 | 100 | 399.53 | 0 | 15981.3 | C+S GST 18% I/P RD | 2876.64 | 18857.94 | 18857.94 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Zero Point Joint Making | 55.97 | R.Ft | 200 | 100 | 279.85 | 0 | 11194 | C+S GST 18% I/P RD | 2014.92 | 13208.92 | 13208.92 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Grill Jali Fitting | 12.66 | R.Ft | 100 | 100 | 31.65 | 0 | 1266 | C+S GST 18% I/P RD | 227.88 | 1493.88 | 1493.88 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Marble Mirror Polish | 70.06 | Sq.Ft | 65 | 100 | 113.85 | 0 | 4553.9 | C+S GST 18% I/P RD | 819.7 | 5373.6 | 5373.6 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Marble Mirror Polish | 2.16 | Sq.Ft | 65 | 100 | 3.51 | 0 | 140.4 | C+S GST 18% I/P RD | 25.28 | 165.68 | 165.68 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | V Grove - BCo | 836.99 | R.Ft | 120 | 100 | 2510.97 | 0 | 100438.8 | C+S GST 18% I/P RD | 18078.98 | 118517.78 | 118517.78 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Tile Grouting-DCH - | 2780.22 | Sq.Ft | 15 | 100 | 1042.58 | 0 | 41703.3 | C+S GST 18% I/P RD | 7506.6 | 49209.9 | 49209.9 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Shelf | 73.18 | Sq.Ft | 90 | 100 | 164.66 | 0 | 6586.2 | C+S GST 18% I/P RD | 1185.52 | 7771.72 | 7771.72 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Italian Marble Shelf | 2.16 | Sq.Ft | 105 | 100 | 5.67 | 0 | 226.8 | C+S GST 18% I/P RD | 40.82 | 267.62 | 267.62 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Top. (L) - BCo | 163.88 | Sq.Ft | 90 | 100 | 368.73 | 0 | 14749.2 | C+S GST 18% I/P RD | 2654.86 | 17404.06 | 17404.06 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Kitchen Counter | 40.39 | R.Ft | 800 | 100 | 807.8 | 0 | 32312 | C+S GST 18% I/P RD | 5816.16 | 38128.16 | 38128.16 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Moulding Polish | 108 | R.Ft | 65 | 100 | 175.5 | 0 | 7020 | C+S GST 18% I/P RD | 1263.6 | 8283.6 | 8283.6 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Vitrified Tile Border | 175.5 | R.Ft | 35 | 100 | 153.56 | 0 | 6142.5 | C+S GST 18% I/P RD | 1105.66 | 7248.16 | 7248.16 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Leather Polish | 255.96 | Sq.Ft | 65 | 100 | 415.94 | 0 | 16637.4 | C+S GST 18% I/P RD | 2994.74 | 19632.14 | 19632.14 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Italian Marble Mirror Polish | 4.16 | R.Ft | 65 | 100 | 6.76 | 0 | 270.4 | C+S GST 18% I/P RD | 48.68 | 319.08 | 319.08 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Edge Polish - Dld | 1517.19 | R.Ft | 35 | 100 | 1327.54 | 0 | 53101.65 | C+S GST 18% I/P RD | 9558.3 | 62659.95 | 62659.95 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Basin Counter | 3 | R.Ft | 1800 | 100 | 135 | 0 | 5400 | C+S GST 18% I/P RD | 972 | 6372 | 6372 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Dado BC | 84.09 | Sq.Ft | 75 | 100 | 157.67 | 0 | 6306.75 | C+S GST 18% I/P RD | 1135.22 | 7441.97 | 7441.97 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Flooring | 298.1 | Sq.Ft | 90 | 100 | 670.73 | 0 | 26829 | C+S GST 18% I/P RD | 4829.22 | 31658.22 | 31658.22 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Granite Dado- ARW | 79.77 | Sq.Ft | 115 | 100 | 229.34 | 0 | 9173.55 | C+S GST 18% I/P RD | 1651.24 | 10824.79 | 10824.79 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Drill Hole | 29 | No. | 130 | 100 | 94.25 | 0 | 3770 | C+S GST 18% I/P RD | 678.6 | 4448.6 | 4448.6 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Vitrified Skirting BC | 85.32 | R.Ft | 50 | 100 | 106.65 | 0 | 4266 | C+S GST 18% I/P RD | 767.88 | 5033.88 | 5033.88 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89896 | 19 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 324 | DA Development Top Terrace Tiling work | Nahani Trap Jali Cutting | 5 | No. | 130 | 100 | 16.25 | 0 | 650 | C+S GST 18% I/P RD | 117 | 767 | 767 | Approved | 0 | 0 | 10851 | 19 Apr 2021
GANGA DHAM TOWERS | 485 | 89891 | 16 Apr 2021 |  | R K INTERIOR | R K INTERIOR |  | DA Development Top Terrace Tiling work | Vitrified Flooring work | 426.35 | Sq.Ft | 50 | 100 | 532.94 | 0 | 21317.5 | C+S GST 18% I/P RD | 3837.16 | 25154.66 | 25154.66 |  | 0 | 0 | 1961 | 16 Apr 2021
GANGA DHAM TOWERS | 485 | 89891 | 16 Apr 2021 |  | R K INTERIOR | R K INTERIOR |  | DA Development Top Terrace Tiling work | Vitrified Flooring work | 2192.95 | Sq.Ft | 35 | 100 | 1918.83 | 0 | 76753.25 | C+S GST 18% I/P RD | 13815.58 | 90568.83 | 90568.83 |  | 0 | 0 | 1961 | 16 Apr 2021
GANGA DHAM TOWERS | 778 | 89890 | 16 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 125 | D Build. 7th Floor RCC Patli (L) | Patli (Band)- BC | 674.82 | R.Ft | 12 | 100 | 202.45 | 0 | 8097.84 | C+S GST 18% I/P RD | 1457.62 | 9555.46 | 9555.46 | Approved | 0 | 0 | 162 | 16 Apr 2021
GANGA DHAM TOWERS | 778 | 89890 | 16 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 125 | D Build. 8th Floor RCC Patli (L) | Patli (Band)- BC | 674.82 | R.Ft | 12 | 100 | 202.45 | 0 | 8097.84 | C+S GST 18% I/P RD | 1457.62 | 9555.46 | 9555.46 | Approved | 0 | 0 | 162 | 16 Apr 2021
GANGA DHAM TOWERS | 493 | 89889 | 16 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 124 | D Bldg North Side External Plaster | External Plaster- BC | 1200 | Sq.Ft | 28 | 100 | 840 | 0 | 33600 | C+S GST 18% I/P RD | 6048 | 39648 | 39648 | Approved | 0 | 0 | 336 | 16 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 2nd Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 8th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 7th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 6th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 5th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 12th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 14th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 15th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 11th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 4th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 13th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 9th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 10th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 16th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 17th Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 767 | 89869 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 76 | B Bldg 1st Floor Lift Openings Brickwork&Plaster | Blockwork/ Plaster-BC | 0.2 | No. | 2500 | 100 | 12.5 | 0 | 500 | C+S GST 18% I/P RD | 90 | 590 | 590 | Approved | 0 | 0 | 80 | 15 Apr 2021
GANGA DHAM TOWERS | 652 | 89868 | 15 Apr 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 192 | A GF Podium Drop Pannel Plaster | Gypsum Patta Plaster Rate Diff (L) | 150 | R.Ft | 7.5 | 100 | 28.13 | 0 | 1125 | C+S GST 18% I/P RD | 202.5 | 1327.5 | 1327.5 | Approved | 0 | 0 | 16 | 15 Apr 2021
GANGA DHAM TOWERS | 652 | 89868 | 15 Apr 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 192 | A P1 Podium Drop Pannel Plaster | Gypsum Patta Plaster Rate Diff (L) | 68 | R.Ft | 7.5 | 100 | 12.75 | 0 | 510 | C+S GST 18% I/P RD | 91.8 | 601.8 | 601.8 | Approved | 0 | 0 | 16 | 15 Apr 2021
GANGA DHAM TOWERS | 696 | 89867 | 15 Apr 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 187 | B Ground Floor Column Plaster | Tikki Dhada rate diff. (L) | 1851.41 | Sq.Ft | 5 | 100 | 231.43 | 0 | 9257.05 | C+S GST 18% I/P RD | 1666.26 | 10923.31 | 10923.31 | Approved | 0 | 0 | 232 | 15 Apr 2021
GANGA DHAM TOWERS | 696 | 89867 | 15 Apr 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 187 | B Ground Floor Staircase & Lobby Plaster | Tikki Dhada rate diff. (L) | 680 | Sq.Ft | 5 | 100 | 85 | 0 | 3400 | C+S GST 18% I/P RD | 612 | 4012 | 4012 | Approved | 0 | 0 | 232 | 15 Apr 2021
GANGA DHAM TOWERS | 696 | 89867 | 15 Apr 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 187 | B P1 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 2116.58 | Sq.Ft | 5 | 100 | 264.57 | 0 | 10582.9 | C+S GST 18% I/P RD | 1904.92 | 12487.82 | 12487.82 | Approved | 0 | 0 | 232 | 15 Apr 2021
GANGA DHAM TOWERS | 649 | 89866 | 15 Apr 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR |  | A P1 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 492 | Sq.Ft | 5 | 100 | 61.5 | 0 | 2460 | C+S GST 18% I/P RD | 442.8 | 2902.8 | 2902.8 |  | 0 | 0 | 49 | 15 Apr 2021
GANGA DHAM TOWERS | 649 | 89866 | 15 Apr 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR |  | A Ground Floor Column Plaster | Tikki Dhada rate diff. (L) | 492 | Sq.Ft | 5 | 100 | 61.5 | 0 | 2460 | C+S GST 18% I/P RD | 442.8 | 2902.8 | 2902.8 |  | 0 | 0 | 49 | 15 Apr 2021
GANGA DHAM TOWERS | 694 | 89865 | 15 Apr 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 193 | B P1 Podium Drop Pannel Plaster | Gypsum Patta Plaster Rate Diff (L) | 971 | R.Ft | 7.5 | 100 | 182.06 | 0 | 7282.5 | C+S GST 18% I/P RD | 1310.86 | 8593.36 | 8593.36 | Approved | 0 | 0 | 152 | 15 Apr 2021
GANGA DHAM TOWERS | 694 | 89865 | 15 Apr 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 193 | B GF Podium Drop Pannel Plaster | Gypsum Patta Plaster Rate Diff (L) | 1051.1 | R.Ft | 7.5 | 100 | 197.08 | 0 | 7883.25 | C+S GST 18% I/P RD | 1418.98 | 9302.23 | 9302.23 | Approved | 0 | 0 | 152 | 15 Apr 2021
GANGA DHAM TOWERS | 997 | 89864 | 15 Apr 2021 | fy21-22/sept002 | AQUARIUS WATERPROOFING | AQUARIUS WATERPROOFING | EV - 950 | DA Development Top Terrace Chemical WP | Chemical W/P - Bco | 650 | Sq.Ft | 50 | 100 | 3250 | 0 | 32500 | C+S GST 18% I/P RD | 5850 | 38350 | 38350 | Approved | 0 | 0 | 325 | 15 Apr 2021
GANGA DHAM TOWERS | 1033 | 89863 | 15 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 130 | Mandir to Construction Gate barricating work | Fabrication work (L) | 136.17 | Kgs | 22.8 | 100 | 77.62 | 0 | 3104.68 | CGST 0% URD I/P | 0 | 3104.68 | 3104.68 | Approved | 0 | 0 | 63 | 15 Apr 2021
GANGA DHAM TOWERS | 1033 | 89863 | 15 Apr 2021 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 130 | Mandir to Construction Gate barricating work | G.I Sheet Fixing- SO. | 640 | Sq.Ft | 5 | 100 | 80 | 0 | 3200 | CGST 0% URD I/P | 0 | 3200 | 3200 | Approved | 0 | 0 | 63 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Drill Hole | 2 | No. | 130 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Granite Flooring | 19.79 | Sq.Ft | 90 | 100 | 44.53 | 0 | 1781.1 | C+S GST 18% I/P RD | 320.6 | 2101.7 | 2101.7 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Dado BC | 22.52 | Sq.Ft | 75 | 100 | 42.23 | 0 | 1689 | C+S GST 18% I/P RD | 304.02 | 1993.02 | 1993.02 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Zero Point Joint Making | 64.58 | R.Ft | 200 | 100 | 322.9 | 0 | 12916 | C+S GST 18% I/P RD | 2324.88 | 15240.88 | 15240.88 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Granite Border-BCo | 368.95 | R.Ft | 90 | 100 | 830.14 | 0 | 33205.5 | C+S GST 18% I/P RD | 5977 | 39182.5 | 39182.5 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Demolition work - DER | 28 | Sq.Ft | 30 | 100 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Granite Champher Polish (L) | 22.65 | R.Ft | 85 | 100 | 48.13 | 0 | 1925.25 | C+S GST 18% I/P RD | 346.54 | 2271.79 | 2271.79 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Granite Skirting | 24.48 | R.Ft | 90 | 100 | 55.08 | 0 | 2203.2 | C+S GST 18% I/P RD | 396.58 | 2599.78 | 2599.78 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | Civil Work- | 2 | No. | 3000 | 100 | 150 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1032 | 89862 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 326 | DA Development Top Terrace Tiling work | V Grove - BCo | 43.16 | R.Ft | 120 | 100 | 129.48 | 0 | 5179.2 | C+S GST 18% I/P RD | 932.26 | 6111.46 | 6111.46 | Approved | 0 | 0 | 1320 | 15 Apr 2021
GANGA DHAM TOWERS | 1017 | 89861 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 77 | Podium Floor Brickwork | Vertical Stiffener | 90.75 | R.Ft | 50 | 100 | 113.44 | 0 | 4537.5 | C+S GST 18% I/P RD | 816.76 | 5354.26 | 5354.26 | Approved | 0 | 0 | 456 | 15 Apr 2021
GANGA DHAM TOWERS | 1017 | 89861 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 77 | Podium Floor Brickwork | Brickwork 9" BC | 412.75 | Sq.Ft | 20 | 100 | 206.38 | 0 | 8255 | C+S GST 18% I/P RD | 1485.9 | 9740.9 | 9740.9 | Approved | 0 | 0 | 456 | 15 Apr 2021
GANGA DHAM TOWERS | 1017 | 89861 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 77 | Podium Floor Brickwork | Patli (Band)- BC | 94 | R.Ft | 12 | 100 | 28.2 | 0 | 1128 | C+S GST 18% I/P RD | 203.04 | 1331.04 | 1331.04 | Approved | 0 | 0 | 456 | 15 Apr 2021
GANGA DHAM TOWERS | 1017 | 89861 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 77 | Podium Floor Brickwork | Patli (Band)- BC | 380 | R.Ft | 12 | 100 | 114 | 0 | 4560 | C+S GST 18% I/P RD | 820.8 | 5380.8 | 5380.8 | Approved | 0 | 0 | 456 | 15 Apr 2021
GANGA DHAM TOWERS | 1017 | 89861 | 15 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 77 | Podium Floor Brickwork | Brickwork 4" BC | 1507.56 | Sq.Ft | 18 | 100 | 678.4 | 0 | 27136.08 | C+S GST 18% I/P RD | 4884.5 | 32020.58 | 32020.58 | Approved | 0 | 0 | 456 | 15 Apr 2021
GANGA DHAM TOWERS | 989 | 89860 | 15 Apr 2021 |  | MSIMPLY AIR COOLING PRIVATE LIMITED | MSIMPLY AIR COOLING PRIVATE LIMITED | EV - 432 | Sales Office Dismentling Work (L) | Dismentalling work-UTI | 1 | No. | 2000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 40 | 15 Apr 2021
GANGA DHAM TOWERS | 1007 | 89859 | 15 Apr 2021 |  | VEER BHADRA ENTERPRISES | VEER BHADRA ENTERPRISES | EV - 75 | A 204 Painting Sample | Painting Work (Lumpsum) ARW | 1 | No. | 6000 | 100 | 0 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 60 | 15 Apr 2021
GANGA DHAM TOWERS | 940 | 89858 | 15 Apr 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 131 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 220 | 15 Apr 2021
GANGA DHAM TOWERS | 485 | 89857 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 325 | DA Development Top Terrace Tiling work | Department Labour - Day | 15 | Day | 1100 | 100 | 412.5 | 0 | 16500 | C+S GST 18% I/P RD | 2970 | 19470 | 19470 | Approved | 0 | 0 | 678 | 15 Apr 2021
GANGA DHAM TOWERS | 485 | 89857 | 15 Apr 2021 |  | R K INTERIOR | R K INTERIOR | EV - 325 | DA Development Top Terrace Tiling work | Dado BC | 232.04 | Sq.Ft | 75 | 100 | 435.08 | 0 | 17403 | C+S GST 18% I/P RD | 3132.54 | 20535.54 | 20535.54 | Approved | 0 | 0 | 678 | 15 Apr 2021
GANGA DHAM TOWERS | 758 | 89856 | 15 Apr 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 63 | B 1401 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1154 | Sq.Ft | 55 | 100 | 1586.75 | 0 | 63470 | C+S GST 18% I/P RD | 11424.6 | 74894.6 | 74894.6 | Approved | 0 | 0 | 1042 | 15 Apr 2021
GANGA DHAM TOWERS | 758 | 89856 | 15 Apr 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 63 | B 1401 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 305 | Sq.Ft | 55 | 100 | 419.38 | 0 | 16775 | C+S GST 18% I/P RD | 3019.5 | 19794.5 | 19794.5 | Approved | 0 | 0 | 1042 | 15 Apr 2021
GANGA DHAM TOWERS | 758 | 89856 | 15 Apr 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 63 | B 1401 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 193 | Sq.Ft | 55 | 100 | 265.38 | 0 | 10615 | C+S GST 18% I/P RD | 1910.7 | 12525.7 | 12525.7 | Approved | 0 | 0 | 1042 | 15 Apr 2021
GANGA DHAM TOWERS | 758 | 89856 | 15 Apr 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 63 | B 1401 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 55 | 100 | 334.13 | 0 | 13365 | C+S GST 18% I/P RD | 2405.7 | 15770.7 | 15770.7 | Approved | 0 | 0 | 1042 | 15 Apr 2021
GANGA DHAM TOWERS | 495 | 89850 | 14 Apr 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 34 | B 1801 Gypsum Plaster | Dhar Core (L) | 685 | R.Ft | 10 | 100 | 171.25 | 0 | 6850 | C+S GST 18% I/P RD | 1233 | 8083 | 8083 | Approved | 0 | 0 | 295 | 14 Apr 2021
GANGA DHAM TOWERS | 495 | 89850 | 14 Apr 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 34 | B 1801 Gypsum Plaster | Gypsum on Wall (L) | 5658 | Sq.Ft | 4 | 100 | 565.8 | 0 | 22632 | C+S GST 18% I/P RD | 4073.76 | 26705.76 | 26705.76 | Approved | 0 | 0 | 295 | 14 Apr 2021
GANGA DHAM TOWERS | 1037 | 89816 | 12 Apr 2021 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 26 | Head Office Security Service | Security Guard AIE - | 62 | Day | 419.35 | 100 | 0 | 0 | 25999.7 | C+S GST 18% I/P RD | 4679.94 | 30679.64 | 30679.64 | Approved | 0 | 0 | 260 | 12 Apr 2021
GANGA DHAM TOWERS | 1037 | 89815 | 12 Apr 2021 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 25 | Head Office Security Service | Security Guard AIE - | 56 | Day | 464.28 | 100 | 0 | 0 | 25999.68 | C+S GST 18% I/P RD | 4679.94 | 30679.62 | 30679.62 | Approved | 0 | 0 | 260 | 12 Apr 2021
GANGA DHAM TOWERS | 1037 | 89814 | 12 Apr 2021 |  | OM SECURITY SERVICES | OM SECURITY SERVICES | EV - 24 | Head Office Security Service | Security Guard AIE - | 62 | Day | 419.35 | 100 | 0 | 0 | 25999.7 | C+S GST 18% I/P RD | 4679.94 | 30679.64 | 30679.64 | Approved | 0 | 0 | 260 | 12 Apr 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.5 | C+S GST 18% I/P RD | 172.54 | 1131.04 | 1131.04 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 446 | 89801 | 31 Mar 2021 |  | TRIDENT SERVICES PRIVATE LIMITED | TRIDENT SERVICES PRIVATE LIMITED | EV - 2475 | DG Annual Maintenance Charges | AMC Charges | 18 | Month | 958.334 | 5.56 | 0 | 0 | 958.32 | C+S GST 18% I/P RD | 172.5 | 1130.82 | 1130.82 | Approved | 0 | 0 | 230 | 31 Mar 2021
GANGA DHAM TOWERS | 744 | 89799 | 12 Apr 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 157 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 0 | 12 Apr 2021
GANGA DHAM TOWERS | 1030 | 89798 | 12 Apr 2021 |  | A K ENTERPRISES | A K ENTERPRISES | EV - 126 | Sales Office Wooden Flooring Work | Wooden Flooring(L)- BC | 300 | Sq.Ft | 12 | 100 | 0 | 0 | 3600 | C+S GST 18% I/P RD | 648 | 4248 | 4248 | Approved | 0 | 0 | 61 | 12 Apr 2021
GANGA DHAM TOWERS | 1030 | 89798 | 12 Apr 2021 |  | A K ENTERPRISES | A K ENTERPRISES | EV - 126 | Sales Office Wooden Flooring Work | Material Charges | 8 | No. | 265 | 100 | 0 | 0 | 2120 | C+S GST 18% I/P RD | 381.6 | 2501.6 | 2501.6 | Approved | 0 | 0 | 61 | 12 Apr 2021
GANGA DHAM TOWERS | 1030 | 89798 | 12 Apr 2021 |  | A K ENTERPRISES | A K ENTERPRISES | EV - 126 | Sales Office Wooden Flooring Work | Material Charges | 1 | No. | 365 | 100 | 0 | 0 | 365 | C+S GST 18% I/P RD | 65.7 | 430.7 | 430.7 | Approved | 0 | 0 | 61 | 12 Apr 2021
GANGA DHAM TOWERS | 678 | 89797 | 12 Apr 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 414 | A 803 NOC | Concrete Cutting Work | 312 | R.Ft | 525 | 100 | 0 | 0 | 163800 | C+S GST 18% I/P RD | 29484 | 193284 | 193284 | Approved | 0 | 0 | 3276 | 12 Apr 2021
GANGA DHAM TOWERS | 1013 | 89796 | 12 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 78 | A 4th Floor Toilet Window BBM/ Plaster Work | Sponge Plaster - BC | 16 | Sq.Ft | 25 | 100 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 12 | 12 Apr 2021
GANGA DHAM TOWERS | 1013 | 89796 | 12 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 78 | A 3rd Floor Toilet Window BBM/ Plaster Work | Sponge Plaster - BC | 16 | Sq.Ft | 25 | 100 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 12 | 12 Apr 2021
GANGA DHAM TOWERS | 1013 | 89796 | 12 Apr 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 78 | A 2nd Floor Toilet Window BBM/ Plaster Work | Sponge Plaster - BC | 16 | Sq.Ft | 25 | 100 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 12 | 12 Apr 2021
GANGA DHAM TOWERS | 1002 | 89795 | 12 Apr 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 412 | A 1604 NOC - 1 No. | Concrete wall Crushing work | 0.345 | Cu.Mtrs | 7200 | 100 | 0 | 0 | 2484 | C+S GST 18% I/P RD | 447.12 | 2931.12 | 2931.12 | Approved | 0 | 0 | 374 | 12 Apr 2021
GANGA DHAM TOWERS | 1002 | 89795 | 12 Apr 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 412 | A 1604 NOC - 1 No. | Concrete Cutting Work | 30.9 | R.Ft | 525 | 100 | 0 | 0 | 16222.5 | C+S GST 18% I/P RD | 2920.06 | 19142.56 | 19142.56 | Approved | 0 | 0 | 374 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 1204 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20 | R.Ft | 50 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 704 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20 | R.Ft | 50 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 204 Parents Toilet dado | L Groove - BCV | 17.108 | R.Ft | 20 | 100 | 8.55 | 0 | 342.16 | C+S GST 18% I/P RD | 61.58 | 403.74 | 403.74 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 204 Powder Toilet dado | L Groove - BCV | 25.074 | R.Ft | 20 | 100 | 12.54 | 0 | 501.48 | C+S GST 18% I/P RD | 90.26 | 591.74 | 591.74 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 704 Master Toilet dado | L Groove - BCV | 30.03 | R.Ft | 20 | 100 | 15.02 | 0 | 600.6 | C+S GST 18% I/P RD | 108.1 | 708.7 | 708.7 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 704 Parents Toilet dado | L Groove - BCV | 17.108 | R.Ft | 20 | 100 | 8.55 | 0 | 342.16 | C+S GST 18% I/P RD | 61.58 | 403.74 | 403.74 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 704 Children Toilet Dado | L Groove - BCV | 30.1 | R.Ft | 20 | 100 | 15.05 | 0 | 602 | C+S GST 18% I/P RD | 108.36 | 710.36 | 710.36 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 204 Children Toilet Dado | L Groove - BCV | 30.1 | R.Ft | 20 | 100 | 15.05 | 0 | 602 | C+S GST 18% I/P RD | 108.36 | 710.36 | 710.36 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 204 Staff Toilet dado | L Groove - BCV | 17.059 | R.Ft | 20 | 100 | 8.53 | 0 | 341.18 | C+S GST 18% I/P RD | 61.42 | 402.6 | 402.6 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 704 Powder Toilet dado | L Groove - BCV | 25.074 | R.Ft | 20 | 100 | 12.54 | 0 | 501.48 | C+S GST 18% I/P RD | 90.26 | 591.74 | 591.74 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 204 Master Toilet dado | L Groove - BCV | 30.03 | R.Ft | 20 | 100 | 15.02 | 0 | 600.6 | C+S GST 18% I/P RD | 108.1 | 708.7 | 708.7 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 404 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 15 | R.Ft | 45 | 100 | 16.88 | 0 | 675 | C+S GST 18% I/P RD | 121.5 | 796.5 | 796.5 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 604 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20 | R.Ft | 45 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 403 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 15 | R.Ft | 45 | 100 | 16.88 | 0 | 675 | C+S GST 18% I/P RD | 121.5 | 796.5 | 796.5 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 551 | 89794 | 12 Apr 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 127 | A 204 Toilet & Dry Balcony Devider Patti | I Marble Patti - BCo | 20 | R.Ft | 45 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 96 | 12 Apr 2021
GANGA DHAM TOWERS | 371 | 89793 | 12 Apr 2021 |  | CONSTROGENESIS | CONSTROGENESIS | EV - 65 | EWS Bldg Built-up Area Diffrence From 1st to LMR OHWT | RCC Superstructure (B-up area) | 778 | Sq.Ft | 160 | 100 | 3112 | 0 | 124480 | C+S GST 18% I/P RD | 22406.4 | 146886.4 | 146886.4 | Approved | 0 | 0 | 2490 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Children Toilet dado | Dado BC | 93.933 | Sq.Ft | 14 | 100 | 32.88 | 0 | 1315.06 | C+S GST 18% I/P RD | 236.72 | 1551.78 | 1551.78 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Powder Toilet dado | L Groove - BCV | 22.729 | R.Ft | 20 | 100 | 11.36 | 0 | 454.58 | C+S GST 18% I/P RD | 81.82 | 536.4 | 536.4 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Master Toilet dado | L Groove - BCV | 19.355 | R.Ft | 20 | 100 | 9.68 | 0 | 387.1 | C+S GST 18% I/P RD | 69.68 | 456.78 | 456.78 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Children Toilet dado | L Groove - BCV | 26.292 | R.Ft | 20 | 100 | 13.15 | 0 | 525.84 | C+S GST 18% I/P RD | 94.66 | 620.5 | 620.5 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Powder Toilet dado | L Groove - BCV | 24.451 | R.Ft | 20 | 100 | 12.23 | 0 | 489.02 | C+S GST 18% I/P RD | 88.02 | 577.04 | 577.04 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Master Toilet dado | L Groove - BCV | 22.547 | R.Ft | 20 | 100 | 11.27 | 0 | 450.94 | C+S GST 18% I/P RD | 81.16 | 532.1 | 532.1 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Master Toilet dado | L Groove - BCV | 22.547 | R.Ft | 20 | 100 | 11.27 | 0 | 450.94 | C+S GST 18% I/P RD | 81.16 | 532.1 | 532.1 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Parents Toilet dado | L Groove - BCV | 30.079 | R.Ft | 20 | 100 | 15.04 | 0 | 601.58 | C+S GST 18% I/P RD | 108.28 | 709.86 | 709.86 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Parents Toilet dado | L Groove - BCV | 28.357 | R.Ft | 20 | 100 | 14.18 | 0 | 567.14 | C+S GST 18% I/P RD | 102.08 | 669.22 | 669.22 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Powder Toilet dado | L Groove - BCV | 22.729 | R.Ft | 20 | 100 | 11.36 | 0 | 454.58 | C+S GST 18% I/P RD | 81.82 | 536.4 | 536.4 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Master Toilet dado | L Groove - BCV | 19.355 | R.Ft | 20 | 100 | 9.68 | 0 | 387.1 | C+S GST 18% I/P RD | 69.68 | 456.78 | 456.78 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Master Toilet dado | L Groove - BCV | 19.355 | R.Ft | 20 | 100 | 9.68 | 0 | 387.1 | C+S GST 18% I/P RD | 69.68 | 456.78 | 456.78 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Master Toilet dado | L Groove - BCV | 22.547 | R.Ft | 20 | 100 | 11.27 | 0 | 450.94 | C+S GST 18% I/P RD | 81.16 | 532.1 | 532.1 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Children Toilet dado | L Groove - BCV | 26.292 | R.Ft | 20 | 100 | 13.15 | 0 | 525.84 | C+S GST 18% I/P RD | 94.66 | 620.5 | 620.5 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Parents Toilet dado | L Groove - BCV | 28.357 | R.Ft | 20 | 100 | 14.18 | 0 | 567.14 | C+S GST 18% I/P RD | 102.08 | 669.22 | 669.22 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Powder Toilet dado | L Groove - BCV | 24.451 | R.Ft | 20 | 100 | 12.23 | 0 | 489.02 | C+S GST 18% I/P RD | 88.02 | 577.04 | 577.04 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Parents Toilet dado | L Groove - BCV | 30.079 | R.Ft | 20 | 100 | 15.04 | 0 | 601.58 | C+S GST 18% I/P RD | 108.28 | 709.86 | 709.86 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Powder Toilet dado | L Groove - BCV | 24.451 | R.Ft | 20 | 100 | 12.23 | 0 | 489.02 | C+S GST 18% I/P RD | 88.02 | 577.04 | 577.04 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Parents Toilet dado | L Groove - BCV | 28.357 | R.Ft | 20 | 100 | 14.18 | 0 | 567.14 | C+S GST 18% I/P RD | 102.08 | 669.22 | 669.22 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Powder Toilet dado | L Groove - BCV | 24.451 | R.Ft | 20 | 100 | 12.23 | 0 | 489.02 | C+S GST 18% I/P RD | 88.02 | 577.04 | 577.04 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Parents Toilet dado | L Groove - BCV | 30.079 | R.Ft | 20 | 100 | 15.04 | 0 | 601.58 | C+S GST 18% I/P RD | 108.28 | 709.86 | 709.86 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Powder Toilet dado | L Groove - BCV | 22.729 | R.Ft | 20 | 100 | 11.36 | 0 | 454.58 | C+S GST 18% I/P RD | 81.82 | 536.4 | 536.4 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Powder Toilet dado | L Groove - BCV | 24.451 | R.Ft | 20 | 100 | 12.23 | 0 | 489.02 | C+S GST 18% I/P RD | 88.02 | 577.04 | 577.04 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Children Toilet Flooring | Vitrified Flooring -BC | 34.356 | Sq.Ft | 13 | 100 | 11.17 | 0 | 446.63 | C+S GST 18% I/P RD | 80.4 | 527.03 | 527.03 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 34.657 | Sq.Ft | 13 | 100 | 11.26 | 0 | 450.54 | C+S GST 18% I/P RD | 81.1 | 531.64 | 531.64 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 35.224 | Sq.Ft | 13 | 100 | 11.45 | 0 | 457.91 | C+S GST 18% I/P RD | 82.42 | 540.33 | 540.33 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 16.03 | Sq.Ft | 13 | 100 | 5.21 | 0 | 208.39 | C+S GST 18% I/P RD | 37.52 | 245.91 | 245.91 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 30.513 | Sq.Ft | 13 | 100 | 9.92 | 0 | 396.67 | C+S GST 18% I/P RD | 71.4 | 468.07 | 468.07 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 20.527 | R.Ft | 45 | 100 | 23.09 | 0 | 923.72 | C+S GST 18% I/P RD | 166.26 | 1089.98 | 1089.98 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1602 Master Bed Marble Flooring | Italian marble Skirting - BCo | 43.485 | R.Ft | 55 | 100 | 59.79 | 0 | 2391.68 | C+S GST 18% I/P RD | 430.5 | 2822.18 | 2822.18 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 74.4835 | R.Ft | 55 | 100 | 102.41 | 0 | 4096.59 | C+S GST 18% I/P RD | 737.38 | 4833.97 | 4833.97 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 16.03 | Sq.Ft | 17 | 100 | 6.81 | 0 | 272.51 | C+S GST 18% I/P RD | 49.06 | 321.57 | 321.57 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 30.835 | Sq.Ft | 17 | 100 | 13.1 | 0 | 524.2 | C+S GST 18% I/P RD | 94.36 | 618.56 | 618.56 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 36.918 | Sq.Ft | 17 | 100 | 15.69 | 0 | 627.61 | C+S GST 18% I/P RD | 112.96 | 740.57 | 740.57 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 34.657 | Sq.Ft | 17 | 100 | 14.73 | 0 | 589.17 | C+S GST 18% I/P RD | 106.06 | 695.23 | 695.23 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Children Toilet | Dado BC | 34.176 | Sq.Ft | 24 | 100 | 20.51 | 0 | 820.22 | C+S GST 18% I/P RD | 147.64 | 967.86 | 967.86 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Master Toilet dado | Dado BC | 54.224 | Sq.Ft | 24 | 100 | 32.53 | 0 | 1301.38 | C+S GST 18% I/P RD | 234.24 | 1535.62 | 1535.62 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Parents Toilet dado | Dado BC | 65.4 | Sq.Ft | 24 | 100 | 39.24 | 0 | 1569.6 | C+S GST 18% I/P RD | 282.52 | 1852.12 | 1852.12 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Powder Toilet dado | Dado BC | 34.36 | Sq.Ft | 24 | 100 | 20.62 | 0 | 824.64 | C+S GST 18% I/P RD | 148.44 | 973.08 | 973.08 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Parents Toilet dado | L Groove - BCV | 30.079 | R.Ft | 20 | 100 | 15.04 | 0 | 601.58 | C+S GST 18% I/P RD | 108.28 | 709.86 | 709.86 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Children Toilet | L Groove - BCV | 22.729 | R.Ft | 20 | 100 | 11.36 | 0 | 454.58 | C+S GST 18% I/P RD | 81.82 | 536.4 | 536.4 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Master Toilet dado | L Groove - BCV | 22.547 | R.Ft | 20 | 100 | 11.27 | 0 | 450.94 | C+S GST 18% I/P RD | 81.16 | 532.1 | 532.1 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Parents Toilet dado | L Groove - BCV | 30.079 | R.Ft | 20 | 100 | 15.04 | 0 | 601.58 | C+S GST 18% I/P RD | 108.28 | 709.86 | 709.86 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Master Toilet dado | L Groove - BCV | 22.547 | R.Ft | 20 | 100 | 11.27 | 0 | 450.94 | C+S GST 18% I/P RD | 81.16 | 532.1 | 532.1 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 36.918 | Sq.Ft | 13 | 100 | 12 | 0 | 479.93 | C+S GST 18% I/P RD | 86.38 | 566.31 | 566.31 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Children Toilet Flooring | Vitrified Flooring -BC | 39.264 | Sq.Ft | 13 | 100 | 12.76 | 0 | 510.43 | C+S GST 18% I/P RD | 91.88 | 602.31 | 602.31 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 34.872 | Sq.Ft | 13 | 100 | 11.33 | 0 | 453.34 | C+S GST 18% I/P RD | 81.6 | 534.94 | 534.94 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.818 | Sq.Ft | 13 | 100 | 13.59 | 0 | 543.63 | C+S GST 18% I/P RD | 97.86 | 641.49 | 641.49 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 35.24 | Sq.Ft | 13 | 100 | 11.45 | 0 | 458.12 | C+S GST 18% I/P RD | 82.46 | 540.58 | 540.58 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 31.864 | Sq.Ft | 13 | 100 | 10.36 | 0 | 414.23 | C+S GST 18% I/P RD | 74.56 | 488.79 | 488.79 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 42.192 | Sq.Ft | 13 | 100 | 13.71 | 0 | 548.5 | C+S GST 18% I/P RD | 98.74 | 647.24 | 647.24 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 40.256 | Sq.Ft | 13 | 100 | 13.08 | 0 | 523.33 | C+S GST 18% I/P RD | 94.2 | 617.53 | 617.53 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 18.32 | Sq.Ft | 13 | 100 | 5.95 | 0 | 238.16 | C+S GST 18% I/P RD | 42.86 | 281.02 | 281.02 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.818 | Sq.Ft | 13 | 100 | 13.59 | 0 | 543.63 | C+S GST 18% I/P RD | 97.86 | 641.49 | 641.49 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 30.835 | Sq.Ft | 13 | 100 | 10.02 | 0 | 400.86 | C+S GST 18% I/P RD | 72.16 | 473.02 | 473.02 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Children Toilet | Dado BC | 131.901 | Sq.Ft | 22 | 100 | 72.55 | 0 | 2901.82 | C+S GST 18% I/P RD | 522.32 | 3424.14 | 3424.14 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Powder Toilet dado | Dado BC | 66.675 | Sq.Ft | 22 | 100 | 36.67 | 0 | 1466.85 | C+S GST 18% I/P RD | 264.04 | 1730.89 | 1730.89 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Master Toilet dado | Dado BC | 86.457 | Sq.Ft | 22 | 100 | 47.55 | 0 | 1902.05 | C+S GST 18% I/P RD | 342.36 | 2244.41 | 2244.41 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Parents Toilet dado | Dado BC | 106.764 | Sq.Ft | 22 | 100 | 58.72 | 0 | 2348.81 | C+S GST 18% I/P RD | 422.78 | 2771.59 | 2771.59 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Master Toilet dado | Dado BC | 86.457 | Sq.Ft | 14 | 100 | 30.26 | 0 | 1210.4 | C+S GST 18% I/P RD | 217.88 | 1428.28 | 1428.28 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Powder Toilet dado | Dado BC | 34.36 | Sq.Ft | 20 | 100 | 17.18 | 0 | 687.2 | C+S GST 18% I/P RD | 123.7 | 810.9 | 810.9 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Master Toilet dado | Dado BC | 101.968 | Sq.Ft | 14 | 100 | 35.69 | 0 | 1427.55 | C+S GST 18% I/P RD | 256.96 | 1684.51 | 1684.51 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Children Toilet | Dado BC | 131.901 | Sq.Ft | 14 | 100 | 46.17 | 0 | 1846.61 | C+S GST 18% I/P RD | 332.38 | 2178.99 | 2178.99 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Master Toilet dado | Dado BC | 59.072 | Sq.Ft | 20 | 100 | 29.54 | 0 | 1181.44 | C+S GST 18% I/P RD | 212.66 | 1394.1 | 1394.1 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Master Toilet dado | Dado BC | 59.072 | Sq.Ft | 20 | 100 | 29.54 | 0 | 1181.44 | C+S GST 18% I/P RD | 212.66 | 1394.1 | 1394.1 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Parents Toilet dado | Dado BC | 65.4 | Sq.Ft | 20 | 100 | 32.7 | 0 | 1308 | C+S GST 18% I/P RD | 235.44 | 1543.44 | 1543.44 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Parents Toilet dado | Dado BC | 52.112 | Sq.Ft | 20 | 100 | 26.06 | 0 | 1042.24 | C+S GST 18% I/P RD | 187.6 | 1229.84 | 1229.84 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Powder Toilet dado | Dado BC | 68.152 | Sq.Ft | 14 | 100 | 23.85 | 0 | 954.13 | C+S GST 18% I/P RD | 171.74 | 1125.87 | 1125.87 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Parents Toilet dado | Dado BC | 103.838 | Sq.Ft | 14 | 100 | 36.34 | 0 | 1453.73 | C+S GST 18% I/P RD | 261.68 | 1715.41 | 1715.41 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Master Toilet dado | Dado BC | 59.072 | Sq.Ft | 20 | 100 | 29.54 | 0 | 1181.44 | C+S GST 18% I/P RD | 212.66 | 1394.1 | 1394.1 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Parents Toilet dado | Dado BC | 52.112 | Sq.Ft | 20 | 100 | 26.06 | 0 | 1042.24 | C+S GST 18% I/P RD | 187.6 | 1229.84 | 1229.84 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Dry Balcony dado | Dado BC | 55.265 | Sq.Ft | 14 | 100 | 19.34 | 0 | 773.71 | C+S GST 18% I/P RD | 139.26 | 912.97 | 912.97 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Parents Toilet dado | Dado BC | 106.764 | Sq.Ft | 14 | 100 | 37.37 | 0 | 1494.7 | C+S GST 18% I/P RD | 269.04 | 1763.74 | 1763.74 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Parents Toilet dado | Dado BC | 52.112 | Sq.Ft | 20 | 100 | 26.06 | 0 | 1042.24 | C+S GST 18% I/P RD | 187.6 | 1229.84 | 1229.84 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Powder Toilet dado | Dado BC | 31.088 | Sq.Ft | 20 | 100 | 15.54 | 0 | 621.76 | C+S GST 18% I/P RD | 111.92 | 733.68 | 733.68 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Powder Toilet dado | Dado BC | 31.088 | Sq.Ft | 20 | 100 | 15.54 | 0 | 621.76 | C+S GST 18% I/P RD | 111.92 | 733.68 | 733.68 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Master Toilet dado | Dado BC | 89.222 | Sq.Ft | 14 | 100 | 31.23 | 0 | 1249.11 | C+S GST 18% I/P RD | 224.84 | 1473.95 | 1473.95 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Powder Toilet dado | Dado BC | 31.088 | Sq.Ft | 20 | 100 | 15.54 | 0 | 621.76 | C+S GST 18% I/P RD | 111.92 | 733.68 | 733.68 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Powder Toilet dado | Dado BC | 66.675 | Sq.Ft | 14 | 100 | 23.34 | 0 | 933.45 | C+S GST 18% I/P RD | 168.02 | 1101.47 | 1101.47 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Children Toilet dado | Dado BC | 110 | Sq.Ft | 14 | 100 | 38.5 | 0 | 1540 | C+S GST 18% I/P RD | 277.2 | 1817.2 | 1817.2 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Powder Toilet dado | Dado BC | 68.152 | Sq.Ft | 14 | 100 | 23.85 | 0 | 954.13 | C+S GST 18% I/P RD | 171.74 | 1125.87 | 1125.87 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Parents Toilet dado | Dado BC | 103.838 | Sq.Ft | 14 | 100 | 36.34 | 0 | 1453.73 | C+S GST 18% I/P RD | 261.68 | 1715.41 | 1715.41 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Parents Toilet dado | Dado BC | 52.112 | Sq.Ft | 15 | 100 | 19.54 | 0 | 781.68 | C+S GST 18% I/P RD | 140.7 | 922.38 | 922.38 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Children Toilet dado | Dado BC | 60 | Sq.Ft | 15 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Parents Toilet dado | Dado BC | 65.4 | Sq.Ft | 15 | 100 | 24.53 | 0 | 981 | C+S GST 18% I/P RD | 176.58 | 1157.58 | 1157.58 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Powder Toilet dado | Dado BC | 34.36 | Sq.Ft | 15 | 100 | 12.89 | 0 | 515.4 | C+S GST 18% I/P RD | 92.78 | 608.18 | 608.18 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Master Toilet dado | Dado BC | 54.224 | Sq.Ft | 15 | 100 | 20.33 | 0 | 813.36 | C+S GST 18% I/P RD | 146.4 | 959.76 | 959.76 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Powder Toilet dado | Dado BC | 31.088 | Sq.Ft | 15 | 100 | 11.66 | 0 | 466.32 | C+S GST 18% I/P RD | 83.94 | 550.26 | 550.26 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Powder Toilet dado | Dado BC | 27.202 | Sq.Ft | 15 | 100 | 10.2 | 0 | 408.03 | C+S GST 18% I/P RD | 73.44 | 481.47 | 481.47 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 502 Children Toilet | Dado BC | 34.176 | Sq.Ft | 15 | 100 | 12.82 | 0 | 512.64 | C+S GST 18% I/P RD | 92.28 | 604.92 | 604.92 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Master Toilet dado | Dado BC | 59.072 | Sq.Ft | 15 | 100 | 22.15 | 0 | 886.08 | C+S GST 18% I/P RD | 159.5 | 1045.58 | 1045.58 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Parents Toilet dado | Dado BC | 52.112 | Sq.Ft | 15 | 100 | 19.54 | 0 | 781.68 | C+S GST 18% I/P RD | 140.7 | 922.38 | 922.38 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Master Toilet dado | Dado BC | 59.072 | Sq.Ft | 15 | 100 | 22.15 | 0 | 886.08 | C+S GST 18% I/P RD | 159.5 | 1045.58 | 1045.58 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 31.591 | Sq.Ft | 21 | 100 | 16.59 | 0 | 663.41 | C+S GST 18% I/P RD | 119.42 | 782.83 | 782.83 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 30.513 | Sq.Ft | 21 | 100 | 16.02 | 0 | 640.77 | C+S GST 18% I/P RD | 115.34 | 756.11 | 756.11 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.818 | Sq.Ft | 21 | 100 | 21.95 | 0 | 878.18 | C+S GST 18% I/P RD | 158.08 | 1036.26 | 1036.26 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.818 | Sq.Ft | 21 | 100 | 21.95 | 0 | 878.18 | C+S GST 18% I/P RD | 158.08 | 1036.26 | 1036.26 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 34.657 | Sq.Ft | 21 | 100 | 18.19 | 0 | 727.8 | C+S GST 18% I/P RD | 131 | 858.8 | 858.8 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 30.142 | Sq.Ft | 21 | 100 | 15.82 | 0 | 632.98 | C+S GST 18% I/P RD | 113.94 | 746.92 | 746.92 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Parents Toilet dado | Dado BC | 103.838 | Sq.Ft | 18 | 100 | 46.73 | 0 | 1869.08 | C+S GST 18% I/P RD | 336.44 | 2205.52 | 2205.52 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 30.513 | Sq.Ft | 17 | 100 | 12.97 | 0 | 518.72 | C+S GST 18% I/P RD | 93.36 | 612.08 | 612.08 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.818 | Sq.Ft | 17 | 100 | 17.77 | 0 | 710.91 | C+S GST 18% I/P RD | 127.96 | 838.87 | 838.87 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 30.513 | Sq.Ft | 17 | 100 | 12.97 | 0 | 518.72 | C+S GST 18% I/P RD | 93.36 | 612.08 | 612.08 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 35.224 | Sq.Ft | 17 | 100 | 14.97 | 0 | 598.81 | C+S GST 18% I/P RD | 107.78 | 706.59 | 706.59 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 27.881 | Sq.Ft | 17 | 100 | 11.85 | 0 | 473.98 | C+S GST 18% I/P RD | 85.32 | 559.3 | 559.3 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 36.918 | Sq.Ft | 17 | 100 | 15.69 | 0 | 627.61 | C+S GST 18% I/P RD | 112.96 | 740.57 | 740.57 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 35.224 | Sq.Ft | 17 | 100 | 14.97 | 0 | 598.81 | C+S GST 18% I/P RD | 107.78 | 706.59 | 706.59 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 41.818 | Sq.Ft | 17 | 100 | 17.77 | 0 | 710.91 | C+S GST 18% I/P RD | 127.96 | 838.87 | 838.87 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Children Toilet Flooring | Vitrified Flooring -BC | 34.356 | Sq.Ft | 17 | 100 | 14.6 | 0 | 584.05 | C+S GST 18% I/P RD | 105.12 | 689.17 | 689.17 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 30.513 | Sq.Ft | 17 | 100 | 12.97 | 0 | 518.72 | C+S GST 18% I/P RD | 93.36 | 612.08 | 612.08 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 201 Staff Toilet dado | Dado BC | 97.968 | Sq.Ft | 13 | 100 | 31.84 | 0 | 1273.58 | C+S GST 18% I/P RD | 229.24 | 1502.82 | 1502.82 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 601 Staff Toilet dado | Dado BC | 85.722 | Sq.Ft | 13 | 100 | 27.86 | 0 | 1114.39 | C+S GST 18% I/P RD | 200.6 | 1314.99 | 1314.99 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Parents Toilet dado | Dado BC | 103.838 | Sq.Ft | 18 | 100 | 46.73 | 0 | 1869.08 | C+S GST 18% I/P RD | 336.44 | 2205.52 | 2205.52 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Powder Toilet dado | Dado BC | 68.152 | Sq.Ft | 18 | 100 | 30.67 | 0 | 1226.74 | C+S GST 18% I/P RD | 220.82 | 1447.56 | 1447.56 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Powder Toilet dado | Dado BC | 66.675 | Sq.Ft | 18 | 100 | 30 | 0 | 1200.15 | C+S GST 18% I/P RD | 216.02 | 1416.17 | 1416.17 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Children Toilet dado | Dado BC | 93.933 | Sq.Ft | 18 | 100 | 42.27 | 0 | 1690.79 | C+S GST 18% I/P RD | 304.34 | 1995.13 | 1995.13 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Powder Toilet dado | Dado BC | 68.152 | Sq.Ft | 18 | 100 | 30.67 | 0 | 1226.74 | C+S GST 18% I/P RD | 220.82 | 1447.56 | 1447.56 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Master Toilet dado | Dado BC | 89.222 | Sq.Ft | 18 | 100 | 40.15 | 0 | 1606 | C+S GST 18% I/P RD | 289.08 | 1895.08 | 1895.08 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1002 Parents Toilet dado | Dado BC | 106.764 | Sq.Ft | 18 | 100 | 48.04 | 0 | 1921.75 | C+S GST 18% I/P RD | 345.92 | 2267.67 | 2267.67 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1101 Master Toilet dado | Dado BC | 89.222 | Sq.Ft | 18 | 100 | 40.15 | 0 | 1606 | C+S GST 18% I/P RD | 289.08 | 1895.08 | 1895.08 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 701 Powder Toilet dado | Dado BC | 68.152 | Sq.Ft | 18 | 100 | 30.67 | 0 | 1226.74 | C+S GST 18% I/P RD | 220.82 | 1447.56 | 1447.56 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Master Toilet dado | Dado BC | 89.222 | Sq.Ft | 18 | 100 | 40.15 | 0 | 1606 | C+S GST 18% I/P RD | 289.08 | 1895.08 | 1895.08 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1001 Parents Toilet dado | Dado BC | 103.838 | Sq.Ft | 18 | 100 | 46.73 | 0 | 1869.08 | C+S GST 18% I/P RD | 336.44 | 2205.52 | 2205.52 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 32.2855 | R.Ft | 55 | 100 | 44.39 | 0 | 1775.7 | C+S GST 18% I/P RD | 319.62 | 2095.32 | 2095.32 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1602 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 74.4835 | R.Ft | 55 | 100 | 102.41 | 0 | 4096.59 | C+S GST 18% I/P RD | 737.38 | 4833.97 | 4833.97 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1302 Master Bed Marble Flooring | Italian marble Skirting - BCo | 43.485 | R.Ft | 55 | 100 | 59.79 | 0 | 2391.68 | C+S GST 18% I/P RD | 430.5 | 2822.18 | 2822.18 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 537 | 89790 | 12 Apr 2021 |  | MONIKA ENTERPRISES | MONIKA ENTERPRISES | EV - 295 | A 1602 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 32.2855 | R.Ft | 55 | 100 | 44.39 | 0 | 1775.7 | C+S GST 18% I/P RD | 319.62 | 2095.32 | 2095.32 | Approved | 0 | 0 | 2395 | 12 Apr 2021
GANGA DHAM TOWERS | 605 | 89789 | 12 Apr 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED (Material) | AGS TECHNOLOGIES INDIA PRIVATE LIMITED (Material) | EV - 47 | A Sprinkler System | Flexible Hose Pipe 25mm Dia (1mtr length) (M) | 688 | No. | 820 | 100 | 0 | 0 | 564160 | C+S GST 18% I/P RD | 101548.8 | 665708.8 | 665708.8 | Approved | 0 | 0 | 0 | 12 Apr 2021
GANGA DHAM TOWERS | 605 | 89789 | 12 Apr 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED (Material) | AGS TECHNOLOGIES INDIA PRIVATE LIMITED (Material) | EV - 47 | A Sprinkler System | Rossete Plate (M) | 688 | No. | 80 | 100 | 0 | 0 | 55040 | C+S GST 18% I/P RD | 9907.2 | 64947.2 | 64947.2 | Approved | 0 | 0 | 0 | 12 Apr 2021
GANGA DHAM TOWERS | 605 | 89789 | 12 Apr 2021 |  | AGS TECHNOLOGIES INDIA PRIVATE LIMITED (Material) | AGS TECHNOLOGIES INDIA PRIVATE LIMITED (Material) | EV - 47 | A Sprinkler System | Sprinkler 15mm 68 dg Pendent (M) | 688 | No. | 228 | 100 | 0 | 0 | 156864 | C+S GST 18% I/P RD | 28235.52 | 185099.52 | 185099.52 | Approved | 0 | 0 | 0 | 12 Apr 2021
GANGA DHAM TOWERS | 953 | 89758 | 09 Apr 2021 |  | RUDRAM FACADES PRIVATE LIMITED | RUDRAM FACADES PRIVATE LIMITED | EV - 57 | Club House Glazing work | Door Patch Cut out | 12 | No. | 150 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 5643 | 09 Apr 2021
GANGA DHAM TOWERS | 953 | 89758 | 09 Apr 2021 |  | RUDRAM FACADES PRIVATE LIMITED | RUDRAM FACADES PRIVATE LIMITED | EV - 57 | Club House Glazing work | 12mm Toughened Glass | 355 | Sq.Ft | 300 | 100 | 2662.5 | 0 | 106500 | C+S GST 18% I/P RD | 19170 | 125670 | 125670 | Approved | 0 | 0 | 5643 | 09 Apr 2021
GANGA DHAM TOWERS | 953 | 89758 | 09 Apr 2021 |  | RUDRAM FACADES PRIVATE LIMITED | RUDRAM FACADES PRIVATE LIMITED | EV - 57 | Club House Glazing work | 12mm Toughened Glass | 53 | Sq.Ft | 300 | 100 | 397.5 | 0 | 15900 | C+S GST 18% I/P RD | 2862 | 18762 | 18762 | Approved | 0 | 0 | 5643 | 09 Apr 2021
GANGA DHAM TOWERS | 953 | 89758 | 09 Apr 2021 |  | RUDRAM FACADES PRIVATE LIMITED | RUDRAM FACADES PRIVATE LIMITED | EV - 57 | Club House Glazing work | Door handle hole | 8 | No. | 50 | 100 | 10 | 0 | 400 | C+S GST 18% I/P RD | 72 | 472 | 472 | Approved | 0 | 0 | 5643 | 09 Apr 2021
GANGA DHAM TOWERS | 953 | 89758 | 09 Apr 2021 |  | RUDRAM FACADES PRIVATE LIMITED | RUDRAM FACADES PRIVATE LIMITED | EV - 57 | Club House Glazing work | Hardware Material | 1 | No. | 52944 | 100 | 1323.6 | 0 | 52944 | C+S GST 18% I/P RD | 9529.92 | 62473.92 | 62473.92 | Approved | 0 | 0 | 5643 | 09 Apr 2021
GANGA DHAM TOWERS | 953 | 89758 | 09 Apr 2021 |  | RUDRAM FACADES PRIVATE LIMITED | RUDRAM FACADES PRIVATE LIMITED | EV - 57 | Club House Glazing work | Ventilators 600mm x 1200mm | 6 | No. | 3500 | 100 | 525 | 0 | 21000 | C+S GST 18% I/P RD | 3780 | 24780 | 24780 | Approved | 0 | 0 | 5643 | 09 Apr 2021
GANGA DHAM TOWERS | 953 | 89758 | 09 Apr 2021 |  | RUDRAM FACADES PRIVATE LIMITED | RUDRAM FACADES PRIVATE LIMITED | EV - 57 | Club House Glass / Carpentary Shifting Work | 12mm Toughened Glass | 501.61 | Sq.Ft | 119.61 | 100 | 0 | 0 | 59997.57 | C+S GST 18% I/P RD | 10799.56 | 70797.13 | 70797.13 | Approved | 0 | 0 | 5643 | 09 Apr 2021
GANGA DHAM TOWERS | 953 | 89758 | 09 Apr 2021 |  | RUDRAM FACADES PRIVATE LIMITED | RUDRAM FACADES PRIVATE LIMITED | EV - 57 | Club House Glazing work | 3 Track Sliding Window | 59 | Sq.Ft | 400 | 100 | 590 | 0 | 23600 | C+S GST 18% I/P RD | 4248 | 27848 | 27848 | Approved | 0 | 0 | 5643 | 09 Apr 2021
GANGA DHAM TOWERS | 237 | 89734 | 09 Apr 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 135 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.9031 | Month | 7000 | 100 | 0 | 0 | 6322 | CGST 0% URD I/P | 0 | 6322 | 6322 | Approved | 0 | 0 | 63 | 09 Apr 2021
GANGA DHAM TOWERS | 145 | 89688 | 08 Apr 2021 |  | PEST-O-CRUSH | PEST-O-CRUSH |  | Fogging Work | Fogging work-SO | 0.25 | Month | 6000 | 100 | 0 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 |  | 0 | 0 | 11 | 08 Apr 2021
GANGA DHAM TOWERS | 126 | 89687 | 08 Apr 2021 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 64 | Site Expenses | Site Expenses -SO | 0.0673 | Month | 15000 | 100 | 0 | 0 | 1010 | CGST 0% URD I/P | 0 | 1010 | 1010 | Approved | 0 | 0 | 0 | 08 Apr 2021
GANGA DHAM TOWERS | 355 | 89686 | 08 Apr 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | B Bldg 23rd Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 |  | 0 | 0 | 160 | 08 Apr 2021
GANGA DHAM TOWERS | 355 | 89686 | 08 Apr 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | B Bldg 25th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 |  | 0 | 0 | 160 | 08 Apr 2021
GANGA DHAM TOWERS | 355 | 89686 | 08 Apr 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | B Bldg 24th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 |  | 0 | 0 | 160 | 08 Apr 2021
GANGA DHAM TOWERS | 355 | 89686 | 08 Apr 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | B Bldg 22nd Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 |  | 0 | 0 | 160 | 08 Apr 2021
GANGA DHAM TOWERS | 291 | 89685 | 08 Apr 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A Bldg 24th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 3000 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 |  | 0 | 0 | 90 | 08 Apr 2021
GANGA DHAM TOWERS | 291 | 89685 | 08 Apr 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A Bldg 23rd Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 3000 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 |  | 0 | 0 | 90 | 08 Apr 2021
GANGA DHAM TOWERS | 291 | 89685 | 08 Apr 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES |  | A Bldg 25th Fl. PVC Plumbing Sleeves Fixing (L) | Sleeves fixing | 1 | Slab | 3000 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 |  | 0 | 0 | 90 | 08 Apr 2021
GANGA DHAM TOWERS | 991 | 89683 | 08 Apr 2021 |  | AVCON TECHNICS PVT LTD | A K INTERIOR CONTRACTOR | EV - 73 | B 1601 NOC | Gypsum Plaster (L) | 397.7895 | Sq.Ft | 9.5 | 100 | 0 | 0 | 3779 | C+S GST 18% I/P RD | 680.22 | 4459.22 | 4459.22 | Approved | 0 | 0 | 38 | 08 Apr 2021
GANGA DHAM TOWERS | 350 | 89638 | 06 Apr 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 680 | Site Expenses | Site Expenses -SO | 1 | Month | 3000 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 0 | 06 Apr 2021
GANGA DHAM TOWERS | 350 | 89638 | 06 Apr 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 680 | Site Expenses | Site Expenses -SO | 1 | Month | 3000 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 0 | 06 Apr 2021
GANGA DHAM TOWERS | 187 | 89637 | 06 Apr 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 74 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 06 Apr 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1501 Gypsum Plaster | Gypsum on Wall (M) | 3522.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12330 | C+S GST 5% I/P RD | 616.5 | 12946.5 | 12946.5 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1502 Gypsum Plaster | Gypsum on Wall (M) | 111.4286 | Sq.Ft | 3.5 | 100 | 0 | 0 | 390 | C+S GST 5% I/P RD | 19.5 | 409.5 | 409.5 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1602 Gypsum Plaster | Gypsum on Wall (M) | 671.4286 | Sq.Ft | 3.5 | 100 | 0 | 0 | 2350 | C+S GST 5% I/P RD | 117.5 | 2467.5 | 2467.5 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1502 Gypsum Plaster | Gypsum on Wall (M) | 345.7143 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1210 | C+S GST 5% I/P RD | 60.5 | 1270.5 | 1270.5 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1402 Gypsum Plaster | Gypsum on Wall (M) | 3443.4286 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12052 | C+S GST 5% I/P RD | 602.6 | 12654.6 | 12654.6 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1302 Gypsum Plaster | Gypsum on Wall (M) | 3443.4286 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12052 | C+S GST 5% I/P RD | 602.6 | 12654.6 | 12654.6 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1401 Gypsum Plaster | Gypsum on Wall (M) | 3523.05 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12330.68 | C+S GST 5% I/P RD | 616.54 | 12947.22 | 12947.22 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1601 Gypsum Plaster | Gypsum on Wall (M) | 3523.05 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12330.68 | C+S GST 5% I/P RD | 616.54 | 12947.22 | 12947.22 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 392 | 89610 | 31 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2450 | A Bldg Flat No. 1301 Gypsum Plaster | Gypsum on Wall (M) | 3523.05 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12330.68 | C+S GST 5% I/P RD | 616.54 | 12947.22 | 12947.22 | Approved | 0 | 390 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 270 | 89607 | 31 Mar 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2449 | C Steel Testing - 1 No. | Tensile Strength & % Elongation-SOS | 9 | No. | 189 | 100 | 0 | 0 | 1701 | C+S GST 18% I/P RD | 306.18 | 2007.18 | 2007.18 | Approved | 0 | 0 | 126 | 31 Mar 2021
GANGA DHAM TOWERS | 270 | 89607 | 31 Mar 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2449 | C Steel Testing - 1 No. | Weight per Meter-SOS | 15 | No. | 28 | 100 | 0 | 0 | 420 | C+S GST 18% I/P RD | 75.6 | 495.6 | 495.6 | Approved | 0 | 0 | 126 | 31 Mar 2021
GANGA DHAM TOWERS | 270 | 89607 | 31 Mar 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2449 | C Steel Testing - 1 No. | Chemical Testing of Steel-SOS | 0.5786 | No. | 420 | 100 | 0 | 0 | 243 | C+S GST 18% I/P RD | 43.74 | 286.74 | 286.74 | Approved | 0 | 0 | 126 | 31 Mar 2021
GANGA DHAM TOWERS | 270 | 89607 | 31 Mar 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2449 | C Steel Testing - 1 No. | 90/180 Bend Test-SOS | 15 | No. | 154 | 100 | 0 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 126 | 31 Mar 2021
GANGA DHAM TOWERS | 270 | 89607 | 31 Mar 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2449 | C Steel Testing - 1 No. | Tensile Strength & % Elongation-SOS | 9 | No. | 154 | 100 | 0 | 0 | 1386 | C+S GST 18% I/P RD | 249.48 | 1635.48 | 1635.48 | Approved | 0 | 0 | 126 | 31 Mar 2021
GANGA DHAM TOWERS | 270 | 89607 | 31 Mar 2021 |  | DUROCRETE ENGINEERING SERVICES PVT LTD | DUROCRETE ENGINEERING SERVICES PVT LTD | EV - 2449 | C Steel Testing - 1 No. | 135/157.5 Rebend Test-SOS | 15 | No. | 154 | 100 | 0 | 0 | 2310 | C+S GST 18% I/P RD | 415.8 | 2725.8 | 2725.8 | Approved | 0 | 0 | 126 | 31 Mar 2021
GANGA DHAM TOWERS | 272 | 89601 | 31 Mar 2021 |  | GOURI INFRA | VISION MANAGEMENT SERVICES | EV - 2443 | A Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 83.2874 | Sq.Ft | 181.3 | 100 | 0 | 0 | 15100 | CGST 0% URD I/P | 0 | 15100 | 15100 | Approved | 0 | 0 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 253 | 89600 | 31 Mar 2021 |  | UNIQUE ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2442 | B Bldg 5th RCC Slab Built-up Area (L) | RCC Rate Diferance BC | 92.5 | Sq.Ft | 200 | 100 | 462.5 | 0 | 18500 | CGST 0% URD I/P | 0 | 18500 | 18500 | Approved | 0 | 0 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 371 | 89599 | 31 Mar 2021 |  | CONSTROGENESIS | VISION MANAGEMENT SERVICES | EV - 2441 | EWS Bldg RCC 13th Slab Built-up Area (Terrace)(L) | RCC Superstructure (B-up area) | 66.6667 | Sq.Ft | 150 | 100 | 250 | 0 | 10000 | CGST 0% URD I/P | 0 | 10000 | 10000 | Approved | 0 | 0 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 372 | 89598 | 31 Mar 2021 |  | B & B ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2440 | B Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 114.4062 | Sq.Ft | 160 | 100 | 0 | 0 | 18305 | CGST 0% URD I/P | 0 | 18305 | 18305 | Approved | 0 | 0 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 537 | 89597 | 31 Mar 2021 |  | MONIKA ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2444 | A 1002 Children Toilet | Dado BC | 188.43 | Sq.Ft | 18 | 100 | 84.79 | 0 | 3391.74 | C+S GST 18% I/P RD | 610.52 | 4002.26 | 4002.26 | Approved | 0 | 0 | 637 | 31 Mar 2021
GANGA DHAM TOWERS | 537 | 89597 | 31 Mar 2021 |  | MONIKA ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2444 | A 1002 Master Toilet dado | Dado BC | 123.5 | Sq.Ft | 18 | 100 | 55.58 | 0 | 2223 | C+S GST 18% I/P RD | 400.14 | 2623.14 | 2623.14 | Approved | 0 | 0 | 637 | 31 Mar 2021
GANGA DHAM TOWERS | 537 | 89597 | 31 Mar 2021 |  | MONIKA ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2444 | A 1002 Kitchen dado | Dado BC | 37.5 | Sq.Ft | 18 | 100 | 16.88 | 0 | 675 | C+S GST 18% I/P RD | 121.5 | 796.5 | 796.5 | Approved | 0 | 0 | 637 | 31 Mar 2021
GANGA DHAM TOWERS | 537 | 89597 | 31 Mar 2021 |  | MONIKA ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2444 | A 1002 Master Toilet dado | Dado BC | 67.78 | Sq.Ft | 20 | 100 | 33.89 | 0 | 1355.6 | C+S GST 18% I/P RD | 244 | 1599.6 | 1599.6 | Approved | 0 | 0 | 637 | 31 Mar 2021
GANGA DHAM TOWERS | 537 | 89597 | 31 Mar 2021 |  | MONIKA ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2444 | A 1002 Children Toilet | Dado BC | 42.7 | Sq.Ft | 20 | 100 | 21.35 | 0 | 854 | C+S GST 18% I/P RD | 153.72 | 1007.72 | 1007.72 | Approved | 0 | 0 | 637 | 31 Mar 2021
GANGA DHAM TOWERS | 491 | 89596 | 31 Mar 2021 |  | KADAVATH VENKAT ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2445 | D Build. 901 Blockwork 5" | Blockwork 5" - BC - | 653.8462 | Sq.Ft | 13 | 100 | 212.5 | 0 | 8500 | C+S GST 18% I/P RD | 1530 | 10030 | 10030 | Approved | 0 | 0 | 638 | 31 Mar 2021
GANGA DHAM TOWERS | 371 | 89595 | 31 Mar 2021 |  | CONSTROGENESIS | VISION MANAGEMENT SERVICES | EV - 2448 | EWS Bldg RCC 13th Slab Built-up Area (Terrace)(L) | RCC Superstructure (B-up area) | 6.6667 | Sq.Ft | 150 | 100 | 25 | 0 | 1000.01 | C+S GST 18% I/P RD | 180 | 1180.01 | 1180.01 | Approved | 0 | 0 | 75 | 31 Mar 2021
GANGA DHAM TOWERS | 372 | 89594 | 31 Mar 2021 |  | B & B ENTERPRISES | VISION MANAGEMENT SERVICES | EV - 2447 | B Bldg 26th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 57.4688 | Sq.Ft | 160 | 100 | 0 | 0 | 9195 | IGST 18% I/P RD | 1655.1 | 10850.1 | 10850.1 | Approved | 0 | 0 | 690 | 31 Mar 2021
GANGA DHAM TOWERS | 272 | 89593 | 31 Mar 2021 |  | GOURI INFRA | VISION MANAGEMENT SERVICES | EV - 2446 | A Bldg 31st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 46.332 | Sq.Ft | 181.3 | 100 | 0 | 0 | 8400 | C+S GST 18% I/P RD | 1512 | 9912 | 9912 | Approved | 0 | 0 | 630 | 31 Mar 2021
GANGA DHAM TOWERS | 494 | 89571 | 31 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2434 | B 1401 Gypsum Plaster | Gypsum on Wall (M) | 5310.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 18588 | C+S GST 18% I/P RD | 3345.84 | 21933.84 | 21933.84 | Approved | 0 | 858 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 494 | 89571 | 31 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2434 | B 1301 Gypsum Plaster | Gypsum on Wall (M) | 5967.7143 | Sq.Ft | 3.5 | 100 | 0 | 0 | 20887 | C+S GST 18% I/P RD | 3759.66 | 24646.66 | 24646.66 | Approved | 0 | 858 | 0 | 31 Mar 2021
GANGA DHAM TOWERS | 189 | 89557 | 30 Mar 2021 |  | ALI EXPLOSIVE AND COMPANY | SS ENTERPRISES | EV - 2409 | Bldg Area Podium Excavtion | Excavation By Bucket (Shifting Outside) | 403.2 | Cu.Mtrs | 130 | 100 | 0 | 0 | 52416 | C+S GST 18% I/P RD | 9434.88 | 61850.88 | 61850.88 | Approved | 0 | 12715 | 1680 | 30 Mar 2021
GANGA DHAM TOWERS | 189 | 89557 | 30 Mar 2021 |  | ALI EXPLOSIVE AND COMPANY | SS ENTERPRISES | EV - 2409 | Bldg Area Podium Excavtion | Excavation By Bucket (Shifting Outside) | 458.3308 | Cu.Mtrs | 130 | 100 | 0 | 0 | 59583 | C+S GST 18% I/P RD | 10724.94 | 70307.94 | 70307.94 | Approved | 0 | 12715 | 1680 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1304 Gypsum Plaster | Gypsum on Wall (M) | 3299.12 | Sq.Ft | 3.5 | 100 | 0 | 0 | 11546.92 | C+S GST 18% I/P RD | 2078.44 | 13625.36 | 13625.36 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1603 Gypsum Plaster | Gypsum on Wall (M) | 2931.16 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10259.06 | C+S GST 18% I/P RD | 1846.64 | 12105.7 | 12105.7 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1503 Gypsum Plaster | Gypsum on Wall (M) | 2931.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10259 | C+S GST 18% I/P RD | 1846.62 | 12105.62 | 12105.62 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1604 Gypsum Plaster | Gypsum on Wall (M) | 368.8571 | Sq.Ft | 3.5 | 100 | 0 | 0 | 1291 | C+S GST 18% I/P RD | 232.38 | 1523.38 | 1523.38 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1504 Gypsum Plaster | Gypsum on Wall (M) | 3299.12 | Sq.Ft | 3.5 | 100 | 0 | 0 | 11546.92 | C+S GST 18% I/P RD | 2078.44 | 13625.36 | 13625.36 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1303 Gypsum Plaster | Gypsum on Wall (M) | 2931.16 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10259.06 | C+S GST 18% I/P RD | 1846.64 | 12105.7 | 12105.7 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1404 Gypsum Plaster | Gypsum on Wall (M) | 3299.12 | Sq.Ft | 3.5 | 100 | 0 | 0 | 11546.92 | C+S GST 18% I/P RD | 2078.44 | 13625.36 | 13625.36 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1403 Gypsum Plaster | Gypsum on Wall (M) | 2931.16 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10259.06 | C+S GST 18% I/P RD | 1846.64 | 12105.7 | 12105.7 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1703 Gypsum Plaster | Gypsum on Wall (M) | 2931.16 | Sq.Ft | 3.5 | 100 | 0 | 0 | 10259.06 | C+S GST 18% I/P RD | 1846.64 | 12105.7 | 12105.7 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 394 | 89556 | 30 Mar 2021 |  | A K INTERIOR CONTRACTOR | SEVEN STAR GYPSUM | EV - 2410 | A Bldg Flat No. 1604 Gypsum Plaster | Gypsum on Wall (M) | 1687.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 5905 | C+S GST 18% I/P RD | 1062.9 | 6967.9 | 6967.9 | Approved | 0 | 0 | 0 | 30 Mar 2021
GANGA DHAM TOWERS | 496 | 89541 | 26 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2383 | B 1402 Gypsum Plaster | Gypsum on Wall (M) | 4054.15 | Sq.Ft | 3.5 | 100 | 0 | 0 | 14189.53 | C+S GST 18% I/P RD | 2554.12 | 16743.65 | 16743.65 | Approved | 0 | 0 | 0 | 26 Mar 2021
GANGA DHAM TOWERS | 496 | 89541 | 26 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2383 | B 1302 Gypsum Plaster | Gypsum on Wall (M) | 4054.15 | Sq.Ft | 3.5 | 100 | 0 | 0 | 14189.53 | C+S GST 18% I/P RD | 2554.12 | 16743.65 | 16743.65 | Approved | 0 | 0 | 0 | 26 Mar 2021
GANGA DHAM TOWERS | 496 | 89541 | 26 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2383 | B 1602 Gypsum Plaster | Gypsum on Wall (M) | 3502.2857 | Sq.Ft | 3.5 | 100 | 0 | 0 | 12258 | C+S GST 18% I/P RD | 2206.44 | 14464.44 | 14464.44 | Approved | 0 | 0 | 0 | 26 Mar 2021
GANGA DHAM TOWERS | 496 | 89541 | 26 Mar 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2383 | B 1502 Gypsum Plaster | Gypsum on Wall (M) | 4054.15 | Sq.Ft | 3.5 | 100 | 0 | 0 | 14189.53 | C+S GST 18% I/P RD | 2554.12 | 16743.65 | 16743.65 | Approved | 0 | 0 | 0 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 17th Floor Back Coat Plaster | Back Coat Plaster | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 14th Floor Back Coat Plaster | Back Coat Plaster | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 13th Floor Back Coat Plaster | Back Coat Plaster | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 16th Floor Back Coat Plaster | Back Coat Plaster | 5 | No. | 2000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 8th Floor Back Coat Plaster | Back Coat Plaster | 3 | No. | 2000 | 100 | 150 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 15th Floor Back Coat Plaster | Back Coat Plaster | 3 | No. | 2000 | 100 | 150 | 0 | 6000 | C+S GST 18% I/P RD | 1080 | 7080 | 7080 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 9th Floor Back Coat Plaster | Back Coat Plaster | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P URD | 360 | 2360 | 2360 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 10th Floor Back Coat Plaster | Back Coat Plaster | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 927 | 89540 | 26 Mar 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2380 | A 12th Floor Back Coat Plaster | Back Coat Plaster | 1 | No. | 2000 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 435 | 26 Mar 2021
GANGA DHAM TOWERS | 978 | 89534 | 26 Mar 2021 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 2362 | 50 Year National Safety Week 2021 | Miscellaneous Expenses | 0.1211 | No. | 7500 | 100 | 0 | 0 | 908 | CGST 0% URD I/P | 0 | 908 | 908 | Approved | 0 | 0 | 0 | 26 Mar 2021
GANGA DHAM TOWERS | 974 | 89516 | 25 Mar 2021 |  | SANDIP VAMANRAO RUPNAWAR | NAVEEN KUMAR JAIN | EV - 2377 | Material Shifting Work | Material Shifting-UTI | 0.1505 | No. | 25000 | 100 | 0 | 0 | 3763 | CGST 0% URD I/P | 0 | 3763 | 3763 | Approved | 0 | 0 | 0 | 25 Mar 2021
GANGA DHAM TOWERS | 904 | 89489 | 24 Mar 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2390 | B 701 NOC | Concrete Cutting Work | 23.7105 | R.Ft | 525 | 100 | 311.2 | 0 | 12448 | C+S GST 18% I/P RD | 2240.64 | 14688.64 | 14688.64 | Approved | 0 | 0 | 205 | 24 Mar 2021
GANGA DHAM TOWERS | 904 | 89489 | 24 Mar 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2390 | B 701 NOC | Concrete Cutting Work | 2.2629 | R.Ft | 525 | 100 | 29.7 | 0 | 1188 | C+S GST 18% I/P RD | 213.84 | 1401.84 | 1401.84 | Approved | 0 | 0 | 205 | 24 Mar 2021
GANGA DHAM TOWERS | 928 | 89463 | 23 Mar 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 2343 | A Bldg 30th Slab Pumping Charges | Pumping Charges-BC | 126 | Cu.Mtrs | 190 | 100 | 0 | 0 | 23940 | C+S GST 18% I/P RD | 4309.2 | 28249.2 | 28249.2 | Approved | 0 | 41148 | 2294 | 23 Mar 2021
GANGA DHAM TOWERS | 928 | 89463 | 23 Mar 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 2343 | A Bldg 30th Slab Pumping Charges | Pumping Charges-BC | 340 | Cu.Mtrs | 190 | 100 | 0 | 0 | 64600 | C+S GST 18% I/P RD | 11628 | 76228 | 76228 | Approved | 0 | 41148 | 2294 | 23 Mar 2021
GANGA DHAM TOWERS | 928 | 89463 | 23 Mar 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 2343 | A Bldg 31st Slab Pumping Charges | Pumping Charges-BC | 338.8684 | Cu.Mtrs | 190 | 100 | 0 | 0 | 64385 | C+S GST 18% I/P RD | 11589.3 | 75974.3 | 75974.3 | Approved | 0 | 41148 | 2294 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 89 | Sq.Ft | 1 | 100 | 2.23 | 0 | 89 | CGST 0% URD I/P | 0 | 89 | 89 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 89 | Sq.Ft | 1 | 100 | 2.23 | 0 | 89 | CGST 0% URD I/P | 0 | 89 | 89 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 89 | Sq.Ft | 1 | 100 | 2.23 | 0 | 89 | CGST 0% URD I/P | 0 | 89 | 89 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 130.4 | Sq.Ft | 1.25 | 100 | 4.08 | 0 | 163 | CGST 0% URD I/P | 0 | 163 | 163 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 200 | Sq.Ft | 1.25 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 200 | Sq.Ft | 1.25 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 102 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 130.4 | Sq.Ft | 1.25 | 100 | 4.08 | 0 | 163 | CGST 0% URD I/P | 0 | 163 | 163 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 130.4 | Sq.Ft | 1.25 | 100 | 4.08 | 0 | 163 | CGST 0% URD I/P | 0 | 163 | 163 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 200 | Sq.Ft | 1.25 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 200 | Sq.Ft | 1.25 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 200 | Sq.Ft | 1.25 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 130.4 | Sq.Ft | 1.25 | 100 | 4.08 | 0 | 163 | CGST 0% URD I/P | 0 | 163 | 163 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 130.4 | Sq.Ft | 1.25 | 100 | 4.08 | 0 | 163 | CGST 0% URD I/P | 0 | 163 | 163 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 200 | Sq.Ft | 1.25 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 130.4 | Sq.Ft | 1.25 | 100 | 4.08 | 0 | 163 | CGST 0% URD I/P | 0 | 163 | 163 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 150.4 | Sq.Ft | 1.25 | 100 | 4.7 | 0 | 188 | CGST 0% URD I/P | 0 | 188 | 188 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 130.4 | Sq.Ft | 1.25 | 100 | 4.08 | 0 | 163 | CGST 0% URD I/P | 0 | 163 | 163 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 200 | Sq.Ft | 1.25 | 100 | 6.25 | 0 | 250 | CGST 0% URD I/P | 0 | 250 | 250 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 202 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 90.4 | Sq.Ft | 1.25 | 100 | 2.83 | 0 | 113 | CGST 0% URD I/P | 0 | 113 | 113 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (L) | 130.4 | Sq.Ft | 1.25 | 100 | 4.08 | 0 | 163 | CGST 0% URD I/P | 0 | 163 | 163 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 89 | Sq.Ft | 1 | 100 | 2.23 | 0 | 89 | CGST 0% URD I/P | 0 | 89 | 89 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 74 | Sq.Ft | 1 | 100 | 1.85 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 827 | 89444 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2406 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (L) - | 55 | Sq.Ft | 1 | 100 | 1.38 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 57 | 23 Mar 2021
GANGA DHAM TOWERS | 991 | 89441 | 23 Mar 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2389 | B 1601 NOC | Concrete wall Crushing work | 2.29 | Cu.Mtrs | 7200 | 100 | 0 | 0 | 16488 | C+S GST 18% I/P RD | 2967.84 | 19455.84 | 19455.84 | Approved | 0 | 0 | 1960 | 23 Mar 2021
GANGA DHAM TOWERS | 991 | 89441 | 23 Mar 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2389 | B 1601 NOC | Concrete Cutting Work | 217.46 | R.Ft | 525 | 100 | 0 | 0 | 114166.5 | C+S GST 18% I/P RD | 20549.98 | 134716.48 | 134716.48 | Approved | 0 | 0 | 1960 | 23 Mar 2021
GANGA DHAM TOWERS | 904 | 89440 | 23 Mar 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2391 | B 1701 NOC | Concrete Cutting Work | 670.1 | R.Ft | 525 | 100 | 0 | 0 | 351802.5 | C+S GST 18% I/P RD | 63324.46 | 415126.96 | 415126.96 | Approved | 0 | 0 | 6108 | 23 Mar 2021
GANGA DHAM TOWERS | 904 | 89440 | 23 Mar 2021 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2391 | B 1701 NOC | Concrete wall Crushing work | 7.69 | Cu.Mtrs | 7200 | 100 | 0 | 0 | 55368 | C+S GST 18% I/P RD | 9966.24 | 65334.24 | 65334.24 | Approved | 0 | 0 | 6108 | 23 Mar 2021
GANGA DHAM TOWERS | 982 | 89438 | 23 Mar 2021 |  | S J INDUSTRIES | S J INDUSTRIES | EV - 2392 | A Facade Scaffolding Fitting & Removing Work | H Frame & Cross Bracing | 100 | set | 3880 | 100 | 0 | 0 | 388000 | C+S GST 18% I/P RD | 69840 | 457840 | 457840 | Approved | 0 | 0 | 2910 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 901 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 200 | Sq.Ft | 1.75 | 100 | 0 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 501 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 502 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 902 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 200 | Sq.Ft | 1.75 | 100 | 0 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 200 | Sq.Ft | 1.75 | 100 | 0 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 200 | Sq.Ft | 1.75 | 100 | 0 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 201 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 401 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 601 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 702 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 200 | Sq.Ft | 1.75 | 100 | 0 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 301 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 801 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 601 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 101 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 402 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 901 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 501 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 130.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 228 | CGST 0% URD I/P | 0 | 228 | 228 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 602 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 701 Toilet Area Ducts Ceiling Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 18.8571 | Sq.Ft | 1.75 | 100 | 0 | 0 | 33 | CGST 0% URD I/P | 0 | 33 | 33 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 802 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 302 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 90.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 158 | CGST 0% URD I/P | 0 | 158 | 158 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 701 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 200 | Sq.Ft | 1.75 | 100 | 0 | 0 | 350 | CGST 0% URD I/P | 0 | 350 | 350 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 801 Toilet Area Duct walls Semi-Acrylic Painting | 1st Coat Semi-Acrylic Paint (M) | 150.2857 | Sq.Ft | 1.75 | 100 | 0 | 0 | 263 | CGST 0% URD I/P | 0 | 263 | 263 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1004 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 804 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1403 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 59 | Sq.Ft | 1 | 100 | 0 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 101 Toilet Area Ducts walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 30 | Sq.Ft | 1 | 100 | 0 | 0 | 30 | CGST 0% URD I/P | 0 | 30 | 30 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 703 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 904 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1504 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 59 | Sq.Ft | 1 | 100 | 0 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 301 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 30 | Sq.Ft | 1 | 100 | 0 | 0 | 30 | CGST 0% URD I/P | 0 | 30 | 30 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 803 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1003 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1203 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 204 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 59 | Sq.Ft | 1 | 100 | 0 | 0 | 59 | CGST 0% URD I/P | 0 | 59 | 59 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 201 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 30 | Sq.Ft | 1 | 100 | 0 | 0 | 30 | CGST 0% URD I/P | 0 | 30 | 30 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 503 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1304 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 103 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 303 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 903 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 74 | Sq.Ft | 1 | 100 | 0 | 0 | 74 | CGST 0% URD I/P | 0 | 74 | 74 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 104 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 401 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 89 | Sq.Ft | 1 | 100 | 0 | 0 | 89 | CGST 0% URD I/P | 0 | 89 | 89 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 704 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 604 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 828 | 89437 | 23 Mar 2021 |  | CHAPLA ADE PENTING CONTRACTOR | CHAPLA ADE PENTING CONTRACTOR | EV - 2407 | A 1404 Toilet Area Duct walls Semi-Acrylic Painting | 1 Coat Primer (External) (M) | 55 | Sq.Ft | 1 | 100 | 0 | 0 | 55 | CGST 0% URD I/P | 0 | 55 | 55 | Approved | 0 | 0 | 0 | 23 Mar 2021
GANGA DHAM TOWERS | 691 | 89428 | 22 Mar 2021 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 2339 | Parking Columns painting sampling work | Painter - SM | 6.5 | No. | 600 | 100 | 0 | 0 | 3900 | CGST 0% URD I/P | 0 | 3900 | 3900 | Approved | 0 | 0 | 0 | 22 Mar 2021
GANGA DHAM TOWERS | 691 | 89428 | 22 Mar 2021 |  | PUNDLIK P MAHAJAN | PUNDLIK P MAHAJAN | EV - 2339 | Parking Columns painting sampling work | Transportation SM | 7 | No. | 100 | 100 | 0 | 0 | 700 | CGST 0% URD I/P | 0 | 700 | 700 | Approved | 0 | 0 | 0 | 22 Mar 2021
GANGA DHAM TOWERS | 957 | 89427 | 22 Mar 2021 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2340 | Electricity Infrastructure-Trnsformer,HT,LT Work | Excavation work.- UTI | 28 | Mtrs | 160 | 100 | 0 | 0 | 4480 | CGST 0% URD I/P | 0 | 4480 | 4480 | Approved | 0 | 0 | 569 | 22 Mar 2021
GANGA DHAM TOWERS | 957 | 89427 | 22 Mar 2021 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2340 | Electricity Infrastructure-Trnsformer,HT,LT Work | Road Cutting work | 23 | Mtrs | 350 | 100 | 0 | 0 | 8050 | CGST 0% URD I/P | 0 | 8050 | 8050 | Approved | 0 | 0 | 569 | 22 Mar 2021
GANGA DHAM TOWERS | 957 | 89427 | 22 Mar 2021 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2340 | Electricity Infrastructure-Trnsformer,HT,LT Work | XLPE Cable laying 300sqmm 3C 22kv (L) | 350 | Mtrs | 140 | 100 | 1225 | 0 | 49000 | CGST 0% URD I/P | 0 | 49000 | 49000 | Approved | 0 | 0 | 569 | 22 Mar 2021
GANGA DHAM TOWERS | 957 | 89427 | 22 Mar 2021 |  | LAXMI ELECTRICALS | LAXMI ELECTRICALS | EV - 2340 | Electricity Infrastructure-Trnsformer,HT,LT Work | Al. Arm. Cable 300Sqmm 3.5C (L)- LC | 160 | Mtrs | 90 | 100 | 360 | 0 | 14400 | CGST 0% URD I/P | 0 | 14400 | 14400 | Approved | 0 | 0 | 569 | 22 Mar 2021
GANGA DHAM TOWERS | 587 | 89420 | 20 Mar 2021 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2397 | Club House Excavation In Lawn Area | Excavation By Needle (Shifting Inside) | 56.6 | Cu.Mtrs | 210 | 100 | 0 | 0 | 11886 | C+S GST 18% I/P RD | 2139.48 | 14025.48 | 14025.48 | Approved | 0 | 0 | 331 | 20 Mar 2021
GANGA DHAM TOWERS | 587 | 89420 | 20 Mar 2021 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2397 | Club House Excavation In Lawn Area | Excavation By Needle (Shifting Outside) | 56.6 | Cu.Mtrs | 210 | 100 | 0 | 0 | 11886 | C+S GST 18% I/P RD | 2139.48 | 14025.48 | 14025.48 | Approved | 0 | 0 | 331 | 20 Mar 2021
GANGA DHAM TOWERS | 587 | 89420 | 20 Mar 2021 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2397 | Club House Excavation In Lawn Area | Spreading & Levelling Work | 56.6 | Cu.Mtrs | 150 | 100 | 0 | 0 | 8490 | C+S GST 18% I/P RD | 1528.2 | 10018.2 | 10018.2 | Approved | 0 | 0 | 331 | 20 Mar 2021
GANGA DHAM TOWERS | 587 | 89420 | 20 Mar 2021 |  | SS ENTERPRISES | SS ENTERPRISES | EV - 2397 | Club House Excavation In Lawn Area | Spreading & Levelling Work | 56.6 | Cu.Mtrs | 15 | 100 | 0 | 0 | 849 | C+S GST 18% I/P RD | 152.82 | 1001.82 | 1001.82 | Approved | 0 | 0 | 331 | 20 Mar 2021
GANGA DHAM TOWERS | 990 | 89419 | 20 Mar 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 2408 | Club House Plumbing Work (L) | Plumbing Work - BCo | 1 | No. | 40000 | 100 | 1000 | 0 | 40000 | CGST 0% URD I/P | 0 | 40000 | 40000 | Approved | 0 | 0 | 300 | 20 Mar 2021
GANGA DHAM TOWERS | 994 | 89417 | 20 Mar 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2384 | Club House Internal False Ceiling | Armstrong False Ceiling- BC | 935.95 | Sq.Ft | 140 | 100 | 3275.83 | 0 | 131033 | C+S GST 18% I/P RD | 23585.94 | 154618.94 | 154618.94 | Approved | 0 | 0 | 3000 | 20 Mar 2021
GANGA DHAM TOWERS | 994 | 89417 | 20 Mar 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2384 | Club House Internal False Ceiling | Gypsum False Ceiling Patta (M+L) | 768.3 | R.Ft | 75 | 100 | 1440.56 | 0 | 57622.5 | C+S GST 18% I/P RD | 10372.06 | 67994.56 | 67994.56 | Approved | 0 | 0 | 3000 | 20 Mar 2021
GANGA DHAM TOWERS | 994 | 89417 | 20 Mar 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2384 | Club House Internal False Ceiling | Grid False Ceiling (M+L) | 326.28 | Sq.Ft | 85 | 100 | 693.35 | 0 | 27733.8 | C+S GST 18% I/P RD | 4992.08 | 32725.88 | 32725.88 | Approved | 0 | 0 | 3000 | 20 Mar 2021
GANGA DHAM TOWERS | 994 | 89417 | 20 Mar 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2384 | Club House Internal False Ceiling | Gypsum Board False Ceiling (M+L) | 2448.5 | Sq.Ft | 75 | 100 | 4590.94 | 0 | 183637.5 | C+S GST 18% I/P RD | 33054.76 | 216692.26 | 216692.26 | Approved | 0 | 0 | 3000 | 20 Mar 2021
GANGA DHAM TOWERS | 995 | 89416 | 20 Mar 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2351 | Club House Pvc False Ceiling | PVC False Ceiling | 150 | Sq.Ft | 70 | 100 | 0 | 0 | 10500 | C+S GST 18% I/P RD | 1890 | 12390 | 12390 | Approved | 0 | 0 | 139 | 20 Mar 2021
GANGA DHAM TOWERS | 995 | 89416 | 20 Mar 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2351 | Club House Pvc False Ceiling | PVC False Ceiling | 150 | Sq.Ft | 53.39 | 100 | 0 | 0 | 8008.5 | C+S GST 18% I/P RD | 1441.54 | 9450.04 | 9450.04 | Approved | 0 | 0 | 139 | 20 Mar 2021
GANGA DHAM TOWERS | 910 | 89411 | 19 Mar 2021 |  | YOGESH MOHAN PAWAR | YOGESH MOHAN PAWAR | EV - 2367 | B 302 Painting Work Sample | Painting work (M+L) -BC | 1467.4286 | Sq.Ft | 7 | 100 | 0 | 0 | 10272 | CGST 0% URD I/P | 0 | 10272 | 10272 | Approved | 0 | 0 | 77 | 19 Mar 2021
GANGA DHAM TOWERS | 970 | 89410 | 19 Mar 2021 |  | YOGESH MOHAN PAWAR | YOGESH MOHAN PAWAR | EV - 2366 | B 302 Painting Work Sample | Oil base Primer-BC | 3727.27 | Sq.Ft | 1 | 100 | 0 | 0 | 3727.27 | C+S GST 0% I/P RD | 0 | 3727.27 | 3727.27 | Approved | 0 | 0 | 280 | 19 Mar 2021
GANGA DHAM TOWERS | 970 | 89410 | 19 Mar 2021 |  | YOGESH MOHAN PAWAR | YOGESH MOHAN PAWAR | EV - 2366 | B 302 Painting Work Sample | 2nd Coat Paint | 3727.27 | Sq.Ft | 3 | 100 | 0 | 0 | 11181.81 | CGST 0% URD I/P | 0 | 11181.81 | 11181.81 | Approved | 0 | 0 | 280 | 19 Mar 2021
GANGA DHAM TOWERS | 970 | 89410 | 19 Mar 2021 |  | YOGESH MOHAN PAWAR | YOGESH MOHAN PAWAR | EV - 2366 | B 302 Painting Work Sample | 1st Coat Paint | 3727.27 | Sq.Ft | 3 | 100 | 0 | 0 | 11181.81 | CGST 0% URD I/P | 0 | 11181.81 | 11181.81 | Approved | 0 | 0 | 280 | 19 Mar 2021
GANGA DHAM TOWERS | 970 | 89410 | 19 Mar 2021 |  | YOGESH MOHAN PAWAR | YOGESH MOHAN PAWAR | EV - 2366 | B 302 Painting Work Sample | Scrapping with 2nd Coat Putty (M) | 3727.27 | Sq.Ft | 1 | 100 | 0 | 0 | 3727.27 | CGST 0% URD I/P | 0 | 3727.27 | 3727.27 | Approved | 0 | 0 | 280 | 19 Mar 2021
GANGA DHAM TOWERS | 970 | 89410 | 19 Mar 2021 |  | YOGESH MOHAN PAWAR | YOGESH MOHAN PAWAR | EV - 2366 | B 302 Painting Work Sample | Scrapping with 1st Coat Putty (M) | 3727.27 | Sq.Ft | 1 | 100 | 0 | 0 | 3727.27 | CGST 0% URD I/P | 0 | 3727.27 | 3727.27 | Approved | 0 | 0 | 280 | 19 Mar 2021
GANGA DHAM TOWERS | 970 | 89410 | 19 Mar 2021 |  | YOGESH MOHAN PAWAR | YOGESH MOHAN PAWAR | EV - 2366 | B 302 Painting Work Sample | Astar Coat | 3727.27 | Sq.Ft | 1 | 100 | 0 | 0 | 3727.27 | CGST 0% URD I/P | 0 | 3727.27 | 3727.27 | Approved | 0 | 0 | 280 | 19 Mar 2021
GANGA DHAM TOWERS | 744 | 89396 | 18 Mar 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 2403 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 0 | 18 Mar 2021
GANGA DHAM TOWERS | 350 | 89395 | 18 Mar 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 2404 | Site Expenses | Site Expenses -SO | 0.5 | Month | 3000 | 100 | 0 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 0 | 18 Mar 2021
GANGA DHAM TOWERS | 696 | 89394 | 18 Mar 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2388 | B P3 Parking Floor Column Plaster | Gypsum Plaster (L) | 1465.73 | Sq.Ft | 4 | 100 | 146.57 | 0 | 5862.92 | C+S GST 18% I/P RD | 1055.32 | 6918.24 | 6918.24 | Approved | 0 | 0 | 59 | 18 Mar 2021
GANGA DHAM TOWERS | 696 | 89394 | 18 Mar 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2388 | B P2 Parking Floor Column Plaster | Gypsum Plaster (L) | 507 | Sq.Ft | 4 | 100 | 50.7 | 0 | 2028 | C+S GST 18% I/P RD | 365.04 | 2393.04 | 2393.04 | Approved | 0 | 0 | 59 | 18 Mar 2021
GANGA DHAM TOWERS | 649 | 89393 | 18 Mar 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 2386 | A P3 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 267 | Sq.Ft | 5 | 100 | 33.38 | 0 | 1335 | C+S GST 18% I/P RD | 240.3 | 1575.3 | 1575.3 | Approved | 0 | 0 | 138 | 18 Mar 2021
GANGA DHAM TOWERS | 649 | 89393 | 18 Mar 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 2386 | A P2 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 1780 | Sq.Ft | 5 | 100 | 222.5 | 0 | 8900 | C+S GST 18% I/P RD | 1602 | 10502 | 10502 | Approved | 0 | 0 | 138 | 18 Mar 2021
GANGA DHAM TOWERS | 649 | 89393 | 18 Mar 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 2386 | A P3 Parking Floor Column Plaster | Gypsum Plaster (L) | 267 | Sq.Ft | 4 | 100 | 26.7 | 0 | 1068 | C+S GST 18% I/P RD | 192.24 | 1260.24 | 1260.24 | Approved | 0 | 0 | 138 | 18 Mar 2021
GANGA DHAM TOWERS | 649 | 89393 | 18 Mar 2021 |  | A K INTERIOR CONTRACTOR | J K INTERIOR | EV - 2386 | A P2 Parking Floor Column Plaster | Gypsum Plaster (L) | 1780 | Sq.Ft | 4 | 100 | 178 | 0 | 7120 | C+S GST 18% I/P RD | 1281.6 | 8401.6 | 8401.6 | Approved | 0 | 0 | 138 | 18 Mar 2021
GANGA DHAM TOWERS | 862 | 89392 | 18 Mar 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2385 | Club House 1st Floor Brickwork/ Plaster | Gypsum Plaster (L) | 483 | Sq.Ft | 9 | 100 | 108.68 | 0 | 4347 | C+S GST 18% I/P RD | 782.46 | 5129.46 | 5129.46 | Approved | 0 | 0 | 86 | 18 Mar 2021
GANGA DHAM TOWERS | 862 | 89392 | 18 Mar 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2385 | Club house GF Brickwork/Plaster | Gypsum Plaster (L) | 796 | Sq.Ft | 9 | 100 | 179.1 | 0 | 7164 | C+S GST 18% I/P RD | 1289.52 | 8453.52 | 8453.52 | Approved | 0 | 0 | 86 | 18 Mar 2021
GANGA DHAM TOWERS | 752 | 89391 | 18 Mar 2021 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2393 | 125KVA & 40KVA DG Earthing (M+L) | Earthing work-UDG | 12 | No. | 4000 | 100 | 1200 | 0 | 48000 | C+S GST 18% I/P RD | 8640 | 56640 | 56640 | Approved | 0 | 0 | 720 | 18 Mar 2021
GANGA DHAM TOWERS | 940 | 89354 | 13 Mar 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 2402 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 165 | 13 Mar 2021
GANGA DHAM TOWERS | 866 | 89342 | 13 Mar 2021 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 2353 | A FAS & PA System | 2C 1.5 sqmm (FRLS) Cable (M) | 3500 | Mtrs | 30 | 100 | 0 | 0 | 105000 | C+S GST 18% I/P RD | 18900 | 123900 | 123900 | Approved | 0 | 0 | 0 | 13 Mar 2021
GANGA DHAM TOWERS | 866 | 89342 | 13 Mar 2021 |  | GLOTECH FIRE ENGINEERS | GLOTECH FIRE ENGINEERS | EV - 2353 | A FAS & PA System | 2C 1.5 sqmm (FRLS) Cable (M) | 3500 | Mtrs | 30 | 100 | 0 | 0 | 105000 | C+S GST 18% I/P RD | 18900 | 123900 | 123900 | Approved | 0 | 0 | 0 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 101 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1154.6667 | Sq.Ft | 45 | 100 | 1299 | 0 | 51960 | C+S GST 18% I/P RD | 9352.8 | 61312.8 | 61312.8 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 101 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 45 | 100 | 273.38 | 0 | 10935 | C+S GST 18% I/P RD | 1968.3 | 12903.3 | 12903.3 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 101 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 305 | Sq.Ft | 45 | 100 | 343.13 | 0 | 13725 | C+S GST 18% I/P RD | 2470.5 | 16195.5 | 16195.5 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 101 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 193.9556 | Sq.Ft | 45 | 100 | 218.2 | 0 | 8728 | C+S GST 18% I/P RD | 1571.04 | 10299.04 | 10299.04 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 1301 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1154.6727 | Sq.Ft | 55 | 100 | 1587.67 | 0 | 63507 | C+S GST 18% I/P RD | 11431.26 | 74938.26 | 74938.26 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 1301 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 305 | Sq.Ft | 55 | 100 | 419.38 | 0 | 16775 | C+S GST 18% I/P RD | 3019.5 | 19794.5 | 19794.5 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 1301 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 193.9455 | Sq.Ft | 55 | 100 | 266.68 | 0 | 10667 | C+S GST 18% I/P RD | 1920.06 | 12587.06 | 12587.06 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 1301 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 55 | 100 | 334.13 | 0 | 13365 | C+S GST 18% I/P RD | 2405.7 | 15770.7 | 15770.7 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 701 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 196.93 | Sq.Ft | 50 | 100 | 246.16 | 0 | 9846.5 | C+S GST 18% I/P RD | 1772.38 | 11618.88 | 11618.88 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 701 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 1030 | Sq.Ft | 50 | 100 | 1287.5 | 0 | 51500 | C+S GST 18% I/P RD | 9270 | 60770 | 60770 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 701 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 243 | Sq.Ft | 50 | 100 | 303.75 | 0 | 12150 | C+S GST 18% I/P RD | 2187 | 14337 | 14337 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 758 | 89340 | 13 Mar 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2368 | B 701 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 305 | Sq.Ft | 50 | 100 | 381.25 | 0 | 15250 | C+S GST 18% I/P RD | 2745 | 17995 | 17995 | Approved | 0 | 0 | 2088 | 13 Mar 2021
GANGA DHAM TOWERS | 903 | 89322 | 11 Mar 2021 |  | OM SAI CORP | OCTOPUS ADVERTISING VERTICALS | EV - 2307 | MEDIA FLEX PASTING | Star Flex | 262.8 | Sq.Ft | 20 | 100 | 0 | 0 | 5256 | C+S GST 18% I/P RD | 946.08 | 6202.08 | 6202.08 | Approved | 0 | 0 | 79 | 11 Mar 2021
GANGA DHAM TOWERS | 956 | 89321 | 11 Mar 2021 |  | OM SAI CORP | OCTOPUS ADVERTISING VERTICALS | EV - 2306 | MEDIA Flex printing | Flex Printing & Pasting | 963 | Sq.Ft | 18 | 100 | 0 | 0 | 17334 | C+S GST 18% I/P RD | 3120.12 | 20454.12 | 20454.12 | Approved | 0 | 0 | 260 | 11 Mar 2021
GANGA DHAM TOWERS | 668 | 89316 | 11 Mar 2021 |  | ACC LTD (SUPPLIER) | LOTUS ENTERPRISES | EV - 2346 | A Bldg 23rd Slab Pump Charges | Pumping Charges-BC | 66 | Cu.Mtrs | 118.644 | 100 | 0 | 0 | 7830.5 | C+S GST 18% I/P RD | 1409.5 | 9240 | 9240 | Approved | 0 | 0 | 374 | 11 Mar 2021
GANGA DHAM TOWERS | 668 | 89316 | 11 Mar 2021 |  | ACC LTD (SUPPLIER) | LOTUS ENTERPRISES | EV - 2346 | A Bldg 23rd Slab Pump Charges | Pumping Charges-BC | 54 | Cu.Mtrs | 118.644 | 100 | 0 | 0 | 6406.78 | C+S GST 18% I/P RD | 1153.22 | 7560 | 7560 | Approved | 0 | 0 | 374 | 11 Mar 2021
GANGA DHAM TOWERS | 668 | 89316 | 11 Mar 2021 |  | ACC LTD (SUPPLIER) | LOTUS ENTERPRISES | EV - 2346 | A Bldg 23rd Slab Pump Charges | Pumping Charges-BC | 90 | Cu.Mtrs | 118.644 | 100 | 0 | 0 | 10677.96 | C+S GST 18% I/P RD | 1922.04 | 12600 | 12600 | Approved | 0 | 0 | 374 | 11 Mar 2021
GANGA DHAM TOWERS | 931 | 89315 | 11 Mar 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 2344 | C Building Grade Slab Pumping Charges | Pumping Charges-BC | 122 | Cu.Mtrs | 190 | 100 | 0 | 0 | 23180 | C+S GST 18% I/P RD | 4172.4 | 27352.4 | 27352.4 | Approved | 0 | 0 | 348 | 11 Mar 2021
GANGA DHAM TOWERS | 929 | 89314 | 11 Mar 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 2345 | B Bldg 30th Slab Pumping Charges | Pumping Charges-BC | 142 | Cu.Mtrs | 190 | 100 | 0 | 0 | 26980 | C+S GST 18% I/P RD | 4856.4 | 31836.4 | 31836.4 | Approved | 0 | 0 | 405 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 602 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 112 | Sq.Ft | 15 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 602 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 25 | R.Ft | 45 | 100 | 28.13 | 0 | 1125 | C+S GST 18% I/P RD | 202.5 | 1327.5 | 1327.5 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 602 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 100 | R.Ft | 45 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 602 Master Bed Marble Flooring | Italian marble Skirting - BCo | 60 | R.Ft | 45 | 100 | 67.5 | 0 | 2700 | C+S GST 18% I/P RD | 486 | 3186 | 3186 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1402 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 55 | 100 | 250.87 | 0 | 10034.75 | C+S GST 18% I/P RD | 1806.26 | 11841.01 | 11841.01 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1402 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 55 | 100 | 787.61 | 0 | 31504.55 | C+S GST 18% I/P RD | 5670.82 | 37175.37 | 37175.37 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1702 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 55 | 100 | 787.61 | 0 | 31504.55 | C+S GST 18% I/P RD | 5670.82 | 37175.37 | 37175.37 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1702 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 206 | Sq.Ft | 55 | 100 | 283.25 | 0 | 11330 | C+S GST 18% I/P RD | 2039.4 | 13369.4 | 13369.4 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1402 Tiling Below Wooden Flooring | Ceramic Flooring work | 141 | Sq.Ft | 18 | 100 | 63.45 | 0 | 2538 | C+S GST 18% I/P RD | 456.84 | 2994.84 | 2994.84 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1702 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 55 | 100 | 250.87 | 0 | 10034.75 | C+S GST 18% I/P RD | 1806.26 | 11841.01 | 11841.01 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 602 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.81 | Sq.Ft | 45 | 100 | 644.41 | 0 | 25776.45 | C+S GST 18% I/P RD | 4639.76 | 30416.21 | 30416.21 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1402 Master Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 206 | Sq.Ft | 55 | 100 | 283.25 | 0 | 11330 | C+S GST 18% I/P RD | 2039.4 | 13369.4 | 13369.4 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 602 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.45 | Sq.Ft | 45 | 100 | 205.26 | 0 | 8210.25 | C+S GST 18% I/P RD | 1477.84 | 9688.09 | 9688.09 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1702 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 126 | Sq.Ft | 55 | 100 | 173.25 | 0 | 6930 | C+S GST 18% I/P RD | 1247.4 | 8177.4 | 8177.4 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 602 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 206 | Sq.Ft | 45 | 100 | 231.75 | 0 | 9270 | C+S GST 18% I/P RD | 1668.6 | 10938.6 | 10938.6 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 602 Tiling Below Wooden Flooring | Ceramic Flooring work | 141 | Sq.Ft | 13 | 100 | 45.83 | 0 | 1833 | C+S GST 18% I/P RD | 329.94 | 2162.94 | 2162.94 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1702 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 112 | Sq.Ft | 24 | 100 | 67.2 | 0 | 2688 | C+S GST 18% I/P RD | 483.84 | 3171.84 | 3171.84 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1402 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 112 | Sq.Ft | 24 | 100 | 67.2 | 0 | 2688 | C+S GST 18% I/P RD | 483.84 | 3171.84 | 3171.84 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1702 Master Bed Marble Flooring | Italian marble Skirting - BCo | 60 | R.Ft | 55 | 100 | 82.5 | 0 | 3300 | C+S GST 18% I/P RD | 594 | 3894 | 3894 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1402 Master Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 60 | R.Ft | 55 | 100 | 82.5 | 0 | 3300 | C+S GST 18% I/P RD | 594 | 3894 | 3894 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1402 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 25 | R.Ft | 55 | 100 | 34.38 | 0 | 1375 | C+S GST 18% I/P RD | 247.5 | 1622.5 | 1622.5 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1702 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 100 | R.Ft | 55 | 100 | 137.5 | 0 | 5500 | C+S GST 18% I/P RD | 990 | 6490 | 6490 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1402 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 100 | R.Ft | 55 | 100 | 137.5 | 0 | 5500 | C+S GST 18% I/P RD | 990 | 6490 | 6490 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 537 | 89312 | 11 Mar 2021 |  | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2303 | A 1702 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 25 | R.Ft | 55 | 100 | 34.38 | 0 | 1375 | C+S GST 18% I/P RD | 247.5 | 1622.5 | 1622.5 | Approved | 0 | 0 | 1470 | 11 Mar 2021
GANGA DHAM TOWERS | 350 | 89281 | 09 Mar 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 2295 | Site Expenses | Site Expenses -SO | 0.5533 | Month | 3000 | 100 | 0 | 0 | 1660 | CGST 0% URD I/P | 0 | 1660 | 1660 | Approved | 0 | 0 | 0 | 09 Mar 2021
GANGA DHAM TOWERS | 350 | 89281 | 09 Mar 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 2295 | Site Expenses | Site Expenses -SO | 0.1867 | Month | 3000 | 100 | 0 | 0 | 560 | CGST 0% URD I/P | 0 | 560 | 560 | Approved | 0 | 0 | 0 | 09 Mar 2021
GANGA DHAM TOWERS | 149 | 89280 | 09 Mar 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 2328 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3640 | No. | 4 | 100 | 0 | 0 | 14560 | CGST 0% URD I/P | 0 | 14560 | 14560 | Approved | 0 | 0 | 0 | 09 Mar 2021
GANGA DHAM TOWERS | 950 | 89278 | 09 Mar 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2334 | Club house 1st Fl External Texture | Texture Paint (M) | 2667.6 | Sq.Ft | 12.97 | 100 | 0 | 0 | 34598.77 | C+S GST 18% I/P RD | 6227.78 | 40826.55 | 40826.55 | Approved | 0 | 0 | 0 | 09 Mar 2021
GANGA DHAM TOWERS | 950 | 89278 | 09 Mar 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2334 | Club House External Column, Beams ,Retaining wall External | Texture Paint (M) | 3211.7965 | Sq.Ft | 12.97 | 100 | 0 | 0 | 41657 | C+S GST 18% I/P RD | 7498.26 | 49155.26 | 49155.26 | Approved | 0 | 0 | 0 | 09 Mar 2021
GANGA DHAM TOWERS | 950 | 89278 | 09 Mar 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2334 | Club house Ground Fl External Texture | Texture Paint (M) | 2045.6 | Sq.Ft | 12.97 | 100 | 0 | 0 | 26531.43 | C+S GST 18% I/P RD | 4775.66 | 31307.09 | 31307.09 | Approved | 0 | 0 | 0 | 09 Mar 2021
GANGA DHAM TOWERS | 126 | 89276 | 09 Mar 2021 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP VAMANRAO RUPNAWAR | EV - 2293 | Site Expenses | Site Expenses -SO | 0.9 | Month | 15000 | 100 | 0 | 0 | 13500 | CGST 0% URD I/P | 0 | 13500 | 13500 | Approved | 0 | 0 | 0 | 09 Mar 2021
GANGA DHAM TOWERS | 126 | 89276 | 09 Mar 2021 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP VAMANRAO RUPNAWAR | EV - 2293 | Site Expenses | Site Expenses -SO | 0.1793 | Month | 15000 | 100 | 0 | 0 | 2689 | CGST 0% URD I/P | 0 | 2689 | 2689 | Approved | 0 | 0 | 0 | 09 Mar 2021
GANGA DHAM TOWERS | 880 | 89245 | 06 Mar 2021 |  | AMFEW AND CO | AMFEW AND CO |  | DA Development AMC Charges For AC | AMC Charges | 1 | No. | 16800 | 8.33 | 0 | 0 | 1400.01 | C+S GST 18% I/P RD | 252 | 1652.01 | 1652.01 |  | 0 | 0 | 11 | 06 Mar 2021
GANGA DHAM TOWERS | 880 | 89244 | 06 Mar 2021 |  | AMFEW AND CO | AMFEW AND CO |  | DA Development AMC Charges For AC | AMC Charges | 1 | No. | 16800 | 8.33 | 0 | 0 | 1400.01 | C+S GST 18% I/P RD | 252 | 1652.01 | 1652.01 |  | 0 | 0 | 11 | 06 Mar 2021
GANGA DHAM TOWERS | 880 | 89243 | 06 Mar 2021 |  | AMFEW AND CO | AMFEW AND CO |  | DA Development AMC Charges For AC | AMC Charges | 1 | No. | 16800 | 8.33 | 0 | 0 | 1400.01 | C+S GST 18% I/P RD | 252 | 1652.01 | 1652.01 |  | 0 | 0 | 11 | 06 Mar 2021
GANGA DHAM TOWERS | 506 | 89242 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2332 | B 17th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 33 | 05 Mar 2021
GANGA DHAM TOWERS | 506 | 89242 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2332 | B 12th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 33 | 05 Mar 2021
GANGA DHAM TOWERS | 506 | 89242 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2332 | B 11th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 33 | 05 Mar 2021
GANGA DHAM TOWERS | 506 | 89242 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2332 | B 16th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 33 | 05 Mar 2021
GANGA DHAM TOWERS | 506 | 89242 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2332 | B 14th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 33 | 05 Mar 2021
GANGA DHAM TOWERS | 506 | 89242 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2332 | B 15th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 33 | 05 Mar 2021
GANGA DHAM TOWERS | 506 | 89242 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2332 | B 13th Floor Common Lobby Chemical Grouting | Chemical Grouting.- BC | 316.35 | Sq.Ft | 2 | 100 | 63.27 | 0 | 632.7 | CGST 0% URD I/P | 0 | 632.7 | 632.7 | Approved | 0 | 0 | 33 | 05 Mar 2021
GANGA DHAM TOWERS | 522 | 89241 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2326 | B Bldg 801 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1250 | 100 | 218.75 | 0 | 8750 | CGST 0% URD I/P | 0 | 8750 | 8750 | Approved | 0 | 0 | 196 | 05 Mar 2021
GANGA DHAM TOWERS | 522 | 89241 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2326 | B Bldg 901 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1 | No. | 1250 | 100 | 31.25 | 0 | 1250 | CGST 0% URD I/P | 0 | 1250 | 1250 | Approved | 0 | 0 | 196 | 05 Mar 2021
GANGA DHAM TOWERS | 522 | 89241 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2326 | B Bldg 1002 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 6 | No. | 1100 | 100 | 165 | 0 | 6600 | CGST 0% URD I/P | 0 | 6600 | 6600 | Approved | 0 | 0 | 196 | 05 Mar 2021
GANGA DHAM TOWERS | 522 | 89241 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2326 | B Bldg 1202 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1 | No. | 1100 | 100 | 27.5 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 196 | 05 Mar 2021
GANGA DHAM TOWERS | 522 | 89241 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2326 | B Bldg 902 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 1 | No. | 1100 | 100 | 27.5 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 196 | 05 Mar 2021
GANGA DHAM TOWERS | 522 | 89241 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2326 | B Bldg 101 Internal Plumbing PPR-C (L) | Int Flat PPRC Work. | 7 | No. | 1050 | 100 | 183.75 | 0 | 7350 | CGST 0% URD I/P | 0 | 7350 | 7350 | Approved | 0 | 0 | 196 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 902 Chemical & IPS Waterproofing | IPS W/P | 424 | Sq.Ft | 11 | 100 | 466.4 | 0 | 4664 | CGST 0% URD I/P | 0 | 4664 | 4664 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 101 Chemical & IPS Waterproofing | IPS W/P | 581.79 | Sq.Ft | 11 | 100 | 639.97 | 0 | 6399.69 | CGST 0% URD I/P | 0 | 6399.69 | 6399.69 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 701 Chemical & IPS Waterproofing | IPS W/P | 581.79 | Sq.Ft | 11 | 100 | 639.97 | 0 | 6399.69 | CGST 0% URD I/P | 0 | 6399.69 | 6399.69 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1002 Chemical & IPS Waterproofing | IPS W/P | 424 | Sq.Ft | 11 | 100 | 466.4 | 0 | 4664 | CGST 0% URD I/P | 0 | 4664 | 4664 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1401 Chemical Grouting | Chemical Grouting.- BC | 2535 | Sq.Ft | 2 | 100 | 507 | 0 | 5070 | CGST 0% URD I/P | 0 | 5070 | 5070 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 902 Chemical Grouting | Chemical Grouting.- BC | 100 | Sq.Ft | 2 | 100 | 20 | 0 | 200 | CGST 0% URD I/P | 0 | 200 | 200 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 701 Chemical Grouting | Chemical Grouting.- BC | 2535 | Sq.Ft | 2 | 100 | 507 | 0 | 5070 | CGST 0% URD I/P | 0 | 5070 | 5070 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 902 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 901 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 581.79 | Sq.Ft | 19 | 100 | 1105.4 | 0 | 11054.01 | CGST 0% URD I/P | 0 | 11054.01 | 11054.01 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 902 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 468.45 | Sq.Ft | 19 | 100 | 890.06 | 0 | 8900.55 | CGST 0% URD I/P | 0 | 8900.55 | 8900.55 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 202 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 165 | Sq.Ft | 19 | 100 | 313.5 | 0 | 3135 | CGST 0% URD I/P | 0 | 3135 | 3135 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 101 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 581.79 | Sq.Ft | 19 | 100 | 1105.4 | 0 | 11054.01 | CGST 0% URD I/P | 0 | 11054.01 | 11054.01 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1002 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 165 | Sq.Ft | 19 | 100 | 313.5 | 0 | 3135 | CGST 0% URD I/P | 0 | 3135 | 3135 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 701 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 581.79 | Sq.Ft | 19 | 100 | 1105.4 | 0 | 11054.01 | CGST 0% URD I/P | 0 | 11054.01 | 11054.01 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 901 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 902 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 701 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 101 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1301 Chemical Grouting | Chemical Grouting.- BC | 2535 | Sq.Ft | 2 | 100 | 507 | 0 | 5070 | CGST 0% URD I/P | 0 | 5070 | 5070 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1501 Chemical Grouting | Chemical Grouting.- BC | 2535 | Sq.Ft | 2 | 100 | 507 | 0 | 5070 | CGST 0% URD I/P | 0 | 5070 | 5070 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1202 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 101 Chemical Grouting | Chemical Grouting.- BC | 2535 | Sq.Ft | 2 | 100 | 507 | 0 | 5070 | CGST 0% URD I/P | 0 | 5070 | 5070 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1302 Chemical Grouting | Chemical Grouting.- BC | 1752.16 | Sq.Ft | 2 | 100 | 350.43 | 0 | 3504.32 | CGST 0% URD I/P | 0 | 3504.32 | 3504.32 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 901 Chemical & IPS Waterproofing | IPS W/P | 581.79 | Sq.Ft | 11 | 100 | 639.97 | 0 | 6399.69 | CGST 0% URD I/P | 0 | 6399.69 | 6399.69 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 902 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 27 | No. | 70 | 100 | 189 | 0 | 1890 | CGST 0% URD I/P | 0 | 1890 | 1890 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 701 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 31 | No. | 70 | 100 | 217 | 0 | 2170 | CGST 0% URD I/P | 0 | 2170 | 2170 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1002 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 1.89 | No. | 70 | 100 | 13.23 | 0 | 132.3 | CGST 0% URD I/P | 0 | 132.3 | 132.3 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 101 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 31 | No. | 70 | 100 | 217 | 0 | 2170 | CGST 0% URD I/P | 0 | 2170 | 2170 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 901 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 31 | No. | 70 | 100 | 217 | 0 | 2170 | CGST 0% URD I/P | 0 | 2170 | 2170 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 902 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 14 | No. | 150 | 100 | 210 | 0 | 2100 | CGST 0% URD I/P | 0 | 2100 | 2100 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 101 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 701 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 1002 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 7 | No. | 150 | 100 | 105 | 0 | 1050 | CGST 0% URD I/P | 0 | 1050 | 1050 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 901 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 16 | No. | 150 | 100 | 240 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 901 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 498 | 89240 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2331 | B 101 Bore Packing, IPS seal coat, Perma Eazee coat | 4" Bore Packing | 8 | No. | 150 | 100 | 120 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 1019 | 05 Mar 2021
GANGA DHAM TOWERS | 884 | 89239 | 05 Mar 2021 |  | YOGESH SANGLE | YOGESH SANGLE | EV - 2335 | DA Dev. Kitchen work | Labour lumpsum | 1 | No. | 1600 | 100 | 0 | 0 | 1600 | CGST 0% URD I/P | 0 | 1600 | 1600 | Approved | 0 | 0 | 12 | 05 Mar 2021
GANGA DHAM TOWERS | 455 | 89238 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2330 | A Bldg Flat No. 1302 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.3571 | No. | 1400 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 149 | 05 Mar 2021
GANGA DHAM TOWERS | 455 | 89238 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2330 | A Bldg Flat No. 1402 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.3571 | No. | 1400 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 149 | 05 Mar 2021
GANGA DHAM TOWERS | 455 | 89238 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2330 | A Bldg Flat No. 903 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.75 | No. | 1200 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 149 | 05 Mar 2021
GANGA DHAM TOWERS | 455 | 89238 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2330 | A Bldg Flat No. 1204 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.75 | No. | 1200 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 149 | 05 Mar 2021
GANGA DHAM TOWERS | 455 | 89238 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2330 | A Bldg Flat No. 703 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.75 | No. | 1200 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 149 | 05 Mar 2021
GANGA DHAM TOWERS | 455 | 89238 | 05 Mar 2021 |  | SHWETA SURESH GOVALKAR | SHWETA SURESH GOVALKAR | EV - 2330 | A Bldg Flat No. 1003 Internal Plumbing PPR-C | Int Flat PPRC Work. | 2.75 | No. | 1200 | 100 | 82.5 | 0 | 3300 | CGST 0% URD I/P | 0 | 3300 | 3300 | Approved | 0 | 0 | 149 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1303 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 104 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1501 Chemical Grouting Work | Chemical Grouting Rate Diff. BCo | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1204 Chemical & IPS Waterproofing | IPS W/P | 230 | Sq.Ft | 11 | 100 | 253 | 0 | 2530 | CGST 0% URD I/P | 0 | 2530 | 2530 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1303 Chemical & IPS Waterproofing | IPS W/P | 230 | Sq.Ft | 11 | 100 | 253 | 0 | 2530 | CGST 0% URD I/P | 0 | 2530 | 2530 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1704 Chemical & IPS Waterproofing | IPS W/P | 200 | Sq.Ft | 11 | 100 | 220 | 0 | 2200 | CGST 0% URD I/P | 0 | 2200 | 2200 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1402 Chemical & IPS Waterproofing | IPS W/P | 230 | Sq.Ft | 11 | 100 | 253 | 0 | 2530 | CGST 0% URD I/P | 0 | 2530 | 2530 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 104 Chemical Grouting Work | Chemical Grouting.- BC | 1461.79 | Sq.Ft | 1 | 100 | 146.18 | 0 | 1461.79 | CGST 0% URD I/P | 0 | 1461.79 | 1461.79 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1303 Chemical Grouting Work | Chemical Grouting.- BC | 1124.36 | Sq.Ft | 1 | 100 | 112.44 | 0 | 1124.36 | CGST 0% URD I/P | 0 | 1124.36 | 1124.36 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1501 Chemical Grouting Work | Chemical Grouting.- BC | 1447 | Sq.Ft | 1 | 100 | 144.7 | 0 | 1447 | CGST 0% URD I/P | 0 | 1447 | 1447 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1303 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 13 | No. | 70 | 100 | 91 | 0 | 910 | CGST 0% URD I/P | 0 | 910 | 910 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1704 Bore Packing, IPS seal coat, Perma Eazee coat | Perma Eazee Coat W/P (M+L) | 13 | No. | 70 | 100 | 91 | 0 | 910 | CGST 0% URD I/P | 0 | 910 | 910 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1402 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1204 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1704 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1303 Bore Packing, IPS seal coat, Perma Eazee coat | 5" Bore Packing | 13 | No. | 150 | 100 | 195 | 0 | 1950 | CGST 0% URD I/P | 0 | 1950 | 1950 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1402 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1704 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1204 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1303 Bore Packing, IPS seal coat, Perma Eazee coat | 3" Bore Packing | 6 | No. | 150 | 100 | 90 | 0 | 900 | CGST 0% URD I/P | 0 | 900 | 900 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1303 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 230 | Sq.Ft | 19 | 100 | 437 | 0 | 4370 | CGST 0% URD I/P | 0 | 4370 | 4370 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1704 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 200 | Sq.Ft | 19 | 100 | 380 | 0 | 3800 | CGST 0% URD I/P | 0 | 3800 | 3800 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 401 | 89237 | 05 Mar 2021 |  | SHREE GURUDATTA ENTERPRISES | SHREE GURUDATTA ENTERPRISES | EV - 2329 | A 1402 Chemical & IPS Waterproofing | Chemical W/P (L+M) | 230 | Sq.Ft | 19 | 100 | 437 | 0 | 4370 | CGST 0% URD I/P | 0 | 4370 | 4370 | Approved | 0 | 0 | 327 | 05 Mar 2021
GANGA DHAM TOWERS | 949 | 89235 | 05 Mar 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2333 | Club House External Column, Beams ,Retaining wall External | Texture Paint (L) | 3211.8298 | Sq.Ft | 11.75 | 100 | 943.48 | 0 | 37739 | C+S GST 18% I/P RD | 6793.02 | 44532.02 | 44532.02 | Approved | 0 | 0 | 698 | 05 Mar 2021
GANGA DHAM TOWERS | 949 | 89235 | 05 Mar 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2333 | Club house Ground Fl External Texture | Texture Paint (L) | 2045.6 | Sq.Ft | 11.75 | 100 | 600.9 | 0 | 24035.8 | C+S GST 18% I/P RD | 4326.44 | 28362.24 | 28362.24 | Approved | 0 | 0 | 698 | 05 Mar 2021
GANGA DHAM TOWERS | 949 | 89235 | 05 Mar 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2333 | Club house 1st Fl External Texture | Texture Paint (L) | 2667.6 | Sq.Ft | 11.75 | 100 | 783.61 | 0 | 31344.3 | C+S GST 18% I/P RD | 5641.98 | 36986.28 | 36986.28 | Approved | 0 | 0 | 698 | 05 Mar 2021
GANGA DHAM TOWERS | 959 | 89234 | 05 Mar 2021 |  | NAMOH GLASSES | NAMOH GLASSES | EV - 2350 | Club House Mirror Work | Mirror fixing.. | 297.4784 | Sq.Ft | 168.94 | 100 | 1256.4 | 0 | 50256 | C+S GST 18% I/P RD | 9046.08 | 59302.08 | 59302.08 | Approved | 0 | 0 | 379 | 05 Mar 2021
GANGA DHAM TOWERS | 959 | 89234 | 05 Mar 2021 |  | NAMOH GLASSES | NAMOH GLASSES | EV - 2350 | Club House Mirror Work | Transportation | 1 | No. | 300 | 100 | 0 | 0 | 300 | C+S GST 18% I/P RD | 54 | 354 | 354 | Approved | 0 | 0 | 379 | 05 Mar 2021
GANGA DHAM TOWERS | 937 | 89233 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2298 | AC Machine (L) | SITC PVC Pipe 32mm (M) | 60 | Mtrs | 104 | 100 | 0 | 0 | 6240 | C+S GST 18% I/P RD | 1123.2 | 7363.2 | 7363.2 | Approved | 0 | 0 | 0 | 05 Mar 2021
GANGA DHAM TOWERS | 937 | 89233 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2298 | AC Machine (L) | Copper Refnet Joints (M) | 11 | No. | 4500 | 100 | 0 | 0 | 49500 | C+S GST 18% I/P RD | 8910 | 58410 | 58410 | Approved | 0 | 0 | 0 | 05 Mar 2021
GANGA DHAM TOWERS | 937 | 89233 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2298 | AC Machine (L) | Copper Piping with insulation (M) | 113.1 | Mtrs | 1000 | 100 | 0 | 0 | 113100 | C+S GST 18% I/P RD | 20358 | 133458 | 133458 | Approved | 0 | 0 | 0 | 05 Mar 2021
GANGA DHAM TOWERS | 937 | 89233 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2298 | AC Machine (L) | SITC PVC Pipe 25mm (M) | 42.375 | Mtrs | 96 | 100 | 0 | 0 | 4068 | C+S GST 18% I/P RD | 732.24 | 4800.24 | 4800.24 | Approved | 0 | 0 | 0 | 05 Mar 2021
GANGA DHAM TOWERS | 937 | 89233 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2298 | AC Machine (L) | 2.5 Sqmm 4 Core Cable (M) | 169 | Mtrs | 100 | 100 | 0 | 0 | 16900 | C+S GST 18% I/P RD | 3042 | 19942 | 19942 | Approved | 0 | 0 | 0 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | Copper Piping with insulation (L) | 1.04 | Mtrs | 250 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | Copper Piping with insulation (L) | 112 | Mtrs | 250 | 100 | 700 | 0 | 28000 | C+S GST 18% I/P RD | 5040 | 33040 | 33040 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | Removing of AC Machine | 1 | No. | 10000 | 100 | 250 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | SITC PVC Pipe 25mm (L) | 43 | Mtrs | 24 | 100 | 25.8 | 0 | 1032 | C+S GST 18% I/P RD | 185.76 | 1217.76 | 1217.76 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | Install. & Commissioning Indoor Units | 12 | No. | 3000 | 100 | 900 | 0 | 36000 | C+S GST 18% I/P RD | 6480 | 42480 | 42480 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | Outdoor Unit-18 HP | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | C+S GST 18% I/P RD | 2160 | 14160 | 14160 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | R4 10 Gas | 12 | Kgs | 750 | 100 | 225 | 0 | 9000 | C+S GST 18% I/P RD | 1620 | 10620 | 10620 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | SITC PVC Pipe 32mm (L) | 60 | Mtrs | 26 | 100 | 39 | 0 | 1560 | C+S GST 18% I/P RD | 280.8 | 1840.8 | 1840.8 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | Gas charging,Pressure testing- BC | 1 | No. | 15000 | 100 | 375 | 0 | 15000 | C+S GST 18% I/P RD | 2700 | 17700 | 17700 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 936 | 89232 | 05 Mar 2021 |  | MADHURA AIR CONDITIONING & REFRIGERATION | MADHURA AIR CONDITIONING & REFRIGERATION | EV - 2299 | AC Machine (L) | 2.5 Sqmm 4 Core Cable (L) | 169 | Mtrs | 25 | 100 | 105.63 | 0 | 4225 | C+S GST 18% I/P RD | 760.5 | 4985.5 | 4985.5 | Approved | 0 | 0 | 878 | 05 Mar 2021
GANGA DHAM TOWERS | 964 | 89229 | 05 Mar 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2396 | CH Sky Light Installation Work | Sky Light Installation work | 1 | No. | 70000 | 100 | 0 | 0 | 70000 | C+S GST 18% I/P RD | 12600 | 82600 | 82600 | Approved | 0 | 0 | 1050 | 05 Mar 2021
GANGA DHAM TOWERS | 909 | 89228 | 05 Mar 2021 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2352 | Landscape Area Lights& Fitting | Earthing work(m+l)- BC | 4 | No. | 4000 | 100 | 0 | 0 | 16000 | C+S GST 18% I/P RD | 2880 | 18880 | 18880 | Approved | 0 | 0 | 240 | 05 Mar 2021
GANGA DHAM TOWERS | 476 | 89201 | 05 Mar 2021 |  | VISION MANAGEMENT SERVICES | VISION MANAGEMENT SERVICES | EV - 2271 | Contract Labour Act Registration & Compliace | Consultancy Charges | 1 | No. | 5000 | 100 | 0 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 375 | 05 Mar 2021
GANGA DHAM TOWERS | 476 | 89200 | 05 Mar 2021 |  | VISION MANAGEMENT SERVICES | VISION MANAGEMENT SERVICES | EV - 2270 | Contract Labour Act Registration & Compliace | B.O.C.W. Act Registration &Compliance. | 1 | No. | 68250 | 100 | 0 | 0 | 68250 | CGST 0% URD I/P | 0 | 68250 | 68250 | Approved | 0 | 0 | 0 | 05 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 35 | 138.25 | 0 | 5530 | C+S GST 18% I/P RD | 995.4 | 6525.4 | 6525.4 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 35 | 89.25 | 0 | 3570 | C+S GST 18% I/P RD | 642.6 | 4212.6 | 4212.6 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1400 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 35 | 8.79 | 0 | 351.75 | C+S GST 18% I/P RD | 63.32 | 415.07 | 415.07 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 35 | 7.62 | 0 | 304.85 | C+S GST 18% I/P RD | 54.88 | 359.73 | 359.73 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 35 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 35 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 35 | 147 | 0 | 5880 | C+S GST 18% I/P RD | 1058.4 | 6938.4 | 6938.4 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 35 | 92.75 | 0 | 3710 | C+S GST 18% I/P RD | 667.8 | 4377.8 | 4377.8 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 35 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1300 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 35 | 25.21 | 0 | 1008.35 | C+S GST 18% I/P RD | 181.5 | 1189.85 | 1189.85 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 35 | 32.24 | 0 | 1289.75 | C+S GST 18% I/P RD | 232.16 | 1521.91 | 1521.91 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | Fan Point | 9 | No. | 200 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | Data Point | 4 | No. | 220 | 35 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2501 Internal Electrical Work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 399 | 89180 | 04 Mar 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2234 | B Bldg Flat No. 2502 Internal Electrical Work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 440 | 04 Mar 2021
GANGA DHAM TOWERS | 389 | 89165 | 04 Mar 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2312 | Loading / Unloading Expenses | Unloading of GYpsum- | 12 | Metric Tonnes | 200 | 100 | 0 | 0 | 2400 | CGST 0% URD I/P | 0 | 2400 | 2400 | Approved | 0 | 0 | 0 | 04 Mar 2021
GANGA DHAM TOWERS | 503 | 89115 | 02 Mar 2021 |  | KISANARAM SUTAR | KISANARAM SUTAR | EV - 2327 | DA Development Carpentary work | Carpentary work (L)-BC | 0.19 | No. | 368735 | 100 | 0 | 0 | 70059.65 | CGST 0% URD I/P | 0 | 70059.65 | 70059.65 | Approved | 0 | 0 | 525 | 02 Mar 2021
GANGA DHAM TOWERS | 372 | 89114 | 02 Mar 2021 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B Bldg 10th Slab Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 232.82 | Sq.Ft | 160 | 100 | 931.28 | 0 | 37251.2 | C+S GST 18% I/P RD | 6705.22 | 43956.42 | 43956.42 |  | 0 | 0 | 4724 | 02 Mar 2021
GANGA DHAM TOWERS | 372 | 89114 | 02 Mar 2021 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B Bldg 15th Slab Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 232.82 | Sq.Ft | 160 | 100 | 931.28 | 0 | 37251.2 | C+S GST 18% I/P RD | 6705.22 | 43956.42 | 43956.42 |  | 0 | 0 | 4724 | 02 Mar 2021
GANGA DHAM TOWERS | 372 | 89114 | 02 Mar 2021 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B Bldg 10th Slab Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 273.19 | Sq.Ft | 480 | 100 | 3278.28 | 0 | 131131.2 | C+S GST 18% I/P RD | 23603.62 | 154734.82 | 154734.82 |  | 0 | 0 | 4724 | 02 Mar 2021
GANGA DHAM TOWERS | 372 | 89114 | 02 Mar 2021 |  | B & B ENTERPRISES | B & B ENTERPRISES |  | B Bldg 15th Slab Refuge Built Up Area (L) | RCC Superstructure (B-up area) | 273.19 | Sq.Ft | 400 | 100 | 2731.9 | 0 | 109276 | C+S GST 18% I/P RD | 19669.68 | 128945.68 | 128945.68 |  | 0 | 0 | 4724 | 02 Mar 2021
GANGA DHAM TOWERS | 968 | 89113 | 02 Mar 2021 |  | MAYUR ARTS & ENTERPRISES | MAYUR ARTS & ENTERPRISES | EV - 2292 | Safety Boards / Flex Printing | Safety Park (Flex Printing) | 1 | No. | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 54 | 02 Mar 2021
GANGA DHAM TOWERS | 968 | 89113 | 02 Mar 2021 |  | MAYUR ARTS & ENTERPRISES | MAYUR ARTS & ENTERPRISES | EV - 2292 | Safety Boards / Flex Printing | Safety Emergency Contact No (Flex Printing) | 1 | No. | 250 | 100 | 0 | 0 | 250 | C+S GST 18% I/P RD | 45 | 295 | 295 | Approved | 0 | 0 | 54 | 02 Mar 2021
GANGA DHAM TOWERS | 968 | 89113 | 02 Mar 2021 |  | MAYUR ARTS & ENTERPRISES | MAYUR ARTS & ENTERPRISES | EV - 2292 | Safety Boards / Flex Printing | Safety Posters (Flex Printing) | 42 | No. | 130 | 100 | 0 | 0 | 5460 | C+S GST 18% I/P RD | 982.8 | 6442.8 | 6442.8 | Approved | 0 | 0 | 54 | 02 Mar 2021
GANGA DHAM TOWERS | 179 | 89112 | 02 Mar 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2400 | Road Divider Garden Maintenance | Garden work. | 25.9997 | Day | 450.89 | 100 | 0 | 0 | 11723 | C+S GST 18% I/P RD | 2110.14 | 13833.14 | 13833.14 | Approved | 0 | 0 | 173 | 02 Mar 2021
GANGA DHAM TOWERS | 179 | 89112 | 02 Mar 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2400 | Road Divider Garden Maintenance | Garden work. | 28 | Day | 407.25 | 100 | 0 | 0 | 11403 | C+S GST 18% I/P RD | 2052.54 | 13455.54 | 13455.54 | Approved | 0 | 0 | 173 | 02 Mar 2021
GANGA DHAM TOWERS | 178 | 89111 | 02 Mar 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2399 | Sales Oiifce Landscape Area . | Garden work. | 54.9982 | Day | 407.25 | 100 | 0 | 0 | 22398 | C+S GST 18% I/P RD | 4031.64 | 26429.64 | 26429.64 | Approved | 0 | 0 | 329 | 02 Mar 2021
GANGA DHAM TOWERS | 178 | 89111 | 02 Mar 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2399 | Sales Oiifce Landscape Area . | Garden work. | 47.5016 | Day | 450.89 | 100 | 0 | 0 | 21418 | C+S GST 18% I/P RD | 3855.24 | 25273.24 | 25273.24 | Approved | 0 | 0 | 329 | 02 Mar 2021
GANGA DHAM TOWERS | 744 | 89109 | 02 Mar 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 2272 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 0 | 02 Mar 2021
GANGA DHAM TOWERS | 744 | 89109 | 02 Mar 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 2272 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 0 | 02 Mar 2021
GANGA DHAM TOWERS | 413 | 89108 | 02 Mar 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2401 | Sales Oiifce Landscape Area . | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 23 | 02 Mar 2021
GANGA DHAM TOWERS | 413 | 89108 | 02 Mar 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2401 | Sales Oiifce Landscape Area . | Supervision Charges | 0.5 | Month | 4000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 23 | 02 Mar 2021
GANGA DHAM TOWERS | 978 | 89097 | 01 Mar 2021 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 2218 | 50 Year National Safety Week 2021 | Miscellaneous Expenses | 0.2667 | No. | 7500 | 100 | 0 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 0 | 01 Mar 2021
GANGA DHAM TOWERS | 965 | 89093 | 27 Feb 2021 |  | PEST-O-CRUSH | PEST-O-CRUSH | EV - 2237 | Ganga Collidium Pest Control work | Pest Control Work | 1 | No. | 800 | 100 | 0 | 0 | 800 | C+S GST 18% I/P RD | 144 | 944 | 944 | Approved | 0 | 0 | 6 | 27 Feb 2021
GANGA DHAM TOWERS | 971 | 89092 | 26 Feb 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 2235 | B 1st Floor Core Cutting | Core Cutting Work 5" BCE | 14 | No. | 300 | 100 | 105 | 0 | 4200 | C+S GST 18% I/P RD | 756 | 4956 | 4956 | Approved | 0 | 0 | 52 | 26 Feb 2021
GANGA DHAM TOWERS | 971 | 89092 | 26 Feb 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 2235 | B 1st Floor Core Cutting | Core Cutting Work 3" BCE | 2 | No. | 300 | 100 | 15 | 0 | 600 | C+S GST 18% I/P URD | 108 | 708 | 708 | Approved | 0 | 0 | 52 | 26 Feb 2021
GANGA DHAM TOWERS | 971 | 89092 | 26 Feb 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 2235 | B 1st Floor Core Cutting | Core Cutting Work 4" BCE | 7 | No. | 300 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 52 | 26 Feb 2021
GANGA DHAM TOWERS | 955 | 89087 | 26 Feb 2021 |  | PRANAV SALES SERVICES | PRANAV SALES SERVICES | EV - 2236 | Tower B - Lift Repair & Maintanance | Carriage charge | 1 | No. | 10000 | 100 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 1155 | 26 Feb 2021
GANGA DHAM TOWERS | 955 | 89087 | 26 Feb 2021 |  | PRANAV SALES SERVICES | PRANAV SALES SERVICES | EV - 2236 | Tower B - Lift Repair & Maintanance | Dismentling work | 80 | Mtrs | 900 | 100 | 0 | 0 | 72000 | C+S GST 18% I/P RD | 12960 | 84960 | 84960 | Approved | 0 | 0 | 1155 | 26 Feb 2021
GANGA DHAM TOWERS | 955 | 89087 | 26 Feb 2021 |  | PRANAV SALES SERVICES | PRANAV SALES SERVICES | EV - 2236 | Tower B - Lift Repair & Maintanance | Erection work | 80 | Mtrs | 900 | 100 | 0 | 0 | 72000 | C+S GST 18% I/P RD | 12960 | 84960 | 84960 | Approved | 0 | 0 | 1155 | 26 Feb 2021
GANGA DHAM TOWERS | 145 | 89086 | 26 Feb 2021 |  | PEST-O-CRUSH | PEST-O-CRUSH | EV - 2297 | Fogging Work | Fogging work-SO | 0.25 | Month | 6000 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 11 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 13 | 100 | 10.4 | 0 | 416 | C+S GST 18% I/P RD | 74.88 | 490.88 | 490.88 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 30 | Sq.Ft | 13 | 100 | 9.75 | 0 | 390 | C+S GST 18% I/P RD | 70.2 | 460.2 | 460.2 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 13 | 100 | 10.4 | 0 | 416 | C+S GST 18% I/P RD | 74.88 | 490.88 | 490.88 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 603 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21 | Sq.Ft | 13 | 100 | 6.83 | 0 | 273 | C+S GST 18% I/P RD | 49.14 | 322.14 | 322.14 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 37 | Sq.Ft | 13 | 100 | 12.03 | 0 | 481 | C+S GST 18% I/P RD | 86.58 | 567.58 | 567.58 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Master Toilet dado | Dado BC | 130 | Sq.Ft | 14 | 100 | 45.5 | 0 | 1820 | C+S GST 18% I/P RD | 327.6 | 2147.6 | 2147.6 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Children Toilet Dado | Dado BC | 120 | Sq.Ft | 14 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Parents Toilet dado | Dado BC | 100 | Sq.Ft | 14 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Powder Toilet dado | Dado BC | 68 | Sq.Ft | 14 | 100 | 23.8 | 0 | 952 | C+S GST 18% I/P RD | 171.36 | 1123.36 | 1123.36 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Master Toilet dado | Dado BC | 120 | Sq.Ft | 14 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 603 Guest Toilet dado | Dado BC | 100 | Sq.Ft | 14 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 603 Powder Toilet dado | Dado BC | 60 | Sq.Ft | 14 | 100 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Powder Toilet dado | Dado BC | 70 | Sq.Ft | 14 | 100 | 24.5 | 0 | 980 | C+S GST 18% I/P RD | 176.4 | 1156.4 | 1156.4 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Guest Toilet dado | Dado BC | 100 | Sq.Ft | 14 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Children Toilet dado | Dado BC | 138 | Sq.Ft | 14 | 100 | 48.3 | 0 | 1932 | C+S GST 18% I/P RD | 347.76 | 2279.76 | 2279.76 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 503 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 85 | Sq.Ft | 15 | 100 | 31.88 | 0 | 1275 | C+S GST 18% I/P RD | 229.5 | 1504.5 | 1504.5 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 504 Tiling Below Wooden Flooring | Ceramic Flooring work | 137 | Sq.Ft | 13 | 100 | 44.53 | 0 | 1781 | C+S GST 18% I/P RD | 320.58 | 2101.58 | 2101.58 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 104 Tiling Below Wooden Flooring | Ceramic Flooring work | 143 | Sq.Ft | 13 | 100 | 46.48 | 0 | 1859 | C+S GST 18% I/P RD | 334.62 | 2193.62 | 2193.62 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Guest Toilet dado | Dado BC | 50 | Sq.Ft | 20 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Powder Toilet dado | Dado BC | 37 | Sq.Ft | 20 | 100 | 18.5 | 0 | 740 | C+S GST 18% I/P RD | 133.2 | 873.2 | 873.2 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Master Toilet dado | Dado BC | 50 | Sq.Ft | 20 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Children Toilet dado | Dado BC | 50 | Sq.Ft | 20 | 100 | 25 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Children Toilet dado | Dado BC | 50 | Sq.Ft | 15 | 100 | 18.75 | 0 | 750 | C+S GST 18% I/P RD | 135 | 885 | 885 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Parents Toilet dado | Dado BC | 48 | Sq.Ft | 15 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Master Toilet dado | Dado BC | 50 | Sq.Ft | 15 | 100 | 18.75 | 0 | 750 | C+S GST 18% I/P RD | 135 | 885 | 885 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 504 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 100 | R.Ft | 45 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 504 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 40 | R.Ft | 45 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 203 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 90 | R.Ft | 45 | 100 | 101.25 | 0 | 4050 | C+S GST 18% I/P RD | 729 | 4779 | 4779 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 203 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 486 | Sq.Ft | 45 | 100 | 546.75 | 0 | 21870 | C+S GST 18% I/P RD | 3936.6 | 25806.6 | 25806.6 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 203 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144.08 | Sq.Ft | 45 | 100 | 162.09 | 0 | 6483.6 | C+S GST 18% I/P RD | 1167.04 | 7650.64 | 7650.64 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 504 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 587 | Sq.Ft | 45 | 100 | 660.38 | 0 | 26415 | C+S GST 18% I/P RD | 4754.7 | 31169.7 | 31169.7 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 104 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 587 | Sq.Ft | 45 | 100 | 660.38 | 0 | 26415 | C+S GST 18% I/P RD | 4754.7 | 31169.7 | 31169.7 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 104 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.1333 | Sq.Ft | 45 | 100 | 170.02 | 0 | 6801 | C+S GST 18% I/P RD | 1224.18 | 8025.18 | 8025.18 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 504 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151.1333 | Sq.Ft | 45 | 100 | 170.02 | 0 | 6801 | C+S GST 18% I/P RD | 1224.18 | 8025.18 | 8025.18 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 104 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.44 | Sq.Ft | 45 | 100 | 236.75 | 0 | 9469.8 | C+S GST 18% I/P RD | 1704.56 | 11174.36 | 11174.36 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 203 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 160 | Sq.Ft | 45 | 100 | 180 | 0 | 7200 | C+S GST 18% I/P RD | 1296 | 8496 | 8496 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 504 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210.44 | Sq.Ft | 45 | 100 | 236.75 | 0 | 9469.8 | C+S GST 18% I/P RD | 1704.56 | 11174.36 | 11174.36 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 25 | R.Ft | 45 | 100 | 28.13 | 0 | 1125 | C+S GST 18% I/P RD | 202.5 | 1327.5 | 1327.5 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 203 Master Bed Marble Flooring | Italian marble Skirting - BCo | 40 | R.Ft | 45 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 13 | 100 | 13 | 0 | 520 | C+S GST 18% I/P RD | 93.6 | 613.6 | 613.6 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 37 | Sq.Ft | 13 | 100 | 12.03 | 0 | 481 | C+S GST 18% I/P RD | 86.58 | 567.58 | 567.58 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 15 | Sq.Ft | 13 | 100 | 4.88 | 0 | 195 | C+S GST 18% I/P RD | 35.1 | 230.1 | 230.1 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 603 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 13 | 100 | 10.4 | 0 | 416 | C+S GST 18% I/P RD | 74.88 | 490.88 | 490.88 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 13 | 100 | 10.4 | 0 | 416 | C+S GST 18% I/P RD | 74.88 | 490.88 | 490.88 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 13 | 100 | 13 | 0 | 520 | C+S GST 18% I/P RD | 93.6 | 613.6 | 613.6 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21 | Sq.Ft | 13 | 100 | 6.83 | 0 | 273 | C+S GST 18% I/P RD | 49.14 | 322.14 | 322.14 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 37 | Sq.Ft | 13 | 100 | 12.03 | 0 | 481 | C+S GST 18% I/P RD | 86.58 | 567.58 | 567.58 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Powder Toilet dado | Dado BC | 75 | Sq.Ft | 18 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Guest Toilet dado | Dado BC | 100 | Sq.Ft | 18 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Children Toilet dado | Dado BC | 138 | Sq.Ft | 18 | 100 | 62.1 | 0 | 2484 | C+S GST 18% I/P RD | 447.12 | 2931.12 | 2931.12 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Master Toilet dado | Dado BC | 130 | Sq.Ft | 18 | 100 | 58.5 | 0 | 2340 | C+S GST 18% I/P RD | 421.2 | 2761.2 | 2761.2 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Guest Toilet dado | Dado BC | 50 | Sq.Ft | 24 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Master Toilet dado | Dado BC | 50 | Sq.Ft | 24 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Children Toilet dado | Dado BC | 50 | Sq.Ft | 24 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Powder Toilet dado | Dado BC | 37 | Sq.Ft | 24 | 100 | 22.2 | 0 | 888 | C+S GST 18% I/P RD | 159.84 | 1047.84 | 1047.84 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 21 | 100 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21.7143 | Sq.Ft | 21 | 100 | 11.4 | 0 | 456 | C+S GST 18% I/P RD | 82.08 | 538.08 | 538.08 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 21 | 100 | 16.8 | 0 | 672 | C+S GST 18% I/P RD | 120.96 | 792.96 | 792.96 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 43 | Sq.Ft | 21 | 100 | 22.58 | 0 | 903 | C+S GST 18% I/P RD | 162.54 | 1065.54 | 1065.54 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 17 | 100 | 17 | 0 | 680 | C+S GST 18% I/P RD | 122.4 | 802.4 | 802.4 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 21 | Sq.Ft | 17 | 100 | 8.93 | 0 | 357 | C+S GST 18% I/P RD | 64.26 | 421.26 | 421.26 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 40 | Sq.Ft | 17 | 100 | 17 | 0 | 680 | C+S GST 18% I/P RD | 122.4 | 802.4 | 802.4 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1003 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 17 | 100 | 13.6 | 0 | 544 | C+S GST 18% I/P RD | 97.92 | 641.92 | 641.92 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 504 Master Bed Marble Flooring | Italian marble Skirting - BCo | 50 | R.Ft | 45 | 100 | 56.25 | 0 | 2250 | C+S GST 18% I/P RD | 405 | 2655 | 2655 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Master Toilet dado | Dado BC | 130 | Sq.Ft | 22 | 100 | 71.5 | 0 | 2860 | C+S GST 18% I/P RD | 514.8 | 3374.8 | 3374.8 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Guest Toilet dado | Dado BC | 100 | Sq.Ft | 22 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Children Toilet dado | Dado BC | 138 | Sq.Ft | 22 | 100 | 75.9 | 0 | 3036 | C+S GST 18% I/P RD | 546.48 | 3582.48 | 3582.48 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 1403 Powder Toilet dado | Dado BC | 75 | Sq.Ft | 22 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Children Toilet Dado | Dado BC | 48 | Sq.Ft | 15 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Guest Toilet dado | Dado BC | 50 | Sq.Ft | 15 | 100 | 18.75 | 0 | 750 | C+S GST 18% I/P RD | 135 | 885 | 885 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Master Toilet dado | Dado BC | 48 | Sq.Ft | 15 | 100 | 18 | 0 | 720 | C+S GST 18% I/P RD | 129.6 | 849.6 | 849.6 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 603 Powder Toilet dado | Dado BC | 37 | Sq.Ft | 15 | 100 | 13.88 | 0 | 555 | C+S GST 18% I/P RD | 99.9 | 654.9 | 654.9 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 204 Powder Toilet dado | Dado BC | 33 | Sq.Ft | 15 | 100 | 12.38 | 0 | 495 | C+S GST 18% I/P RD | 89.1 | 584.1 | 584.1 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 403 Powder Toilet dado | Dado BC | 30 | Sq.Ft | 15 | 100 | 11.25 | 0 | 450 | C+S GST 18% I/P RD | 81 | 531 | 531 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 551 | 89084 | 26 Feb 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2296 | A 603 Guest Toilet dado | Dado BC | 50 | Sq.Ft | 15 | 100 | 18.75 | 0 | 750 | C+S GST 18% I/P RD | 135 | 885 | 885 | Approved | 0 | 0 | 1489 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Secondary Light Points (Looping) | 44 | No. | 100 | 35 | 38.5 | 0 | 1540 | C+S GST 18% I/P RD | 277.2 | 1817.2 | 1817.2 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Secondary Light Points (Looping) | 39 | No. | 100 | 35 | 34.13 | 0 | 1365 | C+S GST 18% I/P RD | 245.7 | 1610.7 | 1610.7 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Fan Point | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Fan Point | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 35 | 37.19 | 0 | 1487.5 | C+S GST 18% I/P RD | 267.76 | 1755.26 | 1755.26 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 35 | 32.81 | 0 | 1312.5 | C+S GST 18% I/P RD | 236.26 | 1548.76 | 1548.76 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 39 | No. | 250 | 35 | 85.31 | 0 | 3412.5 | C+S GST 18% I/P RD | 614.26 | 4026.76 | 4026.76 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 40 | No. | 250 | 35 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2501 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 359 | 89082 | 26 Feb 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2233 | A Bldg Flat No.-2502 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 606 | 26 Feb 2021
GANGA DHAM TOWERS | 978 | 89065 | 24 Feb 2021 |  | SACHIN PRALHAD GAIKWAD | SACHIN PRALHAD GAIKWAD | EV - 2206 | 50 Year National Safety Week 2021 | Miscellaneous Expenses | 0.5333 | No. | 7500 | 100 | 0 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 0 | 24 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | Data Point | 4 | No. | 220 | 35 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | Data Point | 4 | No. | 220 | 35 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | Fan Point | 9 | No. | 200 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | Fan Point | 9 | No. | 200 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 35 | 25.21 | 0 | 1008.35 | C+S GST 18% I/P RD | 181.5 | 1189.85 | 1189.85 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 35 | 32.24 | 0 | 1289.75 | C+S GST 18% I/P RD | 232.16 | 1521.91 | 1521.91 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 35 | 25.21 | 0 | 1008.35 | C+S GST 18% I/P RD | 181.5 | 1189.85 | 1189.85 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 35 | 32.24 | 0 | 1289.75 | C+S GST 18% I/P RD | 232.16 | 1521.91 | 1521.91 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 35 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 35 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 35 | 147 | 0 | 5880 | C+S GST 18% I/P RD | 1058.4 | 6938.4 | 6938.4 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 35 | 147 | 0 | 5880 | C+S GST 18% I/P RD | 1058.4 | 6938.4 | 6938.4 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 35 | 92.75 | 0 | 3710 | C+S GST 18% I/P RD | 667.8 | 4377.8 | 4377.8 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 35 | 92.75 | 0 | 3710 | C+S GST 18% I/P RD | 667.8 | 4377.8 | 4377.8 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 35 | 7.62 | 0 | 304.85 | C+S GST 18% I/P RD | 54.88 | 359.73 | 359.73 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 35 | 8.79 | 0 | 351.75 | C+S GST 18% I/P RD | 63.32 | 415.07 | 415.07 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 35 | 8.79 | 0 | 351.75 | C+S GST 18% I/P RD | 63.32 | 415.07 | 415.07 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 35 | 7.62 | 0 | 304.85 | C+S GST 18% I/P RD | 54.88 | 359.73 | 359.73 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 35 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 35 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 35 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 35 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 35 | 89.25 | 0 | 3570 | C+S GST 18% I/P RD | 642.6 | 4212.6 | 4212.6 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 35 | 138.25 | 0 | 5530 | C+S GST 18% I/P RD | 995.4 | 6525.4 | 6525.4 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 35 | 138.25 | 0 | 5530 | C+S GST 18% I/P RD | 995.4 | 6525.4 | 6525.4 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 35 | 89.25 | 0 | 3570 | C+S GST 18% I/P RD | 642.6 | 4212.6 | 4212.6 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2401 Internal Electrical Work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2302 Internal Electrical Work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2301 Internal Electrical Work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 399 | 89061 | 23 Feb 2021 |  | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2195 | B Bldg Flat No. 2402 Internal Electrical Work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 852 | 23 Feb 2021
GANGA DHAM TOWERS | 371 | 89045 | 20 Feb 2021 |  | CONSTROGENESIS | CONSTROGENESIS | EV - 2325 | EWS Bldg Built-up Area Diffrence From 1st to LMR OHWT | RCC Superstructure (B-up area) | 778 | Sq.Ft | 160 | 100 | 3112 | 0 | 124480 | C+S GST 18% I/P RD | 22406.4 | 146886.4 | 146886.4 | Approved | 0 | 0 | 1867 | 20 Feb 2021
GANGA DHAM TOWERS | 493 | 89044 | 20 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2238 | D Bldg West Side External Plaster | External Plaster- BC | 2380 | Sq.Ft | 35 | 100 | 2082.5 | 0 | 83300 | C+S GST 18% I/P RD | 14994 | 98294 | 98294 | Approved | 0 | 0 | 625 | 20 Feb 2021
GANGA DHAM TOWERS | 778 | 89043 | 20 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2239 | D Build. 6th Floor RCC Patli (L) | Patli (Band)- BC | 674.82 | R.Ft | 12 | 100 | 202.45 | 0 | 8097.84 | C+S GST 18% I/P RD | 1457.62 | 9555.46 | 9555.46 | Approved | 0 | 0 | 61 | 20 Feb 2021
GANGA DHAM TOWERS | 958 | 89029 | 17 Feb 2021 |  | M.B PRINTERS | M.B PRINTERS | EV - 2166 | MEDIA PRINTING | CALLENDER | 10000 | No. | 16 | 100 | 0 | 0 | 160000 | C+S GST 18% I/P RD | 28800 | 188800 | 188800 | Approved | 0 | 0 | 1200 | 17 Feb 2021
GANGA DHAM TOWERS | 389 | 89028 | 17 Feb 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2381 | Loading / Unloading Expenses | Unloading of AAC Blocks | 3686 | No. | 2 | 100 | 0 | 0 | 7372 | CGST 0% URD I/P | 0 | 7372 | 7372 | Approved | 0 | 0 | 0 | 17 Feb 2021
GANGA DHAM TOWERS | 389 | 89028 | 17 Feb 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2381 | Loading / Unloading Expenses | Unloading work-SO | 1 | No. | 500 | 100 | 0 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 0 | 17 Feb 2021
GANGA DHAM TOWERS | 389 | 89028 | 17 Feb 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2381 | Loading / Unloading Expenses | Unloading work-SO | 4 | No. | 1000 | 100 | 0 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 0 | 17 Feb 2021
GANGA DHAM TOWERS | 389 | 89028 | 17 Feb 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 2381 | Loading / Unloading Expenses | Unloading of tiles. | 5 | Metric Tonnes | 160 | 100 | 0 | 0 | 800 | CGST 0% URD I/P | 0 | 800 | 800 | Approved | 0 | 0 | 0 | 17 Feb 2021
GANGA DHAM TOWERS | 126 | 89022 | 17 Feb 2021 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 2175 | Site Expenses | Site Expenses -SO | 0.0346 | Month | 15000 | 100 | 0 | 0 | 519 | CGST 0% URD I/P | 0 | 519 | 519 | Approved | 0 | 0 | 0 | 17 Feb 2021
GANGA DHAM TOWERS | 126 | 89022 | 17 Feb 2021 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 2175 | Site Expenses | Site Expenses -SO | 0.0475 | Month | 15000 | 100 | 0 | 0 | 712 | CGST 0% URD I/P | 0 | 712 | 712 | Approved | 0 | 0 | 0 | 17 Feb 2021
GANGA DHAM TOWERS | 954 | 89021 | 17 Feb 2021 |  | INDIE VISUAL WORKS | INDIE VISUAL WORKS | EV - 2240 | Club House Model Shifting Work | Dismentling & Installation work (L) | 1 | No. | 200000 | 100 | 0 | 0 | 200000 | IGST 18% I/P RD | 36000 | 236000 | 236000 | Approved | 0 | 0 | 1500 | 17 Feb 2021
GANGA DHAM TOWERS | 496 | 89012 | 13 Feb 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2163 | B 1102 Gypsum Plaster | Gypsum on Wall (M) | 4054.15 | Sq.Ft | 3.5 | 100 | 0 | 0 | 14189.53 | C+S GST 18% I/P RD | 2554.12 | 16743.65 | 16743.65 | Approved | 0 | 2770 | 0 | 13 Feb 2021
GANGA DHAM TOWERS | 496 | 89012 | 13 Feb 2021 |  | J K INTERIOR | SEVEN STAR GYPSUM | EV - 2163 | B 1202 Gypsum Plaster | Gypsum on Wall (M) | 1157.1429 | Sq.Ft | 3.5 | 100 | 0 | 0 | 4050 | C+S GST 18% I/P RD | 729 | 4779 | 4779 | Approved | 0 | 2770 | 0 | 13 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Duco PU Paint | 1 | No. | 8000 | 100 | 200 | 0 | 8000 | C+S GST 18% I/P RD | 1440 | 9440 | 9440 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | French Polish | 1076.26 | Sq.Ft | 40 | 100 | 1076.26 | 0 | 43050.4 | C+S GST 18% I/P RD | 7749.08 | 50799.48 | 50799.48 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Luster Paint (m+l)- BCo | 38.71 | Sq.Ft | 22.4 | 100 | 21.68 | 0 | 867.1 | C+S GST 18% I/P RD | 156.08 | 1023.18 | 1023.18 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Premium Emulsion Paint (m+l)-BCo | 1447.51 | Sq.Ft | 20 | 100 | 723.76 | 0 | 28950.2 | C+S GST 18% I/P RD | 5211.04 | 34161.24 | 34161.24 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Matt Finish Polish | 2 | No. | 1600 | 100 | 80 | 0 | 3200 | C+S GST 18% I/P RD | 576 | 3776 | 3776 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Matt Finish Polish | 20 | No. | 400 | 100 | 200 | 0 | 8000 | C+S GST 18% I/P RD | 1440 | 9440 | 9440 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Duco Metallic PU Patta | 3294.17 | R.Ft | 55 | 100 | 4529.48 | 0 | 181179.35 | C+S GST 18% I/P RD | 32612.28 | 213791.63 | 213791.63 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Luster Paint Patta | 223.24 | R.Ft | 15 | 100 | 83.72 | 0 | 3348.6 | C+S GST 18% I/P RD | 602.74 | 3951.34 | 3951.34 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Apex Paint (M+L) - BC | 1173.3 | Sq.Ft | 18 | 100 | 527.99 | 0 | 21119.4 | C+S GST 18% I/P RD | 3801.5 | 24920.9 | 24920.9 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | French Polish Patta | 379.44 | R.Ft | 15 | 100 | 142.29 | 0 | 5691.6 | C+S GST 18% I/P RD | 1024.48 | 6716.08 | 6716.08 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | P.U. Matt | 1683.19 | R.Ft | 55 | 100 | 2314.39 | 0 | 92575.45 | C+S GST 18% I/P RD | 16663.58 | 109239.03 | 109239.03 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Oil paint BC (M+L) | 700.4 | Sq.Ft | 18 | 100 | 315.18 | 0 | 12607.2 | C+S GST 18% I/P RD | 2269.3 | 14876.5 | 14876.5 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Matt Finish Polish | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 601 | 88996 | 12 Feb 2021 |  | NISAR AHMAD ANSARI | NISAR AHMAD ANSARI | EV - 2211 | DA Development Painting & Polishing work | Oil paint BC | 42 | R.Ft | 9 | 100 | 9.45 | 0 | 378 | C+S GST 18% I/P RD | 68.04 | 446.04 | 446.04 | Approved | 0 | 0 | 3097 | 12 Feb 2021
GANGA DHAM TOWERS | 929 | 88951 | 09 Feb 2021 |  | SHIVAM LOGISTICS AND RMC SUPPLIERS | LOTUS ENTERPRISES | EV - 2194 | B Bldg 31st Slab Pumping Charges | Pumping Charges-BC | 197 | Cu.Mtrs | 190 | 100 | 0 | 0 | 37430 | C+S GST 18% I/P RD | 6737.4 | 44167.4 | 44167.4 | Approved | 0 | 0 | 561 | 09 Feb 2021
GANGA DHAM TOWERS | 149 | 88950 | 09 Feb 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 2173 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3356 | No. | 4 | 100 | 0 | 0 | 13424 | CGST 0% URD I/P | 0 | 13424 | 13424 | Approved | 0 | 0 | 0 | 09 Feb 2021
GANGA DHAM TOWERS | 272 | 88949 | 09 Feb 2021 |  | GOURI INFRA | MARVEL ENTERPRISES | EV - 2196 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 54.3579 | Sq.Ft | 142.5 | 100 | 0 | 0 | 7746 | C+S GST 18% I/P RD | 1394.28 | 9140.28 | 9140.28 | Approved | 0 | 0 | 349 | 09 Feb 2021
GANGA DHAM TOWERS | 272 | 88949 | 09 Feb 2021 |  | GOURI INFRA | MARVEL ENTERPRISES | EV - 2196 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 95.9257 | Sq.Ft | 161.5 | 100 | 0 | 0 | 15492 | C+S GST 18% I/P RD | 2788.56 | 18280.56 | 18280.56 | Approved | 0 | 0 | 349 | 09 Feb 2021
GANGA DHAM TOWERS | 272 | 88949 | 09 Feb 2021 |  | GOURI INFRA | MARVEL ENTERPRISES | EV - 2196 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 101.9211 | Sq.Ft | 152 | 100 | 0 | 0 | 15492 | C+S GST 18% I/P RD | 2788.56 | 18280.56 | 18280.56 | Approved | 0 | 0 | 349 | 09 Feb 2021
GANGA DHAM TOWERS | 272 | 88949 | 09 Feb 2021 |  | GOURI INFRA | MARVEL ENTERPRISES | EV - 2196 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 50.9605 | Sq.Ft | 152 | 100 | 0 | 0 | 7746 | C+S GST 18% I/P RD | 1394.28 | 9140.28 | 9140.28 | Approved | 0 | 0 | 349 | 09 Feb 2021
GANGA DHAM TOWERS | 493 | 88948 | 09 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2171 | D Bldg West Side External Plaster | External Plaster- BC | 1692 | Sq.Ft | 35 | 100 | 1480.5 | 0 | 59220 | C+S GST 18% I/P RD | 10659.6 | 69879.6 | 69879.6 | Approved | 0 | 0 | 444 | 09 Feb 2021
GANGA DHAM TOWERS | 933 | 88947 | 09 Feb 2021 |  | REVANTI FURNITURE | REVANTI FURNITURE | EV - 2167 | Club House Furniture Work | Carpentary work (L)-BC | 0.2 | No. | 500000 | 100 | 0 | 0 | 100000 | CGST 0% URD I/P | 0 | 100000 | 100000 | Approved | 0 | 0 | 750 | 09 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | Commercial Building Architectural Consultancy | Architectural Consultancy | 21036 | Sq.Ft | 30 | 5 | 0 | 0 | 31554 | C+S GST 18% I/P RD | 5679.72 | 37233.72 | 37233.72 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | Commercial Building Architectural Consultancy | Architectural Consultancy | 21036 | Sq.Ft | 30 | 5 | 0 | 0 | 31554 | C+S GST 18% I/P RD | 5679.72 | 37233.72 | 37233.72 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | Commercial Building Architectural Consultancy | Architectural Consultancy | 21036 | Sq.Ft | 30 | 5 | 0 | 0 | 31554 | C+S GST 18% I/P RD | 5679.72 | 37233.72 | 37233.72 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | EWS Building Architectural Consultancy | Architectural Consultancy | 36885.5556 | Sq.Ft | 18 | 5 | 0 | 0 | 33197 | C+S GST 18% I/P RD | 5975.46 | 39172.46 | 39172.46 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 25 | 0 | 0 | 165987 | C+S GST 18% I/P RD | 29877.66 | 195864.66 | 195864.66 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | EWS Building Architectural Consultancy | Architectural Consultancy | 36886 | Sq.Ft | 18 | 5 | 0 | 0 | 33197.4 | C+S GST 18% I/P RD | 5975.54 | 39172.94 | 39172.94 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 10 | 0 | 0 | 20275 | C+S GST 18% I/P RD | 3649.5 | 23924.5 | 23924.5 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 10 | 0 | 0 | 20275 | C+S GST 18% I/P RD | 3649.5 | 23924.5 | 23924.5 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 15 | 0 | 0 | 30412.5 | C+S GST 18% I/P RD | 5474.26 | 35886.76 | 35886.76 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 594 | 88939 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2253 | Club House Architectural Consultancy | Architectural Consultancy | 4055 | Sq.Ft | 50 | 5 | 0 | 0 | 10137.5 | C+S GST 18% I/P RD | 1824.76 | 11962.26 | 11962.26 | Approved | 0 | 0 | 38080 | 08 Feb 2021
GANGA DHAM TOWERS | 19 | 88938 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2252 | Parking Area Architectural Consultancy | Architectural Consultancy | 189275 | Sq.Ft | 10 | 5 | 0 | 0 | 94637.5 | C+S GST 18% I/P RD | 17034.76 | 111672.26 | 111672.26 | Approved | 0 | 0 | 51433 | 08 Feb 2021
GANGA DHAM TOWERS | 19 | 88938 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2252 | C Architectural Consultancy | Architectural Consultancy | 274382 | Sq.Ft | 25 | 5 | 0 | 0 | 342977.5 | C+S GST 18% I/P RD | 61735.96 | 404713.46 | 404713.46 | Approved | 0 | 0 | 51433 | 08 Feb 2021
GANGA DHAM TOWERS | 19 | 88938 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2252 | B Architectural Consultancy | Architectural Consultancy | 176055 | Sq.Ft | 25 | 5 | 0 | 0 | 220068.75 | C+S GST 18% I/P RD | 39612.38 | 259681.13 | 259681.13 | Approved | 0 | 0 | 51433 | 08 Feb 2021
GANGA DHAM TOWERS | 19 | 88938 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2252 | A Architectural Consultancy | Architectural Consultancy | 6418.4 | Sq.Ft | 25 | 5 | 0 | 0 | 8023 | C+S GST 18% I/P RD | 1444.14 | 9467.14 | 9467.14 | Approved | 0 | 0 | 51433 | 08 Feb 2021
GANGA DHAM TOWERS | 19 | 88938 | 08 Feb 2021 |  | METAPHORS | METAPHORS | EV - 2252 | B Architectural Consultancy | Architectural Consultancy | 16056 | Sq.Ft | 25 | 5 | 0 | 0 | 20070 | C+S GST 18% I/P RD | 3612.6 | 23682.6 | 23682.6 | Approved | 0 | 0 | 51433 | 08 Feb 2021
GANGA DHAM TOWERS | 727 | 88929 | 06 Feb 2021 | GG/GD/011 | S N RAUT CONSULTANTS | S N RAUT CONSULTANTS | EV - 2251 | Tower A, B & C HVAC consultancy | HVAC Consultancy. | 0.5556 | No. | 300000 | 30 | 0 | 0 | 50000 | C+S GST 18% I/P RD | 9000 | 59000 | 59000 | Approved | 0 | 0 | 7500 | 06 Feb 2021
GANGA DHAM TOWERS | 727 | 88929 | 06 Feb 2021 | GG/GD/011 | S N RAUT CONSULTANTS | S N RAUT CONSULTANTS | EV - 2251 | Tower A, B & C HVAC consultancy | HVAC Consultancy. | 1 | No. | 300000 | 10 | 0 | 0 | 30000 | C+S GST 18% I/P RD | 5400 | 35400 | 35400 | Approved | 0 | 0 | 7500 | 06 Feb 2021
GANGA DHAM TOWERS | 727 | 88929 | 06 Feb 2021 | GG/GD/011 | S N RAUT CONSULTANTS | S N RAUT CONSULTANTS | EV - 2251 | Club House HVAC consultancy | HVAC Consultancy. | 1 | No. | 100000 | 10 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 7500 | 06 Feb 2021
GANGA DHAM TOWERS | 727 | 88929 | 06 Feb 2021 | GG/GD/011 | S N RAUT CONSULTANTS | S N RAUT CONSULTANTS | EV - 2251 | Commercial building HVAC consultancy | HVAC Consultancy. | 1 | No. | 100000 | 10 | 0 | 0 | 10000 | C+S GST 18% I/P RD | 1800 | 11800 | 11800 | Approved | 0 | 0 | 7500 | 06 Feb 2021
GANGA DHAM TOWERS | 122 | 88927 | 06 Feb 2021 |  | ALI EXPLOSIVE AND COMPANY | SS ENTERPRISES | EV - 2120 | C Bldg Excavation Excavtion | Excavation By Bucket (Shifting Outside) | 2049.2 | Cu.Mtrs | 130 | 100 | 0 | 0 | 266396 | C+S GST 18% I/P RD | 47951.28 | 314347.28 | 314347.28 | Approved | 0 | 0 | 4580 | 06 Feb 2021
GANGA DHAM TOWERS | 122 | 88927 | 06 Feb 2021 |  | ALI EXPLOSIVE AND COMPANY | SS ENTERPRISES | EV - 2120 | C Bldg Excavation Excavtion | Excavation By Bucket (Shifting Outside) | 2648.2692 | Cu.Mtrs | 130 | 100 | 0 | 0 | 344275 | C+S GST 18% I/P RD | 61969.5 | 406244.5 | 406244.5 | Approved | 0 | 0 | 4580 | 06 Feb 2021
GANGA DHAM TOWERS | 371 | 88909 | 05 Feb 2021 |  | CONSTROGENESIS | KADAVATH VENKAT ENTERPRISES | EV - 2172 | EWS Bldg RCC 4th Slab Built-up Area (L) | Schedule & Quality | 3400 | Sq.Ft | 2.5 | 100 | 212.5 | 0 | 8500 | C+S GST 18% I/P RD | 1530 | 10030 | 10030 | Approved | 0 | 0 | 94 | 05 Feb 2021
GANGA DHAM TOWERS | 371 | 88909 | 05 Feb 2021 |  | CONSTROGENESIS | KADAVATH VENKAT ENTERPRISES | EV - 2172 | EWS Bldg RCC 5th Slab Built-up Area (L) | Schedule & Quality | 1600 | Sq.Ft | 2.5 | 100 | 100 | 0 | 4000 | C+S GST 18% I/P RD | 720 | 4720 | 4720 | Approved | 0 | 0 | 94 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 701 Blockwork 5" | Blockwork 5" - BC - | 986.46 | Sq.Ft | 13 | 100 | 320.6 | 0 | 12823.98 | C+S GST 18% I/P RD | 2308.32 | 15132.3 | 15132.3 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 705 Blockwork 8" | Blockwork 5" - BC - | 1169.49 | Sq.Ft | 13 | 100 | 380.08 | 0 | 15203.37 | C+S GST 18% I/P RD | 2736.6 | 17939.97 | 17939.97 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 702 Blockwork 5" | Blockwork 5" - BC - | 849.86 | Sq.Ft | 13 | 100 | 276.2 | 0 | 11048.18 | C+S GST 18% I/P RD | 1988.68 | 13036.86 | 13036.86 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 703 Blockwork 5" | Blockwork 5" - BC - | 644.19 | Sq.Ft | 13 | 100 | 209.36 | 0 | 8374.47 | C+S GST 18% I/P RD | 1507.4 | 9881.87 | 9881.87 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 704 Blockwork 5" | Blockwork 5" - BC - | 813.08 | Sq.Ft | 13 | 100 | 264.25 | 0 | 10570.04 | C+S GST 18% I/P RD | 1902.6 | 12472.64 | 12472.64 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 703 Blockwork 8" | Blockwork 8" - BC | 77.5 | Sq.Ft | 15 | 100 | 29.06 | 0 | 1162.5 | C+S GST 18% I/P RD | 209.26 | 1371.76 | 1371.76 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 701 Blockwork 8" | Blockwork 8" - BC | 62 | Sq.Ft | 15 | 100 | 23.25 | 0 | 930 | C+S GST 18% I/P RD | 167.4 | 1097.4 | 1097.4 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 705 Blockwork 8" | Blockwork 8" - BC | 204.09 | Sq.Ft | 15 | 100 | 76.53 | 0 | 3061.35 | C+S GST 18% I/P RD | 551.04 | 3612.39 | 3612.39 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 491 | 88908 | 05 Feb 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2170 | D Build. 704 Blockwork 8" | Blockwork 8" - BC | 206.67 | Sq.Ft | 15 | 100 | 77.5 | 0 | 3100.05 | C+S GST 18% I/P RD | 558 | 3658.05 | 3658.05 | Approved | 0 | 0 | 497 | 05 Feb 2021
GANGA DHAM TOWERS | 258 | 88864 | 30 Jan 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 2176 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.9032 | Month | 2500 | 100 | 0 | 0 | 2258 | CGST 0% URD I/P | 0 | 2258 | 2258 | Approved | 0 | 0 | 17 | 30 Jan 2021
GANGA DHAM TOWERS | 237 | 88863 | 30 Jan 2021 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 2177 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.9031 | Month | 7000 | 100 | 0 | 0 | 6322 | CGST 0% URD I/P | 0 | 6322 | 6322 | Approved | 0 | 0 | 47 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 205 Vitrified Flooring (L) | Vitrified Flooring work | 407.2435 | Sq.Ft | 13 | 100 | 132.35 | 0 | 5294.17 | C+S GST 18% I/P RD | 952.96 | 6247.13 | 6247.13 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 301 Vitrified Flooring (L) | Vitrified Flooring work | 407.2435 | Sq.Ft | 13 | 100 | 132.35 | 0 | 5294.17 | C+S GST 18% I/P RD | 952.96 | 6247.13 | 6247.13 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 305 Vitrified Flooring (L) | Vitrified Flooring work | 407.2435 | Sq.Ft | 13 | 100 | 132.35 | 0 | 5294.17 | C+S GST 18% I/P RD | 952.96 | 6247.13 | 6247.13 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 405 Vitrified Flooring (L) | Vitrified Flooring work | 407.2435 | Sq.Ft | 13 | 100 | 132.35 | 0 | 5294.17 | C+S GST 18% I/P RD | 952.96 | 6247.13 | 6247.13 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 102 Vitrified Flooring (L) | Vitrified Flooring work | 296.259 | Sq.Ft | 13 | 100 | 96.28 | 0 | 3851.37 | C+S GST 18% I/P RD | 693.24 | 4544.61 | 4544.61 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 302 Vitrified Flooring (L) | Vitrified Flooring work | 296.259 | Sq.Ft | 13 | 100 | 96.28 | 0 | 3851.37 | C+S GST 18% I/P RD | 693.24 | 4544.61 | 4544.61 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 502 Vitrified Flooring (L) | Vitrified Flooring work | 296.259 | Sq.Ft | 13 | 100 | 96.28 | 0 | 3851.37 | C+S GST 18% I/P RD | 693.24 | 4544.61 | 4544.61 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 402 Vitrified Flooring (L) | Vitrified Flooring work | 296.259 | Sq.Ft | 13 | 100 | 96.28 | 0 | 3851.37 | C+S GST 18% I/P RD | 693.24 | 4544.61 | 4544.61 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 101 Vitrified Flooring (L) | Vitrified Flooring work | 407 | Sq.Ft | 13 | 100 | 132.28 | 0 | 5291 | C+S GST 18% I/P RD | 952.38 | 6243.38 | 6243.38 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 401 Vitrified Flooring (L) | Vitrified Flooring work | 407.2435 | Sq.Ft | 13 | 100 | 132.35 | 0 | 5294.17 | C+S GST 18% I/P RD | 952.96 | 6247.13 | 6247.13 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 204 Vitrified Flooring (L) | Vitrified Flooring work | 292.961 | Sq.Ft | 13 | 100 | 95.21 | 0 | 3808.49 | C+S GST 18% I/P RD | 685.52 | 4494.01 | 4494.01 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 105 Vitrified Flooring (L) | Vitrified Flooring work | 407.2435 | Sq.Ft | 13 | 100 | 132.35 | 0 | 5294.17 | C+S GST 18% I/P RD | 952.96 | 6247.13 | 6247.13 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 201 Vitrified Flooring (L) | Vitrified Flooring work | 407.2435 | Sq.Ft | 13 | 100 | 132.35 | 0 | 5294.17 | C+S GST 18% I/P RD | 952.96 | 6247.13 | 6247.13 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 792 | 88862 | 30 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2232 | D 202 Vitrified Flooring (L) | Vitrified Flooring work | 296.259 | Sq.Ft | 13 | 100 | 96.28 | 0 | 3851.37 | C+S GST 18% I/P RD | 693.24 | 4544.61 | 4544.61 | Approved | 0 | 0 | 491 | 30 Jan 2021
GANGA DHAM TOWERS | 927 | 88861 | 30 Jan 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2394 | A 9th Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 165 | 30 Jan 2021
GANGA DHAM TOWERS | 927 | 88861 | 30 Jan 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2394 | A 12th Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 165 | 30 Jan 2021
GANGA DHAM TOWERS | 927 | 88861 | 30 Jan 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2394 | A 7th Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 165 | 30 Jan 2021
GANGA DHAM TOWERS | 927 | 88861 | 30 Jan 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2394 | A 10th Floor Back Coat Plaster | Back Coat Plaster | 2 | No. | 2000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 165 | 30 Jan 2021
GANGA DHAM TOWERS | 927 | 88861 | 30 Jan 2021 |  | VENKAT RATHOD | KADAVATH VENKAT ENTERPRISES | EV - 2394 | A 2nd Floor Back Coat Plaster | Back Coat Plaster | 3 | No. | 2000 | 100 | 150 | 0 | 6000 | CGST 0% URD I/P | 0 | 6000 | 6000 | Approved | 0 | 0 | 165 | 30 Jan 2021
GANGA DHAM TOWERS | 372 | 88860 | 30 Jan 2021 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 2229 | B Bldg 30th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2437.1082 | Sq.Ft | 175.174 | 100 | 0 | 0 | 426918 | IGST 18% I/P RD | 76845.24 | 503763.24 | 503763.24 | Approved | 0 | 0 | 15766 | 30 Jan 2021
GANGA DHAM TOWERS | 372 | 88860 | 30 Jan 2021 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 2229 | B Bldg 30th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3562.8918 | Sq.Ft | 175.174 | 100 | 0 | 0 | 624126 | IGST 18% I/P RD | 112342.68 | 736468.68 | 736468.68 | Approved | 0 | 0 | 15766 | 30 Jan 2021
GANGA DHAM TOWERS | 433 | 88821 | 27 Jan 2021 |  | SHAIKH HANIF HUSSAIN | SHAIKH HANIF HUSSAIN |  | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 18000 | 100 | 0 | 0 | 18000 | CGST 0% URD I/P | 0 | 18000 | 18000 |  | 0 | 0 | 270 | 27 Jan 2021
GANGA DHAM TOWERS | 433 | 88821 | 27 Jan 2021 |  | SHAIKH HANIF HUSSAIN | SHAIKH HANIF HUSSAIN |  | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 18000 | 100 | 0 | 0 | 18000 | CGST 0% URD I/P | 0 | 18000 | 18000 |  | 0 | 0 | 270 | 27 Jan 2021
GANGA DHAM TOWERS | 363 | 88820 | 27 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1498.68 | C+S GST 18% I/P RD | 269.76 | 1768.44 | 1768.44 |  | 0 | 0 | 15 | 27 Jan 2021
GANGA DHAM TOWERS | 363 | 88819 | 27 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.12 | C+S GST 18% I/P RD | 270.02 | 1770.14 | 1770.14 |  | 0 | 0 | 15 | 27 Jan 2021
GANGA DHAM TOWERS | 363 | 88818 | 27 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES |  | Weigh Bridge Maintenance | AMC Charges | 12 | Month | 1500 | 8.33 | 0 | 0 | 1500.12 | C+S GST 18% I/P RD | 270.02 | 1770.14 | 1770.14 |  | 0 | 0 | 15 | 27 Jan 2021
GANGA DHAM TOWERS | 933 | 88816 | 27 Jan 2021 |  | REVANTI FURNITURE | REVANTI FURNITURE | EV - 2095 | Club House Furniture Work | Carpentary work (L)-BC | 0.2 | No. | 500000 | 100 | 0 | 0 | 100000 | CGST 0% URD I/P | 0 | 100000 | 100000 | Approved | 0 | 0 | 750 | 27 Jan 2021
GANGA DHAM TOWERS | 351 | 88810 | 27 Jan 2021 |  | TECHKNOW EARTHMOVING SERVICES | PURVA ENTERPRISES | EV - 2106 | A Bldg 28th SlabTower Crane Jumping Work | Tower Crane Jumping Charges | 1 | No. | 30000 | 100 | 0 | 0 | 30000 | C+S GST 18% I/P RD | 5400 | 35400 | 35400 | Approved | 0 | 0 | 450 | 27 Jan 2021
GANGA DHAM TOWERS | 940 | 88787 | 25 Jan 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 2138 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 495 | 25 Jan 2021
GANGA DHAM TOWERS | 940 | 88787 | 25 Jan 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 2138 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 495 | 25 Jan 2021
GANGA DHAM TOWERS | 940 | 88787 | 25 Jan 2021 |  | RESHMA JALINDAR CHANDGUDE | RESHMA JALINDAR CHANDGUDE | EV - 2138 | Road Divider Garden Maintenance | Garden work - Mkt | 1 | Month | 22000 | 100 | 0 | 0 | 22000 | CGST 0% URD I/P | 0 | 22000 | 22000 | Approved | 0 | 0 | 495 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88782 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2058 | Weigh Bridge Maintenance | AMC Charges | 1 | Month | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 20 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88782 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2058 | Weigh Bridge Maintenance | AMC Charges | 0.3333 | Month | 1500 | 100 | 0 | 0 | 499.95 | C+S GST 18% I/P RD | 90 | 589.95 | 589.95 | Approved | 0 | 0 | 20 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88781 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2057 | Weigh Bridge Maintenance | AMC Charges | 1 | Month | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 206 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88781 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2057 | Weigh Bridge Maintenance | AMC Charges | 1 | Month | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 206 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88781 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2057 | Weigh Bridge Maintenance | AMC Charges | 1 | Month | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 206 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88781 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2057 | Weigh Bridge Maintenance | AMC Charges | 1 | Month | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 206 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88781 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2057 | Weigh Bridge Maintenance | AMC Charges | 1 | Month | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 206 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88781 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2057 | Weigh Bridge Maintenance | AMC Charges | 1 | Month | 1500 | 100 | 0 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 206 | 25 Jan 2021
GANGA DHAM TOWERS | 363 | 88781 | 25 Jan 2021 |  | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | ROCKWAY WEIGHBRIDGE TECHNOLOGIES | EV - 2057 | Weigh Bridge Maintenance | Stamping Charges | 1 | No. | 18500 | 100 | 0 | 0 | 18500 | C+S GST 18% I/P RD | 3330 | 21830 | 21830 | Approved | 0 | 0 | 206 | 25 Jan 2021
GANGA DHAM TOWERS | 209 | 88774 | 22 Jan 2021 |  | UNIQUE ENTERPRISES | A K INTERIOR CONTRACTOR | EV - 2015 | A Bldg 2nd RCC Slab (P1 Floor) Built-up Area (L) | Hacking Work | 1375 | Sq.Ft | 5 | 100 | 171.88 | 0 | 6875 | C+S GST 18% I/P RD | 1237.5 | 8112.5 | 8112.5 | Approved | 0 | 0 | 52 | 22 Jan 2021
GANGA DHAM TOWERS | 902 | 88773 | 22 Jan 2021 |  | AMENDS CORPORATIONS | AMENDS CORPORATIONS | EV - 2013 | B 401 Terrace PVC Panel Sample | PVC Panel (M+L) | 194 | Sq.Ft | 61.86 | 100 | 0 | 0 | 12000.84 | C+S GST 18% I/P RD | 2160.16 | 14161 | 14161 | Approved | 0 | 0 | 90 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 84.4154 | Sq.Ft | 130 | 100 | 0 | 0 | 10974 | C+S GST 18% I/P RD | 1975.32 | 12949.32 | 12949.32 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 42.2077 | Sq.Ft | 130 | 100 | 0 | 0 | 5487 | C+S GST 18% I/P RD | 987.66 | 6474.66 | 6474.66 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 94.3538 | Sq.Ft | 130 | 100 | 0 | 0 | 12266 | C+S GST 18% I/P RD | 2207.88 | 14473.88 | 14473.88 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 47.1769 | Sq.Ft | 130 | 100 | 0 | 0 | 6133 | C+S GST 18% I/P RD | 1103.94 | 7236.94 | 7236.94 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 8th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 91.45 | Sq.Ft | 120 | 100 | 0 | 0 | 10974 | C+S GST 18% I/P RD | 1975.32 | 12949.32 | 12949.32 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 8th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 45.7333 | Sq.Ft | 120 | 100 | 0 | 0 | 5488 | C+S GST 18% I/P RD | 987.84 | 6475.84 | 6475.84 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 6th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 112.9667 | Sq.Ft | 120 | 100 | 0 | 0 | 13556 | C+S GST 18% I/P RD | 2440.08 | 15996.08 | 15996.08 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 59.9429 | Sq.Ft | 140 | 100 | 0 | 0 | 8392 | C+S GST 18% I/P RD | 1510.56 | 9902.56 | 9902.56 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 29.9714 | Sq.Ft | 140 | 100 | 0 | 0 | 4196 | C+S GST 18% I/P RD | 755.28 | 4951.28 | 4951.28 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 73.16 | Sq.Ft | 150 | 100 | 0 | 0 | 10974 | C+S GST 18% I/P RD | 1975.32 | 12949.32 | 12949.32 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 36.58 | Sq.Ft | 150 | 100 | 0 | 0 | 5487 | C+S GST 18% I/P RD | 987.66 | 6474.66 | 6474.66 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 372 | 88772 | 22 Jan 2021 |  | B & B ENTERPRISES | MARVEL ENTERPRISES | EV - 2014 | B Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 73.16 | Sq.Ft | 150 | 100 | 0 | 0 | 10974 | C+S GST 18% I/P RD | 1975.32 | 12949.32 | 12949.32 | Approved | 0 | 0 | 1574 | 22 Jan 2021
GANGA DHAM TOWERS | 933 | 88770 | 22 Jan 2021 |  | REVANTI FURNITURE | REVANTI FURNITURE | EV - 2074 | Club House Furniture Work | Carpentary work (L)-BC | 0.2 | No. | 500000 | 100 | 0 | 0 | 100000 | CGST 0% URD I/P | 0 | 100000 | 100000 | Approved | 0 | 0 | 750 | 22 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 402 4th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 901 9th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1202 12th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1701 17th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1001 10th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1501 15th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 801 8th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1302 13th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1601 16th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 372.14 | Sq.Ft | 2 | 100 | 0 | 0 | 744.28 | C+S GST 18% I/P RD | 133.98 | 878.26 | 878.26 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 802 8th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1702 17th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 702 7th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1201 12th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1402 14th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1502 15th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1002 10th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1401 14th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 902 9th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1602 16th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1301 13th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 502 5th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 601 6th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 372.14 | Sq.Ft | 2 | 100 | 0 | 0 | 744.28 | C+S GST 18% I/P RD | 133.98 | 878.26 | 878.26 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 602 6th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 701 7th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 401 4th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1102 11th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 1101 11th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 372.14 | Sq.Ft | 2 | 100 | 0 | 0 | 744.28 | C+S GST 18% I/P RD | 133.98 | 878.26 | 878.26 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 912 | 88761 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2087 | B 501 5th Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 601 6th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 902 9th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1501 15th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 802 8th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 401 4th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 901 9th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1101 11th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 372.14 | Sq.Ft | 2 | 100 | 18.61 | 0 | 744.28 | C+S GST 18% I/P RD | 133.98 | 878.26 | 878.26 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 701 7th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1002 10th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 501 5th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1201 12th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 402 4th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1702 17th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1402 14th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1502 15th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1102 11th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1202 12th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 602 6th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1301 13th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 502 5th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1701 17th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 801 8th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1602 16th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1401 14th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1001 10th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1302 13th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 702 7th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 911 | 88760 | 20 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2088 | B 1601 16th Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 372.14 | Sq.Ft | 2 | 100 | 18.61 | 0 | 744.28 | C+S GST 18% I/P RD | 133.98 | 878.26 | 878.26 | Approved | 0 | 0 | 161 | 20 Jan 2021
GANGA DHAM TOWERS | 696 | 88757 | 19 Jan 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2269 | B P1 Parking Floor Column Plaster | Gypsum Plaster (L) | 1058.29 | Sq.Ft | 4 | 100 | 105.83 | 0 | 4233.16 | C+S GST 18% I/P RD | 761.96 | 4995.12 | 4995.12 | Approved | 0 | 0 | 60 | 19 Jan 2021
GANGA DHAM TOWERS | 696 | 88757 | 19 Jan 2021 |  | J K INTERIOR | A K INTERIOR CONTRACTOR | EV - 2269 | B Ground Floor Column Plaster | Gypsum Plaster (L) | 925.705 | Sq.Ft | 4 | 100 | 92.57 | 0 | 3702.82 | C+S GST 18% I/P RD | 666.5 | 4369.32 | 4369.32 | Approved | 0 | 0 | 60 | 19 Jan 2021
GANGA DHAM TOWERS | 649 | 88756 | 19 Jan 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2432 | A P1 Parking Floor Column Plaster | Tikki Dhada rate diff. (L) | 2736.265 | Sq.Ft | 5 | 100 | 342.03 | 0 | 13681.33 | C+S GST 18% I/P RD | 2462.64 | 16143.97 | 16143.97 | Approved | 0 | 0 | 287 | 19 Jan 2021
GANGA DHAM TOWERS | 649 | 88756 | 19 Jan 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2432 | A Ground Floor Column Plaster | Tikki Dhada rate diff. (L) | 2736.265 | Sq.Ft | 5 | 100 | 342.03 | 0 | 13681.33 | C+S GST 18% I/P RD | 2462.64 | 16143.97 | 16143.97 | Approved | 0 | 0 | 287 | 19 Jan 2021
GANGA DHAM TOWERS | 649 | 88756 | 19 Jan 2021 |  | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 2432 | A P1 Parking Floor Column Plaster | Gypsum Plaster (L) | 2736.265 | Sq.Ft | 4 | 100 | 273.63 | 0 | 10945.06 | C+S GST 18% I/P RD | 1970.12 | 12915.18 | 12915.18 | Approved | 0 | 0 | 287 | 19 Jan 2021
GANGA DHAM TOWERS | 948 | 88754 | 19 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2174 | A 3rd Floor Staircase Sample 1 - 1 No. | Kota Riser (L)- BCO | 50 | R.Ft | 45 | 100 | 56.25 | 0 | 2250 | C+S GST 18% I/P RD | 405 | 2655 | 2655 | Approved | 0 | 0 | 77 | 19 Jan 2021
GANGA DHAM TOWERS | 948 | 88754 | 19 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2174 | A 3rd Floor Staircase Sample 1 - 1 No. | Kota Flooring (L)- BCO | 84.91 | Sq.Ft | 50 | 100 | 106.14 | 0 | 4245.5 | C+S GST 18% I/P RD | 764.2 | 5009.7 | 5009.7 | Approved | 0 | 0 | 77 | 19 Jan 2021
GANGA DHAM TOWERS | 948 | 88754 | 19 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2174 | A 3rd Floor Staircase Sample 1 - 1 No. | Kota Skirting (L)- BCO | 18.8 | R.Ft | 30 | 100 | 14.1 | 0 | 564 | C+S GST 18% I/P RD | 101.52 | 665.52 | 665.52 | Approved | 0 | 0 | 77 | 19 Jan 2021
GANGA DHAM TOWERS | 948 | 88754 | 19 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2174 | A 3rd Floor Staircase Sample 1 - 1 No. | Kota Skirting (L)- BCO | 25.42 | R.Ft | 30 | 100 | 19.07 | 0 | 762.6 | C+S GST 18% I/P RD | 137.26 | 899.86 | 899.86 | Approved | 0 | 0 | 77 | 19 Jan 2021
GANGA DHAM TOWERS | 948 | 88754 | 19 Jan 2021 |  | PAPPU BAGELA | PAPPU BAGELA | EV - 2174 | A 3rd Floor Staircase Sample 1 - 1 No. | Kota Tread (L) - DSP | 50 | R.Ft | 50 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 77 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 112 | Sq.Ft | 15 | 100 | 42 | 0 | 1680 | C+S GST 18% I/P RD | 302.4 | 1982.4 | 1982.4 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Parents Toilet dado | Dado BC | 125 | Sq.Ft | 14 | 100 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Dry Balcony dado | Dado BC | 75 | Sq.Ft | 14 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Master Toilet dado | Dado BC | 100 | Sq.Ft | 14 | 100 | 35 | 0 | 1400 | C+S GST 18% I/P RD | 252 | 1652 | 1652 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Children Toilet | Dado BC | 150 | Sq.Ft | 14 | 100 | 52.5 | 0 | 2100 | C+S GST 18% I/P RD | 378 | 2478 | 2478 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Powder Toilet dado | Dado BC | 75 | Sq.Ft | 14 | 100 | 26.25 | 0 | 1050 | C+S GST 18% I/P RD | 189 | 1239 | 1239 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 108 | R.Ft | 45 | 100 | 121.5 | 0 | 4860 | C+S GST 18% I/P RD | 874.8 | 5734.8 | 5734.8 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Staff Toilet dado | Dado BC | 116 | Sq.Ft | 13 | 100 | 37.7 | 0 | 1508 | C+S GST 18% I/P RD | 271.44 | 1779.44 | 1779.44 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 20 | Sq.Ft | 13 | 100 | 6.5 | 0 | 260 | C+S GST 18% I/P RD | 46.8 | 306.8 | 306.8 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 21 | Sq.Ft | 13 | 100 | 6.83 | 0 | 273 | C+S GST 18% I/P RD | 49.14 | 322.14 | 322.14 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 37 | Sq.Ft | 13 | 100 | 12.03 | 0 | 481 | C+S GST 18% I/P RD | 86.58 | 567.58 | 567.58 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 46 | Sq.Ft | 13 | 100 | 14.95 | 0 | 598 | C+S GST 18% I/P RD | 107.64 | 705.64 | 705.64 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 49 | Sq.Ft | 13 | 100 | 15.93 | 0 | 637 | C+S GST 18% I/P RD | 114.66 | 751.66 | 751.66 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 34 | Sq.Ft | 13 | 100 | 11.05 | 0 | 442 | C+S GST 18% I/P RD | 79.56 | 521.56 | 521.56 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 13 | 100 | 10.4 | 0 | 416 | C+S GST 18% I/P RD | 74.88 | 490.88 | 490.88 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Tiling Below Wooden Flooring | Ceramic Flooring work | 140 | Sq.Ft | 13 | 100 | 45.5 | 0 | 1820 | C+S GST 18% I/P RD | 327.6 | 2147.6 | 2147.6 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Parents Toilet dado | Dado BC | 65 | Sq.Ft | 15 | 100 | 24.38 | 0 | 975 | C+S GST 18% I/P RD | 175.5 | 1150.5 | 1150.5 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Children Toilet | Dado BC | 35 | Sq.Ft | 15 | 100 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Powder Toilet dado | Dado BC | 35 | Sq.Ft | 15 | 100 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Master Toilet dado | Dado BC | 60 | Sq.Ft | 15 | 100 | 22.5 | 0 | 900 | C+S GST 18% I/P RD | 162 | 1062 | 1062 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 37 | R.Ft | 45 | 100 | 41.63 | 0 | 1665 | C+S GST 18% I/P RD | 299.7 | 1964.7 | 1964.7 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 537 | 88753 | 19 Jan 2021 |  | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 2072 | A 202 Master Bed Marble Flooring | Italian marble Skirting - BCo | 66 | R.Ft | 45 | 100 | 74.25 | 0 | 2970 | C+S GST 18% I/P RD | 534.6 | 3504.6 | 3504.6 | Approved | 0 | 0 | 418 | 19 Jan 2021
GANGA DHAM TOWERS | 885 | 88742 | 16 Jan 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 2121 | D Beam Core Cutting | Core Cutting Work 4" BCE | 20 | No. | 210 | 100 | 105 | 0 | 4200 | C+S GST 18% I/P RD | 756 | 4956 | 4956 | Approved | 0 | 0 | 60 | 16 Jan 2021
GANGA DHAM TOWERS | 885 | 88742 | 16 Jan 2021 |  | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 2121 | D Beam Core Cutting | Core Cutting Work 5" BCE | 18 | No. | 210 | 100 | 94.5 | 0 | 3780 | C+S GST 18% I/P RD | 680.4 | 4460.4 | 4460.4 | Approved | 0 | 0 | 60 | 16 Jan 2021
GANGA DHAM TOWERS | 493 | 88741 | 16 Jan 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2046 | D Bldg West Side External Plaster | External Plaster- BC | 402 | Sq.Ft | 35 | 100 | 351.75 | 0 | 14070 | C+S GST 18% I/P RD | 2532.6 | 16602.6 | 16602.6 | Approved | 0 | 0 | 106 | 16 Jan 2021
GANGA DHAM TOWERS | 209 | 88737 | 15 Jan 2021 |  | UNIQUE ENTERPRISES | A K INTERIOR CONTRACTOR | EV - 1964 | A Bldg 2nd RCC Slab (P1 Floor) Built-up Area (L) | Hacking Work | 2700 | Sq.Ft | 5 | 100 | 337.5 | 0 | 13500 | C+S GST 18% I/P RD | 2430 | 15930 | 15930 | Approved | 0 | 0 | 326 | 15 Jan 2021
GANGA DHAM TOWERS | 209 | 88737 | 15 Jan 2021 |  | UNIQUE ENTERPRISES | A K INTERIOR CONTRACTOR | EV - 1964 | A Bldg 2nd RCC Slab (P1 Floor) Built-up Area (L) | Hacking Work | 6000 | Sq.Ft | 5 | 100 | 750 | 0 | 30000 | C+S GST 18% I/P RD | 5400 | 35400 | 35400 | Approved | 0 | 0 | 326 | 15 Jan 2021
GANGA DHAM TOWERS | 917 | 88724 | 13 Jan 2021 |  | J K INTERIOR (MATERIAL) | J K INTERIOR (MATERIAL) | EV - 2119 | A 3rd Floor False Ceiling Sample - 1 Sq.Ft | Gypsum Board False Ceiling (M) | 612.2 | Sq.Ft | 50 | 100 | 0 | 0 | 30610 | C+S GST 18% I/P RD | 5509.8 | 36119.8 | 36119.8 | Approved | 0 | 0 | 0 | 13 Jan 2021
GANGA DHAM TOWERS | 856 | 88723 | 13 Jan 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2101 | Club House 1st Floor External Sand Face Plaster | Sand Face Plaster DCH | 1089.8 | Sq.Ft | 28 | 100 | 762.86 | 0 | 30514.4 | C+S GST 18% I/P RD | 5492.6 | 36007 | 36007 | Approved | 0 | 0 | 1055 | 13 Jan 2021
GANGA DHAM TOWERS | 856 | 88723 | 13 Jan 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2101 | External Column, Pergola Beam SF Plaster | Sand Face Plaster DCH | 3023.424 | Sq.Ft | 28 | 100 | 2116.4 | 0 | 84655.87 | C+S GST 18% I/P RD | 15238.06 | 99893.93 | 99893.93 | Approved | 0 | 0 | 1055 | 13 Jan 2021
GANGA DHAM TOWERS | 856 | 88723 | 13 Jan 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2101 | Club House 1st Floor External Sand Face Plaster | Sand Face Plaster Rate Diff. - DCH | 1473.8 | Sq.Ft | 8 | 100 | 294.76 | 0 | 11790.4 | C+S GST 18% I/P RD | 2122.28 | 13912.68 | 13912.68 | Approved | 0 | 0 | 1055 | 13 Jan 2021
GANGA DHAM TOWERS | 856 | 88723 | 13 Jan 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2101 | Club House Ground Floor External Sand Face Plaster | Sand Face Plaster Rate Diff. - DCH | 1719.84 | Sq.Ft | 8 | 100 | 343.97 | 0 | 13758.72 | C+S GST 18% I/P RD | 2476.56 | 16235.28 | 16235.28 | Approved | 0 | 0 | 1055 | 13 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 StaffToilet Dado | Dado BC | 136.45 | Sq.Ft | 21 | 100 | 71.64 | 0 | 2865.45 | C+S GST 18% I/P RD | 515.78 | 3381.23 | 3381.23 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Children Toilet 1 Dado | Dado BC | 162.77 | Sq.Ft | 22 | 100 | 89.52 | 0 | 3580.94 | C+S GST 18% I/P RD | 644.56 | 4225.5 | 4225.5 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Parents Toilet Dado | Dado BC | 181 | Sq.Ft | 22 | 100 | 99.55 | 0 | 3982 | C+S GST 18% I/P RD | 716.76 | 4698.76 | 4698.76 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Master Toilet Dado | Dado BC | 173.61 | Sq.Ft | 22 | 100 | 95.49 | 0 | 3819.42 | C+S GST 18% I/P RD | 687.5 | 4506.92 | 4506.92 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Guest Toilet Dado | Dado BC | 134.85 | Sq.Ft | 22 | 100 | 74.17 | 0 | 2966.7 | C+S GST 18% I/P RD | 534 | 3500.7 | 3500.7 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Dry Balcony Dado | Dado BC | 81.38 | Sq.Ft | 22 | 100 | 44.76 | 0 | 1790.36 | C+S GST 18% I/P RD | 322.26 | 2112.62 | 2112.62 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Powder Toilet Dado | Dado BC | 94.94 | Sq.Ft | 22 | 100 | 52.22 | 0 | 2088.68 | C+S GST 18% I/P RD | 375.96 | 2464.64 | 2464.64 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Guest Toilet Dado | Dado BC | 65.93 | Sq.Ft | 24 | 100 | 39.56 | 0 | 1582.32 | C+S GST 18% I/P RD | 284.82 | 1867.14 | 1867.14 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Parents Toilet Dado | Dado BC | 54.06 | Sq.Ft | 24 | 100 | 32.44 | 0 | 1297.44 | C+S GST 18% I/P RD | 233.54 | 1530.98 | 1530.98 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Children Toilet 1 Dado | Dado BC | 49.58 | Sq.Ft | 24 | 100 | 29.75 | 0 | 1189.92 | C+S GST 18% I/P RD | 214.18 | 1404.1 | 1404.1 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Master Toilet Dado | Dado BC | 56.7 | Sq.Ft | 24 | 100 | 34.02 | 0 | 1360.8 | C+S GST 18% I/P RD | 244.94 | 1605.74 | 1605.74 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Powder Toilet Dado | Dado BC | 38.77 | Sq.Ft | 24 | 100 | 23.26 | 0 | 930.48 | C+S GST 18% I/P RD | 167.48 | 1097.96 | 1097.96 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 55 | 100 | 906.9 | 0 | 36275.8 | C+S GST 18% I/P RD | 6529.64 | 42805.44 | 42805.44 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 55 | 100 | 370.45 | 0 | 14818.1 | C+S GST 18% I/P RD | 2667.26 | 17485.36 | 17485.36 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Parents Bed Marble Flooring - 1 No. | Italian Marble Flooring - BCo | 205.59 | Sq.Ft | 55 | 100 | 282.69 | 0 | 11307.45 | C+S GST 18% I/P RD | 2035.34 | 13342.79 | 13342.79 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 758 | 88711 | 12 Jan 2021 |  | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 2073 | B 1302 Ceramic Tiling | Ceramic Flooring work | 356.56 | Sq.Ft | 18 | 100 | 160.45 | 0 | 6418.08 | C+S GST 18% I/P RD | 1155.26 | 7573.34 | 7573.34 | Approved | 0 | 0 | 722 | 12 Jan 2021
GANGA DHAM TOWERS | 145 | 88710 | 12 Jan 2021 |  | PEST-O-CRUSH | PEST-O-CRUSH | EV - 2083 | Fogging Work | Fogging work-SO | 0.75 | Month | 6000 | 100 | 0 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 34 | 12 Jan 2021
GANGA DHAM TOWERS | 540 | 88709 | 12 Jan 2021 | 88709 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2010 | A 204 NOC | Italian Marble Flooring - BCo | 125 | Sq.Ft | 55 | 100 | 171.88 | 0 | 6875 | C+S GST 18% I/P RD | 1237.5 | 8112.5 | 8112.5 | Approved | 0 | 0 | 111 | 12 Jan 2021
GANGA DHAM TOWERS | 540 | 88709 | 12 Jan 2021 | 88709 | MONIKA ENTERPRISES | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2010 | A 204 NOC | Italian Marble Flooring - BCo | 143 | Sq.Ft | 55 | 100 | 196.63 | 0 | 7865 | C+S GST 18% I/P RD | 1415.7 | 9280.7 | 9280.7 | Approved | 0 | 0 | 111 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 703 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 85 | Sq.Ft | 20 | 100 | 42.5 | 0 | 1700 | C+S GST 18% I/P RD | 306 | 2006 | 2006 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 204 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 13 | 100 | 10.4 | 0 | 416 | C+S GST 18% I/P RD | 74.88 | 490.88 | 490.88 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 603 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 13 | 100 | 10.4 | 0 | 416 | C+S GST 18% I/P RD | 74.88 | 490.88 | 490.88 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1303 Terrace Vitrified Flooring | Vitrified Flooring -BC | 100 | Sq.Ft | 24 | 100 | 60 | 0 | 2400 | C+S GST 18% I/P RD | 432 | 2832 | 2832 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 603 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 25 | Sq.Ft | 13 | 100 | 8.13 | 0 | 325 | C+S GST 18% I/P RD | 58.5 | 383.5 | 383.5 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 204 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 25 | Sq.Ft | 13 | 100 | 8.13 | 0 | 325 | C+S GST 18% I/P RD | 58.5 | 383.5 | 383.5 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1603 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 160 | Sq.Ft | 55 | 100 | 220 | 0 | 8800 | C+S GST 18% I/P RD | 1584 | 10384 | 10384 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 503 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 160 | Sq.Ft | 45 | 100 | 180 | 0 | 7200 | C+S GST 18% I/P RD | 1296 | 8496 | 8496 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1303 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 486 | Sq.Ft | 55 | 100 | 668.25 | 0 | 26730 | C+S GST 18% I/P RD | 4811.4 | 31541.4 | 31541.4 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1303 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 160 | Sq.Ft | 55 | 100 | 220 | 0 | 8800 | C+S GST 18% I/P RD | 1584 | 10384 | 10384 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 503 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144 | Sq.Ft | 45 | 100 | 162 | 0 | 6480 | C+S GST 18% I/P RD | 1166.4 | 7646.4 | 7646.4 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1603 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 486 | Sq.Ft | 55 | 100 | 668.25 | 0 | 26730 | C+S GST 18% I/P RD | 4811.4 | 31541.4 | 31541.4 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 204 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 151 | Sq.Ft | 45 | 100 | 169.88 | 0 | 6795 | C+S GST 18% I/P RD | 1223.1 | 8018.1 | 8018.1 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1603 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144 | Sq.Ft | 55 | 100 | 198 | 0 | 7920 | C+S GST 18% I/P RD | 1425.6 | 9345.6 | 9345.6 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 204 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 210 | Sq.Ft | 45 | 100 | 236.25 | 0 | 9450 | C+S GST 18% I/P RD | 1701 | 11151 | 11151 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 204 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 587 | Sq.Ft | 45 | 100 | 660.38 | 0 | 26415 | C+S GST 18% I/P RD | 4754.7 | 31169.7 | 31169.7 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 503 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 486 | Sq.Ft | 45 | 100 | 546.75 | 0 | 21870 | C+S GST 18% I/P RD | 3936.6 | 25806.6 | 25806.6 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1303 Guest Bed Marble Flooring | Italian Marble Flooring - BCo | 144 | Sq.Ft | 55 | 100 | 198 | 0 | 7920 | C+S GST 18% I/P RD | 1425.6 | 9345.6 | 9345.6 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 204 Terrace Vitrified Flooring | Vitrified Flooring -BC | 127 | Sq.Ft | 15 | 100 | 47.63 | 0 | 1905 | C+S GST 18% I/P RD | 342.9 | 2247.9 | 2247.9 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 403 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 85 | Sq.Ft | 15 | 100 | 31.88 | 0 | 1275 | C+S GST 18% I/P RD | 229.5 | 1504.5 | 1504.5 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 503 Terrace Vitrified Flooring | Vitrified Flooring -BC | 100 | Sq.Ft | 15 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 204 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 121 | Sq.Ft | 15 | 100 | 45.38 | 0 | 1815 | C+S GST 18% I/P RD | 326.7 | 2141.7 | 2141.7 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1204 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 100 | R.Ft | 50 | 100 | 125 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A-1203 Guest Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 33 | R.Ft | 50 | 100 | 41.25 | 0 | 1650 | C+S GST 18% I/P RD | 297 | 1947 | 1947 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 704 Master Bed Marble Flooring | Italian marble Skirting - BCo | 50 | R.Ft | 50 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A-1203 Living,Dining,Passa. Marble Flooring - 1 No. | Italian marble Skirting - BCo | 90 | R.Ft | 50 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 704 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 100 | R.Ft | 50 | 100 | 125 | 0 | 5000 | C+S GST 18% I/P RD | 900 | 5900 | 5900 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A-1203 Master Bed Marble Flooring - 1 No. | Italian marble Skirting - BCo | 40 | R.Ft | 50 | 100 | 50 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1204 Master Bed Marble Flooring | Italian marble Skirting - BCo | 50 | R.Ft | 50 | 100 | 62.5 | 0 | 2500 | C+S GST 18% I/P RD | 450 | 2950 | 2950 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1204 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 38 | R.Ft | 50 | 100 | 47.5 | 0 | 1900 | C+S GST 18% I/P RD | 342 | 2242 | 2242 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 704 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 38 | R.Ft | 50 | 100 | 47.5 | 0 | 1900 | C+S GST 18% I/P RD | 342 | 2242 | 2242 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1603 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 33 | R.Ft | 55 | 100 | 45.38 | 0 | 1815 | C+S GST 18% I/P RD | 326.7 | 2141.7 | 2141.7 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1603 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 96 | R.Ft | 55 | 100 | 132 | 0 | 5280 | C+S GST 18% I/P RD | 950.4 | 6230.4 | 6230.4 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1303 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 96 | R.Ft | 55 | 100 | 132 | 0 | 5280 | C+S GST 18% I/P RD | 950.4 | 6230.4 | 6230.4 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1303 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 33 | R.Ft | 55 | 100 | 45.38 | 0 | 1815 | C+S GST 18% I/P RD | 326.7 | 2141.7 | 2141.7 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1603 Master Bed Marble Flooring | Italian marble Skirting - BCo | 40 | R.Ft | 55 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 1303 Master Bed Marble Flooring | Italian marble Skirting - BCo | 40 | R.Ft | 55 | 100 | 55 | 0 | 2200 | C+S GST 18% I/P RD | 396 | 2596 | 2596 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 903 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 25 | Sq.Ft | 17 | 100 | 10.63 | 0 | 425 | C+S GST 18% I/P RD | 76.5 | 501.5 | 501.5 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 903 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 32 | Sq.Ft | 17 | 100 | 13.6 | 0 | 544 | C+S GST 18% I/P RD | 97.92 | 641.92 | 641.92 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 503 Master Bed Marble Flooring | Italian marble Skirting - BCo | 40 | R.Ft | 45 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 503 Guest Bed Marble Flooring | Italian marble Skirting - BCo | 33 | R.Ft | 45 | 100 | 37.13 | 0 | 1485 | C+S GST 18% I/P RD | 267.3 | 1752.3 | 1752.3 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 551 | 88708 | 12 Jan 2021 |  | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | D D SHARMA CONTRACTOR (PROP. MUKESH KUMAR SHARMA) | EV - 2071 | A 503 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 96 | R.Ft | 45 | 100 | 108 | 0 | 4320 | C+S GST 18% I/P RD | 777.6 | 5097.6 | 5097.6 | Approved | 0 | 0 | 1735 | 12 Jan 2021
GANGA DHAM TOWERS | 493 | 88702 | 11 Jan 2021 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2047 | D Bldg West Side External Plaster | External Plaster- BC | 1290 | Sq.Ft | 35 | 100 | 1128.75 | 0 | 45150 | C+S GST 18% I/P RD | 8127 | 53277 | 53277 | Approved | 0 | 0 | 339 | 11 Jan 2021
GANGA DHAM TOWERS | 920 | 88696 | 09 Jan 2021 |  | POONA NEON | POONA NEON | EV - 1929 | MEDIA Branding | LED STRIP LIGHT PANEL | 1 | No. | 36000 | 100 | 0 | 0 | 36000 | C+S GST 18% I/P RD | 6480 | 42480 | 42480 | Approved | 0 | 0 | 806 | 09 Jan 2021
GANGA DHAM TOWERS | 920 | 88696 | 09 Jan 2021 |  | POONA NEON | POONA NEON | EV - 1929 | MEDIA Branding | LED STRIP LIGHT PANEL | 1 | No. | 7210 | 100 | 0 | 0 | 7210 | C+S GST 18% I/P RD | 1297.8 | 8507.8 | 8507.8 | Approved | 0 | 0 | 806 | 09 Jan 2021
GANGA DHAM TOWERS | 920 | 88696 | 09 Jan 2021 |  | POONA NEON | POONA NEON | EV - 1929 | MEDIA Branding | ALUMINIUM COMPOSITE ACP SHEET PANEL | 292 | Sq.Ft | 220 | 17.13 | 0 | 0 | 11004.31 | C+S GST 18% I/P RD | 1980.78 | 12985.09 | 12985.09 | Approved | 0 | 0 | 806 | 09 Jan 2021
GANGA DHAM TOWERS | 920 | 88696 | 09 Jan 2021 |  | POONA NEON | POONA NEON | EV - 1929 | MEDIA Branding | ALUMINIUM COMPOSITE ACP SHEET PANEL | 292 | Sq.Ft | 220 | 17.13 | 0 | 0 | 11004.31 | C+S GST 18% I/P RD | 1980.78 | 12985.09 | 12985.09 | Approved | 0 | 0 | 806 | 09 Jan 2021
GANGA DHAM TOWERS | 920 | 88696 | 09 Jan 2021 |  | POONA NEON | POONA NEON | EV - 1929 | MEDIA Branding | ALUMINIUM COMPOSITE ACP SHEET PANEL | 292 | Sq.Ft | 220 | 31.5 | 0 | 0 | 20235.6 | C+S GST 18% I/P RD | 3642.4 | 23878 | 23878 | Approved | 0 | 0 | 806 | 09 Jan 2021
GANGA DHAM TOWERS | 920 | 88696 | 09 Jan 2021 |  | POONA NEON | POONA NEON | EV - 1929 | MEDIA Branding | ALUMINIUM COMPOSITE ACP SHEET PANEL | 292 | Sq.Ft | 220 | 34.24 | 0 | 0 | 21995.78 | C+S GST 18% I/P RD | 3959.24 | 25955.02 | 25955.02 | Approved | 0 | 0 | 806 | 09 Jan 2021
GANGA DHAM TOWERS | 912 | 88685 | 09 Jan 2021 | 912 | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2011 | B 102 1st Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 912 | 88685 | 09 Jan 2021 | 912 | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2011 | B 201 2nd Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 912 | 88685 | 09 Jan 2021 | 912 | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2011 | B 202 2nd Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 912 | 88685 | 09 Jan 2021 | 912 | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2011 | B 301 3rd Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 912 | 88685 | 09 Jan 2021 | 912 | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2011 | B 302 3rd Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 347 | Sq.Ft | 2 | 100 | 0 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 912 | 88685 | 09 Jan 2021 | 912 | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2011 | B 101 1st Floor Toilet Ceiling & Walls | Cement Paint (M)- BC | 429.5 | Sq.Ft | 2 | 100 | 0 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 911 | 88684 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2021 | B 301 3rd Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 35 | 09 Jan 2021
GANGA DHAM TOWERS | 911 | 88684 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2021 | B 101 1st Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 35 | 09 Jan 2021
GANGA DHAM TOWERS | 911 | 88684 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2021 | B 102 1st Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 35 | 09 Jan 2021
GANGA DHAM TOWERS | 911 | 88684 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2021 | B 201 2nd Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 429.5 | Sq.Ft | 2 | 100 | 21.48 | 0 | 859 | C+S GST 18% I/P RD | 154.62 | 1013.62 | 1013.62 | Approved | 0 | 0 | 35 | 09 Jan 2021
GANGA DHAM TOWERS | 911 | 88684 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2021 | B 202 2nd Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 35 | 09 Jan 2021
GANGA DHAM TOWERS | 911 | 88684 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2021 | B 302 3rd Floor Toilet Ceiling & Walls | Cement Paint (L)- BC | 347 | Sq.Ft | 2 | 100 | 17.35 | 0 | 694 | C+S GST 18% I/P RD | 124.92 | 818.92 | 818.92 | Approved | 0 | 0 | 35 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1302 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1203 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 458 | Sq.Ft | 2 | 50 | 0 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1603 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 458 | Sq.Ft | 2 | 50 | 0 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1604 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1102 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1301 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1702 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1703 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 458 | Sq.Ft | 2 | 50 | 0 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1202 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1403 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 458 | Sq.Ft | 2 | 50 | 0 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1303 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 458 | Sq.Ft | 2 | 50 | 0 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1602 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1104 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1503 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 458 | Sq.Ft | 2 | 50 | 0 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1304 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1401 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1402 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1101 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1204 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1501 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1701 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1201 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1504 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1601 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1502 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1704 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 840 | 88683 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2024 | A 1103 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 458 | Sq.Ft | 2 | 50 | 0 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 0 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1604 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1701 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1502 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1503 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 458 | Sq.Ft | 2 | 50 | 11.45 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1102 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1504 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1402 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1403 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 458 | Sq.Ft | 2 | 50 | 11.45 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1302 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1103 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 458 | Sq.Ft | 2 | 50 | 11.45 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1602 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1704 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1203 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 458 | Sq.Ft | 2 | 50 | 11.45 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1404 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1304 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1501 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1601 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1204 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1301 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1603 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 458 | Sq.Ft | 2 | 50 | 11.45 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1104 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1401 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1703 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 458 | Sq.Ft | 2 | 50 | 11.45 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1202 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1201 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1702 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1101 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 839 | 88682 | 09 Jan 2021 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 2018 | A 1303 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 458 | Sq.Ft | 2 | 50 | 11.45 | 0 | 458 | C+S GST 18% I/P RD | 82.44 | 540.44 | 540.44 | Approved | 0 | 0 | 119 | 09 Jan 2021
GANGA DHAM TOWERS | 933 | 88676 | 08 Jan 2021 |  | REVANTI FURNITURE | REVANTI FURNITURE | EV - 2017 | Club House Furniture Work | Carpentary work (L)-BC | 0.2 | No. | 500000 | 100 | 0 | 0 | 100000 | CGST 0% URD I/P | 0 | 100000 | 100000 | Approved | 0 | 0 | 750 | 08 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Exhaust Fan Point | 1 | No. | 225 | 35 | 1.97 | 0 | 78.75 | C+S GST 18% I/P RD | 14.18 | 92.93 | 92.93 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 23 | No. | 250 | 35 | 50.31 | 0 | 2012.5 | C+S GST 18% I/P RD | 362.26 | 2374.76 | 2374.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 35 | 32.81 | 0 | 1312.5 | C+S GST 18% I/P RD | 236.26 | 1548.76 | 1548.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 21 | No. | 250 | 35 | 45.94 | 0 | 1837.5 | C+S GST 18% I/P RD | 330.76 | 2168.26 | 2168.26 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 39 | No. | 250 | 35 | 85.31 | 0 | 3412.5 | C+S GST 18% I/P RD | 614.26 | 4026.76 | 4026.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 40 | No. | 250 | 35 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | AC Point BC | 1 | No. | 450 | 35 | 3.94 | 0 | 157.5 | C+S GST 18% I/P RD | 28.36 | 185.86 | 185.86 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 9 | No. | 450 | 35 | 35.44 | 0 | 1417.5 | C+S GST 18% I/P RD | 255.16 | 1672.66 | 1672.66 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 1 | No. | 450 | 35 | 3.94 | 0 | 157.5 | C+S GST 18% I/P RD | 28.36 | 185.86 | 185.86 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Data Point | 2 | No. | 350 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Fan Point | 2 | No. | 250 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Fan Point | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Fan Point | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Fan Point | 1 | No. | 250 | 35 | 2.19 | 0 | 87.5 | C+S GST 18% I/P RD | 15.76 | 103.26 | 103.26 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Fan Point | 7 | No. | 250 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | 6 AMP Plug point (Independent) | 20 | No. | 250 | 35 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 35 | 37.19 | 0 | 1487.5 | C+S GST 18% I/P RD | 267.76 | 1755.26 | 1755.26 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | 6 AMP Plug point (Independent) | 30 | No. | 250 | 35 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Secondary Light Points (Looping) | 39 | No. | 100 | 35 | 34.13 | 0 | 1365 | C+S GST 18% I/P RD | 245.7 | 1610.7 | 1610.7 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Secondary Light Points (Looping) | 38 | No. | 100 | 35 | 33.25 | 0 | 1330 | C+S GST 18% I/P RD | 239.4 | 1569.4 | 1569.4 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Secondary Light Points (Looping) | 44 | No. | 100 | 35 | 38.5 | 0 | 1540 | C+S GST 18% I/P RD | 277.2 | 1817.2 | 1817.2 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Secondary Light Points (Looping) | 42 | No. | 100 | 35 | 36.75 | 0 | 1470 | C+S GST 18% I/P RD | 264.6 | 1734.6 | 1734.6 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Telephone Point | 1 | No. | 350 | 35 | 3.06 | 0 | 122.5 | C+S GST 18% I/P RD | 22.06 | 144.56 | 144.56 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2402 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2401 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2404 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 359 | 88654 | 06 Jan 2021 |  | A.D. ASSOCIATES ELECTRICALS PVT LTD | A.D. ASSOCIATES ELECTRICALS PVT LTD | EV - 2197 | A Bldg Flat No.-2403 Internal Electrical Work | TV Point | 1 | No. | 350 | 35 | 3.06 | 0 | 122.5 | C+S GST 18% I/P RD | 22.06 | 144.56 | 144.56 | Approved | 0 | 0 | 1212 | 06 Jan 2021
GANGA DHAM TOWERS | 272 | 88653 | 06 Jan 2021 | 16 | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1978 | A Bldg 30th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3582.1401 | Sq.Ft | 181.3 | 100 | 0 | 0 | 649442 | C+S GST 18% I/P RD | 116899.56 | 766341.56 | 766341.56 | Approved | 0 | 0 | 17231 | 06 Jan 2021
GANGA DHAM TOWERS | 272 | 88653 | 06 Jan 2021 | 16 | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1978 | A Bldg 30th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2753.861 | Sq.Ft | 181.3 | 100 | 0 | 0 | 499275 | C+S GST 18% I/P RD | 89869.5 | 589144.5 | 589144.5 | Approved | 0 | 0 | 17231 | 06 Jan 2021
GANGA DHAM TOWERS | 887 | 88629 | 05 Jan 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 2032 | Club House Planter Chemical+ IPS | Chemical W/P (L+M) | 5.49 | Sq.Ft | 19 | 100 | 10.43 | 0 | 104.31 | CGST 0% URD I/P | 0 | 104.31 | 104.31 | Approved | 0 | 0 | 252 | 05 Jan 2021
GANGA DHAM TOWERS | 887 | 88629 | 05 Jan 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 2032 | Club House Toilet & Planter Chemical + IPS Waterproofing - | Chemical W/P (L+M) | 164.97 | Sq.Ft | 19 | 100 | 313.44 | 0 | 3134.43 | CGST 0% URD I/P | 0 | 3134.43 | 3134.43 | Approved | 0 | 0 | 252 | 05 Jan 2021
GANGA DHAM TOWERS | 887 | 88629 | 05 Jan 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 2032 | Club House Toilet & Planter Chemical + IPS Waterproofing - | IPS W/P | 164.97 | Sq.Ft | 12 | 100 | 197.96 | 0 | 1979.64 | CGST 0% URD I/P | 0 | 1979.64 | 1979.64 | Approved | 0 | 0 | 252 | 05 Jan 2021
GANGA DHAM TOWERS | 887 | 88629 | 05 Jan 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 2032 | Club House Planter Chemical+ IPS | IPS W/P | 5.49 | Sq.Ft | 12 | 100 | 6.59 | 0 | 65.88 | CGST 0% URD I/P | 0 | 65.88 | 65.88 | Approved | 0 | 0 | 252 | 05 Jan 2021
GANGA DHAM TOWERS | 887 | 88629 | 05 Jan 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 2032 | Terrace Brickbat Waterproofing | Brickbat W/P | 1651.95 | Sq.Ft | 15 | 100 | 2477.93 | 0 | 24779.25 | CGST 0% URD I/P | 0 | 24779.25 | 24779.25 | Approved | 0 | 0 | 252 | 05 Jan 2021
GANGA DHAM TOWERS | 887 | 88629 | 05 Jan 2021 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 2032 | Club House Toilet Brick batt | Brickbat W/P | 231.43 | Sq.Ft | 15 | 100 | 347.15 | 0 | 3471.45 | CGST 0% URD I/P | 0 | 3471.45 | 3471.45 | Approved | 0 | 0 | 252 | 05 Jan 2021
GANGA DHAM TOWERS | 873 | 88621 | 04 Jan 2021 |  | PATHAN HAROON | PATHAN HAROON | EV - 1922 | 3rd Floor Sample For 304 - 1 No. | Making Wooden Beam for AC fixing (L) | 1 | No. | 5000 | 100 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 0 | 04 Jan 2021
GANGA DHAM TOWERS | 149 | 88620 | 04 Jan 2021 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1940 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 3366 | No. | 4 | 100 | 0 | 0 | 13464 | CGST 0% URD I/P | 0 | 13464 | 13464 | Approved | 0 | 0 | 0 | 04 Jan 2021
GANGA DHAM TOWERS | 916 | 88619 | 04 Jan 2021 |  | J K INTERIOR | J K INTERIOR | EV - 2090 | A 3rd Floor False Ceiling Sample - 1 Sq.Ft | Gypsum Board False Ceiling (L) | 612.2 | Sq.Ft | 15 | 100 | 229.58 | 0 | 9183 | C+S GST 18% I/P RD | 1652.94 | 10835.94 | 10835.94 | Approved | 0 | 0 | 69 | 04 Jan 2021
GANGA DHAM TOWERS | 350 | 88618 | 04 Jan 2021 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 1923 | Site Expenses | Site Expenses -SO | 0.2567 | Month | 3000 | 100 | 0 | 0 | 770 | CGST 0% URD I/P | 0 | 770 | 770 | Approved | 0 | 0 | 0 | 04 Jan 2021
GANGA DHAM TOWERS | 187 | 88617 | 04 Jan 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2048 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 04 Jan 2021
GANGA DHAM TOWERS | 747 | 88616 | 04 Jan 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2051 | Sales Office-Waterbody Maintenance | Maintainance Material | 0.95 | Month | 1000 | 100 | 0 | 0 | 950 | C+S GST 18% I/P RD | 171 | 1121 | 1121 | Approved | 0 | 0 | 0 | 04 Jan 2021
GANGA DHAM TOWERS | 186 | 88615 | 04 Jan 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2191 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 31 | Day | 580.645 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 645 | 04 Jan 2021
GANGA DHAM TOWERS | 186 | 88615 | 04 Jan 2021 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2191 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 150.4983 | Day | 451.613 | 100 | 0 | 0 | 67967 | C+S GST 18% I/P RD | 12234.06 | 80201.06 | 80201.06 | Approved | 0 | 0 | 645 | 04 Jan 2021
GANGA DHAM TOWERS | 413 | 88614 | 04 Jan 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 1925 | Sales Oiifce Landscape Area . | Supervision Charges | 0.5 | Month | 4000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 150 | 04 Jan 2021
GANGA DHAM TOWERS | 179 | 88613 | 04 Jan 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2109 | Road Divider Work | Garden work - Mkt | 0.9516 | Month | 12120 | 100 | 0 | 0 | 11533 | C+S GST 18% I/P RD | 2075.94 | 13608.94 | 13608.94 | Approved | 0 | 0 | 86 | 04 Jan 2021
GANGA DHAM TOWERS | 178 | 88612 | 04 Jan 2021 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2108 | Sales Oiifce Landscape Area . | Garden work - Mkt | 0.5968 | Month | 36360 | 100 | 0 | 0 | 21698 | C+S GST 18% I/P RD | 3905.64 | 25603.64 | 25603.64 | Approved | 0 | 0 | 163 | 04 Jan 2021
GANGA DHAM TOWERS | 461 | 88611 | 04 Jan 2021 |  | PRAKASH CONTRACTOR | PRAKASH CONTRACTOR | EV - 2089 | DA Development Demolition/ Departmental work | Departmental Labour | 5 | No. | 400 | 100 | 50 | 0 | 2000 | CGST 0% URD I/P | 0 | 2000 | 2000 | Approved | 0 | 0 | 15 | 04 Jan 2021
GANGA DHAM TOWERS | 878 | 88610 | 04 Jan 2021 |  | SAI NIRMAL COLOURS & TEXTURES | SAI NIRMAL COLOURS & TEXTURES | EV - 2053 | DA Development Painting & Polishing work | Texture Paint (m+l) | 189.46 | Sq.Ft | 40 | 100 | 0 | 0 | 7578.4 | C+S GST 18% I/P RD | 1364.12 | 8942.52 | 8942.52 | Approved | 0 | 0 | 57 | 04 Jan 2021
GANGA DHAM TOWERS | 938 | 88609 | 04 Jan 2021 |  | SMITA ARTS | SMITA ARTS | EV - 2099 | DA Development Carpentary work | Name Board fixing-BC | 1 | No. | 850 | 100 | 0 | 0 | 850 | C+S GST 18% I/P RD | 153 | 1003 | 1003 | Approved | 0 | 0 | 6 | 04 Jan 2021
GANGA DHAM TOWERS | 871 | 88597 | 02 Jan 2021 |  | SANDIP VAMANRAO RUPNAWAR | DILIP KAMATI | EV - 1989 | Tower A Staff Incentive & Certificates | Incentive- | 0.063 | No. | 139500 | 12.5 | 0 | 0 | 1099 | CGST 0% URD I/P | 0 | 1099 | 1099 | Approved | 0 | 0 | 0 | 02 Jan 2021
GANGA DHAM TOWERS | 871 | 88596 | 02 Jan 2021 |  | SANDIP VAMANRAO RUPNAWAR | SUNIL KUMAR DUBEY | EV - 1996 | Tower A Staff Incentive & Certificates | Incentive- | 0.063 | No. | 139500 | 12.5 | 0 | 0 | 1099 | CGST 0% URD I/P | 0 | 1099 | 1099 | Approved | 0 | 0 | 0 | 02 Jan 2021
GANGA DHAM TOWERS | 389 | 88595 | 02 Jan 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1909 | Loading / Unloading Expenses | Unloading work-SO | 3 | No. | 1000 | 100 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 0 | 02 Jan 2021
GANGA DHAM TOWERS | 389 | 88595 | 02 Jan 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1909 | Loading / Unloading Expenses | Unloading of AAC Blocks | 900 | No. | 2 | 100 | 0 | 0 | 1800 | CGST 0% URD I/P | 0 | 1800 | 1800 | Approved | 0 | 0 | 0 | 02 Jan 2021
GANGA DHAM TOWERS | 389 | 88595 | 02 Jan 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1909 | Loading / Unloading Expenses | Unloading of tiles. | 8.5 | Metric Tonnes | 160 | 100 | 0 | 0 | 1360 | CGST 0% URD I/P | 0 | 1360 | 1360 | Approved | 0 | 0 | 0 | 02 Jan 2021
GANGA DHAM TOWERS | 389 | 88595 | 02 Jan 2021 |  | SAGARSINGH BINDUSINGH TAK | SAGARSINGH BINDUSINGH TAK | EV - 1909 | Loading / Unloading Expenses | Unloading of GYpsum- | 27.2 | Metric Tonnes | 200 | 100 | 0 | 0 | 5440 | CGST 0% URD I/P | 0 | 5440 | 5440 | Approved | 0 | 0 | 0 | 02 Jan 2021
GANGA DHAM TOWERS | 272 | 88574 | 01 Jan 2021 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1908 | A Bldg 28th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2722 | Sq.Ft | 171 | 100 | 0 | 0 | 465462 | C+S GST 18% I/P RD | 83783.16 | 549245.16 | 549245.16 | Approved | 0 | 0 | 16252 | 01 Jan 2021
GANGA DHAM TOWERS | 272 | 88574 | 01 Jan 2021 |  | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1908 | A Bldg 28th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3614 | Sq.Ft | 171 | 100 | 0 | 0 | 617994 | C+S GST 18% I/P RD | 111238.92 | 729232.92 | 729232.92 | Approved | 0 | 0 | 16252 | 01 Jan 2021
GANGA DHAM TOWERS | 871 | 88563 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | DATTA LAXMAN NIKSHE | EV - 1986 | Tower A Staff Incentive & Certificates | Incentive- | 0.2925 | No. | 139500 | 12.5 | 0 | 0 | 5100 | CGST 0% URD I/P | 0 | 5100 | 5100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88562 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | RUSHIKESH ROHIDAS HADKE | EV - 1988 | Tower A Staff Incentive & Certificates | Incentive- | 0.1139 | No. | 139500 | 12.5 | 0 | 0 | 1986 | CGST 0% URD I/P | 0 | 1986 | 1986 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88562 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | RUSHIKESH ROHIDAS HADKE | EV - 1988 | Tower A Staff Incentive & Certificates | Incentive- | 0.0639 | No. | 139500 | 12.5 | 0 | 0 | 1114 | CGST 0% URD I/P | 0 | 1114 | 1114 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88561 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | DUCON CONTACTORS PRIVATE LIMITED | EV - 1980 | Tower A Staff Incentive & Certificates | Incentive- | 0.2688 | No. | 139500 | 12.5 | 0 | 0 | 4687 | CGST 0% URD I/P | 0 | 4687 | 4687 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88561 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | DUCON CONTACTORS PRIVATE LIMITED | EV - 1980 | Tower A Staff Incentive & Certificates | Incentive- | 0.9247 | No. | 139500 | 12.5 | 0 | 0 | 16125 | CGST 0% URD I/P | 0 | 16125 | 16125 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88561 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | DUCON CONTACTORS PRIVATE LIMITED | EV - 1980 | Tower A Staff Incentive & Certificates | Incentive- | 1 | No. | 139500 | 12.5 | 0 | 0 | 17437.5 | CGST 0% URD I/P | 0 | 17437.5 | 17437.5 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88560 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | B & B ENTERPRISES | EV - 1979 | Tower A Staff Incentive & Certificates | Incentive- | 0.7312 | No. | 139500 | 12.5 | 0 | 0 | 12750 | CGST 0% URD I/P | 0 | 12750 | 12750 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88559 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SURESH GOWALKAR | EV - 1982 | Tower A Staff Incentive & Certificates | Incentive- | 0.2867 | No. | 139500 | 12.5 | 0 | 0 | 5000 | CGST 0% URD I/P | 0 | 5000 | 5000 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88558 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1981 | Tower A Staff Incentive & Certificates | Incentive- | 1 | No. | 139500 | 12.5 | 0 | 0 | 17437.5 | CGST 0% URD I/P | 0 | 17437.5 | 17437.5 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88558 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1981 | Tower A Staff Incentive & Certificates | Incentive- | 0.0752 | No. | 139500 | 12.5 | 0 | 0 | 1312 | CGST 0% URD I/P | 0 | 1312 | 1312 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88558 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1981 | Tower A Staff Incentive & Certificates | Incentive- | 0.1291 | No. | 139500 | 12.5 | 0 | 0 | 2251 | CGST 0% URD I/P | 0 | 2251 | 2251 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88557 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SAVITA SUJIT TAKALE | EV - 1987 | Tower A Staff Incentive & Certificates | Incentive- | 0.1778 | No. | 139500 | 12.5 | 0 | 0 | 3100 | CGST 0% URD I/P | 0 | 3100 | 3100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88556 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | PATHAN NURKHA NASHIBKHA | EV - 2000 | Tower A Staff Incentive & Certificates | Incentive- | 0.0631 | No. | 139500 | 12.5 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88555 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | ABHISHEK SHYAMSUNDAR RAWAT | EV - 1999 | Tower A Staff Incentive & Certificates | Incentive- | 0.0631 | No. | 139500 | 12.5 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88554 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | MAHADEV RAMESH KHAMKAR | EV - 1998 | Tower A Staff Incentive & Certificates | Incentive- | 0.0631 | No. | 139500 | 12.5 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88553 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | BANDU DEVARAO GADALE | EV - 1997 | Tower A Staff Incentive & Certificates | Incentive- | 0.0631 | No. | 139500 | 12.5 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88552 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SAMU KALURAM DUBEY | EV - 1995 | Tower A Staff Incentive & Certificates | Incentive- | 0.0631 | No. | 139500 | 12.5 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88551 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | DATTAKUMAR BABURAO AUNDHKAR | EV - 1994 | Tower A Staff Incentive & Certificates | Incentive- | 0.0631 | No. | 139500 | 12.5 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88550 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP LAXMAN MORE | EV - 1993 | Tower A Staff Incentive & Certificates | Incentive- | 0.1778 | No. | 139500 | 12.5 | 0 | 0 | 3100 | CGST 0% URD I/P | 0 | 3100 | 3100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88550 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP LAXMAN MORE | EV - 1993 | Tower A Staff Incentive & Certificates | Incentive- | 0.172 | No. | 139500 | 12.5 | 0 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88549 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | AJIT KUMAR OJHA | EV - 1992 | Tower A Staff Incentive & Certificates | Incentive- | 0.0631 | No. | 139500 | 12.5 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88548 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | NABI AHAMAD SHAIKH | EV - 1991 | Tower A Staff Incentive & Certificates | Incentive- | 0.0631 | No. | 139500 | 12.5 | 0 | 0 | 1100 | CGST 0% URD I/P | 0 | 1100 | 1100 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88547 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SAGAR KATTIMANI | EV - 1990 | Tower A Staff Incentive & Certificates | Incentive- | 0.0436 | No. | 139500 | 12.5 | 0 | 0 | 760 | CGST 0% URD I/P | 0 | 760 | 760 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88547 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SAGAR KATTIMANI | EV - 1990 | Tower A Staff Incentive & Certificates | Incentive- | 0.0194 | No. | 139500 | 12.5 | 0 | 0 | 338 | CGST 0% URD I/P | 0 | 338 | 338 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88546 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | VIRAJ TATYASO MACHALE | EV - 1985 | Tower A Staff Incentive & Certificates | Incentive- | 0.6308 | No. | 139500 | 12.5 | 0 | 0 | 11000 | CGST 0% URD I/P | 0 | 11000 | 11000 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88545 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 1984 | Tower A Staff Incentive & Certificates | Incentive- | 0.3255 | No. | 139500 | 12.5 | 0 | 0 | 5676 | CGST 0% URD I/P | 0 | 5676 | 5676 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88545 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI | EV - 1984 | Tower A Staff Incentive & Certificates | Incentive- | 0.3053 | No. | 139500 | 12.5 | 0 | 0 | 5323 | CGST 0% URD I/P | 0 | 5323 | 5323 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 871 | 88544 | 31 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP VAMANRAO RUPNAWAR | EV - 1983 | Tower A Staff Incentive & Certificates | Incentive- | 0.6308 | No. | 139500 | 12.5 | 0 | 0 | 11000 | CGST 0% URD I/P | 0 | 11000 | 11000 | Approved | 0 | 0 | 0 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14.0658 | Sq.Ft | 152 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 20th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14.0658 | Sq.Ft | 152 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14.0658 | Sq.Ft | 152 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 19th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14.0658 | Sq.Ft | 152 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14.0658 | Sq.Ft | 152 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 18th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 14.0658 | Sq.Ft | 152 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 20.1513 | Sq.Ft | 152 | 100 | 0 | 0 | 3063 | C+S GST 18% I/P RD | 551.34 | 3614.34 | 3614.34 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 21st Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 7.9803 | Sq.Ft | 152 | 100 | 0 | 0 | 1213 | C+S GST 18% I/P RD | 218.34 | 1431.34 | 1431.34 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 7.5108 | Sq.Ft | 161.5 | 100 | 0 | 0 | 1213 | C+S GST 18% I/P RD | 218.34 | 1431.34 | 1431.34 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 13th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.1579 | Sq.Ft | 133 | 100 | 0 | 0 | 4277 | C+S GST 18% I/P RD | 769.86 | 5046.86 | 5046.86 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 12th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.1579 | Sq.Ft | 133 | 100 | 0 | 0 | 4277 | C+S GST 18% I/P RD | 769.86 | 5046.86 | 5046.86 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 10th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 160.7895 | Sq.Ft | 133 | 100 | 0 | 0 | 21385 | C+S GST 18% I/P RD | 3849.3 | 25234.3 | 25234.3 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 11th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 32.1579 | Sq.Ft | 133 | 100 | 0 | 0 | 4277 | C+S GST 18% I/P RD | 769.86 | 5046.86 | 5046.86 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 15th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 16th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 17th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 14th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 15.0035 | Sq.Ft | 142.5 | 100 | 0 | 0 | 2138 | C+S GST 18% I/P RD | 384.84 | 2522.84 | 2522.84 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 272 | 88543 | 31 Dec 2020 |  | GOURI INFRA | SAI NIRMAL COLOURS & TEXTURES | EV - 2035 | A Bldg 22nd Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 18.9659 | Sq.Ft | 161.5 | 100 | 0 | 0 | 3063 | C+S GST 18% I/P RD | 551.34 | 3614.34 | 3614.34 | Approved | 0 | 0 | 545 | 31 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 503 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 104 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 204 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 701 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 702 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 901 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 404 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 704 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 1002 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 403 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 803 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 1003 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 101 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 601 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 602 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 1001 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 502 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 902 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 501 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 201 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 1004 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 504 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 804 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 401 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 801 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 588.76 | Sq.Ft | 2 | 50 | 0 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 202 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 102 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 604 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 103 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 402 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 603 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 903 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 703 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 203 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 608.11 | Sq.Ft | 2 | 50 | 0 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 802 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 620.33 | Sq.Ft | 2 | 50 | 0 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 840 | 88512 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1949 | A 904 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (M)- BC | 607.02 | Sq.Ft | 2 | 50 | 0 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 0 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 102 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 703 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 704 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 404 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 901 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 202 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 903 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 103 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 403 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 504 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 802 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 1002 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 803 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 502 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 503 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 604 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 402 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 104 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 702 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 902 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 804 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 602 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 620.33 | Sq.Ft | 2 | 50 | 15.51 | 0 | 620.33 | C+S GST 18% I/P RD | 111.66 | 731.99 | 731.99 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 204 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 904 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 603 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 1003 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 201 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 701 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 801 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 1001 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 501 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 203 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 608.11 | Sq.Ft | 2 | 50 | 15.2 | 0 | 608.11 | C+S GST 18% I/P RD | 109.46 | 717.57 | 717.57 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 1004 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 607.02 | Sq.Ft | 2 | 50 | 15.18 | 0 | 607.02 | C+S GST 18% I/P RD | 109.26 | 716.28 | 716.28 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 101 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 401 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 839 | 88511 | 29 Dec 2020 |  | CHAPLA ADE PENTING CONTRACTOR | AKSHAY DECORATORS & PAINTING CONTRACTOR | EV - 1948 | A 601 All Toilet,Staff R,Dry Balc Cement Paint | Cement Paint (L)- BC | 588.76 | Sq.Ft | 2 | 50 | 14.72 | 0 | 588.76 | C+S GST 18% I/P RD | 105.98 | 694.74 | 694.74 | Approved | 0 | 0 | 164 | 29 Dec 2020
GANGA DHAM TOWERS | 258 | 88498 | 28 Dec 2020 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 2115 | Labour Camp Housekeeping Work | Housekeeping Work - SO | 0.8664 | Month | 2500 | 100 | 0 | 0 | 2166 | CGST 0% URD I/P | 0 | 2166 | 2166 | Approved | 0 | 0 | 16 | 28 Dec 2020
GANGA DHAM TOWERS | 237 | 88497 | 28 Dec 2020 |  | UTTAM RAMESH MAKWANA | UTTAM RAMESH MAKWANA | EV - 2116 | Labour Camp Toilet Cleaning | Toilet Cleaning- S.O. | 0.8666 | Month | 7000 | 100 | 0 | 0 | 6066 | CGST 0% URD I/P | 0 | 6066 | 6066 | Approved | 0 | 0 | 45 | 28 Dec 2020
GANGA DHAM TOWERS | 372 | 88496 | 28 Dec 2020 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 2230 | B Bldg 29th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2437.1125 | Sq.Ft | 160 | 100 | 0 | 0 | 389938 | IGST 18% I/P RD | 70188.84 | 460126.84 | 460126.84 | Approved | 0 | 0 | 14400 | 28 Dec 2020
GANGA DHAM TOWERS | 372 | 88496 | 28 Dec 2020 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 2230 | B Bldg 29th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3562.89 | Sq.Ft | 160 | 100 | 0 | 0 | 570062.4 | IGST 18% I/P RD | 102611.23 | 672673.63 | 672673.63 | Approved | 0 | 0 | 14400 | 28 Dec 2020
GANGA DHAM TOWERS | 780 | 88495 | 28 Dec 2020 |  | FINE TRADERS | FINE TRADERS | EV - 2033 | B 3rd Floor Lobby Flooring & cladding work | SS Clamp (M) | 62 | No. | 185 | 100 | 0 | 0 | 11470 | C+S GST 18% I/P RD | 2064.6 | 13534.6 | 13534.6 | Approved | 0 | 0 | 0 | 28 Dec 2020
GANGA DHAM TOWERS | 126 | 88494 | 28 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | SANDIP VAMANRAO RUPNAWAR | EV - 1946 | Site Expenses | Site Expenses -SO | 0.4165 | Month | 15000 | 100 | 0 | 0 | 6247 | CGST 0% URD I/P | 0 | 6247 | 6247 | Approved | 0 | 0 | 0 | 28 Dec 2020
GANGA DHAM TOWERS | 493 | 88493 | 28 Dec 2020 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2102 | D Bldg North Side External Plaster | External Plaster- BC | 1548.0357 | Sq.Ft | 28 | 100 | 1083.62 | 0 | 43345 | C+S GST 18% I/P RD | 7802.1 | 51147.1 | 51147.1 | Approved | 0 | 0 | 325 | 28 Dec 2020
GANGA DHAM TOWERS | 915 | 88492 | 28 Dec 2020 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD |  | B Core Cutting Work | Core Cutting work 1.6" | 24 | No. | 300 | 100 | 180 | 0 | 7200 | C+S GST 18% I/P RD | 1296 | 8496 | 8496 |  | 0 | 0 | 108 | 28 Dec 2020
GANGA DHAM TOWERS | 537 | 88491 | 28 Dec 2020 | 34 | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1947 | A 202 Living,Dining,Passa. Marble Flooring | Italian Marble Flooring - BCo | 572.8 | Sq.Ft | 45 | 100 | 644.4 | 0 | 25776 | C+S GST 18% I/P RD | 4639.68 | 30415.68 | 30415.68 | Approved | 0 | 0 | 325 | 28 Dec 2020
GANGA DHAM TOWERS | 537 | 88491 | 28 Dec 2020 | 34 | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1947 | A 202 Master Bed Marble Flooring | Italian Marble Flooring - BCo | 206.2444 | Sq.Ft | 45 | 100 | 232.02 | 0 | 9281 | C+S GST 18% I/P RD | 1670.58 | 10951.58 | 10951.58 | Approved | 0 | 0 | 325 | 28 Dec 2020
GANGA DHAM TOWERS | 537 | 88491 | 28 Dec 2020 | 34 | MONIKA ENTERPRISES | RAHUL ENTERPRISES (Prop Laburi) | EV - 1947 | A 202 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 182.4444 | Sq.Ft | 45 | 100 | 205.25 | 0 | 8210 | C+S GST 18% I/P RD | 1477.8 | 9687.8 | 9687.8 | Approved | 0 | 0 | 325 | 28 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 StaffToilet Dado | Dado BC | 136.45 | Sq.Ft | 17 | 100 | 57.99 | 0 | 2319.65 | C+S GST 18% I/P RD | 417.54 | 2737.19 | 2737.19 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Master Bed,Dreeser Marble Flooring | Italian marble Skirting - BCo | 58.22 | R.Ft | 50 | 100 | 72.78 | 0 | 2911 | C+S GST 18% I/P RD | 523.98 | 3434.98 | 3434.98 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 38.54 | R.Ft | 50 | 100 | 48.18 | 0 | 1927 | C+S GST 18% I/P RD | 346.86 | 2273.86 | 2273.86 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Living,Dining,Ent.Lobby Marble Flooring | Italian marble Skirting - BCo | 86.7 | R.Ft | 50 | 100 | 108.38 | 0 | 4335 | C+S GST 18% I/P RD | 780.3 | 5115.3 | 5115.3 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 147.75 | Sq.Ft | 20 | 100 | 73.88 | 0 | 2955 | C+S GST 18% I/P RD | 531.9 | 3486.9 | 3486.9 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Living Terrace Vitrified Flooing | Vitrified Flooring -BC | 207.64 | Sq.Ft | 20 | 100 | 103.82 | 0 | 4152.8 | C+S GST 18% I/P RD | 747.5 | 4900.3 | 4900.3 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Dry Balcony Dado | Dado BC | 81.38 | Sq.Ft | 18 | 100 | 36.62 | 0 | 1464.84 | C+S GST 18% I/P RD | 263.68 | 1728.52 | 1728.52 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Children Toilet 1 Dado | Dado BC | 162.77 | Sq.Ft | 18 | 100 | 73.25 | 0 | 2929.86 | C+S GST 18% I/P RD | 527.38 | 3457.24 | 3457.24 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Children Toilet 1 Dado | Dado BC | 49.58 | Sq.Ft | 20 | 100 | 24.79 | 0 | 991.6 | C+S GST 18% I/P RD | 178.48 | 1170.08 | 1170.08 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Parents Toilet Dado | Dado BC | 54.06 | Sq.Ft | 20 | 100 | 27.03 | 0 | 1081.2 | C+S GST 18% I/P RD | 194.62 | 1275.82 | 1275.82 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Guest Toilet Dado | Dado BC | 65.93 | Sq.Ft | 20 | 100 | 32.97 | 0 | 1318.6 | C+S GST 18% I/P RD | 237.34 | 1555.94 | 1555.94 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Powder Toilet Dado | Dado BC | 38.77 | Sq.Ft | 20 | 100 | 19.39 | 0 | 775.4 | C+S GST 18% I/P RD | 139.58 | 914.98 | 914.98 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Master Toilet Dado | Dado BC | 56.7 | Sq.Ft | 20 | 100 | 28.35 | 0 | 1134 | C+S GST 18% I/P RD | 204.12 | 1338.12 | 1338.12 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 59 | Sq.Ft | 17 | 100 | 25.08 | 0 | 1003 | C+S GST 18% I/P RD | 180.54 | 1183.54 | 1183.54 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Staff Toilet Vitrified Flooring | Vitrified Flooring -BC | 22.28 | Sq.Ft | 17 | 100 | 9.47 | 0 | 378.76 | C+S GST 18% I/P RD | 68.18 | 446.94 | 446.94 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Guest Toilet Vitrified Flooring | Vitrified Flooring -BC | 42.73 | Sq.Ft | 17 | 100 | 18.16 | 0 | 726.41 | C+S GST 18% I/P RD | 130.76 | 857.17 | 857.17 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Powder Toilet Vitrified Flooring | Vitrified Flooring -BC | 24.22 | Sq.Ft | 17 | 100 | 10.29 | 0 | 411.74 | C+S GST 18% I/P RD | 74.12 | 485.86 | 485.86 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Master Toilet Vitrified Flooring | Vitrified Flooring -BC | 59.63 | Sq.Ft | 17 | 100 | 25.34 | 0 | 1013.71 | C+S GST 18% I/P RD | 182.46 | 1196.17 | 1196.17 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 51.34 | Sq.Ft | 17 | 100 | 21.82 | 0 | 872.78 | C+S GST 18% I/P RD | 157.1 | 1029.88 | 1029.88 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Store Vitrified Flooring | Vitrified Flooring -BC | 46.1765 | Sq.Ft | 17 | 100 | 19.63 | 0 | 785 | C+S GST 18% I/P RD | 141.3 | 926.3 | 926.3 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Parents Toilet Vitrified Flooring | Vitrified Flooring -BC | 59.74 | Sq.Ft | 17 | 100 | 25.39 | 0 | 1015.58 | C+S GST 18% I/P RD | 182.8 | 1198.38 | 1198.38 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Children Toilet Vitrified Flooring | Vitrified Flooring -BC | 50.27 | Sq.Ft | 17 | 100 | 21.36 | 0 | 854.59 | C+S GST 18% I/P RD | 153.82 | 1008.41 | 1008.41 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Ceramic Tiling | Ceramic Flooring work | 355.5625 | Sq.Ft | 16 | 100 | 142.23 | 0 | 5689 | C+S GST 18% I/P RD | 1024.02 | 6713.02 | 6713.02 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Powder Toilet Dado | Dado BC | 94.94 | Sq.Ft | 18 | 100 | 42.72 | 0 | 1708.92 | C+S GST 18% I/P RD | 307.6 | 2016.52 | 2016.52 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Master Toilet Dado | Dado BC | 173.61 | Sq.Ft | 18 | 100 | 78.12 | 0 | 3124.98 | C+S GST 18% I/P RD | 562.5 | 3687.48 | 3687.48 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Parents Toilet Dado | Dado BC | 181 | Sq.Ft | 18 | 100 | 81.45 | 0 | 3258 | C+S GST 18% I/P RD | 586.44 | 3844.44 | 3844.44 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Guest Toilet Dado | Dado BC | 134.85 | Sq.Ft | 18 | 100 | 60.68 | 0 | 2427.3 | C+S GST 18% I/P RD | 436.92 | 2864.22 | 2864.22 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Living,Dining,Ent.Lobby Marble Flooring | Italian Marble Flooring - BCo | 659.56 | Sq.Ft | 50 | 100 | 824.45 | 0 | 32978 | C+S GST 18% I/P RD | 5936.04 | 38914.04 | 38914.04 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Parents Bed Marble Flooring | Italian Marble Flooring - BCo | 203.52 | Sq.Ft | 50 | 100 | 254.4 | 0 | 10176 | C+S GST 18% I/P RD | 1831.68 | 12007.68 | 12007.68 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 758 | 88470 | 25 Dec 2020 | 33 | RAHUL ENTERPRISES (Prop Laburi) | RAHUL ENTERPRISES (Prop Laburi) | EV - 1942 | B 1202 Master Bed,Dreeser Marble Flooring | Italian Marble Flooring - BCo | 269.42 | Sq.Ft | 50 | 100 | 336.78 | 0 | 13471 | C+S GST 18% I/P RD | 2424.78 | 15895.78 | 15895.78 | Approved | 0 | 0 | 811 | 25 Dec 2020
GANGA DHAM TOWERS | 886 | 88455 | 23 Dec 2020 | 136 | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1847 | CH Non- Structural Wall Core Cutting | Core Cutting Work 5" BCE | 4 | No. | 210 | 100 | 21 | 0 | 840 | C+S GST 18% I/P RD | 151.2 | 991.2 | 991.2 | Approved | 0 | 0 | 11 | 23 Dec 2020
GANGA DHAM TOWERS | 886 | 88455 | 23 Dec 2020 | 136 | PATIL CONSTRUCTION | PATIL CONSTRUCTION | EV - 1847 | CH Non- Structural Wall Core Cutting | Core Cutting Work 2.5" BCE | 3 | No. | 210 | 100 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 11 | 23 Dec 2020
GANGA DHAM TOWERS | 864 | 88454 | 23 Dec 2020 | 135 | B.D. DONGARE | PATIL CONSTRUCTION | EV - 1837 | B Core Cutting Work For Fire Work | Core Cutting Work 4" BCE | 29 | No. | 300 | 100 | 0 | 0 | 8700 | C+S GST 18% I/P RD | 1566 | 10266 | 10266 | Approved | 0 | 0 | 423 | 23 Dec 2020
GANGA DHAM TOWERS | 864 | 88454 | 23 Dec 2020 | 135 | B.D. DONGARE | PATIL CONSTRUCTION | EV - 1837 | B Core Cutting Work For Fire Work | Core Cutting Work 5" BCE | 8 | No. | 300 | 100 | 0 | 0 | 2400 | C+S GST 18% I/P RD | 432 | 2832 | 2832 | Approved | 0 | 0 | 423 | 23 Dec 2020
GANGA DHAM TOWERS | 864 | 88454 | 23 Dec 2020 | 135 | B.D. DONGARE | PATIL CONSTRUCTION | EV - 1837 | B Core Cutting Work For Fire Work | Core Cutting Work 3" BCE | 151 | No. | 300 | 100 | 0 | 0 | 45300 | C+S GST 18% I/P RD | 8154 | 53454 | 53454 | Approved | 0 | 0 | 423 | 23 Dec 2020
GANGA DHAM TOWERS | 272 | 88450 | 23 Dec 2020 | 15 | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1941 | A Bldg 29th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 4733.82 | Sq.Ft | 171 | 100 | 0 | 0 | 809483.22 | C+S GST 18% I/P RD | 145706.98 | 955190.2 | 955190.2 | Approved | 0 | 0 | 16252 | 23 Dec 2020
GANGA DHAM TOWERS | 272 | 88450 | 23 Dec 2020 | 15 | GOURI INFRA | DUCON CONTACTORS PRIVATE LIMITED | EV - 1941 | A Bldg 29th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1602.1813 | Sq.Ft | 171 | 100 | 0 | 0 | 273973 | C+S GST 18% I/P RD | 49315.14 | 323288.14 | 323288.14 | Approved | 0 | 0 | 16252 | 23 Dec 2020
GANGA DHAM TOWERS | 272 | 88449 | 23 Dec 2020 |  | GOURI INFRA | B & B ENTERPRISES | EV - 2231 | A Bldg 29th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 1824 | Sq.Ft | 171 | 100 | 0 | 0 | 311904 | C+S GST 18% I/P RD | 56142.72 | 368046.72 | 368046.72 | Approved | 0 | 0 | 2339 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 40 | No. | 250 | 35 | 87.5 | 0 | 3500 | C+S GST 18% I/P RD | 630 | 4130 | 4130 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 23 | No. | 250 | 35 | 50.31 | 0 | 2012.5 | C+S GST 18% I/P RD | 362.26 | 2374.76 | 2374.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 39 | No. | 250 | 35 | 85.31 | 0 | 3412.5 | C+S GST 18% I/P RD | 614.26 | 4026.76 | 4026.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 35 | No. | 250 | 35 | 76.56 | 0 | 3062.5 | C+S GST 18% I/P RD | 551.26 | 3613.76 | 3613.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 35 | 32.81 | 0 | 1312.5 | C+S GST 18% I/P RD | 236.26 | 1548.76 | 1548.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Smoke Detector | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Smoke Detector | 10 | No. | 250 | 35 | 21.88 | 0 | 875 | C+S GST 18% I/P RD | 157.5 | 1032.5 | 1032.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | DB LV | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | DB LV | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | DB LV | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | DB LV | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Secondary Light Points (Looping) | 39 | No. | 100 | 35 | 34.13 | 0 | 1365 | C+S GST 18% I/P RD | 245.7 | 1610.7 | 1610.7 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Secondary Light Points (Looping) | 44 | No. | 100 | 35 | 38.5 | 0 | 1540 | C+S GST 18% I/P RD | 277.2 | 1817.2 | 1817.2 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Secondary Light Points (Looping) | 42 | No. | 100 | 35 | 36.75 | 0 | 1470 | C+S GST 18% I/P RD | 264.6 | 1734.6 | 1734.6 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Secondary Light Points (Looping) | 38 | No. | 100 | 35 | 33.25 | 0 | 1330 | C+S GST 18% I/P RD | 239.4 | 1569.4 | 1569.4 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Fan Point | 9 | No. | 250 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Fan Point | 7 | No. | 250 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Fan Point | 8 | No. | 250 | 35 | 17.5 | 0 | 700 | C+S GST 18% I/P RD | 126 | 826 | 826 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | 6 AMP Plug point (Independent) | 30 | No. | 250 | 35 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 35 | 37.19 | 0 | 1487.5 | C+S GST 18% I/P RD | 267.76 | 1755.26 | 1755.26 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | 6 AMP Plug point (Independent) | 20 | No. | 250 | 35 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 500 | 35 | 4.38 | 0 | 175 | C+S GST 18% I/P RD | 31.5 | 206.5 | 206.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2302 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2303 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2301 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 359 | 88448 | 23 Dec 2020 | PLVE/20-21/22 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1974 | A Bldg Flat No.-2304 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1127 | 23 Dec 2020
GANGA DHAM TOWERS | 497 | 88441 | 21 Dec 2020 |  | J K INTERIOR | J K INTERIOR | EV - 2387 | B 102 Gypsum Plaster | Dhar Core (L) | 501 | R.Ft | 10 | 100 | 125.25 | 0 | 5010 | C+S GST 18% I/P RD | 901.8 | 5911.8 | 5911.8 | Approved | 0 | 0 | 145 | 21 Dec 2020
GANGA DHAM TOWERS | 497 | 88441 | 21 Dec 2020 |  | J K INTERIOR | J K INTERIOR | EV - 2387 | B 102 Gypsum Plaster | Gypsum on Wall (L) | 3579 | Sq.Ft | 4 | 100 | 357.9 | 0 | 14316 | C+S GST 18% I/P RD | 2576.88 | 16892.88 | 16892.88 | Approved | 0 | 0 | 145 | 21 Dec 2020
GANGA DHAM TOWERS | 495 | 88440 | 21 Dec 2020 | 297 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1876 | B 1401 Gypsum Plaster | Gypsum on Wall (L) | 5092.75 | Sq.Ft | 4 | 100 | 509.28 | 0 | 20371 | C+S GST 18% I/P RD | 3666.78 | 24037.78 | 24037.78 | Approved | 0 | 0 | 653 | 21 Dec 2020
GANGA DHAM TOWERS | 495 | 88440 | 21 Dec 2020 | 297 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1876 | B 1301 Gypsum Plaster | Gypsum on Wall (L) | 5092.75 | Sq.Ft | 4 | 100 | 509.28 | 0 | 20371 | C+S GST 18% I/P RD | 3666.78 | 24037.78 | 24037.78 | Approved | 0 | 0 | 653 | 21 Dec 2020
GANGA DHAM TOWERS | 495 | 88440 | 21 Dec 2020 | 297 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1876 | B 1601 Gypsum Plaster (Refuge Flat) | Gypsum on Wall (L) | 4730.25 | Sq.Ft | 4 | 100 | 473.03 | 0 | 18921 | C+S GST 18% I/P RD | 3405.78 | 22326.78 | 22326.78 | Approved | 0 | 0 | 653 | 21 Dec 2020
GANGA DHAM TOWERS | 495 | 88440 | 21 Dec 2020 | 297 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1876 | B 1601 Gypsum Plaster (Refuge Flat) | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 653 | 21 Dec 2020
GANGA DHAM TOWERS | 495 | 88440 | 21 Dec 2020 | 297 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1876 | B 101 Gypsum Plaster | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 653 | 21 Dec 2020
GANGA DHAM TOWERS | 495 | 88440 | 21 Dec 2020 | 297 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1876 | B 1301 Gypsum Plaster | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 653 | 21 Dec 2020
GANGA DHAM TOWERS | 495 | 88440 | 21 Dec 2020 | 297 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1876 | B 1401 Gypsum Plaster | Dhar Core (L) | 684.75 | R.Ft | 10 | 100 | 171.19 | 0 | 6847.5 | C+S GST 18% I/P RD | 1232.56 | 8080.06 | 8080.06 | Approved | 0 | 0 | 653 | 21 Dec 2020
GANGA DHAM TOWERS | 909 | 88439 | 21 Dec 2020 |  | P.L. VISHWAKARMA ELECTRICALS (FIRM) | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 2097 | Steel Godown/ Yard Earthing Work | Earthing work(m+l)- BC | 5 | No. | 4000 | 100 | 0 | 0 | 20000 | C+S GST 18% I/P RD | 3600 | 23600 | 23600 | Approved | 0 | 0 | 300 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | Square Chamber (3ft x 2ft) | 8 | No. | 1000 | 100 | 200 | 0 | 8000 | CGST 0% URD I/P | 0 | 8000 | 8000 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | PVC Pipe Laying 5" | 180 | R.Ft | 4 | 100 | 18 | 0 | 720 | CGST 0% URD I/P | 0 | 720 | 720 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | 10" HDPE Pipe Laying-USL | 207 | R.Ft | 12 | 100 | 62.1 | 0 | 2484 | CGST 0% URD I/P | 0 | 2484 | 2484 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | Round chamber 2ft dia (2m ht) | 1 | No. | 5600 | 100 | 140 | 0 | 5600 | CGST 0% URD I/P | 0 | 5600 | 5600 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | 8" HDPE Pipe Laying-USL | 178 | R.Ft | 10 | 100 | 44.5 | 0 | 1780 | CGST 0% URD I/P | 0 | 1780 | 1780 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | 12" HDPE Pipe Laying-USL | 94 | R.Ft | 14 | 100 | 32.9 | 0 | 1316 | CGST 0% URD I/P | 0 | 1316 | 1316 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | Round chamber 2ft dia (2.5m ht) | 1 | No. | 7500 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | Round chamber 2ft dia (2.5m ht) | 1 | No. | 7500 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | Round chamber 2ft dia (2.5m ht) | 1 | No. | 7500 | 100 | 187.5 | 0 | 7500 | CGST 0% URD I/P | 0 | 7500 | 7500 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 926 | 88438 | 21 Dec 2020 |  | SUSHANT ENTERPRISES | SUSHANT ENTERPRISES | EV - 1872 | Storm Water line From CH To STP To PMC - 1 No. | Round chamber 2ft dia (1.5m ht) | 2 | No. | 4200 | 100 | 210 | 0 | 8400 | CGST 0% URD I/P | 0 | 8400 | 8400 | Approved | 0 | 0 | 381 | 21 Dec 2020
GANGA DHAM TOWERS | 371 | 88432 | 19 Dec 2020 |  | CONSTROGENESIS | KADAVATH VENKAT ENTERPRISES | EV - 2117 | EWS Bldg RCC 1st Slab Built-up Area (L) | Schedule & Quality | 3520 | Sq.Ft | 2.5 | 100 | 220 | 0 | 8800 | C+S GST 18% I/P RD | 1584 | 10384 | 10384 | Approved | 0 | 0 | 150 | 19 Dec 2020
GANGA DHAM TOWERS | 371 | 88432 | 19 Dec 2020 |  | CONSTROGENESIS | KADAVATH VENKAT ENTERPRISES | EV - 2117 | EWS Bldg RCC 3rd Slab Built-up Area (L) | Schedule & Quality | 1080 | Sq.Ft | 2.5 | 100 | 67.5 | 0 | 2700 | C+S GST 18% I/P RD | 486 | 3186 | 3186 | Approved | 0 | 0 | 150 | 19 Dec 2020
GANGA DHAM TOWERS | 371 | 88432 | 19 Dec 2020 |  | CONSTROGENESIS | KADAVATH VENKAT ENTERPRISES | EV - 2117 | EWS Bldg RCC 2nd Slab Built-up Area (L) | Schedule & Quality | 3400 | Sq.Ft | 2.5 | 100 | 212.5 | 0 | 8500 | C+S GST 18% I/P RD | 1530 | 10030 | 10030 | Approved | 0 | 0 | 150 | 19 Dec 2020
GANGA DHAM TOWERS | 371 | 88431 | 19 Dec 2020 |  | CONSTROGENESIS | MARVEL ENTERPRISES | EV - 2025 | EWS Bldg RCC 13th Slab Built-up Area (Terrace)(L) | RCC Superstructure (B-up area) | 222.5333 | Sq.Ft | 150 | 100 | 834.5 | 0 | 33380 | C+S GST 18% I/P RD | 6008.4 | 39388.4 | 39388.4 | Approved | 0 | 0 | 775 | 19 Dec 2020
GANGA DHAM TOWERS | 371 | 88431 | 19 Dec 2020 |  | CONSTROGENESIS | MARVEL ENTERPRISES | EV - 2025 | EWS Bldg RCC 11th Slab Built-up Area (L) | RCC Superstructure (B-up area) | 466.6667 | Sq.Ft | 150 | 100 | 1750 | 0 | 70000.01 | C+S GST 18% I/P RD | 12600 | 82600.01 | 82600.01 | Approved | 0 | 0 | 775 | 19 Dec 2020
GANGA DHAM TOWERS | 772 | 88423 | 17 Dec 2020 | 8 | RAHUL ENTERPRISES (Prop Laburi) | AVCON TECHNICS PVT LTD | EV - 1951 | A 503 NOC | Concrete Cutting Work | 184.1695 | R.Ft | 525 | 100 | 0 | 0 | 96689 | C+S GST 18% I/P RD | 17404.02 | 114093.02 | 114093.02 | Approved | 0 | 0 | 1450 | 17 Dec 2020
GANGA DHAM TOWERS | 856 | 88414 | 16 Dec 2020 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2100 | Club House Ground Floor External Sand Face Plaster | Sand Face Plaster DCH | 1074 | Sq.Ft | 20 | 100 | 537 | 0 | 21480 | C+S GST 18% I/P RD | 3866.4 | 25346.4 | 25346.4 | Approved | 0 | 0 | 369 | 16 Dec 2020
GANGA DHAM TOWERS | 856 | 88414 | 16 Dec 2020 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2100 | Club House 1st Floor External Sand Face Plaster | Sand Face Plaster DCH | 736 | Sq.Ft | 20 | 100 | 368 | 0 | 14720 | C+S GST 18% I/P RD | 2649.6 | 17369.6 | 17369.6 | Approved | 0 | 0 | 369 | 16 Dec 2020
GANGA DHAM TOWERS | 856 | 88414 | 16 Dec 2020 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2100 | Club House Steps Pcc - 1 No. | PCC DCH | 565.09 | Sq.Ft | 3 | 100 | 0 | 0 | 1695.27 | C+S GST 18% I/P RD | 305.14 | 2000.41 | 2000.41 | Approved | 0 | 0 | 369 | 16 Dec 2020
GANGA DHAM TOWERS | 856 | 88414 | 16 Dec 2020 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2100 | Club House Ground Floor Steps Rough Plaster | Rough Plaster | 461 | Sq.Ft | 15 | 100 | 172.88 | 0 | 6915 | C+S GST 18% I/P RD | 1244.7 | 8159.7 | 8159.7 | Approved | 0 | 0 | 369 | 16 Dec 2020
GANGA DHAM TOWERS | 856 | 88414 | 16 Dec 2020 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2100 | Club house GF Brickwork/Plaster | Brickwork 4" DCH | 105.15 | Sq.Ft | 20 | 100 | 0 | 0 | 2103 | C+S GST 18% I/P RD | 378.54 | 2481.54 | 2481.54 | Approved | 0 | 0 | 369 | 16 Dec 2020
GANGA DHAM TOWERS | 856 | 88414 | 16 Dec 2020 |  | KADAVATH VENKAT ENTERPRISES | KADAVATH VENKAT ENTERPRISES | EV - 2100 | Club House 1st Floor Brickwork/ Plaster | Brickwork 4" DCH | 114.65 | Sq.Ft | 20 | 100 | 0 | 0 | 2293 | C+S GST 18% I/P RD | 412.74 | 2705.74 | 2705.74 | Approved | 0 | 0 | 369 | 16 Dec 2020
GANGA DHAM TOWERS | 744 | 88405 | 15 Dec 2020 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 1846 | Sales office & Sample Flats garbage collection | Garbage Collection- SO | 0.6 | Month | 1000 | 100 | 0 | 0 | 600 | CGST 0% URD I/P | 0 | 600 | 600 | Approved | 0 | 0 | 0 | 15 Dec 2020
GANGA DHAM TOWERS | 914 | 88402 | 15 Dec 2020 |  | SAURABH FABRICATION | SAURABH FABRICATION | EV - 2098 | Near Mandir Plot MS Frame Working - 1 Sq.Ft | MS Frame Making & Fixing | 1257.04 | Sq.Ft | 6 | 100 | 188.56 | 0 | 7542.24 | CGST 0% URD I/P | 0 | 7542.24 | 7542.24 | Approved | 0 | 0 | 57 | 15 Dec 2020
GANGA DHAM TOWERS | 901 | 88401 | 15 Dec 2020 |  | MARVEL ENTERPRISES | MARVEL ENTERPRISES | EV - 2034 | D Safety Net Fixing & Removing work | Safety Net Removing- SO | 10975 | Sq.Ft | 1 | 100 | 0 | 0 | 10975 | C+S GST 18% I/P RD | 1975.5 | 12950.5 | 12950.5 | Approved | 0 | 0 | 607 | 15 Dec 2020
GANGA DHAM TOWERS | 901 | 88401 | 15 Dec 2020 |  | MARVEL ENTERPRISES | MARVEL ENTERPRISES | EV - 2034 | Podium A1 & A2 part Periphery fabrication work for Safety ne | Safety Net Removing- SO | 1936 | Sq.Ft | 1 | 100 | 0 | 0 | 1936 | C+S GST 18% I/P RD | 348.48 | 2284.48 | 2284.48 | Approved | 0 | 0 | 607 | 15 Dec 2020
GANGA DHAM TOWERS | 901 | 88401 | 15 Dec 2020 |  | MARVEL ENTERPRISES | MARVEL ENTERPRISES | EV - 2034 | Podium A1 & A2 part Periphery fabrication work for Safety ne | Safety Net Fixing- SO | 10974 | Sq.Ft | 2.7 | 100 | 0 | 0 | 29629.8 | C+S GST 18% I/P RD | 5333.36 | 34963.16 | 34963.16 | Approved | 0 | 0 | 607 | 15 Dec 2020
GANGA DHAM TOWERS | 901 | 88401 | 15 Dec 2020 |  | MARVEL ENTERPRISES | MARVEL ENTERPRISES | EV - 2034 | D Safety Net Fixing & Removing work | Safety Net Fixing- SO | 14238 | Sq.Ft | 2.7 | 100 | 0 | 0 | 38442.6 | C+S GST 18% I/P RD | 6919.66 | 45362.26 | 45362.26 | Approved | 0 | 0 | 607 | 15 Dec 2020
GANGA DHAM TOWERS | 904 | 88400 | 15 Dec 2020 |  | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 2107 | B 701 NOC | Concrete Cutting Work | 180.8895 | R.Ft | 525 | 100 | 2374.17 | 0 | 94967 | C+S GST 18% I/P RD | 17094.06 | 112061.06 | 112061.06 | Approved | 0 | 0 | 1425 | 15 Dec 2020
GANGA DHAM TOWERS | 678 | 88398 | 15 Dec 2020 | 10 | AVCON TECHNICS PVT LTD | AVCON TECHNICS PVT LTD | EV - 1950 | A 501 NOC | Concrete Cutting Work | 70.4305 | R.Ft | 525 | 100 | 924.4 | 0 | 36976 | C+S GST 18% I/P RD | 6655.68 | 43631.68 | 43631.68 | Approved | 0 | 0 | 555 | 15 Dec 2020
GANGA DHAM TOWERS | 395 | 88397 | 15 Dec 2020 | 295 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1877 | A Bldg Flat No. 104 Gypsum Plaster | Gypsum on Wall (L) | 2680.25 | Sq.Ft | 4 | 100 | 268.03 | 0 | 10721 | C+S GST 18% I/P RD | 1929.78 | 12650.78 | 12650.78 | Approved | 0 | 0 | 270 | 15 Dec 2020
GANGA DHAM TOWERS | 395 | 88397 | 15 Dec 2020 | 295 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1877 | A Bldg Flat No. 103 Gypsum Plaster | Gypsum on Wall (L) | 2193 | Sq.Ft | 4 | 100 | 219.3 | 0 | 8772 | C+S GST 18% I/P RD | 1578.96 | 10350.96 | 10350.96 | Approved | 0 | 0 | 270 | 15 Dec 2020
GANGA DHAM TOWERS | 395 | 88397 | 15 Dec 2020 | 295 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1877 | A Bldg Flat No. 104 Gypsum Plaster | Dhar Core (L) | 550 | R.Ft | 10 | 100 | 137.5 | 0 | 5500 | C+S GST 18% I/P RD | 990 | 6490 | 6490 | Approved | 0 | 0 | 270 | 15 Dec 2020
GANGA DHAM TOWERS | 395 | 88397 | 15 Dec 2020 | 295 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1877 | A Bldg Flat No. 204 Gypsum Plaster | Dhar Core (L) | 550 | R.Ft | 10 | 100 | 137.5 | 0 | 5500 | C+S GST 18% I/P RD | 990 | 6490 | 6490 | Approved | 0 | 0 | 270 | 15 Dec 2020
GANGA DHAM TOWERS | 395 | 88397 | 15 Dec 2020 | 295 | A K INTERIOR CONTRACTOR | A K INTERIOR CONTRACTOR | EV - 1877 | A Bldg Flat No. 103 Gypsum Plaster | Dhar Core (L) | 550 | R.Ft | 10 | 100 | 137.5 | 0 | 5500 | C+S GST 18% I/P RD | 990 | 6490 | 6490 | Approved | 0 | 0 | 270 | 15 Dec 2020
GANGA DHAM TOWERS | 393 | 88396 | 15 Dec 2020 |  | J K INTERIOR | J K INTERIOR | EV - 2096 | A Bldg Flat No. 101 Gypsum Plaster | Dhar Core (L) | 550 | R.Ft | 10 | 100 | 137.5 | 0 | 5500 | C+S GST 18% I/P RD | 990 | 6490 | 6490 | Approved | 0 | 0 | 122 | 15 Dec 2020
GANGA DHAM TOWERS | 393 | 88396 | 15 Dec 2020 |  | J K INTERIOR | J K INTERIOR | EV - 2096 | A Bldg Flat No. 101 Gypsum Plaster | Gypsum on Wall (L) | 2690.5 | Sq.Ft | 4 | 100 | 269.05 | 0 | 10762 | C+S GST 18% I/P RD | 1937.16 | 12699.16 | 12699.16 | Approved | 0 | 0 | 122 | 15 Dec 2020
GANGA DHAM TOWERS | 903 | 88385 | 14 Dec 2020 |  | OM SAI CORP | OM SAI CORP | EV - 1819 | MEDIA FLEX PASTING | Backlet Box / Backlet Display Frame / Board | 750 | Sq.Ft | 210 | 100 | 0 | 0 | 157500 | C+S GST 18% I/P RD | 28350 | 185850 | 185850 | Approved | 0 | 0 | 1799 | 14 Dec 2020
GANGA DHAM TOWERS | 903 | 88385 | 14 Dec 2020 |  | OM SAI CORP | OM SAI CORP | EV - 1819 | MEDIA FLEX PASTING | Black Back Flex | 1184 | Sq.Ft | 20 | 100 | 0 | 0 | 23680 | C+S GST 18% I/P RD | 4262.4 | 27942.4 | 27942.4 | Approved | 0 | 0 | 1799 | 14 Dec 2020
GANGA DHAM TOWERS | 903 | 88385 | 14 Dec 2020 |  | OM SAI CORP | OM SAI CORP | EV - 1819 | MEDIA FLEX PASTING | Star Flex | 2932.4 | Sq.Ft | 20 | 100 | 0 | 0 | 58648 | C+S GST 18% I/P RD | 10556.64 | 69204.64 | 69204.64 | Approved | 0 | 0 | 1799 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Fan Fixing - Mkt | 3 | No. | 100 | 100 | 7.5 | 0 | 300 | CGST 0% URD I/P | 0 | 300 | 300 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Light Fitting Removing | 15 | No. | 100 | 100 | 37.5 | 0 | 1500 | CGST 0% URD I/P | 0 | 1500 | 1500 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Light Fitting Removing | 2 | No. | 100 | 100 | 5 | 0 | 200 | CGST 0% URD I/P | 0 | 200 | 200 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Light Fitting Removing | 5 | No. | 100 | 100 | 12.5 | 0 | 500 | CGST 0% URD I/P | 0 | 500 | 500 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Data Point | 1 | No. | 2700 | 100 | 67.5 | 0 | 2700 | CGST 0% URD I/P | 0 | 2700 | 2700 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | 6 AMP Plug point (Dependent) | 5 | No. | 600 | 100 | 75 | 0 | 3000 | CGST 0% URD I/P | 0 | 3000 | 3000 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Fan Point | 2 | No. | 1350 | 100 | 67.5 | 0 | 2700 | CGST 0% URD I/P | 0 | 2700 | 2700 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Electrical work lump- SOS | 1 | No. | 12000 | 100 | 300 | 0 | 12000 | CGST 0% URD I/P | 0 | 12000 | 12000 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | USB Point | 1 | No. | 2350 | 100 | 58.75 | 0 | 2350 | CGST 0% URD I/P | 0 | 2350 | 2350 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | 4 Pole 63 Amp MCB & RCCB | 1 | No. | 4000 | 100 | 100 | 0 | 4000 | CGST 0% URD I/P | 0 | 4000 | 4000 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | 6 AMP Plug point (Independent) | 21 | No. | 1375 | 100 | 721.88 | 0 | 28875 | CGST 0% URD I/P | 0 | 28875 | 28875 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | AC Point BC | 2 | No. | 4150 | 100 | 207.5 | 0 | 8300 | CGST 0% URD I/P | 0 | 8300 | 8300 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Fancy Light fitting- Mkt | 4 | No. | 200 | 100 | 20 | 0 | 800 | C+S GST 0% I/P RD | 0 | 800 | 800 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Secondary Light Points (Looping) | 3 | No. | 450 | 100 | 33.75 | 0 | 1350 | CGST 0% URD I/P | 0 | 1350 | 1350 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | LED Strip fitting- BC | 14 | Mtrs | 50 | 100 | 17.5 | 0 | 700 | CGST 0% URD I/P | 0 | 700 | 700 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | Light Fitting Fixing | 10 | No. | 100 | 100 | 25 | 0 | 1000 | CGST 0% URD I/P | 0 | 1000 | 1000 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 837 | 88381 | 14 Dec 2020 | 21 | SANTOSH ELECTRICALS | SANTOSH ELECTRICALS | EV - 1873 | DA Development Electrical work | TV Fixing | 2 | No. | 600 | 100 | 30 | 0 | 1200 | CGST 0% URD I/P | 0 | 1200 | 1200 | Approved | 0 | 0 | 536 | 14 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2002 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2103 Internal Electrical Work | 6 AMP Plug point (Independent) | 30 | No. | 250 | 35 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2101 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 35 | 37.19 | 0 | 1487.5 | C+S GST 18% I/P RD | 267.76 | 1755.26 | 1755.26 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1902 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2104 Internal Electrical Work | 6 AMP Plug point (Independent) | 20 | No. | 250 | 35 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1903 Internal Electrical Work | 6 AMP Plug point (Independent) | 30 | No. | 250 | 35 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2004 Internal Electrical Work | 6 AMP Plug point (Independent) | 20 | No. | 250 | 35 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2202 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2102 Internal Electrical Work | 6 AMP Plug point (Independent) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2203 Internal Electrical Work | 6 AMP Plug point (Independent) | 30 | No. | 250 | 35 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1901 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 35 | 37.19 | 0 | 1487.5 | C+S GST 18% I/P RD | 267.76 | 1755.26 | 1755.26 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2001 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 35 | 37.19 | 0 | 1487.5 | C+S GST 18% I/P RD | 267.76 | 1755.26 | 1755.26 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2204 Internal Electrical Work | 6 AMP Plug point (Independent) | 20 | No. | 250 | 35 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1904 Internal Electrical Work | 6 AMP Plug point (Independent) | 20 | No. | 250 | 35 | 43.75 | 0 | 1750 | C+S GST 18% I/P RD | 315 | 2065 | 2065 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2003 Internal Electrical Work | 6 AMP Plug point (Independent) | 30 | No. | 250 | 35 | 65.63 | 0 | 2625 | C+S GST 18% I/P RD | 472.5 | 3097.5 | 3097.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2201 Internal Electrical Work | 6 AMP Plug point (Independent) | 17 | No. | 250 | 35 | 37.19 | 0 | 1487.5 | C+S GST 18% I/P RD | 267.76 | 1755.26 | 1755.26 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1904 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 21 | No. | 250 | 35 | 45.94 | 0 | 1837.5 | C+S GST 18% I/P RD | 330.76 | 2168.26 | 2168.26 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2204 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 21 | No. | 250 | 35 | 45.94 | 0 | 1837.5 | C+S GST 18% I/P RD | 330.76 | 2168.26 | 2168.26 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2102 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1903 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 23 | No. | 250 | 35 | 50.31 | 0 | 2012.5 | C+S GST 18% I/P RD | 362.26 | 2374.76 | 2374.76 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2201 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 35 | 32.81 | 0 | 1312.5 | C+S GST 18% I/P RD | 236.26 | 1548.76 | 1548.76 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2003 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 23 | No. | 250 | 35 | 50.31 | 0 | 2012.5 | C+S GST 18% I/P RD | 362.26 | 2374.76 | 2374.76 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1902 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2104 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 21 | No. | 250 | 35 | 45.94 | 0 | 1837.5 | C+S GST 18% I/P RD | 330.76 | 2168.26 | 2168.26 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2004 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 21 | No. | 250 | 35 | 45.94 | 0 | 1837.5 | C+S GST 18% I/P RD | 330.76 | 2168.26 | 2168.26 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2001 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 35 | 32.81 | 0 | 1312.5 | C+S GST 18% I/P RD | 236.26 | 1548.76 | 1548.76 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2203 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 23 | No. | 250 | 35 | 50.31 | 0 | 2012.5 | C+S GST 18% I/P RD | 362.26 | 2374.76 | 2374.76 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2103 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 23 | No. | 250 | 35 | 50.31 | 0 | 2012.5 | C+S GST 18% I/P RD | 362.26 | 2374.76 | 2374.76 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2002 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 18 | No. | 250 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-2101 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 15 | No. | 250 | 35 | 32.81 | 0 | 1312.5 | C+S GST 18% I/P RD | 236.26 | 1548.76 | 1548.76 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1901 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 359 | 88345 | 11 Dec 2020 | PLVE/20-21/19 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1866 | A Bldg Flat No.-1902 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 10 | No. | 450 | 35 | 39.38 | 0 | 1575 | C+S GST 18% I/P RD | 283.5 | 1858.5 | 1858.5 | Approved | 0 | 0 | 878 | 11 Dec 2020
GANGA DHAM TOWERS | 187 | 88344 | 10 Dec 2020 | 73 | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 1811 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 10 Dec 2020
GANGA DHAM TOWERS | 126 | 88327 | 09 Dec 2020 |  | SANDIP VAMANRAO RUPNAWAR | PRADEEP SOHANI |  | Site Expenses | Site Expenses -SO | 0.1103 | Month | 15000 | 100 | 0 | 0 | 1654 | CGST 0% URD I/P | 0 | 1654 | 1654 |  | 0 | 0 | 0 | 09 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | AC Point BC | 9 | No. | 220 | 35 | 17.33 | 0 | 693 | C+S GST 18% I/P RD | 124.74 | 817.74 | 817.74 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | AC Point BC | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1400 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 51 | No. | 200 | 35 | 89.25 | 0 | 3570 | C+S GST 18% I/P RD | 642.6 | 4212.6 | 4212.6 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | Primary Light Pt. (Controlled by Sw. Board) | 79 | No. | 200 | 35 | 138.25 | 0 | 5530 | C+S GST 18% I/P RD | 995.4 | 6525.4 | 6525.4 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | Data Point | 4 | No. | 220 | 35 | 7.7 | 0 | 308 | C+S GST 18% I/P RD | 55.44 | 363.44 | 363.44 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | Data Point | 7 | No. | 220 | 35 | 13.48 | 0 | 539 | C+S GST 18% I/P RD | 97.02 | 636.02 | 636.02 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | Fan Point | 11 | No. | 200 | 35 | 19.25 | 0 | 770 | C+S GST 18% I/P RD | 138.6 | 908.6 | 908.6 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | Fan Point | 9 | No. | 200 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 200 | 35 | 14 | 0 | 560 | C+S GST 18% I/P RD | 100.8 | 660.8 | 660.8 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | Exhaust Fan Point | 5 | No. | 200 | 35 | 8.75 | 0 | 350 | C+S GST 18% I/P RD | 63 | 413 | 413 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1300 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | Secondary Light Points (Looping) | 55 | No. | 67 | 35 | 32.24 | 0 | 1289.75 | C+S GST 18% I/P RD | 232.16 | 1521.91 | 1521.91 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | Telephone Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | Telephone Point | 5 | No. | 220 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 200 | 35 | 92.75 | 0 | 3710 | C+S GST 18% I/P RD | 667.8 | 4377.8 | 4377.8 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | 6 AMP Plug point (Independent) | 84 | No. | 200 | 35 | 147 | 0 | 5880 | C+S GST 18% I/P RD | 1058.4 | 6938.4 | 6938.4 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | Video Door Phone (L)- BC | 1 | No. | 200 | 35 | 1.75 | 0 | 70 | C+S GST 18% I/P RD | 12.6 | 82.6 | 82.6 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | 6 AMP Plug point (Dependent) | 15 | No. | 67 | 35 | 8.79 | 0 | 351.75 | C+S GST 18% I/P RD | 63.32 | 415.07 | 415.07 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 67 | 35 | 7.62 | 0 | 304.85 | C+S GST 18% I/P RD | 54.88 | 359.73 | 359.73 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 3 | No. | 220 | 35 | 5.78 | 0 | 231 | C+S GST 18% I/P RD | 41.58 | 272.58 | 272.58 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 220 | 35 | 3.85 | 0 | 154 | C+S GST 18% I/P RD | 27.72 | 181.72 | 181.72 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | TV Point | 6 | No. | 220 | 35 | 11.55 | 0 | 462 | C+S GST 18% I/P RD | 83.16 | 545.16 | 545.16 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2201 Internal Electrical Work | TV Point | 8 | No. | 220 | 35 | 15.4 | 0 | 616 | C+S GST 18% I/P RD | 110.88 | 726.88 | 726.88 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 399 | 88307 | 07 Dec 2020 | PLVE/20-21/23 | SAHOO ELECTRICAL | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1975 | B Bldg Flat No. 2202 Internal Electrical Work | Secondary Light Points (Looping) | 43 | No. | 67 | 35 | 25.21 | 0 | 1008.35 | C+S GST 18% I/P RD | 181.5 | 1189.85 | 1189.85 | Approved | 0 | 0 | 440 | 07 Dec 2020
GANGA DHAM TOWERS | 145 | 88300 | 05 Dec 2020 |  | PEST-O-CRUSH | PEST-O-CRUSH | EV - 2104 | Fogging Work | Fogging work-SO | 0.75 | Month | 6000 | 100 | 0 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 45 | 05 Dec 2020
GANGA DHAM TOWERS | 372 | 88299 | 05 Dec 2020 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1810 | B Bldg 28th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 2412.3875 | Sq.Ft | 160 | 100 | 0 | 0 | 385982 | C+S GST 18% I/P RD | 69476.76 | 455458.76 | 455458.76 | Approved | 0 | 0 | 14400 | 05 Dec 2020
GANGA DHAM TOWERS | 372 | 88299 | 05 Dec 2020 |  | B & B ENTERPRISES | B & B ENTERPRISES | EV - 1810 | B Bldg 28th Slab Built-up Area (L) | RCC Mi-van Labour (B-up Basis)BC | 3587.59 | Sq.Ft | 160 | 100 | 0 | 0 | 574014.4 | C+S GST 18% I/P RD | 103322.6 | 677337 | 677337 | Approved | 0 | 0 | 14400 | 05 Dec 2020
GANGA DHAM TOWERS | 413 | 88298 | 05 Dec 2020 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2193 | Sales Oiifce Landscape Area . | Supervision Charges | 0.5 | Month | 4000 | 100 | 0 | 0 | 2000 | C+S GST 18% I/P RD | 360 | 2360 | 2360 | Approved | 0 | 0 | 15 | 05 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2204 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2202 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1902 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1903 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2102 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2003 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2104 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2001 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2101 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2002 Internal Electrical Work | 6 AMP Plug point (Independent) | 52 | No. | 250 | 35 | 113.75 | 0 | 4550 | C+S GST 18% I/P RD | 819 | 5369 | 5369 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1904 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2103 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2201 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2004 Internal Electrical Work | 6 AMP Plug point (Independent) | 51 | No. | 250 | 35 | 111.56 | 0 | 4462.5 | C+S GST 18% I/P RD | 803.26 | 5265.76 | 5265.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2203 Internal Electrical Work | 6 AMP Plug point (Independent) | 43 | No. | 250 | 35 | 94.06 | 0 | 3762.5 | C+S GST 18% I/P RD | 677.26 | 4439.76 | 4439.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1901 Internal Electrical Work | 6 AMP Plug point (Independent) | 53 | No. | 250 | 35 | 115.94 | 0 | 4637.5 | C+S GST 18% I/P RD | 834.76 | 5472.26 | 5472.26 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2101 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2201 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2103 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1904 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2004 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2204 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1903 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2202 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2102 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2104 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2003 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1902 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2001 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1901 Internal Electrical Work | Data Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2002 Internal Electrical Work | Data Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2203 Internal Electrical Work | Data Point | 3 | No. | 350 | 35 | 9.19 | 0 | 367.5 | C+S GST 18% I/P RD | 66.16 | 433.66 | 433.66 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1901 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1904 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2201 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2001 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2002 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2102 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1903 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2004 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2204 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2101 Internal Electrical Work | Exhaust Fan Point | 8 | No. | 225 | 35 | 15.75 | 0 | 630 | C+S GST 18% I/P RD | 113.4 | 743.4 | 743.4 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2103 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1902 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2104 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2003 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2202 Internal Electrical Work | Exhaust Fan Point | 7 | No. | 225 | 35 | 13.78 | 0 | 551.25 | C+S GST 18% I/P RD | 99.22 | 650.47 | 650.47 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2203 Internal Electrical Work | Exhaust Fan Point | 6 | No. | 225 | 35 | 11.81 | 0 | 472.5 | C+S GST 18% I/P RD | 85.06 | 557.56 | 557.56 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2001 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2104 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2004 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2204 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2003 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1903 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2201 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2002 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2101 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1901 Internal Electrical Work | 6 AMP Plug point (Dependent) | 13 | No. | 100 | 35 | 11.38 | 0 | 455 | C+S GST 18% I/P RD | 81.9 | 536.9 | 536.9 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2202 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2103 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1902 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1904 Internal Electrical Work | 6 AMP Plug point (Dependent) | 11 | No. | 100 | 35 | 9.63 | 0 | 385 | C+S GST 18% I/P RD | 69.3 | 454.3 | 454.3 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2102 Internal Electrical Work | 6 AMP Plug point (Dependent) | 14 | No. | 100 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2203 Internal Electrical Work | 6 AMP Plug point (Dependent) | 7 | No. | 100 | 35 | 6.13 | 0 | 245 | C+S GST 18% I/P RD | 44.1 | 289.1 | 289.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2201 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2202 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2004 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2001 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2102 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2203 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2101 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1901 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1903 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1902 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2103 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2003 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2002 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2204 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1904 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2104 Internal Electrical Work | Power Point (2.5 & 1.5 Sqmm) | 2 | No. | 450 | 35 | 7.88 | 0 | 315 | C+S GST 18% I/P RD | 56.7 | 371.7 | 371.7 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2004 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2102 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2201 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1904 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2003 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1903 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2101 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1902 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2002 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2202 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2103 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2001 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2203 Internal Electrical Work | Telephone Point | 4 | No. | 350 | 35 | 12.25 | 0 | 490 | C+S GST 18% I/P RD | 88.2 | 578.2 | 578.2 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1901 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2103 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2102 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2204 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2104 Internal Electrical Work | Telephone Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2201 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2204 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2004 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1902 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2001 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2101 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1901 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2104 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2002 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2202 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2203 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2003 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1904 Internal Electrical Work | AC Point BC | 6 | No. | 450 | 35 | 23.63 | 0 | 945 | C+S GST 18% I/P RD | 170.1 | 1115.1 | 1115.1 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1903 Internal Electrical Work | AC Point BC | 5 | No. | 450 | 35 | 19.69 | 0 | 787.5 | C+S GST 18% I/P RD | 141.76 | 929.26 | 929.26 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2001 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2003 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1904 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1901 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2101 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2203 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2002 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2103 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1902 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-1903 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2201 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2202 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2004 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2104 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 359 | 88293 | 04 Dec 2020 | PLVE/20-21/21 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1864 | A Bldg Flat No.-2102 Internal Electrical Work | 8 Way TPN DB | 1 | No. | 1500 | 35 | 13.13 | 0 | 525 | C+S GST 18% I/P RD | 94.5 | 619.5 | 619.5 | Approved | 0 | 0 | 1940 | 04 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Marble Window Sill | Italian Marble Sill- BC- | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Children Toilet | Dado BC | 32 | Sq.Ft | 14 | 100 | 11.2 | 0 | 448 | C+S GST 18% I/P RD | 80.64 | 528.64 | 528.64 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 401 Powder Toilet dado | Dado BC | 16 | Sq.Ft | 14 | 100 | 5.6 | 0 | 224 | C+S GST 18% I/P RD | 40.32 | 264.32 | 264.32 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Master Toilet dado | Dado BC | 56 | Sq.Ft | 14 | 100 | 19.6 | 0 | 784 | C+S GST 18% I/P RD | 141.12 | 925.12 | 925.12 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Tiling Below Wooden Flooring | Ceramic Flooring work | 150 | Sq.Ft | 13 | 100 | 48.75 | 0 | 1950 | C+S GST 18% I/P RD | 351 | 2301 | 2301 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Living,Dining,Passa. Marble Flooring | Italian marble Skirting - BCo | 100 | R.Ft | 45 | 100 | 112.5 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Master Bed Marble Flooring | Italian marble Skirting - BCo | 30 | R.Ft | 45 | 100 | 33.75 | 0 | 1350 | C+S GST 18% I/P RD | 243 | 1593 | 1593 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Parents Bed Marble Flooring | Italian marble Skirting - BCo | 40 | R.Ft | 45 | 100 | 45 | 0 | 1800 | C+S GST 18% I/P RD | 324 | 2124 | 2124 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Parents Toilet dado | Dado BC | 80 | Sq.Ft | 15 | 100 | 30 | 0 | 1200 | C+S GST 18% I/P RD | 216 | 1416 | 1416 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 401 Staff Room Vitrified Flooring | Vitrified Flooring -BC | 30 | Sq.Ft | 13 | 100 | 9.75 | 0 | 390 | C+S GST 18% I/P RD | 70.2 | 460.2 | 460.2 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Dry Balcony Vitrified Flooring | Vitrified Flooring -BC | 30 | Sq.Ft | 13 | 100 | 9.75 | 0 | 390 | C+S GST 18% I/P RD | 70.2 | 460.2 | 460.2 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 537 | 88290 | 03 Dec 2020 |  | MONIKA ENTERPRISES | CHANDRASHEKHAR ENTERPRISES |  | A 402 Kitchen Vitrified Flooring | Vitrified Flooring -BC | 100 | Sq.Ft | 15 | 100 | 37.5 | 0 | 1500 | C+S GST 18% I/P RD | 270 | 1770 | 1770 |  | 0 | 0 | 238 | 03 Dec 2020
GANGA DHAM TOWERS | 149 | 88289 | 03 Dec 2020 |  | NARPAT SINGH CHOUHAN | DILIP KUMAR | EV - 1805 | Site Office Indirect Expenses | TEa Expenses AIE - No. | 2698 | No. | 4 | 100 | 0 | 0 | 10792 | CGST 0% URD I/P | 0 | 10792 | 10792 | Approved | 0 | 0 | 0 | 03 Dec 2020
GANGA DHAM TOWERS | 145 | 88288 | 03 Dec 2020 |  | PEST-O-CRUSH | PEST-O-CRUSH | EV - 2103 | Fogging Work | Fogging work-SO | 0.75 | Month | 6000 | 100 | 0 | 0 | 4500 | C+S GST 18% I/P RD | 810 | 5310 | 5310 | Approved | 0 | 0 | 45 | 03 Dec 2020
GANGA DHAM TOWERS | 747 | 88279 | 02 Dec 2020 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2049 | Sales Office-Waterbody Maintenance | Maintainance Material | 0.95 | Month | 1000 | 100 | 0 | 0 | 950 | C+S GST 18% I/P RD | 171 | 1121 | 1121 | Approved | 0 | 0 | 0 | 02 Dec 2020
GANGA DHAM TOWERS | 186 | 88277 | 02 Dec 2020 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2192 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 30 | Day | 600 | 100 | 0 | 0 | 18000 | C+S GST 18% I/P RD | 3240 | 21240 | 21240 | Approved | 0 | 0 | 709 | 02 Dec 2020
GANGA DHAM TOWERS | 186 | 88277 | 02 Dec 2020 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2192 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping Work- | 164.0016 | Day | 466.66 | 100 | 0 | 0 | 76533 | C+S GST 18% I/P RD | 13775.94 | 90308.94 | 90308.94 | Approved | 0 | 0 | 709 | 02 Dec 2020
GANGA DHAM TOWERS | 178 | 88276 | 02 Dec 2020 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2085 | Sales Oiifce Landscape Area . | Garden work - Mkt | 0.6222 | Month | 36360 | 100 | 0 | 0 | 22624 | C+S GST 18% I/P RD | 4072.32 | 26696.32 | 26696.32 | Approved | 0 | 0 | 170 | 02 Dec 2020
GANGA DHAM TOWERS | 179 | 88275 | 02 Dec 2020 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | EV - 2086 | Road Divider Work | Garden work - Mkt | 0.8667 | Month | 12120 | 100 | 0 | 0 | 10504 | C+S GST 18% I/P RD | 1890.72 | 12394.72 | 12394.72 | Approved | 0 | 0 | 79 | 02 Dec 2020
GANGA DHAM TOWERS | 413 | 88274 | 02 Dec 2020 |  | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) | SHREE GANESH ENTERPRISES (PROP DHIRAJ CHOPADA) |  | Sales Oiifce Landscape Area . | Supervision Charges | 0.25 | Month | 4000 | 100 | 0 | 0 | 1000 | C+S GST 18% I/P RD | 180 | 1180 | 1180 |  | 0 | 0 | 8 | 02 Dec 2020
GANGA DHAM TOWERS | 187 | 88273 | 02 Dec 2020 |  | MMAK PROPERTY MANAGEMENT SERVICES | MMAK PROPERTY MANAGEMENT SERVICES | EV - 2050 | Sales Off&Sample Flats - Housekeeping Work | Housekeeping (M) | 1 | Month | 7864 | 100 | 0 | 0 | 7864 | C+S GST 18% I/P RD | 1415.52 | 9279.52 | 9279.52 | Approved | 0 | 0 | 0 | 02 Dec 2020
GANGA DHAM TOWERS | 350 | 88272 | 02 Dec 2020 |  | HEMANT G MAHABALESHWARKAR | HEMANT G MAHABALESHWARKAR | EV - 1806 | Site Expenses | Site Expenses -SO | 0.999 | Month | 3000 | 100 | 0 | 0 | 2997 | CGST 0% URD I/P | 0 | 2997 | 2997 | Approved | 0 | 0 | 0 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2201 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-1903 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2001 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2002 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2003 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2204 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-1902 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2101 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2104 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2102 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2203 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2202 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-1904 Internal Electrical Work | TV Point | 6 | No. | 350 | 35 | 18.38 | 0 | 735 | C+S GST 18% I/P RD | 132.3 | 867.3 | 867.3 | Approved | 0 | 0 | 1523 | 02 Dec 2020
GANGA DHAM TOWERS | 359 | 88271 | 02 Dec 2020 | PLVE/20-21/20 | A.D. ASSOCIATES ELECTRICALS PVT LTD | P.L. VISHWAKARMA ELECTRICALS (FIRM) | EV - 1865 | A Bldg Flat No.-2103 Internal Electrical Work | TV Point | 5 | No. | 350 | 35 | 15.31 | 0 | 612.5 | C+S GST 18% I/P RD | 110.26 | 722.76 | 722.76 | Approved | 0 | 0 | 1523 | 02 Dec 2020